## 2026-2035 STIP
DRAFT 2026-2035 STATE TRANSPORTATION IMPROVEMENT PROGRAM Please note that ALL INFORMATION AND DATA is considered DRAFT and is SUBJECT TO CHANGE.
NOTES: AMOUNTS SHOWN ARE PROJECT ESTIMATE AMOUNTS REMAINING. ANY AMOUNTS PROGRAMMED FOR ACTIVITIES OTHER THAN RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION ARE INCLUDED UNDER "OTHER ACTIVITIES".
BASIC PROJECT INFORMATION | [11 empty] | FISCAL YEAR PROJECT PHASE SCHEDULED TO START
COUNTY(S) | ROUTE/CITY | RESPONSIBLE AGENCY | DESCRIPTION | LENGTH (MILES) | MODE | FUNDING PROGRAM | DIVISION(S) | MPOs/RPOs | PROJECT ID | STI CATEGORY FUNDED | FUNDING SOURCE (SEE FUNDING SOURCES TAB FOR MORE INFO) | RIGHT-OF-WAY PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR RIGHT-OF-WAY | UTILITIES PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR UTILITIES | CONSTRUCTION PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR CONSTRUCTION | PROJECTED SCHEDULE FOR OTHER ACTIVITIES | TOTAL REMAINING FUNDS FOR OTHER ACTIVITIES | TOTAL REMAINING FUNDS NEEDED | COMMENT
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN THE RUNWAY 24 APPROACH. |  | Aviation | STI (Prioritization) | 7 | Burlington-Graham MPO | AV-5737 | Division 7 | L, T | 2027 | 1200000 | [6 empty] | 1200000
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | CONSTRUCT 100 FT PAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. |  | Aviation | STI (Prioritization) | 7 | Burlington-Graham MPO | AV-5851 | Division 7 | T |  |  |  |  | 2029 | 2080000 |  |  | 2080000
ALAMANCE | US 70 (NORTH CHURCH STREET) | BURLINGTON | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | Bike & Ped | STI (Prioritization) | 7 | Burlington-Graham MPO | EB-5879 | Division 7 | L(M), TA50200 | 2025 | 3300000 | 2025 | 950000 | 2025 | 930000 | 2024 | 16000 | 5196000
ALAMANCE | US 70 (NORTH CHURCH STREET) | BURLINGTON | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.47 | Bike & Ped | STI (Prioritization) | 7 | Burlington-Graham MPO | EB-5885 | Division 7 | L, TA50200 | 2025 | 30000 | 2025 | 750000 | 2025 | 690000 |  |  | 1470000
ALAMANCE | LEE AVENUE | ELON | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | Bike & Ped | STI (Prioritization) | 7 | Burlington-Graham MPO | EB-5988 | Division 7 | L, TA50200 | 2026 | 40000 | 2026 | 280000 | 2027 | 310000 | 2024 | 30000 | 660000
ALAMANCE | BURLINGTON |  | PURCHASE, CONSTRUCTION, AND INSTALLATION OF ELECTRIC CHARGING STATION AT JOE DAVIDSON PARK IN BURLINGTON. |  | Highway | Locally Selected | 7 | Burlington-Graham MPO | HL-0130 | Exempt | CRPDA, L |  |  |  |  | 2024 | 165000 |  |  | 165000
ALAMANCE | NC 87 | NCDOT | NC 87 AT I-40 EASTBOUND ON-RAMP. INSTALL PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 7 | Burlington-Graham MPO | HS-2007F | Region D | HSIP |  |  |  |  | 2024 | 87000 |  |  | 87000
ALAMANCE | SR 1301 (BOONE STATION DRIVE) | NCDOT | SR 1301 (ST. MARKS CHURCH ROAD) / JAVA LANE AND GLIDWELL DRIVE / TIKI LANE IN BURLINGTON. INSTALL PEDESTRIAN SIGNALS AND CURB RAMPS, AND REVISE PAVEMENT MARKINGS. | 0.5 | Highway | Safety | 7 | Burlington-Graham MPO | W-5807B | Division 7 | HSIP |  |  |  |  | 2023 | 75000 |  |  | 75000
ALAMANCE | NC 49 (MAPLE AVENUE) | NCDOT | I-85 / I-40 TO NC 54 AND PLAZA DRIVE INTERSECTION IN BURLINGTON. RELOCATION OF MAPLE AVENUE ON NEW ALIGNMENT FROM I-85 / I-40 TO NC 54, AND RELOCATION OF PLAZA DRIVE INTERSECTION WITH A NEW SIGNALIZED FOUR-LEGGED INTERSECTION AT RELOCATED PLANTATION DRIVE. INCLUDED LANDSCAPED MEDIANS AND MULTI-USE PATHS. | 1 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | HP-0022 | Region D | BG50200 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 |  |  | 6600000
ALAMANCE | US 70 (CHURCH STREET) | NCDOT | NC 62 INTERSESCTION IN BURLINGTON. IMPROVE INTERSECTION. PROJECT INCLUDES IMPROVEMENTS TO NC 62. |  | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | HP-0030 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 |  |  | 2400000
ALAMANCE | I-40 / I-85 | NCDOT | SR 1007 (MEBANE-OAKS ROAD) IN MEBANE. INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | I-5711 | Statewide Mobility | NHP |  |  |  |  | 2020 | 9830000 |  |  | 9830000 | UNDER CONSTRUCTION;
ALAMANCE | I-40 / I-85 | NCDOT | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | I-6009 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1990000 |  |  | 2790000
ALAMANCE | I-40 / I-85 | NCDOT | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | I-6059 | Division 7 | HF, T | 2025 | 2000000 | 2025 | 2500000 | 2025 | 32380000 |  |  | 36880000 | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE)
ALAMANCE | NC 119 | NCDOT | NC 119 RELOCATION, I-85 TO SOUTH OF SR 1918 (MRS. WHITE ROAD) IN MEBANE. FOUR-TO-SIX-LANE FACILITY ON NEW LOCATION. | 4.2 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-3109
ALAMANCE | NC 119 | NCDOT | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | 3.01 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-3109A | Region D | T |  |  |  |  | 2019 | 42967000 | 2021 | 360000 | 43327000 | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NC 119 | NCDOT | NC 119 RELOCATION, NORTH OF SR 1921 (MEBANE ROGERS ROAD) TO SOUTH OF SR 1918 (MRS. WHITE ROAD) | 1.49 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-3109B | Region D | T |  |  |  |  | 2021 | 5835000 |  |  | 5835000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.533 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | US 70 (NORTH CHURCH STREET) | NCDOT | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-5843 | Division 7 | T |  |  |  |  | 2019 | 2167000 | 2021 | 810000 | 2977000 | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NC 62 | NCDOT | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO A THREE LANE FACILITY. | 1.13 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-5844 | Division 7 | T | 2024 | 13300000 | 2025 | 2600000 | 2027 | 25195000 |  |  | 41095000 | BUILD NC BONDS: $8M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE)
ALAMANCE | US 70 (SOUTH CHURCH STREET) | NCDOT | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | 0.93 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6009 | Region D | T | 2028 | 26600000 | 2028 | 5100000 | 2030 | 25555000 |  |  | 57255000 | BUILD NC BONDS: $10M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE).
ALAMANCE | US 70 (SOUTH CHURCH STREET) | NCDOT | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | 5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6010 | Region D | T | 2020 | 6000000 |  |  | 2022 | 16100000 |  |  | 22100000 | UNDER CONSTRUCTION
ALAMANCE | US 70 (SOUTH CHURCH STREET) | NCDOT | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6011 | Region D | T | 2022 | 3000000 | 2022 | 630000 | 2025 | 3000000 |  |  | 6630000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | NC 119 | NCDOT | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 0.52 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6013 | Division 7 | T | 2023 | 5500000 | 2023 | 900000 | 2028 | 9999000 |  |  | 16399000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | SR 1716 (GRAHAM- HOPEDALE ROAD) | NCDOT | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO A THREE LANE FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.38 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6014 | Division 7 | T | 2024 | 1500000 | 2025 | 1200000 | 2027 | 19100000 |  |  | 21800000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | VARIOUS | NCDOT | UPGRADE BURLINGTON-GRAHAM SIGNAL SYSTEM. |  | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6015 | Division 7 | T |  |  |  |  | 2021 | 6125000 |  |  | 6125000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | NC 49 (EAST ELM STREET) INTERSECTION IN GRAHAM. IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6017 | Division 7 | T | 2022 | 2000000 | 2022 | 550000 | 2024 | 2100000 |  |  | 4650000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | NC 62 (ALAMANCE ROAD) | NCDOT | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6114 | Region D | T | 2028 | 840000 | 2028 | 270000 | 2031 | 1100000 |  |  | 2210000
ALAMANCE | NC 54 | NCDOT | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) TO SOUTH OF SR 2107 (WHITTEMORE ROAD) IN GRAHAM. IMPROVE SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTION, UPGRADE RAMP INTERSECTIONS AT I-40 / I-85, IMPROVE SR 2106 (WOODY ROAD) INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115 | Region D
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115A | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3501000 |  |  | 5101000
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | 1 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115B | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 |  |  | 9500000
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115C | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 250000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 |  |  | 6150000
ALAMANCE | NC 54 (EAST HARDEN STREET) | NCDOT | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. |  | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6115D | Not Funded | T | NOT FUNDED | 490000 | NOT FUNDED | 120000 | NOT FUNDED | 2100000 | NOT FUNDED |  | 2710000
ALAMANCE | NC 54 (WEST HARDEN STREET) | NCDOT | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | 0.5 | Highway | STI (Prioritization) | 7 | Burlington-Graham MPO | U-6131 | Region D | BG50200 | 2025 | 4100000 | 2025 | 1100000 | 2026 | 6700000 |  |  | 11900000
ALAMANCE | LINK TRANSIT | LINK TRANSIT | IMPROVEMENTS, BUS SHELTERS, CONSTRUCTION, ENGINEERING AND DESIGN. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Burlington-Graham MPO | TA-6322 | Public Transit | 5307, L | [6 empty] | 2023 | 1081000 | 1081000
ALAMANCE | LINK TRANSIT |  | THIS FUNDING PROVIDES FOR THE DESIGN, ENGINEERING AND CONSTRUCTION OF TRANSIT MAINTENANCE FACILITY AND TRANSIT TRANSFER HUB TO SUPPORT THE LINK TRANSIT SYSTEM. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Burlington-Graham MPO | TC-0034 | Public Transit | 5307, L, S | [6 empty] | 2024 | 1920000 | 1920000
ALAMANCE | BURLINGTON | BURLINGTON | CAPITAL FOR PEDESTRIAN IMPROVEMENTS FOR FIXED ROUTR SERVICES |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Burlington-Graham MPO | TD-6322 | Public Transit | 5307, L | [6 empty] | 2020 | 60000 | 60000 | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | LINK TRANSIT | LINK TRANSIT | CAPITAL IMPROVEMENTS FOR TRANSIT VEHICLES. |  | Public Transportation (Transit) | Locally Selected | 7 | Burlington-Graham MPO | TL-0029 | Public Transit | 5307, L | [6 empty] | 2022 | 1550000 | 1550000
ALAMANCE | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-5134 | Public Transit | 5307, L | [6 empty] | 2023 | 3740000 | 3740000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | ALAMANACE COUNTY TRANSPORTATION | ALAMANACE COUNTY TRANSPORTATION | OPERATING FOR ALAMANCE COUNTY TRANSPORTATION IN THE BURLINGTON URBAN AREA - THROUGH NCDOT |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-5214 | Public Transit | 5307, L | [6 empty] | 2023 | 9070000 | 9070000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | LINK TRANSIT | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-6170 | Public Transit | 5307, L | [6 empty] | 2023 | 9840000 | 9840000 | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO.
ALAMANCE | LINK TRANSIT | LINK TRANSIT | ADA SERVICE. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-6812A | Public Transit | 5307, L | [6 empty] | 2023 | 1356000 | 1356000
ALAMANCE | LINK TRANSIT | LINK TRANSIT | PURCHASE TWO ELECTRIC PARATRANSIT VEHICLES AND INSTALL CHARGER. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 7 | Burlington-Graham MPO | TN-6134 | Exempt | CRPDA, L(M) | [6 empty] | 2025 | 560000 | 560000
ALAMANCE | BURLINGTON | BURLINGTON | ADA SERVICES |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TG-6812A | Public Transit | 5307, L | [6 empty] | 2020 | 211000 | 211000 | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | ALAMANACE COUNTY TRANSPORTATION | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TK-6103 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1424000 | 1424000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | LINK TRANSIT | LINK TRANSIT | PREVENTATIVE MAINTENANCE. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0046 | Public Transit | 5307, L | [6 empty] | 2023 | 3072000 | 3072000
ALAMANCE | ALAMANCE COUNTY TRANSPORTATION AUTHORITY |  | ROLLING STOCK-SHOP SERVICE VEHICLE (5307). |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Burlington-Graham MPO | TM-0051 | Public Transit | 5307, L | [6 empty] | 2024 | 865000 | 865000
ALAMANCE | LINK TRANSIT | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. |  | Public Transportation (Transit) | Planning | 7 | Burlington-Graham MPO | TA-6733 | Public Transit | 5307, 5309, L, S | [6 empty] | 2023 | 865000 | 865000 | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | BURLINGTON | BURLINGTON | PLANNING FOR FIXED ROUTE SERVICE EXPANSION |  | Public Transportation (Transit) | Planning | 7 | Burlington-Graham MPO | TP-5161 | Public Transit | 5307, L | [6 empty] | 2020 | 5000 | 5000 | ADD PROJECT TP-5161 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | BURLINGTON | BURLINGTON | PLANNING FOR PLANNING FACILITY FEASIBILITY STUDY |  | Public Transportation (Transit) | Planning | 7 | Burlington-Graham MPO | TP-5162 | Public Transit | 5307, L | [6 empty] | 2020 | 95000 | 95000 | ADD PROJECT TP-5162 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | ALAMANCE COUNTY TRANSPORTATION AUTHORITY |  | ACTA PLANNING AND FEASIBILITY STUDY (5307). |  | Public Transportation (Transit) | Planning | 7 | Burlington-Graham MPO | TU-0017 | Public Transit | 5307, L | [6 empty] | 2024 | 150000 | 150000
ALAMANCE | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | ROUTINE CAPITAL/PREVENTATIVE, MAINTENANCE/PASSENGER AMENITIES/MOBILITY MANAGEMENT |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO | TG-0012 | Public Transit | 5307, L | [6 empty] | 2023 | 2263000 | 2263000
ALAMANCE | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PASSENGER AMENITIES, PARTS, EQUIPMENT, PREVENTIVE MAINTENANCE, AND CAPITAL COST OF CONTRACTING. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO | TG-6137B | Public Transit | 5307, L | [6 empty] | 2020 | 750000 | 750000
ALAMANCE | PIEDMONT CORRIDOR | PIEDMONT CORRIDOR | GRAHAM TO HAW RIVER. SIDING AND CURVE REALIGNMENT. |  | Rail | Pre-STI (Historic) | 7 | Burlington-Graham MPO | P-5205 | Pre-STI (Transition) | [10 empty] | COMPLETED
ALAMANCE, CASWELL, GUILFOR D, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5707REG | Region D | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | BO-2407 | Division 7 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | BO-2607 | Division 7 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | R-5787 | Division 7 | HF, TA |  |  |  |  | 2020 | 4500000 |  |  | 4500000 | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2007 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 7 | Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, Piedmont Triad RPO | HS-2007C | Division 7 | HSIP |  |  |  |  | 2021 | 1717000 |  |  | 1717000 | UNDER CONSTRUCTION
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 7. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2022
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2022DIV | Division 7 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2022REG | Region D | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2022SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2407 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | HS-2607 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5707 | [11 empty] | IN PROGRESS
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5707DIV | Division 7 | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5707SW | Statewide Mobility | HSIP | 2020 | 120000 |  |  | 2020 | 740000 |  |  | 860000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | Highway | Safety | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | W-5807
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 7. |  | Rail | Rail-Highway Grade Crossing Closure | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | RC-2007 | Division 7 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | RX-2007 | Division 7 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | RX-2407 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | RX-2607 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALAMANCE, CUMBERLAND, DURHAM, GUILFORD, WAKE, CASWELL, CHATHAM, GRANVILLE, HARNETT, HOKE, LEE, MONTGOMERY, MOORE, ORANGE, PERSON, RANDOLPH, RICHMOND, ROCKINGHAM, SCOTLAND | STATEWIDE | NCDOT | LIDAR DATA COLLECTION |  | Highway | Other | 5, 6, 7, 8 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Fayetteville Area MPO, Greensboro Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Kerr-Tar RPO, Lumber River RPO, Mid-Carolina RPO, Northwest Piedmont RPO, Piedmont T | M-0563D | Statewide Mobility | PROTCT | [6 empty] | 2024 | 1285000 | 1285000
ALAMANCE, GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-5136 | Public Transit | SMAP | [6 empty] | 2020 | 3268000 | 3268000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE, GUILFORD, ORANGE | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE BURLINGON PLANNING ORGANIZATION. |  | Highway | Locally Selected | 7 | Burlington-Graham MPO | HL-0091 | Exempt | CRPDA, L |  |  |  |  | 2023 | 1708000 |  |  | 1708000
ALAMANCE, GUILFORD, ORANGE | ALAMANACE COUNTY TRANSPORTATION | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO | TG-6811B | Public Transit | 5307, FED, L | [6 empty] | 2024 | 250000 | 250000
ALEXANDER | ALEXANDER COUNTY | NCDOT | CONSTRUCT ACCESS ROAD INTO ALEXANDER INDUSTRIAL PARK. | 0.49 | Highway | Appalachian Development Highway System | 12 | Greater Hickory MPO | R-5870 | Exempt | ADHSL, T |  |  |  |  | 2021 | 1675000 |  |  | 1675000 | COMPLETE - ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING.
ALEXANDER | SR 1348 | NCDOT | REPLACE BRIDGE 10291 OVER DUCK CREEK. | 0.25 | Highway | Bridges | 12 | Greater Hickory MPO | BR-0201 | Highway Fund | HFB |  |  |  |  | 2021 | 1050000 |  |  | 1050000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.88
ALEXANDER | NC 16 | NCDOT | INTERSECTION OF NC 16 AND SR 1609 (COUNTY HOME ROAD). CONSTRUCT INTERSECTION IMPROVMENTS. | 0.5 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-5762 | Division 12 | T | 2022 | 120000 |  |  | 2023 | 885000 |  |  | 1005000 | UNDER CONSTRUCTION.
ALEXANDER | US 64 | NCDOT | SR 1124 (CHURCH ROAD). ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90. |  | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-6041 | Division 12 | BGLT5 | 2024 | 200000 | 2024 | 400000 | 2025 | 1450000 |  |  | 2050000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY |  | PREVENTATIVE MAINTENANCE |  |  |  | 11, 12, 13 | Greater Hickory MPO | TA-4774A | Public Transit | 5307, L(M) | [6 empty] | 2024 | 1875000 | 1875000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TA-4928 | Public Transit | 5307, L, S | [6 empty] | 2024 | 840000 | 840000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ALEXANDER |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TA-4929 | Public Transit | 5307, L, S | [6 empty] | 2020 | 1893000 | 1893000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 |  | TA-6507 | Public Transit | 5311, L, S | [6 empty] | 2020 | 920000 | 920000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TA-6707 | Public Transit | 5307, L | [6 empty] | 2023 | 2520000 | 2520000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY |  | VEHICLES, BUS STOPS |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TC-0028 | Public Transit | 5339, L | [6 empty] | 2024 | 240000 | 240000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY |  | ROUTINE CAPITAL |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TC-0032 | Public Transit | 5339, L | [6 empty] | 2024 | 240000 | 240000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY |  | TC-0033 - ROLLING STOCK |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TC-0033 | Public Transit | 5309, L | [6 empty] | 2024 | 240000 | 240000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TP-5106 | Public Transit | 5303, HF, L(M), S | [6 empty] | 2023 | 299000 | 299000 | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | CAPITAL PURCHASE OF SERVICE. |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TQ-9039 | Public Transit | 5310, L | [6 empty] | 2024 | 1000000 | 1000000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | SAFETY & SECURITY |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TS-5128 | Public Transit | 5307, L | [6 empty] | 2020 | 24000 | 24000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | SAFETY AND SECURITY |  | Public Transportation (Transit) | Capital (Non-STI) | 11, 12, 13 | Greater Hickory MPO | TS-7002 | Public Transit | 5307, L | [6 empty] | 2020 | 414000 | 414000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PROGRAM ADMINISTRATION |  | Public Transportation (Transit) | Locally Selected | 11, 12, 13 | Greater Hickory MPO | TL-6110 | Public Transit | 5310 | [6 empty] | 2020 | 232000 | 232000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 11, 12, 13 | Greater Hickory MPO | TO-6162 | Public Transit | 5307, L | [6 empty] | 2020 | 19730000 | 19730000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-4774A | Public Transit | 5307, L | [6 empty] | 2023 | 740000 | 740000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | REGIONAL TRANSPORTATION WESTERN PIEDMONT | OPERATING ASSISTANCE ‐ ADA PARATRANSIT SERVICE |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-4774B | Public Transit | 5307, L | [6 empty] | 2024 | 936000 | 936000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-6801 | Public Transit | 5307, L | [6 empty] | 2024 | 1500000 | 1500000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE-ADA PARATRANSIT |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-6802 | Public Transit | 5310, L | [6 empty] | 2020 | 300000 | 300000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ELDERLY AND DISABLED PERSONS |  | Public Transportation (Transit) | Operations and Maintenance | 11, 12, 13 | Greater Hickory MPO | TQ-6507 | Public Transit | 5310, L | [6 empty] | 2023 | 948000 | 948000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY |  | PURCHASE REPLACEMENT BUSES. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-0023 |  | 5339, L | [6 empty] | 2025 | 125000 | 125000
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-4774 | Public Transit | 5307, L | [6 empty] | 2023 | 530000 | 530000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, COMPUTER HARDWARE AND SOFTWARE, AVL SOFTWARE, ETC. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 11, 12, 13 | Greater Hickory MPO | TG-6800 | Public Transit | 5307, L | [6 empty] | 2024 | 1440000 | 1440000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, CATAWBA | NC 127 | NCDOT | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | 3.7 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3603
ALEXANDER, CATAWBA | NC 127 | NCDOT | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | 3.67 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3603A | Division 12 | BGANY | 2030 | 16200000 | 2030 | 7300000 | 2034 | 115699000 |  |  | 139199000 | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040).
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | BO-2412 | Division 12 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 600000 | 6100000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | BO-2612 | Division 12 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | R-5792 | Division 12 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2012 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 12. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2027
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2027DIV | Division 12 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2027REG | Region F | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2027SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2412 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | HS-2612 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5212 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS; SEGMENT J: ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. HF(M) IS SPOT SAFETY FUNDS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5712 | [11 empty] | IN PROGRESS
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5712DIV | Division 12 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5712REG | Region F | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5712SW | Statewide Mobility | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | W-5812 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 12. |  | Rail | Rail-Highway Grade Crossing Closure | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | RC-2012 | Division 12 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | RX-2012 | Division 12 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | RX-2412 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | RX-2612 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, IREDELL | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ON APPROXIMATELY 65 SECONDARY ROADS. |  | Highway | Safety | 12 | Cabarrus-Rowan MPO, Charlotte Regional TPO | HS-2012D | Division 12 | HSIP |  |  |  |  | 2023 | 3615000 |  |  | 3615000 | UNDER CONSTRUCTION.
ALLEGHANY | SR 1422 | NCDOT | REPLACE BRIDGE 20035 OVER GLADE CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0206 | Highway Fund | HFB |  |  |  |  | 2022 | 750000 |  |  | 750000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.157
ALLEGHANY | SR 1433 | NCDOT | REPLACE BRIDGE 20133 OVER LITTLE RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0207 | Highway Fund | HFB |  |  |  |  | 2022 | 500000 |  |  | 500000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.159
ALLEGHANY | (SCENIC VALLEY ROAD) SR 1433 | NCDOT | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0067 | Exempt | BGOFF, DP, HFB | 2025 | 199000 | 2025 | 10000 | 2026 | 1700000 | 2023 | 139000 | 2048000 | DP REPRESENTS RAISE GRANT FUNDS.
ALLEGHANY | ALLEGHANY COUNTY | ALLEGHANY COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 11 | High Country RPO | TK-6105 | Public Transit | 5311, L, S | [6 empty] | 2020 | 620000 | 620000 | FUNDS AUTHORIZED IN PROGRESS
ANSON | SR 1627 (PINKSTON RIVER ROAD) | NCDOT | REPLACE BRIDGE 030307 OVER WSSB RAILROAD. | 0.25 | Highway | Bridges | 10 | Rocky River RPO | B-4410 | [11 empty] | UNDER CONSTRUCTION. LOCAL FUNDING PROVIDED BY TOWN OF ANSONVILLE
ANSON | SR 1627 (PINKSTON RIVER ROAD) | NCDOT | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. |  | Highway | Bridges | 10 | Rocky River RPO | B-4410A | Pre-STI (Transition) | L, T | 2022 | 25000 |  |  | 2023 | 1013000 |  |  | 1038000 | UNDER CONSTRUCTION.
ANSON | SR 1812 (DIGGS ROAD) | NCDOT | REPLACE BRIDGE 030039 OVER JONES CREEK. | 0.25 | Highway | Bridges | 10 | Rocky River RPO | B-6048 | Division 10 | BGOFF | 2023 | 355000 |  |  | 2027 | 4100000 |  |  | 4455000 | RIGHT-OF-WAY IN PROGRESS.
ANSON | US 74 | NCDOT | ANSON HIGH SCHOOL ROAD INTERSECTION IN WADESBORO. INSTALL CROSSWALK, CURB RAMPS, AND GUARDRAIL. |  | Highway | Safety | 10 | Rocky River RPO | HS-2410F | Statewide Mobility | HSIP | 2026 | 6000 | 2027 | 6000 | 2027 | 184000 |  |  | 196000
ANSON | US 74 (ANDREW JACKSON HIGHWAY) | NCDOT | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | 2.87 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-5798 | Statewide Mobility | BGLT5 | 2029 | 14800000 | 2029 | 4900000 | 2032 | 65100000 |  |  | 84800000
ANSON | NEW ROUTE - WADESBORO BYPASS | NCDOT | US 74 WEST OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 11.3 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-5878
ANSON | NEW ROUTE - WADESBORO BYPASS | NCDOT | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. |  | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-5878A | Not Funded | NHP | NOT FUNDED | 4000000 | NOT FUNDED | 600000 | NOT FUNDED | 104300000 | NOT FUNDED |  | 108900000
ANSON | NEW ROUTE - WADESBORO BYPASS | NCDOT | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 6.44 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-5878B | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 315700000 |  |  | 350000000
ANSON | ANSON COUNTY | ANSON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Rocky River RPO | TK-6106 | Public Transit | 5311, L, S | [6 empty] | 2020 | 820000 | 820000 | FUNDS AUTHORIZED IN PROGRESS
ANSON | SR 1714 (STANBACK FERRY ICE PLANT ROAD) | NCDOT | CSX CROSSING 631750C NEAR WADESBORO. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO | RX-2010B | Division 10 | RR |  |  |  |  | 2024 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
ANSON | CSX SF LINE | NCDOT | CONSTRUCT SIDING EXTENSION IN POLKTON |  | Rail | STI (Prioritization) | 10 | Rocky River RPO | P-5750 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
ANSON | CSX SF LINE | CSXT RR | CONSTRUCT SIDING EXTENSION IN POLKTON. |  | Rail | STI (Prioritization) | 10 | Rocky River RPO | P-5750A | Region E | DP, T |  |  |  |  | 2024 | 13037000 |  |  | 13037000
ANSON | CSX SF LINE | NCDOT | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. |  | Rail | STI (Prioritization) | 10 | Rocky River RPO | P-5750B | Region E | T | 2029 | 2000000 |  |  | 2031 | 16380000 |  |  | 18380000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | BO-2410 | Division 10 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 625000 | 6125000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | BO-2610 | Division 10 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | R-5790 | Division 10 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2010 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 10. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2025
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2025DIV | Division 10 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2025REG | Region E | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2025SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2410 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2610 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5710 | [11 empty] | HF(M) FOR SEGMENTS Y & Z ARE SPOT SAFETY FUNDS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5710DIV | Division 10 | HSIP | 2020 | 410000 |  |  | 2020 | 2025000 |  |  | 2435000 | IN PROGRESS.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5710REG | Region E | HSIP | 2020 | 540000 |  |  | 2020 | 720000 |  |  | 1260000 | IN PROGRESS.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5710SW | Statewide Mobility | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | Highway | Safety | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | W-5810 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 10. |  | Rail | Rail-Highway Grade Crossing Closure | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | RC-2010 | Division 10 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | RX-2010 | Division 10 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | RX-2410 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | RX-2610 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
ANSON, ROBESON, RICHMOND, SCOTLAND, UNION | US 74 | NCDOT | EASTERN END OF MONROE BYPASS TO I-95 IN LUMBERTON. INSTALL BROADBAND AND ITS COMPONENTS INCLUDING CONNECTIONS TO SIGNAL SYSTEMS, DMS, AND CCTV. | 86.48 | Highway | Other | 6, 8, 10 | Lumber River RPO, Rocky River RPO, Charlotte Regional TPO | HO-0002B | Statewide Mobility | HSIP |  |  |  |  | 2021 | 14216000 |  |  | 14216000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002C. UNDER CONSTRUCTION.
ASHE | ASHE COUNTY AIRPORT (GEV) | ASHE COUNTY AIRPORT (GEV) | CONSTRUCT APRON EXPANSONS. |  | Aviation | STI (Prioritization) | 11 | High Country RPO | AV-5848 | Division 11 | T |  |  |  |  | 2021 | 2700000 |  |  | 2700000 | UNDER CONSTRUCTION.
ASHE | NORTHWEST DRIVE, AEV LANE | NCDOT | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AMERICAN EMERGENCY VEHICLES LANE FROM NORTHWEST DRIVE TO AMERICAN EMERGENCY VEHICLES FACILITY. WIDEN ROAD TO 12' LANES. | 0.49 | Highway | Appalachian Development Highway System | 11 | High Country RPO | HA-0006 | Exempt | ADHSL | 2025 | 60000 |  |  | 2025 | 643000 | 2023 | 47000 | 750000 | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000
ASHE | SR 1523 | NCDOT | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0043 | Exempt | BGOFF, DP, HFB | 2025 | 200000 | 2025 | 70000 | 2026 | 1500000 | 2023 | 125000 | 1895000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | (MCNEIL ROAD) SR 1644 | NCDOT | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0044 | Exempt | BGOFF, DP, HFB | 2025 | 291000 | 2025 | 10000 | 2026 | 2200000 | 2023 | 209000 | 2710000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1609 | NCDOT | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0045 | Exempt | BGOFF, DP, HFB | 2025 | 271000 | 2025 | 40000 | 2026 | 1600000 | 2023 | 139000 | 2050000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1105 | NCDOT | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0046 | Exempt | BGOFF, DP, HFB | 2025 | 220000 | 2025 | 10000 | 2026 | 2299000 | 2023 | 181000 | 2710000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1528 | NCDOT | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0047 | Exempt | BGOFF, DP, HFB | 2025 | 209000 | 2025 | 20000 | 2026 | 1599000 | 2023 | 111000 | 1939000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1606 | NCDOT | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0048 | Exempt | BGOFF, DP, HFB | 2025 | 399000 | 2025 | 20000 | 2026 | 1600000 | 2023 | 139000 | 2158000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1602 | NCDOT | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0049 | Exempt | BGOFF, DP, HFB | 2025 | 140000 | 2025 | 50000 | 2026 | 2301000 | 2023 | 278000 | 2769000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1563 | NCDOT | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0050 | Exempt | BGOFF, DP, HFB | 2025 | 1700000 | 2025 | 10000 | 2026 | 3700000 | 2023 | 278000 | 5688000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | (BOGGS ROAD) SR 1159 | NCDOT | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0051 | Exempt | BGOFF, DP, HFB | 2025 | 209000 | 2025 | 10000 | 2026 | 2185000 | 2023 | 209000 | 2613000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1104 | NCDOT | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0052 | Exempt | BGOFF, DP, HFB | 2025 | 209000 | 2025 | 15000 | 2026 | 2399000 | 2023 | 181000 | 2804000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | (ED LITTLE ROAD) SR 1126 | NCDOT | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0053 | Exempt | BGOFF, DP, HFB | 2025 | 280000 | 2025 | 40000 | 2026 | 1701000 | 2023 | 125000 | 2146000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | SR 1222 | NCDOT | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0054 | Exempt | BGOFF, DP, HFB | 2025 | 150000 | 2025 | 30000 | 2026 | 3701000 | 2023 | 278000 | 4159000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | (HELTON ROAD) SR 1527 | NCDOT | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0068 | Exempt | BGOFF, DP, HFB | 2025 | 140000 | 2025 | 10000 | 2026 | 1401000 |  |  | 1551000 | DP REPRESENTS RAISE GRANT FUNDS.
ASHE | NC 16 | NCDOT | US 221 TO THE VIRGINIA STATE LINE. INSTALL NEW AND UPGRADE EXISTING GUARDRAIL. |  | Highway | Safety | 11 | High Country RPO | HS-2011E | Region F | HSIP |  |  |  |  | 2023 | 1575000 |  |  | 1575000 | UNDER CONSTRUCTION.
ASHE | US 221 | NCDOT | NORTH OF SOUTH FORK NEW RIVER TO SOUTH OF NC 194 | 4.2 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2915C | Division 11 | BGLT5 |  |  |  |  | 2017 | 19700000 |  |  | 19700000 | COMPLETE
ASHE | US 221 | NCDOT | US 221 BYPASS TO US 221 BUSINESS/NC 88 IN JEFFERSON | 3.55 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2915E | Division 11 | T |  |  |  |  | 2020 | 44684000 |  |  | 44684000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
ASHE | NC 88 | NCDOT | NC 88 TO NC 194. UPGRADE ROADWAY. | 3.76 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5832 | Division 11 | BGLT5 | 2025 | 12801000 | 2025 | 4600000 | 2028 | 32701000 |  |  | 50102000
ASHE | US 221 | NCDOT | SR 1003 (IDLEWILD ROAD) TO NORTH OF SOUTH FORK NEW RIVER | 1 | Highway | Transition | 11 | High Country RPO | R-2915B | Pre-STI (Transition) | [10 empty] | COMPLETE
ASHE | US 221 | NCDOT | SOUTH OF NC 194 TO US 221 BYPASS | 3.8 | Highway | Transition | 11 | High Country RPO | R-2915D | Pre-STI (Transition) | [10 empty] | COMPLETE
ASHE | ASHE COUNTY TRANSPORTATION | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. |  | Public Transportation (Transit) | Capital (Non-STI) | 11 | High Country RPO | TA-6674 | Division 11 | 5311, L, T
ASHE | ASHE COUNTY TRANSPORTATION | ASHE COUNTY TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 11 | High Country RPO | TK-6108 | Public Transit | 5311, L, S | [6 empty] | 2020 | 784000 | 784000 | FUNDS AUTHORIZED IN PROGRESS
ASHE, WATAUGA | US 221 | NCDOT | US 421 IN WATAUGA COUNTY TO US 221 BUSINESS/NC 88 IN JEFFERSON. WIDEN TO FOUR LANES DIVIDED. | 16.1 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2915
ASHE, WATAUGA | US 221 | NCDOT | US 421 IN WATAUGA COUNTY TO SR 1003 (IDLEWILD ROAD) IN ASHE COUNTY | 3.6 | Highway | Transition | 11 | High Country RPO | R-2915A | Pre-STI (Transition) | [10 empty] | COMPLETE
AVERY | SR 1306 (HICKS HOLLOW ROAD) | NCDOT | REPLACE BRIDGE 050125 OVER ELK RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | B-5835 | Division 11 | BGOFF | 2025 | 150000 | 2025 | 160000 | 2026 | 2000000 |  |  | 2310000
AVERY | SR 1326 | NCDOT | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0055 | Exempt | BGOFF, DP, HFB | 2025 | 270000 | 2025 | 10000 | 2026 | 1800000 | 2023 | 139000 | 2219000 | DP REPRESENTS RAISE GRANT FUNDS.
AVERY | SR 1511 (ROSEBORO ROAD) | NCDOT | INSTALL SHOULDER GUARDRAIL. | 0.05 | Highway | Safety | 11 | High Country RPO | HS-2011C | Division 11 | HSIP |  |  |  |  | 2021 | 20000 |  |  | 20000 | UNDER CONSTRUCTION.
AVERY | US 19E | NCDOT | NC 194 INTERSECTION. CONSTRUCT RIGHT TURN LANE FROM US 19E NORTHBOUND TO NC 194 EASTBOUND. | 0.5 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5911 | Division 11 | BGLT5 | 2022 | 200000 |  |  | 2023 | 1200000 |  |  | 1400000 | UNDER CONSTRUCTION.
AVERY, BUNCOMBE, BURKE, HAYWOOD, HENDERSON, JACKSON, McDOWELL, MITCHELL, SWAIN, TRANSYLVANIA, ALLEGHANY, ASHE, CALDWELL, WATAUGA, WILKES | BLUE RIDGE PARKWAY | NCDOT | MARKETING AND BRANDING FOR BLUE RIDGE PARKWAY ASSOCIATION. |  | Highway | Other | 11, 13, 14 | French Broad River MPO, Greater Hickory MPO, High Country RPO, Land-of-Sky RPO, Southwestern RPO, Foothills RPO | HO-0015 | Exempt | DP | [6 empty] | 2024 | 460000 | 460000 | DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING.
AVERY, WATAUGA | NC 105 | NCDOT | US 221 IN AVERY COUNTY TO SR 1136 (CLARKS CREEK ROAD) IN WATAUGA COUNTY. |  | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566A | Not Funded | T | NOT FUNDED | 1000000 | NOT FUNDED |  | NOT FUNDED | 60351000 | NOT FUNDED |  | 61351000
BEAUFORT | WARREN FIELD (OCW) | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | 0 | Aviation | STI (Prioritization) | 2 | Mid-East RPO | AV-5743 | Division 2 | T | 2030 | 1635000 |  |  | 2032 | 7100000 |  |  | 8735000
BEAUFORT | SR 1112 (MOUTH OF THE CREEK ROAD) | NCDOT | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | 0.25 | Highway | Bridges | 2 | Mid-East RPO | B-5614 | Division 2 | BGOFF | 2022 | 319000 | 2022 | 750000 | 2025 | 17200000 |  |  | 18269000 | RIGHT-OF-WAY IN PROGRESS.
BEAUFORT | US 264 | NCDOT | CONSTRUCT REDUCED CONFLICT INTERSECTION AT US 264 AND SR 1410 (VOA ROAD). | 0.5 | Highway | Safety | 2 | Mid-East RPO | HS-2002D | Statewide Mobility | HSIP | 2022 | 15000 |  |  | 2022 | 939000 |  |  | 954000 | UNDER CONSTRUCTION.
BEAUFORT | US 17 BUSINESS (CAROLINA AVENUE) | NCDOT | WASHINGTON STREET INTERSECTION IN WASHINGTON. INSTALL CHANNELIZATION, PEDESTRIAN SIGNALS, AND OTHER ACCOMMODATIONS. |  | Highway | Safety | 2 | Mid-East RPO | HS-2402K | Region B | HSIP |  |  |  |  | 2025 | 97000 |  |  | 97000
BEAUFORT | US 264 | NCDOT | NC 32 TO THE WESTERN TOWN LIMITS OF PANTEGO. INSTALL RUMBLE STRIPES. |  | Highway | Safety | 2 |  | HS-2402W | Region B | HSIP |  |  |  |  | 2025 | 575000 |  |  | 575000
BEAUFORT | US 17 | NCDOT | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). |  | Highway | STI (Prioritization) | 2 | Mid-East RPO | R-2513E | Not Funded | T | NOT FUNDED | 4600000 | NOT FUNDED | 600000 | NOT FUNDED | 18300000 | NOT FUNDED |  | 23500000
BEAUFORT | SR 1306 (15TH STREET) | NCDOT | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | 1.56 | Highway | STI (Prioritization) | 2 | Mid-East RPO | U-5860 | Division 2 | T | 2026 | 8899000 | 2026 | 4200000 | 2028 | 33600000 |  |  | 46699000
BEAUFORT | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Mid-East RPO | TK-6110 | Public Transit | 5311, L, S | [6 empty] | 2020 | 564000 | 564000 | FUNDS AUTHORIZED IN PROGRESS
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | NCDOT | REPLACEMENT VESSEL (SUPPORT FLEET) FOR TUGS AND BARGES |  | Ferry | STI (Prioritization) | 1, 2, 3 | Jacksonville Urban Area MPO, Albemarle RPO, Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RPO | F-5703 | Division 1, 2, 3
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | NCDOT | Z-DRIVE TOWING AND PUSHING TUG |  | Ferry | STI (Prioritization) | 1, 2, 3 | Albemarle RPO, Cape Fear RPO, Down East RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RP | F-5703A | Division 1, 2, 3 | T |  |  |  |  | 2019 | 3250000 |  |  | 3250000 | COMPLETED.
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | NCDOT | TWO SUPPORT/ANCHOR TUGS, ONE SUPPORT TUG, THREE BARGES |  | Ferry | STI (Prioritization) | 1, 2, 3 | Albemarle RPO, Cape Fear RPO, Down East RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RP | F-5703B | Division 1, 2, 3 | T |  |  |  |  | 2019 | 2100000 |  |  | 2100000 | COMPLETED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | BO-2402 | Division 2 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | BO-2602 | Division 2 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | R-5782 | Division 2 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2002 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 2. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2017
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2017DIV | Division 2 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2017REG | Region B | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2017SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2402 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | HS-2602 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | DIVISION 2 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO | W-5202 | Region B | [10 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | W-5702 | [11 empty] | IN PROGRESS
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | W-5702DIV | Division 2 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | W-5702REG | Region B | HSIP | 2020 | 131000 |  |  | 2020 | 3125000 |  |  | 3256000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | W-5702SW | Statewide Mobility | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 2. |  | Rail | Rail-Highway Grade Crossing Closure | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | RC-2002 | Division 2
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | RX-2002 | Division 2 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | RX-2402 | Division 2 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | RX-2602 | Division 2 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BEAUFORT, PASQUOTANK, PITT, WILSON, BERTIE, CHOWAN, EDGECOMBE, FRANKLIN, MARTIN, NASH, PERQUIMANS, WAKE | GREYHOUND LINES | GREYHOUND LINES | INTERCITY BUS FROM RALEIGH TO NORFOLK, VA VIA ELIZABETH CITY ALONG US 64, US 301, US 264, AND US 17 WITH STOPS AT RALEIGH, ROCKY MOUNT, WILSON, GREENVILLE, WASHINGTON, WILLIAMSTON, EDENTON, AND ELIZABETH CITY |  | Public Transportation (Transit) | Operations and Maintenance | 1, 2, 4, 5 |  | TI-6104 | Public Transit | 5311, L | [6 empty] | 2020 | 9248000 | 9248000 | FUNDS AUTHORIZED IN PROGRESS
BEAUFORT, PITT, EDGECOMBE, PAMLICO | NC 33 | NCDOT | SR 1240 (MAYO ROAD) TO 1625 FEET WEST OF SR 1002 (BAY CITY ROAD) IN BEAUFORT COUNTY; 600 FEET WEST OF SR 1965 (MAIN STREET EXTENSION) TO 700 FEET EAST OF SR 1136 (GRAY ROAD) IN CHOCOWINITY; 525 FEET WEST OF SR 1143 (TAYLOR ROAD) TO 300 FEET EAST OF SR 1568 (CALVERT STREET) IN PITT COUNTY; FRANK EVANS LANE TO SR 2405 (RIVERCREST DRIVE) IN PITT COUNTY; US 264 INTERCHANGE IN GREENVILLE TO NC 42 IN EDGECOMBE COUNTY. INSTALL RUMBLE STRIPS. | 56 | Highway | Safety | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Upper Coastal Plain RPO | HS-2402C | Region A, B | HSIP |  |  |  |  | 2025 | 1400000 |  |  | 1400000
BERTIE | US 13 / US 17 | NCDOT | OVER ROANOKE RIVER OVERFLOW IN BERTIE COUNTY. REPAIR BRIDGES 070155, 070156, 070158, AND 070159. | 1 | Highway | Bridges | 1 | Peanut Belt RPO | HB-0070 | Statewide Mobility | BFP |  |  |  |  | 2025 | 5000000 |  |  | 5000000
BERTIE | US 13 / US 17 | NCDOT | SR 1154 (BUDS LANE) TO US 13 BUSINESS OVERPASS. REHABILITATE PAVEMENT | 2.18 | Highway | Interstate Maintenance | 1 | Peanut Belt RPO | HI-0024 | Statewide Mobility | NHPIM |  |  |  |  | 2029 | 2200000 |  |  | 2200000
BERTIE | US 17 | NCDOT | US 13 BUSINESS OVERPASS TO PAVEMENT JOINT NEAR US 17. REHABILITATE OPEN GRADE FRICTION COURSE PAVEMENT. | 6.48 | Highway | Interstate Maintenance | 1 | Peanut Belt RPO | HI-0025 | Statewide Mobility | NHPIM |  |  |  |  | 2029 | 2000000 |  |  | 2000000
BERTIE | NC 45 | NCDOT | HERTFORD COUNTY LINE TO WASHINGTON COUNTY LINE. MODERNIZE ROADWAY. | 24.8 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5809
BERTIE | NC 45 | NCDOT | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. MODERNIZE ROADWAY. | 9.26 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5809A | Division 1 | BGLT5, T | 2023 | 315000 | 2023 | 150000 | 2025 | 13201000 |  |  | 13666000 | RIGHT-OF-WAY IN PROGRESS.
BERTIE | NC 45 | NCDOT | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. MODERNIZE ROADWAY. | 12.41 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5809B | Division 1 | BGLT5 | 2025 | 4420000 | 2025 | 12944000 | 2028 | 33000000 |  |  | 50364000
BERTIE | NC 45 | NCDOT | SOUTHERN CITY LIMITS OF COLERAIN TO HERTFORD COUNTY LINE. MODERNIZE ROADWAY. | 3.15 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5809C | Division 1 | [10 empty] | COMPLETED.
BERTIE, CURRITUCK | VARIOUS | NCDOT | UPGRADE WARNING SIGNS AT CURVES AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Peanut Belt RPO, Albemarle RPO | HS-2001E | Division 1 | HSIP |  |  |  |  | 2023 | 12000 |  |  | 12000 | UNDER CONSTRUCTION.
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5701DIV | Division 1 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5701REG | Region A | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5701SW | Statewide Mobility | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
BERTIE, HALIFAX, HERTFORD, NORTHAMPTON | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 1, 4 | Peanut Belt RPO | TK-6119 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1972000 | 1972000 | FUNDS AUTHORIZED IN PROGRESS
BERTIE, HERTFORD, GATES | US 13; NC 11 / SR 1212 (SHORTCUT ROAD) | NCDOT | SR 1302 (LEAN LUMBER COMPANY ROAD) IN BERTIE COUNTY TO 0.25 MILES NORTH OF SR 1418 (ARROW ROAD) IN HERTFORD COUNTY, AND SR 1212 (SHORTCUT ROAD) IN HERTFORD COUNTY TO US 158 IN GATES COUNTY; 450 FEET SOUTH OF SR 1130 (MODLIN ROAD) TO US 13. | 22.2 | Highway | Safety | 1 | Peanut Belt RPO, Albemarle RPO | HS-2001G | Statewide Mobility | HSIP |  |  |  |  | 2024 | 895000 |  |  | 895000
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | BO-2401 | Division 1 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | BO-2601 | Division 1 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | R-5781 | Division 1 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2001 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 1. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2016
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2016DIV | Division 1 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2016REG | Region A | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2016SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2401 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | DIVISION 1 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5201 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5701 | [11 empty] | IN PROGRESS.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5801DIV | Division 1
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5801REG | Region A
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | W-5801SW | Statewide Mobility
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 1. |  | Rail | Rail-Highway Grade Crossing Closure | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | RC-2001 | Division 1 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. |  | Rail | Rail-Highway Grade Crossing Improvement | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | RX-2001 | Division 1 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. |  | Rail | Rail-Highway Grade Crossing Improvement | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | RX-2401 | Division 1 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. |  | Rail | Rail-Highway Grade Crossing Improvement | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | RX-2601 | Division 1 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2601 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BLADEN | FIELD (EYF) CURTIS L BROWN JR | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. |  | Aviation | STI (Prioritization) | 6 | Mid-Carolina RPO | AV-5826 | Division 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 920000 | 10120000
BLADEN | SR 1534 (OVER LYON ROAD) | NCDOT | REPLACE BRIDGE 080197 OVER KELLY CANAL. | 0.25 | Highway | Bridges | 6 | Mid-Carolina RPO | B-6004 | Division 6 | [10 empty] | UNDER CONSTRUCTION.
BLADEN | SR 1536 (JAMES PORTER ROAD) | NCDOT | REPLACE BRIDGE 080198 OVER KELLY CANAL. | 0.25 | Highway | Bridges | 6 | Mid-Carolina RPO | B-6008 | Division 6 | [10 empty] | UNDER CONSTRUCTION.
BLADEN | NC 87 | NCDOT | IMPROVE ROADWAY FOR SMITHFIELD FOODS PROCESSING CENTER. | 1.2 | Highway | Economic Development | 6 | Mid-Carolina RPO | R-5866 | Region C | T |  |  |  |  | 2018 | 1042000 |  |  | 1042000 | COMPLETED. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SMITHFIELD FOODS PROCESSING.
BLADEN | NC 410 / NC 131 | DIVISION | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Mid-Carolina RPO | HN-0025 | Exempt | CRPLT5, T(M) |  |  | 2025 | 20000 | 2025 | 2375000 | 2024 | 275000 | 2670000
BLADEN | NC 87 | NCDOT | NC 87 AT SR 1004 (TAR HEEL ROAD) AND SR 1316 (TAR HEEL FERRY ROAD). REVISE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 6 | Mid-Carolina RPO | HS-2006L | Statewide Mobility | HSIP |  |  |  |  | 2023 | 121000 |  |  | 121000 | UNDER CONSTRUCTION.
BLADEN | SR 1325 (GUM SPRINGS ROAD) | NCDOT | SR 1325 (GUM SPRINGS ROAD) NEAR SR 1327. CURVE IMPROVEMENTS. | 0.25 | Highway | Safety | 6 | Mid-Carolina RPO | HS-2006M | Division 6 | HSIP |  |  |  |  | 2024 | 174000 |  |  | 174000
BLADEN | US 701 | NCDOT | SR 1806 (MERCER MILL ROAD), SWANZY STREET, AND KING STREET INTERSECTIONS IN ELIZABETHTOWN. INSTALL CROSSWALKS, PEDESTRIAN SIGNAL HEADS, AND UPGRADE TRAFFIC SIGNALS. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406E | Region C | HSIP |  |  |  |  | 2025 | 715000 |  |  | 715000
BLADEN | NC 87 | NCDOT | ONSLOW COUNTY LINE TO NC 41 ; NC 41 / NC 241 IN BEULAVILLE TO NC 11 ; NC 11 / NC 903 TO WAYNE COUNTY LINE. INSTALL CENTERLINE AND SHOULDER SINUSOIDAL RUMBLE STRIPS. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406HA | Statewide Mobility | HSIP |  |  |  |  | 2025 | 340000 |  |  | 340000
BLADEN | NC 87 | NCDOT | COLUMBUS COUNTY LINE TO SR 1725 (BRADDY PLANTATION ROAD) BLADEN COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406HB | Statewide Mobility | HSIP |  |  |  |  | 2025 | 300000 |  |  | 300000
BLADEN | NC 87 | NCDOT | NC 131 INTERSECTION IN TARHEEL. INSTALL TRAFFIC SIGNAL. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406N | Region C | HSIP | 2025 | 5000 | 2025 | 130000 | 2025 | 510000 |  |  | 645000
BLADEN | NC 87 | NCDOT | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. |  | Highway | STI (Prioritization) | 6 | Cape Fear RPO, Mid-Carolina RPO | R-2561B | Not Funded | T | NOT FUNDED | 18800000 | NOT FUNDED | 6900000 | NOT FUNDED | 100800000 | NOT FUNDED |  | 126500000
BLADEN | BLADEN COUNTY | BLADEN COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Mid-Carolina RPO | TK-6111 | Public Transit | 5311, L, S | [6 empty] | 2020 | 484000 | 484000 | FUNDS AUTHORIZED IN PROGRESS
BLADEN, COLUMBUS | NC 87 | NCDOT | ELIZABETHTOWN BYPASS IN BLADEN COUNTY TO US 74/US 76 IN COLUMBUS COUNTY. WIDEN TO MULTI-LANES. | 30.2 | Highway | STI (Prioritization) | 6 | Cape Fear RPO, Mid-Carolina RPO | R-2561
BLADEN, COLUMBUS | NC 87 | NCDOT | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. |  | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | R-2561A | Not Funded | T | NOT FUNDED | 23000000 | NOT FUNDED | 8300000 | NOT FUNDED | 157400000 | NOT FUNDED |  | 188700000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | BO-2406 | Division 6 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | BO-2606 | Division 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | R-5786 | Division 6 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | Highway | Safety | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | HS-2006 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 6. |  | Highway | Safety | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | HS-2021
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | HS-2021DIV | Division 6 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | HS-2021REG | Region C | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | HS-2021SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | Highway | Safety | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | HS-2406 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | Highway | Safety | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | HS-2606 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5706 | [11 empty] | IN PROGRESS. "HF" FUNDING REPRESENTS HIGH IMPACT / LOW COST (HILC) FUNDS.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5706DIV | Division 6 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5706REG | Region C | HSIP | 2020 | 135000 |  |  | 2020 | 519000 |  |  | 654000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5706SW | Statewide Mobility | HSIP | 2020 | 90000 |  |  | 2020 | 500000 |  |  | 590000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | W-5806
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 6. |  | Rail | Rail-Highway Grade Crossing Closure | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | RC-2006 | Division 6 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | RX-2006 | Division 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | RX-2406 | Division 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | RX-2606 | Division 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BRUNSWICK | CAPE FEAR REGIONAL (SUT) | CAPE FEAR REGIONAL (SUT) | APPROACH CLEARING AT RUNWAY 5 AND RUNWAY 23. | 0 | Aviation | STI (Prioritization) | 3 | Cape Fear RPO | AV-5739 | Division 3 | [10 empty] | COMPLETED.
BRUNSWICK | VARIOUS | NCDOT | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION TRANSPORTATION ALTERNATIVES PROGRAM. |  | Bike & Ped | Locally Selected | 3 | Grand Strand Area Transportation Study | BL-0021 | Division 3 | TADA |  |  |  |  | 2022 | 1752000 |  |  | 1752000
BRUNSWICK | SR 1116 (OCEAN BOULEVARD) | NCDOT | INSTALL BIKE LANES ALONG SR 1116 (OCEAN BOULEVARD) FROM JUST WEST OF SHELL DRIVE TO DUNESCAPE DRIVE IN HOLDEN BEACH. | 6.14 | Bike & Ped | Locally Selected | 3 | Grand Strand Area Transportation Study | BL-0046 | Division 3 | BGDA, L |  |  |  |  | 2022 | 1613000 |  |  | 1613000 | UNDER CONSTRUCTION.
BRUNSWICK | US 17 | LELAND | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 0.1 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0074 | Division 3 | BGDA, L | 2025 | 24000 |  |  | 2025 | 548000 | 2023 | 262000 | 834000
BRUNSWICK | GULLAH GEECHEE HERITAGE TRAIL GAP | BELVILLE | CONSTRUCT MULTI-USE PATH ADJACENT TO NC 133. | 0.22 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0153 | Division 3 | BGDA, L(M) |  |  |  |  | 2027 | 738000 | 2025 | 162000 | 900000
BRUNSWICK | VARIOUS | ST. JAMES | LOCATIONS IN ST. JAMES. REPLACE STREET LIGHTS WITH LED LIGHTS. |  | Bike & Ped | Locally Selected | 3 | Cape Fear RPO | BN-0023 | Exempt | CRP550, L(M) |  |  |  |  | 2025 | 400000 |  |  | 400000
BRUNSWICK | RICE HOPE MULTI-USE PATH | BELVILLE | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 0.17 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6025 | Division 3 | BGDA, L |  |  |  |  | 2023 | 182000 | 2020 | 18000 | 200000 | UNDER CONSTRUCTION.
BRUNSWICK | BELVILLE ELEMENTARY MULTI-USE PATH | BELVILLE | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 0.37 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6026 | Division 3 | L, TADA |  |  |  |  | 2023 | 442000 | 2020 | 52000 | 494000 | UNDER CONSTRUCTION.
BRUNSWICK | SR 1144 (FIRST STREET) | OCEAN ISLE BEACH | CONSTRUCTION OF BIKE LANES ON BOTH SIDES OF FIRST STREET FROM EAST OF WEST FIRST STREET EXTENSION TO EAST OF GREENSBORO STREET IN OCEAN ISLE BEACH. | 2.88 | Bike & Ped | Locally Selected | 3 | Grand Strand Area Transportation Study | EB-6034 | Division 3 | BGDA, L |  |  |  |  | 2021 | 1036000 |  |  | 1036000 | UNDER CONSTRUCTION.
BRUNSWICK | NC 211 (NORTH HOWE STREET) | SOUTHPORT | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 0.26 | Bike & Ped | STI (Prioritization) | 3 | Cape Fear RPO | EB-5982 | Division 3 | L, TA5T50 | 2025 | 50000 |  |  | 2025 | 175000 | 2023 | 30000 | 255000
BRUNSWICK | SR 1342 (MAKATOKA ROAD NORTHWEST) | NCDOT | REPLACE BRIDGE 090100 OVER MUDDY BRANCH. | 0.25 | Highway | Bridges | 3 | Cape Fear RPO | B-4439 | Division 3 | BGOFF | 2022 | 550000 |  |  | 2022 | 1250000 |  |  | 1800000 | UNDER CONSTRUCTION.
BRUNSWICK | SR 1515 (OLD MILL CREEK ROAD SE) | NCDOT | REPLACE BRIDGE 090040 OVER MILL CREEK. | 0.25 | Highway | Bridges | 3 | Cape Fear RPO | B-5629 | Division 3 | BGOFF | 2022 | 115000 |  |  | 2023 | 2759000 |  |  | 2874000 | UNDER CONSTRUCTION.
BRUNSWICK | SR 1300 (ASH-LITTLE RIVER ROAD NORTHWEST) | NCDOT | REPLACE BRIDGE 090126 OVER CAWCAW SWAMP. | 0.25 | Highway | Bridges | 3 | Grand Strand Area Transportation Study | B-5996 | Division 3 | BGOFF | 2022 | 100000 |  |  | 2022 | 2100000 |  |  | 2200000 | UNDER CONSTRUCTION.
BRUNSWICK | NEW ROUTE | NCDOT | ALONG NORTH SIDE OF US 74 FROM 0.5 MILES EAST OF BRUNSWICK COUNTY LINE TO 1.5 MILES EAST OF BRUNSWICK COUNTY LINE. CONSTRUCT ROAD ON NEW LOCATION AND CONSTRUCT INTERSECTIONS WITH US 74 ON EAST AND WEST TERMINI. | 1 | Highway | Economic Development | 3 | Cape Fear RPO | HE-0016 | Division 3 | T |  |  | 2025 | 40000 | 2025 | 9360000 | 2024 | 600000 | 10000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS.
BRUNSWICK | I-140 | NCDOT | US 17 TO NORTH OF US 74. PAVEMENT REHABILITATION. | 5.08 | Highway | Interstate Maintenance | 3 | Wilmington Urban Area MPO | I-6036 | Statewide Mobility | NHPIM |  |  |  |  | 2024 | 11080000 |  |  | 11080000 | UNDER CONSTRUCTION.
BRUNSWICK | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GRAND STRAND AREA TRANSPORTATION STUDY PLANNING ORGANIZATION. |  | Highway | Locally Selected | 3 | Grand Strand Area Transportation Study | HL-0103 | Exempt | CRPDA, L |  |  |  |  | 2023 | 214000 |  |  | 214000
BRUNSWICK | NC 133 | BELVILLE | BELVILLE RIVERWALK PARK ENTRANCE. CONSTRUCT TRAFFIC SIGNAL AND RELATED PEDESTRIAN INFRASTRUCTURE. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0131 | Exempt | CRPDA, L |  |  |  |  | 2026 | 1458000 | 2025 | 81000 | 1539000
BRUNSWICK | SHALLOTTE | SHALLOTTE | INSTALL ADAPTIVE SIGNAL SYSTEM IN SHALLOTTE. |  | Highway | Locally Selected | 3 | Grand Strand Area Transportation Study | HL-0132 | Division 3 | BGDA, CRPDA, HF(M) |  |  |  |  | 2024 | 398000 |  |  | 398000 | HF(M) FUNDS REPRESENT DIVISION 3 HIGH IMPACT LOW COST FUNDS.
BRUNSWICK | VARIOUS | NCDOT | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | Highway | Locally Selected | 3 | Grand Strand Area Transportation Study | U-5910 | Division 3 | BGDA, L | [6 empty] | 2023 | 540000 | 540000 | IN PROGRESS
BRUNSWICK | VARIOUS | NCDOT | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | Highway | Locally Selected | 3 | Grand Strand Area Transportation Study | U-5990 | Division 3 | BGANY, BGDA |  |  |  |  | 2022 | 13977000 |  |  | 13977000
BRUNSWICK | US 17 BUSINESS | NCDOT | AT NC 906 (MIDWAY ROAD). INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Cape Fear RPO | HS-2003AR | Region B | HSIP | 2025 | 48000 |  |  | 2025 | 257000 |  |  | 305000
BRUNSWICK | US 74/76 (ANDREW JACKSON HIGHWAY) | NCDOT | EASTBOUND RAMP AT SR 1426 (LANVALE ROAD). INSTALLTRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AS | Region B | HSIP |  |  |  |  | 2025 | 237000 |  |  | 237000
BRUNSWICK | US 17 | NCDOT | US 17 AND SR 1130 (MOUNT PISGAH ROAD) / SR 1344 (SELLERS ROAD). INSTALL SIGNALIZED LEFTOVER. |  | Highway | Safety | 3 | Grand Strand Area Transportation Study | HS-2003D | Statewide Mobility | HSIP |  |  |  |  | 2025 | 269000 |  |  | 269000
BRUNSWICK | NC 130 | NCDOT | NC 130 AND SR 1120 (SABBATH HOME ROAD) / SR 1239 (OCEAN VIEW AVENUE) IN HOLDEN BEACH. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 0.5 | Highway | Safety | 3 | Grand Strand Area Transportation Study | HS-2003G | Region B | HSIP |  |  |  |  | 2024 | 101000 |  |  | 101000
BRUNSWICK | US 74/76 | NCDOT | US 74/76 AT SR 1714 (ENTERPRISE DRIVE) AND US 74/76 AT SR 1494 (WOOD TREATMENT ROAD). INSTALL TRAFFIC SIGNALS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003O | Statewide Mobility | HSIP |  |  |  |  | 2026 | 533000 |  |  | 533000
BRUNSWICK | US 17 | NCDOT | US 17 AT SR 1136 (RED BUG ROAD) AND US 17 AT SR 1345 (ROYAL OAK ROAD). INSTALL A REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | Safety | 3 | Grand Strand Area Transportation Study | HS-2003W | Statewide Mobility | HSIP |  |  |  |  | 2023 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION.
BRUNSWICK | NC 211 | NCDOT | SR 1500 (MIDWAY ROAD) TO NC 87. WIDEN TO FOUR LANES. | 6.55 | Highway | STI (Prioritization) | 3 | Cape Fear RPO | R-5021 | Division 3 | BGANY |  |  | 2023 | 10850000 | 2022 | 239876000 |  |  | 250726000 | UNDER CONSTRUCTION.
BRUNSWICK | US 17 | NCDOT | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 1 | Highway | STI (Prioritization) | 3 | Grand Strand Area Transportation Study | R-5857 | Statewide Mobility | T | 2023 | 770000 | 2024 | 325000 | 2026 | 26199000 |  |  | 27294000 | RIGHT-OF-WAY IN PROGRESS.
BRUNSWICK | US 17 BUSINESS (MAIN STREET) | NCDOT | WALL STREET/SHALLOTTE AVENUE. REALIGN INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Grand Strand Area Transportation Study | U-5788 | Division 3 | T |  |  |  |  | 2021 | 1964000 |  |  | 1964000 | UNDER CONSTRUCTION.
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | NCDOT | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 3 | Grand Strand Area Transportation Study | U-5862 | Region B | T | 2028 | 8500000 | 2028 | 1900000 | 2031 | 43600000 |  |  | 54000000
BRUNSWICK | NC 133 | NCDOT | US 17/US 74/US 76 TO SR 1554 (OLD RIVER ROAD). MODERNIZE ROADWAY. | 0.48 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5914 | Division 3 | T |  |  |  |  | 2023 | 6933000 |  |  | 6933000 | UNDER CONSTRUCTION.
BRUNSWICK | I-140/US 17 WILMINGTON BYPASS | NCDOT | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO SR 1430 (CEDAR HILL ROAD). | 7.6 | Highway | Transition | 3 | Wilmington Urban Area MPO | R-2633BA | Pre-STI (Transition) | NHP |  |  |  |  | 2014 | 30750000 |  |  | 30750000 | COMPLETED. GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK 2014 - 2025.
BRUNSWICK | BRUNSWICK TRANSIT SYSTEM, INC. | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Cape Fear RPO | TK-6112 | Public Transit | 5311, L, S | [6 empty] | 2020 | 712000 | 712000 | FUNDS AUTHORIZED IN PROGRESS
BRUNSWICK, NEW HANOVER | SOUTHPORT - FORT FISHER | NCDOT | CONSTRUCT MOORING FACILITIES. |  | Ferry | STI (Prioritization) | 3 | Cape Fear RPO, Wilmington Urban Area MPO | F-5707 | Region B | FBP, T |  |  |  |  | 2025 | 5000000 | 2023 | 2031000 | 7031000
BRUNSWICK, NEW HANOVER | I-140/US 17 (WILMINGTON BYPASS) | NCDOT | US 17 SOUTH OF NC 87 IN BRUNSWICK COUNTY TO I-40 IN NEW HANOVER COUNTY. FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | 20.2 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. | 5.3 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633AA | Pre-STI (Transition) | NHP |  |  |  |  | 2010 | 6810000 |  |  | 6810000 | COMPLETED. GARVEE BOND FUNDING: $31.05M FOR CONSTRUCTION, PAYBACK 2010 - 2021.
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. |  | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633AB | [11 empty] | COMPLETED.
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO WEST OF US 421 NORTH OF WILMINGTON. |  | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633BC | [11 empty] | COMPLETED.
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | IMPLEMENTATION OF INTELLIGENT TRANSPORTATION SYSTEMS (ITS). | 20.13 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633D | Pre-STI (Transition) | [10 empty] | COMPLETED.
BRUNSWICK, NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE OPERATING ASSISTANCE PROJECT WILL ALLOW THE CONTINUATION OF COMPLEMENTARY PARATRANSIT SERVICE TO TWO COUNTIES AND FOUR MUNICIPLITIES WITHIN THE UZA. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-5246 | Public Transit | 5307, L | [6 empty] | 2023 | 1093000 | 1093000
BRUNSWICK, ONSLOW, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO, Grand Strand Area Transportation Study, Wilmington Urban Area MPO | W-5203SW | Statewide Mobility
BUNCOMBE | ASHEVILLE REGIONAL AIRPORT | ASHEVILLE REGIONAL AIRPORT (AVL) | MODERNIZE AIRPORT TERMINAL BUILDING. |  | Aviation | Other | 13 | French Broad River MPO | AO-0001 | Exempt | FED, HF, L |  |  |  |  | 2022 | 153808000 |  |  | 153808000 | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "HF" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT
BUNCOMBE | ASHEVILLE REGIONAL AIRPORT (AVL) | ASHEVILLE REGIONAL AIRPORT (AVL) | AIRFIELD IMPROVEMENTS PROGRAM - RUNWAY CONSTRUCTION |  | Aviation | STI (Prioritization) | 13 | French Broad River MPO | AV-5735 | Region G | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | NC 251/ SR 1781 (BROADWAY STREET) | NCDOT | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 0.23 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | BL-0005 | Division 13 | BGDA, HF, HF(M), HSIP |  |  |  |  | 2022 | 1124000 | 2021 | 4000 | 1128000 | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID.
BUNCOMBE | VARIOUS | NCDOT | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | BL-0006 | Division 13 | BGDA, L |  |  |  |  | 2027 | 750000 | 2026 | 75000 | 825000
BUNCOMBE | RICEVILLE ROAD | NCDOT | US 70 TO NORTH OF THE VETERANS AFFAIRS HOSPITAL DRIVEWAY. CONSTRUCT SIDEWALK AND CROSSING IMPROVEMENTS. | 0.16 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | BL-0076 | Division 13 | HF(M), TADA | 2025 | 788000 |  |  | 2026 | 1951000 | 2024 | 374000 | 3113000 | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP
BUNCOMBE | SWANNANOA GREENWAY | ASHEVILLE | BLEACHERY BOULEVARD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | BL-0077 | Division 13 | BGDA, L, TAANY |  |  |  |  | 2028 | 3115000 | 2027 | 10000 | 3125000 | $2.381M OF STBG-DA FUNDS SWAPPED FOR $2.381M IN TAP-ANYAREA FUNDS ON 8-15-24.
BUNCOMBE | TEXAS ROAD | MONTREAT | REPLACE EXISTING HIGHWAY BRIDGE WITH PEDESTRIAN BRIDGE. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | BL-0079 | Division 13 | BGDA, L |  |  |  |  | 2024 | 181000 | 2024 | 10000 | 191000
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | BLACK MOUTAIN | CONSTRUCT MULTI-USE PATH FROM EXISTING FLAT CREEK GREENWAY TRAILHEAD NORTH OF US 70 TO THE OAKS TRAIL. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5547 | Division 13 | [10 empty] | $3.234M IN BGANY USED AS PART OF MULTIPLE FUND SWAPS. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.991M. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.915M.
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | BLACK MOUTAIN | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5547A | Division 13 | BGANY, L | 2025 | 40000 |  |  | 2026 | 1559000 | 2023 | 290000 | 1889000
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | BLACK MOUTAIN | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5547B | Division 13 | BGANY, L | 2025 | 20000 |  |  | 2026 | 1551000 | 2022 | 184000 | 1755000
BUNCOMBE | NC 251 (RIVERSIDE DRIVE) MULTI-USE PATH | BUNCOMBE COUNTY | US 19/23/70 (EXIT 25) TO US 25. CONSTRUCT MULTI-USE PATH VIA BEAVERDAM CREEK. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5774 | Division 13 | BGDA, L | [6 empty] | 2020 | 2000000 | 2000000 | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION
BUNCOMBE | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | ASHEVILLE | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5774A | Division 13 | BGDA, L, TADA | 2025 | 4259000 |  |  | 2026 | 6010000 |  |  | 10269000
BUNCOMBE | BEAVERDAM CREEK GREENWAY | ASHEVILLE | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5774B | Division 13 | BGANY, BGDA, L, TADA | 2025 | 608000 |  |  | 2026 | 3450000 |  |  | 4058000
BUNCOMBE | ASHEVILLE | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5790 | Division 13 | BGDA, L, TAANY |  |  |  |  | 2024 | 1639000 |  |  | 1639000 | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23.
BUNCOMBE | REEMS CREEK GREENWAY | BUNCOMBE COUNTY | CONSTRUCT MULTI-USE PATH ALONG REEMS CREEK CORRIDOR FROM WESTERN EDGE OF TOWN OF WEAVERVILLE TO KARPEN SOCCER FIELDS |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5821 | Division 13 | BGDA, L | [6 empty] | 2029 | 600000 | 600000 | IN PROGRESS
BUNCOMBE | BENT CREEK GREENWAY | BUNCOMBE COUNTY | HOMINY CREEK RIVER PARK TO WESTERN NC FARMERS MARKET. CONSTRUCT MULTI-USE PATH. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5823 | Division 13 | BGDA, L | [6 empty] | 2029 | 400000 | 400000
BUNCOMBE | ENKA HERITAGE TRAIL | NCDOT | WARREN HAYNES DRIVE AND SAND HILL ROAD INTERSECTION TO EAST OF US 19 / US 23 AND SAND HILL ROAD INTERSECTION. CONSTRUCT MULTI-USE PATH. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5824 | Division 13 | BGANY, BGDA, L(M) |  |  |  |  | 2026 | 3844000 | 2021 | 1310000 | 5154000 | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES.
BUNCOMBE | ASHEVILLE | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5831 | Division 13 | BGANY, BGDA, L(M), TADA | 2025 | 300000 |  |  | 2026 | 11003000 | 2023 | 900000 | 12203000 | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP.
BUNCOMBE | JOHNSTON BOULEVARD ASHEVILLE | ASHEVILLE | PATTON AVENUE TO IONA CIRCLE IN ASHEVILLE. CONSTRUCT SIDEWALKS. | 0.95 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5944 | Division 13 | BGDA, L |  |  |  |  | 2025 | 2350000 |  |  | 2350000
BUNCOMBE | NEW HAW CREEK ROAD ASHEVILLE | ASHEVILLE | BEVERLY ROAD TO BELL ROAD IN ASHEVILLE. CONSTRUCT SIDEWALKS. | 0.79 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5947 | Division 13 | BGANY, L |  |  |  |  | 2024 | 2365000 | 2024 | 10000 | 2375000 | $1.9M IN BGANY USED AS PART OF FUND SWAP
BUNCOMBE | ASHEVILLE | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | 0.39 | Bike & Ped | Locally Selected | 13 | French Broad River MPO | EB-5948 | Division 13 | BGDA, L, TADA |  |  |  |  | 2023 | 1140000 |  |  | 1140000 | UNDER CONSTRUCTION.
BUNCOMBE | GREENWAY WILMA DYKEMAN | NCDOT | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | Bike & Ped | STI (Prioritization) | 13 | French Broad River MPO | EB-5822 | Division 13 | L, TAANY | 2026 | 129000 |  |  | 2027 | 4000000 | 2019 | 600000 | 4729000 | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23.
BUNCOMBE | DEAVERVIEW ROAD | ASHEVILLE | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | Bike & Ped | STI (Prioritization) | 13 | French Broad River MPO | EB-5965 | Division 13 | L, TAANY | 2029 | 250000 | 2029 | 1100000 | 2031 | 6950000 | 2028 | 710000 | 9010000
BUNCOMBE | NEW LEICESTER HIGHWAY | ASHEVILLE | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. |  | Bike & Ped | Transition | 13 | French Broad River MPO | U-5190 | Pre-STI (Transition) | BGANY, BGDA, L | 2020 | 241000 |  |  | 2022 | 3322000 |  |  | 3563000 | UNDER CONSTRUCTION. $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE
BUNCOMBE | NEW ROUTE- ENKA HERITAGE ROAD | NCDOT | CONSTRUCT ACCESS ROAD FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | 0.3 | Highway | Appalachian Development Highway System | 13 | French Broad River MPO | U-6251 | Exempt | ADHSL | [6 empty] | 2022 | 140000 | 140000 | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. HF REPRESENTS SPOT MOBILITY FUNDS.
BUNCOMBE | NEW ROUTE - ENKA HERITAGE ROAD | NCDOT | US 19/23 (SMOKEY PARK HIGHWAY) TO WALKOFF WAY. CONSTRUCT ACCESS ROAD ON NEW LOCATION. | 0.3 | Highway | Appalachian Development Highway System | 13 | French Broad River MPO | U-6251A | Exempt | ADHSL, L |  |  |  |  | 2022 | 2850000 |  |  | 2850000 | UNDER CONSTRUCTION.
BUNCOMBE | US 19/23 (SMOKEY PARK HIGHWAY) | NCDOT | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Appalachian Development Highway System | 13 | French Broad River MPO | U-6251B | Exempt | ADHSL, HF, L | 2022 | 900000 |  |  | 2023 | 395000 |  |  | 1295000 | UNDER CONSTRUCTION.
BUNCOMBE | US 19/US 23/US 25/ US 70 | NCDOT | REPLACE BRIDGE 100370, AND BRIDGE 100373 OVER REEMS CREEK. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-4442 | Statewide Mobility | NHPB | 2022 | 400000 |  |  | 2022 | 29996000 |  |  | 30396000 | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION.
BUNCOMBE | US 19/US 23/US 25/ US 70 | NCDOT | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-4443 | Statewide Mobility | BFP | 2025 | 700000 | 2025 | 700000 | 2029 | 50100000 |  |  | 51500000 | COORDINATE WITH A-0010A
BUNCOMBE | US 19/23/25/70 | NCDOT | REHABILITATE DECK ON BRIDGE 100353 OVER SR 1882. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-4444 | Statewide Mobility | [10 empty] | COORDINATE WITH A-0010A.
BUNCOMBE | SR 2027 (MARTINS CREEK ROAD) | NCDOT | REPLACE BRIDGE 100142 OVER MARTIN CREEK. | 0.25 | Highway | Bridges | 13 | Land-of-Sky RPO | B-6016 | Division 13 | BGOFF | 2022 | 50000 |  |  | 2022 | 700000 |  |  | 750000 | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014
BUNCOMBE | SR 1296 (BROOKS BRANCH ROAD) | NCDOT | REPLACE BRIDGE 100536 OVER NEWFOUND CREEK. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-6018 | Division 13 | BGOFF | 2021 | 55000 |  |  | 2021 | 872000 |  |  | 927000 | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION.
BUNCOMBE | I-26 | NCDOT | CONSTRUCT NEW INTERCHANGE NEAR AN ACCESS ROAD NEAR MILEMARKER 35, CONNECTING TO FREDERICK LAW OLMSTEAD WAY EAST. | 1 | Highway | Economic Development | 13 | French Broad River MPO | HE-0001 | Exempt | HF | 2022 | 200000 |  |  |  |  | 2022 | 4358000 | 4558000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. HIGHWAY FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY.
BUNCOMBE | I-26 |  | MILEMARKER 35. CONSTRUCT INTERCHANGE. |  | Highway | Economic Development | 13 | French Broad River MPO | HE-0001A | Exempt | HF |  |  |  |  | 2024 | 24360000 |  |  | 24360000
BUNCOMBE | NEW ROUTE |  | FREDERICK LAW OLMSTEAD WAY EAST TO I-26. CONSTRUCT TWO LANE ROAD WITH SIDEWALK. |  | Highway | Economic Development | 13 | French Broad River MPO | HE-0001B | Exempt | ADHSL, HF |  |  |  |  | 2025 | 10582000 |  |  | 10582000
BUNCOMBE | WALK OFF WAY | NCDOT | CONSTRUCT WALK OFF WAY EXTENSION FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | 0.27 | Highway | Economic Development | 13 | French Broad River MPO | U-6230 | Division 13 | T |  |  |  |  | 2021 | 1300000 |  |  | 1300000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR HAAKON INDUSTRIES. AWARD AMOUNT = $1,300,000 - COMPLETE.
BUNCOMBE | I-40 | NCDOT | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 1.39 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-2513AA | Statewide Mobility | HP, NHFP, NHPIM | 2023 | 2000000 | 2023 | 100000 | 2024 | 83029000 |  |  | 85129000 | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS.
BUNCOMBE | I-40 | NCDOT | MILE MARKER 37 TO MILE MARKER 44. REHABILIATE PAVEMENT AND BRIDGES. | 6.5 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5888 | Statewide Mobility
BUNCOMBE | I-40 | NCDOT | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE PAVEMENT AND BRIDGES. | 6.73 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5888A | Statewide Mobility | [10 empty] | COMPLETE
BUNCOMBE | I-40 | NCDOT | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE BRIDGES. | 7.17 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5888B | Statewide Mobility | NHPIM |  |  |  |  | 2027 | 6900000 |  |  | 6900000
BUNCOMBE | I-40 | NCDOT | MILE MARKER 44 TO MILE MARKER 50. REHABILTATE PAVEMENT AND PRESERVE BRIDGES. | 4 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5889
BUNCOMBE | I-40 | NCDOT | MILE MARKER 46 TO MILE MARKER 50. PRESERVE BRIDGES. | 4.65 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5889A | Statewide Mobility | [10 empty] | COMPLETED
BUNCOMBE | I-40 | NCDOT | MILE MARKER 44 TO MILE MARKER 50. REHABILITATE PAVEMENT AND PRESERVE BRIDGES 100352, 100356, 100344, 100347, 100339, AND 100334. | 4.62 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5889B | Statewide Mobility | NHPIM, T |  |  |  |  | 2023 | 36186000 |  |  | 36186000 | UNDER CONSTRUCTION.
BUNCOMBE | I-40 | NCDOT | MILEMARKER 55 TO MILEMARKER 67.5. PAVEMENT REHABILITATION. | 11.99 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5890 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 23160000 |  |  | 23160000 | COMPLETE - GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033.
BUNCOMBE | I-240 | NCDOT | MILEMARKER 4 TO MILEMARKER 9. PAVEMENT REHABILITATION. | 4.69 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-5901 | Statewide Mobility | NHPIM |  |  |  |  | 2027 | 20908000 |  |  | 20908000
BUNCOMBE | I-40 | NCDOT | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | 4.96 | Highway | Interstate Maintenance | 13 | French Broad River MPO | I-6063 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 30222000 |  |  | 30222000 | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034
BUNCOMBE | US 19/23 BUSINESS (HAYWOOD ROAD) | NCDOT | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 1.88 | Highway | Locally Selected | 13 | French Broad River MPO | HL-0003 | Region G | BGANY, BGDA, HF(M) |  |  |  |  | 2025 | 7523000 | 2022 | 320000 | 7843000 | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
BUNCOMBE | I-240 | NCDOT | US 70 (CHARLOTTE STREET) INTERSECTIONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS AND A RIGHT TURN LANE ON THE I-240 EASTBOUND OFF-RAMP. | 0.5 | Highway | Locally Selected | 13 | French Broad River MPO | HL-0012 | Exempt | BGDA, HF(M) |  |  |  |  | 2023 | 1680000 |  |  | 1680000 | UNDER CONSTRUCTION. "HF(M)" FUNDS REPRESENT SPOT MOBILITY AND HIGH IMPACT/LOW COST FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. PE AND ROW FUNDED UNDER SM-5713E (HIGHWAY FUNDS).
BUNCOMBE | 9TH STREET | NCDOT | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | Highway | Locally Selected | 13 | French Broad River MPO | HL-0013 | Division 13 | BGANY, BGDA, L | 2025 | 120000 |  |  | 2026 | 680000 | 2022 | 315000 | 1115000 | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP
BUNCOMBE | SR 3214 (BILTMORE AVENUE) | ASHEVILLE | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | Highway | Locally Selected | 13 | French Broad River MPO | HL-0014 | Division 13 | BGANY, BGDA, L | 2026 | 25000 |  |  | 2027 | 340000 | 2022 | 75000 | 440000 | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | NCDOT | SR 3081 (ROCK HILL ROAD) TO SR 3079 (ROBERTS ROAD) | 1.473 | Highway | Pre-STI (Historic) | 13 | French Broad River MPO | U-2801B | [11 empty] | COMPLETE
BUNCOMBE | NC 63 (LEICESTER HIGHWAY) | NCDOT | SR 1615 (GILBERT ROAD) TO WEST OF SR 1004 (NEWFOUND ROAD) IN ASHEVILLE. WIDEN TO MULTI-LANES, SOME RELOCATION. | 4.32 | Highway | Pre-STI (Historic) | 13 | French Broad River MPO | U-3301 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION - DESIGN BUILD PROJECT
BUNCOMBE | SR 1003 (REEMS CREEK ROAD) | NCDOT | SR 2106 TO SR 2114 NEAR WEAVERVILLE. INSTALL GUARDRAIL. | 3.61 | Highway | Safety | 13 | French Broad River MPO | HS-2013K | Division 13 | HSIP |  |  |  |  | 2024 | 274000 |  |  | 274000
BUNCOMBE | SR 3075 (ONTEORA BOULEVARD) | NCDOT | BRIDGE #100460 OVER I-40. CONSTRUCT SIDEWALK AND UPGRADE BRIDGE RAIL. | 0.5 | Highway | Safety | 13 | French Broad River MPO | HS-2013O | Division 13 | HSIP |  |  |  |  | 2025 | 395000 |  |  | 395000
BUNCOMBE | NC 63 | NCDOT | SR 1220 (SOUTH TURKEY CREEK ROAD) NEAR LEICESTER. CONSTRUCT TURN LANE. | 0.5 | Highway | Safety | 13 | French Broad River MPO | HS-2013P | Region G | HSIP | 2025 | 5000 |  |  | 2026 | 715000 |  |  | 720000
BUNCOMBE | SR 3136 (CANE CREEK ROAD) | NCDOT | SR 3116 (MILLS GAP ROAD) TO US 74 ALTERNATE NEAR FAIRVIEW. INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 13 | French Broad River MPO | HS-2413G | Division 13 | HSIP |  |  |  |  | 2026 | 235000 |  |  | 235000
BUNCOMBE | SR 1002 (OLD LEICESTER HIGHWAY) | NCDOT | NC 63 TO SR 1607 NEAR LEICESTER. INSTALL GUARDRAIL. |  | Highway | Safety | 13 | French Broad River MPO | HS-2413I | Division 13 | HSIP |  |  |  |  | 2025 | 267000 |  |  | 267000
BUNCOMBE | SR 1727 (MONTICELLO ROAD) | NCDOT | SR 1882 (NEW STOCK ROAD) TO EAST OF NC 251 (OLD MARSHALL HIGHWAY). INSTALL GUARDRAIL. |  | Highway | Safety | 13 | French Broad River MPO | HS-2413J | Division 13 | HSIP |  |  |  |  | 2025 | 300000 |  |  | 300000
BUNCOMBE | US 19 / US 23 / US 74 ALT (SMOKEY PARK HIGHWAY) | NCDOT | I-40 TO COOPER BOULEVARD. INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND SIDEWALK. | 26.2 | Highway | Safety | 13 | French Broad River MPO | HS-2413K | Region G | HSIP |  |  | 2025 | 25000 | 2025 | 905000 |  |  | 930000
BUNCOMBE | VARIOUS | NCDOT | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. |  | Highway | Safety | 13 | French Broad River MPO | W-5213DIV | Division 13 | HSIP | 2020 | 50000 |  |  | 2020 | 700000 |  |  | 750000 | IN PROGRESS.
BUNCOMBE | SR 2002 (RICEVILLE ROAD) | NCDOT | NORTH OF US 70 TO SR 2419 (BULL CREEK ROAD) NEAR HAW CREEK. INSTALL 6" LONG LIFE PAVEMENT MARKINGS. | 3.64 | Highway | Safety | 13 | French Broad River MPO | W-5213G | Division 13 | HSIP |  |  |  |  | 2024 | 909000 |  |  | 909000 | UNDER CONSTRUCTION.
BUNCOMBE | US 25 | NCDOT | US 25 (MCDOWELL STREET) AT DOCTOR'S DRIVE/ASHEVILLE HIGH SCHOOL ENTRANCE. INSTALL PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | 0.5 | Highway | Safety | 13 | French Broad River MPO | W-5813A | Region G | HSIP |  |  |  |  | 2022 | 64000 |  |  | 64000 | UNDER CONSTRUCTION.
BUNCOMBE | SR 1332 | NCDOT | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | 0.5 | Highway | Safety | 13 | French Broad River MPO | W-5813C | Division 13 | HSIP | 2022 | 2000 |  |  | 2023 | 155000 |  |  | 157000 | UNDER CONSTRUCTION.
BUNCOMBE | US 19-23-74 ALT | NCDOT | US 19-23-74 ALT (PATTON AVENUE) AT US 19-23 BUS (HAYWOOD ROAD)/SR 1319 (JOHNSTON ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS AND CURB RAMPS. | 0.5 | Highway | Safety | 13 | French Broad River MPO | W-5813E | Region G | HSIP |  |  |  |  | 2023 | 145000 |  |  | 145000 | UNDER CONSTRUCTION.
BUNCOMBE | US 19-23-74 ALT | NCDOT | US 19-23-74 ALT (SMOKEY PARK HIGHWAY) AT OLD HAYWOOD ROAD. INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | 0.5 | Highway | Safety | 13 | French Broad River MPO | W-5813F | Region G | HSIP |  |  |  |  | 2023 | 105000 |  |  | 105000 | UNDER CONSTRUCTION.
BUNCOMBE | US 70; US 74 ALT | NCDOT | (1) US 70 (TUNNEL ROAD) AT OLD CHUNNS COVE ROAD, (2) US 74 ALT (S. TUNNEL ROAD) AT MAIN MALL ENTRANCE (EAST LEG), (3) US 74 ALT (S. TUNNEL ROAD) AT LOWER MALL ENTRANCE. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | 1 | Highway | Safety | 13 | French Broad River MPO | W-5813G | Region G | HSIP |  |  |  |  | 2022 | 336000 |  |  | 336000 | UNDER CONSTRUCTION.
BUNCOMBE | SR 2806 | NCDOT | SR 2806 (GARREN CREEK ROAD) FROM SR 2815 TO SR 2786, NEAR FAIRVIEW. INSTALL SHOULDER GUARDRAIL. | 6.53 | Highway | Safety | 13 | Land-of-Sky RPO | W-5813I | Division 13 | HSIP |  |  |  |  | 2022 | 460000 |  |  | 460000 | COMPLETE
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | BREAK NO LONGER USED. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AA | Region G
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | NC 251/SR 1781 (BROADWAY STREET) INTERCHANGE. IMPROVE INTERCHANGE. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AB | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26499000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34400000 |  |  | 62699000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | SR 1684 (ELK MOUNTAIN ROAD) INTERCHANGE. IMPROVE INTERCHANGE. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AC | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22106000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1697000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 42700000 |  |  | 66503000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | US 25 (MERRIMON AVENUE) INTERCHANGE. IMPROVE INTERCHANGE. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AD | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 46300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74500000 |  |  | 122400000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | SR 1882 (NEW STOCK ROAD) INTERCHANGE. IMPROVE INTERCHANGE AREA INCLUDING WIDENING I-26 TO NORTH OF SR 1720 (AIKEN ROAD). |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AE | Region G | NHP | 2028 | 24100000 | 2028 | 2300000 | 2031 | 93900000 |  |  | 120300000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | US 25/US 70 INTERCHANGE. IMPROVE INTERCHANGE. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AF | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4656000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 737000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36400000 |  |  | 41793000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | NC 251/SR 1728 (BROADWAY STREET) TO US 25/US 70. WIDEN ROADWAY TO EIGHT AND SIX LANES. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AG | Region G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 230000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 207600000 |  |  | 212430000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | US 25/US 70 TO SR 2207 (N BUNCOMBE SCHOOL ROAD). UPGRADE TO ROADWAY TO INTERSTATE STANDARDS. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AJ | Not Funded | T | NOT FUNDED | 5600000 | NOT FUNDED |  | NOT FUNDED | 72001000 | NOT FUNDED |  | 77601000
BUNCOMBE | I-26 (US 19/US 23) | NCDOT | SR 2207 (N BUNCOMBE SCHOOL ROAD) TO SOUTH OF SR 2148 (STOCKTON ROAD). UPGRADE ROADWAY TO INTERSTATE STANDARDS. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | A-0010AK | Not Funded | T | NOT FUNDED | 700000 | NOT FUNDED |  | NOT FUNDED | 27001000 | NOT FUNDED |  | 27701000
BUNCOMBE | I-26/I-240 | NCDOT | I-26 CONNECTOR, I-40 TO US 19/US 23. CONSTRUCT MULTI-LANE FREEWAY, PART ON NEW LOCATION. | 4.7 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513
BUNCOMBE | I-26, I-40 | NCDOT | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513AB | Region G | HP, NHP | 2023 | 3400000 | 2023 | 100000 | 2024 | 39508000 |  |  | 43008000 | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS.
BUNCOMBE | I-26/I-240 | NCDOT | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 1.85 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513AC | Region G | T | 2023 | 41969000 | 2023 | 3750000 | 2027 | 264650000 |  |  | 310369000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE);
BUNCOMBE | I-40, I-26 | NCDOT | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET). | 2.75 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513B | Statewide Mobility | NHP | 2024 | 150700000 | 2024 | 24100000 | 2024 | 1245990000 |  |  | 1420790000 | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D.
BUNCOMBE | I-26/I-240 | NCDOT | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513C | Not Funded | NHP | NOT FUNDED | 8900000 | NOT FUNDED | 13400000 | NOT FUNDED | 261701000 | NOT FUNDED |  | 284001000
BUNCOMBE | SR 1477 (RIVERSIDE DRIVE) | NCDOT | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET). | 1.44 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-2513D | Division 13 | BGANY | 2024 | 24900000 | 2024 | 3300000 | 2024 | 21600000 |  |  | 49800000 | TO BE LET WITH I-2513B.
BUNCOMBE | SR 2500 (BLUE RIDGE ROAD) | NCDOT | CONVERT I-40 / SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4409 | Division 13 | NHP, T | 2024 | 6300000 | 2024 | 900000 | 2026 | 41975000 |  |  | 49175000 | NC BUILD BOND FUNDING: $15M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE)
BUNCOMBE | I-40 | NCDOT | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 1.52 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4759 | Statewide Mobility | BGANY, BGDA | 2019 | 15582000 | 2019 | 700000 | 2030 | 88899000 |  |  | 105181000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033
BUNCOMBE | I-40, SR 1228 (LIBERTY ROAD) | NCDOT | CLEARING ONLY. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-4759A | Statewide Mobility | BGANY |  |  |  |  | 2029 | 500000 |  |  | 500000
BUNCOMBE | I-26 | NCDOT | NC 191 (BREVARD ROAD). UPGRADE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 13 | French Broad River MPO | I-5504 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION AS DESIGN-BUILD PROJECT
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | NCDOT | US 25 (HENDERSONVILLE ROAD) TO ROBERTS ROAD IN ASHEVILLE. WIDEN TO MULTI-LANES. | 7.3 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-2801
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | NCDOT | US 25 (HENDERSONVILLE ROAD) TO SR 3116 (MILLS GAP ROAD) | 2.77 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-2801AA | Not Funded | BGANY | NOT FUNDED | 92500000 | NOT FUNDED | 10200000 | NOT FUNDED | 39400000 | NOT FUNDED |  | 142100000
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | NCDOT | SR 3116 (MILLS GAP ROAD) TO SR 3081 (ROCK HILL ROAD) | 2.68 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-2801AB | Region G | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56599000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 151500000 |  |  | 215199000
BUNCOMBE | CITYWIDE | NCDOT | SIGNAL IMPROVEMENTS |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-4715B | Division 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | SR 3556 (AMBOY ROAD/ MEADOW ROAD) | NCDOT | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). UPGRADE ROADWAY WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | 2.87 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-4739 | Division 13 | BGANY, T | 2027 | 24100000 | 2027 | 5400000 | 2030 | 65130000 |  |  | 94630000 | NC BUILD BONDS: $13M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
BUNCOMBE | ASHEVILLE EAST OF THE RIVERWAY MULTI-MODAL NETWORK | NCDOT | CONSTRUCT INTERCONNECTED NETWORK OF PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. PROJECT INCLUDES: CLINGMAN FOREST AND TOWN BRANCH GREENWAYS, FRENCH BROAD RIVER WEST GREENWAY, WILMA DIKEMAN RIVERWAY AND FIVE POINTS ROUNDABOUT, LIVINGSTON S |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019 | [11 empty] | SEGMENT A - $3.42M IN BGANY USED AS PART OF FUND SWAP, $8K USED FOR PRELIMINARY ENGINEERING
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | CONSTRUCT NASTY BRANCH GREENWAY. | 0.71 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019A | Division 13 | BGANY, L(M) |  |  |  |  | 2025 | 4267000 |  |  | 4267000
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | FRENCH BROAD RIVER WEST GREENWAY, FRENCH BROAD RIVER PARK TO HAYWOOD ROAD. | 0.9 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019B | Division 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | WILMA DYKEMAN RIVERWAY - RADTIP AND FIVE POINTS ROUNDABOUT. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019C | Division 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | LIVINGSTON STREET COMPLETE STREETS IMPROVEMENTS. | 0.64 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019D | Division 13 | L(M) |  |  |  |  | 2026 | 1500000 |  |  | 1500000
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | NCDOT | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER. | 0.11 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5019E | Division 13 | BGANY, L(M) |  |  |  |  | 2028 | 5300000 |  |  | 5300000
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | NCDOT | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | 1.62 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5832 | Division 13 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 69700000 |  |  | 145000000
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | NCDOT | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | 1.91 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5834 | Division 13 | BGANY, T | 2019 | 12333000 |  |  | 2026 | 34600000 |  |  | 46933000 | RIGHT-OF-WAY IN PROGRESS.
BUNCOMBE | ASHEVILLE | NCDOT | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY) . CONSTRUCTION INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5971
BUNCOMBE | ASHEVILLE | NCDOT | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT INITIAL INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5971A | Region G | [10 empty] | SUPPLEMENT WITH SPOT MOBILITY FUNDS. UNDER CONSTRUCTION
BUNCOMBE | ASHEVILLE | NCDOT | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT DRAINAGE IMPROVEMENTS. |  | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5971AA | Region G | T | 2021 | 100000 |  |  | 2022 | 550000 |  |  | 650000 | WORK TO BE PERFORMED BY STATE FORCES. UNDER CONSTRUCTION.
BUNCOMBE | ASHEVILLE | NCDOT | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-5971B | Not Funded | T | NOT FUNDED | 35590000 | NOT FUNDED | 300000 | NOT FUNDED | 6500000 | NOT FUNDED |  | 42390000
BUNCOMBE | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NCDOT | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY TO MULTI-LANES. | 3.59 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-6047 | Division 13 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 61100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 106800000 |  |  | 175800000
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | NCDOT | SR 3136 (CANE CREEK ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | Highway | STI (Prioritization) | 13 | French Broad River MPO | U-6163 | Division 13 | BGANY, HF | 2025 | 100000 | 2025 | 300000 | 2025 | 2400000 |  |  | 2800000 | HIGHWAY FUNDS ARE HIGH IMPACT/LOW COST FUNDS
BUNCOMBE | MONTREAT (TEXAS ROAD) | NCDOT | REPLACE BRIDGE 100528 OVER FLAT CREEK. | 0.25 | Highway | Transition | 13 | French Broad River MPO | B-5196 | Division 13 | [10 empty] | MUNICIPAL BRIDGE - COMPLETE
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | ART BUSES AND OTHER ROUTINE CAPITAL ITEMS |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TA-6626 | Public Transit | 5339, L | [6 empty] | 2020 | 1439000 | 1439000
BUNCOMBE | BUNCOMBE MOUNTAIN MOBILITY - | BUNCOMBE MOUNTAIN MOBILITY - | REPLACEMENT VANS |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TA-6701 | Public Transit | 5307, L | [6 empty] | 2020 | 544000 | 544000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT LO-NO TRANSIT VEHICLE PURCHASE |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TA-6703 | Public Transit | 5339, L | [6 empty] | 2020 | 3365000 | 3365000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | PLANNING ASSISTANCE |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TP-5113 | Public Transit | 5303, L, S | [6 empty] | 2020 | 180000 | 180000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | ASHEVILLE REDEFINES TRANSIT | ASHEVILLE REDEFINES TRANSIT | 5310 TRADITIONAL PROJECTS |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TQ-6186 | Public Transit | 5310, L | [6 empty] | 2020 | 693000 | 693000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT. 5310 ADMINISTRATIVE OVERSIGHT. |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TQ-7010 | Public Transit | 5310 | [6 empty] | 2021 | 67000 | 67000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 13 | French Broad River MPO | TS-5102 | Public Transit | 5307, L | [6 empty] | 2021 | 36000 | 36000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | TRANSIT OPERATIONS |  | Public Transportation (Transit) | Miscellaneous/Other | 13 | French Broad River MPO | TO-4075 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 1965000 | 1965000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | BUNCOMBE COUNTY TRANSIT OPERATING ASSISTANCE. |  | Public Transportation (Transit) | Miscellaneous/Other | 13 | French Broad River MPO | TO-6154 | Public Transit | 5307, L | [6 empty] | 2020 | 2251000 | 2251000
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 13 |  | TK-6148 | Public Transit | 5309, 5311, L, S | [6 empty] | 2020 | 1816000 | 1816000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | JARC OPERATIONS |  | Public Transportation (Transit) | Operations and Maintenance | 13 | French Broad River MPO | TM-5138 | Public Transit | 3037, L | [6 empty] | 2021 | 734000 | 734000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | 5310 OTHER PROJECTS |  | Public Transportation (Transit) | Operations and Maintenance | 13 | French Broad River MPO | TQ-6187 | Public Transit | 5310, L | [6 empty] | 2020 | 688000 | 688000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | PLANNING FOR MOUNTAIN MOBILITY |  | Public Transportation (Transit) | Planning | 13 | French Broad River MPO | TP-5153 | Public Transit | 5307, L | [6 empty] | 2020 | 604000 | 604000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | BUSES AND BUS FACILITIES - BUS STOP IMPROVEMENT PROGRAM |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 13 | French Broad River MPO | TG-0011 | Public Transit | 5339, L | [6 empty] | 2021 | 1250000 | 1250000
BUNCOMBE | CITY OF ASHEVILLE | CITY OF ASHEVILLE | TRANSIT PREVENTATIVE MAINTENANCE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 13 | French Broad River MPO | TG-6183B | Public Transit | 5307, L | [6 empty] | 2024 | 7135000 | 7135000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY BUNCOMBE - BUNCOMBE COUNTY TRANSIT ROUTINE CAPITAL COST OF CONTRACTING. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 13 | French Broad River MPO | TG-6786 | Public Transit | 5307, L | [6 empty] | 2021 | 1927000 | 1927000
BUNCOMBE | SR 1319 (JOHNSTON BOULEVARD) | NCDOT | BLU CROSSING 720399N IN ASHEVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2013A | Division 13 | RR |  |  |  |  | 2025 | 294000 |  |  | 294000
BUNCOMBE | NC 9 (BROADWAY STREET) | NCDOT | NSR CROSSING 726262P IN BLACK MOUNTAIN. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2013B | Division 13 | RR |  |  |  |  | 2025 | 492000 |  |  | 492000
BUNCOMBE | BEAR CREEK ROAD | NCDOT | BLU CROSSING 720397A IN ASHEVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2413A | Division 13 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
BUNCOMBE | SR 3541 (BUCK SHOALS ROAD) | NCDOT | BLU CROSSING 720637E IN ASHEVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2413B | Division 13 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
BUNCOMBE | SR 1128 (LINDSEY ROAD) | NCDOT | BLU CROSSING 720381D IN CANDLER. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 13 | French Broad River MPO | RX-2413C | Division 13 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
BUNCOMBE, ALLEGHANY, JACKSON, WATAUGA, ASHE, SWAIN, HAYWOOD, AVERY, McDOWELL, TRANSYLVANIA, YANCEY, MITCHELL, HENDERSON, WILKES, BURKE, CALDWELL | BLUE RIDGE PARKWAY ASSOCIATION | BLUE RIDGE PARKWAY ASSOCIATION | UPDATE THE BLUE RIDGE PARKWAY ASSOCIATION TRAVEL PLANNER AND MAP BROCHURE. REDESIGN BLUE RIDGE PARKWAY WEBSITE AND MOBILE APPLICATION. IMPLEMENT MARKETING PLAN FOR BLUE RIDGE PARKWAY ASSOCIATION. |  | Highway | Other | 11, 13, 14 | High Country RPO, French Broad River MPO, Southwestern RPO, Land-of-Sky RPO, Foothills RPO, Greater Hickory MPO | HO-0012 | Exempt | DP, L | [6 empty] | 2024 | 575000 | 575000 | NATIONAL SCENIC BYWAYS GRANT AWARD: $460,000. DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING. LOCAL MATCH PROVIDED BY BLUE RIDGE PARKWAYS ASSOCIATION.
BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | BO-2413 | Division 13 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | BO-2613 | Division 13 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | R-5793 | Division 13 | HF, TA |  |  |  |  | 2020 | 6404000 |  |  | 6404000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS. HSIP FUNDS TO BE USED ON R-5793KB.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2013 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 13. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2028
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2028DIV | Division 13 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2028REG | Region G | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2028SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2413 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | HS-2613 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5213 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5713 | [11 empty] | COMPLETE
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5713DIV | Division 13 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5713REG | Region G | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5713SW | Statewide Mobility | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | Highway | Safety | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | W-5813
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 13. |  | Rail | Rail-Highway Grade Crossing Closure | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | RC-2013 | Division 13 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | RX-2013 | Division 13 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | RX-2413 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | RX-2613 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
BUNCOMBE, HAYWOOD | CITY OF ASHEVILLE | CITY OF ASHEVILLE | CITY OF ASHEVILLE ADMINISTRATIVE OVERSIGHT OF JARC PROJECTS IN THE ASHEVILLE UAZ |  | Public Transportation (Transit) | Locally Selected | 13, 14 | French Broad River MPO | TM-5163 | Public Transit | L | [6 empty] | 2020 | 85000 | 85000
BUNCOMBE, HENDERSON | I-26 | NCDOT | NC 280 (EXIT 40) TO I-40 AT ASHEVILLE. ADD ADDITIONAL LANES. | 9.32 | Highway | STI (Prioritization) | 13, 14 | French Broad River MPO | I-4700 | Statewide Mobility | NHP |  |  |  |  | 2019 | 62468000 |  |  | 62468000 | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033
BUNCOMBE, HENDERSON, HAYWOOD | VARIOUS | NCDOT | STBG-DA IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. |  | Highway | Locally Selected | 13, 14 | French Broad River MPO | U-5100 | Division 13, 14 | BGANY, BGDA, L |  |  |  |  | 2024 | 52754000 |  |  | 52754000
BUNCOMBE, HENDERSON, HAYWOOD, MADISON | VARIOUS | NCDOT | FRENCH BROAD RIVER MPO TRANSPORTATION ALTERNATIVES (TA) PROGRAM. |  | Bike & Ped | Locally Selected | 13, 14 | French Broad River MPO | U-5535 | Division 13, 14 | L, TADA |  |  |  |  | 2024 | 820000 |  |  | 820000
BUNCOMBE, HENDERSON, HAYWOOD, MADISON | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. |  | Highway | Locally Selected | 13, 14 | French Broad River MPO | HL-0090 | Exempt | CRPDA, L |  |  |  |  | 2024 | 749000 |  |  | 749000
BUNCOMBE, HENDERSON, HAYWOOD, MADISON | VARIOUS | NCDOT | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | Highway | Locally Selected | 13, 14 | French Broad River MPO | U-5616 | Division 13, 14 | BGDA, L | [6 empty] | 2024 | 4214000 | 4214000
BUNCOMBE, MADISON | I-26 (US 19/US 23) | NCDOT | SR 1781 (BROADWAY STREET) IN ASHEVILLE TO TENNESSEE STATE LINE AT SAMS GAP. MULTI-LANE FREEWAY, PART ON NEW LOCATION. | 28.3 | Highway | Appalachian Development Highway System | 13 | French Broad River MPO, Land-of-Sky RPO | A-0010 | [11 empty] | COORDINATE WITH B-4442, B-4443, B-4444.
BUNCOMBE, MADISON | I-26 (US 19/US 23) | NCDOT | SOUTH OF SR 2148 IN BUNCOMBE COUNTY TO NORTH OF NC 213 | 2.975 | Highway | Appalachian Development Highway System | 13 | Land-of-Sky RPO, French Broad River MPO | A-0010BA | [11 empty] | COMPLETE
BUNCOMBE, McDOWELL, YANCEY, MADISON, BURKE, RUTHERFORD, MITCHELL | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ON VARIOUS PRIMARY AND SECONDARY TWO LANE ROADWAYS AND FOUR LANE ROADWAYS. |  | Highway | Safety | 13 | French Broad River MPO, Foothills RPO, High Country RPO, Land-of-Sky RPO, Greater Hickory MPO | HS-2013Q | Region G | HSIP |  |  |  |  | 2025 | 3337000 |  |  | 3337000
BURKE | MAIN AVENUE EAST | NCDOT | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | BL-0001 | Division 13 | BGANY, BGDA, L | 2025 | 100000 |  |  | 2026 | 340000 | 2024 | 80000 | 520000 | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
BURKE | LOVELADY ROAD | WPCOG | LAUREL STREET TO LAKE RHODHISS DRIVE IN VALDESE. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | BL-0140 | Division 13
BURKE | LOVELADY ROAD | WPCOG | LAUREL STREET TO CRESCENT STREET IN VALDESE. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | BL-0140A | Division 13 | BGDA, L(M) |  |  |  |  | 2027 | 1281000 | 2025 | 150000 | 1431000
BURKE | LOVELADY ROAD | WPCOG | CRESCENT STREET TO LAKE RHODHISS DRIVE IN VALDESE. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | BL-0140B | Division 13
BURKE | NC 126 | NCDOT | BENFIELD'S LANDING BURKE ROAD TO EASTSIDE BURKE AVENUE IN NEBO. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | BL-0141 | Division 13 | BGDA, L(M) | 2026 | 200000 |  |  | 2027 | 1250000 | 2025 | 100000 | 1550000
BURKE | MORGANTON | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | EB-5807 | Division 13 | BGANY, BGDA, L |  |  |  |  | 2021 | 1619000 |  |  | 1619000 | RIGHT-OF-WAY IN PROGRESS
BURKE | FONTA FLORA TRAIL | BURKE COUNTY | FONTA FLORA STATE TRAIL, INTERSECTION OF LAUREL RIDGE COURT AND NORTH POWERHOUSE ROAD TO THE PROPOSED HARRIS WHISNANT TRAILHEAD AT THE INTERSECTION OF HARRY WHISNANT ROAD AND COBB ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN FACILITY. |  | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | EB-5827 | Division 13 | BGANY, L | 2023 | 626000 | [6 empty] | 626000 | $410K IN STBG-DA FUNDS SWITCHED WITH $410K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
BURKE | HICKORY | HICKORY | RIVERWALK. CONSTRUCT MULTI-USE PATH FROM OLD LENOIR ROAD AT CITY OWNED PROPERTY TO END OF PROPOSED ROSALES BRIDGE. | 0.59 | Bike & Ped | Locally Selected | 13 | Greater Hickory MPO | EB-5939 | Division 13 | BGDA, L |  |  |  |  | 2023 | 6500000 |  |  | 6500000 | UNDER CONSTRUCTION.
BURKE | COLLEGE STREET MULTIMODAL CONNECTOR | MORGANTON | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 1.33 | Bike & Ped | STI (Prioritization) | 13 | Greater Hickory MPO | EB-5978 | Division 13 | L, TAANY | 2026 | 100000 |  |  | 2026 | 2900000 |  |  | 3000000
BURKE | NEW ROUTE | NCDOT | CONSTRUCT ACCESS ROAD INTO BURKE COUNTY INDUSTRIAL PARK. | 0.36 | Highway | Appalachian Development Highway System | 13 | Greater Hickory MPO | HA-0001 | Exempt | ADHSL |  |  |  |  | 2024 | 1700000 | 2021 | 200000 | 1900000 | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000
BURKE | SR 1687 (GOAT FARM ROAD) | NCDOT | IMPROVE EXISTING SR 1687 (GOAT FARM ROAD) ACCESS ROAD INTO THE PROPOSED INDUSTRIAL PARK. | 0.88 | Highway | Appalachian Development Highway System | 13 | Greater Hickory MPO | R-5967 | Exempt | ADHSL, L |  |  |  |  | 2023 | 2152000 |  |  | 2152000 | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY. UNDER CONSTRUCTION.
BURKE | US 64/70 | NCDOT | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | B-5869 | Region G | BFP, BGDA | 2021 | 3200000 | 2021 | 270000 | 2023 | 25861000 |  |  | 29331000 | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION.
BURKE | SR 1430 (HARLAND ROAD) | NCDOT | REPLACE BRIDGE 110145 OVER BRISTOL CREEK. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | B-6011 | Division 13 | BGOFF | 2022 | 65000 |  |  | 2022 | 725000 |  |  | 790000 | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION.
BURKE | SR 1913 (SUGAR LOAF ROAD) | NCDOT | REPLACE BRIDGE 110237 OVER ROCK CREEK. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | B-6015 | Division 13 | BGOFF | 2021 | 100000 |  |  | 2021 | 1369000 |  |  | 1469000 | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION.
BURKE | I-40 | NCDOT | REPLACE BRIDGES 110114 AND 110120 OVER SILVER CREEK. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | BR-0130 | Statewide Mobility | BFP |  |  |  |  | 2030 | 11800000 |  |  | 11800000
BURKE | SR 1001 (CONNELLY SPRINGS ROAD) | NCDOT | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | 0.25 | Highway | Bridges | 13 | Greater Hickory MPO | R-3430B | Highway Fund | HFB | 2022 | 880000 | 2022 | 370000 | 2026 | 22902000 |  |  | 24152000 | RIGHT-OF-WAY IN PROGRESS.
BURKE | I-40 | NCDOT | MILE MARKER 93 TO MILE MARKER 119. REHABILITATE PAVEMENT AND BRIDGES. | 23.92 | Highway | Interstate Maintenance | 13 | Greater Hickory MPO | I-5891
BURKE | I-40 | NCDOT | MILE MARKER 93 TO MILE MARKER 119. REHABILITATE PAVEMENT. | 25.73 | Highway | Interstate Maintenance | 13 | Greater Hickory MPO | I-5891A | Statewide Mobility | [10 empty] | COMPLETE
BURKE | I-40 | NCDOT | MILE MARKER 93 TO MILE MARKER 119. REHABILITATE BRIDGES. | 26.03 | Highway | Interstate Maintenance | 13 | Greater Hickory MPO | I-5891B | Statewide Mobility | NHPIM |  |  |  |  | 2029 | 4000000 |  |  | 4000000
BURKE | US 321 | NCDOT | BRIDGES #366 AND #367 AT THE CATAWBA COUNTY LINE. INSTALL GUARDRAIL. | 0.19 | Highway | Safety | 13 | Greater Hickory MPO | HS-2013A | Statewide Mobility | HSIP |  |  |  |  | 2021 | 92000 |  |  | 92000 | COMPLETE
BURKE | NC 181 | NCDOT | US 64 TO SR 1405 (BROWN MOUNTAIN BEACH ROAD). UPGRADE GUARDRAIL. | 11.35 | Highway | Safety | 13 | Greater Hickory MPO | HS-2013C | Region G | HSIP |  |  |  |  | 2021 | 195000 |  |  | 195000 | COMPLETE
BURKE | US 64/NC 18 | NCDOT | NC 181 TO CALDWELL COUNTY LINE. UPGRADE GUARDRAIL. | 7.49 | Highway | Safety | 13 | Greater Hickory MPO | HS-2013E | Region G | HSIP |  |  |  |  | 2021 | 385000 |  |  | 385000 | COMPLETE
BURKE | US 70 | NCDOT | INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 13 | Greater Hickory MPO | HS-2413E | Region G | HSIP |  |  |  |  | 2026 | 270000 |  |  | 270000
BURKE | VARIOUS | NCDOT | PRIMARY AND SECONDARY ROUTES IN DIVISION 13. INSTALL HORIZONTAL ALIGNMENT WARNING SIGNS. |  | Highway | Safety | 13 | Greater Hickory MPO | HS-2413H | Region G | HSIP |  |  |  |  | 2026 | 438000 |  |  | 438000
BURKE | I-40 | NCDOT | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 13 | Greater Hickory MPO | I-5990 | Division 13 | NHP | 2025 | 2500000 | 2025 | 1100000 | 2026 | 35000000 |  |  | 38600000
BURKE | SR 1001 (MALCOLM BOULEVARD) | NCDOT | US 70 TO CATAWBA RIVER. |  | Highway | STI (Prioritization) | 13 | Greater Hickory MPO | R-3430A | Not Funded | T | NOT FUNDED | 10000000 | NOT FUNDED | 1600000 | NOT FUNDED | 20000000 | NOT FUNDED |  | 31600000
BURKE | NC 181 | NCDOT | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | 0.92 | Highway | STI (Prioritization) | 13 | Greater Hickory MPO | U-5836 | Region G | T | 2027 | 3000000 |  |  | 2030 | 16240000 |  |  | 19240000 | NC BUILD BONDS: $3.3M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
BURKE | HOGAN STREET | NCDOT | NSR CROSSING 729506G IN MORGANTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 13 | Greater Hickory MPO | RX-2013C | Division 13 | RR |  |  |  |  | 2026 | 451000 |  |  | 451000
BURKE, CALDWELL | US 321 | NCDOT | INTERIM STRUCTURE IMPROVEMENTS ON US 321 SOUTHBOUND BRIDGE OVER LAKE HICKORY. | 0.5 | Highway | Bridges | 11, 13 | Greater Hickory MPO | U-4700AA | Statewide Mobility | NHP |  |  |  |  | 2022 | 2705000 |  |  | 2705000 | UNDER CONSTRUCTION.
BURKE, MADISON, RUTHERFORD, McDOWELL | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ON VARIOUS PRIMARY AND SECONDARY TWO LANE ROADWAYS. |  | Highway | Safety | 13 | Foothills RPO, Greater Hickory MPO, Land-of-Sky RPO, French Broad River MPO | HS-2013R | Region G | HSIP |  |  |  |  | 2024 | 2966000 |  |  | 2966000
BURKE, MITCHELL, RUTHERFORD | US 321, US 70, US 19E, US 221A | NCDOT | UPGRADE GUARDRAIL. |  | Highway | Safety | 13 | Greater Hickory MPO, Foothills RPO, High Country RPO | HS-2013F | Statewide Mobility | HSIP |  |  |  |  | 2021 | 348000 |  |  | 348000 | COMPLETE
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) |  | Aviation | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | AV-5731 | Region E | O, T |  |  |  |  | 2025 | 7917000 |  |  | 7917000
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONCORD REGIONAL AIRPORT (JQF) | REHABILITATE APRON AND TAXIWAY PAVEMENT. |  | Aviation | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | AV-5890 | Region E | T |  |  |  |  | 2020 | 300000 |  |  | 300000 | COMPLETE.
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. |  | Aviation | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | AV-5892 | Region E | O, T |  |  |  |  | 2024 | 2170000 |  |  | 2170000 | OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT
CABARRUS | NORTH WASHINGTON STREET | MOUNT PLEASANT | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 0.17 | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | BL-0043 | Exempt | CMAQ, L |  |  |  |  | 2024 | 524000 | 2022 | 115000 | 639000
CABARRUS | CLARKE CREEK GREENWAY | CONCORD | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | 3.6 | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | BL-0060 | Exempt | CMAQ, L |  |  |  |  | 2025 | 4587000 | 2023 | 13000 | 4600000
CABARRUS | SR 1138 (HICKORY RIDGE ROAD) | HARRISBURG | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | BL-0086 | Division 10 | L(M), TADA | 2026 | 172000 | 2026 | 56000 | 2027 | 1563000 | 2024 | 287000 | 2078000
CABARRUS | VARIOUS CONCORD | CONCORD | ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. GLENN STREET NORTHWEST FROM ELM AVENUE NORTHWEST TO ACADEMY AVENUE NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. CONSTRUCT SIDEWALKS. |  | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | BL-0087 | Division 10 | L(M), TADA |  |  |  |  | 2026 | 1615000 | 2024 | 10000 | 1625000
CABARRUS | CONCORD | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. |  | Bike & Ped | Locally Selected | 10 | Cabarrus-Rowan MPO | EB-5903 | Division 10 | CMAQ, L, TADA |  |  |  |  | 2020 | 866000 |  |  | 866000 | COMPLETE.
CABARRUS | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | NCDOT | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 1.71 | Bike & Ped | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | EB-5732 | Division 10 | L, TAANY | 2029 | 2747000 |  |  | 2031 | 10500000 |  |  | 13247000
CABARRUS | KANNAPOLIS | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2.02 | Bike & Ped | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | EB-5844 | Division 10 | CMAQ, L, TAANY | 2024 | 400000 |  |  | 2025 | 5500000 |  |  | 5900000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | US 29 | NCDOT | REPLACE BRIDGE 120014 AND 120019 OVER ROCKY RIVER AND ACCESS ROAD. | 0.322 | Highway | Bridges | 10 | Cabarrus-Rowan MPO | B-5123 | Region E | [10 empty] | COMPLETE
CABARRUS | SR 1132 (MIAMI CHURCH ROAD) | NCDOT | REPLACE BRIDGE 120137 OVER DUTCH BUFFALO CREEK. | 0.25 | Highway | Bridges | 10 | Cabarrus-Rowan MPO | B-5375 | Division 10 | BGOFF |  |  |  |  | 2022 | 1573000 |  |  | 1573000 | UNDER CONSTRUCTION.
CABARRUS | US 29 US 601 | NCDOT | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | 0.25 | Highway | Bridges | 10 | Cabarrus-Rowan MPO | B-5808 | Region E | BFP, NHPB | 2021 | 255000 | 2021 | 1156000 | 2023 | 10100000 |  |  | 11511000 | UNDER CONSTRUCTION.
CABARRUS | NC 49 | NCDOT | PRINCE CIRCLE TO WEST OF GENERAL SERVICES DRIVE SW. CONVERT EXISTING FULL ACCESS CROSSOVER TO REDUCED CONFLICT INTERSECTION WITH LEFTOVERS AND SIGNALIZED U-TURN LEFTOVERS. |  | Highway | Economic Development | 10 | Cabarrus-Rowan MPO | HE-0015 | Division 10 | O, T |  |  |  |  | 2023 | 4091000 |  |  | 4091000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841.
CABARRUS | VARIOUS | KANNAPOLIS | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73. CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD). CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP |  | Highway | Economic Development | 10 | Cabarrus-Rowan MPO | U-6098 | Division 10 | T |  |  |  |  | 2019 | 1450000 |  |  | 1450000 | ECONOMIC DEVELOPMENT PROJECT FOR AMAZON - UNDER CONSTRUCTION.
CABARRUS | SR 1394 (POPLAR TENT ROAD) | CONCORD | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0001 | Division 10 | BGANY, BGDA, L | 2025 | 5520000 |  |  | 2026 | 7850000 | 2022 | 1710000 | 15080000 | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022.
CABARRUS | NC 49 | HARRISBURG | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0062 | Exempt | BGANY, BGDA, L | 2025 | 955000 | 2025 | 382000 | 2026 | 6445000 | 2023 | 1396000 | 9178000 | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24.
CABARRUS | SR 1173 (CALDWELL ROAD) | HARRISBURG | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0063 | Division 10 | L, T(DA) | 2025 | 1108000 | 2025 | 10000 | 2026 | 4156000 | 2023 | 833000 | 6107000 | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24.
CABARRUS | CONCORD |  | UPGRADE SOFTWARE FOR CONCORD CITYWIDE SIGNAL SYSTEM. |  | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0123 | Exempt | CRPDA, L |  |  |  |  | 2025 | 500000 | 2024 | 1000000 | 1500000
CABARRUS | I-85 | NCDOT | GEORGES LILES PARKWAY INTERCHANGE. INSTALL LIGHTING AT INTERCHANGE. | 0.1 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | HL-0157 | Statewide Mobility | BGDA, HF(M), L(M) |  |  |  |  | 2025 | 1000000 |  |  | 1000000
CABARRUS | SR 1445 (DERITA ROAD) | NCDOT | SR 2894 (CONCORD MILLS BOULEVARD) TO AVIATION BOULEVARD. WIDEN TO 4-LANES DIVIDED. | 1 | Highway | Locally Selected | 10 | Cabarrus-Rowan MPO | U-4910A | Division 10 | [10 empty] | UNDER CONSTRUCTION
CABARRUS | ROBERTA ROAD | CONCORD | MAIN STREET INTERSECTION. CONSTRUCT ROUNDABOUT. |  | Highway | NCDOT Selected (Other Selection Process) | 10 | Cabarrus-Rowan MPO | HN-0036 | Division 10 | CMAQ, L | 2027 | 250000 |  |  | 2028 | 1741000 | 2025 | 715000 | 2706000
CABARRUS | SR 1643 (BETHPAGE ROAD) | KANNAPOLIS | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS. |  | Highway | Other | 10 | Cabarrus-Rowan MPO | C-5603F | Exempt | CMAQ, L(M) | 2025 | 117000 |  |  | 2025 | 2365000 |  |  | 2482000
CABARRUS | US 601 | CONCORD | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION. |  | Highway | Other | 10 | Cabarrus-Rowan MPO | C-5603I | Exempt | CMAQ, L(M) | 2025 | 250000 |  |  | 2025 | 4881000 |  |  | 5131000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | I-85 | NCDOT | ITS FOR I-3802 A | 7.35 | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | I-3802AA | Pre-STI (Transition) | CMAQ, CRPDA, T(M) |  |  |  |  | 2023 | 2523000 |  |  | 2523000 | COMPLETE
CABARRUS | I-85 | NCDOT | SOUTH OF SR 2894 (CONCORD MILLS - BRUTON SMITH BOULEVARD) TO NC 73 IN CABARRUS COUNTY. WIDEN TO 8-LANES. |  | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | I-3803B | Pre-STI (Transition) | NHP |  |  |  |  | 2010 | 22592000 |  |  | 22592000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
CABARRUS | GEORGE LILES PARKWAY | NCDOT | SR 1304 (ROBERTA ROAD) TO SR 1431 (WEDDINGTON ROAD). | 2.98 | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | R-2246B | [11 empty] | COMPLETE
CABARRUS | GEORGE LILES PARKWAY | NCDOT | SR 1431 (WEDDINGTON ROAD) TO SOUTH OF I-85. | 1.236 | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | R-2246C | [11 empty] | COMPLETE
CABARRUS | SR 1445 (DERITA ROAD) | NCDOT | AVIATION BOULEVARD TO SR 1394 (POPLAR TENT ROAD). WIDEN TO 4-LANES DIVIDED. | 1.54 | Highway | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO | U-4910B | Pre-STI (Transition) | BGDA, T(M) |  |  |  |  | 2024 | 1135000 |  |  | 1135000 | UNDER CONSTRUCTION
CABARRUS | NC 24/27 | NCDOT | SR 1120 (BETHEL SCHOOL ROAD) INTERSECTION. INSTALL A REDUCED CONFLICT INTERSECTION (RCI) WITH SIGNALIZED BULBOUTS. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010D | Region E | HSIP | 2023 | 301000 |  |  | 2024 | 769000 |  |  | 1070000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | NC 24/27 | NCDOT | NC 24/27 AND SR 1100 (PINE BLUFF ROAD/ REED MINE ROAD) NEAR LOCUST. INSTALL A REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010F | Region E | HSIP | 2023 | 5000 |  |  | 2024 | 1160000 |  |  | 1165000
CABARRUS | NC 49 | NCDOT | SR 1155 (ZION CHURCH ROAD) INTERSECTION NEAR CONCORD. INSTALL REDUCED CONFLICT INTERSECTION WITH SIGNALIZED BULBOUTS. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010H | Statewide Mobility | HSIP | 2024 | 210000 | 2024 | 70000 | 2026 | 1949000 |  |  | 2229000
CABARRUS | NC 49; US 601; NC 3 | NCDOT | MILE MARKER 13.8 TO MILE MARKER 15.8; MILE MARKER 5.4 TO MILE MARKER 12.3; MILE MARKER 13.8 TO MILE MARKER 20.3. INSTALL RUMBLE STRIPS AND LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010P | Region E | HSIP |  |  |  |  | 2024 | 885000 |  |  | 885000
CABARRUS | NC 49 | NCDOT | SR 2635 (OLD AIRPORT ROAD). INSTALL DIRECTIONAL CROSSOVER WITH U-TURN BULBOUT. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010Q | Statewide Mobility | HSIP | 2025 | 10000 | 2026 | 10000 | 2027 | 750000 |  |  | 770000
CABARRUS | SR 1168 (ROBINSON CHURCH ROAD) | NCDOT | SR 1169 (PEACH ORCHARD ROAD) NEAR HARRISBURG. WIDEN SHOULDERS AND IMPROVE SUPERELEVATION. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2010R | Division 10 | HSIP | 2025 | 50000 | 2027 | 25000 | 2027 | 715000 |  |  | 790000
CABARRUS | SR 1790 (WINECOFF SCHOOL ROAD) | NCDOT | NEAR WINCOFF ELEMENTARY SCHOOL IN CONCORD. INSTALL PEDESTRIAN ACCOMODATIONS. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2410A | Division 10 | HSIP | 2026 | 10000 |  |  | 2028 | 97000 |  |  | 107000
CABARRUS | US 29 (CONCORD PARKWAY) | NCDOT | SR 2894 (BRUTON SMITH BOULEVARD) INTERSECTION IN CONCORD. INSTALL PEDESTRIAN SIGNAL UPGRADES. |  | Highway | Safety | 10 | Cabarrus-Rowan MPO | HS-2410D | Region E | HSIP |  |  |  |  | 2025 | 29000 |  |  | 29000
CABARRUS | VARIOUS | NCDOT | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN REGIONAL CATEGORY. |  | Highway | Safety | 10 | Cabarrus-Rowan MPO | W-5210REG | Region E
CABARRUS | SR 1002 (OLD SALISBURY CONCORD ROAD) | NCDOT | SR 2400 (IRISH POTATO ROAD) NEAR KANNAPOLIS. CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | Highway | Safety | 10 | Cabarrus-Rowan MPO | W-5710AO | Division 10 | HSIP |  |  |  |  | 2024 | 1296000 |  |  | 1296000
CABARRUS | GEORGE LILES PARKWAY | NCDOT | NC 49 TO SOUTH OF I-85. WIDEN TO FOUR LANES DIVIDED, SOME NEW LOCATION. | 6.5 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | R-2246
CABARRUS | GEORGE LILES PARKWAY | NCDOT | NC 49 TO SR 1304 (ROBERTA ROAD). | 1.59 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | R-2246A | Division 10 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 42100000 |  |  | 55000000
CABARRUS | NC 73 (DAVIDSON HIGHWAY) | NCDOT | EAST OF SR 1394 (POPLAR TENT ROAD) TO I-85. | 6.07 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | R-5706BA | Not Funded | NHP | NOT FUNDED | 26000000 | NOT FUNDED | 6500000 | NOT FUNDED | 139000000 | NOT FUNDED |  | 171500000
CABARRUS | NC 73 (DAVIDSON HIGHWAY) | NCDOT | I-85 TO US 29. | 2.79 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | R-5706BB | Not Funded | NHP | NOT FUNDED | 16500000 | NOT FUNDED | 8000000 | NOT FUNDED | 50700000 | NOT FUNDED |  | 75200000
CABARRUS | SR 1394 (POPLAR TENT ROAD) | NCDOT | SR 1445 (DERITA ROAD) TO US 29/601 BYPASS. WIDEN TO MULTI-LANES. | 6.1 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-3415
CABARRUS | SR 1394 (POPLAR TENT ROAD) | NCDOT | EAST OF I-85 TO GEORGE LILES PARKWAY. WIDEN TO MULTI-LANES. | 2.96 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-3415A | Division 10 | BGANY | 2029 | 12900000 | 2029 | 900000 | 2032 | 49400000 |  |  | 63200000
CABARRUS | SR 1394 (POPLAR TENT ROAD) | NCDOT | GEORGE LILES PARKWAY TO US 29/601. WIDEN TO MULTI-LANES. |  | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-3415B | Not Funded | T | NOT FUNDED | 9900000 | NOT FUNDED | 13200000 | NOT FUNDED | 32900000 | NOT FUNDED |  | 56000000
CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) | NCDOT | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-5761 | Region E | T |  |  |  |  | 2027 | 8100000 |  |  | 8100000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | SR 2894 (CONCORD MILLS BOULEVARD) | NCDOT | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | 1 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-5806 | Division 10 | T |  |  |  |  | 2021 | 10380000 | 2021 | 1755000 | 12135000 | COMPLETE. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.363 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
CABARRUS | US 29 | NCDOT | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. |  | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | U-5956 | Region E | T | 2022 | 3400000 | 2025 | 2050000 | 2026 | 27155000 |  |  | 32605000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $10M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE);
CABARRUS | US 29/US 601 | NCDOT | REPLACE BRIDGE 120066 AND BRIDGE 120069 OVER SOUTHERN RAILROAD. | 0.25 | Highway | Transition | 10 | Cabarrus-Rowan MPO | B-5136 | Region E | T |  |  |  |  | 2021 | 2790000 |  |  | 2790000 | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
CABARRUS | I-85 | NCDOT | ITS FOR I-3803B |  | Highway | Transition | 10 | Cabarrus-Rowan MPO | I-3803BA | Pre-STI (Transition)
CABARRUS | NC 3 | NCDOT | WEST SIDE BYPASS TO SR 1691 (LOOP ROAD) IN KANNAPOLIS. WIDEN TO A FOUR-LANE DIVIDED FACILITY. | 2.58 | Highway | Transition | 10 | Cabarrus-Rowan MPO | U-3440 | Pre-STI (Transition) | T | 2025 | 561000 |  |  | 2025 | 2500000 |  |  | 3061000 | UNDER CONSTRUCTION
CABARRUS | SR 1445 (DERITA ROAD) | NCDOT | SR 2894 (CONCORD MILLS BOULEVARD) TO SR 1394 (POPLAR TENT ROAD) IN CONCORD. WIDEN TO 4-LANES DIVIDED. | 2.6 | Highway | Transition | 10 | Cabarrus-Rowan MPO | U-4910 | [11 empty] | SEGMENTS A AND B LET TOGETHER
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - CAPITAL |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5128A | Public Transit | 5310, L | [6 empty] | 2020 | 2500000 | 2500000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - OPERATING |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5128B | Public Transit | 5310, L | [6 empty] | 2020 | 1350000 | 1350000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | ADMINISTRATION OF 5310 PROGRAM |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5128C | Public Transit | 5310 | [6 empty] | 2020 | 200000 | 200000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | 5339 BUS AND BUS FACILITIES - EXPANSION VEHICLES |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5130B | Public Transit | 5339, L | [6 empty] | 2020 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT/ CONCORD | RIDER TRANSIT / CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TA-5173 | Public Transit | 5307, L, S | [6 empty] | 2021 | 8500000 | 8500000
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TP-5118 | Public Transit | 5303, L, S | [6 empty] | 2020 | 304000 | 304000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Cabarrus-Rowan MPO | TS-5116 | Public Transit | 5307 | [6 empty] | 2020 | 100000 | 100000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | CONCORD | CONCORD | PURCHASE NEW 35 FOOT HYBRID ELECTRIC HEAVY DUTY LOW FLOOR BUS |  | Public Transportation (Transit) | Locally Selected | 10 | Cabarrus-Rowan MPO | TL-0021 | Division 10 | BGDACV, L |  |  |  |  | 2023 | 725000 |  |  | 725000
CABARRUS | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 10 | Cabarrus-Rowan MPO | TO-5138 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 10852000 | 10852000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | CABARRUS COUNTY | CABARRUS COUNTY | CAPITAL FOR CABARRUS COUNTY THROUGH THE CITY OF CONCORD |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Cabarrus-Rowan MPO | TG-6789 | Public Transit | 5307, L | [6 empty] | 2020 | 2256000 | 2256000
CABARRUS | KANNAPOLIS | NCDOT | CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL, SIGNALING EQUIPMENT. |  | Rail | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | P-5725 | Region E | T |  |  |  |  | 2025 | 13500000 |  |  | 13500000 | RIGHT-OF-WAY IN PROGRESS
CABARRUS | NORFOLK SOUTHERN MAINLINE | NCDOT | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. |  | Rail | STI (Prioritization) | 10 | Cabarrus-Rowan MPO | Y-4810K | Statewide Mobility | O, T |  |  |  |  | 2023 | 19170000 |  |  | 19170000 | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN
CABARRUS, MECKLENBURG | NC 73 (DAVIDSON HIGHWAY) | NCDOT | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO US 29. WIDEN TO MULTI-LANES. | 10.9 | Highway | STI (Prioritization) | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | R-5706 | [11 empty] | COORDINATE WITH R-2632AB.
CABARRUS, MECKLENBURG | PIEDMONT CORRIDOR | NCDOT | PIEDMONT CORRIDOR, RESTORE DOUBLE TRACK, HAYDOCK TO JUNKER. |  | Rail | Pre-STI (Historic) | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | P-5208 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
CABARRUS, ROWAN | VARIOUS | NCDOT | CABARRUS ROWAN MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | Bike & Ped | Locally Selected | 9, 10 | Cabarrus-Rowan MPO | U-5545 | Division 9, 10 | L, TADA |  |  |  |  | 2024 | 7754000 |  |  | 7754000
CABARRUS, ROWAN | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CABARRUS-ROWAN PLANNING ORGANIZATION. |  | Highway | Locally Selected | 9, 10 | Cabarrus-Rowan MPO | HL-0093 | Exempt | CRPDA, L |  |  |  |  | 2024 | 0
CABARRUS, ROWAN | VARIOUS | NCDOT | STBG-DA IN THE CABARRUS-ROWAN METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. |  | Highway | Locally Selected | 9, 10 | Cabarrus-Rowan MPO | U-5614 | Division 9, 10 | BGANY, BGDA, L |  |  |  |  | 2024 | 53016000 |  |  | 53016000 | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP
CABARRUS, ROWAN | VARIOUS | CONCORD | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | Highway | Other | 9, 10 | Cabarrus-Rowan MPO | C-5603 | Exempt | CMAQ, L(M) | 2020 | 309000 |  |  | 2020 | 1848000 | 2020 | 927000 | 3084000 | IN PROGRESS
CABARRUS, ROWAN | I-85 | NCDOT | NC 73 IN CABARRUS COUNTY (EXIT 55) TO US 29 / US 601 CONNECTOR (EXIT 68) IN ROWAN COUNTY. WIDEN TO EIGHT LANES. | 13.6 | Highway | STI (Prioritization) | 9, 10 | Cabarrus-Rowan MPO | I-3802 | [11 empty] | PROJECT COMPLETED. SEGMENT B INCLUDES B-5365 AND I-3610
CABARRUS, ROWAN | I-85 | NCDOT | NC 73 IN CABARRUS COUNTY (EXIT 55) TO SR 2180 (LANE STREET) IN CABARRUS COUNTY. | 7.35 | Highway | Transition | 9, 10 | Cabarrus-Rowan MPO | I-3802A | Pre-STI (Transition) | [10 empty] | COMPLETE
CABARRUS, ROWAN | CONCORD KANNAPOLIS AREA TRANSIT | CONCORD KANNAPOLIS AREA TRANSIT | TO SUPPORT THE PURCHASE OF ROUTINE CAPITAL: BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, VEHICLES ETC USING SECTION 5339 FUNDS AT A FEDERAL SHARE OF $200,000 AND LOCAL SHARE OF $50,000. |  | Public Transportation (Transit) | Capital (Non-STI) | 9, 10 |  | TA-5130A | Public Transit | 5339, L | [6 empty] | 2020 | 1000000 | 1000000
CABARRUS, ROWAN | CONCORD KANNAPOLIS AREA TRANSIT | CONCORD KANNAPOLIS AREA TRANSIT | EXPANSION BUS |  | Public Transportation (Transit) | Locally Selected | 9, 10 | Cabarrus-Rowan MPO | TL-0005 | Division 9, 10 | BGDA, L |  |  |  |  | 2022 | 725000 |  |  | 725000
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - ADA SERVICES |  | Public Transportation (Transit) | Operations and Maintenance | 9, 10 | Cabarrus-Rowan MPO | TG-5103B | Public Transit | 5307, L | [6 empty] | 2020 | 1563000 | 1563000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 9, 10 | Cabarrus-Rowan MPO | TG-5103C | Public Transit | 5307, L | [6 empty] | 2020 | 6750000 | 6750000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9, 10 | Cabarrus-Rowan MPO | TG-5103A | Public Transit | 5307, L | [6 empty] | 2020 | 2500000 | 2500000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS, STANLY | NC 73 | NCDOT | MILE MARKER 0 TO MILE MARKER 4.3, MILE MARKER 13.1 TO MILE MARKER 18.9, MILE MARKER 20.9 TO MILE MARKER 24.0 IN CABARRUS COUNTY; MILE MARKER 0 TO MILE MARKER 8.1 IN STANLY COUNTY. INSTALL RUMBLE STRIPS AND LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 10 | Cabarrus-Rowan MPO, Rocky River RPO | HS-2010O | Region E | HSIP |  |  |  |  | 2024 | 1400000 |  |  | 1400000
CALDWELL | HUDSON US 321A (MAIN STREET)/ | NCDOT | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 0.23 | Bike & Ped | Locally Selected | 11 | Greater Hickory MPO | BL-0002 | Division 11 | BGDA, L(M), TAANY | 2025 | 24000 |  |  | 2025 | 440000 | 2024 | 80000 | 544000 | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22.
CALDWELL | LENIOR GREENWAY | LENOIR | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 0.84 | Bike & Ped | Locally Selected | 11 | Greater Hickory MPO | BL-0065 | Division 11 | BGDA, L | 2025 | 281000 |  |  | 2026 | 1581000 | 2024 | 306000 | 2168000
CALDWELL | LENOIR | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 11 | Greater Hickory MPO | EB-5806 | Division 11 | BGANY, BGDA, L, TADA | 2021 | 120000 |  |  | 2024 | 3050000 |  |  | 3170000 | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION.
CALDWELL | SR 1514 | NCDOT | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0056 | Exempt | BGOFF, DP, HFB | 2025 | 270000 | 2025 | 80000 | 2026 | 1800000 | 2023 | 139000 | 2289000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | (OLD JOHNS RIVER ROAD) SR 1356 | NCDOT | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0057 | Exempt | BGOFF, DP, HFB | 2025 | 290000 | 2025 | 10000 | 2026 | 2600000 | 2023 | 139000 | 3039000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | (OLD JOHNS RIVER ROAD) SR 1356 | NCDOT | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0058 | Exempt | BGOFF, DP, HFB | 2025 | 160000 | 2025 | 60000 | 2026 | 2299000 | 2023 | 139000 | 2658000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | (OLD JOHNS RIVER ROAD) SR 1356 | NCDOT | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0059 | Exempt | BGOFF, DP, HFB | 2025 | 120000 | 2025 | 40000 | 2026 | 2200000 | 2023 | 139000 | 2499000 | DP REPRESENTS RAISE GRANT FUNDS
CALDWELL | SR 1356 | NCDOT | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0060 | Exempt | BGOFF, DP, HFB | 2025 | 269000 | 2025 | 60000 | 2026 | 2399000 | 2023 | 181000 | 2909000 | DP REPRESENTS RAISE GRANT FUNDS.
CALDWELL | SR 1574 | NCDOT | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | Highway | Bridges | 11 | Greater Hickory MPO | HB-0061 | Exempt | BGOFF, DP, HFB | 2025 | 140000 | 2025 | 40000 | 2026 | 1500000 | 2023 | 111000 | 1791000 | DP REPRESENTS RAISE GRANT FUNDS
CALDWELL | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | NCDOT | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 2.19 | Highway | Federal Lands Access Program | 11 | Greater Hickory MPO | HF-0001 | Exempt | FLAP, HF(M) |  |  |  |  | 2022 | 235000 | 2022 | 5000 | 240000 | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION.
CALDWELL | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | NCDOT | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 2.19 | Highway | Federal Lands Access Program | 11 | Greater Hickory MPO | HF-0003 | Exempt | FLAP, HF(M) |  |  |  |  | 2025 | 1575000 | 2022 | 175000 | 1750000 | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS.
CALDWELL | GRANITE FALLS | NCDOT | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 11 | Greater Hickory MPO | R-5775 | Exempt | BGDA, HF(M) |  |  |  |  | 2022 | 2735000 |  |  | 2735000 | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - HF(M) IS SPOT SAFETY (SS-4911 AL);
CALDWELL | SR 1001 (CONNELLY SPRINGS ROAD) | NCDOT | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | 7.04 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | R-3430C | Division 11 | BGANY | 2030 | 27500000 | 2030 | 4000000 | 2034 | 101600000 |  |  | 133100000
CALDWELL | US 64/NC 90/NC 18 (WILKESBORO BLVD) | NCDOT | INTERSECTION OF US 64/NC 90/NC 18 (WILKESBORO BOULEVARD) AND US 64/NC 90 (TAYLORSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | R-5745 | Division 11 | T |  |  |  |  | 2019 | 1695000 |  |  | 1695000 | COMPLETE; BUILD NC BOND FUNDING: $1.313M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE)
CALDWELL | US 321 | NCDOT | US 321A TO SR 1108 (MISSION ROAD) | 0 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700B | Not Funded | NHP | NOT FUNDED | 35000000 | NOT FUNDED | 4000000 | NOT FUNDED | 57500000 | NOT FUNDED |  | 96500000
CALDWELL | US 321 | NCDOT | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | 0 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700C | Not Funded | NHP | NOT FUNDED | 5000000 | NOT FUNDED | 2000000 | NOT FUNDED | 12000000 | NOT FUNDED |  | 19000000
CALDWELL | US 321 | NCDOT | SR 1160 (MOUNT HERMAN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700CA | Region F | NHP | 2020 | 420000 |  |  | 2025 | 7200000 |  |  | 7620000 | DESIGN BY DIVISION. UNDER CONSTRUCTION.
CALDWELL | US 321 | NCDOT | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700CB | Statewide Mobility | NHP | 2020 | 770000 | 2020 | 100000 | 2025 | 11998000 |  |  | 12868000 | RIGHT-OF-WAY IN PROGRESS.
CALDWELL | US 321 | NCDOT | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO REDUCED CONFLICT INTERSECTION - WITHIN THE LIMITS OF U-4700 C. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-4700CC | Statewide Mobility | NHP | 2020 | 450000 | 2020 | 100000 | 2025 | 8300000 |  |  | 8850000 | RIGHT-OF-WAY IN PROGRESS.
CALDWELL | US 64/ NC 18 | NCDOT | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6033 | Division 11 | T | 2019 | 400000 | 2019 | 668000 | 2023 | 4261000 |  |  | 5329000 | UNDER CONSTRUCTION.
CALDWELL | US 321 ALT | NCDOT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | 1.33 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6034 | Division 11 | BGANY | 2025 | 15000000 | 2025 | 2200000 | 2027 | 17300000 |  |  | 34500000
CALDWELL | SR 1002 (DUDLEY SHOALS ROAD) | NCDOT | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. |  | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6035 | Division 11 | T | 2019 | 200000 | 2019 | 275000 | 2024 | 2900000 |  |  | 3375000 | RIGHT-OF-WAY IN PROGRESS
CALDWELL | SR 1109 (PINEWOOD ROAD) | NCDOT | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | 0.6 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6036 | Division 11 | T | 2019 | 1500000 | 2019 | 560000 | 2024 | 13317000 |  |  | 15377000 | RIGHT-OF-WAY IN PROGRESS
CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) | NCDOT | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | 3.39 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6157 | Division 11 | BGANY | 2025 | 13000000 | 2025 | 7000000 | 2027 | 23900000 |  |  | 43900000 | RIGHT-OF-WAY IN PROGRESS.
CALDWELL | US 321 | NCDOT | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | 1 | Highway | STI (Prioritization) | 11 | Greater Hickory MPO | U-6161 | Division 11 | NHP | 2025 | 800000 | 2025 | 270000 | 2027 | 6300000 |  |  | 7370000 | COORDINATE WITH U-4700A
CALDWELL, BURKE | SR 1001 (MALCOLM BLVD/ CONNELLY SPRINGS ROAD) | NCDOT | US 70 TO SR 1933 (SOUTH-WEST BOULEVARD) IN LENOIR. MODERNIZE ROADWAY TO INCLUDE BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 10 | Highway | STI (Prioritization) | 11, 13 | Greater Hickory MPO | R-3430
CALDWELL, CATAWBA, BURKE | US 321 | NCDOT | NORTH OF US 70 IN HICKORY TO SR 1933 (SOUTHWEST BOULEVARD). WIDEN TO SIX LANES. | 13.3 | Highway | STI (Prioritization) | 11, 12, 13 | Greater Hickory MPO | U-4700 | [11 empty] | INCLUDES B-4450.
CALDWELL, CATAWBA, LINCOLN, MECKLENBURG, WATAUGA | COACH AMERICA | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE |  | Public Transportation (Transit) | Operations and Maintenance | 10, 11, 12 |  | TI-6101 | Public Transit | 5311, L, S | [6 empty] | 2020 | 2384000 | 2384000 | FUNDS AUTHORIZED IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | BO-2411 | Division 11 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 7500000 | 2024 | 650000 | 8650000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | BO-2611 | Division 11 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | R-5791 | Division 11 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2011 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2011A | Division 11 | HSIP |  |  |  |  | 2021 | 1816000 |  |  | 1816000 | UNDER CONSTRUCTION.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2011D | Division 11 | HSIP |  |  |  |  | 2021 | 855000 |  |  | 855000 | UNDER CONSTRUCTION.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 11. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2026
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2026DIV | Division 11 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2026REG | Region F | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2026SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2411 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | HS-2611 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | W-5711
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | W-5711DIV | Division 11 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | W-5711REG | Region F | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | W-5711SW | Statewide Mobility | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 11. |  | Rail | Rail-Highway Grade Crossing Closure | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | RC-2011 | Division 11 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. |  | Rail | Rail-Highway Grade Crossing Improvement | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | RX-2011 | Division 11 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. |  | Rail | Rail-Highway Grade Crossing Improvement | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | RX-2411 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. |  | Rail | Rail-Highway Grade Crossing Improvement | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | RX-2611 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CAMDEN | US 17 | NCDOT | US 17 BUSINESS / NC 343 INTERSECTION. MODIFY THE MEDIAN OPENING AND INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 1 | Albemarle RPO | HS-2401A | Region A | HSIP |  |  |  |  | 2025 | 1086000 |  |  | 1086000
CAMDEN | SR 1224 (OLD SWAMP ROAD) | NCDOT | 0.15 SOUTH OF SR 1225 (LILLY ROAD) TO 0.25 MILES NORTH OF SR 1225 (LILLY ROAD). | 0.4 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5717A | Division 1 | [10 empty] | UNDER CONSTRUCTION.
CAMDEN | SR 1224 (OLD SWAMP ROAD) | NCDOT | REPLACE BRIDGE 140013 OVER JOYCE CREEK. |  | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5717B | Division 1 | T |  |  |  |  | 2026 | 1900000 |  |  | 1900000
CAMDEN | NC 343 | NCDOT | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 6.82 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5807 | Division 1 | BGANY, T | 2025 | 2000000 | 2025 | 9600000 | 2028 | 32855000 |  |  | 44455000 | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE).
CAMDEN, CHOWAN, CURRITUCK, PASQUOTANK, PERQUIMANS | ALBEMARLE REGIONAL HEALTH SERVICE | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 1 | Albemarle RPO | TK-6104 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1656000 | 1656000 | FUNDS AUTHORIZED IN PROGRESS
CAMDEN, CURRITUCK | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NCDOT | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN EXISTING LANES, WIDEN EXISTING SHOULDERS, AND INTERSECTION IMPROVEMENTS. | 11 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5717 | Division 1 | T |  |  |  |  | 2026 | 44000000 |  |  | 44000000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE).
CARTERET | MICHAEL J. SMITH FIELD (MRH) | MICHAEL J. SMITH FIELD (MRH) | FULL PARALLEL TAXIWAY 8-26. |  | Aviation | STI (Prioritization) | 2 | Down East RPO | AV-5746 | Division 2 | [10 empty] | COMPLETE
CARTERET | NC 58 | ATLANTIC BEACH | LEE DRIVE TO CEDAR LANE IN ATLANTIC BEACH. CONSTRUCT SIDEWALK ON NORTH SIDE. | 2 | Bike & Ped | Locally Selected | 2 | Down East RPO | BN-0019 | Exempt | CRP550, L(M) | 2025 | 214000 |  |  | 2026 | 400000 | 2025 | 110000 | 724000
CARTERET | NC 24 | CAPE CARTERET | YAUPON DRIVE TO BAYSHORE DRIVE IN CAPE CARTERET. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE. | 1 | Bike & Ped | Locally Selected | 2 | Down East RPO | BN-0022 | Exempt | CRP550, L(M) |  |  |  |  | 2026 | 1000000 | 2025 | 155000 | 1155000
CARTERET | US 70 | NCDOT | REPLACE BRIDGE 150033 OVER NORTH RIVER AND REPAIRS TO EXISTING STRUCTURE TO SERVE AS DETOUR. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-4722 | Region B
CARTERET | SR 1335 (ISLAND ROAD) | NCDOT | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | 0.75 | Highway | Bridges | 2 | Down East RPO | B-4863 | Division 2 | DP, T |  |  |  |  | 2021 | 73735000 |  |  | 73735000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS.
CARTERET | SR 1182 (ATLANTIC BEACH CAUSEWAY) | NCDOT | REHABILITATE BRIDGE 150068 OVER BOGUE SOUND. | 0.75 | Highway | Bridges | 2 | Down East RPO | B-5938 | Division 2 | T |  |  |  |  | 2019 | 7995000 |  |  | 7995000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE)
CARTERET | NC 58 | NCDOT | REHABILITATE BRIDGE 150006 OVER BOGUE SOUND. | 0.75 | Highway | Bridges | 2 | Down East RPO | B-5939 | Region B | T |  |  |  |  | 2024 | 3000000 |  |  | 3000000 | UNDER CONSTRUCTION
CARTERET | NC 58 | NCDOT | APPROXIMATELY 1280 FEET EAST OF LEE DRIVE IN ATLANTIC BEACH. INSTALL RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AA | Region B | HSIP |  |  |  |  | 2024 | 32000 |  |  | 32000
CARTERET | US 70 | NCDOT | AT SR 1174 (TURNER STREET) IN BEAUFORT. ADD PEDESTRIAN SIGNAL HEADS AT EXISTING CROSSWALKS. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AB | Region B | HSIP |  |  |  |  | 2024 | 55000 |  |  | 55000
CARTERET | US 70 | NCDOT | AT SR 1300 (MERRIMON ROAD). UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AC | Region B | HSIP |  |  |  |  | 2024 | 25000 |  |  | 25000
CARTERET | US 70 | NCDOT | FROM GLADYS TEASLEY LANE TO SR 1753 (ARTHUR FARM ROAD) IN MOREHEAD CITY. CONSTRUCT REDUCED CONFLICT INTERSECTION INCLUDING MODIFICATION OF FIVE FULL-MOVEMENT MEDIAN OPENINGS. | 0.65 | Highway | Safety | 2 | Down East RPO | HS-2002AF | Region B | HSIP |  |  | 2025 | 150000 | 2025 | 940000 |  |  | 1090000
CARTERET | US 70 | NCDOT | AT NC 101 IN BEAUFORT. UPGRADE TRAFFIC SIGNAL AND INSTALL ADVANCE SIGNAL AHEAD FLASHERS. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AI | Region B | HSIP |  |  |  |  | 2024 | 55000 |  |  | 55000
CARTERET | NC 24 | NCDOT | NC 24 BETWEEN SR 1259 (TAYLOR NOTION ROAD) AND US 70. INSTALL PAVEMENT MARKINGS AND RUMBLE STRIPES ON TWO-WAY LEFT TURN LANE. | 15.07 | Highway | Safety | 2 | Down East RPO | HS-2002B | Statewide Mobility | HSIP |  |  |  |  | 2021 | 640000 |  |  | 640000 | COMPLETED.
CARTERET | NC 58 (SALTER PATH ROAD) | NCDOT | NC 58 (SALTER PATH ROAD) AT THE OCEAN CLUB ENTRANCE JUST WEST OF TRADEWINDS DRIVE. INSTALL CROSSWALK WITH RAPID FLASHING BEACONS. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002G | Region B | HSIP |  |  |  |  | 2022 | 25000 |  |  | 25000 | COMPLETED.
CARTERET | NC 58 (WEST FORT MACON ROAD) | NCDOT | NC 58 (WEST FORT MACON ROAD) AT ATLANTIC STATION SHOPPING CENTER / ATLANTIC BEACH TOWN PARK. INSTALL PEDESTRIAN HEADS FOR EXISTING SIGNAL AND WHEEL CHAIR RAMP REVISIONS. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002H | Region B | HSIP |  |  |  |  | 2022 | 12000 |  |  | 12000 | UNDER CONSTRUCTION.
CARTERET | NC 58 | NCDOT | NC 58 JUST WEST OF CEDAR LANE. INSTALL CROSSWALKS, CONCRETE MONOLITHIC PEDESTRIAN REFUGE ISLAND, SIDEWALKS, AND RECTANGULAR RAPID-FLASHING BEACONS. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002I | Region B | HSIP |  |  |  |  | 2024 | 95000 |  |  | 95000
CARTERET | SR 1310 (LENNOXVILLE ROAD) | NCDOT | AT CARTERET AVENUE IN BEAUFORT. INSTALL CROSSWALK SIGNALIZATION. |  | Highway | Safety | 2 | Down East RPO | HS-2002U | Division 2 | HSIP |  |  |  |  | 2024 | 25000 |  |  | 25000 | UNDER CONSTRUCTION.
CARTERET | NC 58 | NCDOT | LOON DRIVE / EMERALD PLANTATION ROAD; MANGROVE DRIVE; BOGUE INLET DRIVE INTERSECTIONS IN EMERALD ISLE. IMPLEMENT A LEADING PEDESTRIAN INTERVAL AT THE SIGNALIZED INTERSECTIONS. |  | Highway | Safety | 2 | Down East RPO | HS-2402E | Region B | HSIP |  |  |  |  | 2025 | 9000 |  |  | 9000
CARTERET | NC 101 | NCDOT | SR 1392 (ADAMS CREEK ROAD) INTERSECTION. IMPROVE INTERSECTION WITH CHANNELIZATION AND SUPPLEMENTAL STOP SIGN INSTALLATION. |  | Highway | Safety | 2 |  | HS-2402P | Region B | HSIP |  |  |  |  | 2025 | 49000 |  |  | 49000
CARTERET | US 70 | NCDOT | SR 1429 (OLGA ROAD) TO NC 12; NC 12 FROM US 70 TO SR 1388 (LOLA ROAD). INSTALL RUMBLE STRIPES. |  | Highway | Safety | 2 |  | HS-2402T | Region B | HSIP |  |  |  |  | 2025 | 675000 |  |  | 675000
CARTERET | SR 1176 (BRIDGES STREET EXTENSION) | NCDOT | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 3.02 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5727 | Division 2 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19901000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 115000000 |  |  | 136201000
CARTERET | NC 58 (WEST FORT MACON) | NCDOT | ATLANTIC BEACH CAUSEWAY. ADD RIGHT TURN LANE. |  | Highway | STI (Prioritization) | 2 | Down East RPO | R-5816 | Region B | T | 2020 | 600000 |  |  | 2023 | 2170000 |  |  | 2770000 | UNDER CONSTRUCTION.
CARTERET | NC 24 | NCDOT | NC 58. INTERSECTION IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5858 | Statewide Mobility | NHP, T | 2023 | 750000 | 2024 | 125000 | 2026 | 8400000 |  |  | 9275000 | RIGHT-OF-WAY IN PROGRESS.
CARTERET | SR 1175 (BRIDGES STREET) | NCDOT | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | 1.3 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5941 | Division 2 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 930000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4000000 |  |  | 12330000
CARTERET | NC 58 (EMERALD DRIVE) | NCDOT | MANGROVE DRIVE. UPGRADE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5944 | Division 2 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 650000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5300000 |  |  | 6050000
CARTERET | US 70 (LIVE OAK STREET) | NCDOT | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | 1.8 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5945 | Division 2 | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27700000 |  |  | 51800000
CARTERET | US 70 (LIVE OAK STREET) | NCDOT | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 2 | Down East RPO | R-5946 | Division 2 | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 |  |  | 9900000
CARTERET | US 70 (LIVE OAK STREET) | NCDOT | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. |  | Highway | STI (Prioritization) | 2 | Down East RPO | U-6058 | Region B | BG5T50, L(M), T | 2023 | 1359000 | 2024 | 1200000 | 2025 | 6300000 |  |  | 8859000 | RIGHT-OF-WAY IN PROGRESS. LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT.
CARTERET | US 70 | NCDOT | REPLACEMENT OF BRIDGE NO. 33 OVER NORTH RIVER. |  | Highway | Transition | 2 | Down East RPO | B-4722B | Region B | [10 empty] | COMPLETED.
CARTERET | CARTERET COUNTY | CARTERET COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Down East RPO | TK-6115 | Public Transit | 5311, L, S | [6 empty] | 2020 | 300000 | 300000 | FUNDS AUTHORIZED IN PROGRESS
CARTERET | CARTERET COUNTY | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. |  | Public Transportation (Transit) | STI (Prioritization) | 2 | Down East RPO | TA-6717 | Division 2 | 5311, L, T |  |  |  |  | 2020 | 70000 |  |  | 70000
CARTERET | CARTERET COUNTY | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. |  | Public Transportation (Transit) | STI (Prioritization) | 2 | Down East RPO | TA-6718 | Division 2 | 5311, L, T |  |  |  |  | 2020 | 70000 |  |  | 70000
CARTERET, CRAVEN | SR 1124 (NINE MILE ROAD) ; SR 1756 (LAKE ROAD) | NCDOT | NC 24 TO PARKER COURT IN NEWPORT; SR 1124 (NINE MILE ROAD / NINE FOOT ROAD) IN CARTERET COUNTY TO SR 1745 (MILLER BOULEVARD) IN CRAVEN COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 13.5 | Highway | Safety | 2 | Down East RPO | HS-2402I | Division 2 | HSIP |  |  |  |  | 2025 | 325000 |  |  | 325000
CARTERET, CRAVEN | NC 101 | NCDOT | SR 1212 (AIRPORT ROAD) NEAR BEAUFORT TO OUTER BANKS DRIVE NEAR HAVELOCK. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 19.3 | Highway | Safety | 2 | Down East RPO | HS-2402L | Region B | HSIP |  |  |  |  | 2025 | 350000 |  |  | 350000
CARTERET, CRAVEN, BEAUFORT, LENOIR | VARIOUS | NCDOT | PRIMARY ROUTES THROUGHOUT DIVISION 2. REPLACE GUARDRAIL END UNITS. |  | Highway | Safety | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO, Eastern Carolina RPO | HS-2402M | Region B | HSIP |  |  |  |  | 2025 | 504000 |  |  | 504000
CARTERET, HYDE | NC 12 | NCDOT | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY |  | Ferry | STI (Prioritization) | 1, 2 | Albemarle RPO, Down East RPO | F-5704 | Division 1, 2 | FBP, T |  |  |  |  | 2025 | 25600000 | 2024 | 1437000 | 27037000
CASWELL | SR 1710 (GRIERS CHURCH ROAD) | NCDOT | REPLACE BRIDGE 160007 OVER HYCO CREEK. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-5725 | Division 7 | BGOFF | 2030 | 30000 |  |  | 2031 | 1700000 |  |  | 1730000
CASWELL | NC 86 | NCDOT | US 158 TO SR 1500 (OLD NC HIGHWAY 86) 1.2 MILES SOUTH OF THE VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | 7.7 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO | R-5822 | Region D | BGLT5 | 2025 | 440000 | 2025 | 1300000 | 2026 | 26600000 |  |  | 28340000 | SCOPE INCLUDES SPOT ID H170625
CASWELL | CASWELL COUNTY | CASWELL COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Piedmont Triad RPO | TK-6116 | Public Transit | 5311, L, S | [6 empty] | 2020 | 448000 | 448000 | FUNDS AUTHORIZED IN PROGRESS
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. |  | Aviation | STI (Prioritization) | 12 | Greater Hickory MPO | AV-5741 | Division 12 | O, T |  |  |  |  | 2029 | 3844000 |  |  | 3844000
CATAWBA | SPRINGS ROAD NE | HICKORY | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0066 | Division 12 | BGDA, L, TAANY, TADA | 2025 | 313000 |  |  | 2026 | 2250000 | 2023 | 437000 | 3000000 | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24.
CATAWBA | AVIATION WALK CONNECTOR | HICKORY | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 0.26 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0067 | Division 12 | BGDA, L | 2025 | 250000 |  |  | 2025 | 1600000 | 2023 | 150000 | 2000000
CATAWBA | ISLAND FORD ROAD | MAIDEN | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 0.56 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0068 | Division 12 | BGDA, L | 2025 | 500000 |  |  | 2027 | 850000 | 2024 | 405000 | 1755000
CATAWBA | CLEMENT BOULEVARD; 21ST STREET NW |  | 21ST STREET NW TO 19TH STREET NW IN HICKORY. CLEMENT BOULEVARD TO 9TH AVENUE DRIVE NW IN HICKORY. CONSTRUCT MULTI-USE TRAIL. | 0.31 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | BL-0115 | Division 12 | BGANY, BGDA, CRPDA, L | 2025 | 50000 |  |  | 2025 | 2650000 | 2024 | 300000 | 3000000 | $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24.
CATAWBA | CONOVER | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | C-5624 | Division 12 | BGANY, CMAQ, L | 2024 | 250000 | 2024 | 660000 | 2025 | 3473000 | 2023 | 209000 | 4592000 | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000.
CATAWBA | CLAREMONT | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5828 | Division 12 | BGANY, BGDA, L | 2024 | 31000 |  |  | 2025 | 541000 |  |  | 572000 | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | CENTENNIAL BOULEVARD | CLAREMONT | NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II) IN CLAREMONT. CONSTRUCT SIDEWALK. | 1.16 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5935 | Division 12 | BGANY, L |  |  |  |  | 2024 | 590000 | 2024 | 10000 | 600000 | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | HICKORY | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 0.61 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5937 | Division 12 | BGANY, L(M), TADA | 2021 | 225000 |  |  | 2023 | 3388000 |  |  | 3613000 | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION.
CATAWBA | HICKORY | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5938 | Division 12 | BGANY, L, TAANY, TADA | 2021 | 105000 |  |  | 2023 | 5095000 | 2019 | 800000 | 6000000 | UNDER CONSTRUCTION.
CATAWBA | 9TH STREET NW CONNECTOR | HICKORY | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 0.27 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-5977 | Division 12 | BGDA, CRPDA, L | 2021 | 108000 |  |  | 2023 | 1460000 |  |  | 1568000 | UNDER CONSTRUCTION.
CATAWBA | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | HICKORY | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 2.58 | Bike & Ped | Locally Selected | 12 | Greater Hickory MPO | EB-6038 | Exempt | DP, L | 2020 | 662000 |  |  | 2021 | 19216000 | 2020 | 2052000 | 21930000 | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT.
CATAWBA | MAIN AVENUE NW/NE | HICKORY | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 1.2 | Bike & Ped | STI (Prioritization) | 12 | Greater Hickory MPO | EB-5750 | Division 12 | L, TAANY |  |  |  |  | 2020 | 14100000 |  |  | 14100000
CATAWBA | OLD LENOIR ROAD MULTI-USE PATH | HICKORY | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | Bike & Ped | STI (Prioritization) | 12 | Greater Hickory MPO | EB-5911 | Division 12 | CRPDA, L, TAANY, TADA | 2021 | 1830000 |  |  | 2023 | 16025000 | 2019 | 1495000 | 19350000 | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP.
CATAWBA | NEW ROUTE |  | FAIRGROVE CHURCH ROAD SE. CONSTRUCT 0.27 MILE ACCESS ROAD TO CUL-DE-SAC. | 0.27 | Highway | Appalachian Development Highway System | 12 | Greater Hickory MPO | HA-0007 | Exempt | ADHS, L |  |  |  |  | 2024 | 1636000 | 2023 | 364000 | 2000000 | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035.
CATAWBA | SR 1709 (ROCK BARN ROAD) | NCDOT | REPLACE BRIDGE 170173 OVER I-40. | 0.25 | Highway | Bridges | 12 | Greater Hickory MPO | B-5847 | Division 12 | BFP | 2023 | 1400000 |  |  | 2030 | 10300000 |  |  | 11700000
CATAWBA | I-40 | NCDOT | REPLACE BRIDGE 170177 AND 170178 OVER LYLE CREEK. | 0.25 | Highway | Bridges | 12 | Greater Hickory MPO | B-6041 | Statewide Mobility | BFP | 2026 | 290000 |  |  | 2030 | 26900000 |  |  | 27190000
CATAWBA | TRIVIUM PARKWAY, NEW ROUTE | HICKORY | EXTEND TRIVIUM PARKWAY AND CONSTRUCT NEW ROADWAY IN TRIVIUM CORPORATE CENTER. | 0.2 | Highway | Economic Development | 12 | Greater Hickory MPO | U-6238 | Division 12 | T |  |  |  |  | 2023 | 1316000 |  |  | 1316000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CATALER NORTH AMERICA.
CATAWBA | US 70 | HICKORY | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 12 | Greater Hickory MPO | HL-0002 | Exempt | BGANY, BGDA, L(M) | 2022 | 100000 |  |  | 2025 | 900000 |  |  | 1000000 | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | 17TH STREET NW | HICKORY | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | Highway | Locally Selected | 12 | Greater Hickory MPO | HL-0004 | Division 12 | BGANY, BGDA, L | 2023 | 720000 |  |  | 2024 | 4800000 | 2021 | 480000 | 6000000 | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | Highway | Other | 12 | Greater Hickory MPO | C-5608 | Exempt | CMAQ, L | 2020 | 51000 |  |  | 2020 | 303000 | 2020 | 153000 | 507000 | IN PROGRESS
CATAWBA | NC 16 | NCDOT | SR 1801 (CLAREMONT ROAD) TO SR 1800 (CALEB SETZER ROAD) | 0.653 | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | R-3100C | [11 empty] | COMPLETE.
CATAWBA | HICKORY | NCDOT | US 70-321 TO NORTH OF I-40. |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307AA | [11 empty] | COMPLETE
CATAWBA | HICKORY | NCDOT | NORTH OF I-40 TO SR 1453 (SPRINGS ROAD) |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307AB | [11 empty] | COMPLETE
CATAWBA | HICKORY | NCDOT | NORTH OF I-40 TO NORTH OF SR 1692 (TATE BOULEVARD) |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307AD | [11 empty] | COMPLETE
CATAWBA | HICKORY | NCDOT | NORTH OF SR 1692 (TATE BOULEVARD) TO SR 1453 (SPRINGS ROAD) |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307AE | [11 empty] | COMPLETE
CATAWBA | HICKORY | NCDOT | HICKORY EAST SIDE THOROUGHFARE TO 15TH AVE SE |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2307C | [11 empty] | COMPLETE
CATAWBA | NC 127 | NCDOT | NORTH OF US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182 |  | Highway | Pre-STI (Historic) | 12 | Greater Hickory MPO | U-2530B | [11 empty] | COMPLETE
CATAWBA | SR 1849 (MOUNT PLEASANT ROAD) | NCDOT | INSTALL GUARDRAIL ON BRIDGE 163 ON SR 1849 OVER MOUNTAIN CREEK PORTION OF LAKE NORMAN | 0.05 | Highway | Safety | 12 | Greater Hickory MPO | HS-2012A | Division 12 | HSIP |  |  |  |  | 2021 | 85000 |  |  | 85000 | COMPLETE
CATAWBA | SR 1844 (SLANTING BRIDGE ROAD) | NCDOT | UPGRADE GUARDRAIL AND END UNITS AT BRIDGE 23 | 0.09 | Highway | Safety | 12 | Greater Hickory MPO | HS-2012B | Division 12 | HSIP |  |  |  |  | 2021 | 372000 |  |  | 372000 | COMPLETE
CATAWBA | NC 10 | NCDOT | MILE MARKER 19.8 TO MILE MARKER 27.1. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | Highway | Safety | 12 | Greater Hickory MPO | HS-2012H | Region F | HSIP |  |  |  |  | 2024 | 467000 |  |  | 467000
CATAWBA | NC 10 | NCDOT | MILE MARKER 11.9 TO MILE MARKER 15.0. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | Highway | Safety | 12 | Greater Hickory MPO | HS-2012I | Region F | HSIP |  |  |  |  | 2024 | 227000 |  |  | 227000
CATAWBA | I-40 | NCDOT | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | I-5716 | Statewide Mobility | NHP |  |  |  |  | 2026 | 12300000 |  |  | 12300000 | RIGHT-OF-WAY IN PROGRESS
CATAWBA | NC 16 | NCDOT | SR 1895 TO SR 1800 SOUTHEAST OF NEWTON. WIDEN TO FOUR LANES. | 9.1 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3100
CATAWBA | NC 16 | NCDOT | SR 1895 (TOWER ROAD) TO SR 1814 (CALDWELL ROAD) | 4.41 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3100A | Division 12 | T |  |  |  |  | 2021 | 42510000 |  |  | 42510000 | COMPLETE; BUILD NC BOND FUNDING: $33.028 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
CATAWBA | NC 16 | NCDOT | SR 1814 (CALDWELL ROAD) TO SR 1801 (CLAREMONT ROAD) | 3.75 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-3100B | Division 12 | [10 empty] | COMPLETE.
CATAWBA | SR 1005 (STARTOWN ROAD) | NCDOT | US 70 TO NC 10. WIDEN TO MULTI-LANES. | 4.62 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | R-5113 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 64800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 57501000 |  |  | 138801000
CATAWBA | HICKORY | NCDOT | EAST SIDE THOROUGHFARE (MCDONALD PARKWAY), US 70-321 TO NC 127. MULTI-LANES, PART ON NEW LOCATION. | 6.6 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-2307
CATAWBA | 29TH AVENUE NE | NCDOT | SR 1453 (SPRINGS ROAD) TO NC 127. WIDEN TO MULTI-LANES. | 3.19 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-2307B | Division 12 | BGANY, T | 2026 | 60100000 | 2026 | 15700000 | 2029 | 64701000 |  |  | 140501000 | NC BUILD BONDS: $12M FOR RIGHT-OF-WAY, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE).
CATAWBA | NC 127 | NCDOT | WIDEN NC 127 TO MULTI-LANES, SR 1132 TO SR 1008. UPGRADE AND EXTEND SR 1213 (CURRENTLY NC 127), PROPOSED US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182. | 4.5 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-2530
CATAWBA | NC 127 | NCDOT | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | 3.14 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-2530A | Division 12 | BGANY | 2025 | 23900000 | 2025 | 3900000 | 2029 | 64400000 |  |  | 92200000
CATAWBA | NC 127 | NCDOT | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. |  | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-5777 | Region F | BGANY, T | 2019 | 2150000 | 2019 | 436000 | 2025 | 6500000 |  |  | 9086000 | RIGHT-OF-WAY IN PROGRESS
CATAWBA | SR 1124 (33RD STREET SW) | NCDOT | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO | U-6042 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3300000 |  |  | 4900000
CATAWBA | CLAREMONT | CLAREMONT | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN CLAREMONT. |  | Highway | Transition | 12 | Greater Hickory MPO | C-5195 | Exempt | [10 empty] | UNDER CONSTRUCTION
CATAWBA | HICKORY | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | Highway | Transition | 12 | Greater Hickory MPO | C-5196 | Division 12 | BGANY, CMAQ, L | 2025 | 2856000 |  |  | 2026 | 4988000 | 2023 | 500000 | 8344000 | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP.
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Greater Hickory MPO | TG-6798 | Public Transit | 5307, L | [6 empty] | 2020 | 970000 | 970000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY |  | PROGRAM ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Greater Hickory MPO | TM-6110 | Public Transit | 5310 | [6 empty] | 2020 | 232000 | 232000
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTIVE MAINTANENCE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 12 | Greater Hickory MPO | TG-6799 | Public Transit | 5307, L | [6 empty] | 2020 | 3894000 | 3894000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | CENTER STREET | NCDOT | NSR CROSSING 729571M IN HICKORY. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2012C | Division 12 | RR |  |  |  |  | 2025 | 492000 |  |  | 492000
CATAWBA | SR 1358 (FOURTH STREET SOUTHWEST) | NCDOT | NSR CROSSING 729568E IN HICKORY. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2012F | Division 12 | RR |  |  |  |  | 2026 | 492000 |  |  | 492000
CATAWBA | SR 1735 (RANKIN AVENUE/ MOUNT OLIVE CHURCH ROAD) | NCDOT | NSR CROSSING 729612P IN NEWTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Greater Hickory MPO | RX-2012G | Division 12 | RR |  |  |  |  | 2027 | 492000 |  |  | 492000
CATAWBA, ALEXANDER, BURKE, CALDWELL | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREATER HICKORY PLANNING ORGANIZATION. |  | Highway | Locally Selected | 11, 12, 13 | Greater Hickory MPO | HL-0100 | Exempt | CRPDA, L |  |  |  |  | 2023 | 0
CATAWBA, ALEXANDER, BURKE, CALDWELL | VARIOUS | NCDOT | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. |  | Highway | Locally Selected | 11, 12, 13 | Greater Hickory MPO | U-5924 | Division 11, 12, 13 | BGDA, L | [6 empty] | 2024 | 1750000 | 1750000
CATAWBA, BURKE, CALDWELL, ALEXANDER | VARIOUS | NCDOT | GREATER HICKORY MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | Bike & Ped | Locally Selected | 11, 12, 13 | Greater Hickory MPO | U-5546 | Division 11, 12, 13 | L, TADA |  |  |  |  | 2024 | 4357000 |  |  | 4357000
CATAWBA, BURKE, CALDWELL, ALEXANDER | VARIOUS | NCDOT | STBG-DA IN THE GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. |  | Highway | Locally Selected | 11, 12, 13 | Greater Hickory MPO | U-5615 | Division 11, 12, 13 | BGANY, BGDA, L |  |  |  |  | 2024 | 46354000 |  |  | 46354000
CATAWBA, CALDWELL, BURKE | US 321 | NCDOT | NORTH OF US 70 IN HICKORY TO US 321A | 3.35 | Highway | STI (Prioritization) | 11, 12, 13 | Greater Hickory MPO | U-4700A | Statewide Mobility | L, NHP, T(M) | 2021 | 75145000 |  |  | 2027 | 276228000 |  |  | 351373000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $35M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035
CATAWBA, IREDELL, LINCOLN | NC 150 | NCDOT | RELOCATED NC 16 (STIP PROJECT R-2206) TO US 21. WIDEN TO MULTI-LANES. | 14.8 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | R-2307 | [11 empty] | SEGMENT B INCORPORATES WORK PREVIOUSLY UNDER I-5717.
CATAWBA, LINCOLN | NC 10 | NCDOT | MILE MARKER 0.0 TO MILE MARKER 2.2 IN LINCOLN COUNTY AND MILE MARKER 0.0 TO MILE MARKER 11.0 IN CATAWBA COUNTY. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | Highway | Safety | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | HS-2012M | Region F | HSIP |  |  |  |  | 2024 | 525000 |  |  | 525000
CATAWBA, LINCOLN | NC 150 | NCDOT | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 7.94 | Highway | STI (Prioritization) | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO | R-2307A | Region F | BGLT5, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 155000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 207200000 |  |  | 371700000
CHATHAM | SILER CITY MUNICIPAL AIRPORT (SCR) | SILER CITY MUNICIPAL AIRPORT (SCR) | ACQUIRE NAVIGATION EASEMENTS IN RUNWAY 4 AND RUNWAY 22 APPROACHES, AND REMOVE OBSTRUCTIONS IN EASEMENTS. |  | Aviation | STI (Prioritization) | 8 | Central Pines RPO | AV-5736 | Division 8 | T | 2024 | 365000 | [6 empty] | 365000
CHATHAM | CHATHAM BUSINESS DR | PITTSBORO | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 0.16 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BL-0035 | Exempt | CMAQ, L | 2022 | 10000 |  |  | 2023 | 160000 | 2022 | 40000 | 210000
CHATHAM | PITTSBORO ELEMENTARY SCHOOL ROAD | PITTSBORO | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 0.11 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BL-0062 | Exempt | CMAQ, L |  |  |  |  | 2024 | 220000 | 2023 | 59000 | 279000
CHATHAM | VARIOUS | NCDOT | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. |  | Bike & Ped | Locally Selected | 8 | Durham-Chapel Hill-Carrboro MPO | BL-0070 | Division 8 | BGDA, BGDACV, HF, L(M) |  |  |  |  | 2023 | 175000 | 2023 | 5000 | 180000 | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS.
CHATHAM | SR 1107 (EAST THIRD STREET) | SILER CITY | SR 1006 (NORTH SECOND AVENUE) TO EAST FIFTH STREET IN SILER CITY. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.8 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BN-0026 | Exempt | CRP550, L(M) | 2025 | 184000 |  |  | 2026 | 2106000 | 2025 | 275000 | 2565000
CHATHAM | SR 1006 (NORTH SECOND AVENUE) | SILER CITY | EAST FOURTH STREET TO US 64 (WEST ELEVENTH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.6 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BN-0027 | Exempt | CRP550, L(M) | 2025 | 198000 |  |  | 2026 | 1517000 | 2025 | 235000 | 1950000
CHATHAM | SALISBURY STREET | PITTSBORO | FAYETTEVILLE STREET TO JA FARRELL STREET IN PITTSBORO. CONSTRUCT SIDEWALK. | 0.5 | Bike & Ped | Locally Selected | 8 | Central Pines RPO | BN-0028 | Exempt | CRPANY, L(M) | 2025 | 28000 |  |  | 2025 | 254000 | 2025 | 119000 | 401000
CHATHAM | TOWN LAKE PARK | PITTSBORO | TOWN LAKE PARK INSTALL SIDEWALK. | 0.33 | Bike & Ped | NCDOT Selected (Other Selection Process) | 8 | Central Pines RPO | BN-0012 | Exempt | CRP550, L | 2025 | 31000 |  |  | 2026 | 455000 | 2024 | 146000 | 632000
CHATHAM | SR 2103 (EAST RALEIGH STREET) | SILER CITY | 6TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 1.1 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5734 | Division 8 | L, TA5T50 | 2024 | 205000 | 2024 | 143000 | 2025 | 1500000 |  |  | 1848000
CHATHAM | SR 1107 (WEST 3RD STREET) | SILER CITY | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-6006 | Division 8 | L, TA5T50 | 2025 | 220000 | 2025 | 160000 | 2026 | 2000000 | 2025 | 333000 | 2713000
CHATHAM | VARIOUS | NCDOT | CONSTRUCT ROADWAY IMPROVEMENTS NEAR THE TRIANGLE INNOVATION POINT MEGASITE. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0006 | Highway Fund | [10 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
CHATHAM | VARIOUS | NCDOT | CONSTRUCTION OF SITE DESIGN 1A. RESURFACING AND STRENGTHENING OF SURROUNDING ROADWAYS NEAR TRIANGLE INNOVATION POINT MEGASITE. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0006A | Highway Fund | HF |  |  |  |  | 2023 | 7000000 |  |  | 7000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
CHATHAM | VARIOUS | NCDOT | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0006B | Highway Fund | HF | 2023 | 10000000 | 2023 | 5000000 | 2024 | 175000000 | 2023 | 3000000 | 193000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
CHATHAM | VARIOUS | NCDOT | CONSTRUCTION OF SITE DESIGN 2A AND 2B. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0006C | Highway Fund | HF |  |  |  |  | 2025 | 50000000 |  |  | 50000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
CHATHAM | VARIOUS | NCDOT | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. |  | Highway | Economic Development | 8 | Central Pines RPO | HE-0011 | Division 8 | T | 2024 | 250000 | 2024 | 250000 | 2024 | 8500000 | 2023 | 1000000 | 10000000 | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED.
CHATHAM | VARIOUS | CHATHAM COUNTY | LOCATIONS IN CHATHAM COUNTY. PURCHASE AND INSTALL TWO ELECTRIC VEHICLE CHARGING STATIONS. |  | Highway | Locally Selected | 8 | Durham-Chapel Hill-Carrboro MPO | HL-0156 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 266000 |  |  | 266000
CHATHAM | VARIOUS | CHATHAM COUNTY | LOCATIONS IN CHATHAM COUNTY. PURCHASE AND INSTALL FOUR ELECTRIC VEHICLE CHARGING STATIONS. |  | Highway | NCDOT Selected (Other Selection Process) | 8 | Central Pines RPO | HN-0035 | Exempt | CRPANY, L(M) |  |  |  |  | 2026 | 46000 | 2025 | 74000 | 120000
CHATHAM | NC 751; SR 1008 (FARRINGTON POINT ROAD) | NCDOT | NC 751 FROM US 64 TO DURHAM COUNTY LINE; SR 1008 (FARRINGTON POINT ROAD) FROM SR 1972 (PEA RIDGE ROAD) TO ORANGE COUNTY LINE. INSTALL RUMBLE STRIPS. | 21.8 | Highway | Safety | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO | HS-2408A | Region E | HSIP |  |  |  |  | 2025 | 695000 |  |  | 695000
CHATHAM | US 421 | NCDOT | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | Safety | 8 | Central Pines RPO | W-5808B | Statewide Mobility | HSIP | 2024 | 100000 |  |  | 2025 | 736000 |  |  | 836000 | RIGHT-OF-WAY IN PROGRESS
CHATHAM | US 15 / US 501 | NCDOT | SOUTH OF US 64 BUSINESS TO POWELL PLACE LANE IN PITTSBORO. WIDEN TO MULTI-LANES, MILL AND RESURFACE, AND CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. | 1.9 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5724 | Division 8
CHATHAM | US 15 / US 501 | NCDOT | US 15 / US 501, SOUTH OF US 64 BUSINESS TO NORTH OF US 64 BUSINESS. CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. |  | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5724A | Division 8 | T |  |  |  |  | 2021 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION
CHATHAM | US 15 / US 501 | NCDOT | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | 1.79 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5724B | Division 8 | T | 2023 | 3900000 | 2023 | 1300000 | 2026 | 18300000 |  |  | 23500000 | RIGHT-OF-WAY IN PROGRESS
CHATHAM | NC 751 | NCDOT | SR 1731 (O'KELLY CHAPEL ROAD). UPGRADE AND REALIGN INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 8 | Durham-Chapel Hill-Carrboro MPO | R-5825 | Division 8 | T |  |  |  |  | 2023 | 1264000 |  |  | 1264000 | RIGHT-OF-WAY IN PROGRESS
CHATHAM | US 64 | NCDOT | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5887 | Region E | NHP | 2030 | 6400000 | 2030 | 3000000 | 2032 | 62300000 |  |  | 71700000
CHATHAM | NEW ROUTE (CHATHAM PARK WAY) | NCDOT | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 2.52 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5930 | Division 8 | O, T | 2023 | 3693000 | 2023 | 360000 |  |  |  |  | 4053000 | "O" FUNDING REFLECTS LOCAL PARTICIPATION.
CHATHAM | NEW ROUTE (CHATHAM PARK WAY) | NCDOT | NORTHERN TERMINUS OF EXISTING CHATHAM PARK WAY JUST NORTH OF US 64 TO NORTH OF PROPOSED GRANT DRIVE. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.11 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5930A | Division 8 | O, T |  |  |  |  | 2024 | 19801000 |  |  | 19801000 | UNDER CONSTRUCTION
CHATHAM | NEW ROUTE (CHATHAM PARK WAY) | NCDOT | NORTH OF PROPOSED GRANT DRIVE TO US 15/ US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.41 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5930B | Division 8 | T |  |  |  |  | 2025 | 27700000 |  |  | 27700000
CHATHAM | (CHATHAM PARK WAY) NEW ROUTE | NCDOT | US 15 / US 501 / NC 87 TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 3.03 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5963 | [11 empty] | Former R-5963B merged into R-5963A. BUILD NC BONDS: $6M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE)
CHATHAM | NEW ROUTE (CHATHAM PARK WAY) | NCDOT | US 15 / US 501 SOUTH OF PITTSBORO TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 1.33 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5963A | Division 8 | T | 2025 | 6259000 | 2025 | 62000 | 2025 | 82759000 |  |  | 89080000 | BUILD NC BOND FUNDING: $22,806,281 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE).
CHATHAM | NEW ROUTE (CHATHAM PARK WAY) | NCDOT | US 64 BUSINESS TO JUST NORTH OF US 64. WIDEN EXISTING 2-LANE ROADWAY TO 4-LANES. | 1.22 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5963C | Not Funded | T | NOT FUNDED |  | NOT FUNDED | 30000 | NOT FUNDED | 32100000 | NOT FUNDED |  | 32130000
CHATHAM | NEW ROUTE (CHATHAM PARK WAY) | NCDOT | CONSTRUCTION OF NEW WESTBOUND ON-RAMP FROM CHATHAM PARK WAY TO US 64 AND REALIGNMENT OF SUTTLES ROAD TO NEW INTERSECTION WITH CHATHAM PARK WAY. | 0.5 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5963D | Division 8 | T | 2024 | 500000 |  |  | 2024 | 6700000 |  |  | 7200000 | ROW BEING DONATED BY TOWN OF PITTSBORO
CHATHAM | US 64 (EAST 11TH STREET) | NCDOT | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTI-USE SIDEPATH. | 2.64 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5737 | Region E | T | 2025 | 10800000 | 2025 | 3400000 | 2029 | 40300000 |  |  | 54500000
CHATHAM | US 15 / US 501 | NCDOT | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | 10.46 | Highway | STI (Prioritization) | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO | U-6192 | Division 8 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83300000 |  |  | 107000000
CHATHAM | PITTSBORO | CHATHAM TRANSIT NETWORK | OPERATING ASSISTANCE FOR NEW TRANSIT SERVICE IN THE TOWN OF PITTSBORO. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 8 | Central Pines RPO | TN-6135 | Exempt | CMAQ, L(M) | [6 empty] | 2025 | 175000 | 175000
CHATHAM | CHATHAM TRANSIT NETWORK | CHATHAM TRANSIT NETWORK | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 8 | Central Pines RPO | TK-6117 | Public Transit | 5311, L, S | [6 empty] | 2020 | 944000 | 944000 | FUNDS AUTHORIZED IN PROGRESS
CHATHAM | VARIOUS | CHATHAM TRANSIT NETWORK | CHATHAM TRANSIT NETWORK. PURCHASE 3 NEW RAMP-EQIPPED MINIVANS. |  | Public Transportation (Transit) | STI (Prioritization) | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO | TA-6719 | Division 8 | L, T | [6 empty] | 2021 | 141000 | 141000
CHATHAM | SR 1916 (CORINTH ROAD) | NCDOT | CSX CROSSING 630723C NEAR HAYWOOD. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Central Pines RPO | RX-2008A | Division 8 | RR |  |  |  |  | 2024 | 800000 |  |  | 800000
CHATHAM, CUMBERLAND, EDGECOMBE, GASTON, HARNETT, HENDERSON, LEE, LINCOLN, MARTIN, TRANSYLVANIA, BERTIE, HERTFORD, NASH, RANDOLPH, WAKE | VARIOUS | NCDOT | INSTALL EV CHARGERS AT MULTIPLE COMMUNITY COLLEGES: BLUE RIDGE COMMUNITY COLLEGE CENTRAL CAROLINA COMMUNITY COLLEGE EDGECOMBE COMMUNITY COLLEGE FAYETTEVILLE COMMUNITY COLLEGE GASTON COLLEGE MARTIN COMMUNITY COLLEGE NASH COMMUNITY COLLEGE RANDOLPH COMMUNITY COLLEGE ROANOKE-CHOWAN COMMUNITY COLLEGE WAKE TECHNICAL COMMUNITY COLLEGE |  | Highway | Other | 1, 4, 5, 6, 8, 12, 14 | Capital Area MPO, Central Pines RPO, Fayetteville Area MPO, French Broad River MPO, Gaston-Cleveland-Lincoln MPO, Land-of-Sky RPO, Mid-Carolina RPO, Peanut Belt RPO, Piedmont Triad RPO, Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | HO-0019 | Exempt | DP, HF(M) |  |  |  |  | 2025 | 1259000 |  |  | 1259000 | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. HF REPRESENT CONTINGENCY FUNDS.
CHATHAM, HOKE, LEE, RANDOLPH, SCOTLAND | VARIOUS | NCDOT | VARIOUS SECONDARY ROUTES IN CHATHAM, LEE, HOKE, RANDOLPH AND SCOTLAND COUNTIES. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 8 | Central Pines RPO, Lumber River RPO, Piedmont Triad RPO, High Point Urban Area MPO, Fayetteville Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2008C | Region E | HSIP |  |  |  |  | 2022 | 1580000 |  |  | 1580000
CHATHAM, LEE | SR 1007 (PLANK ROAD) | NCDOT | REPLACE BRIDGE 180169 OVER DEEP RIVER. | 0.25 | Highway | Bridges | 8 | Central Pines RPO | HB-0034 | Division 8 | BGOFF | 2030 | 325000 | 2030 | 325000 | 2032 | 6500000 |  |  | 7150000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | BO-2408 | Division 8 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | BO-2608 | Division 8 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | R-5788 | Division 8 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | HS-2008 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 8. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | HS-2023
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | HS-2023DIV | Division 8 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | HS-2023REG | Region E | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | HS-2023SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | HS-2408 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2608 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | DIVISION 8 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | W-5208 | [11 empty] | UNDER CONSTRUCTION
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | W-5708 | [11 empty] | IN PROGRESS
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | W-5708DIV | Division 8 | HSIP | 2020 | 90000 |  |  | 2020 | 540000 |  |  | 630000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | W-5708REG | Region E | HSIP | 2020 | 90000 |  |  | 2020 | 540000 |  |  | 630000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | W-5708SW | Statewide Mobility | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | Highway | Safety | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | W-5808
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 8. |  | Rail | Rail-Highway Grade Crossing Closure | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | RC-2008 | Division 8 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | RX-2008 | Division 8 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | RX-2408 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | RX-2608 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHATHAM, ORANGE | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | Highway | Other | 7, 8 | Central Pines RPO | C-5618 | Exempt | CMAQ, L | 2020 | 45000 |  |  | 2020 | 255000 | 2020 | 135000 | 435000
CHEROKEE | SR 1326 | NCDOT | REPLACE BRIDGE 190159 OVER HANGING DOG CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-4069 | Division 14 | BGOFF | 2025 | 295000 |  |  | 2027 | 1800000 |  |  | 2095000
CHEROKEE | SR 1548 (OLD HIGHWAY 64) | NCDOT | REPLACE BRIDGE 190223 OVER HIWASSEE RIVER. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-5925 | Division 14 | BFP | 2025 | 660000 | 2025 | 320000 | 2026 | 6500000 |  |  | 7480000
CHEROKEE | NC 141 | NCDOT | SR 1533 (HENDRIX ROAD) INTERSECTION. CONSTRUCT LEFT TURN LANE. |  | Highway | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | HN-0029 | Region G | CRPLT5, T(M) |  |  |  |  | 2024 | 600000 |  |  | 600000
CHEROKEE | SR 1564 (BRASSTOWN ROAD) | NCDOT | JOHN C. CAMPBELL FOLK SCHOOL. INSTALL FOUR RECTANGULAR RAPID FLASHING BEACONS AND CONSTRUCT CONCRETE LANDING PADS. | 0.49 | Highway | Safety | 14 | Southwestern RPO | HS-2014V | Division 14 | HSIP |  |  |  |  | 2024 | 61000 |  |  | 61000
CHEROKEE | US 64/US 74 | NCDOT | NC 60 NEAR MURPHY. CONSTRUCT DIRECTIONAL LEFTOVER WITH U-TURN BULBOUTS. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014X | Statewide Mobility | HSIP |  |  |  |  | 2024 | 525000 |  |  | 525000
CHEROKEE | US 19 BUSINESS | NCDOT | SR 1424 (CONNAHETTA STREET) AND MAPLE STREET INTERSECTIONS. INSTALL PEDESTRIAN RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2414B | Region G | HSIP |  |  |  |  | 2025 | 75000 |  |  | 75000
CHEROKEE | US 19/US 74/ US 64/US 129 | NCDOT | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 0.07 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5735 | Division 14 | T | 2020 | 4815000 |  |  | 2020 | 15390000 | 2020 | 2700000 | 22905000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE)
CHEROKEE | US 19/US 74/US 64/US 129 | NCDOT | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 0.73 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5735A | Division 14 | [10 empty] | CLEARING ONLY.
CHEROKEE | US 19/129 | NCDOT | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | 3.8 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5861 | Division 14 | BGLT5, T | 2022 | 11400000 | 2022 | 1850000 | 2024 | 77933000 |  |  | 91183000 | RIGHT-OF-WAY IN PROGRESS.
CHEROKEE | CHEROKEE COUNTY | CHEROKEE COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6118 | Public Transit | 5311, L, S | [6 empty] | 2020 | 712000 | 712000 | FUNDS AUTHORIZED IN PROGRESS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | BO-2414 | Division 14 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 600000 | 6100000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | BO-2614 | Division 14 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | R-5794 | Division 14 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2014 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 14. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2029
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2029DIV | Division 14 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2029REG | Region G | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2029SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2414 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2614 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5714 | [11 empty] | IN PROGRESS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5714DIV | Division 14 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5714REG | Region G | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5714SW | Statewide Mobility | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | Highway | Safety | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | W-5814
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 14. |  | Rail | Rail-Highway Grade Crossing Closure | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | RC-2014 | Division 14 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | RX-2014 | Division 14 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | RX-2414 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | RX-2614 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
CHEROKEE, GRAHAM, JACKSON, SWAIN | VARIOUS | FHWA | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. |  | Highway | Other | 14 | Southwestern RPO | R-5966 | Exempt | FTTP |  |  |  |  | 2023 | 25490000 |  |  | 25490000 | PROGRAM IN PROGRESS
CHEROKEE, GRAHAM, JACKSON, SWAIN | EASTERN BAND OF CHEROKE INDIANS | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 |  | TK-6127 | Public Transit | 5311, L, S | [6 empty] | 2020 | 464000 | 464000 | FUNDS AUTHORIZED IN PROGRESS
CHOWAN | SR 1202 (HICKORY FORK ROAD) | NCDOT | OVER PEMBROKE CREEK IN CHOWAN COUNTY. REPLACE CULVERT BP-021-2074. |  | Highway | Other | 1 | Albemarle RPO | HO-0023 | Exempt | DP, HF(M) | 2026 | 150000 |  |  | 2026 | 350000 | 2025 | 100000 | 600000 | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22
CLAY | US 64/NC 69 | NCDOT | NC 69, GEORGIA STATE LINE TO US 64. WIDEN TO FOUR LANES DIVIDED. US 64, NC 69 TO EAST OF NC 175. WIDEN TO MULTI-LANES. | 7.3 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011 | [11 empty] | APD FUNDS ARE 100% FEDERAL
CLAY | NC 69 | NCDOT | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). UPGRADE EXISTING TWO-LANES | 3.51 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011A | [11 empty] | COMPLETE
CLAY | US 64 | NCDOT | NC 69 IN HAYESVILLE TO EAST OF THE HIWASSEE RIVER | 0.946 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011BA | [11 empty] | COMPLETE
CLAY | US 64 | NCDOT | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175 | 3.8 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011BB | [11 empty] | COMPLETE
CLAY | NC 69 | NCDOT | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). WIDEN TO FOUR-LANES | 3.51 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011C | Exempt | ADHS |  |  |  |  | 2020 | 52600000 |  |  | 52600000 | UNDER CONSTRUCTION
CLAY | US 64 | NCDOT | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. |  | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0011D | Not Funded | ADHS | NOT FUNDED | 20845000 | NOT FUNDED | 378000 | NOT FUNDED | 52800000 | NOT FUNDED |  | 74023000
CLAY | SR 1140 (MYERS CHAPEL ROAD) | NCDOT | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | Highway | Bridges | 14 | Southwestern RPO | HF-0005 | Exempt | FLAP, HF, HF(M) | 2024 | 310000 | 2024 | 286000 | 2025 | 3680000 | 2021 | 745000 | 5021000 | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS.
CLAY | US 64 | NCDOT | SR 1147 (OAK FOREST ROAD) NEAR HAYESVILLE. EXTEND TWO-WAY LEFT TURN LANE. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014AA | Region G | HSIP |  |  |  |  | 2024 | 51000 |  |  | 51000
CLAY | SR 1100 (OLD HIGHWAY 64 WEST) | NCDOT | SR 1135 (SETTAWIG ROAD) NEAR BRASSTOWN. INSTALL GUARDRAIL ON CULVERT. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014F | Division 14 | HSIP |  |  |  |  | 2023 | 45000 |  |  | 45000 | UNDER CONSTRUCTION.
CLAY | NC 175 | NCDOT | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5742 | Division 14 | T | 2020 | 540000 |  |  | 2020 | 32847000 | 2020 | 2505000 | 35892000 | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
CLAY | NC 175 | NCDOT | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5742A | Division 14 | [10 empty] | CLEARING ONLY.
CLAY | US 64 BUSINESS | NCDOT | US 64 TO SR 1307 (MAIN STREET). UPGRADE ROADWAY. | 1.19 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5863 | Division 14 | T | 2022 | 4200000 |  |  | 2026 | 13900000 |  |  | 18100000 | RIGHT-OF-WAY IN PROGRESS.
CLAY | US 64 | NCDOT | US 64 BUSINESS INTERSECTION (WESTERN) IN HAYESVILLE. INSTALL TRAFFIC SIGNAL. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5863A | Division 14 | T |  |  |  |  | 2025 | 330000 |  |  | 330000
CLAY | CLAY COUNTY | CLAY COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6120 | Public Transit | 5311, L, S | [6 empty] | 2020 | 704000 | 704000 | FUNDS AUTHORIZED IN PROGRESS
CLEVELAND | SHELBY RAIL TRAIL | SHELBY | SOUTH DEKALB STREET TO GARDNER STREET IN SHELBY. GRAHAM STREET TO WEST MARION STREET IN SHELBY. CONSTRUCT MULTI-USE PATH. | 10.41 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | EB-6037A | Division 12 | L, TAANY |  |  |  |  | 2025 | 5198000 | 2024 | 10000 | 5208000
CLEVELAND | SR 1607 (EASTRIDGE DRIVE) | NCDOT | REPLACE BRIDGE 220392 OVER BUFFALO CREEK. |  | Highway | Bridges | 12 | Gaston-Cleveland-Lincoln MPO | B-5858 | Division 12 | BGOFF | 2027 | 20000 | 2027 | 225000 | 2029 | 1500000 |  |  | 1745000
CLEVELAND | US 74 | NCDOT | REPLACE BRIDGES 220048 AND 220049 OVER SANDY RUN. | 0.25 | Highway | Bridges | 12 | Gaston-Cleveland-Lincoln MPO | BR-0012 | Highway Fund | HFB | 2022 | 42000 |  |  | 2024 | 61591000 |  |  | 61633000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | WEST OF SR 1162 (PEACHTREE ROAD) TO EAST OF SR 1315 (PLATO LEE ROAD). RIGHT-OF-WAY ONLY. | 3.9 | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707A | [11 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF SR 1318 (KIMBRELL ROAD) TO EAST OF NC 226. PAVING | 5.27 | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707F | Pre-STI (Transition) | [10 empty] | COMPLETE
CLEVELAND | NEW ROUTE | NCDOT | CONSTRUCT IMPROVEMENTS TO SR 1313 (WASHBURN SWITCH ROAD) AND A NEW 3-LANE ROAD OFF SR 1313 (WASHBURN SWITCH ROAD) FOR ACCESS TO NEW INDUSTRIAL SITES. |  | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | R-5849 | Division 12 | [10 empty] | UNDER CONSTRUCTION
CLEVELAND | NC 18 | NCDOT | MILE MARKER 0.0 TO MILE MARKER 6.0. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012G | Region F | HSIP |  |  |  |  | 2024 | 451000 |  |  | 451000
CLEVELAND | NC 18 | NCDOT | MILE MARKER 13.5 TO MILE MARKER 18.6. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012L | Region F | HSIP |  |  |  |  | 2024 | 186000 |  |  | 186000
CLEVELAND | US 74 (SHELBY BYPASS) | NCDOT | FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | 18.6 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | 5.42 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707C | Region F | T |  |  |  |  | 2020 | 40335000 | 2021 | 75000 | 40410000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 4.26 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707D | Region F | T | 2019 | 20684000 |  |  | 2024 | 276202000 |  |  | 296886000 | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE);
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | US 74 WEST OF SR 2238 (LONG BRANCH ROAD) TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | 3.03 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-2707E | Region F | T | 2019 | 35532000 | 2023 | 5300000 |  |  |  |  | 40832000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). R-2707E CONSTRUCTION FUNDED UNDER R-2707D.
CLEVELAND | US 74 | NCDOT | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 1.35 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-4045 | Region F | DP, T | 2023 | 16000000 | 2023 | 5600000 | 2023 | 61591000 |  |  | 83191000 | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION.
CLEVELAND | US 74 | NCDOT | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 5.96 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-5713 | Region F | NHP |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 |  |  | 3200000
CLEVELAND | US 74 (DIXON BOULEVARD) | NCDOT | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-2567 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21199000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1350000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48400000 |  |  | 70949000 | TO BE LET WITH U-5929
CLEVELAND | US 74 BUSINESS (MARION STREET) | NCDOT | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5775 | Region F | L, T |  |  |  |  | 2022 | 10366000 |  |  | 10366000 | UNDER CONSTRUCTION. $702,705 FROM CITY OF SHELBY
CLEVELAND | US 74 (DIXON BOULEVARD) | NCDOT | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5929 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13600000 |  |  | 22500000 | TO BE LET WITH U-2567
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF SR 1318 (KIMBRELL ROAD) TO EAST OF SR 1315 (PLATO LEE ROAD). GRADING AND STRUCTURES | 2.68 | Highway | Transition | 12 | Gaston-Cleveland-Lincoln MPO | R-2707AB | Pre-STI (Transition) | [10 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | NCDOT | EAST OF SR 1315 (PLATO LEE ROAD) TO EAST OF NC 226. GRADING AND STRUCTURES | 2.58 | Highway | Transition | 12 | Gaston-Cleveland-Lincoln MPO | R-2707B | Pre-STI (Transition) | [10 empty] | COMPLETE
CLEVELAND | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TK-6166 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1196000 | 1196000 | FUNDS AUTHORIZED IN PROGRESS
CLEVELAND | LINBERGER STREET | NCDOT | CSX CROSSING 631872G IN SHELBY. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO | RX-2012A | Division 12 | RR |  |  |  |  | 2025 | 474000 |  |  | 474000
CLEVELAND | SR 2263 (MARGRACE ROAD) | NCDOT | NSR CROSSING 716273A IN KINGS MOUNTAIN. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO | RX-2012E | Division 12 | RR |  |  |  |  | 2026 | 555000 |  |  | 555000
CLEVELAND, GASTON | KINGS MOUNTAIN | NCDOT | INSTALL 20 EV CHARGERS ACROSS FIVE LOCATIONS IN KINGS MOUNTAIN. |  | Highway | Other | 12 | Gaston-Cleveland-Lincoln MPO | HO-0018 | Exempt | DP, L |  |  |  |  | 2025 | 1029000 |  |  | 1029000 | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT.
CLEVELAND, GASTON | NC 150 | NCDOT | MILEPOST 19.3 TO GASTON COUNTY LINE AND FROM THE CLEVELAND COUNTY LINE TO MILEPOST 1.2. CONSTRUCT SAFETY IMPROVEMENTS. | 5.88 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | W-5712U | Region F | HSIP |  |  |  |  | 2025 | 625000 |  |  | 625000
CLEVELAND, GASTON | I-85 | NCDOT | SOUTH CAROLINA STATE LINE TO US 74. INSTALL BROADBAND. | 9.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719FC | Statewide Mobility | DP, T(M) |  |  |  |  | 2025 | 7050000 |  |  | 7050000 | DP REPRESENTS 2022 INFRA GRANT.
CLEVELAND, GASTON | KINGS MOUNTAIN |  | INSTALL 20 EV CHARGERS ACROSS FIVE LOCATIONS IN KINGS MOUNTAIN. |  | Public Transportation (Transit) | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | TO-6813 | Exempt | DP, L |  |  |  |  | 2024 | 1029000 |  |  | 1029000 | DP REPRESENTS CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT
CLEVELAND, POLK, GASTON, HENDERSON, RUTHERFORD, MECKLENBURG, BUNCOMBE | US 74 | NCDOT | I-40 IN ASHEVILLE TO I-77 AT I-485 (SOUTH) IN CHARLOTTE. INSTALL BROADBAND. | 123.09 | Highway | Other | 10, 12, 13, 14 | Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Charlotte Regional TPO | HO-0002A | Statewide Mobility | HSIP |  |  |  |  | 2021 | 18435000 |  |  | 18435000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002B, AND HO-0002C.
COLUMBUS | CPC | CPC | COLUMBUS COUNTY MUNICIPAL AIRPORT. EXTEND RUNWAY. |  | Aviation | STI (Prioritization) | 6 | Cape Fear RPO | AP-0006 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 248000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3677000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 390000 | 4315000
COLUMBUS | CPC | CPC | COLUMBUS COUNTY MUNICIPAL AIRPORT. IMPROVE RUNWAY SAFETY AREA AND WIDEN RUNWAY. |  | Aviation | STI (Prioritization) | 6 | Cape Fear RPO | AP-0007 | Division 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10536000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1054000 | 11590000
COLUMBUS | COLUMBUS COUNTY AIRPORT (CPC) | COLUMBUS COUNTY AIRPORT (CPC) | APRON EXPANSION. |  | Aviation | STI (Prioritization) | 6 | Cape Fear RPO | AV-5748 | Division 6 | T |  |  |  |  | 2024 | 3000000 |  |  | 3000000
COLUMBUS | US 701 BUSINESS (E 5TH STREET) |  | FROM WEST OF LYNWOOD NORRIS ROAD TO US 701 BYPASS IN TABOR CITY. CONSTRUCT SIDEWALK AND SIGNALIZED PEDESTRIAN CROSSING. | 0.2 | Bike & Ped | NCDOT Selected (Other Selection Process) | 6 | Cape Fear RPO | BN-0006 | Exempt | CRPLT5, HF(M) |  |  |  |  | 2025 | 250000 |  |  | 250000 | HF(M) FUNDING REPRESENT LEGISLATIVE CONTINGENCY FUNDS.
COLUMBUS | SR 1159 (OLD TRAM ROAD) | NCDOT | REPLACE BRIDGE 230313 OVER BOOGY BRANCH. | 0.25 | Highway | Bridges | 6 | Cape Fear RPO | B-6006 | Division 6 | [10 empty] | COMPLETED.
COLUMBUS | ROAD) SR 1800 (BLACKSMITH | NCDOT | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | 0.25 | Highway | Bridges | 6 | Cape Fear RPO | HB-0009 | Division 6 | BGOFF | 2029 | 140000 | 2029 | 110000 | 2030 | 1400000 |  |  | 1650000
COLUMBUS | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM EAST OF NC 214 TO WEST OF SR 1824 (WATER TANK ROAD). PAVEMENT REHABILITATION. | 7 | Highway | Interstate Maintenance | 6 | Cape Fear RPO | HI-0015 | Statewide Mobility | BGLT5 |  |  |  |  | 2024 | 10300000 |  |  | 10300000
COLUMBUS | US 74 (FUTURE I-74) | NCDOT | WEST OF US 701 BUSINESS TO WEST OF NC 214. PAVEMENT REHABILITATION. | 17.59 | Highway | Interstate Maintenance | 6 | Cape Fear RPO | HI-0018 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2025 | 32900000 |  |  | 32900000
COLUMBUS | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM WEST OF SR 1585 (UNION VALLEY ROAD) TO WEST OF US 701 BUSINESS. PAVEMENT REHABILITATION. | 6.54 | Highway | Interstate Maintenance | 6 | Cape Fear RPO | HI-0019 | Statewide Mobility | NHPIM |  |  |  |  | 2031 | 5400000 |  |  | 5400000
COLUMBUS | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM THE ROBESON COUNTY LINE TO WEST OF SR 1585 (UNION VALLEY ROAD). PAVEMENT REHABILITATION. | 13.86 | Highway | Interstate Maintenance | 6 | Cape Fear RPO | HI-0020 | Statewide Mobility | NHPIM |  |  |  |  | 2031 | 15000000 |  |  | 15000000
COLUMBUS | VARIOUS | COLUMBUS COUNTY | LOCATIONS IN COLUMBUS COUNTY. PURCHASE AND INSTALL 24 ELECTRIC VEHICLE CHARGING STATIONS. |  | Highway | Locally Selected | 6 | Cape Fear RPO | HN-0034 | Exempt | CRPANY, L(M) |  |  |  |  | 2026 | 144000 | 2025 | 12000 | 156000
COLUMBUS | US 701 BUSINESS (MADISON STREET) |  | AT SR 1916 (LEE STREET), AND SR 1953 (FRANKLIN STREET). CONSTRUCT ROUNDABOUT TO REPLACE EXISTING TRAFFIC SIGNAL. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Cape Fear RPO | HN-0023 | Region C | CRPLT5, T(M) | 2025 | 100000 |  |  | 2026 | 3000000 | 2024 | 400000 | 3500000
COLUMBUS | NC 211 | NCDOT | NC 211 FROM THE BRUNSWICK COUNTY LINE TO NC 214. INSTALL RUMBLE STRIPES. | 9.48 | Highway | Safety | 6 | Cape Fear RPO | HS-2006F | Region C | HSIP |  |  |  |  | 2023 | 1051000 |  |  | 1051000 | UNDER CONSTRUCTION.
COLUMBUS | NC 87 | NCDOT | MILE MARKER 1.033 TO MILE MARKER 6.933 NEAR RIEGELWOOD. INSTALL RUMBLE STRIPS AND PAVEMENT MARKERS. | 5.9 | Highway | Safety | 6 | Cape Fear RPO | HS-2406A | Statewide Mobility | HSIP |  |  |  |  | 2025 | 290000 |  |  | 290000
COLUMBUS | NC 130 ; NC 410 | NCDOT | MILEPOST 0 TO MILEPOST 17.04 ; MILEPOST 2.62 TO 13.6. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | Highway | Safety | 6 | Cape Fear RPO | HS-2406J | Region C | HSIP |  |  |  |  | 2025 | 890000 |  |  | 890000
COLUMBUS | NC 410 (BROWN STREET) | NCDOT | FIRST AVENUE INTERSECTION IN CHADBOURN. UPGRADE TRAFFIC SIGNAL WITH PEDESTRIAN HEADS. |  | Highway | Safety | 6 | Cape Fear RPO | HS-2406Q | Region C | HSIP |  |  |  |  | 2025 | 85000 |  |  | 85000
COLUMBUS | NC 11 | NCDOT | SR 1740 (OLD LAKE ROAD) INTERSECTION SOUTH OF SANDYFIELD. IMPROVE INTERSECTION INCLUDING MILLING AND GRADING. | 0.5 | Highway | Safety | 6 | Cape Fear RPO | W-5806A | Region C | HSIP |  |  |  |  | 2025 | 50000 |  |  | 50000
COLUMBUS | NC 87 | NCDOT | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | 5.99 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-2561C | Not Funded | T | NOT FUNDED | 26511000 | NOT FUNDED | 4488000 | NOT FUNDED | 85799000 | NOT FUNDED |  | 116798000
COLUMBUS | NC 87 | NCDOT | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-2561CA | Region C | BGLT5, T | 2020 | 3904000 | 2020 | 3000000 | 2023 | 41376000 |  |  | 48280000 | UNDER CONSTRUCTION.
COLUMBUS | NC 87 | NCDOT | CONSTRUCT DETOUR ROUTE. |  | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-2561CB | Region C | T |  |  |  |  | 2023 | 1756000 |  |  | 1756000 | UNDER CONSTRUCTION.
COLUMBUS | US 701 BYPASS (MADISON STREET- POWELL BOULEVARD) | NCDOT | SOUTH OF SR 1166 (PLEASANT PLAINS ROAD) TO NORTH OF US 74/US 76 BYPASS IN WHITEVILLE. WIDEN TO MULTI-LANE FACILITY. | 3.92 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5020 | [11 empty] | RIGHT-OF-WAY IN PROGRESS.
COLUMBUS | US 701 BYPASS | NCDOT | SR 1166 (PLEASANT PLAINS CHURCH ROAD) TO SR 1437 (VIRGIL AVENUE). | 2.18 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5020A | Region C | NHP |  |  |  |  | 2030 | 65600000 |  |  | 65600000 | RIGHT-OF-WAY IN PROGRESS.
COLUMBUS | US 701 BYPASS | NCDOT | SR 1437 (VIRGIL AVENUE) TO US 74/US 76. | 1.74 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5020B | Division 6 | T |  |  |  |  | 2022 | 32485000 |  |  | 32485000 | UNDER CONSTRUCTION.
COLUMBUS | US 74 | NCDOT | SR 1506 (BOARDMAN ROAD). UPGRADE AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5797 | Region C | T |  |  |  |  | 2021 | 18620000 |  |  | 18620000 | UNDER CONSTRUCTION.
COLUMBUS | US 74/US 76 | NCDOT | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | 3 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5819 | Region C | T | 2021 | 346000 | 2021 | 129000 | 2022 | 11665000 |  |  | 12140000 | COMBINE WITH R-5820. UNDER CONSTRUCTION.
COLUMBUS | US 74 / 76 | NCDOT | ADVANCED CONSTRUCTION OF TEMPORARY REDUCED CONFLICT INTERSECTIONS AT SR 1735 (CHAUNCEY TOWN ROAD) AND SR 1740 (OLD LAKE ROAD). | 0.5 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5819A | Region C | T |  |  |  |  | 2021 | 2300000 |  |  | 2300000 | UNDER CONSTRUCTION.
COLUMBUS | US 74/US 76 | NCDOT | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 6 | Cape Fear RPO | R-5820 | Region C | T | 2021 | 1184000 | 2021 | 1297000 | 2022 | 50713000 |  |  | 53194000 | COMBINE WITH R-5819. UNDER CONSTRUCTION.
COLUMBUS | COLUMBUS COUNTY | COLUMBUS COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Cape Fear RPO | TK-6121 | Public Transit | 5311, L, S | [6 empty] | 2020 | 688000 | 688000 | FUNDS AUTHORIZED IN PROGRESS
COLUMBUS | SR 1305 (SANDY BLUFF ROAD) | NCDOT | RJCS CROSSING 629312A IN TABOR CITY. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 6 | Cape Fear RPO | RX-2406A | Division 6 | RR |  |  |  |  | 2026 | 425000 |  |  | 425000
COLUMBUS, BLADEN | US 701 | NCDOT | MILEPOST 1.96 TO 9.46 IN BLADEN COUNTY, MILEPOST 2.57 TO 15.48 AND MILEPOST 19.97 TO 30.35 IN COLUMBUS COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 30.79 | Highway | Safety | 6 | Cape Fear RPO, Mid-Carolina RPO | HS-2406G | Region C | HSIP |  |  |  |  | 2025 | 970000 |  |  | 970000
COLUMBUS, ROBESON | US 74 | NCDOT | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | 22.71 | Highway | STI (Prioritization) | 6 | Cape Fear RPO, Lumber River RPO | I-6011 | Not Funded | T | NOT FUNDED | 179000 | NOT FUNDED | 1469000 | NOT FUNDED | 169100000 | NOT FUNDED |  | 170748000
COLUMBUS, ROBESON, ANSON, SCOTLAND, RICHMOND, BRUNSWICK, UNION | US 74 | NCDOT | EASTERN END OF MONROE BYPASS TO I-140 IN WILMINGTON. VULNERABILITY ASSESSMENTS, INSTALLATION OF FLOOD GAUGES, AND FLOOD MONITORING. | 156.15 | Highway | Other | 3, 6, 8, 10 | Lumber River RPO, Cape Fear RPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO | HO-0002D | Statewide Mobility | DP, T | [6 empty] | 2022 | 2200000 | 2200000
COLUMBUS, ROBESON, BRUNSWICK | US 74 | NCDOT | I-95 IN LUMBERTON TO I-140 IN WILMINGTON. INSTALL BROADBAND. | 69.67 | Highway | Other | 3, 6 | Cape Fear RPO, Lumber River RPO, Wilmington Urban Area MPO | HO-0002C | Statewide Mobility | HSIP |  |  |  |  | 2021 | 10456000 |  |  | 10456000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002B. UNDER CONSTRUCTION.
COLUMBUS, ROBESON, CLEVELAND, ANSON, GASTON, POLK, SCOTLAND, HENDERSON, RICHMOND, RUTHERFORD, MECKLENBURG, BRUNSWICK, BUNCOMBE, UNION | US 74 | NCDOT | I-40 IN ASHEVILLE TO I-140 IN WILMINGTON. IMPLEMENT BROADBAND, ITS, AND RESILIENCY IMPROVEMENTS. | 279.24 | Highway | Other | 3, 6, 8, 10, 12, 13, 14 | Lumber River RPO, Cape Fear RPO, Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO | HO-0002 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS.
CRAVEN | WEBB BOULEVARD | HAVELOCK | NORTH OF METHODIST DRIVE IN HAVELOCK. CONSTRUCT APPROXIMATELY 550 FEET OF SIDEWALK ON EAST SIDE. |  | Bike & Ped | Locally Selected | 2 | Down East RPO | BN-0020 | Exempt | CRP550, L(M) |  |  |  |  | 2026 | 396000 | 2025 | 80000 | 476000
CRAVEN | SR 1763 (CHURCH ROAD) | HAVELOCK | SOUTH OF US 70 INTERSECTION IN HAVELOCK. CONSTRUCT APPROXIMATELY 580 FEET OF SIDEWALK ON THE WEST SIDE. | 0.11 | Bike & Ped | Locally Selected | 2 | Down East RPO | BN-0021 | Exempt | CRP550, L(M) | 2025 | 5000 |  |  | 2026 | 125000 | 2025 | 50000 | 180000
CRAVEN | INTEGRATED MOBILITY DIVISION | NCDOT | CHERRY BRANCH FERRY TERMINAL - RURAL FERRY PROGRAM |  | Ferry | Other | 2 | Down East RPO | FO-0001 | Public Transit | FSRC, T | [6 empty] | 2024 | 500000 | 500000
CRAVEN | ROAD) SR 1470 (MAPLE CYPRESS | NCDOT | REPLACE BRIDGE 240138 AND 240139 OVER NEUSE RIVER. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-4484 | Division 2 | T |  |  |  |  | 2021 | 18700000 |  |  | 18700000 | UNDER CONSTRUCTION.
CRAVEN | NC 43 CONNECTOR | NCDOT | US 70 TO NC 43/NC 55. |  | Highway | Economic Development | 2 | New Bern Area MPO | R-4463B | [11 empty] | COMPLETED. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOSCH CORPORATION.
CRAVEN | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE NEW BERN PLANNING ORGANIZATION. |  | Highway | Locally Selected | 2 | New Bern Area MPO | HL-0104 | Exempt | CRPDA, L |  |  |  |  | 2023 | 899000 |  |  | 899000
CRAVEN | US 17 | NCDOT | MILLS STREET IN BRIDGETON TO NORTH "C" STREET. |  | Highway | Pre-STI (Historic) | 2 | Down East RPO | R-3403AA | [11 empty] | COMPLETED.
CRAVEN | US 17 | NCDOT | NORTH "C" STREET TO NORTH OF SR 1433 (ANTIOCH ROAD). |  | Highway | Pre-STI (Historic) | 2 | Down East RPO | R-3403AB | [11 empty] | COMPLETED.
CRAVEN | NC 43 CONNECTOR | NCDOT | NC 43/NC 55 TO US 17 IN NEW BERN. CONSTRUCT ROUTE ON NEW LOCATION WITH INTERCHANGE AT US 70. | 4.2 | Highway | Pre-STI (Historic) | 2 | New Bern Area MPO | R-4463
CRAVEN | SR 1001 / SR 1256 (MAIN STREET) | NCDOT | AT SR 1005 (SUNSET BOULEVARD). INSTALL ALL WAY STOP, REVISE OVERHEAD FLASHER, AND INSTALL CHANNELIZATION. | 1 | Highway | Safety | 2 | Down East RPO | HS-2002F | Division 2 | HSIP | 2022 | 15000 |  |  | 2025 | 58000 |  |  | 73000 | RIGHT-OF-WAY IN PROGRESS.
CRAVEN | US 17 BUSINESS (MARTIN LUTHER KING JR. BOULEVARD) | NCDOT | US 17 BUSINESS (MARTIN LUTHER KING JR. BOULEVARD) AT TRENT CREEK ROAD. INSTALL FLASHER. | 0.5 | Highway | Safety | 2 | New Bern Area MPO | HS-2002O | Region B | HSIP |  |  |  |  | 2023 | 42000 |  |  | 42000 | UNDER CONSTRUCTION.
CRAVEN | NC 55 (NEUSE BOULEVARD) | NCDOT | AT SR 1215 (SIMMONS STREET) IN NEW BERN. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 0.5 | Highway | Safety | 2 | New Bern Area MPO | HS-2002V | Region B | HSIP |  |  |  |  | 2024 | 18000 |  |  | 18000
CRAVEN | NC 55 (NEUSE BOULEVARD) | NCDOT | AT SR 1309 / SR 1402 (GLENBURNIE ROAD) IN NEW BERN. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 0.5 | Highway | Safety | 2 | New Bern Area MPO | HS-2002W | Region B | HSIP |  |  |  |  | 2024 | 18000 |  |  | 18000
CRAVEN | NC 55 (NEUSE BOULEVARD) | NCDOT | AT FORT TOTTEN DRIVE AND FIRST STREET INTERSECTIONS IN NEW BERN. INSTALL PEDESTRIAN HEADS AT FORT TOTTEN DRIVE. UPGRADE BOTH TRAFFIC SIGNALS. | 0.5 | Highway | Safety | 2 | New Bern Area MPO | HS-2002Y | Region B | HSIP |  |  |  |  | 2024 | 76000 |  |  | 76000
CRAVEN | US 70 (HAVELOCK BYPASS) | NCDOT | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 10.1 | Highway | STI (Prioritization) | 2 | Down East RPO, New Bern Area MPO | R-1015 | [11 empty] | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8M FOR RIGHT-OF-WAY, $2.2M FOR UTILITIES, AND $100M FOR CONSTRUCTION, PAYBACK FY 2019 - 2033.
CRAVEN | US 70 (HAVELOCK BYPASS) | NCDOT | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-1015DIV | Division 2 | NHP, T(M) | 2019 | 2603000 | 2019 | 1517000 | 2019 | 114172000 |  |  | 118292000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
CRAVEN | US 70 (HAVELOCK BYPASS) | NCDOT | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-1015REG | Region B | NHP, T(M) | 2019 | 2603000 | 2019 | 1517000 | 2019 | 105707000 |  |  | 109827000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
CRAVEN | US 17 | NCDOT | NC 43 TO SR 1438 (SPRUILL TOWN ROAD). WIDEN TO MULTI-LANES. | 15.2 | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513
CRAVEN | US 17 | NCDOT | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | 1.86 | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513A | Division 2 | T | 2030 | 3001000 | 2030 | 2400000 | 2033 | 24600000 |  |  | 30001000
CRAVEN | US 17 | NCDOT | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). |  | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513B | Not Funded | T | NOT FUNDED | 5800000 | NOT FUNDED | 800000 | NOT FUNDED | 16300000 | NOT FUNDED |  | 22900000
CRAVEN | US 17 | NCDOT | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). |  | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513C | Not Funded | T | NOT FUNDED | 2300000 | NOT FUNDED | 600000 | NOT FUNDED | 11300000 | NOT FUNDED |  | 14200000
CRAVEN | US 17 | NCDOT | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. |  | Highway | STI (Prioritization) | 2 | Down East RPO | R-2513D | Not Funded | T | NOT FUNDED | 4600000 | NOT FUNDED | 600000 | NOT FUNDED | 21000000 | NOT FUNDED |  | 26200000
CRAVEN | US 17 | NCDOT | MILLS STREET IN BRIDGETON TO NC 43. WIDEN TO MULTI-LANES. | 9.8 | Highway | STI (Prioritization) | 2 | Down East RPO, New Bern Area MPO | R-3403 | Region B
CRAVEN | US 17 | NCDOT | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | 7.19 | Highway | STI (Prioritization) | 2 | Down East RPO, New Bern Area MPO | R-3403B | Region B | T | 2030 | 5999000 | 2030 | 4100000 | 2033 | 129100000 |  |  | 139199000
CRAVEN | NC 43 CONNECTOR | NCDOT | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2.29 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-4463A | Region B | T | 2020 | 8023000 | 2023 | 1350000 | 2026 | 43400000 | 2020 | 1725000 | 54498000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
CRAVEN | US 70 | NCDOT | SR 1124 (GRANTHAM ROAD) TO THE PROPOSED US 70 HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY. | 8.6 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-5777
CRAVEN | US 70 | NCDOT | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-5777A | Statewide Mobility | T | 2020 | 47438000 | 2020 | 300000 | 2020 | 50778000 |  |  | 98516000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713.
CRAVEN | US 70 | NCDOT | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-5777B | Region B | T | 2020 | 47447000 | 2020 | 300000 | 2020 | 50778000 | 2020 | 105000 | 98630000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
CRAVEN | US 70 | NCDOT | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | 6.88 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | R-5777C | Statewide Mobility | T | 2023 | 49129000 | 2023 | 20586000 | 2023 | 278703000 |  |  | 348418000 | RIGHT-OF-WAY IN PROGRESS.
CRAVEN | NC 101 / SR 1763 (FONTANA BOULEVARD / MILLER BOULE | NCDOT | FROM SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. SR 1756 (LAKE ROAD) FROM SR 1763 (MILLER BOULEVARD) TO HAVELOCK BYPASS. CONSTRUCT ROAD IMPROVEMENTS. | 3.05 | Highway | STI (Prioritization) | 2 | Down East RPO | U-3431 | Division 2 | T | 2027 | 17301000 | 2027 | 3000000 | 2030 | 91500000 |  |  | 111801000
CRAVEN | US 70 | NCDOT | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | 1.8 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | U-5713 | Statewide Mobility | T | 2020 | 88668000 | 2020 | 1000000 | 2020 | 152337000 |  |  | 242005000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND R-5777B.
CRAVEN | NC 55 (NEUSE BOULEVARD) | NCDOT | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | 0.5 | Highway | STI (Prioritization) | 2 | New Bern Area MPO | U-5993 | Region B | T | 2027 | 790000 |  |  | 2030 | 5700000 |  |  | 6490000
CRAVEN | NC 43 CONNECTOR | NCDOT | SOUTH OF US17/US 70 TO US 70. | 2.5 | Highway | Transition | 2 | New Bern Area MPO | R-4463AA | [11 empty] | COMPLETED.
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | TA-5165 RURAL VEHICLE REPLACEMENT. |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | New Bern Area MPO | TA-5165 | Public Transit | 5307, L | [6 empty] | 2020 | 463000 | 463000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | MOBILITY MANAGEMENT |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | New Bern Area MPO | TC-5100 | Public Transit | 5307, L | [6 empty] | 2023 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | LEASE OF TABLETS |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | New Bern Area MPO | TT-5206 | Public Transit | 5307, L | [6 empty] | 2020 | 36000 | 36000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE. |  | Public Transportation (Transit) | Miscellaneous/Other | 2 | New Bern Area MPO | TO-5024 | Public Transit | 5307, L | [6 empty] | 2023 | 2350000 | 2350000
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 2 | New Bern Area MPO | TO-5204 | Public Transit | 5307, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 2 | Down East RPO | TO-6102 | Public Transit | 5311, L | [6 empty] | 2020 | 344000 | 344000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Down East RPO | TK-6122 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1356000 | 1356000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | SHORT RANGE PLANNING |  | Public Transportation (Transit) | Planning | 2 | New Bern Area MPO | TP-5122 | Public Transit | 5307, L | [6 empty] | 2020 | 30000 | 30000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CARTS | CARTS | TG-5026 LEASE OF TABLETS |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 2 | New Bern Area MPO | TG-5026 | Public Transit | 5307, L | [6 empty] | 2022 | 0
CRAVEN | CARTS | CARTS | TG-5122 SHORT RANGE PLANNING |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 2 | New Bern Area MPO | TG-5122 | Public Transit | 5307, L | [6 empty] | 2023 | 0
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 2 | New Bern Area MPO | TG-5256 | Public Transit | 5307, L | [6 empty] | 2020 | 170000 | 170000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | ADA/PARATRANSIT |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 2 | New Bern Area MPO | TG-5257 | Public Transit | 5307, L | [6 empty] | 2020 | 313000 | 313000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN, JOHNSTON, WAYNE, LENOIR, CARTERET, WAKE | US 70 | NCDOT | INSTALL BROADBAND FIBER ALONG US 70 FROM I-40 TO PORT OF MOREHEAD CITY. | 138.47 | Highway | STI (Prioritization) | 2, 4, 5 | Down East RPO, Eastern Carolina RPO, New Bern Area MPO, Upper Coastal Plain RPO, Goldsboro Urban Area MPO, Capital Area MPO | R-5777D | Statewide Mobility | DP, T |  |  |  |  | 2021 | 33500000 |  |  | 33500000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5986C, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
CRAVEN, JONES, BEAUFORT | US 17 | NCDOT | 1.1 MILES NORTH OF ONSLOW COUNTY LINE TO 2000 FEET SOUTH OF NC 58 IN JONES COUNTY; 0.25 MILES NORTH OF SR 1433 (ANTIOCH ROAD) TO 0.3 MILES NORTH OF SR 1134 (OLD NEW BERN ROAD) IN BEAUFORT COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 26.5 | Highway | Safety | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO | HS-2402B | Statewide Mobility | HSIP |  |  |  |  | 2025 | 655000 |  |  | 655000
CUMBERLAND | FAYETTEVILLE REGIONAL AIRPORT | FAYETTEVILLE REGIONAL AIRPORT | EXTEND RUNWAY 10/28. |  | Aviation | STI (Prioritization) | 6 | Fayetteville Area MPO | AP-0002 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | 2400000
CUMBERLAND | FAYETTEVILLE REGIONAL AIRPORT | FAYETTEVILLE REGIONAL AIRPORT | EXTEND RUNWAY 4/22. |  | Aviation | STI (Prioritization) | 6 | Fayetteville Area MPO | AP-0003 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | 2400000
CUMBERLAND | FAYETTEVILLE REGIONAL AIRPORT | FAYETTEVILLE REGIONAL AIRPORT | UPGRADE PAVEMENT AND PAINT THE GENERAL AVIATION APRON ON CONTROL TOWER ROAD. |  | Aviation | STI (Prioritization) | 6 | Fayetteville Area MPO | AP-0004 | Region C | O, T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 |  |  | 2300000 | O FUNDS REPRESENT FUNDING FROM FAYETTEVILLE REGIONAL AIRPORT.
CUMBERLAND | REGIONAL AIRPORT (FAY) FAYETTEVILLE | FAYETTEVILLE REGIONAL AIRPORT (FAY) | REPLACE PERIMETER FENCING AND ROAD. |  | Aviation | STI (Prioritization) | 6 | Fayetteville Area MPO | AV-5734 | Region C | O, T |  |  |  |  | 2026 | 3440000 |  |  | 3440000
CUMBERLAND | SR 1131 (CAMERON ROAD) | HOPE MILLS | FROM HOPE MILLS MIDDLE SCHOOL TO NC 59 (SOUTH MAIN STREET) IN HOPE MILLS. INSTALL NEW CONCRETE SIDEWALK. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0130 | Division 6 | L(M), TADA | 2026 | 25000 |  |  | 2027 | 524000 | 2025 | 25000 | 574000
CUMBERLAND | CAPE FEAR RIVER TRAIL | FAYETTEVILLE | IN FAYETTEVILLE. CONSTRUCT 10 FOOT WIDE MULTI-USE PATH. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0131 | Division 6 | L(M), TADA | 2025 | 50000 |  |  | 2026 | 1100000 | 2025 | 220000 | 1370000
CUMBERLAND | CAPE FEAR RIVER TRAIL | FAYETTEVILLE | FAYETTEVILLE TO COUNTY LINE (ARNETTE PARK). CONSTRUCT 10 FOOT MULTI-USE PATH. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0132 | Division 6 | L(M), TADA | 2025 | 50000 |  |  | 2026 | 1100000 | 2025 | 220000 | 1370000
CUMBERLAND | CAPE FEAR RIVER TRAIL | FAYETTEVILLE | ALONG MILAN ROAD AND EUFAULA ROAD IN FAYETTEVILLE. CONSTRUCT EXTENSION TO CAPE FEAR RIVER TRAIL. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0133 | Division 6 | BGDA, L(M) | 2026 | 500000 |  |  | 2027 | 2051000 | 2025 | 146000 | 2697000
CUMBERLAND | EAST SHORE TRAIL | FAYETTEVILLE | FROM ESSEX PLACE TO COLEY DRIVE AND MURCHISON ROAD INTERSECTION ALONG GLENVILLE LAKE IN FAYETTEVILLE. CONSTRUCT 10 FOOT MULTI-USE PATH INCLUDING SIDEWALK CONNECTIONS ALONG MATTHEWS STREET AND FROM COLEY DRIVE TO MURCHISON ROAD. |  | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0134 | Division 6 | BGDA, L(M) | 2025 | 77000 |  |  | 2026 | 1686000 | 2025 | 337000 | 2100000
CUMBERLAND | VARIOUS | FAYETTEVILLE | LOCATIONS IN FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, RETAINING WALL AND BUS PAD UPGRADES. | 5.35 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0137 | Division 6 | BGDA, L(M) | 2025 | 350000 |  |  | 2026 | 2050000 | 2025 | 300000 | 2700000
CUMBERLAND | NC162 (BUNCE ROAD / BINGHAM DRIVE SR 1400 (CLIFFDA | FAYETTEVILLE | RAEFORD ROAD TO REILLY ROAD ; LAKERIDGE DRIVE TO RAEFORD ROAD IN WEST FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, AND BUS PAD UPGRADES. | 4.9 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | BL-0138 | Division 6 | BGDA, L(M) | 2025 | 200000 |  |  | 2026 | 2050000 | 2025 | 200000 | 2450000
CUMBERLAND | US 401 BYPASS (SKIBO ROAD) | FAYETTEVILLE | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 2.73 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-6030 | Division 6 | L, TADA | 2024 | 100000 |  |  | 2025 | 1500000 | 2022 | 75000 | 1675000
CUMBERLAND | US 401 (RAMSEY STREET) | FAYETTEVILLE | CONSTRUCT SIDEWALK FROM SUMMERCHASE DRIVE TO SR 1611 (ANDREWS ROAD). | 0.17 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-6031 | Division 6 | L, TADA |  |  |  |  | 2021 | 85000 |  |  | 85000 | COMPLETED.
CUMBERLAND | NC 59 (HOPE MILLS ROAD) | FAYETTEVILLE | CONSTRUCT SIDEWALK FROM FAYETTEVILLE CITY LIMITS TO SUMAC CIRCLE. | 1.32 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-6032 | Division 6 | L, TADA |  |  |  |  | 2022 | 375000 |  |  | 375000 | COMPLETED.
CUMBERLAND | SPRING LAKE | FAYETTEVILLE | CONSTRUCT 5-MILES OF UNPAVED GREENWAY TRAIL BETWEEN CHAPEL HILL ROAD AND THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 5 | Bike & Ped | Locally Selected | 6 | Fayetteville Area MPO | EB-6041 | Division 6 | BGDA, L, TADA | 2025 | 128000 |  |  | 2020 | 2080000 | 2025 | 238000 | 2446000 | UNDER CONSTRUCTION.
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | CAPE FEAR RIVER GREENWAY, CLARK PARK SOUTH TO THE CAPE FEAR BOTANICAL GARDENS. CONSTRUCT SECOND PHASE OF AN OFF-ROAD MULTI-USE TRAIL. |  | Bike & Ped | Pre-STI (Historic) | 6 | Fayetteville Area MPO | EB-4539 | Pre-STI (Transition)
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | I-95 BUSINESS/US 301 TO THE SOUTH SIDE OF CSX RAIL LINE. | 1.23 | Bike & Ped | Pre-STI (Historic) | 6 | Fayetteville Area MPO | EB-4539A | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION.
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | EXISTING TRAIL AT CLARK PARK TO NORTH SIDE OF CSX RAIL LINE. | 1.26 | Bike & Ped | Pre-STI (Historic) | 6 | Fayetteville Area MPO | EB-4539BB | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION.
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | NORTH OF CSX RAIL LINE TO SOUTH OF CSX RAIL LINE. | 0.27 | Bike & Ped | Pre-STI (Historic) | 6 | Fayetteville Area MPO | EB-4539BC | Pre-STI (Transition) | L, TAANY |  |  |  |  | 2020 | 951000 |  |  | 951000 | UNDER CONSTRUCTION.
CUMBERLAND | BLOUNTS CREEK GREENWAY | NCDOT | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | Bike & Ped | STI (Prioritization) | 6 | Fayetteville Area MPO | BP-0001 | Division 6 | L(M), TAANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 86000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1195000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 253000 | 1544000 | BLOUNTS CREEK PHASE III
CUMBERLAND | LITTLE CROSS CREEK GREENWAY EXTENSION | FAYETTEVILLE | FILTER PLANT DRIVE TO ROWAN STREET BRIDGE IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.75 | Bike & Ped | STI (Prioritization) | 6 | Fayetteville Area MPO | EB-5540 | Division 6 | L, TAANY |  |  |  |  | 2027 | 750000 |  |  | 750000
CUMBERLAND | BIG CROSS CREEK GREENWAY | FAYETTEVILLE | LITTLE CROSS CREEK TO 295 FOR A POSSIBLE FUTURE CONNECTION TO FORT LIBERTY TRAILS OUTSIDE OF FORT LIBERTY. CONSTRUCT MULTIUSE TRAIL. |  | Bike & Ped | STI (Prioritization) | 6 | Fayetteville Area MPO | EB-5541 | Not Funded | L(M), TADA | NOT FUNDED |  | NOT FUNDED |  | NOT FUNDED |  | NOT FUNDED | 475000 | 475000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY USING STBGDA FUNDS.
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 0.94 | Bike & Ped | STI (Prioritization) | 6 | Fayetteville Area MPO | EB-5907 | Division 6 | L, TAANY | 2026 | 630000 |  |  | 2028 | 800000 | 2023 | 84000 | 1514000
CUMBERLAND | NC 59 | NCDOT | REPLACE BRIDGE 250022 OVER I-95 BUSINESS/US 301. | 0.25 | Highway | Bridges | 6 | Fayetteville Area MPO | B-4491 | Region C | NHPB |  |  |  |  | 2018 | 3533000 |  |  | 3533000 | COMPLETED.
CUMBERLAND | SR 1716 (JACKIE LEE ROAD) | NCDOT | REPLACE BRIDGE 250091 OVER WADE CANAL. | 0.25 | Highway | Bridges | 6 | Fayetteville Area MPO | HB-0010 | Division 6 | BGOFF | 2028 | 120000 |  |  | 2030 | 850000 |  |  | 970000
CUMBERLAND | FAYETTEVILLE | NCDOT | CONSTRUCT NEW ACCESS ROAD WITH IMPROVEMENTS AT INTERSECTION WITH SR 1838 (DUNN ROAD) IN FAYETTEVILLE. | 0.2 | Highway | Economic Development | 6 | Fayetteville Area MPO | HE-0012 | Division 6 | T | 2023 | 20000 | 2023 | 50000 | 2023 | 1100000 |  |  | 1170000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC.
CUMBERLAND | SR 1711 (BETHUNE DRIVE) | NCDOT | EAST OF US 401 INTERSECTION IN FAYETTEVILLE. PART OF ROUTE ON NEW LOCATION. INSTALL SIGNAL AT US 401 (RAMSEY STREET) INTERSECTION AND EXTEND SR 1711 (BETHUNE DRIVE). |  | Highway | Economic Development | 6 | Fayetteville Area MPO | HE-0017 | Division 6 | T | 2026 | 300000 | 2026 | 700000 | 2027 | 6900000 | 2025 | 800000 | 8700000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL.
CUMBERLAND | I-95 | NCDOT | I-95 FROM THE ROBESON COUNTY LINE TO NC 53/210. PAVEMENT REHABILITATION. | 10.28 | Highway | Interstate Maintenance | 6 | Fayetteville Area MPO | HI-0021 | Statewide Mobility | NHPIM |  |  |  |  | 2029 | 7999000 |  |  | 7999000
CUMBERLAND | I-95 | NCDOT | I-95 FROM NC 53 TO I-95 BUSINESS / US 301. PAVEMENT REHABILITATION. | 8.92 | Highway | Interstate Maintenance | 6 | Fayetteville Area MPO | HI-0022 | Statewide Mobility | NHPIM |  |  |  |  | 2029 | 5800000 |  |  | 5800000
CUMBERLAND | NC 59 (NORTH MAIN STREET) | HOPE MILLS | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW MULTI-USE PATH ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 1.5 | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0036 | Division 6 | L, TADA |  |  |  |  | 2024 | 768000 | 2021 | 50000 | 818000
CUMBERLAND | NC 24 | FAYETTEVILLE | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0143 | Region C | BGDA, HF(M) | 2026 | 200000 | 2026 | 100000 | 2028 | 350000 | 2025 | 75000 | 725000
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | FAYETTEVILLE | NEAR ROCKFISH ELEMENTRAY SCHOOL. CONSTRUCT ADDITIONAL RIGHT TURN LANE ON SR 1112 (ROCKFISH ROAD). |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0145 | Division 6 | BGDA, HF(M) | 2026 | 100000 |  |  | 2028 | 2752000 | 2025 | 250000 | 3102000
CUMBERLAND | NC 24 | NCDOT | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO SR 1853 (JOHN NUNNERY ROAD). | 6.15 | Highway | Pre-STI (Historic) | 6 | Mid-Carolina RPO, Fayetteville Area MPO | R-2303A | Pre-STI (Transition) | [10 empty] | COMPLETED.
CUMBERLAND | I-295 | NCDOT | EAST OF SR 1415 (YADKIN ROAD) TO WEST OF NC24/NC 87 (BRAGG BOULEVARD). |  | Highway | Pre-STI (Historic) | 6 | Fayetteville Area MPO | U-2519DA | [11 empty] | COMPLETED.
CUMBERLAND | SR 1415 (YADKIN ROAD) | NCDOT | SR 1415 (YADKIN ROAD) AT US 401 (SKIBO ROAD), AT SR 1437 (SANTE FE DRIVE), AND AT SOUTHWICK DRIVE. ADD SIGNALIZED PEDESTRIAN CROSSINGS TO ALL THREE INTERSECTIONS AND UPGRADE SIGNAL AT SOUTHWICK DRIVE. | 1 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006A | Division 6 | HSIP, TADA |  |  |  |  | 2024 | 1450000 |  |  | 1450000
CUMBERLAND | SR 1006 (PERSON STREET) | NCDOT | SR 1006 (PERSON STREET) FROM US 301 / I-95 BUSINESS (EASTERN BOULEVARD) TO JUST EAST OF WATER STREET. CONVERT SECTION FROM FOUR LANES TO THREE LANES WITH INTERSECTION IMPROVEMENTS AT BROAD STREET AND EASTERN BOULEVARD IN FAYETTEVILLE. | 0.34 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006B | Division 6 | HSIP |  |  |  |  | 2022 | 651000 |  |  | 651000 | UNDER CONSTRUCTION.
CUMBERLAND | NC 53 (CEDAR CREEK ROAD) | NCDOT | NC 53 (CEDAR CREEK ROAD) FROM JUST NORTH OF PLYMOUTH STREET TO JUST SOUTH OF TROY DRIVE. INSTALL MEDIAN WITH SOUTHBOUND U-TURN AND BULB-OUT, SIDEWALK, AND RECTANGULAR RAPID FLASHING BEACON PEDESTRIAN CROSSING WITH REFUGE IN FAYETTEVILLE. | 0.21 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006C | Region C | HSIP | 2023 | 210000 |  |  | 2024 | 1631000 |  |  | 1841000 | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND | SR 1835 (ROCK HILL ROAD) | NCDOT | SR 1835 (ROCK HILL ROAD) AT SR 1838 (DUNN ROAD) IN EASTOVER. REALIGN SR 1838 (DUNN ROAD) TO FORM A T-INTERSECTION WITH SR 1835 (ROCK HILL ROAD) AND REMOVE SLIP LANES. | 0.15 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006G | Division 6 | HSIP |  |  |  |  | 2023 | 282000 |  |  | 282000 | UNDER CONSTRUCTION.
CUMBERLAND | SR 1596 (GLENSFORD DRIVE) | NCDOT | FROM US 401 (RAEFORD ROAD) AND SR 1400 (CLIFFDALE ROAD) IN FAYETTEVILLE. PAVEMENT MARKING AND SIGNING IMPROVEMENTS. | 1.16 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006N | Division 6 | HSIP |  |  |  |  | 2025 | 81000 |  |  | 81000
CUMBERLAND | SR 1596 (GLENSFORD DRIVE) | NCDOT | SR 1596 (GLENSFORD DRIVE) AT BEREAN BAPTIST ACADEMY AND AT CHAMBERSURG ROAD IN FAYETTEVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS WITH REFUGE ISLANDS. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006O | Division 6 | HSIP |  |  |  |  | 2025 | 334000 |  |  | 334000
CUMBERLAND | SR 3950 (RAMSEY STREET) | NCDOT | SR 3950 (RAMSEY STREET) AT RAILROAD BRIDGE 250216 IN FAYETTEVILLE. INSTALL GUARDRAIL. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006P | Division 6 | HSIP |  |  |  |  | 2025 | 250000 |  |  | 250000
CUMBERLAND | SR 1600 (MCARTHUR ROAD) | NCDOT | SR 1600 (MCARTHUR ROAD) AT SR 1615 (ROSEHILL ROAD/STACY WEAVER ROAD) IN FAYETTEVILLE. CONSTRUCT SIGNALIZED PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006V | Division 6 | HSIP |  |  |  |  | 2024 | 1450000 |  |  | 1450000
CUMBERLAND | US 401 (SKIBO ROAD) | NCDOT | AT SR 1007 (ALL AMERICAN FREEWAY) NORTHBOUND AND SOUTHBOUND RAMPS IN FAYETTEVILLE. INSTALL SIGNALIZED PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006X | Statewide Mobility | HSIP |  |  |  |  | 2024 | 1450000 |  |  | 1450000
CUMBERLAND | SR 1414 (BROADFOOT ROAD) | NCDOT | SR 1414 (RAEFORD ROAD/BROADFOOT AVENUE) AT ARSENAL AVENUE IN FAYETTEVILLE. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNAL HEAD. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006Z | Division 6 | HSIP |  |  |  |  | 2024 | 390000 |  |  | 390000
CUMBERLAND | US 401 (RAMSEY STREET) | NCDOT | AT NORTHGATE SHOPPING CENTER IN FAYETTEVILLE. INSTALL CROSSWALK, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, AND UPGRADE TRAFFIC SIGNAL. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406C | Region C | HSIP |  |  |  |  | 2025 | 330000 |  |  | 330000
CUMBERLAND | US 401 BUSINESS (RAMSEY STREET) | NCDOT | LANGDON STREET AND COLONIAL DRIVE INTERSECTIONS IN FAYETTEVILLE. INSTALL CROSSWALK, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, AND UPGRADE TRAFFIC SIGNAL. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406D | Region C | HSIP |  |  |  |  | 2025 | 280000 |  |  | 280000
CUMBERLAND | US 401 (RAMSEY STREET) | NCDOT | TREETOP DRIVE INTERSECTION IN FAYETTEVILLE. INSTALL / UPGRADE CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, AND UPGRADE TRAFFIC SIGNAL. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406F | Region C | HSIP |  |  |  |  | 2025 | 200000 |  |  | 200000
CUMBERLAND | US 401 (SKIBO ROAD) | NCDOT | SR 1400 (CLIFFDALE ROAD) INTERSECTION IN FAYETTEVILLE. REVISE TRAFFIC SIGNAL, AND INSTALL CROSSWALKS AND PEDESTRIAN SIGNAL HEADS. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406O | Region C | HSIP |  |  |  |  | 2025 | 260000 |  |  | 260000
CUMBERLAND | US 401 BUSINESS (ROBESON STREET) | NCDOT | SR 1168 (WHITFIELD STREET) INTERSECTION IN FAYETTEVILLE. REVISE TRAFFIC SIGNAL, AND INSTALL CROSSWALKS AND PEDESTRIAN SIGNAL HEADS. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406P | Region C | HSIP |  |  |  |  | 2026 | 180000 |  |  | 180000
CUMBERLAND | SR 1404 (MORGANTON ROAD) | NCDOT | MCPHERSON CHURCH ROAD. INSTALL/UPGRADE CROSSWALKS, CROSSWALK RAMPS SIGNALIZED PEDESTRIAN HEADS, AND TRAFFIC SIGNAL. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406R | Division 6
CUMBERLAND | US 401 (SKIBO ROAD) | NCDOT | NC 24-87 (BRAGG BOULEVARD) EASTBOUND RAMPS (SWAIN STREET). INSTALL/UPGRADE CROSSWALKS AND TRAFFIC SIGNAL. |  | Highway | Safety | 6 | Fayetteville Area MPO | HS-2406S | Statewide Mobility
CUMBERLAND | NC 24 (BRAGG BOULEVARD) | NCDOT | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | 2.53 | Highway | Safety | 6 | Fayetteville Area MPO | U-6229 | Division 6 | HSIP, T |  |  | 2022 | 200000 | 2023 | 7672000 |  |  | 7872000 | UNDER CONSTRUCTION.
CUMBERLAND | VARIOUS | NCDOT | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 6 | Fayetteville Area MPO | W-5206DIV | Division 6
CUMBERLAND | VARIOUS | NCDOT | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 6 | Fayetteville Area MPO | W-5206SW | Statewide Mobility
CUMBERLAND | I-95 BUSINESS/US 301 | NCDOT | NC 87 SOUTH TO NC 59. SAFETY IMPROVEMENTS. | 7.29 | Highway | Safety | 6 | Fayetteville Area MPO | W-5519 | Region C | [10 empty] | COMPLETED.
CUMBERLAND | SR 1404 (HAY STREET / MORGANTON ROAD) | NCDOT | AT THE SR 3578 (FORT BRAGG ROAD), OAKRIDGE AVENUE, AND HIGHLAND AVENUE INTERSECTION IN FAYETTEVILLE. UPGRADE TRAFFIC SIGNALS AND IMPROVE PEDESTRIAN CROSSINGS. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | W-5706U | Division 6 | HSIP |  |  |  |  | 2025 | 100000 |  |  | 100000
CUMBERLAND | SR 1615 (ROSEHILL ROAD) | NCDOT | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | 0.5 | Highway | Safety | 6 | Fayetteville Area MPO | W-5806C | Division 6 | HSIP | 2021 | 75000 |  |  | 2023 | 3113000 |  |  | 3188000 | UNDER CONSTRUCTION.
CUMBERLAND | US 401 BYPASS (PAMALEE DRIVE) | NCDOT | NC 24 / 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). CONSTRUCT RAISED CENTER MEDIAN WITH ACCESS MANAGEMENT IMPROVEMENTS. | 2.32 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0015 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 23200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28400000 |  |  | 70500000
CUMBERLAND | I-295 | NCDOT | SOUTH OF SR 1118 (PARKTON ROAD) TO SOUTH OF SR 1003 (CAMDEN ROAD). | 4.88 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO, Lumber River RPO | U-2519AB | Region C | [10 empty] | DESIGN BUILD PROJECT. WORK BEING ACCOMPLISHED UNDER U-2519AA.
CUMBERLAND | I-295 | NCDOT | SOUTH OF SR 1003 (CAMDEN ROAD) TO SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD). | 3.96 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519BA | Region C | NHP |  |  |  |  | 2022 | 161113000 |  |  | 161113000 | UNDER CONSTRUCTION.
CUMBERLAND | I-295 | NCDOT | SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD) TO SOUTH OF US 401. | 0.79 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519BB | Region C | [10 empty] | UNDER CONSTRUCTION. FUNDING AUTHORIZED UNDER U-2519BA.
CUMBERLAND | I-295 | NCDOT | SOUTH OF US 401 TO SOUTH OF SR 1400 (CLIFFDALE ROAD). | 2.63 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519CA | Statewide Mobility | NHP | 2024 | 10000 | [6 empty] | 10000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT.
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NCDOT | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO SR 1596 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO FOUR LANES. | 3.52 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-3422 | Division 6 | BGANY | 2021 | 16175000 | 2021 | 5225000 |  |  |  |  | 21400000 | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NCDOT | FROM PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO JUST WEST OF SR 1112 (ROCKFISH ROAD). | 1.53 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-3422A | Division 6 | O, T |  |  |  |  | 2025 | 31795000 |  |  | 31795000 | O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE).
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NCDOT | FROM JUST WEST OF SR 1112 (ROCKFISH ROAD) TO SR 1596 (HOPE MILLS ROAD). | 1.99 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-3422B | Division 6 | O, T |  |  |  |  | 2027 | 67601000 |  |  | 67601000 | O FUNDS REPRESENT WET UTILITY PAYBACK FROM PWC. BULD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $15,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE).
CUMBERLAND | US 401 (RAMSEY STREET) | NCDOT | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO NORTH OF SLOCUMB ROAD. WIDEN TO MULTI-LANES. | 8.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4403
CUMBERLAND | US 401 BUSINESS | NCDOT | NC 24/210 (GROVE STREET) TO US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY). |  | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4403A | Not Funded | T | NOT FUNDED | 3121000 | NOT FUNDED |  | NOT FUNDED | 7400000 | NOT FUNDED |  | 10521000
CUMBERLAND | US 401 BUSINESS | NCDOT | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | 2.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4403B | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39000000 |  |  | 65300000
CUMBERLAND | US 401 | NCDOT | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | 5.08 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4403C | Division 6 | T | 2030 | 23400000 | 2030 | 20900000 | 2033 | 55300000 |  |  | 99600000
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | NCDOT | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | 0.94 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4404 | Division 6 | T | 2029 | 39000000 | 2029 | 5400000 | 2032 | 29500000 |  |  | 73900000
CUMBERLAND | US 401 (RAEFORD ROAD) | NCDOT | SR 3569 (OLD RAEFORD ROAD) TO EAST OF SR 3828 (ROBESON STREET) IN FAYETTEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 6 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4405 | Division 6 | [10 empty] | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND | US 401 (RAEFORD ROAD) | NCDOT | OLD RAEFORD ROAD TO EAST OF BUNCE ROAD. | 2.22 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4405A | Division 6 | BGANY |  |  |  |  | 2022 | 35403000 |  |  | 35403000 | UNDER CONSTRUCTION.
CUMBERLAND | US 401 (RAEFORD ROAD) | NCDOT | EAST OF BUNCE ROAD TO EAST OF BRIGHTON ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.61 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4405B | Division 6 | BGANY |  |  |  |  | 2025 | 52600000 |  |  | 52600000
CUMBERLAND | US 401 (RAEFORD ROAD) | NCDOT | EAST OF BRIGHTON ROAD TO EAST OF ROBESON STREET. | 2.38 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4405C | Division 6 | T |  |  |  |  | 2026 | 80195000 |  |  | 80195000 | BUILD NC BOND FUNDING: $20,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $12,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE).
CUMBERLAND | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | NCDOT | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO SR 1596 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO SR 1596 (MAIN STREET). WIDEN TO FOUR LANES. | 1.05 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4709 | Division 6 | T | 2022 | 9556000 | 2022 | 1575000 | 2025 | 26446000 |  |  | 37577000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE).
CUMBERLAND | NC 210 (MURCHISON ROAD) | NCDOT | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | 2.33 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-4900 | Exempt | BGDA, T(M) | 2023 | 10600000 | 2023 | 15000000 | 2026 | 23299000 |  |  | 48899000 | RIGHT-OF-WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT.
CUMBERLAND | SR 1437 (SHAW ROAD) SR 1614 (SHAW MILL ROAD) SR 16 | NCDOT | NC 24 (BRAGG BOULEVARD) TO US 401 (RAMSEY STREET). WIDEN ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 3.6 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5101 | Division 6
CUMBERLAND | SR 1437 (SHAW ROAD) | NCDOT | NC 24 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | 1.89 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5101A | Division 6 | T | 2030 | 10400000 | 2030 | 8800000 | 2033 | 39000000 |  |  | 58200000
CUMBERLAND | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NCDOT | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. |  | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5101B | Not Funded | T | NOT FUNDED | 38500000 | NOT FUNDED | 21445000 | NOT FUNDED | 36300000 | NOT FUNDED |  | 96245000
CUMBERLAND | FAYETTEVILLE | NCDOT | FAYETTEVILLE COMPUTERIZED TRAFFIC SIGNAL SYSTEM. | 0 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5742 | Region C | T |  |  |  |  | 2019 | 735000 |  |  | 735000 | COMPLETED. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
CUMBERLAND | SR 1102 (GILLIS HILL ROAD) | NCDOT | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO FOUR LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | 1.07 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5798A | Division 6 | T | 2020 | 9322000 | 2020 | 475000 | 2022 | 26036000 |  |  | 35833000 | UNDER CONSTRUCTION.
CUMBERLAND | NC 24 (NORTH BRAGG BOULEVARD) | NCDOT | SR 1451 (MANCHESTER ROAD). CONSTRUCT CONTINUOUS FLOW INTERCHANGE. | 1 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5930 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 67500000 |  |  | 97400000
CUMBERLAND | NC 59 (SOUTH MAIN STREET) | NCDOT | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO MULTI-LANES. | 1.19 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6001 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15400000 |  |  | 18100000
CUMBERLAND | SR 1107 (FISHER ROAD) | NCDOT | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | 2.1 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6073 | Division 6 | BGANY | 2030 | 22500000 | 2030 | 2400000 | 2033 | 25101000 |  |  | 50001000
CUMBERLAND | US 401 BUSINESS (SKIBO ROAD) | NCDOT | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6133 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8200000 |  |  | 18900000
CUMBERLAND | US 401 (ROBESON STREET) | NCDOT | US 401 (RAEFORD ROAD) TO NORTH OF WALTER STREET. CONVERT TO FOUR LANE DIVIDED FACILITY. | 2.09 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-6152 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29300000 |  |  | 49600000
CUMBERLAND | I-295 | NCDOT | SOUTH OF SR 1400 (CLIFFDALE ROAD) TO EAST OF SR 1415 (YADKIN ROAD). | 4.69 | Highway | Transition | 6 | Fayetteville Area MPO | U-2519CB | Pre-STI (Transition) | [10 empty] | COMPLETED.
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TA-4743A | Public Transit | 5307, L, S | [6 empty] | 2021 | 225000 | 225000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TA-4743B | Public Transit | 5307, 5339, L, S | [6 empty] | 2021 | 1850000 | 1850000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TA-4948A | Public Transit | 5307, L, S | [6 empty] | 2020 | 2750000 | 2750000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (NON-TRADITIONAL) |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TA-5139 | Public Transit | 5310, L | [6 empty] | 2020 | 500000 | 500000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TP-5103 | Public Transit | 5303, L, S | [6 empty] | 2020 | 264000 | 264000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TS-5109 | Public Transit | 5307, L | [6 empty] | 2020 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES |  | Public Transportation (Transit) | Capital (Non-STI) | 6 | Fayetteville Area MPO | TT-5204 | Public Transit | 5307, L, S | [6 empty] | 2022 | 50000 | 50000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | CITY OF FAYETTEVILLE TRANSIT DEPARTMENT (FAST) | FAYETTEVILLE | IMPLEMENT A CASHLESS FARE SYSTEM ACROSS THE FIXED ROUTE AND PARATRANSIT FLEET. |  | Public Transportation (Transit) | Locally Selected | 6 | Fayetteville Area MPO | TL-0060 | Exempt | CRPDA, L(M) |  |  |  |  | 2025 | 156000 |  |  | 156000
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 6 | Fayetteville Area MPO | TO-5132 | Public Transit | SMAP | [6 empty] | 2020 | 2136000 | 2136000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE (LESS THAN 75 BUSES) MAP 21 |  | Public Transportation (Transit) | Miscellaneous/Other | 6 | Fayetteville Area MPO | TO-5144 | Public Transit | 5307, L | [6 empty] | 2020 | 1600000 | 1600000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | SYSTEM TRANSIT FAYETTEVILLE AREA | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Fayetteville Area MPO | TG-5224A | Public Transit | 5307, L | [6 empty] | 2020 | 6000000 | 6000000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | CUMBERLAND COUNTY | CUMBERLAND COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Mid-Carolina RPO | TK-6123 | Public Transit | 5311, L, S | [6 empty] | 2020 | 320000 | 320000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Fayetteville Area MPO | TP-5103B | Public Transit | 5307, L, S | [6 empty] | 2020 | 1800000 | 1800000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (TRADITIONAL) |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Fayetteville Area MPO | TQ-6514 | Public Transit | 5310, L | [6 empty] | 2020 | 624000 | 624000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 6 | Fayetteville Area MPO | TG-5224C | Public Transit | 5307, L, S | [6 empty] | 2020 | 840000 | 840000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - SUPPORT VEHICLE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 6 | Fayetteville Area MPO | TG-5224D | Public Transit | 5307, L | [6 empty] | 2022 | 100000 | 100000
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - ADA SERVICES |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 6 | Fayetteville Area MPO | TG-5224E | Public Transit | 5307, L | [6 empty] | 2020 | 363000 | 363000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. |  | Public Transportation (Transit) | STI (Prioritization) | 6 | Fayetteville Area MPO | TA-6685 | Division 6 | FEDT, L, T |  |  |  |  | 2026 | 490000 |  |  | 490000
CUMBERLAND | FAYETTEVILLE AREA SYSTEM OF TRANSIT | FAYETTEVILLE AREA SYSTEM OF TRANSIT | ADD SHELTER PACKAGES TO EXISTING STOPS. |  | Public Transportation (Transit) | STI (Prioritization) | 6 | Fayetteville Area MPO | TP-0005 | Division 6 | T |  |  |  |  | 2028 | 43000 |  |  | 43000
CUMBERLAND | SR 1714 (CHURCH STREET) | NCDOT | CSX CROSSING 629869Y IN WADE. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO | RX-2006A | Division 6 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
CUMBERLAND | SR 2311 (GILLESPIE STREET) | NCDOT | AR CROSSING 847218L IN FAYETTEVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 6 | Fayetteville Area MPO | RX-2406C | Division 6 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
CUMBERLAND | WINSLOW | NCDOT | AR CROSSING 847215R IN FAYETTEVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 6 | Fayetteville Area MPO | RX-2406D | Division 6 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
CUMBERLAND | CSX A LINE |  | HAY STREET CROSSING IN FAYETTEVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING #629881F IN FAYETTEVILLE |  | Rail | STI (Prioritization) | 6 | Fayetteville Area MPO | RP-0002 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34000000 |  |  | 49200000
CUMBERLAND, COLUMBUS, BLADEN | VARIOUS | NCDOT | ROUTES IN BLADEN, COLUMBUS, AND CUMBERLAND COUNTIES. UPGRADE 60 GUARDRAIL END UNITS. |  | Highway | Safety | 6 | Fayetteville Area MPO, Cape Fear RPO, Mid-Carolina RPO | HS-2406I | Region C | HSIP |  |  |  |  | 2025 | 609000 |  |  | 609000
CUMBERLAND, HARNETT | NC 210 | NCDOT | FROM THE BLADEN COUNTY LINE TO NC 53 IN CUMBERLAND COUNTY AND FROM THE CUMBERLAND COUNTY LINE TO LILLINGTON CITY LIMITS IN HARNETT COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO | HS-2006AC | Region C | HSIP |  |  |  |  | 2024 | 1170000 |  |  | 1170000
CUMBERLAND, HARNETT | NC 24 / NC 87 | NCDOT | FROM SR 1117 (NURSERY ROAD) TO SR 1451 (MANCHESTER ROAD). WIDEN ROADWAY. | 3.23 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0020 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33300000 |  |  | 64000000
CUMBERLAND, HARNETT | I-95 | NCDOT | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 15.76 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO, Fayetteville Area MPO | I-5986A | Statewide Mobility | NHP, PROTCT, T | 2019 | 21073000 | 2023 | 2000000 | 2019 | 425400000 |  |  | 448473000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | NCDOT | FAYETTEVILLE URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. |  | Bike & Ped | Locally Selected | 6, 8 | Fayetteville Area MPO | U-5528 | Division 6, 8 | TADA |  |  |  |  | 2020 | 23297000 |  |  | 23297000 | IN PROGRESS.
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | NCDOT | FAYETTEVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | Highway | Locally Selected | 6, 8 | Fayetteville Area MPO | HL-0026 | Division 6, 8 | BGANY, BGDA |  |  |  |  | 2022 | 93326000 |  |  | 93326000
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FAYETTEVILLE PLANNING ORGANIZATION. |  | Highway | Locally Selected | 6, 8 | Fayetteville Area MPO | HL-0095 | Exempt | CRPDA, L |  |  |  |  | 2023 | 7158000 |  |  | 7158000
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | NCDOT | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. |  | Highway | Locally Selected | 6, 8 | Fayetteville Area MPO | U-5207 | Division 6, 8 | BGDA, L | [6 empty] | 2020 | 3432000 | 3432000 | IN PROGRESS.
CUMBERLAND, HARNETT, JOHNSTON | I-95 | NCDOT | I-95 BUSINESS/US 301 (EXIT 56) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 26 | Highway | STI (Prioritization) | 4, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Upper Coastal Plain RPO | I-5986
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | NCDOT | US 401 (RAEFORD ROAD) TO SR 1418 (LINDSAY ROAD). WIDEN TO FOUR LANES. | 2.4 | Highway | STI (Prioritization) | 6, 8 | Fayetteville Area MPO | U-5798 | Division 6, 8 | [10 empty] | COORDINATE WITH U-5753, U-5857, AND U-5858.
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | NCDOT | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO FOUR LANES. | 1.21 | Highway | STI (Prioritization) | 6, 8 | Fayetteville Area MPO | U-5798B | Division 6, 8 | T | 2024 | 3700000 | 2024 | 710000 | 2026 | 17400000 |  |  | 21810000 | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND, MOORE, ANSON, HOKE, RICHMOND, UNION | COACH AMERICA | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON |  | Public Transportation (Transit) | Operations and Maintenance | 6, 8, 10 |  | TI-6102 | Public Transit | 5311, L, S | [6 empty] | 2020 | 2584000 | 2584000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND, ROBESON | I-295 | NCDOT | WEST OF EXIT 34 TO I-95 INTERCHANGE TO THE SOUTH. INSTALL ITS ALONG FAYETTEVILLE OUTER LOOP. | 34 | Highway | Pre-STI (Historic) | 6 | Fayetteville Area MPO, Lumber River RPO | U-2519F | Statewide Mobility | NHP |  |  |  |  | 2025 | 5999000 |  |  | 5999000
CUMBERLAND, ROBESON | I-295 (FAYETTEVILLE OUTER LOOP) | NCDOT | I-95 SOUTH OF FAYETTEVILLE TO WEST OF NC 24/87 (BRAGG BOULEVARD). FREEWAY ON NEW LOCATION. | 22.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO, Lumber River RPO | U-2519
CUMBERLAND, ROBESON, COLUMBUS, HARNETT | VARIOUS | NCDOT | I-95, US 74, US 301, NC 87, AND SR 1007. INSTALL PAVEMENT MARKING ARROWS AND RAISED PAVEMENT MARKERS ON FREEWAY/EXPRESSWAY RAMPS. |  | Highway | Safety | 6 | Lumber River RPO, Fayetteville Area MPO, Mid-Carolina RPO, Cape Fear RPO | HS-2006AB | Statewide Mobility | HSIP |  |  |  |  | 2024 | 200000 |  |  | 200000
CURRITUCK | US 158 | NCDOT | REHABILITATE BRIDGE 260016 OVER CURRITUCK SOUND. | 3.16 | Highway | Bridges | 1 | Albemarle RPO | B-5937 | Statewide Mobility | [10 empty] | COMPLETED.
CURRITUCK | NC 615 (MARSH CAUSEWAY) | NCDOT | HQ/ VC ENTRANCE ROAD TO WEST OF KNOTTS ISLAND ROAD. IMPROVE CORRIDOR AT VARIOUS LOCATIONS. | 3.89 | Highway | Federal Lands Access Program | 1 | Albemarle RPO | HF-0008 | Exempt | FLAP |  |  |  |  | 2025 | 650000 | 2023 | 50000 | 700000 | FLAP PROJECT NC 71. AWARDED $700K.
CURRITUCK | US 158 | NCDOT | CONSTRUCT ROUNDABOUT AT US 158 AND SR 1147 (INDIANTOWN ROAD). | 0.5 | Highway | Safety | 1 | Albemarle RPO | HS-2001A | Region A | HSIP |  |  |  |  | 2023 | 45000 |  |  | 45000 | UNDER CONSTRUCTION.
CURRITUCK | US 158 | NCDOT | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 0.36 | Highway | Safety | 1 | Albemarle RPO | HS-2001F | Region A | HSIP, T | 2026 | 2300000 | 2026 | 800000 | 2025 | 2400000 |  |  | 5500000 | RIGHT-OF-WAY IN PROGRESS.
CURRITUCK | US 158 | NCDOT | SR 1186 (WALNUT ISLAND BOULEVARD) TO SR 1131 (POPLAR BRANCH ROAD) IN GRANDY. INSTALL PEDESTRIAN SIGNAL HEADS, CROSSWALKS, AND SIDEWALKS. | 0.25 | Highway | Safety | 1 | Albemarle RPO | HS-2401J | Statewide Mobility | HSIP |  |  |  |  | 2025 | 185000 |  |  | 185000
CURRITUCK | US 158 | NCDOT | NC 168 TO WRIGHT BROTHERS MEMORIAL BRIDGE, AND US 158 TO NORTH OF LARK DRIVE. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 40 | Highway | Safety | 1 | Albemarle RPO | HS-2401K | Statewide Mobility | HSIP |  |  |  |  | 2025 | 635000 |  |  | 635000
CURRITUCK | NC 168 | NCDOT | SR 1229 (BAXTER LANE) INTERSECTION AND CURRITUCK SAND COMPANY ACCESS NORTH OF MOYOCK. INSTALL TRAFFIC SIGNAL. |  | Highway | Safety | 1 | Albemarle RPO | HS-2401N | Statewide Mobility | HSIP |  |  |  |  | 2025 | 325000 |  |  | 325000
CURRITUCK | NEW ROUTE | NCDOT | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. TOLL PROJECT. | 6.93 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-2576 | Division 1 | BGANY, BOND R, T(M) | 2026 | 16496000 | 2026 | 17412000 | 2026 | 434004000 |  |  | 467912000 | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2026-2040.
CURRITUCK, CAMDEN | NC 34 | NCDOT | US 158 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 9 | Highway | Safety | 1 | Albemarle RPO | HS-2401O | Region A | HSIP |  |  |  |  | 2025 | 290000 |  |  | 290000
DARE | US 158 | NCDOT | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | 3.87 | Bike & Ped | STI (Prioritization) | 1 | Albemarle RPO | EB-5848 | Division 1 | L(M), TA5T50 |  |  |  |  | 2026 | 7200000 | 2024 | 100000 | 7300000
DARE | NC 12 | NCDOT | HATTERAS PARKING LOT IMPROVEMENTS AND CONNECTIVITY MEASURES, HATTERAS LOADING FACILITY |  | Ferry | Other | 1 | Albemarle RPO | F-5702A | Division 1 | [10 empty] | COMPLETED. WORK ACCOMPLISHED UNDER F-5702B.
DARE | NC 12 | NCDOT | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS. | 0.25 | Highway | Bridges | 1 | Albemarle RPO | B-5610 | Region A | BGLT5, NHPB | 2021 | 520000 | 2021 | 460000 | 2024 | 5220000 |  |  | 6200000 | RIGHT-OF-WAY IN PROGRESS.
DARE | US 64 | NCDOT | PRESERVATION OF BRIDGE 270009 ON US 64 IN MANNS HARBOR. | 2.85 | Highway | Bridges | 1 | Albemarle RPO | HB-0017 | Region A | BFP |  |  |  |  | 2022 | 38823000 |  |  | 38823000 | UNDER CONSTRUCTION.
DARE | NC 12 | NCDOT | RODANTHE TO OREGON INLET. CONDUCT PLANNING STUDY FOR THE LONG-TERM OPERATION OF THE ROADWAY DURING MAJOR STORM EVENTS. |  | Highway | Other | 1 | Albemarle RPO | HO-0020 | Exempt | DP | [6 empty] | 2025 | 1865000 | 1865000 | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT AWARD.
DARE | VARIOUS | NCDOT | DEPLOYMENT OF AUTOMATED SHUTTLE AT WRIGHT BROTHERS NATIONAL MEMORIAL. |  | Highway | Other | 1 | Albemarle RPO | R-5753A | Exempt | FLTP | [6 empty] | 2021 | 95000 | 95000
DARE | NC 12 | NCDOT | REPLACE BRIDGE 270011 (HERBERT C. BONNER BRIDGE) OVER OREGON INLET AND NC 12 IMPROVEMENTS. | 2.7 | Highway | Pre-STI (Historic) | 1 | Albemarle RPO | B-2500 | Pre-STI (Transition)
DARE | NC 12 | NCDOT | PHASE II, SHORT-TERM IMPROVEMENTS AT PEA ISLAND. |  | Highway | Pre-STI (Historic) | 1 | Albemarle RPO | B-2500AB | Pre-STI (Transition) | [10 empty] | COMPLETED.
DARE | US 158 | NCDOT | SR 1206 (THE WOODS ROAD) / DOGWOOD TRAIL INTERSECTION IN KITTY HAWK. INSTALL CURB, GUTTER, RAMPS AND CROSSWALKS. |  | Highway | Safety | 1 | Albemarle RPO | HS-2401I | Statewide Mobility | HSIP |  |  |  |  | 2025 | 113000 |  |  | 113000
DARE | NC 12 (VIRGINIA DARE TRAIL) | NCDOT | NEPTUNE DRIVE INTERSECTION IN KILL DEVIL HILLS. REMOVE EXISTING CROSSWALK, INSTALL NEW CROSSWALK WITH PEDESTRIAN HEADS, AND REVISE SIGNAL. |  | Highway | Safety | 1 | Albemarle RPO | HS-2401L | Region A | HSIP |  |  |  |  | 2025 | 100000 |  |  | 100000
DARE | SR 1217 (COLLINGTON ROAD) | NCDOT | DEAD END TO US 158 (CROATON HIGHWAY) IN KILL DEVIL HILLS. OPERATIONAL-SAFETY IMPROVEMENTS. | 4.35 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5014 | Division 1 | BGANY |  |  |  |  | 2022 | 22368000 |  |  | 22368000 | UNDER CONSTRUCTION.
DARE | SR 1208 (WEST KITTY HAWK ROAD) | NCDOT | SR 1210 (BOB PERRY ROAD) TO IVY LANE. UPGRADE FACILITY AND REPLACE BRIDGE 270040. | 1.01 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5738 | Division 1 | T |  |  |  |  | 2019 | 4646000 |  |  | 4646000 | COMPLETED. BUILD NC BOND FUNDING: $3,561,232 FOR CONSTRUCTION PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
DARE | NC 12 | NCDOT | PHASE II, LONG-TERM IMPROVEMENTS AT RODANTHE. |  | Highway | Transition | 1 | Albemarle RPO | B-2500B | Pre-STI (Transition) | BGLT5 |  |  |  |  | 2023 | 1300000 |  |  | 1300000 | COMPLETED.
DARE | RURAL FERRY |  | SHIPYARD PAINT FACILITY REHABILITATION - RURAL FERRY PROGRAM. |  | Public Transportation (Transit) | Locally Selected | 1 | Albemarle RPO | TL-0047 | Public Transit | 5307, S |  |  |  |  | 2024 | 2000000 |  |  | 2000000
DARE | DARE COUNTY | DARE COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 1 | Albemarle RPO | TK-6124 | Public Transit | 5311, L, S | [6 empty] | 2020 | 512000 | 512000 | FUNDS AUTHORIZED IN PROGRESS
DARE, HALIFAX | NC 12 | NCDOT | HATTERAS AND OCRACOKE DOCK IMPROVEMENTS |  | Ferry | Other | 1, 4 | Albemarle RPO | F-5702E | Division 1, 4 | [10 empty] | COMPLETED. WORK ACCOMPLISHED UNDER F-5702B.
DARE, HYDE | NC 12 | NCDOT | HATTERAS AND OCRACOKE ISLAND FERRY RAMP AND DOCK IMPROVEMENTS. |  | Ferry | Federal Lands Access Program | 1 | Albemarle RPO | FF-0001 | Exempt | FLAP |  |  |  |  | 2026 | 2430000 | 2023 | 1070000 | 3500000 | FLAP PROJECT NC 62. AWARDED $3.5M.
DARE, HYDE | NC 12 | NCDOT | HATTERAS FERRY DOCK IN DARE COUNTY TO OCRACOKE FERRY DOCKS IN HYDE COUNTY. CONSTRUCT TWO PASSENGER FERRIES TO BE USED ALONG NEW ROUTE. IMPLEMENT TRANSIT SYSTEM TO AID PASSENGERS ON OCRACOKE ISLAND. |  | Ferry | Other | 1 | Albemarle RPO | F-5702 | Division 1 | [10 empty] | OTHER FUNDS ARE FROM STATE APPROPRIATION 7355.
DARE, HYDE | NC 12 | NCDOT | CONSTRUCT TWO PASSENGER FERRIES |  | Ferry | Other | 1 | Albemarle RPO | F-5702C | Division 1 | [10 empty] | UNDER CONSTRUCTION.
DARE, HYDE | NC 12 | NCDOT | CONSTRUCT RIVER CLASS FERRY. |  | Ferry | STI (Prioritization) | 1 | Albemarle RPO | F-5700 | Division 1 | [10 empty] | COMPLETE
DAVIDSON | DAVIDSON COUNTY AIRPORT (EXX) | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE AND STRENGTHEN RUNWAY TO ACCOMMODATE LARGER PRIVATE AIRCRAFT. |  | Aviation | STI (Prioritization) | 9 | High Point Urban Area MPO | AV-5831 | Division 9 | T |  |  |  |  | 2022 | 14551000 |  |  | 14551000 | UNDER CONSTRUCTION. TO BE LET WITH AV-5900.
DAVIDSON | DAVIDSON COUNTY AIRPORT (EXX) | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE TAXIWAY AND APRON. |  | Aviation | STI (Prioritization) | 9 | High Point Urban Area MPO | AV-5900 | Division 9 | [10 empty] | UNDER CONSTRUCTION, LET WITH AV-5831. FUNDING SHOWN UNDER PROJECT AV-5831
DAVIDSON | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | NCDOT | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | 0.25 | Highway | Bridges | 9 | High Point Urban Area MPO | B-5779 | Region D | BFP | 2028 | 110000 | 2028 | 350000 | 2029 | 11800000 |  |  | 12260000
DAVIDSON | US 29 / US 70 / BUSINESS 85 | NCDOT | REPLACE BRIDGE 280164 AND BRIDGE 280168 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | Highway | Bridges | 9 | High Point Urban Area MPO | B-5783 | Region D | BFP |  |  |  |  | 2023 | 5778000 |  |  | 5778000 | UNDER CONSTRUCTION
DAVIDSON | I-85 | NCDOT | REHABILITATE BRIDGE 280181 AND BRIDGE 280182. | 0.25 | Highway | Bridges | 9 | High Point Urban Area MPO | I-5740A | Statewide Mobility | [10 empty] | COMPLETE
DAVIDSON | US 64 | NCDOT | EXTEND LEFT TURN LANE AND CONSTRUCT RIGHT TURN LANE AT PROPOSED NEW ACCESS ROAD ACROSS FROM SR 2112 (DECKER ROAD) AND WIDEN RAIL CROSSING 836515Y. | 0.09 | Highway | Economic Development | 9 | High Point Urban Area MPO | HE-0008 | Division 9 | T |  |  |  |  | 2023 | 1500000 | 2022 | 300000 | 1800000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR.
DAVIDSON | SR 1104 OLD LINWOOD ROAD | NCDOT | CONSTRUCT NEW ACCESS ROAD NORTH OF SR 1254 (BROWN STREET) AND IMPROVEMENTS TO SR 1104 (OLD LINWOOD ROAD). |  | Highway | Economic Development | 9 | High Point Urban Area MPO | HE-0014 | Division 9 | T |  |  | 2024 | 10000 | 2024 | 8590000 | 2023 | 400000 | 9000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY.
DAVIDSON | I-85 | NCDOT | SR 2205 (OLD US 64) TO 0.4 MILES NORTH OF US 64. PAVEMENT REHABILITATION. | 2.6 | Highway | Interstate Maintenance | 9 | High Point Urban Area MPO | I-5740 | Statewide Mobility | [10 empty] | COMPLETE
DAVIDSON | I-85 | NCDOT | I-285 / US 29 / US 52 / US 70 TO NORTH OF US 64. PAVEMENT REHABILITATION. | 9.58 | Highway | Interstate Maintenance | 9 | High Point Urban Area MPO | I-5950 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 28542000 |  |  | 28542000
DAVIDSON | NC 109 | NCDOT | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | Highway | Locally Selected | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | HL-0061 | Exempt | BGDA, CMAQ, CRPDA, L(M) | 2025 | 1982000 | 2026 | 518000 | 2027 | 2007000 | 2024 | 400000 | 4907000
DAVIDSON | I-85 | NCDOT | NORTH OF NC 150 TO US 29-70-52/BUSINESS 85 IN DAVIDSON COUNTY |  | Highway | Pre-STI (Historic) | 9 | High Point Urban Area MPO | I-2304AD | Pre-STI (Transition) | NHP | 2009 | 984000 | [6 empty] | 984000 | COMPLETE; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021
DAVIDSON | US 64 | NCDOT | US 64 FROM SR 2782 (BOWERS ROAD TO EAST OF SR 2012 / SR 2227 (HEATH CHURCH ROAD / NEW BOWERS ROAD). CONSTRUCT 4 REDUCED CONFLICT INTERSECTIONS AND LEFT-OVER WITH U-TURN BULB EAST OF SR 2012 / SR 2227. | 0.61 | Highway | Safety | 9 | High Point Urban Area MPO | HS-2009B | Region D | HSIP |  |  | 2023 | 20000 | 2023 | 2686000 |  |  | 2706000 | UNDER CONSTRUCTION
DAVIDSON | US 29 / US 70 | NCDOT | US 29 / US 70, VICINITY OF FLEET DARR ROAD WEST OF SR 2123 (LEXINGTON AVENUE) CONNECTOR. INSTALL DIRECTIONAL LEFTOVERS. | 0.5 | Highway | Safety | 9 | High Point Urban Area MPO | HS-2009C | Region D | HSIP |  |  |  |  | 2026 | 500000 |  |  | 500000
DAVIDSON | NC 109 | NCDOT | NC 109 AT SR 2335 CANAAN CHURCH ROAD AND SNYDER STATION ROAD NEAR DENTON. INSTALL TURN LANES. | 0.5 | Highway | Safety | 9 | High Point Urban Area MPO | HS-2009K | Region D | CRPLT5, T(M) |  |  |  |  | 2024 | 620000 |  |  | 620000
DAVIDSON | NC 62 | NCDOT | NC 62 (CLONINGER) DRIVE AT SR 2055 (LIBERTY DRIVE) IN THOMASVILLE. IMPROVE VERTICAL ALIGNMENT. | 0.5 | Highway | Safety | 9 | High Point Urban Area MPO | HS-2009L | Region D | HSIP |  |  |  |  | 2025 | 530000 |  |  | 530000
DAVIDSON | NC 109 | NCDOT | DENTON NORTHERN MUNICIPAL BOUNDARY TO SR 2067 (LAMBETH ROAD), AND SR 1798 (OLD GREENSBORO ROAD) / SR 1756 (WEST LEXINGTON AVENUE EXTENSION) TO SR 1711 (GUMTREE ROAD). INSTALL RUMBLE STRIPS AND LONG-LIFE PAVEMENT MARKINGS. | 15.99 | Highway | Safety | 9 | High Point Urban Area MPO | W-5809A | Region D | HSIP |  |  |  |  | 2022 | 1100000 |  |  | 1100000 | UNDER CONSTRUCTION
DAVIDSON | US 64 | NCDOT | US 64, I-85 BUSINESS IN LEXINGTON TO EAST OF I-85. |  | Highway | STI (Prioritization) | 9 | High Point Urban Area MPO | R-2220A | [11 empty] | COMPLETE
DAVIDSON | US 64 | NCDOT | I-85 EAST OF LEXINGTON TO NC 109 |  | Highway | STI (Prioritization) | 9 | High Point Urban Area MPO | R-2220B | Not Funded | T | NOT FUNDED | 30992000 | NOT FUNDED | 5635000 | NOT FUNDED | 40572000 | NOT FUNDED |  | 77199000
DAVIDSON | US 29 / US 70 / BUSINESS 85 | NCDOT | SR 1798 (OLD GREENSBORO ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 9 | High Point Urban Area MPO | R-5737 | Division 9 | T |  |  |  |  | 2022 | 29777000 |  |  | 29777000 | UNDER CONSTRUCTION; INCLUDES PARTICIPATION BY DAVIDSON COUNTY COMMUNITY COLLEGE
DAVIDSON | NC 8 (WINSTON ROAD) | NCDOT | US 29 / US 70 TO SR 1846 (ARRINGTON DRIVE) IN LEXINGTON. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.51 | Highway | STI (Prioritization) | 9 | High Point Urban Area MPO | U-5757 | Region D | T | 2019 | 17575000 |  |  | 2025 | 14400000 |  |  | 31975000 | RIGHT-OF-WAY IN PROGRESS
DAVIDSON | SR 1508 (HICKORY TREE ROAD) | NCDOT | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTI-LANES. | 2.91 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5786 | Division 9 | BGANY, T | 2030 | 12308000 | 2030 | 5200000 | 2033 | 45700000 |  |  | 63208000
DAVIDSON | NC 8 | NCDOT | REPLACE BRIDGE 280027 OVER US 29 / US 64 / US 70 / I-85 BUSINESS IN LEXINGTON. | 0.25 | Highway | Transition | 9 | High Point Urban Area MPO | B-3159 | Region D | [10 empty] | COMPLETE
DAVIDSON | DAVIDSON COUNTY TRANSPORTATION SYSTEM | DAVIDSON COUNTY TRANSPORTATION SYSTEM | INSTALLING COVERED BUS SHELTERS WITH ADA ACCESS TO MAJOR STOPS SUCH AS WALMART AND BIG LOTS. INSTALL SIMME SEATS AT THE REMAINDER OF BUS STOPS. SIMME SEATS PROVIDE TWO SEATS ATTACHED TO THE BUS STOP SIGN POLE. |  | Public Transportation (Transit) | Locally Selected | 9 | Winston-Salem Area TPO | TL-0014 | Division 9 | BGDA, L | [6 empty] | 2021 | 140000 | 140000
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | OPERATING FUNIDING FOR DAVIDSON COUNTY TRANSPORATION FOR SERVICE IN THE HIGH POINT URBAN AREA - THROUGH NCDOT |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | High Point Urban Area MPO | TO-5215 | Public Transit | 5307, L | [6 empty] | 2020 | 360000 | 360000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | TO-6165 | Public Transit | 5307, L | [6 empty] | 2020 | 326688000 | 326688000
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Piedmont Triad RPO | TK-6125 | Public Transit | 5311, L, S | [6 empty] | 2020 | 836000 | 836000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON | DAVIDSON COUNTY TRANSPORTATION SYSTEM |  | OPERATE OUR DEVIATED FIXED ROUTES BASED IN THOMASVILLE, NC ALONG WITH DEMAND RESPONSE TRIPS. |  | Public Transportation (Transit) | Operations and Maintenance | 9 | High Point Urban Area MPO | TM-0048 | Public Transit | 5317, L | [6 empty] | 2024 | 3300000 | 3300000
DAVIDSON | VARIOUS | LEXINGTON | TRANSIT OPERATIONS SUPPORT FOR CITY OF LEXINGTON CIRCULATOR ROUTE AND THOMASVILLE / LEXINGTON CONNECTOR ROUTE. |  | Public Transportation (Transit) | Pre-STI (Historic) | 9 | High Point Urban Area MPO | C-5559 | Exempt | [10 empty] | IMPLEMENTATION BY DAVIDSON COUNTY - IN PROGRESS
DAVIDSON | DAVIDSON COUNTY TRANSPORTATION SYSTEM |  | ROUTINE CAPITAL/PREVENTATIVE MAINTENANCE FOR OPERATIONS IN THOMASVILLE, NC. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | High Point Urban Area MPO | TG-0021 | Public Transit | 5317, L | [6 empty] | 2024 | 360000 | 360000
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | TG-6808B | Public Transit | 5307, L |  |  |  |  | 2020 | 408360000 |  |  | 408360000
DAVIDSON | DAVIDSON COUNTY | DAVIDSON COUNTY | ROUTINE CAPITAL - PASSENGER SHELTERS, PASSENGER AMENITIESA, SHOP EQUIPMENT, SPARE PARTS, CAPITAL COST OF CONTRACTING, ETC. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | TG-6809 | Public Transit | 5307, L |  |  |  |  | 2020 | 204180000 |  |  | 204180000
DAVIDSON | NCRR | LEXINGTON | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTI-MODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. |  | Rail | Other | 9 | High Point Urban Area MPO | P-5732 | Exempt | DP, L, O |  |  |  |  | 2025 | 15700000 |  |  | 15700000 | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT
DAVIDSON | LS (FIRST STREET) | NCDOT | WSS CROSSING 849955C IN DENTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | High Point Urban Area MPO | RX-2009A | Division 9 | RR |  |  |  |  | 2025 | 303000 |  |  | 303000
DAVIDSON | SR 1101 (WILDLIFE RECREATION AREA ACCESS ROAD) | NCDOT | IMPROVEMENTS TO WSS CROSSING 849835L IN SOUTHMONT. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | High Point Urban Area MPO | RX-2409A | Division 9 | RR |  |  |  |  | 2026 | 475000 |  |  | 475000
DAVIDSON | NORFOLK SOUTHERN | LEXINGTON | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD TRACK. |  | Rail | STI (Prioritization) | 9 | High Point Urban Area MPO | P-5722 | Region D | O, T |  |  |  |  | 2027 | 2038000 |  |  | 2038000 | "O" FUNDING REPRESENTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION.
DAVIDSON | NORFOLK SOUTHERN | NCDOT | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. |  | Rail | STI (Prioritization) | 9 | High Point Urban Area MPO | P-5731 | Division 9 | DP, L, T | 2025 | 6900000 |  |  | 2026 | 49800000 |  |  | 56700000 | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT
DAVIDSON | NCRR / NORFOLK SOUTHERN MAIN LINE | NCDOT | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. |  | Rail | STI (Prioritization) | 9 | High Point Urban Area MPO | P-5751 | Division 9 | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22003000 |  |  | 27003000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DAVIDSON, ALAMANCE, CABARRUS, DURHAM, GUILFORD, MECKLENBURG, ORANGE, ROWAN, WAKE | PIEDMONT CORRIDOR | NCDOT | NEW TRAINS AND MAINTENANCE FACILITY. |  | Rail | STI (Prioritization) | 5, 7, 9, 10 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO | P-5719C | Region C, D, E | DP, T |  |  |  |  | 2026 | 212528000 |  |  | 212528000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | BO-2409 | Division 9 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | BO-2609 | Division 9 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | R-5789 | Division 9 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2009 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Area TPO | HS-2009A | Division 9 | HSIP |  |  |  |  | 2021 | 1900000 |  |  | 1900000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 9. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2024
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2024DIV | Division 9 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2024REG | Region D | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2024SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2409 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | HS-2609 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5709 | [11 empty] | IN PROGRESS; $2.5M NHP FUNDING APPLIED TO W-5709E.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5709DIV | Division 9 | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5709REG | Region D | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5709SW | Statewide Mobility | HSIP | 2020 | 120000 |  |  | 2020 | 740000 |  |  | 860000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | Highway | Safety | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | W-5809
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 9. |  | Rail | Rail-Highway Grade Crossing Closure | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | RC-2009 | Division 9 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | RX-2009 | Division 9 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | RX-2409 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | RX-2609 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DAVIDSON, FORSYTH | NC 109 | NCDOT | NC 109. FORSYTH COUNTY FROM MILE POST 0.256 TO DAVIDSON COUNTY MILE POST 38.367. INSTALL CENTERLINE AND EDGELINE SINUSOIDAL RUMBLESTRIPES. | 0.48 | Highway | Safety | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | HS-2009F | Region D | HSIP |  |  |  |  | 2023 | 238000 |  |  | 238000 | UNDER CONSTRUCTION
DAVIDSON, GUILFORD, FORSYTH | VARIOUS | HIGH POINT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | Highway | Other | 7, 9 | High Point Urban Area MPO | C-5609 | Exempt | CMAQ, L(M) | 2020 | 243000 |  |  | 2020 | 1455000 | 2020 | 729000 | 2427000 | IN PROGRESS
DAVIDSON, GUILFORD, RANDOLPH | HIGH POINT TRANSIT SYSTEM / HI-TRAN | HIGH POINT TRANSIT SYSTEM / HI-TRAN | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 7, 8, 9 | High Point Urban Area MPO | TS-5113 | Public Transit | 5307, L | [6 empty] | 2020 | 64000 | 64000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON, GUILFORD, RANDOLPH, FORSYTH | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE HIGH POINT PLANNING ORGANIZATION. |  | Highway | Locally Selected | 7, 8, 9 | High Point Urban Area MPO | HL-0101 | Exempt | CRPDA, L |  |  |  |  | 2023 | 2366000 |  |  | 2366000
DAVIDSON, RANDOLPH | US 64 | NCDOT | US 64, EAST OF I-85 BUSINESS IN LEXINGTON TO ASHEBORO BYPASS. WIDEN TO MULTI-LANES. |  | Highway | STI (Prioritization) | 8, 9 | High Point Urban Area MPO, Piedmont Triad RPO | R-2220
DAVIDSON, ROWAN | I-85 | NCDOT | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO US 29 / US 52 / US 70 / BUSINESS 85 IN DAVIDSON COUNTY. ADDITIONAL LANES AND YADKIN RIVER BRIDGE RECONSTRUCTION. (PROJECT INCLUDES B-3833). | 6.8 | Highway | Pre-STI (Historic) | 9 | High Point Urban Area MPO, Cabarrus-Rowan MPO | I-2304 | Pre-STI (Transition) | [10 empty] | INCLUDES B-3833; TIGER AWARD / INTERSTATE MAINTENANCE DISCRETIONARY FUNDING $11.7 MILLION; GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
DAVIDSON, ROWAN | I-85 | NCDOT | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO NORTH OF NC 150 IN DAVIDSON COUNTY, INCLUDING YADKIN RIVER BRIDGE |  | Highway | Pre-STI (Historic) | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | I-2304AC | Exempt | NHP | 2009 | 1066000 |  |  | 2010 | 8220000 |  |  | 9286000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC
DAVIDSON, ROWAN | I-85 | NCDOT | IMPLEMENTATION OF INTELLIGENT TRANSPORTATION SYSTEM (ITS) |  | Highway | Transition | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | I-2304AF | Pre-STI (Transition) | [10 empty] | COMPLETE
DAVIE | NC 801 | BERMUDA RUN | US 158 TO YADKIN VALLEY ROAD AT ATRIUM WAKE FOREST BAPTIST HOSPITAL. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0144 | Division 9 | BGDA, L(M) | 2026 | 145000 |  |  | 2026 | 660000 | 2025 | 248000 | 1053000
DAVIE | BLUE HERON TRAIL | BERMUDA RUN | CONSTRUCT BLUE HERON TRAIL PHASE III FROM ROYAL TROON DRIVE TO NC 801. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0146 | Division 9 | L(M), TADA | 2026 | 110000 |  |  | 2026 | 660000 | 2025 | 275000 | 1045000
DAVIE | BLUE HERON TRAIL | BERMUDA RUN | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 1 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5958 | Division 9 | BGANY, BGDA, L |  |  |  |  | 2022 | 3693000 |  |  | 3693000 | UNDER CONSTRUCTION
DAVIE | DUKE STREET | MOCKSVILLE | CONSTRUCT SIDEWALK FROM SR 1147 (HARDISON STREET) TO SR 1853 (AVGOL DRIVE). | 0.15 | Bike & Ped | NCDOT Selected (Other Selection Process) | 9 | Northwest Piedmont RPO | BN-0014 | Exempt | CRP550, L(M) |  |  |  |  | 2025 | 715000 |  |  | 715000
DAVIE | SR 1436 (PINEBROOK SCHOOL ROAD) | NCDOT | REPLACE BRIDGE 290076 OVER I-40. |  | Highway | Bridges | 9 | Northwest Piedmont RPO | BR-0152 | Division 9 | BGOFF |  |  |  |  | 2025 | 5800000 |  |  | 5800000 | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM
DAVIE | I-40 | NCDOT | SR 1436 (PINEBROOK SCHOOL ROAD) TO WEST OF NC 801. PAVEMENT REHABILITATION. | 4.76 | Highway | Interstate Maintenance | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO | I-6003 | Statewide Mobility | NHPIM |  |  |  |  | 2021 | 7677000 |  |  | 7677000 | UNDER CONSTRUCTION
DAVIE | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | Highway | Other | 9 | Northwest Piedmont RPO | C-5614 | Exempt | CMAQ, L | 2020 | 12000 |  |  | 2020 | 57000 | 2020 | 36000 | 105000
DAVIE | US 158 | NCDOT | NC 801 INTERSECTION IN WINSTON-SALEM. UPGRADE INTERSECTION WITH LEFT TURN LANE ON EB US 158, AND RIGHT THRU LANE AND RIGHT TURN LANE ON NC 801. | 0.5 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | HP-0023 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 |  |  | 7300000
DAVIE | US 601 | NCDOT | SOUTH SALISBURY STREET IN MOCKSVILLE. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5728 | Region D | [10 empty] | UNDER CONSTRUCTION
DAVIE | US 601 | NCDOT | SR 1301 (MADISON ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | 1.52 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5736 | Division 9 | BGANY | 2029 | 6400000 | 2029 | 800000 | 2032 | 32100000 |  |  | 39300000
DAVIE | SR 1410 (FARMINGTON ROAD) | NCDOT | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | 1 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5854 | Division 9 | T | 2023 | 100000 | 2023 | 200000 | 2025 | 1500000 |  |  | 1800000 | RIGHT-OF-WAY IN PROGRESS
DAVIE | WILKESBORO STREET | NCDOT | YADKINVILLE ROAD IN MOCKSVILLE. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | U-6002 | Division 9 | T |  |  |  |  | 2022 | 1800000 |  |  | 1800000 | RIGHT-OF-WAY IN PROGRESS
DAVIE | NEW ROUTE | NCDOT | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | 0.71 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6187 | Division 9 | BGANY, T | 2024 | 4000000 | 2025 | 1000000 | 2026 | 64410000 |  |  | 69410000 | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE)
DAVIE, FORSYTH | I-40 | NCDOT | WEST OF NC 801 IN DAVIE COUNTY TO SR 1101 (HARPER ROAD) IN FORSYTH COUNTY. | 2.33 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | I-0911A | Region D | T |  |  |  |  | 2021 | 35894000 |  |  | 35894000 | COMPLETE; DESIGN-BUILD PROJECT; BUILD NC BONDS: $27.889 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
DAVIE, STOKES, SURRY, YADKIN | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 9, 11 | Northwest Piedmont RPO | TK-6174 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1704000 | 1704000 | FUNDS AUTHORIZED IN PROGRESS
DUPLIN | SR 1828 (CYPRESS CREEK ROAD) | NCDOT | REPLACE BRIDGE 300187 OVER BACK SWAMP. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | B-5632 | Division 3 | BGOFF | 2023 | 190000 |  |  | 2023 | 5186000 |  |  | 5376000 | UNDER CONSTRUCTION.
DUPLIN | NC 11 | NCDOT | REPLACE BRIDGE 300036 OVER MAXWELL CREEK. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | B-5639 | Highway Fund | HFB | 2020 | 56000 |  |  | 2021 | 3422000 |  |  | 3478000 | UNDER CONSTRUCTION.
DUPLIN | SR 1135 (PROVIDENCE CHURCH ROAD) | NCDOT | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | B-5647 | Division 3 | BGOFF | 2023 | 60000 | 2023 | 25000 | 2024 | 1750000 |  |  | 1835000 | RIGHT-OF-WAY IN PROGRESS.
DUPLIN | US 117 NBL | NCDOT | REPLACE BRIDGE 300016 OVER CSX RAILROAD. BRIDGE PRESERVATION OF BRIDGE 300017 OVER CSX. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | B-5981 | Statewide Mobility | BGLT5 | 2022 | 443000 |  |  | 2024 | 10866000 |  |  | 11309000 | RIGHT OF WAY IN PROGRESS
DUPLIN | SR 1162 (BAY ROAD) | NCDOT | REPLACE BRIDGE 300045 OVER ISLAND CREEK. | 0.25 | Highway | Bridges | 3 | Eastern Carolina RPO | BR-0243 | Highway Fund | HFB |  |  |  |  | 2022 | 1700000 |  |  | 1700000 | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.83 PROJECT.
DUPLIN | I-40 | NCDOT | I-40 FROM THE SAMPSON COUNTY LINE (MILE MARKER 360) TO THE PENDER COUNTY LINE (MILE MARKER 388). PAVEMENT REHABILITATION. | 28 | Highway | Interstate Maintenance | 3 | Eastern Carolina RPO | HI-0012 | Statewide Mobility | NHPIM |  |  |  |  | 2030 | 31100000 |  |  | 31100000
DUPLIN | SR 1535 (LIDDELL ROAD) | NCDOT | SR 1535 (LIDDELL ROAD) AND SR 1534 (DRUMMERSVILLE ROAD). INSTALL ALL WAY STOP. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003C | Division 3 | HSIP |  |  |  |  | 2025 | 51000 |  |  | 51000
DUPLIN | US 117 (SYCAMORE STREET) | NCDOT | US 117 (SYCAMORE STREET) AND SR 1102 (CHARITY ROAD) IN ROSE HILL. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003E | Region B | HSIP |  |  |  |  | 2025 | 102000 |  |  | 102000
DUPLIN | NC 403 | NCDOT | NC 403 AT SR 1306 (BEAUTANCUS ROAD). INSTALL ALL WAY STOP, STOP AHEAD WARNING SIGNS, BRIGHTSIDES, STOP BARS, CONCRETE ISLAND, AND REFRESH PAVEMENT MARKINGS. REMOVE ACTUATED CURVE WARNING FLASHER. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003I | Region B | HSIP |  |  |  |  | 2025 | 224000 |  |  | 224000
DUPLIN | US 117 (NORWOOD STREET) | NCDOT | US 117 (NORWOOD STREET) AND SR 1173 (SOUTHERLAND STREET) IN WALLACE. REVISE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003M | Region B | HSIP |  |  |  |  | 2025 | 44000 |  |  | 44000
DUPLIN | NC 24 BUSINESS (ROUTELEDGE ROAD) | NCDOT | NC 24 BUSINESS (ROUTELEDGE ROAD) AND NC 24 / NC 903 (SOUTH KENANSVILLE BYPASS). REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 0.5 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2003N | Statewide Mobility | HSIP |  |  |  |  | 2023 | 252000 |  |  | 252000
DUPLIN | NC 111 | NCDOT | ONSLOW COUNTY LINE TO NC 41 ; NC 41 / NC 241 IN BEULAVILLE TO NC 11 ; NC 11 / NC 903 TO WAYNE COUNTY LINE. INSTALL CENTERLINE AND SHOULDER SINUSOIDAL RUMBLE STRIPS. | 27.8 | Highway | Safety | 3 | Eastern Carolina RPO | HS-2403C | Region B | HSIP |  |  |  |  | 2025 | 1360000 |  |  | 1360000
DUPLIN | DUPLIN COUNTY | DUPLIN COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Eastern Carolina RPO | TK-6177 | Public Transit | 5311, L, S | [6 empty] | 2020 | 836000 | 836000 | FUNDS AUTHORIZED IN PROGRESS
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | BO-2403 | Division 3 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | BO-2603 | Division 3 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | R-5783 | Division 3 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | HS-2003 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 3 EXCEPT IN GRAND STRAND MPO. |  | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO | HS-2018
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM EXCLUDING GRAND STRAND MPO. |  | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO | HS-2018DIV | Division 3 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM EXCLUDING GRAND STRAND MPO. |  | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO | HS-2018REG | Region B | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM EXCLUDING GRAND STRAND MPO. |  | Highway | Safety | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO | HS-2018SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | HS-2403 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | HS-2603 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO | W-5203 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC). IN PROGRESS.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5703 | [11 empty] | IN PROGRESS
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5703DIV | Division 3 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5703REG | Region B | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5703SW | Statewide Mobility | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | Highway | Safety | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | W-5803
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 3. |  | Rail | Rail-Highway Grade Crossing Closure | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | RC-2003 | Division 3 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. |  | Rail | Rail-Highway Grade Crossing Improvement | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | RX-2003 | Division 3 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. |  | Rail | Rail-Highway Grade Crossing Improvement | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | RX-2403 | Division 3 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. |  | Rail | Rail-Highway Grade Crossing Improvement | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | RX-2603 | Division 3 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DUPLIN, PENDER | I-40 | NCDOT | DUPLIN COUNTY LINE (MILE MARKER 360) TO WEST OF US 117 (MILE MARKER 390). PAVEMENT AND BRIDGE REHABILITATION. | 35.89 | Highway | Interstate Maintenance | 3 | Eastern Carolina RPO, Cape Fear RPO | I-5940 | Statewide Mobility | BGIM |  |  |  |  | 2019 | 29576000 |  |  | 29576000 | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION.
DUPLIN, SAMPSON | US 117 | NCDOT | FROM I-40 IN SAMPSON COUTY TO THE WAYNE COUNTY LINE. INSTALL GUARDRAIL. | 6.95 | Highway | Safety | 3 | Eastern Carolina RPO, Mid-Carolina RPO | HS-2003AH | Statewide Mobility | HSIP |  |  |  |  | 2025 | 507000 |  |  | 507000
DUPLIN, SAMPSON | VARIOUS | NCDOT | INSTALL PAVEMENT MARKINGS ALONG VARIOUS ROUTES. |  | Highway | Safety | 3 | Eastern Carolina RPO, Mid-Carolina RPO | HS-2003B | Division 3 | HSIP |  |  |  |  | 2021 | 3432000 |  |  | 3432000 | UNDER CONSTRUCTION.
DUPLIN, SAMPSON | US 117 (FUTURE 1-795) | NCDOT | I-40 TO SR 1006 (WEST TRADE ROAD). | 5.31 | Highway | STI (Prioritization) | 3 | Eastern Carolina RPO, Mid-Carolina RPO | U-3125A | Not Funded | NHP | NOT FUNDED | 7300000 | NOT FUNDED | 1200000 | NOT FUNDED | 219400000 | NOT FUNDED |  | 227900000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
DURHAM | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | DURHAM | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 4.44 | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | BL-0028 | Division 5 | BGDA, CMAQ, L |  |  |  |  | 2024 | 2565000 | 2024 | 175000 | 2740000
DURHAM | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | DURHAM | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 8.67 | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | BL-0030 | Division 5 | BGDA, BGDACV, L |  |  |  |  | 2025 | 179000 | 2022 | 36000 | 215000
DURHAM | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | DURHAM | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STEPHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 8.23 | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | BL-0031 | Division 5 | BGDA, L |  |  |  |  | 2024 | 404000 | 2024 | 60000 | 464000
DURHAM | (HORTON ROAD) SR 1443 | DURHAM | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 1.6 | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | BL-0063 | Exempt | CMAQ, L | 2025 | 571000 |  |  | 2025 | 275000 | 2024 | 359000 | 1205000
DURHAM | SR 1999 (DAVIS DRIVE) | RESEARCH TRIANGLE PARK | I-40 TO SR 1121 (CORNWALLIS ROAD). RECONSTRUCT MULTI-USE PATH. | 0.63 | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | BL-0152 | Division 5 | L(M), TADA |  |  |  |  | 2026 | 1211000 | 2025 | 10000 | 1221000
DURHAM | VARIOUS | DURHAM | CONSTRUCT SIDEWALKS IN DURHAM. |  | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | C-5183 | Division 5
DURHAM | SR 1945 (S. ALSTON AVE.) | DURHAM | SR 1171 (RIDDLE RD.) TO CAPPS STREET. | 0.44 | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | C-5183B | Exempt | BGDA, CMAQ, L, TADA |  |  |  |  | 2023 | 1795000 |  |  | 1795000 | UNDER CONSTRUCTION
DURHAM | SR 1321 (HILLANDALE ROAD) | DURHAM | I-85 TO NC 147 (DURHAM FREEWAY) IN DURHAM. PEDESTRIAN IMPROVEMENTS. |  | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | U-4726HN | Exempt | CMAQ, L |  |  |  |  | 2025 | 1965000 |  |  | 1965000
DURHAM | CARPENTER - FLETCHER ROAD | DURHAM | WOODCROFT PARKWAY (CITY MAINTAINED ) TO SR 1945 (ALSTON AVENUE). CONSTRUCT BIKE LANES AND SIDEWALKS. |  | Bike & Ped | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | U-4726HO | Division 5 | BGANY, L, TADA | 2025 | 27000 |  |  | 2025 | 7881000 | 2023 | 10000 | 7918000
DURHAM | LASALLE STREET | DURHAM | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 0.69 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5703 | Division 5 | L, TAANY | 2022 | 150000 |  |  | 2025 | 1300000 |  |  | 1450000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | RAYNOR STREET | DURHAM | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 0.35 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5704 | Division 5 | L, TAANY | 2022 | 169000 |  |  | 2025 | 580000 |  |  | 749000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | NC 54 | DURHAM | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 0.57 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5708 | Division 5 | L, SRTS, TAANY | 2021 | 177000 |  |  | 2025 | 430000 |  |  | 607000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | US 501 BYPASS (NORTH DUKE STREET) | DURHAM | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 2.42 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5715 | Division 5 | L, TAANY | 2021 | 296000 |  |  | 2025 | 2680000 |  |  | 2976000 | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM
DURHAM | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | DURHAM | NC 55 TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 1.11 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5720 | Division 5 | HP, L(M), TAANY | 2025 | 1800000 |  |  | 2026 | 4600000 |  |  | 6400000 | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT.
DURHAM | NC 157 / SR 1322 (GUESS ROAD) | DURHAM | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 1.14 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5834 | Division 5 | L, L(M), TAANY | 2025 | 204000 |  |  | 2026 | 2104000 |  |  | 2308000
DURHAM | NC 55 (APEX HIGHWAY) | DURHAM | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 1.07 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5835 | Division 5 | L, TAANY | 2030 | 50000 |  |  | 2031 | 1196000 | 2023 | 105000 | 1351000
DURHAM | THIRD FORK CREEK TRAIL | DURHAM | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 1.6 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5837 | Division 5 | L, TAANY | 2024 | 963000 |  |  | 2026 | 5800000 |  |  | 6763000
DURHAM | DURHAM RAIL TRAIL | DURHAM | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 1.75 | Bike & Ped | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | EB-5904 | Division 5 | BGDA, DP, L, TAANY, TADA |  |  |  |  | 2025 | 17409000 |  |  | 17409000 | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT
DURHAM | SR 1158 (CORNWALLIS ROAD) | DURHAM | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | 1.17 | Bike & Ped | Transition | 5 | Durham-Chapel Hill-Carrboro MPO | U-4724 | Pre-STI (Transition) | BGANY, BGDA, L | 2024 | 2233000 |  |  | 2025 | 4978000 |  |  | 7211000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | US 15 / US 501 NORTHBOUND | NCDOT | REPLACE BRIDGE 310080 OVER SR 1308 (CORNWALLIS ROAD) IN DURHAM. | 0.25 | Highway | Bridges | 5 | Durham-Chapel Hill-Carrboro MPO | B-5674 | Region C | BFP | 2026 | 700000 |  |  | 2028 | 5449000 |  |  | 6149000
DURHAM | VARIOUS | NCDOT | CONSTRUCT ACCESS ROAD AND INTERSECTION IMPROVEMENTS AT SR 1004 (OLD OXFORD ROAD), SR 1794 (TEKNIKA PARKWAY), AND SR 2635 (INTERNATIONAL DRIVE). |  | Highway | Economic Development | 5 | Durham-Chapel Hill-Carrboro MPO | HE-0007 | Division 5 | [10 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK.
DURHAM | SR 1004 (OLD OXFORD ROAD) | NCDOT | FIRST AVE (MERCK DRIVEWAY). CONSTRUCT RIGHT TURN LANE. | 0.1 | Highway | Economic Development | 5 | Durham-Chapel Hill-Carrboro MPO | HE-0007A | Division 5 | T |  |  |  |  | 2024 | 165000 | 2023 | 25000 | 190000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK.
DURHAM | SR 1794 (TEKNIKA PARKWAY) | NCDOT | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | 0.5 | Highway | Economic Development | 5 | Durham-Chapel Hill-Carrboro MPO | HE-0007B | Division 5 | T | 2024 | 95000 |  |  | 2025 | 815000 | 2023 | 90000 | 1000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS.
DURHAM | SR 2635 (INTERNATIONAL DRIVE) | NCDOT | SR 1004 (OLD OXFORD RD) TO NEW LOCATION. CONSTRUCT NEW LANES. | 0.49 | Highway | Economic Development | 5 | Durham-Chapel Hill-Carrboro MPO | HE-0007C | Division 5 | T | [6 empty] | 2023 | 600000 | 600000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
DURHAM | SR 1631 (SNOW HILL ROAD) | NCDOT | SR 1004 (OLD OXFORD ROAD) INTERSECTION. CONSTRUCT A LEFT TURN LANE AND SIGNALIZE INTERSECTION | 0.5 | Highway | Economic Development | 5 | Durham-Chapel Hill-Carrboro MPO | HE-0007D | Division 5 | T | 2026 | 50000 | 2026 | 75000 | 2027 | 700000 | 2025 | 200000 | 1025000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK.
DURHAM | I-885 | NCDOT | I-40 TO 0.4 MILES NORTH OF TW ALEXANDER DRIVE. PAVEMENT REHABILITATION. | 2.28 | Highway | Interstate Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | HI-0023 | Statewide Mobility | NHPIM |  |  |  |  | 2024 | 4363000 |  |  | 4363000
DURHAM | I-85 | NCDOT | ORANGE COUNTY LINE TO US 15 / US 501 IN DURHAM. PAVEMENT REHABILITATION | 2.49 | Highway | Interstate Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | I-5941 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2024 | 13489000 |  |  | 13489000
DURHAM | I-40 | NCDOT | US 15 / US 501 TO EAST OF NC 147. PAVEMENT REHABILITATION. | 9.24 | Highway | Interstate Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | I-5993 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2026 | 38131000 |  |  | 38131000 | TO BE LET WITH I-5994
DURHAM | ERWIN ROAD |  | ERWIN ROAD AT CORNWALLIS ROAD. CONSTRUCT TURN LANES. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Durham-Chapel Hill-Carrboro MPO | HN-0013 | Exempt | CMAQ, T(M) | 2026 | 100000 |  |  | 2027 | 746000 | 2024 | 258000 | 1104000
DURHAM | CORNWALLIS ROAD |  | CORNWALLIS ROAD AND ALSTON AVENUE. CONSTRUCT TURN LANES. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Durham-Chapel Hill-Carrboro MPO | HN-0014 | Exempt | CMAQ, T(M) | 2026 | 44000 |  |  | 2027 | 546000 | 2024 | 248000 | 838000
DURHAM | VARIOUS | DURHAM | DESIGN AND INSTALL PEDESTRIAN AND VEHICLE WAYFINDING SIGNAGE TO FACILITATE NAVIGATION TO POINTS OF INTEREST AND PARKING IN DURHAM. |  | Highway | Other | 5 | Durham-Chapel Hill-Carrboro MPO | C-5605H | Exempt | CMAQ, L(M) |  |  |  |  | 2024 | 605000 |  |  | 605000
DURHAM | DURHAM | NCDOT | CONSTRUCT EV CHARGING STATIONS ALONG I-85, US 70, AND POSSIBLY I-40. |  | Highway | Other | 5 | Durham-Chapel Hill-Carrboro MPO | HO-0017 | Exempt | DP, L(M) |  |  |  |  | 2025 | 6080000 |  |  | 6080000 | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT
DURHAM | DURHAM | NCDOT | INSTALL EV CHARGING EQUIPMENT TO SUPPORT EQUITABLE ELECTRIFICATION IN THE CITY OF DURHAM. |  | Highway | Other | 5 | Durham-Chapel Hill-Carrboro MPO | HO-0022 | Exempt | DP, L |  |  |  |  | 2025 | 5000000 |  |  | 5000000 | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT
DURHAM | I-40 | NCDOT | ORANGE COUNTY LINE TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM | 10.626 | Highway | Pre-STI (Historic) | 5 | Durham-Chapel Hill-Carrboro MPO | I-3306B | [11 empty] | COMPLETE
DURHAM | NC 54 | NCDOT | NC 55 IN DURHAM. INSTALL CONCRETE PEDESTRIAN REFUGE ISLANDS IN ALL QUADRANTS. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2005C | Region C | HSIP |  |  |  |  | 2024 | 75000 |  |  | 75000
DURHAM | SR 1303 (PICKETT ROAD) | NCDOT | SR 1116 (GARRETT ROAD)/(LUNA LANE) INTERSECTION IN DURHAM. INSTALL ALL WAY STOP. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2005D | Division 5 | HSIP | 2024 | 2000 |  |  | 2024 | 40000 |  |  | 42000
DURHAM | US 15 / US 501 BUSINESS | NCDOT | NC 751 (ACADEMY ROAD) INTERCHANGE IN DURHAM. INSTALL GUARDRAIL. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2005E | Region C | HSIP |  |  |  |  | 2024 | 175000 |  |  | 175000
DURHAM | SR 1973 (PAGE ROAD) | NCDOT | CHURCHILL HALL/ARBY'S/MCDONALD DRIVEWAY. INSTALL DIRECTIONAL CROSSOVER. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2005H | Division 5 | HSIP |  |  |  |  | 2025 | 20000 |  |  | 20000
DURHAM | SR 1327 (GREGSON STREET) | NCDOT | SR 1327 (GREGSON STREET) AT KNOX STREET. INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2005L | Division 5 | HSIP |  |  |  |  | 2025 | 110000 |  |  | 110000
DURHAM | NC 55 (ALSTON AVENUE) | NCDOT | SR 1670 (GEER STREET) IN DURHAM. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNAL HEADS. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2005M | Region C | HSIP |  |  |  |  | 2024 | 62000 |  |  | 62000
DURHAM | NC 98 | NCDOT | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2005N | Region C | HSIP, L, T | 2025 | 500000 |  |  | 2026 | 1785000 |  |  | 2285000
DURHAM | NC 98 NC 98 | NCDOT | NC 98 NC 98 AT SR 1815 (MINERAL SPRINGS ROAD). CONSTRUCT RIGHT TURN LANES AND SIDEWALK. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2005S | Region C | HSIP |  |  |  |  | 2025 | 700000 |  |  | 700000
DURHAM | NC 54 (MIAMI BOULEVARD) | NCDOT | SR 1978 (HOPSON ROAD) INTERSECTION. CONSTRUCT MULTI-USE PATH ALONG NC 54 NORTH OF THE INTERSECTION AND UPGRADE CROSSWALKS. |  | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2405AH | Division 5 | HSIP |  |  |  |  | 2026 | 150000 |  |  | 150000
DURHAM | NC 157 (GUESS ROAD) | NCDOT | NC 157 (GUESS ROAD) FROM DURHAM MUNICIPAL LIMITS TO ORANGE COUNTY LINE. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2405B | Region C | HSIP |  |  |  |  | 2025 | 223000 |  |  | 223000
DURHAM | SR 1110 (BARBEE CHAPEL ROAD) | NCDOT | SR 1110 (BARBEE CHAPEL ROAD) AT DOWNING CREEK PARKWAY/HALES WOOD ROAD. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2405I | Division 5 | HSIP | 2025 | 2000 | 2025 | 2000 | 2025 | 120000 |  |  | 124000
DURHAM | US 501 BUSINESS | NCDOT | MAYNARD AVENUE INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS AND CONNECT TO THE DURHAM SIGNAL SYSTEM. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2405M | Region C | HSIP | 2025 | 25000 |  |  | 2025 | 177000 |  |  | 202000
DURHAM | US 501 (ROXBORO ROAD) | NCDOT | RIPPLING STREAM ROAD INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | HS-2405P | Region C | HSIP | 2025 | 5000 | 2025 | 5000 | 2025 | 123000 |  |  | 133000
DURHAM | US 501 BUSINESS (ROXBORO STREET) | NCDOT | US 501 BUSINESS (ROXBORO STREET) AT SR 1443 (HORTON ROAD) AND SR 1641 (DENFIELD STREET). CONSTRUCT LEFT TURN LANES | 0.5 | Highway | Safety | 5 | Durham-Chapel Hill-Carrboro MPO | W-5705AI | Region C | HSIP |  |  |  |  | 2025 | 1320000 |  |  | 1320000
DURHAM | NC 55 (APEX HIGHWAY) | NCDOT | AT CORNWALLIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | HP-0018 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 |  |  | 3000000
DURHAM | I-40 | NCDOT | NC 55 (ALSTON AVENUE) TO I-885 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | 0.53 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | I-5707 | Statewide Mobility | NHP | 2025 | 800000 | 2025 | 190000 | 2027 | 9299000 |  |  | 10289000
DURHAM | US 15 / US 501 | NCDOT | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5717 | Statewide Mobility | NHP |  |  |  |  | 2030 | 53300000 |  |  | 53300000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067
DURHAM | US 70 (MIAMI BOULEVARD) | NCDOT | LYNN ROAD TO EAST OF SR 2095 (PAGE ROAD EXTENSION). UPGRADE TO CONTROLLED-ACCESS FACILITY AND CONVERT SR 1811 AT-GRADE INTERSECTION TO INTERCHANGE. | 5 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5720
DURHAM | US 70 | NCDOT | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). |  | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5720C | [11 empty] | PROJECT DELETED - WORK TO BE ACCOMPLISHED UNDER U-5720B
DURHAM | NC 751 (HOPE VALLEY ROAD) | NCDOT | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5745 | Region C | T | 2019 | 435000 |  |  | 2019 | 1313000 | 2019 | 624000 | 2372000 | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT-OF-WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
DURHAM | NC 54 | NCDOT | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | 1.64 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5774C | Not Funded | T | NOT FUNDED | 934000 | NOT FUNDED | 267000 | NOT FUNDED | 11599000 | NOT FUNDED |  | 12800000
DURHAM | NC 54 | NCDOT | FALCONBBRIDGE ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 0.5 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5774D | [11 empty] | SCOPE INCLUDED IN U-5774F
DURHAM | NC 54 | NCDOT | SR 1110 (FARRINGTON ROAD). CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION. | 0.5 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5774E | [11 empty] | SCOPE INCLUDED IN U-5774F
DURHAM | I-40 | NCDOT | NC 54 INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS, INCLUDING UPGRADE OF NC 54 FROM EAST OF LITTLE CREEK TO EAST OF I-40. | 1 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5774F | Statewide Mobility | NHP | 2030 | 91500000 | 2030 | 1600000 | 2033 | 156100000 |  |  | 249200000
DURHAM | NC 54 | NCDOT | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. |  | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5774G | Not Funded | T | NOT FUNDED | 1800000 | NOT FUNDED | 800000 | NOT FUNDED | 16901000 | NOT FUNDED |  | 19501000
DURHAM | NC 54 | NCDOT | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. |  | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5774H | Not Funded | T | NOT FUNDED | 5900000 | NOT FUNDED | 726000 | NOT FUNDED | 17999000 | NOT FUNDED |  | 24625000
DURHAM | NC 54 | NCDOT | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. |  | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5774I | Not Funded | T | NOT FUNDED | 2500000 | NOT FUNDED | 617000 | NOT FUNDED | 12300000 | NOT FUNDED |  | 15417000
DURHAM | NC 54 | NCDOT | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. |  | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5774J | Not Funded | T | NOT FUNDED | 3200000 | NOT FUNDED | 420000 | NOT FUNDED | 17100000 | NOT FUNDED |  | 20720000
DURHAM | WOODCROFT PARKWAY EXTENSION | DURHAM | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | 0.24 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5823 | Division 5 | BGANY, L(M) | 2025 | 1400000 | 2025 | 1800000 | 2026 | 6000000 |  |  | 9200000 | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM
DURHAM | I-885 | NCDOT | I-40 TO NC 147 IN DURHAM. ADD LANES, REHABILITATE PAVEMENT, AND PRIORITIZE THE ADDITION OF TRANSIT ACCOMMODATIONS. | 4.82 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5934 | Statewide Mobility | NHP | 2028 | 100000 | 2028 | 300000 | 2030 | 142300000 |  |  | 142700000
DURHAM | VARIOUS | NCDOT | CITY OF DURHAM. UPGRADE ITS / SIGNAL SYSTEM. |  | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-5968 | Region C | T |  |  |  |  | 2021 | 13000000 |  |  | 13000000 | UNDER CONSTRUCTION; BUILD NC BONDS: $13 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
DURHAM | NC 55 | NCDOT | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE, UPGRADE RAMP TERMINALS, AND INCLUDE BIKE-PED FACILITIES. | 2 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-6118 | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 350000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6801000 |  |  | 7551000
DURHAM | NC 98 (HOLLOWAY STREET) | NCDOT | SR 1838 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN. INCLUDE SHARED USE PATHS ON BOTH SIDES OF THE ROADWAY AND TRANSIT STOP IMPROVEMENTS THROUGHOUT THE ENTIRETY OF THE PROJECT LIMITS, AND TRAFFIC SIGNALS WHERE NEEDED. | 0.83 | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-6120
DURHAM | NC 98 (HOLLOWAY STREET) | NCDOT | SR 1838 (JUNCTION ROAD TO WEST OF SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN. INCLUDE SHARED USE PATHS ON BOTH SIDES OF THE ROADWAY AND TRANSIT STOP IMPROVEMENTS THROUGHOUT PROJECT LIMITS, AND TRAFFIC SIGNALS WHERE NEEDED. |  | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-6120A | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10501000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17800000 |  |  | 30001000
DURHAM | NC 98 (HOLLOWAY STREET) | NCDOT | SR 1919 (LYNN ROAD) INTERSECTION. IMPROVE INTERSECTION INCLUDING ADDING LEFT-TURN LANES, SAFETY IMPROVEMENTS, AND PEDESTRIAN ACCOMMDATIONS. |  | Highway | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | U-6120B | Division 5 | HSIP, L, T | 2028 | 610000 | 2028 | 0 | 2030 | 7800000 |  |  | 8410000 | LOCAL FUNDS PROVIDED BY THE CITY OF DURHAM.
DURHAM | SR 1317 (MORREENE ROAD) | DURHAM | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | Highway | Transition | 5 | Durham-Chapel Hill-Carrboro MPO | C-4928 | Division 5 | BGDA, CMAQ, L | 2023 | 1338000 |  |  | 2025 | 11857000 | 2015 | 994000 | 14189000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS
DURHAM | SR 2220 | NCDOT | SR 1113 (POPE ROAD) TO SR 1116 (GARRETT ROAD) | 2.63 | Highway | Transition | 5 | Durham-Chapel Hill-Carrboro MPO | EB-4707B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
DURHAM | NEW ROUTE | NCDOT | EAST END CONNECTOR, NC 147 (DURHAM FREEWAY) TO NORTH OF NC 98 IN DURHAM. FOUR-LANE DIVIDED FREEWAY WITH AUXILIARY LANES, PART ON NEW LOCATION. | 2.52 | Highway | Transition | 5 | Durham-Chapel Hill-Carrboro MPO | U-0071 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
DURHAM | NC 55 (ALSTON AVENUE) | NCDOT | NC 147 (DURHAM FREEWAY) TO US 70 BUSINESS / NC 98 (HOLLOWAY STREET) IN DURHAM. WIDEN TO FOUR-LANE DIVIDED FACILITY FROM NC 147 TO MAIN STREET AND REPLACE NORFOLK SOUTHERN RAILROAD BRIDGES. MODERNIZE FROM MAIN STREET TO US 70 BUSINESS / NC 98 (HOLLOWAY ST | 0.9 | Highway | Transition | 5 | Durham-Chapel Hill-Carrboro MPO | U-3308 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
DURHAM | GODURHAM | GODURHAM | REPLACEMENT BUS. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Durham-Chapel Hill-Carrboro MPO | TA-4923 | Division 5 | 5307, 5339, L | [6 empty] | 2021 | 6184000 | 6184000 | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY
DURHAM | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | PARATRANSIT VEHICLES, BUS REFURBISHMENT, AND BUS SHELTERS. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Durham-Chapel Hill-Carrboro MPO | TA-5019A | Division 5 | [10 empty] | IN PROGRESS BY CHAPEL HILL TRANSIT
DURHAM | GO TRIANGLE TRANSIT | GOTRIANGLE | ROUGEMONT PARK-AND-RIDE. PROFESSIONAL SERVICES AND PROPERTY ACQUISITION. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Durham-Chapel Hill-Carrboro MPO | TD-5273 | Exempt | BGDA, L |  |  |  |  | 2023 | 177000 |  |  | 177000 | IN PROGRESS BY TRIANGLE TRANSIT
DURHAM | GO TRIANGLE | GO TRIANGLE | NC 98 (HOLLOWAY STREET) TRANSIT CORRIDOR. CONSTRUCT ACCESS AND BUS STOP IMPROVEMENTS. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Durham-Chapel Hill-Carrboro MPO | TD-5294 | Region C | [10 empty] | UNDER CONSTRUCTION BY GO TRIANGLE
DURHAM | GODURHAM | GODURHAM | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Durham-Chapel Hill-Carrboro MPO | TP-5108 | Public Transit | 5303, L, S | [6 empty] | 2020 | 560000 | 560000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GODURHAM | GODURHAM | PLANNING ASSISTANCE - 5307 |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Durham-Chapel Hill-Carrboro MPO | TP-5109 | Public Transit | 5307, L, S | [6 empty] | 2020 | 1920000 | 1920000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GODURHAM | GODURHAM | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Durham-Chapel Hill-Carrboro MPO | TS-5108 | Public Transit | 5307, L | [6 empty] | 2020 | 172000 | 172000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GO TRIANGLE | GO TRIANGLE | SAFETY AND SECURITY - CAMERAS. |  | Public Transportation (Transit) | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | TG-5235 | Division 5 | BGDA, L | [9 empty] | IN PROGRESS
DURHAM | GOTRIANGLE |  | THE NC 54-FALCONBRIDGE CONSTRUCTION PROJECT AIMS TO ADDRESS CRITICAL TRANSIT ACCESS AND TRANSIT OPERATIONS SAFETY CONCERNS ALONG NC 54 IN THE FALCONBRIDGE AREA IN SOUTHWESTERN DURHAM COUNTY, THEREBY INCREASING TRANSIT RIDERSHIP AND REDUCING EMISSIONS. THE PROJECT IS LOCATED WITHIN CITY OF DURHAM CITY LIMITS FROM FARRINGTON ROAD TO HUNTINGRIDGE ROAD. THE PROJECT WILL PROVIDE SAFE PEDSTRIAN CONNECTIONS FOR TRANSIT USERS TO EXISTING AND PLANNED SIGNALIZED CROSSINGS IN THIS CORRIDOR, GIVEN THE HIGH SPPEDS AND TRAFFIC VOLUMES ON NC-54. THE PROJECT INCLUDES CONSTRUCTION OF BUS STOPLANDING PADS, SHELTERS, BENCHES, BUT PULLOUT AND TAPERS, SIDEWALK, CURB AND GUTTER, CURB RAMPS, CROSSWALKS, PEDSTRIAN MEDIAN REFUDE ISLANDS, APPROPRIATE SAFETY SIGNAGE, PEDSTRIAN SIGNAL HEADS AND COMPLIMENTARY TRAFFIC SIGNAL MODIFICATIONS, AND OTHER SUPPORTING ROADWAY MODIFICATIONS. |  | Public Transportation (Transit) | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | TL-0027 | Public Transit | CMAQ, L |  |  |  |  | 2023 | 1136000 |  |  | 1136000
DURHAM | GOTRIANGLE |  | THIS TRANSIT PROJECT WILL IMPROVE 13 STOPS ON THE GOTRIANGLE 805 CORRIDOR ON WOODCROFT PARKWAY PLUS TWO STOPS ON NC 54. 12 STOPS WILL ADD ADA-COMPLIANT LANDING PADS AND CONTINUOUS PEDESTRIAN CONNECTIVITY TO THE EXISTING SIDEWALK/SIDEPATH NETWORK FROM EACH STOP WHERE NEEDED. STOP 1208 MEETS BOARDING WARRANTS FOR SEATING AND WILL ALSO INCLUDE SEATING. |  | Public Transportation (Transit) | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | TL-0052 | Public Transit | BGDA, L(M) |  |  |  |  | 2024 | 782000 |  |  | 782000
DURHAM | TRIANGLE MOBILITY HUB | GOTRIANGLE | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | Public Transportation (Transit) | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | TL-0064 | Exempt | BGDA, DP, L, L(M) |  |  |  |  | 2026 | 34500000 | 2025 | 17500000 | 52000000 | "DP" FUNDING REFLECTS RAISE GRANT AWARD.
DURHAM | GODURHAM | GODURHAM | PURCHASE BATTERY ELECTRIC BUSES. |  | Public Transportation (Transit) | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | TL-0065 | Division 5 | BGDA, L, L(M) | [6 empty] | 2027 | 1182000 | 1182000
DURHAM | GOTRIANGLE | GOTRIANGLE | PURCHASE TWO 40 FOOT BUSSES. |  | Public Transportation (Transit) | Locally Selected | 5 | Durham-Chapel Hill-Carrboro MPO | TL-6111 | Division 5 | BGDA, L, L(M) | [6 empty] | 2025 | 1360000 | 1360000
DURHAM | GODURHAM | GODURHAM | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Durham-Chapel Hill-Carrboro MPO | TO-5130 | Public Transit | SMAP | [6 empty] | 2020 | 11224000 | 11224000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GODURHAM | GODURHAM | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | TG-4738A | Public Transit | 5307, L | [6 empty] | 2023 | 22500000 | 22500000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | DURHAM COUNTY ACCESS | DURHAM COUNTY ACCESS | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | TK-6126 | Public Transit | 5311, L, S | [6 empty] | 2020 | 252000 | 252000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GODURHAM | GODURHAM | ACQUISITION OF SIX (6) ELECTRIC TRANSIT BUSES. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | TM-0043 | Public Transit | CMAQ, L | [6 empty] | 2023 | 1692000 | 1692000
DURHAM | GODURHAM | GODURHAM | GODURHAM IS PLANNING IMPROVEMENTS TO DURHAM STATION TO EXPAND EQUITABLE ACCESS TO TRANSIT, IMPROVE STATION AMENITIES, AND INCREASE CONNECTIONS TO EMPLOYMENT, HEALTHCARE AND EDUCATION OPPORTUNITIES AND CONSTRUCT 8 BUS BAYS, REDESIGNED BUS LANES, AND PLACE NEW PAVEMENT. |  | Public Transportation (Transit) | Planning | 5 | Durham-Chapel Hill-Carrboro MPO | TU-0013 | Public Transit | 5339(b), L | [6 empty] | 2023 | 13500000 | 13500000
DURHAM | GODURHAM | GODURHAM | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | TG-4738 | Public Transit | 5307, 5339, CMAQ, L | [6 empty] | 2023 | 5594000 | 5594000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GO TRIANGLE | GO TRIANGLE | ESTABLISH NEIGHBORHOOD TRANSIT CENTERS IN DURHAM. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | TG-5255 | Region C | [10 empty] | IN PROGRESS
DURHAM | VARIOUS | GODURHAM | NEIGHBORHOOD TRANSIT CENTER IN SOUTH DURHAM IN CONNECTION WITH SOUTHPOINT PARK-AND-RIDE FACILITY. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | TG-5255B | Region C
DURHAM | VARIOUS | GODURHAM | NEIGHBORHOOD TRANSIT CENTER IN SOUTHWEST DURHAM IN CONNECTION WITH PATTERSON PLACE T PARK-AND-RIDE FACILITY. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO | TG-5255E | Region C
DURHAM | GO TRIANGLE | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | TD-5286 | Region C | 5307, L, T |  |  |  |  | 2021 | 1590000 |  |  | 1590000
DURHAM | SR 1980 (CHURCH STREET) | NCDOT | NORFOLK SOUTHERN RAILROAD / NC RAILROAD TO SR 1978 (HOPSON ROAD) REALIGN AND CLOSE CROSSING 734 748M OF THE NORFOLK SOUTHERN-NORTH CAROLINA RAILROAD |  | Rail | Pre-STI (Historic) | 5 | Durham-Chapel Hill-Carrboro MPO | U-4716B | Pre-STI (Transition) | [10 empty] | PROJECT COMPLETE
DURHAM | NORFOLK SOUTHERN H LINE | NCDOT | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | 6.9 | Rail | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | P-5706 | Statewide Mobility | T | 2023 | 9328000 |  |  | 2030 | 65999000 |  |  | 75327000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS.
DURHAM | NORFOLK SOUTHERN H LINE | NCDOT | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. |  | Rail | STI (Prioritization) | 5 | Durham-Chapel Hill-Carrboro MPO | P-5717 | Region C | T | 2022 | 4378000 | 2022 | 1878000 | 2026 | 34900000 |  |  | 41156000 | RIGHT-OF-WAY IN PROGRESS.
DURHAM, ORANGE | SR 2220 (OLD CHAPEL HILL ROAD) SR 1838 (OLD DURHAM | DURHAM | US 15 / US 501 IN ORANGE COUNTY TO SR 1116 (GARRETT ROAD) IN DURHAM COUNTY. BICYCLE, PEDESTRIAN, AND TRANSIT IMPROVEMENTS; AND CONSTRUCTION OF ROUNDABOUT. | 2.7 | Bike & Ped | Pre-STI (Historic) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | EB-4707 | Pre-STI (Transition)
DURHAM, ORANGE | CENTRAL PINES REGIONAL COUNCIL |  | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | Highway | NCDOT Selected (Other Selection Process) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | HN-0026B | Exempt | CMAQ, L(M) | [6 empty] | 2024 | 3065000 | 3065000
DURHAM, ORANGE | NC 54 | NCDOT | US 15 / US 501 IN CHAPEL HILL TO NC 55 IN DURHAM. UPGRADE ROADWAY CORRIDOR. | 8.4 | Highway | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | U-5774 | [11 empty] | PARTS A THROUGH F ON EXPANDED NHS
DURHAM, ORANGE | GOTRIANGLE | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | Public Transportation (Transit) | Capital (Non-STI) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | TA-4818B | Public Transit | 5307, L, S | [6 empty] | 2024 | 2916000 | 2916000
DURHAM, ORANGE | GOTRIANGLE | GOTRIANGLE | EXPANSION BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | TA-5123B | Public Transit | 5307, L, S | [6 empty] | 2020 | 3242000 | 3242000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | GOTRIANGLE | GOTRIANGLE | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | TS-5119 | Public Transit | 5307, L | [6 empty] | 2020 | 76000 | 76000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | GODURHAM | GODURHAM | OPERATING ASSISTANCE - NEW FREEDOM - URBAN |  | Public Transportation (Transit) | Operations and Maintenance | 5, 7 | Durham-Chapel Hill-Carrboro MPO | TN-5102 | Public Transit | 5317, L | [6 empty] | 2020 | 504000 | 504000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | GOTRIANGLE | GOTRIANGLE | PLANNING ASSISTANCE |  | Public Transportation (Transit) | Planning | 5, 7 | Durham-Chapel Hill-Carrboro MPO | TP-4732A | Public Transit | 5307, L, S | [6 empty] | 2020 | 2952000 | 2952000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | GO TRIANGLE ROUTE 800 | GO TRIANGLE | PURCHASE THREE VEHICLES; CONSTRUCT STOP AND ACCESS IMPROVEMENTS; IMPROVE EXISTING FACILITY AT SOUTHPOINT TRANSIT CENTER. |  | Public Transportation (Transit) | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | TP-0001 | Region C, D | BGANY, L |  |  |  |  | 2030 | 14500000 |  |  | 14500000
DURHAM, ORANGE | GO TRIANGLE | GO TRIANGLE | CONSTRUCT BUS RAPID TRANSIT LANES ALONG US 15/501 FROM DURHAM TO CARRBORO. |  | Public Transportation (Transit) | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | TP-0004 | Region C, D | BGANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40000000 |  |  | 40000000
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. |  | Bike & Ped | Locally Selected | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | U-4726 | Division 5, 7, 8 | BGANY, BGDA, L | 2021 | 1909000 |  |  | 2021 | 11766000 |  |  | 13675000 | IN PROGRESS
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | Bike & Ped | Locally Selected | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | U-6219 | Division 5, 7, 8 | TADA |  |  |  |  | 2031 | 3803000 |  |  | 3803000
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE DURHAM PLANNING ORGANIZATION. |  | Highway | Locally Selected | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | HL-0094 | Exempt | CRPDA, L |  |  |  |  | 2025 | 2295000 |  |  | 2295000
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. |  | Highway | Locally Selected | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | U-4727 | Division 5, 7, 8 | BGDA, L | [6 empty] | 2024 | 25861000 | 25861000 | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | Highway | Locally Selected | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | U-5023 | Division 5, 7, 8 | BGANY, BGDA |  |  |  |  | 2025 | 49242000 |  |  | 49242000 | INCLUDES $137K TO BE ALLOCATED TO TG-5235; $1548K ALLOCATED TO U-4726.
DURHAM, ORANGE, CHATHAM | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | Highway | Other | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | C-5605 | Exempt | CMAQ, L(M) | 2020 | 447000 |  |  | 2020 | 6095000 | 2020 | 2051000 | 8593000 | IN PROGRESS
DURHAM, PERSON | US 501 (ROXBORO ROAD / DURHAM ROAD) | NCDOT | SR 1002 (MASON ROAD)/SR 1631 (SNOW HILL ROAD) TO PERSON COUNTY LINE; PERSON CO., US 501 FROM DURHAM COUNTY LINE TO TO 1,100 FEET SOUTH OF SR 1147 (BESSIE DANIEL ROAD), EXCLUDING 5-LANE SECTIONS. INSTALL RUMBLE STRIPS. | 16 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AD | Region C | HSIP |  |  |  |  | 2025 | 115000 |  |  | 115000
DURHAM, WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | CONSTRUCT BUS RAPID TRANSIT LANES FROM RESEARCH TRIANGLE PARK TO THE TOWN OF CARY AND FROM DOWNTOWN RALEIGH TO NORTH HILLS. PURCHASE 24 VEHICLES. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | TP-0002 | Region C | BGANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000000 |  |  | 100000000
DURHAM, WAKE | GO TRIANGLE DRX ROUTE | GO TRIANGLE | PURCHASE TWO VEHICLES AND INSTALL ELECTRIC CHARGING INFRASTRUCTURE. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | TP-0003 | Region C | BGANY, L |  |  |  |  | 2027 | 3000000 |  |  | 3000000
DURHAM, WAKE | VARIOUS PIEDMONT CORRIDOR | NCDOT | VARIOUS ROUTES AND NORFOLK SOUTHERN RAILROAD-NORTH CAROLINA RAILROAD IN DURHAM AND MORRISVILLE, SOUTH OF I-40 TO NORTH OF MCCRIMMON PARKWAY. CONSTRUCT A GRADE SEPARATION AT SR 1978 (HOPSON ROAD), EXTEND CHURCH STREET TO HOPSON ROAD, CLOSE CHURCH STREET C |  | Rail | Other | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO | U-4716
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | BO-2405 | Division 5 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | BO-2605 | Division 5 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | R-5785 | Division 5 | HF, TA |  |  |  |  | 2023 | 1100000 |  |  | 1100000 | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2005 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 5. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2020
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2020DIV | Division 5 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2020REG | Region C | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2020SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2405 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | ALL FREEWAY RAMP LOCATIONS IN DIVISION 5. BRING WRONG WAY DRIVER DETERRENCE MARKINGS UP TO STANDARD. |  | Highway | Safety | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Kerr-Tar RPO | HS-2405L | Statewide Mobility | HSIP |  |  |  |  | 2025 | 950000 |  |  | 950000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | HS-2605 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | W-5205 | [11 empty] | UNDER CONSTRUCTION
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | W-5705 | [11 empty] | IN PROGRESS; $150K NHP FUNDING APPLIED TO W-5705S.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | W-5705DIV | Division 5 | HSIP | 2020 | 104000 |  |  | 2020 | 540000 |  |  | 644000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | W-5705REG | Region C | HSIP | 2020 | 104000 |  |  | 2020 | 540000 |  |  | 644000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | W-5705SW | Statewide Mobility | HSIP | 2020 | 137000 |  |  | 2020 | 720000 |  |  | 857000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5 |  | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | W-5805 | [11 empty] | W-5805B PROJECT DELETED AT REQUEST OF DIVISION; WORK TO BE ACCOMPLISHED UNDER U-6023.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 5. |  | Rail | Rail-Highway Grade Crossing Closure | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | RC-2005 | Division 5 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. |  | Rail | Rail-Highway Grade Crossing Improvement | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | RX-2005 | Division 5 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. |  | Rail | Rail-Highway Grade Crossing Improvement | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | RX-2405 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. |  | Rail | Rail-Highway Grade Crossing Improvement | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | RX-2605 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE | NC 43 BUSINESS | ROCKY MOUNT | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 0.58 | Bike & Ped | Locally Selected | 4 | Rocky Mount Urban Area MPO | BL-0032 | Division 4 | CMAQ, L(M) | 2025 | 10000 |  |  | 2024 | 340000 | 2024 | 100000 | 450000
EDGECOMBE | US 64 WEST ALTERNATE | TARBORO | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | Bike & Ped | Locally Selected | 4 | Upper Coastal Plain RPO | BL-0064 | Exempt | CMAQ, L(M) | 2025 | 51000 |  |  | 2025 | 586000 | 2023 | 134000 | 771000
EDGECOMBE | EAST RALEIGH BOULEVARD | ROCKY MOUNT | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 2.28 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5984 | Division 4 | L, TA50200 | 2029 | 700000 |  |  | 2031 | 3700000 | 2027 | 300000 | 4700000
EDGECOMBE | US 258 | NCDOT | REPLACE BRIDGE 320022 OVER TOWN CREEK. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-4931 | Highway Fund | HFB |  |  |  |  | 2021 | 2129000 |  |  | 2129000 | COMPLETE.
EDGECOMBE | NC 33 | NCDOT | REPLACE BRIDGE 320080 OVER TAR RIVER. REPLACE BRIDGE 320049 OVER TAR RIVER OVERFLOW. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-4933 | Region A | BFP | 2025 | 860000 |  |  | 2028 | 16100000 |  |  | 16960000
EDGECOMBE | NC 111 / NC 122 | NCDOT | REPLACE BRIDGE 320011 OVER TOWN CREEK. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5655 | Highway Fund | HFB |  |  |  |  | 2021 | 1950000 |  |  | 1950000 | COMPLETE.
EDGECOMBE | NC 97 | NCDOT | REPLACE BRIDGE 320087 OVER SWIFT CREEK. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5671 | Highway Fund | HFB |  |  |  |  | 2021 | 2279000 |  |  | 2279000 | COMPLETE.
EDGECOMBE | SR 1126 (FAITH BAPTIST CHURCH ROAD) | NCDOT | REPLACE BRIDGE 320064 OVER TOWN CREEK. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-6002 | Highway Fund | HFB |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | COMPLETE.
EDGECOMBE | SR 1404 (SEVEN BRIDGES ROAD) | NCDOT | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | 0.5 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0111 | Division 4 | DP | 2020 | 420000 | 2020 | 56000 | 2021 | 5450000 |  |  | 5926000 | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
EDGECOMBE | SR 1616 (SHARP POINT ROAD) | NCDOT | REPLACE BRIDGE 320035 OVER OTTER CREEK. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0112 | Division 4 | DP |  |  |  |  | 2021 | 1112000 |  |  | 1112000 | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
EDGECOMBE | SR 1243 (LEGGETT ROAD) | NCDOT | REPLACE BRIDGE 320054 OVER TAR RIVER. | 0.25 | Highway | Bridges | 4 | Rocky Mount Urban Area MPO | BR-0241 | Highway Fund | HFB |  |  |  |  | 2021 | 3600000 |  |  | 3600000 | COMPLETE. PROJECT REPRESENTS HFB 4.R.101 PROJECT.
EDGECOMBE | NEW ROUTE | NCDOT | SR 1252 (DUNBAR ROAD) TO SR 1225 (KINGSBORO ROAD). CONSTRUCT TWO LANE ROAD ON NEW LOCATION AND IMPROVEMENTS TO SR 1225 TO SERVE KINGSBORO MEGASITE. | 2.5 | Highway | Economic Development | 4 | Upper Coastal Plain RPO | R-5868 | Division 4 | [10 empty] | UNDER CONSTRUCTION. THIS IN AN ECONOMIC DEVELOPMENT PROJECT FOR TRIANGLE TYRE.
EDGECOMBE | US 64 (FUTURE I-87) | NCDOT | SR 1225 (KINGSBORO ROAD) TO NC 33. PAVEMENT REHABILITATION. | 10.18 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6041 | Statewide Mobility | HP, NHPIM, T(M) |  |  |  |  | 2023 | 20659000 |  |  | 20659000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196.
EDGECOMBE | US 64 (FUTURE I-87) | NCDOT | REHABILITATE BRIDGES 320104, 320155, 320148, 320153, 320154, 320156, 320157, 320320, 320325, AND 320326. |  | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6041A | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION.
EDGECOMBE | US 64 (FUTURE I-87) | NCDOT | NC 33 TO MARTIN COUNTY LINE. PAVEMENT REHABILITATION. | 10.45 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6042 | Statewide Mobility | HP, NHPIM, T(M) |  |  |  |  | 2023 | 19700000 |  |  | 19700000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196.
EDGECOMBE | US 64 (FUTURE I-87) | NCDOT | REHABILITATE BRIDGE 320327 AND 320328. |  | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6042A | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 300000 |  |  | 300000 | UNDER CONSTRUCTION.
EDGECOMBE | US 64 BUSINESS (RALEIGH BOULEVARD) | NCDOT | AT NC 43 (FAIRVIEW ROAD) IN ROCKY MOUNT. INSTALL PEDESTRIAN SIGNAL HEADS. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004AB | Region A | HSIP |  |  |  |  | 2024 | 28000 |  |  | 28000
EDGECOMBE | US 258 | NCDOT | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | 1.77 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5949 | Division 4 | T | 2029 | 1901000 | 2029 | 2600000 | 2031 | 54000000 |  |  | 58501000
EDGECOMBE | NC 111 (WILSON STREET) | NCDOT | US 64 ALTERNATE (WESTERN BOULEVARD) TO NC 122 (MCNAIR ROAD). WIDEN TO THREE LANES. | 2.28 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-4424 | Division 4 | T |  |  |  |  | 2023 | 24347000 |  |  | 24347000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE).
EDGECOMBE | SR 1250 (SPRINGFIELD ROAD) | NCDOT | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO THREE LANES. | 1.26 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-4762 | Division 4 | T |  |  |  |  | 2019 | 6255000 | 2021 | 1995000 | 8250000 | COMPLETE. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
EDGECOMBE | CSX A LINE | CSXT RR | CCX INTERMODAL TERMINAL AND TRACK IMPROVEMENTS. |  | Rail | Other | 4 | Rocky Mount Urban Area MPO | P-5711A | Statewide Mobility | T |  |  |  |  | 2020 | 43100000 |  |  | 43100000 | UNDER CONSTRUCTION.
EDGECOMBE, HALIFAX | US 258 | NCDOT | US 258 BETWEEN THE PITT COUNTY LINE AND US 64 IN EDGECOMBE COUNTY AND BETWEEN PRINCEVILLE AND SR 1102 (MULLIN ROAD) IN HALIFAX COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS, SNOWPLOWABLE PAVEMENT MARKERS, AND RUMBLE STRIPES. | 31.69 | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | HS-2004R | Region A | HSIP |  |  |  |  | 2023 | 780000 |  |  | 780000 | UNDER CONSTRUCTION.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | BO-2404 | Division 4 | TA, TALT5 | 2024 | 250000 | 2024 | 250000 | 2024 | 5000000 | 2024 | 500000 | 6000000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | BO-2604 | Division 4 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | Bike & Ped | Other | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | R-5784 | Division 4 | HF, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2004 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 4. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2019
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | HS-2019DIV | Division 4 | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | HS-2019REG | Region A | VRU |  |  |  |  | 2023 | 300000 |  |  | 300000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | HS-2019SW | Statewide Mobility | VRU |  |  |  |  | 2023 | 400000 |  |  | 400000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2404 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2604 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5204 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5704 | [11 empty] | IN PROGRESS
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5704DIV | Division 4 | HSIP | 2020 | 144000 |  |  | 2022 | 360000 |  |  | 504000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO | W-5704REG | Region A | HSIP | 2022 | 30000 |  |  | 2020 | 455000 |  |  | 485000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5704SW | Statewide Mobility | HSIP | 2022 | 40000 |  |  | 2022 | 480000 |  |  | 520000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | W-5804
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 4. |  | Rail | Rail-Highway Grade Crossing Closure | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | RC-2004 | Division 4
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | RX-2004 | Division 4 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, WAYNE, WILSON, HALIFAX, NASH | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | RX-2404 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, WAYNE, WILSON, HALIFAX, NASH | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | RX-2604 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
EDGECOMBE, NASH | THOMAS STREET |  | CONSTRUCT PEDESTRIAN BRIDGE OVER MAIN STREET IN ROCKY MOUNT. |  | Bike & Ped | Other | 4 | Rocky Mount Urban Area MPO | BO-2417 | Exempt | HP, L | 2025 | 390000 |  |  | 2026 | 5803000 | 2025 | 1248000 | 7441000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198.
EDGECOMBE, NASH | ROCKY MOUNT | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 2.43 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5763 | Division 4 | L(M), TA50200 | 2025 | 300000 |  |  | 2026 | 1500000 | 2024 | 200000 | 2000000
EDGECOMBE, NASH | US 64 (FUTURE I-87) | NCDOT | SR 1603 (OLD CARRIAGE ROAD) TO SR 1225 (KINGSBORO ROAD). PAVEMENT REHABILITATION. | 12.63 | Highway | Interstate Maintenance | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | I-6046 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 24006000 |  |  | 24006000 | UNDER CONSTRUCTION.
EDGECOMBE, NASH | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | Highway | Other | 4 | Rocky Mount Urban Area MPO | C-5616 | Exempt | CMAQ, L | 2020 | 116000 |  |  | 2020 | 910000 | 2020 | 348000 | 1374000
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | PURCHASE AND INSTALL 20 BUS SHELTERS |  | Public Transportation (Transit) | Capital (Non-STI) | 4 | Rocky Mount Urban Area MPO | TL-0015 | Public Transit | CARES | [6 empty] | 2022 | 150000 | 150000
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | UPDATE THE TAR RIVER TANSIT AUTOMATED VEHICLE LOCATOR SYSTEM |  | Public Transportation (Transit) | Capital (Non-STI) | 4 | Rocky Mount Urban Area MPO | TL-0016 | Public Transit | CARES | [6 empty] | 2022 | 300000 | 300000
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 4 | Rocky Mount Urban Area MPO | TO-5127 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 4000000 | 4000000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Rocky Mount Urban Area MPO | TG-4785A | Public Transit | 5307, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Rocky Mount Urban Area MPO | TG-4785B | Public Transit | 5307, L | [6 empty] | 2020 | 2400000 | 2400000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Rocky Mount Urban Area MPO | TK-5180 | Public Transit | 5311, L, S | [6 empty] | 2020 | 780000 | 780000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | CSX A LINE | CSXT RR | CONSTRUCT FREIGHT RAIL AND INTERMODAL TERMINAL INFRASTRUCTURE (CCX) ALONG NATIONAL GATEWAY CORRIDOR. | 12 | Rail | Other | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | P-5711 | Statewide Mobility
EDGECOMBE, NASH | CSX A LINE | NCDOT | HIGHWAY IMPROVEMENTS |  | Rail | Other | 4 | Rocky Mount Urban Area MPO | P-5711C | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION.
FORSYTH | SMITH REYNOLDS AIRPORT (INT) | SMITH REYNOLDS AIRPORT (INT) | ACQUIRE LAND AND CLEAR TERRAIN OBSTRUCTIONS EAST OF RUNWAY 15-33 TO DRAIN AND GRADE MATERIAL IN PLACE. |  | Aviation | STI (Prioritization) | 9 | Winston-Salem Area TPO | AV-5738 | Division 9 | T |  |  |  |  | 2031 | 2450000 |  |  | 2450000 | RIGHT-OF-WAY IN PROGRESS BY AIRPORT
FORSYTH | SMITH REYNOLDS AIRPORT (INT) | SMITH REYNOLDS AIRPORT (INT) | CONSTRUCT NEW TAXILANE. |  | Aviation | STI (Prioritization) | 9 | Winston-Salem Area TPO | AV-5832 | Division 9 | T |  |  |  |  | 2027 | 15700000 |  |  | 15700000
FORSYTH | SR 4278 (SOUTH CHERRY STREET) | KERNERSVILLE | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0014 | Division 9 | BGANY, BGDA, L | 2026 | 145000 |  |  | 2027 | 2257000 | 2022 | 361000 | 2763000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | BROAD STREET | KERNERSVILLE | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 0.17 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0015 | Division 9 | BGDA, L | 2025 | 99000 |  |  | 2027 | 964000 | 2025 | 47000 | 1110000
FORSYTH | HARMON LANE | KERNERSVILLE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0016 | Division 9 | BGDA, L | 2025 | 79000 | 2025 | 19000 | 2025 | 346000 | 2024 | 10000 | 454000
FORSYTH | SOUTHERN STREET GREENWAY | KERNERSVILLE | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 0.13 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0017 | Division 9 | BGDA, L | 2026 | 50000 |  |  | 2027 | 851000 | 2025 | 146000 | 1047000
FORSYTH | BREWER ROAD | WINSTON-SALEM | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.76 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0018 | Division 9 | BGANY, BGDA, L | 2025 | 513000 |  |  | 2026 | 2326000 | 2023 | 205000 | 3044000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | LONG BRANCH TRAIL PHASE II | WINSTON-SALEM | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.28 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0019 | Division 9 | BGDA, DP, L | 2025 | 100000 |  |  | 2025 | 7500000 | 2024 | 1000000 | 8600000 | DP REPRESENT RAISE GRANT FUNDS
FORSYTH | DEPOT STREET | WALKERTOWN | US 311 (MAIN STREET) TO SR 1992 (SULLIVANTOWN ROAD) IN WALKERTOWN. CONSTRUCT SIDEWALK. | 0.22 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0020 | Division 9 | BGDA, L |  |  |  |  | 2025 | 1061000 |  |  | 1061000
FORSYTH | SALEM CREEK GREENWAY BRIDGE | WINSTON-SALEM | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0072 | Division 9 | BGDA, L | 2027 | 115000 |  |  | 2027 | 575000 | 2023 | 322000 | 1012000
FORSYTH | SHALLOWFORD ROAD |  | LOWES FOODS DRIVE TO SHALLOWFORD RESERVE DRIVE IN LEWISVILLE. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0114 | Exempt | CMAQ, CRPDA, L | 2027 | 159000 |  |  | 2028 | 948000 | 2026 | 209000 | 1316000
FORSYTH | SR 1103 (LEWISVILLE-CLEMMONS ROAD) | CLEMMONS | AUGUST DRIVE TO BRANDON FARM ROAD. CONSTRUCT SIDEWALK AND IMPROVE CROSSWALK AT WEST FORSYTH HIGH SCHOOL. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0142 | Division 9 | L(M), TADA | 2025 | 44000 |  |  | 2026 | 263000 | 2025 | 13000 | 320000
FORSYTH | FRIENDLY ROAD; RUXTON DRIVE | WALKERTOWN | MAIN STREET TO YORK PLACE DRIVE NE. CONSTRUCT SIDEWALK ON RUXTON DRIVE AND IMPROVE WALKERTOWN ELEMENTARY SCHOOL CROSSWALK AT FRIENDLY ROAD. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0143 | Division 9 | L(M), TADA | 2026 | 13000 |  |  | 2027 | 580000 | 2025 | 13000 | 606000
FORSYTH | SR 1261 (MARTY LANE) | CLEMMONS | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0145 | Division 9 | BGDA, CRPDA, L(M) | 2027 | 197000 |  |  | 2028 | 1444000 | 2026 | 236000 | 1877000
FORSYTH | LEWISVILLE | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 1.9 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | C-5705 | Exempt | CMAQ, L | 2027 | 100000 |  |  | 2028 | 1512000 | 2023 | 155000 | 1767000
FORSYTH | BRUSHY FORK GREENWAY | WINSTON-SALEM | WATERWORKS ROAD TO REYNOLDS PARK ROAD IN WINSTON-SALEM. PAVED MULTI-USE TRAIL. | 2.2 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-4020 | Pre-STI (Transition)
FORSYTH | BRUSHY FORK GREENWAY | WINSTON-SALEM | WATERWORKS ROAD TO OLD GREENSBORO ROAD |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-4020A | [11 empty] | COMPLETE
FORSYTH | BRUSHY FORK GREENWAY | WINSTON-SALEM | OLD GREENSBORO ROAD TO LOWERY STREET |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-4020B | [11 empty] | COMPLETE
FORSYTH | FAIRLAWN DRIVE | WINSTON-SALEM | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.39 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5952 | Division 9 | BGANY, BGDA, L | 2022 | 248000 |  |  | 2025 | 741000 |  |  | 989000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 4000 (UNIVERSITY PARKWAY) | WINSTON-SALEM | SR-1686 (SHATTALON DRIVE) TO ROBIN WOOD LANE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.3 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5953 | Division 9 | BGDA, L |  |  |  |  | 2025 | 635000 |  |  | 635000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM
FORSYTH | GRIFFITH ROAD | WINSTON-SALEM | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 1.07 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5954 | Division 9 | BGANY, L | 2025 | 293000 |  |  | 2026 | 3680000 | 2025 | 40000 | 4013000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 1348 (ROBINHOOD ROAD) | WINSTON-SALEM | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5955 | Division 9 | BGANY, BGDA, L(M) | 2022 | 66000 |  |  | 2025 | 828000 | 2025 | 53000 | 947000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 1992 (SULLIVANTOWN ROAD) | WALKERTOWN | US 311 AT HARLEY DRIVE TO WALKERTOWN HIGH/MIDDLE SCHOOL IN WALKERTOWN. INSTALL BICYCLE AND PEDESTRIAN FACILITIES AND CONSTRUCT SIDEWALK. | 0.44 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5956 | Division 9 | BGDA, L |  |  |  |  | 2025 | 868000 |  |  | 868000
FORSYTH | SR 2648 (OLD WINSTON ROAD) | KERNERSVILLE | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 0.09 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5957 | Division 9 | BGANY, BGDA, L | 2021 | 36000 |  |  | 2024 | 232000 |  |  | 268000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SR 3000 (IDOLS ROAD) | CLEMMONS | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5959 | Division 9 | BGANY, L | 2025 | 245000 | 2025 | 420000 | 2027 | 150000 | 2025 | 192000 | 1007000 | IN PROGRESS
FORSYTH | SR 1101 (HARPER ROAD) | CLEMMONS | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-5960 | Division 9 | BGANY, L | 2025 | 257000 | 2025 | 200000 | 2026 | 2671000 | 2021 | 125000 | 3253000 | IN PROGRESS
FORSYTH | SR 1101 (HARPER ROAD) | CLEMMONS | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | EB-6040 | Division 9 | BGDA, L | 2025 | 112000 | 2025 | 20000 | 2026 | 1455000 | 2022 | 66000 | 1653000
FORSYTH | PIEDMONT REGIONAL GREENWAY | WINSTON-SALEM | LINVILLE ROAD NEAR SALEM LAKE TO HASTINGS HILL ROAD. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | U-4741OK | Division 9 | L, TADA | 2025 | 900000 |  |  | 2027 | 1998000 | 2025 | 123000 | 3021000
FORSYTH | NC 67 (SILAS CREEK PARKWAY) | WINSTON-SALEM | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5722 | Division 9 | BGANY, BGDA, L, TAANY, TADA | 2022 | 1340000 |  |  | 2025 | 8318000 | 2025 | 40000 | 9698000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | BARBARA JANE AVENUE | WINSTON-SALEM | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5810 | Division 9 | BGDA, L, TAANY | 2025 | 5000 |  |  | 2025 | 671000 | 2025 | 10000 | 686000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SALEM CREEK GREENWAY | WINSTON-SALEM | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.04 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5812 | Division 9 | L, TAANY |  |  |  |  | 2026 | 10400000 | 2020 | 150000 | 10550000
FORSYTH | US 158 / US 421 / NC 150 (SALEM PARKWAY) | WINSTON-SALEM | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.52 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5840 | Division 9 | BGDA, L, TAANY, TADA |  |  |  |  | 2024 | 3730000 |  |  | 3730000 | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION
FORSYTH | SR 1122 (JONESTOWN ROAD) | WINSTON-SALEM | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-5920 | Division 9 | L, TAANY | 2025 | 200000 | 2025 | 800000 | 2026 | 900000 | 2025 | 200000 | 2100000
FORSYTH | US 158 / US 421 (SALEM PARKWAY) | WINSTON-SALEM | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | Bike & Ped | STI (Prioritization) | 9 | Winston-Salem Area TPO | EB-6008 | Division 9 | CMAQ, CRPDA, L(M), TAANY | 2025 | 408000 |  |  | 2026 | 5444000 | 2020 | 339000 | 6191000
FORSYTH | BRUSHY FORK GREENWAY | WINSTON-SALEM | LOWERY STREET TO REYNOLDS PARK ROAD | 0.53 | Bike & Ped | Transition | 9 | Winston-Salem Area TPO | EB-4020C | Pre-STI (Transition) | BGANY, L |  |  |  |  | 2025 | 2158000 |  |  | 2158000 | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | SALISBURY RIDGE ROAD | NCDOT | REPLACE BRIDGE 330243 OVER NC 150 IN WINSTON-SALEM. | 0.25 | Highway | Bridges | 9 | Winston-Salem Area TPO | B-5770 | Division 9 | BGOFF |  |  |  |  | 2022 | 6001000 |  |  | 6001000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | NC 67 (WESTBOUND SILAS CREEK PARKWAY) | NCDOT | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | 0.25 | Highway | Bridges | 9 | Winston-Salem Area TPO | B-5950 | Region D | BFP | 2026 | 800000 | 2026 | 3100000 | 2027 | 8500000 |  |  | 12400000
FORSYTH | SR 1109 (KINNAMON ROAD) | NCDOT | REPLACE BRIDGE 330135 OVER I-40. |  | Highway | Bridges | 9 | Winston-Salem Area TPO | BR-0075 | Division 9 | BGOFF | 2027 | 700000 | 2027 | 100000 | 2029 | 12000000 |  |  | 12800000
FORSYTH | THIRD STREET; FOURTH STREET; FIFTH STREET; | NCDOT | REPLACE BRIDGES 330185, 330191, AND 330203 OVER US 52 / US 311 IN DOWNTOWN WINSTON-SALEM. | 0.5 | Highway | Bridges | 9 | Winston-Salem Area TPO | HB-0031 | Division 9 | BGOFF | 2026 | 950000 | 2026 | 50000 | 2027 | 9500000 |  |  | 10500000
FORSYTH | POLO ROAD | NCDOT | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | 0.25 | Highway | Bridges | 9 | Winston-Salem Area TPO | HB-0033 | Division 9 | BFP | 2027 | 300000 | 2027 | 300000 | 2029 | 6000000 |  |  | 6600000
FORSYTH | SIXTEENTH STREET | NCDOT | REPLACE BRIDGE 330390 OVER RAIL CORRIDOR AND BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | 0.5 | Highway | Bridges | 9 | Winston-Salem Area TPO | HB-0036 | Division 9 | BGOFF | 2026 | 210000 | 2026 | 210000 | 2027 | 4200000 |  |  | 4620000
FORSYTH | SR 2377 (OLD GREENSBORO ROAD NE) | NCDOT | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | Highway | Bridges | 9 | Winston-Salem Area TPO | U-6059A | Division 9 | BGOFF | 2026 | 4229000 | 2026 | 1100000 | 2028 | 6800000 |  |  | 12129000
FORSYTH | NEW ROUTE | NCDOT | SR 4001 (REYNOLDS BOULEVARD) TO SR 2264 (AKRON DRIVE) AT INTERSECTION OF SR 1763 (INDIANA AVENUE) IN WINSTON-SALEM. CONSTRUCT ACCESS ROAD. | 0.34 | Highway | Economic Development | 9 | Winston-Salem Area TPO | U-6231 | Division 9 | L, T |  |  |  |  | 2021 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR COOK MEDICAL.
FORSYTH | I-40 | NCDOT | 0.3 MILE EAST OF SR 3153 (HANES MALL BOULEVARD) TO 0.9 MILE EAST OF NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM AND SR 2747 (CLEMMONSVILLE ROAD) IN WINSTON-SALEM TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION AND REHABILITATION OF BRIDGES 330161, 330162, 330444, 330448, 330449,330508, AND 330509. | 13.66 | Highway | Interstate Maintenance | 9 | Winston-Salem Area TPO | I-5795 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2020 | 23814000 |  |  | 23814000 | UNDER CONSTRUCTION
FORSYTH | I-40 | NCDOT | SR 1101 (HARPER ROAD) IN CLEMMONS TO EAST OF US 421 / BUSINESS 40 IN WINSTON-SALEM. PAVEMENT REHABILITATION. | 5.97 | Highway | Interstate Maintenance | 9 | Winston-Salem Area TPO | I-5952 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION. DELETE I-5952A. WORK ACCOMPLISHED UNDER I-5795.
FORSYTH | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | KERNERSVILLE | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0015 | Exempt | BGANY, BGDA, L(M) | 2024 | 282000 |  |  | 2025 | 3413000 | 2022 | 821000 | 4516000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | US 311 (MAIN STREET) | WALKERTOWN | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 0.5 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0016 | Exempt | BGDA, L | 2024 | 90000 |  |  | 2024 | 515000 | 2024 | 10000 | 615000
FORSYTH | NC 8 (GERMANTON ROAD) | NCDOT | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0059 | Region D | BGDA, CMAQ, HF, L(M) | 2024 | 1059000 | 2024 | 570000 | 2026 | 3036000 | 2023 | 151000 | 4816000 | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS
FORSYTH | (LEWISVILLE-CLEMMONS ROAD) SR 1103 |  | LEWISVILLE-CLEMMONS ROAD INTERSECTION AT HOLDER ROAD IN CLEMMONS. INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0125 | Exempt | CRPDA, L | 2024 | 236000 |  |  |  |  | 2024 | 15000 | 251000
FORSYTH | US 311 (HARLEY DRIVE) | WALKERTOWN | US 311 (MAIN STREET) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0153 | Division 9 | BGDA, L(M) | 2026 | 13000 |  |  | 2027 | 1487000 | 2025 | 13000 | 1513000
FORSYTH | US 421 (SALEM PARKWAY) | WINSTON-SALEM | SILAS CREEK PARKWAY TO MARTIN LUTHER KING JR DRIVE. REPLACE EXISTING LIGHTING ON SALEM PARKWAY WITH LED LIGHTING. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0154 | Exempt | CRPDA, L(M) |  |  |  |  | 2026 | 960000 | 2025 | 40000 | 1000000
FORSYTH | NEW ROUTE | WINSTON-SALEM | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | 1.09 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-2925C | Division 9 | BGANY, BGDA, L |  |  |  |  | 2025 | 1358000 | 2021 | 453000 | 1811000 | UNDER CONSTRUCTION, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | WINSTON-SALEM | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | 1.01 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-5539A | Division 9 | BGANY, L(M) | 2025 | 600000 |  |  | 2026 | 2188000 |  |  | 2788000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022
FORSYTH | SR 1173 (WILLIAMS ROAD) | LEWISVILLE | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | 0.28 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-5617 | Division 9 | BGANY, L(M) |  |  |  |  | 2023 | 2109000 |  |  | 2109000 | UNDER CONSTRUCTION.
FORSYTH | SR 1308 (LEWISVILLE-VIENNA ROAD) | LEWISVILLE | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-6154 | Division 9 | BGANY, BGDA, L | 2023 | 474000 |  |  | 2025 | 1867000 | 2023 | 341000 | 2682000 | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022. RIGHT-OF-WAY IN PROGRESS
FORSYTH | WEST FIRST STREET | WINSTON-SALEM | REPLACE BRIDGE 330296 OVER NORFOLK SOUTHERN RAILWAY IN WINSTON-SALEM. | 0.25 | Highway | Municipal Bridge | 9 | Winston-Salem Area TPO | B-5007 | Division 9 | BFPOFF | 2023 | 600000 |  |  | 2025 | 6100000 |  |  | 6700000
FORSYTH | OLD GREENSBORO ROAD | WINSTON-SALEM | REPLACE BRIDGE 330330 OVER BRUSHY FORK CREEK. | 0.25 | Highway | Municipal Bridge | 9 | Winston-Salem Area TPO | HM-0004 | Division 9 | BFPOFF | 2027 | 300000 | 2027 | 475000 | 2028 | 2800000 | 2026 | 1240000 | 4815000
FORSYTH | SR 2667 (HASTINGS HILL ROAD) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, BRIDGE NO. 366 OVER US 421 / NC 150 / BUSINESS 40 |  | Highway | Pre-STI (Historic) | 9 | Winston-Salem Area TPO | U-2579G | [11 empty] | PROJECT COMPLETE
FORSYTH | NEW ROUTE | NCDOT | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE) TO SR 4325 (MARTIN LUTHER KING, JR. DRIVE) IN WINSTON-SALEM. MULTI-LANE FACILITY ON NEW LOCATION. | 1.81 | Highway | Pre-STI (Historic) | 9 | Winston-Salem Area TPO | U-2925 | Pre-STI (Transition) | [10 empty] | DESIGN-BUILD PROJECT COMPLETE
FORSYTH | SR 1528 (NORTH POINT BOULEVARD) | NCDOT | SR 1528 (NORTH POINT BOULEVARD) AT UNIVERSITY PLAZA SHOPPING CENTER MAIN DRIVEWAY AND BP FILLING STATION DRIVEWAY, AND SR 1528 (NORTH POINT BOULEVARD) AT NORTHPOINT DRIVE NORTHCLIFFE DRIVE. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 1 | Highway | Safety | 9 | Winston-Salem Area TPO | HS-2009H | Division 9 | HSIP |  |  | 2024 | 25000 | 2025 | 995000 |  |  | 1020000
FORSYTH | NC 150 | NCDOT | SR 2983 (FISHEL ROAD) INTERSECTION SOUTH OF WINSTON-SALEM. CONSTRUCT REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | Safety | 9 | Winston-Salem Area TPO | HS-2409A | Region D | HSIP |  |  | 2025 | 50000 | 2025 | 1100000 |  |  | 1150000
FORSYTH | SR 1725 (UNIVERSITY PARKWAY) | NCDOT | WEST 14TH STREET INTERSECTION IN WINSTON-SALEM. UPGRADE TRAFFIC SIGNAL, INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS, AND MODIFY SIDEWALK AND MEDIAN. | 0.5 | Highway | Safety | 9 | Winston-Salem Area TPO | HS-2409C | Division 9 | HSIP |  |  |  |  | 2025 | 515000 |  |  | 515000
FORSYTH | I-40 | NCDOT | US 158 (STRATFORD ROAD) |  | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | HP-0026 | Region D | BGANY |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3300000 |  |  | 3800000
FORSYTH | US 52 (FUTURE I-285) | NCDOT | US 421 (SALEM PARKWAY) - EXIT 109 TO SR 2264 (AKRON DRIVE) - EXIT 112. UPGRADE US 52 TO INTERSTATE STANDARDS (I-285) BY WIDENING EXISTING FACILIITIES TO SIX LANES. |  | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | HP-0027 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 317100000 |  |  | 377700000
FORSYTH | US 421 | NCDOT | SR 1122 (JONESTOWN ROAD) INTERSECTION IN WINSTON-SALEM. UPGRADE INTERSECTION REMOVE TWO-WAY TRAFFIC FROM US 421 NB ON RAMP, AND EXTEND ACCELERATION LANE DISTANCE ONTO MAINLINE. |  | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | HP-0031 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14900000 |  |  | 20700000
FORSYTH | I-40 / US 311 | NCDOT | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | I-5880 | Region D | NHP | 2023 | 3600000 | 2023 | 1400000 | 2025 | 26600000 |  |  | 31600000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, I-40 TO US 52. FOUR LANE EXPRESSWAY ON NEW LOCATION., INCLUDING ITS DEPLOYMENT. | 17.4 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | 1.95 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247A | Not Funded | NHP, T | NOT FUNDED | 13200000 | NOT FUNDED | 18900000 | NOT FUNDED | 39101000 | NOT FUNDED |  | 71201000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | 1.43 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247B | Region D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 149499000 |  |  | 184399000
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247CA | Region D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 261000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 140900000 |  |  | 141661000
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | 3.24 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247CB | Region D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 92002000 |  |  | 117002000
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, MUDDY CREEK. REPLACE BRIDGE NO. 221 AND BRIDGE NO. 222 |  | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247CC | [11 empty] | COMPLETE - WORK ACCOMPLISHED UNDER B-4507
FORSYTH | SR 1891 / NON-SYSTEM (PEACE HAVEN ROAD) | NCDOT | SR 1891 / NON-SYSTEM (PEACE HAVEN ROAD) - US 421 INTERCHANGE AND APPROACHES | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247CD | Statewide Mobility | [10 empty] | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247EC
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | 4.61 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247D | Region D | T | 2028 | 2299000 | 2028 | 6500000 | 2031 | 159100000 |  |  | 167899000
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | 4.53 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247EA | Region D | NHP, T | 2027 | 19700000 | 2027 | 6700000 | 2030 | 284575000 |  |  | 310975000 | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE)
FORSYTH | NEW ROUTE (FUTURE NC 452) | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE AT US 52 | 2.3 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247EB | Statewide Mobility | BGDA, NHP, T | 2025 | 517000 |  |  | 2018 | 86737000 |  |  | 87254000 | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032
FORSYTH | US 52 / FUTURE I-74 | NCDOT | NC 65 INTERCHANGE. RECONSTRUCT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2247EC | Statewide Mobility | [10 empty] | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247CD
FORSYTH | US 158 | NCDOT | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 5.21 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2577A | Region D | T | 2021 | 36300000 | 2021 | 469000 | 2024 | 128720000 |  |  | 165489000 | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE).
FORSYTH | US 158 | NCDOT | SR 1965 (BELEWS CREEK ROAD) TO NORTH OF SR 1969 (PINEY GROVE ROAD)/SR 1962 (KERNERSVILLE ROAD). WIDEN TO MULTI-LANES. | 7.53 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | R-2577B | Not Funded | T | NOT FUNDED | 38800000 | NOT FUNDED | 9700000 | NOT FUNDED | 60300000 | NOT FUNDED |  | 108800000
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO US 52. MULTI-LANE FREEWAY ON NEW LOCATION. | 17.1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579 |  | T | 2025 | 175000 | [6 empty] | 175000 | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO I-40 | 0.87 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579AA | Region D | BGDA, NHP, T |  |  |  |  | 2023 | 153665000 |  |  | 153665000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $20M CONSTRUCTION PAYBACK FY 2026-2040 (SALE 6 / 2026).
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | 3.27 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579AB | Region D | NHP, T(M) |  |  |  |  | 2022 | 310367000 |  |  | 310367000 | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | 1.41 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579C | Region D | NHP, T | 2016 | 6138000 |  |  | 2018 | 27222000 |  |  | 33360000 | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 311 TO SR 2211 (BAUX MOUNTAIN ROAD) | 3.2 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579D | Statewide Mobility | NHP |  |  |  |  | 2018 | 42380000 |  |  | 42380000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $38 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, SR 2211 (BAUX MOUNTAIN ROAD) TO NC 8 | 2.21 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579E | Statewide Mobility | NHP |  |  |  |  | 2018 | 33462000 |  |  | 33462000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $30 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, NC 8 TO WEST OF NC 66 (UNIVERSITY PARKWAY) | 2.44 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2579F | Statewide Mobility | NHP |  |  |  |  | 2018 | 26767000 |  |  | 26767000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $24 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | SR 1672 (HANES MILL ROAD) | NCDOT | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO MULTI-LANE DIVIDED FACILITY. | 0.42 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2729 | Division 9 | T | 2019 | 686000 |  |  | 2023 | 19911000 | 2020 | 1092000 | 21689000 | UNDER CONSTRUCTION; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE); $7,500,000 FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE)
FORSYTH | US 158 / US 421 / NC 150 / BUSINESS 40 | NCDOT | WEST OF FOURTH STREET TO EAST OF CHURCH STREET | 1.2 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-2827B | Region D | [10 empty] | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE | NCDOT | MACY GROVE ROAD EXTENSION, SR 1005 (EAST MOUNTAIN STREET) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. FOUR-LANE DIVIDED FACILITY ON NEW LOCATION. | 1.52 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-4734 | Division 9 | T |  |  |  |  | 2019 | 11172000 |  |  | 11172000 | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
FORSYTH | NEW ROUTE | NCDOT | PROPOSED GREAT WAGON ROAD FROM SR 1001 (SHALLOWFORD ROAD) TO SR 1308 (LEWISVILLE-VIENNA ROAD) IN LEWISVILLE. TWO LANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 0.88 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5536 | Division 9 | T | 2022 | 14792000 | 2025 | 1300000 | 2025 | 25150000 |  |  | 41242000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE)
FORSYTH | KERNERSVILLE SOUTHERN LOOP (PHASE I) | NCDOT | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) TO A TWO LANE DIVIDED FACILITY AND CONSTRUCT INTERCHANGE AT US 421 / NC 150. | 2.05 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5760 | Division 9 | T | 2022 | 11500000 | 2022 | 4000000 | 2025 | 85255000 |  |  | 100755000 | IN PROGRESS. BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE) AND $18 MILLION FOR CONSTRUCTION - PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE)
FORSYTH | NC 66 (OLD HOLLOW ROAD) | NCDOT | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO A MULTI-LANE DIVIDED FACILITY. | 1.61 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5824 | Division 9 | T | 2021 | 18798000 |  |  | 2024 | 22770000 |  |  | 41568000 | UNDER CONSTRUCTION; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE)
FORSYTH | NEW ROUTE | NCDOT | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 0.44 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-5899 | Division 9 | T | 2022 | 4300000 | 2022 | 1300000 | 2025 | 16000000 |  |  | 21600000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | NEW ROUTE | NCDOT | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.94 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6003 | Division 9 | T |  |  |  |  | 2024 | 12400000 |  |  | 12400000 | UNDER CONSTRUCTION
FORSYTH | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | NCDOT | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | 1.43 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6004 | Division 9 | BGANY, T | 2024 | 33600000 | 2026 | 3000000 | 2029 | 37425000 |  |  | 74025000 | BUILD NC BONDS: $9 MILLION FOR CONSTRUCTION - PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE)
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | NCDOT | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.17 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6005 | Division 9 | T | 2023 | 3800000 | 2023 | 900000 | 2026 | 17150000 |  |  | 21850000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $6 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE)
FORSYTH | US 421 (SALEM PARKWAY) | NCDOT | SR 2662 (LINVILLE ROAD) IN WINSTON-SALEM. UPGRADE INTERCHANGE AND REPLACE BRIDGE 330211 ON SR 2377 (OLD GREENSBORO ROAD NE) OVER NORFOLK SOUTHERN RAILROAD. | 1.5 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6059
FORSYTH | US 421 (SALEM PARKWAY) | NCDOT | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | 1 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6059B | Not Funded | T | NOT FUNDED | 12600000 | NOT FUNDED | 800000 | NOT FUNDED | 42900000 | NOT FUNDED |  | 56300000 | COORDINATE WITH U-6068
FORSYTH | SR 1969 (PINEY GROVE ROAD) | NCDOT | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.52 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6188 | Division 9 | T | 2028 | 2200000 | 2028 | 500000 | 2030 | 6800000 |  |  | 9500000
FORSYTH | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | NCDOT | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO THREE LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 2.31 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6189 | Division 9 | T | 2030 | 14600000 | 2030 | 3300000 | 2033 | 27000000 |  |  | 44900000
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | NCDOT | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | 0.25 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | U-6190 | Division 9 | T | 2028 | 2900000 | 2028 | 900000 | 2030 | 3800000 |  |  | 7600000
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158 | 2.92 | Highway | Transition | 9 | Winston-Salem Area TPO | U-2579B | Pre-STI (Transition) | NHP |  |  |  |  | 2015 | 68971000 |  |  | 68971000 | UNDER CONSTRUCTION; GARVEE BONDS: $96 MILLION FOR CONSTRUCTION - PAYBACK 2015-2026
FORSYTH | FUTURE I-74 | NCDOT | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158. STREAM RELOCATION. | 2.92 | Highway | Transition | 9 | Winston-Salem Area TPO | U-2579BA | Pre-STI (Transition) | NHP |  |  |  |  | 2021 | 9300000 |  |  | 9300000 | UNDER CONSTRUCTION
FORSYTH | FUTURE I-74 | NCDOT | CONSTRUCT NOISE WALL | 2.92 | Highway | Transition | 9 | Winston-Salem Area TPO | U-2579BB | Pre-STI (Transition) | T |  |  | 2022 | 234000 | 2023 | 2855000 |  |  | 3089000 | UNDER CONSTRUCTION
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | WINSTON-SALEM EXPRESS. PURCHASE ONE EXPANSION 40-FT BUS. |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TA-6682 | Region D
FORSYTH | WINSTON-SALEM TRANSIT AUTHORITY | WINSTON-SALEM TRANSIT AUTHORITY | PURCHASE ONE LARGE HYBRID-DIESEL REPLACEMENT BUS AND ONE SMALL HYBRID-DIESEL REPLACEMENT BUS. |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TC-0025 | Exempt | CMAQ, L(M) | [6 empty] | 2025 | 1230000 | 1230000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5339 BUS AND BUS FACILITIES GRANT |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TD-5303 | Public Transit | 5339, L | [6 empty] | 2024 | 2915000 | 2915000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TP-5105 | Public Transit | 5303, L, S | [6 empty] | 2020 | 618000 | 618000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Winston-Salem Area TPO | TS-5120 | Public Transit | 5307, L, SMAP | [6 empty] | 2024 | 127000 | 127000
FORSYTH | WINSTON SALEM TRANSIT AUTHORITY | WINSTON SALEM TRANSIT AUTHORITY | THE INNOVATIVE COORDINATED ACCESS AND MOBILITY (ICAM) GRANT WILL BE USED TO IMPROVE PARATRANSIT TRACKING AND ACCESSIBILITY THROUGH GPS AND NOTIFICATION SERVICES, AS WELL AS PROVIDE MOBILE TICKETING OPTIONS FOR WINSTON SALEM TRANSIT AUTHORITY`S (WSTA) FIXED ROUTE BUS SERVICES. |  | Public Transportation (Transit) | Locally Selected | 9 | Winston-Salem Area TPO | TL-0025 | Public Transit | 5307, L | [6 empty] | 2023 | 400000 | 400000
FORSYTH | WINSTON SALEM TRANSIT AUTHORITY | WSTA | WSTA BUS REPLACEMENTS. |  | Public Transportation (Transit) | Locally Selected | 9 | Winston-Salem Area TPO | TL-0054 | Division 9 | BGDA, L(M) | [6 empty] | 2024 | 7699000 | 7699000
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PART | PURCHASE CUTAWAY VEHICLES AND HEAVY DUTY BUSSES |  | Public Transportation (Transit) | Locally Selected | 9 | Winston-Salem Area TPO | TL-0063 | Division 9 | BGDA, L(M) | [6 empty] | 2025 | 2063000 | 2063000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Winston-Salem Area TPO | TO-5126 | Public Transit | 5307, L, SMAP | [6 empty] | 2024 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Winston-Salem Area TPO | TO-6150 | Public Transit | 5307, L | [6 empty] | 2022 | 7252000 | 7252000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TG-5126 | Public Transit | 5307, L | [6 empty] | 2024 | 9284000 | 9284000
FORSYTH | WINSTON-SALEM TRANSIT AUTHORITY | WINSTON-SALEM TRANSIT AUTHORITY | CONTINUATION OF WSTA NIGHT, SATURDAY, AND SUNDAY SERVICES. |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TM-0037 | Exempt | CMAQ, L(M) | [6 empty] | 2025 | 1013000 | 1013000
FORSYTH | WINSTON SALEM TRANSIT |  | LOW - NO EMISSIONS PROGRAM FOR THE PURCHASE OF FIVE (5) HYBRID-ELECTRIC BUSES. |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TM-0055 | Public Transit | 5339(b), L | [6 empty] | 2024 | 5233000 | 5233000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TM-5309 | Public Transit | 5316, L | [6 empty] | 2020 | 660000 | 660000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPETITIVE GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE TRANSPORTATION NEEDS OF LOW INCOME, DISABLED AND ELDERLY POPULATIONS |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TQ-6702 | Public Transit | 5310, L | [6 empty] | 2024 | 1172000 | 1172000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPETE GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE NEEDS OF LOW INCOME, DISABLED, AND ELDERLY POPULATIONS |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Winston-Salem Area TPO | TQ-6782 | Public Transit | 5310, L | [6 empty] | 2020 | 3607000 | 3607000
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Winston-Salem Area TPO | TG-5241 | Public Transit | 5307, L | [6 empty] | 2024 | 13016000 | 13016000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | WINSTON SALEM TRANSIT | WINSTON SALEM TRANSIT |  |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Winston-Salem Area TPO | TG-6731 | Public Transit | CMAQ, L | [6 empty] | 2020 | 1013000 | 1013000
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL, PASSENGER SHELTERS, PASSENGER AMENITIES, SHOP EQUIPMENT, SPARE PARTS |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Winston-Salem Area TPO | TG-6783 | Public Transit | 5307, L | [6 empty] | 2022 | 1457000 | 1457000
FORSYTH | SR 2385 (WALKERTOWN-GUTHRIE ROAD) | NCDOT | NORFOLK SOUTHERN CROSSING 722063Y IN WALKERTOWN. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Winston-Salem Area TPO | RX-2009B | Division 9 | RR |  |  |  |  | 2025 | 411000 |  |  | 411000
FORSYTH | SR 2381 (WILLSTON ROAD) | NCDOT | NORFOLK SOUTHERN CROSSING 470210K IN WALKERTOWN. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Winston-Salem Area TPO | RX-2009C | Division 9 | RR |  |  |  |  | 2026 | 601000 |  |  | 601000
FORSYTH | SR 1686 (SHATTALON DRIVE) | NCDOT | NORFOLK SOUTHERN CROSSING 722024H IN WINSTON-SALEM. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 9 | Winston-Salem Area TPO | RX-2009D | Division 9 | RR |  |  |  |  | 2027 | 492000 |  |  | 492000
FORSYTH, DAVIDSON | I-285 / US 52 / NC 8 | NCDOT | I-40 IN FORSYTH COUNTY TO SR 3010 (OLD US 52) IN DAVIDSON COUNTY. PAVEMENT REHABILITATION. | 18.55 | Highway | Interstate Maintenance | 9 | Winston-Salem Area TPO | HI-0005 | Statewide Mobility | NHPIM |  |  |  |  | 2025 | 28800000 |  |  | 28800000
FORSYTH, DAVIDSON, DAVIE | VARIOUS | WINSTON-SALEM | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | Highway | Other | 9 | Winston-Salem Area TPO | C-5620 | Exempt | CMAQ, L | 2020 | 366000 |  |  | 2020 | 5331000 | 2020 | 1098000 | 6795000 | IN PROGRESS
FORSYTH, DAVIDSON, DAVIE | VARIOUS | NCDOT | MULTIPLE FREEWAY AND EXPRESSWAY RAMPS. INSTALL LONG LIFE WRONG WAY PAVEMENT MARKINGS. |  | Highway | Safety | 9 | High Point Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Area TPO | HS-2009J | Statewide Mobility | HSIP |  |  |  |  | 2024 | 525000 |  |  | 525000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | U-4741 | Division 9 | BGANY, BGDA, L, TADA | 2022 | 788000 |  |  | 2020 | 2953000 |  |  | 3741000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | U-6221 | Division 9 | TADA |  |  |  |  | 2029 | 6149000 |  |  | 6149000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WINSTON-SALEM PLANNING ORGANIZATION. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | HL-0108 | Exempt | CRPDA, L |  |  |  |  | 2024 | 0
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-4742 | Division 9 | BGDA, L |  |  |  |  | 2020 | 875000 |  |  | 875000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-4951 | Division 9 | BGDA, L | [6 empty] | 2024 | 5589000 | 5589000 | FORMERLY U-9999D - IN PROGRESS
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | NCDOT | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | Highway | Locally Selected | 9 | Winston-Salem Area TPO | U-5022 | Division 9 | BGANY, BGDA |  |  |  |  | 2025 | 91646000 |  |  | 91646000
FORSYTH, DAVIE | I-40 | NCDOT | WEST OF NC 801 IN BERMUDA RUN TO WEST OF SR 1122 (JONESTOWN ROAD) IN WINSTON-SALEM. ADD LANES. | 7 | Highway | STI (Prioritization) | 9 | Winston-Salem Area TPO | I-0911 | [11 empty] | PARTS B AND C COMPLETE
FORSYTH, GUILFORD | I-40 | NCDOT | I-74 US 311 IN WINSTON-SALEM TO US 421 / BUSINESS 40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 10.1 | Highway | STI (Prioritization) | 7, 9 | Winston-Salem Area TPO, High Point Urban Area MPO | I-5981
FORSYTH, GUILFORD | US 158 | NCDOT | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS IN WINSTON-SALEM TO US 220 IN STOKESDALE. WIDEN TO A FOUR LANE DIVIDED FACILITY | 18.8 | Highway | STI (Prioritization) | 7, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO | R-2577
FORSYTH, GUILFORD, RANDOLPH | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE VEHICLES FOR VANPOOL FLEET EXPANSION. |  | Public Transportation (Transit) | STI (Prioritization) | 7, 8, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO, High Point Urban Area MPO | TA-6722 | Division 7, 8, 9 | L, T |  |  |  |  | 2021 | 100000 |  |  | 100000
FORSYTH, GUILFORD, WATAUGA, WILKES, YADKIN | COACH AMERICA | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE |  | Public Transportation (Transit) | Operations and Maintenance | 7, 9, 11 |  | TI-6103 | Public Transit | 5311, L, S | [6 empty] | 2020 | 3520000 | 3520000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH, SURRY | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 |  | Public Transportation (Transit) | STI (Prioritization) | 9, 11 | Northwest Piedmont RPO, Winston-Salem Area TPO | TA-6681 | Region D, F | FEDT, L, T | [6 empty] | 2020 | 466000 | 466000
FRANKLIN | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. |  | Aviation | STI (Prioritization) | 5 | Capital Area MPO | AV-5819 | Division 5 | T | 2026 | 3100000 |  |  | 2031 | 22700000 |  |  | 25800000
FRANKLIN | FRANKLIN COUNTY RAILS TO TRAILS | FRANKLINTON | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 2.82 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0053 | Exempt | CMAQ, L | 2025 | 120000 |  |  | 2025 | 3000000 | 2024 | 600000 | 3720000
FRANKLIN | MAIN STREET | FRANKLINTON | UPGRADE CROSSWALKS ALONG MAIN STREET, ADD A NEW MID-BLOCK CROSSING AT THE INTERSECTION OF WATER STREET AND MAIN STREET, AND AN IMPROVED CROSSING CONFIGURATION FOR THE FRANKLINTON TO NOVOZYMES RAIL TRAIL. | 0.5 | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | BL-0127 | Division 5 | BGDA, L(M) |  |  |  |  | 2025 | 750000 | 2025 | 85000 | 835000
FRANKLIN | SMOKE TREE WAY, NORTH MAIN STREET, HOSPITAL DRIVE |  | SMOKE TREE WAY, NORTH MAIN STREET, AND HOSPITAL DRIVE. CONSTRUCT 2245 FEET OF SIDEWALKS WITH CROSSWALK AT SMOKE TREE WAY. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | C-5610E | Exempt | CMAQ, L | 2024 | 157000 |  |  | 2025 | 550000 | 2024 | 148000 | 855000
FRANKLIN | SR 1600 (EAST RIVER ROAD) | NCDOT | REPLACE BRIDGE 340076 OVER SYCAMORE CREEK. | 0.25 | Highway | Bridges | 5 | Kerr-Tar RPO | B-5210 | Division 5 | [10 empty] | UNDER CONSTRUCTION - BRIDGE PURCHASE ORDER CONTRACT (BPOC)
FRANKLIN | SR 1609 (BAPTIST CHURCH ROAD) | NCDOT | REPLACE BRIDGE 340078 OVER TAR RIVER | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-6003 | Division 5 | BGOFF | 2029 | 430000 |  |  | 2031 | 7600000 |  |  | 8030000
FRANKLIN | US-401 | NCDOT | REPLACE BRIDGE 340056 OVER SANDY CREEK. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | HB-0024 | Division 5 | BGLT5 | 2027 | 60000 | 2027 | 180000 | 2029 | 3700000 |  |  | 3940000
FRANKLIN | (BUNN ROAD) SR 1230 | LOUISBURG | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.35 | Highway | Locally Selected | 5 | Kerr-Tar RPO | HL-0044 | Exempt | CMAQ, L | 2025 | 38000 |  |  | 2025 | 462000 | 2022 | 106000 | 606000
FRANKLIN | US 401 | NCDOT | SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG TO NC 39 IN LOUISBURG | 1.022 | Highway | Pre-STI (Historic) | 5 | Kerr-Tar RPO | R-2814E | [11 empty] | COMPLETE
FRANKLIN | NC 96 (EAST MAIN STREET) | NCDOT | CROSS STREET INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AL | Region C | HSIP | 2026 | 10000 | 2026 | 10000 | 2027 | 165000 |  |  | 185000
FRANKLIN | US 401 | NCDOT | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | 5.31 | Highway | STI (Prioritization) | 5 | Capital Area MPO, Kerr-Tar RPO | R-2814D | Division 5 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 64500000 |  |  | 80400000
FRANKLIN | US 401 / NC 39 | NCDOT | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | 1.36 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | R-3608 | Region C | T | 2030 | 8500000 | 2030 | 3400000 | 2033 | 35000000 |  |  | 46900000 | COORDINATE WITH U-6024
FRANKLIN | NC 56 | NCDOT | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO FOUR LANES. | 2.28 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | R-5893 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36300000 |  |  | 45500000
FRANKLIN | US 401 / NC 39 (BICKETT BOULEVARD) | NCDOT | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.38 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-6024 | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29800000 |  |  | 39400000 | COORDINATE WITH R-3608
FRANKLIN | CSX S-LINE | NCDOT | HOLDING AVENUE GRADE SEPARATION, ELM AVENUE IMPROVEMENTS AND BRICK STREET PEDESTRIAN CROSSING. |  | Rail | Other | 5 | Capital Area MPO | P-5753BD | Statewide Mobility
FRANKLIN | CSX S-LINE | NCDOT | MAIN STREET AND NC 96 BYPASS GRADE SEPARATION AND YOUNGSVILLE ROADWAY IMPROVEMENTS. |  | Rail | Other | 5 | Capital Area MPO | P-5753BE | Statewide Mobility
FRANKLIN, GRANVILLE, VANCE, WARREN | KERR AREA TRANSPORTATION | KERR AREA TRANSPORTATION | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Kerr-Tar RPO | TO-6103 | Public Transit | 5311, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
FRANKLIN, GRANVILLE, VANCE, WARREN | KERR AREA TRANSPORTATION | KERR AREA TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Kerr-Tar RPO | TK-6139 | Public Transit | 5311, L, S | [6 empty] | 2020 | 2048000 | 2048000 | FUNDS AUTHORIZED IN PROGRESS
FRANKLIN, LEE, VANCE, WARREN, WAKE | INTEGRATED MOBILITY DIVISION | LINK TRANSIT | THIS PLANNING PROJECT WILL FUND THE PLANNING OF MOBILITY HUBS IN SEVEN COMMUNITIES ALONG THE S-LINE PASSENGER RAIL CORRIDOR. PARTICIPATING COMMUNITIES INCLUDE SANFORD, APEX, WAKE FOREST, YOUNGSVILLE, HENDERSON, FRANLINTON, AND NORLINA. PLANNING ACTIVTIES INCLUDE FEASIBILLITY AND SITE ASSESSMENTS FOR ALL PARTNER COMMUNITIES, AND NATIONAL ENVIRONMENT POLICY ACT (NEPA) COMPLIANCE AND PRELIMINARY ENGINEERING FOR THREE COMMUNITIES. |  | Public Transportation (Transit) | Planning | 5, 8 | STATEWIDE PROJECT | TU-0016 | Public Transit | 5307, DP, L | [6 empty] | 2023 | 5170000 | 5170000 | DP FUNDING REPRESENTS RAISE GRANT FUNDS
FRANKLIN, VANCE | US 1 | NCDOT | NC 96 TO CHAPPELL LANE. INSTALL RUMBLE STRIPS. | 12.7 | Highway | Safety | 5 | Capital Area MPO, Kerr-Tar RPO | HS-2405AF | Statewide Mobility | HSIP |  |  |  |  | 2025 | 77000 |  |  | 77000
FRANKLIN, VANCE, WAKE, WARREN | CSX S-LINE | NCDOT | CSX S-LINE FROM RALEIGH TO VIRGINIA STATE LINE AND CSX SA-LINE FROM RALEIGH TO WELDON. AQUIRE RIGHT OF WAY, UPGRADE EXISTING TRACK AND CONSTRUCT NEW TRACK. | 50 | Rail | Other | 5 | Capital Area MPO, Kerr-Tar RPO | P-5753 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
FRANKLIN, WAKE | US 401 | NCDOT | NORTH OF SR 2044 (LIGON MILL ROAD) TO NC 39 IN LOUISBURG. WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY, SOME NEW LOCATION. | 18.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO, Kerr-Tar RPO | R-2814 | [11 empty] | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
FRANKLIN, WAKE | US 401 | NCDOT | NC 96 TO SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) | 5.98 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2814C | Division 5 | BGLT5 |  |  |  |  | 2018 | 36803000 |  |  | 36803000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING $33 MILLION FOR CONSTRUCTION - PAYBACK FY 2018 - FY 2032
GASTON | (TRYON COURTHOUSE ROAD) NC 274 | GASTON COUNTY | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 0.31 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | BL-0033 | Exempt | CMAQ, L | 2024 | 50000 |  |  | 2025 | 1449000 | 2023 | 188000 | 1687000
GASTON | DALLAS PARK GREENWAY (LEISURE LANE) |  | NC 275 TO TRAILHEAD FOR C-5606E NEAR SPORTSMAN DRIVE. CONSTRUCT GREEWAY. |  | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | BL-0105 | Exempt | CMAQ, L |  |  |  |  | 2026 | 424000 | 2024 | 155000 | 579000
GASTON | NC 161 | BESSEMER CITY | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 0.47 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606B | Exempt | CMAQ, L(M) | 2025 | 5000 |  |  | 2025 | 529000 | 2018 | 126000 | 660000 | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847.
GASTON | US 321 BUSINESS, NC 275/279 | DALLAS | CONSTRUCT SIDEWALKS ALONG PORTIONS OF US 321 BUSINESS AND NC 275/279 NEAR GASTON COLLEGE, INCLUDING A CROSSWALK ACROSS NC 275/279. |  | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606D | Exempt | CMAQ, L(M) |  |  |  |  | 2023 | 393000 |  |  | 393000 | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $383,779.
GASTON | NEW ROUTE | GASTON COUNTY | TECHNOLOGY PARK TO GASTON COLLEGE. CONSTRUCT GREENWAY. | 0.63 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606E | Exempt | CMAQ, L(M) |  |  |  |  | 2023 | 588000 |  |  | 588000 | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $513,300.
GASTON | NEW ROUTE | GASTON COUNTY | CONSTRUCT POSTON PARK SIDEWALK CONNECTOR. | 0.26 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606J | Exempt | CMAQ, L(M) |  |  |  |  | 2023 | 186000 |  |  | 186000 | CMAQ AWARD AMOUNT IS $334,379.
GASTON | NEW ROUTE | GASTON COUNTY | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 0.8 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606K | Exempt | CMAQ, L(M) | 2023 | 15000 |  |  | 2024 | 1581000 | 2023 | 129000 | 1725000 | CMAQ AWARD AMOUNT IS $757,478.
GASTON | NEAL HAWKINS ROAD | GASTON COUNTY | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 1.82 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606M | Exempt | CMAQ, L(M) | 2024 | 19000 |  |  | 2025 | 1364000 | 2023 | 477000 | 1860000 | CMAQ AWARD AMOUNT IS $1,488,462.
GASTON | GASTON COUNTY | GASTON COUNTY | HIGHLAND BRANCH GREENWAY, PHASE I. CONSTRUCT GREENWAY | 0.62 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5622 | Exempt | L |  |  |  |  | 2022 | 53000 |  |  | 53000 | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $1,068,204.
GASTON | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CRAMERTON | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5704 | Exempt | CMAQ, L | 2025 | 51000 |  |  | 2025 | 1363000 | 2022 | 317000 | 1731000 | CMAQ AWARD AMOUNT IS $1,183,200
GASTON | NC 7 (RIVERSIDE DRIVE) | NCDOT | HICKORY GROVE ROAD TO FUTURE RIVERLINK TRAIL EXTENSION IN CRAMERTON. CONSTRUCT SIDEWALK. | 0.2 | Bike & Ped | NCDOT Selected (Other Selection Process) | 12 | Gaston-Cleveland-Lincoln MPO | BN-0029 | Exempt | CMAQ, L(M) | 2026 | 40000 |  |  | 2026 | 2413000 | 2025 | 47000 | 2500000 | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR.
GASTON | US 29/74 (EAST FRANKLIN BOULEVARD) | GASTONIA | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 0.52 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5701 | Division 12 | L, TA50200 | 2023 | 220000 | 2023 | 75000 | 2024 | 1533000 |  |  | 1828000
GASTON | NC 279 (SOUTH NEW HOPE ROAD) | GASTONIA | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 1.12 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5743 | Division 12 | L, TA50200 |  |  |  |  | 2025 | 1285000 | 2023 | 321000 | 1606000
GASTON | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | GASTONIA | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 1.11 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5745 | Division 12 | L, TA50200 | 2024 | 900000 |  |  | 2025 | 2500000 | 2023 | 308000 | 3708000
GASTON | BEATY ROAD | MOUNT HOLLY | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.36 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5748 | Division 12 | L, TA50200 |  |  |  |  | 2027 | 800000 | 2022 | 101000 | 901000
GASTON | SOUTH MARIETTA STREET/ HILLTOP DRIVE | GASTONIA | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5768 | Division 12 | L, TA50200 | 2026 | 1200000 | 2026 | 800000 | 2026 | 1000000 | 2023 | 350000 | 3350000
GASTON | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5912 | Division 12 | L, TA50200, TAANY | 2025 | 2500000 | 2025 | 430000 | 2027 | 4500000 | 2023 | 436000 | 7866000
GASTON | CRAMERTON | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 0.14 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5913 | Division 12 | L, TA50200 |  |  |  |  | 2025 | 354000 | 2023 | 164000 | 518000
GASTON | NC 279 (NEW HOPE ROAD) | GASTONIA | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 1.03 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5975 | Division 12 | L, TA50200 |  |  |  |  | 2025 | 2065000 | 2023 | 516000 | 2581000
GASTON | SR 2200 (COX ROAD) | GASTONIA | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 0.6 | Bike & Ped | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | EB-5976 | Division 12 | L, TA50200 |  |  |  |  | 2025 | 1400000 | 2023 | 350000 | 1750000
GASTON | BESSEMER CITY | BESSEMER CITY | PHASE I: 12TH STREET, CHADWICK COURT TO KAISER ROAD. PHASE II: YELLOW JACKET LANE/BESS TOWN ROAD, 12TH STREET TO 14TH STREET (NC 274). CONSTRUCT SIDEWALKS. | 0.4 | Bike & Ped | Transition | 12 | Gaston-Cleveland-Lincoln MPO | EB-5531 | Pre-STI (Transition) | BGANY |  |  |  |  | 2022 | 300000 |  |  | 300000
GASTON | GASTONIA | GASTONIA | POSTON PARK TO SOUTH FORK RIVER GREENWAY. CONSTRUCT TRAIL. |  | Bike & Ped | Transition | 12 | Gaston-Cleveland-Lincoln MPO | EB-5533 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
GASTON | SR 1421 (MARYS GROVE ROAD) | NCDOT | REPLACE BRIDGE 350097 OVER UN-NAMED TRIBUTARY OF MUDDY FORK CREEK. | 0.25 | Highway | Bridges | 12 | Gaston-Cleveland-Lincoln MPO | B-5961 | Division 12 | BGOFF | 2021 | 67000 |  |  | 2022 | 705000 |  |  | 772000 | UNDER CONSTRUCTION.
GASTON | I-85 | NCDOT | CLEVELAND COUNTY LINE TO MILE MARKER 14. PAVEMENT REHABILITATION. | 5.91 | Highway | Interstate Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | I-5921 | Statewide Mobility | NHPIM |  |  |  |  | 2027 | 16830000 |  |  | 16830000
GASTON | NC 275 / NC 279 |  | US 321 TO US 321 BUSINESS. EXTEND RIGHT TURN LANE. ADD RIGHT TURN LANE ON SOUTHBOUND OFF RAMP FROM US 321. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 12 | Gaston-Cleveland-Lincoln MPO | HN-0027 | Region F | CRPANY, HF(M) |  |  |  |  | 2025 | 1040000 | 2024 | 205000 | 1245000 | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS
GASTON | GASTONIA | NCDOT | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. |  | Highway | Other | 12 | Gaston-Cleveland-Lincoln MPO | C-5703 | Region F | CMAQ, L(M), T(M) | 2022 | 750000 |  |  | 2022 | 11363000 |  |  | 12113000 | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1).
GASTON | NC 279 (NEW HOPE ROAD) | NCDOT | NC 279 (NEW HOPE ROAD), BURTONWOOD DRIVE TO SR 2466 (GARRISON BOULEVARD) IN GASTONIA. ADD TURN LANE. | 0.53 | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | C-4934 | Exempt | [10 empty] | UNDER CONSTRUCTION
GASTON | NC 279 | NCDOT | NC 7 (OZARK AVENUE) TO NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD). |  | Highway | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | U-2523A | [11 empty] | COMPLETE
GASTON | NC 275 | NCDOT | MILE MARKER 5.1 TO MILE MARKER 9.7. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012J | Region F | HSIP |  |  |  |  | 2024 | 152000 |  |  | 152000
GASTON | NC 279 (DALLAS CHERRYVILLE HIGHWAY) | NCDOT | SOUTH OF (ST MARK'S CHURCH ROAD) TO NORTH OF NC 275 - CONSTRUCT SAFETY IMPROVEMENTS, INCLUDING PASSING ZONES | 8.02 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | W-5212N | Region F | T |  |  |  |  | 2021 | 12750000 |  |  | 12750000 | COMPLETE; BUILD NC BOND FUNDING: $9.912 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
GASTON | NC 274 | NCDOT | SR 1443 (DAMERON ROAD) TO SR 1405 (RAMSEUR ROAD). INSTALL RUMBLE STRIPS. | 0.5 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | W-5601R | Region F | HSIP |  |  |  |  | 2023 | 90000 |  |  | 90000
GASTON | I-85 | NCDOT | I-85/US 321. GEOMETRIC SAFETY IMPROVEMENTS TO INTERCHANGE. | 0.17 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5000 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
GASTON | I-85 | NCDOT | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 9.8 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719 | Statewide Mobility | [10 empty] | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT.
GASTON | I-85 | NCDOT | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). WIDEN TO EIGHT LANES. | 6.6 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719A | Statewide Mobility | NHP, T | 2029 | 50438000 | 2029 | 12300000 | 2028 | 603197000 |  |  | 665935000 | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043.
GASTON | I-85 | NCDOT | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719B | Statewide Mobility | DP, NHP, T(M) | 2025 | 23732000 | 2025 | 47900000 | 2025 | 500495000 |  |  | 572127000 | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041.
GASTON | I-85 | NCDOT | RECONSTRUCTION OF THE PIEDMONT NORTHERN RAILROAD BRIDGE, TWO NORFOLK SOUTHERN RAILROAD BRIDGES, AND SR 2213 (GROVE STREET) BRIDGE WITHIN THE LIMITS OF SECTION A. |  | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719C | Statewide Mobility | NHP, T | 2026 | 3531000 | 2026 | 2600000 | 2026 | 232400000 |  |  | 238531000
GASTON | I-85 | NCDOT | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT AND INCIDENT MANAGEMENT. | 6.6 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719FA | Statewide Mobility | NHP, T(M) |  |  |  |  | 2028 | 4100000 |  |  | 4100000
GASTON | I-85 | NCDOT | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT AND INCIDENT MANAGEMENT. | 3.4 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719FB | Statewide Mobility | DP, T(M) |  |  |  |  | 2025 | 7150000 |  |  | 7150000 | DP REPRESENTS 2022 INFRA GRANT.
GASTON | NC 279 | NCDOT | NC 7 TO WEST OF NC 275 IN DALLAS. WIDEN TO MULTI-LANES. | 3.6 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-2523 | Region F
GASTON | NC 279 | NCDOT | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | 1.94 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-2523B | Region F | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39100000 |  |  | 60900000 | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778).
GASTON | NC 273 (SOUTH MAIN STREET) | NCDOT | TUCKASEEGEE ROAD (AT BEATTY DRIVE) TO HIGHLAND STREET (AT A & E DRIVE) IN MOUNT HOLLY. WIDEN TO FOUR-LANES DIVIDED. | 1.1 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-3633 | Region F | T |  |  |  |  | 2021 | 6315000 |  |  | 6315000 | COMPLETE; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746
GASTON | NC 7 | NCDOT | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5800 | Region F | BG50200 | 2025 | 5200000 | 2025 | 3700000 | 2025 | 19700000 |  |  | 28600000 | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719B.
GASTON | NC 27 (WEST CHARLOTTE AVENUE) | NCDOT | SR 2534 (HAWTHORNE STREET) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5819 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5200000 |  |  | 6500000
GASTON | NC 279 (NEW HOPE ROAD) | NCDOT | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4 LANES. | 0 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5821 | Division 12 | T | 2024 | 51200000 | 2026 | 17000000 | 2028 | 109800000 |  |  | 178000000 | RIGHT-OF-WAY IN PROGRESS.
GASTON | NC 274 (UNION ROAD) | NCDOT | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | 1.02 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5961 | Region F | BG50200, O | 2027 | 13401000 | 2027 | 3900000 | 2031 | 29000000 |  |  | 46301000 | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA
GASTON | US 29 (FRANKLIN BOULEVARD) | NCDOT | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5965 | Region F | BG50200, T | 2023 | 6900000 | 2023 | 300000 | 2025 | 7200000 |  |  | 14400000 | RIGHT-OF-WAY IN PROGRESS.
GASTON | US 74 (WILKINSON BOULEVARD) | NCDOT | NC 7 (CATAWBA STREET) TO SR 2209 (WESLEYAN DRIVE). IMPLEMENT ADAPTIVE SIGNAL SYSTEM. | 3.87 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6038 | Division 12 | T |  |  |  |  | 2019 | 600000 |  |  | 600000 | COMPLETE - BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE)
GASTON | US 29/US 74 (FRANKLIN BOULEVARD) | NCDOT | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | 1.06 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6043 | Division 12 | BG50200, T | 2023 | 1300000 | 2023 | 900000 | 2025 | 2700000 |  |  | 4900000 | RIGHT-OF-WAY IN PROGRESS.
GASTON | SR 2200 (COX ROAD) | NCDOT | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | 0.27 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6044 | Division 12 | BG50200 | 2029 | 49500000 | 2029 | 1500000 | 2029 | 14300000 |  |  | 65300000 | TO BE LET WITH I-5719.
GASTON | NC 275 | NCDOT | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD). | 1.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6078 | Division 12 | BGANY | 2025 | 1400000 | 2025 | 780000 | 2027 | 5500000 |  |  | 7680000
GASTON | NC 279 (NORTH NEW HOPE ROAD) | NCDOT | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6138 | Region F | BG50200 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 880000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 70000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 |  |  | 2950000
GASTON | NC 7 (EAST CATAWBA STREET) | NCDOT | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6143 | Region F | L, NHP | 2023 | 630000 | 2023 | 280000 | 2025 | 7200000 |  |  | 8110000 | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT. RIGHT-OF-WAY IN PROGRESS.
GASTON | US 29/74 (WILKINSON BOULEVARD) | NCDOT | MARKET STREET TO SR 2015 (ALBERTA AVENUE). WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRIDGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | 1.19 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6146 | Region F | HFB, T | 2022 | 8380000 | 2021 | 5500000 | 2025 | 43500000 |  |  | 57380000 | RIGHT-OF-WAY IN PROGRESS. HFB IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
GASTON | BELMONT | BELMONT | RAIL TRAIL, WOODLAWN AVENUE TO BELMONT ABBEY COLLEGE AND DOWNTOWN. CONVERT ABANDONED NCDOT RAILROAD LINE TO A PEDESTRIAN TRAIL. |  | Highway | Transition | 12 | Gaston-Cleveland-Lincoln MPO | C-5505 | Exempt | [10 empty] | IN PROGRESS
GASTON | GASTONIA TRANSIT |  | CAPITAL ROLLING STOCK |  | Public Transportation (Transit) | Capital (Non-STI) | 12 | Gaston-Cleveland-Lincoln MPO | TM-0047 | Public Transit | 5307, L | [6 empty] | 2025 | 1000000 | 1000000
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 12 | Gaston-Cleveland-Lincoln MPO | TO-5142 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 1068000 | 1068000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | OPERATING EXPENSES |  | Public Transportation (Transit) | Miscellaneous/Other | 12 | Gaston-Cleveland-Lincoln MPO | TO-6061 | Public Transit | 5307, L | [6 empty] | 2022 | 6640000 | 6640000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | ADA PARATRANSIT SERVICE |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TG-6183A | Public Transit | 5307, L | [6 empty] | 2022 | 767000 | 767000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | PREVENTATIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TG-6184B | Public Transit | 5307, L | [6 empty] | 2022 | 1260000 | 1260000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | TRANSIT APP |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TG-6804 | Public Transit | 5307, L | [6 empty] | 2020 | 63000 | 63000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTON COUNTY ACCESS | GASTON COUNTY ACCESS | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TK-6128 | Public Transit | 5311, L, S | [6 empty] | 2020 | 936000 | 936000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | GASTONIA TRANSIT PAYMENT KIOSK. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TM-0045 | Public Transit | 5307, L | [6 empty] | 2023 | 219000 | 219000
GASTON | GASTONIA TRANSIT | GASTONIA TRANSIT | PURCHASE AN EV ADA VAN. |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TM-0058 | Public Transit | 5307, L |  |  |  |  | 2025 | 117000 |  |  | 117000
GASTON | GASTON TRANSIT | GASTON TRANSIT | TRANSIT ENHANCEMENTS - PEDESTRIAN WALKWAYS |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 12 | Gaston-Cleveland-Lincoln MPO | TG-6792 | Public Transit | 5307, L |  |  |  |  | 2024 | 458000 |  |  | 458000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | P & N CORRIDOR REACTIVATION | NCDOT | CROSSING SIGNAL CONSTRUCTION. |  | Rail | Other | 12 | Gaston-Cleveland-Lincoln MPO | P-5200A | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVATION | NCDOT | CROSSING SIGN/PAVEMENT MARKING INSTALLATION. |  | Rail | Other | 12 | Gaston-Cleveland-Lincoln MPO | P-5200B | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVATION | NCDOT | RAIL TRACK CONSTRUCTION ENGINEERING OVERSIGHT. |  | Rail | Other | 12 | Gaston-Cleveland-Lincoln MPO | P-5200C | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVIATION | NCDOT | BELMONT SPUR. |  | Rail | Pre-STI (Historic) | 12 | Gaston-Cleveland-Lincoln MPO | P-5200D | Pre-STI (Transition) | BGANY | 2025 | 50000 |  |  | 2025 | 850000 |  |  | 900000
GASTON | SR 2412 (LITTLE MOUNTAIN ROAD) | NCDOT | NSR CROSSING 729966J IN GASTONIA. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Gaston-Cleveland-Lincoln MPO | RX-2012H | Division 12 | RR |  |  |  |  | 2027 | 556000 |  |  | 556000
GASTON, CLEVELAND | I-85 | NCDOT | IMPLEMENT FLOOD RISK, VULNERABILITY ASSESSMENT, AND FLOOD WARNING SYSTEM ALONG THE I-85 CORRIDOR. |  | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719D | Statewide Mobility | DP, T(M) | [6 empty] | 2025 | 200000 | 200000 | DP REPRESENTS 2022 INFRA GRANT.
GASTON, CLEVELAND | I-85 | NCDOT | INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR |  | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719E | Statewide Mobility | DP, T(M) |  |  |  |  | 2025 | 560000 | 2025 | 140000 | 700000 | DP REPRESENTS 2022 INFRA GRANT.
GASTON, CLEVELAND | I-85 | NCDOT | SOUTH CAROLINA STATE LINE TO NC 273. IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM STATEWIDE RESILIENCE, CONNECTED VEHICLE TECHNOLOGY, AND TRAVELER INFORMATION. | 26.8 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | I-5719FD | Statewide Mobility | DP, T(M) |  |  |  |  | 2025 | 6970000 |  |  | 6970000 | DP REPRESENTS 2022 INFRA GRANT.
GASTON, CLEVELAND, LINCOLN | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GASTON CLEVELAND LINCOLN PLANNING ORGANIZATION. |  | Highway | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | HL-0096 | Exempt | CRPDA, L |  |  |  |  | 2024 | 1540000 |  |  | 1540000
GASTON, CLEVELAND, LINCOLN | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GASTON-CLEVELAND-LINCOLN MPO. |  | Highway | Other | 12 | Gaston-Cleveland-Lincoln MPO | C-5606 | Exempt | [10 empty] | "HF" FUNDS ON SEGMENT I REPRESENT CONTIGENCY FUNDS
GASTON, IREDELL, CATAWBA | VARIOUS | NCDOT | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE REGIONAL CATEGORY. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO, Greater Hickory MPO | W-5212REG | Region F
GASTON, LINCOLN | LINCOLN COUNTY | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE |  | Public Transportation (Transit) | Capital (Non-STI) | 12 | Gaston-Cleveland-Lincoln MPO | TA-5185 | Division 12 | 5310, L, T
GASTON, MECKLENBURG | US 29 / US 74 | NCDOT | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 0.25 | Highway | Bridges | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | B-6051 | Region E, F | BFP, HIB | 2023 | 5100000 | 2023 | 1300000 | 2025 | 76000000 |  |  | 82400000 | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143.
GASTON, MECKLENBURG | PIEDMONT AND NORTHERN RAILROAD | NCDOT | RAIL CORRIDOR BETWEEN GASTONIA AND MOUNT HOLLY INCLUDING THE BELMONT SPUR. REACTIVATION OF RAIL CORRIDOR |  | Rail | Other | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO | P-5200
GATES | GATES COUNTY | GATES COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 1 | Albemarle RPO | TK-6129 | Public Transit | 5311 | [6 empty] | 2020 | 544000 | 544000 | FUNDS AUTHORIZED IN PROGRESS
GATES, CHOWAN | NC 32 | NCDOT | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | 17.27 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5938 | Division 1 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48640000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 160600000 |  |  | 224940000
GATES, PASQUOTANK | US 158 | NCDOT | SR 1002 (ACORN HILL ROAD) TO PASQUOTANK COUNTY LINE. MODERNIZE ROADWAY. | 3.99 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5808 | Division 1 | BGLT5, NHP | 2022 | 143000 |  |  | 2025 | 19701000 |  |  | 19844000 | RIGHT-OF-WAY IN PROGRESS.
GRAHAM | US 129, NC 143 | NCDOT | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | 4.14 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009CA | Exempt | ADHS | 2021 | 1900000 | 2021 | 2030000 | 2022 | 54624000 |  |  | 58554000 | UNDER CONSTRUCTION.
GRAHAM | NC 143 | NCDOT | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | 3.91 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009CB | Exempt | ADHS | 2021 | 3300000 | 2021 | 1300000 | 2022 | 133871000 |  |  | 138471000 | UNDER CONSTRUCTION.
GRAHAM | NC 143, NC 28 | NCDOT | NC 143 FROM NORTH OF APPALACHIAN TRAIL TO NC 28; NC 28 FROM NC 143 TO WEST OF SR 1228 (STECOAH ROAD). UPGRADE ROADWAY. | 2.4 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009CC | Exempt | ADHS | 2021 | 2300000 | 2021 | 550000 | 2023 | 77500000 |  |  | 80350000 | UNDER CONSTRUCTION.
GRAHAM | NC 28 | NCDOT | WEST OF SR 1228 (STECOAH ROAD) TO SR 1235 (GUNTERS GAP ROAD). UPGRADE ROADWAY. | 1.42 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009CD |  | ADHS, DP |  |  |  |  | 2025 | 36000000 |  |  | 36000000
GRAHAM | NC 28 | NCDOT | WEST OF SR 1231 (TOBACCO BRANCH ROAD) TO CALFPEN GAP | 2.337 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009DC | [11 empty] | COMPLETE
GRAHAM | NC 28 | NCDOT | NC 28 AT STECOAH TO WEST OF SR 1231 (TOBACCO BRANCH ROAD) | 2.859 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009DD | [11 empty] | COMPLETE
GRAHAM | NC 28 | NCDOT | SR 1238 (BILL CRISP ROAD) TO SR 1230 (HYDE TOWN ROAD). CONSTRUCT MULTI-USE PATH. |  | Highway | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | A-0009CE | Exempt | CRPLT5 |  |  |  |  | 2024 | 5000000 |  |  | 5000000
GRAHAM | NC 143 | NCDOT | NC 143 BUSINESS, SOUTH OF SR 1115 TO NORTH OF SR 1125 |  | Highway | Pre-STI (Historic) | 14 | Southwestern RPO | R-2822A | [11 empty] | COMPLETE
GRAHAM | NC 143 | NCDOT | LONG HUNGRY ROAD INTERSECTION. IMPROVE SUPERELEVATION. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014G | Region G | HSIP | 2024 | 2000 |  |  | 2025 | 515000 |  |  | 517000
GRAHAM | NC 143 | NCDOT | NC 143, WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-2822
GRAHAM | NC 143 | NCDOT | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 4.94 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-2822B | Region G | T | 2023 | 1100000 | 2023 | 1900000 |  |  |  |  | 3000000 | RIGHT-OF-WAY IN PROGRESS.
GRAHAM | NC 143 | NCDOT | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 4.94 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-2822BA | Region G | T |  |  |  |  | 2030 | 40000000 |  |  | 40000000
GRAHAM | NC 143 | NCDOT | BRIDGE 370013 OVER SNOWBIRD CREEK . REPLACE BRIDGE. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-2822BB | Region G | T |  |  |  |  | 2027 | 33500000 |  |  | 33500000
GRAHAM | NC 28 | NCDOT | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | 1.14 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839BA | Division 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17801000 |  |  | 18101000
GRAHAM | NC 28 | NCDOT | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839BB | Not Funded | T | NOT FUNDED | 46332000 | NOT FUNDED | 80000 | NOT FUNDED | 37000000 | NOT FUNDED |  | 83412000
GRAHAM | NC 28 | NCDOT | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839C | Not Funded | T | NOT FUNDED | 90000 | NOT FUNDED | 20000 | NOT FUNDED | 58300000 | NOT FUNDED |  | 58410000
GRAHAM | NC 28 | NCDOT | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839D | Not Funded | T | NOT FUNDED | 730000 | NOT FUNDED | 80000 | NOT FUNDED | 57500000 | NOT FUNDED |  | 58310000
GRAHAM | NC 28 | NCDOT | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839E | Not Funded | T | NOT FUNDED | 60000 | NOT FUNDED | 100000 | NOT FUNDED | 22000000 | NOT FUNDED |  | 22160000
GRAHAM | NEW ROUTE | NCDOT | US 129 (RODNEY ORR BYPASS) TO ROBINSVILLE HIGH SCHOOL AND MIDDLE SCHOOL. CONSTRUCT NEW ROUTE INCLUDING BRIDGE OVER CHEOAH RIVER. | 0.31 | Highway | STI (Prioritization) | 14 | Southwestern RPO | U-5866 | Division 14 | [10 empty] | UNDER CONSTRUCTION
GRAHAM, CHEROKEE | US 19, US 74, US 129 | NCDOT | US 19 BUSINESS IN ANDREWS TO US 129 SOUTH OF SR 1275 (FIVE POINT ROAD) IN ROBBINSVILLE, UPGRADE ROADWAY. | 7.71 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009A | Not Funded | NHP | NOT FUNDED | 14300000 | NOT FUNDED | 925000 | NOT FUNDED | 366000000 | NOT FUNDED |  | 381225000
GRAHAM, SWAIN | SR 1286/ SR 1383 (TSALI ROAD) | NCDOT | NC 28 TO END OF MAINTENANCE. RESURFACE AND REPAIR CORRIDOR. | 1.85 | Highway | Federal Lands Access Program | 14 | Southwestern RPO | HF-0007 | Exempt | FLAP |  |  |  |  | 2025 | 1050000 | 2023 | 150000 | 1200000 | FLAP PROJECT NC 65. AWARDED $1.2M.
GRAHAM, SWAIN | NC 28 (FONTANA ROAD) | NCDOT | US 129 TO NC 143. UPGRADE ROADWAY. | 20.4 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839
GRAHAM, SWAIN, CHEROKEE | US 19, US 74, US 129, NC 28, NC 143 | NCDOT | CORRIDOR "K", ANDREWS TO NC 28 EAST OF ALMOND. UPGRADE ROADWAY TO INCLUDE EXISTING FACILITIES AND NEW LOCATION. | 27.1 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009 | [11 empty] | Use Toll Credits on A-0009CE
GRANVILLE | NC 56 | CREEDMOOR | GREENWAY IN CREEDMOOR. CONSTRUCT BIKE-PEDESTRIAN TRAIL SYSTEM. | 2.76 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | C-5166 | Exempt | [10 empty] | PROJECT COMPLETE BY TOWN OF CREEDMOOR; LET WITH EB-5513
GRANVILLE | NC 56 | CREEDMOOR | GREENWAY IN CREEDMOOR - WESTERN SECTION | 1.15 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | C-5166B | Exempt | [10 empty] | PROJECT COMPLETE
GRANVILLE | EAST INDUSTRY DRIVE SIDEWALK |  | 250 FEET WEST OF THE INTERSECTION OF LEWIS STREET AND EAST INDUSTRY DRIVE TO SPEED EEZ CARWASH DRIVEWAY. CONSTRUCT SIDEWALK. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | BN-0002 | Exempt | CMAQ, L |  |  |  |  | 2024 | 659000 | 2024 | 10000 | 669000
GRANVILLE | EAST INDUSTRY DRIVE SIDEWALK |  | 250 FEET WEST OF THE INTERSECTION OF LEWIS STREET AND EAST INDUSTRY DRIVE TO SPEED EEZ CARWASH DRIVEWAY. CONSTRUCT SIDEWALK. | 0.85 | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | C-5610B | Exempt | CMAQ, L |  |  |  |  | 2025 | 961000 |  |  | 961000
GRANVILLE | NC 56 | CREEDMOOR | GREENWAY IN CREEDMOOR - EASTERN SECTION | 1.61 | Bike & Ped | Transition | 5 | Capital Area MPO | C-5166A | Exempt | [10 empty] | PROJECT COMPLETE
GRANVILLE | SR 1442 (DAVE WINSTON ROAD) | NCDOT | REPLACE BRIDGE 380143 OVER JOHNSON CREEK. | 0.25 | Highway | Bridges | 5 | Kerr-Tar RPO | B-5323 | Division 5 | BFPOFF |  |  |  |  | 2023 | 4183000 |  |  | 4183000 | UNDER CONSTRUCTION
GRANVILLE | SR 1629 (FLAT ROCK ROAD) | NCDOT | REPLACE BRIDGE 380199 OVER FORK CREEK. |  | Highway | Bridges | 5 | Capital Area MPO | HB-0072 | Division 5 | BGOFF, HP, T(M) |  |  |  |  | 2026 | 2201000 |  |  | 2201000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC077.
GRANVILLE | US 158 |  | US 158 AND DORSEY ROAD. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | HN-0015 | Region C | CMAQ, CRPLT5, T(M) | 2025 | 156000 |  |  | 2026 | 1945000 | 2024 | 700000 | 2801000
GRANVILLE | US 15 |  | HESTER ROAD AND US 15. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0017 | Exempt | CMAQ, HF(M) | 2025 | 140000 |  |  | 2026 | 1636000 | 2024 | 442000 | 2218000 | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS
GRANVILLE | VEAZEY ROAD |  | INTERSECTION OF VEAZEY ROAD, CENTRAL AVENUE, AND WESTBROOK. INSTALL ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | HN-0024 | Division 5 | CRPLT5, HF(M), L(M), T(M) |  |  |  |  | 2024 | 2009000 | 2024 | 700000 | 2709000 | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS
GRANVILLE | SR 1602 (MAIN STREET) | NCDOT | SR 1207 (SPRING STREET) INTERSECTION IN OXFORD. CONSTRUCT MINI-ROUNDABOUT. |  | Highway | Safety | 5 | Kerr-Tar RPO | HS-2005A | Division 5 | HSIP |  |  |  |  | 2021 | 100000 |  |  | 100000 | UNDER CONSTRUCTION
GRANVILLE | US 158 | NCDOT | US 158 BUSINESS (WILLIAMSBORO STREET) AT US 158 (OXFORD LOOP ROAD) AND SR 1646 (SE INDUSTRY DRIVE). UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405A | Region C | HSIP |  |  |  |  | 2025 | 43000 |  |  | 43000
GRANVILLE | US 15 | NCDOT | I-85 TO VIRGINIA STATE LINE. INSTALL RUMBLE STRIPS. | 37 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AE | Region C | HSIP |  |  |  |  | 2025 | 1105000 |  |  | 1105000
GRANVILLE | NC 96 (MARTIN LUTHER KING JR. AVENUE) | NCDOT | SR 1646 (E. INDUSTRY DRIVE) INTERSECTION. INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405N | Region C | HSIP |  |  |  |  | 2025 | 284000 |  |  | 284000
GRANVILLE | NC 56 | NCDOT | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-5707 | Region C | T |  |  |  |  | 2019 | 4988000 | 2021 | 989000 | 5977000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GRANVILLE | NC 56 (EAST C STREET) | NCDOT | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-6020 | Division 5 | L, T | 2024 | 100000 |  |  | 2025 | 8200000 |  |  | 8300000 | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER
GRANVILLE | SR 1136 (TALLY HO ROAD) | NCDOT | NORFOLK SOUTHERN CROSSING 734 895A IN STEM. CLOSE RAILWAY-HIGHWAY CROSSING. |  | Rail | Rail-Highway Grade Crossing Closure | 5 | Kerr-Tar RPO | Y-5500EC | Division 5 | RR |  |  |  |  | 2025 | 150000 |  |  | 150000
GRANVILLE | CHURCH STREET | NCDOT | NORFOLK SOUTHERN CROSSING 734 896G IN STEM. CLOSE RAILWAY-HIGHWAY CROSSING. |  | Rail | Rail-Highway Grade Crossing Closure | 5 | Kerr-Tar RPO | Y-5500ED | Division 5 | RR |  |  |  |  | 2025 | 300000 |  |  | 300000
GRANVILLE, DURHAM | I-85 / US 15 | NCDOT | NORTH OF SR 1637 (REDWOOD ROAD) IN DURHAM COUNTY TO SOUTH OF US 15 / SR 1100 (GATE ONE ROAD) IN GRANVILLE COUNTY. PAVEMENT REHABILITATION. | 2.03 | Highway | Interstate Maintenance | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO, Kerr-Tar RPO | HI-0001 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 5665000 |  |  | 5665000 | UNDER CONSTRUCTION
GRANVILLE, FRANKLIN, PERSON | VARIOUS | HENDERSON COUNTY | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | Highway | Other | 5 | Kerr-Tar RPO | C-5610 | Exempt | CMAQ, L | 2020 | 105000 |  |  | 2020 | 618000 | 2020 | 315000 | 1038000 | IN PROGRESS
GRANVILLE, PERSON | US 158 | NCDOT | HARDWOOD DRIVE IN PERSON COUNTY (MP 11.495) TO US TOBACCO COOPERATIVE DRIVEWAY IN GRANVILLE COUNTY (MP 15.230). INSTALL RUMBLE STRIPES. | 3.7 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AM | Statewide Mobility | HSIP |  |  |  |  | 2025 | 1331000 |  |  | 1331000
GRANVILLE, VANCE, PERSON | VARIOUS | NCDOT | VARIOUS SECONDARY ROUTES INSTALL LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405F | Division 5 | HSIP |  |  |  |  | 2024 | 1850000 |  |  | 1850000
GREENE | US 264 (FUTURE I-587) | NCDOT | PITT COUNTY LINE TO WILSON COUNTY LINE. PAVEMENT REHABILITATION. | 4.18 | Highway | Interstate Maintenance | 2 | Eastern Carolina RPO | I-6032 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 4830000 |  |  | 4830000 | COMPLETED. LET WITH I-6035. GARVEE BOND FUNDING: $4,020,000 FOR CON, PAYBACK FY 2019-2033.
GREENE | US 13 BYPASS | NCDOT | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 1.18 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5812 | Division 2 | L, T |  |  |  |  | 2020 | 9165000 | 2020 | 1290000 | 10455000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
GREENE | US 13 | NCDOT | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5943 | Division 2 | BGLT5 | 2026 | 4700000 | 2026 | 600000 | 2028 | 10500000 |  |  | 15800000
GREENE | GREENE COUNTY | GREENE COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Eastern Carolina RPO | TK-6131 | Public Transit | 5311, L, S | [6 empty] | 2020 | 460000 | 460000 | FUNDS AUTHORIZED IN PROGRESS
GREENE, LENOIR | NC 58 | NCDOT | NORTH OF SR 1745 (CUNNINGHAM ROAD) IN LENOIR COUNTY TO NORTHWEST OF CAROLINA DRIVE IN GREENE COUNTY; NORTHWESTERN INTERSECTION OF US 13 TO WILSON COUNTY LINE IN GREENE COUNTY. INSTALL RUMBLE STRIPES. |  | Highway | Safety | 2 |  | HS-2402V | Region B | HSIP |  |  |  |  | 2025 | 660000 |  |  | 660000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L EXTENSION PROGRAM |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5701 | Statewide Mobility | O, T |  |  |  |  | 2025 | 21000000 |  |  | 21000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY G. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5707 | Statewide Mobility | O, T |  |  |  |  | 2026 | 16900000 |  |  | 16900000 | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY OVER FUTURE I-73 EAST OF SR 2085 (BRYAN BOULEVARD). |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5708 | Statewide Mobility | T |  |  |  |  | 2020 | 1500000 |  |  | 1500000 | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5711 | Statewide Mobility | O, T |  |  |  |  | 2026 | 9000000 |  |  | 9000000 | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5715 | Statewide Mobility | O, T |  |  |  |  | 2028 | 11000000 |  |  | 11000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | HIGH SPEED TAXIWAY TO RUNWAY 5R-23L. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5718 | Statewide Mobility | O, T |  |  |  |  | 2027 | 4000000 |  |  | 4000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY J EXTENSION, TAXIWAY D TO TAXIWAY J2. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5800 | Statewide Mobility | O, T |  |  |  |  | 2026 | 7000000 |  |  | 7000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT NORTHWEST APRON TO INCREASE CAPACITY FOR FUTURE EXPANSION. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5802 | Statewide Mobility | O, T |  |  |  |  | 2028 | 11000000 |  |  | 11000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. |  | Aviation | STI (Prioritization) | 7 | Greensboro Urban Area MPO | AV-5803 | Statewide Mobility | O, T |  |  |  |  | 2028 | 28000000 |  |  | 28000000
GUILFORD | LATHAM PARK GREENWAY LAKE DANIEL GREENWAY; | GREENSBORO | LAKE DANIEL GREENWAY, FRIENDLY AVENUE TO JOSEPHINE BOYD STREET, AND LATHAM PARK GREENWAY AT TENNIS COURTS NEAR WENDOVER AVENUE IN GREENSBORO. REPAIR SURFACES. | 1.33 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0041 | Division 7 | L, TAANY |  |  |  |  | 2025 | 500000 |  |  | 500000
GUILFORD | VANCE ARLINGTON GREENWAY | GREENSBORO | NORTH OF FLORIDA STREET TO BRAGG STREET IN GREENSBORO. CONSTRUCT GREENWAY AND SIDEPATH. | 0.81 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0042 | Division 7 | L, TAANY |  |  |  |  | 2025 | 1200000 |  |  | 1200000
GUILFORD | HIGH POINT | HIGH POINT | SUNSET DRIVE FROM HARVELL PARK AND GOLDSTON PARK. CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. | 4.3 | Bike & Ped | Locally Selected | 7 | High Point Urban Area MPO | BL-0071 | Exempt | DP | 2025 | 2000000 |  |  |  |  | 2023 | 5000000 | 7000000 | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING.
GUILFORD | SOUTHWEST HERITAGE GREENWAY | HIGH POINT | CONSTRUCT GREENWAY ON NEW LOCATION CONNECTING HARVELL PARK AND GOLDSTON PARK. | 0.72 | Bike & Ped | Locally Selected | 7 | High Point Urban Area MPO | BL-0071A | Exempt | DP, HF, L |  |  |  |  | 2025 | 7826000 |  |  | 7826000
GUILFORD | ELM STREET | HIGH POINT | CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS FROM SUNSET DRIVE TO COMMERCE AVENUE. |  | Bike & Ped | Locally Selected | 7 | High Point Urban Area MPO | BL-0071B | Exempt | DP, L, O |  |  |  |  | 2025 | 13864000 |  |  | 13864000
GUILFORD | A & Y GREENWAY | GREENSBORO | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0116 | Division 7 | HP, L(M), TAANY | 2026 | 938000 |  |  | 2027 | 5813000 | 2024 | 1100000 | 7851000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205.
GUILFORD | A & Y GREENWAY | GREENSBORO | A & Y GREENWAY AT LAKE BRANDT. REPLACE BRIDGE, IMPROVE GREENWAY, AND IMPROVE CROSSING AT STRAWBERRY ROAD. | 0.5 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | BL-0117 | Division 7 | L, TAANY |  |  |  |  | 2025 | 2428000 | 2024 | 110000 | 2538000
GUILFORD | VARIOUS | GREENSBORO | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.86 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | C-5555E | Exempt | BGDA, CMAQ, L |  |  |  |  | 2022 | 1153000 |  |  | 1153000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | OAKDALE ROAD | JAMESTOWN | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | 0.53 | Bike & Ped | Locally Selected | 7 | High Point Urban Area MPO | C-5700 | Exempt | CMAQ, L |  |  |  |  | 2025 | 170000 | 2024 | 10000 | 180000
GUILFORD | A&Y GREENWAY | GREENSBORO | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 3.08 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | EB-6037C | Division 7 | BGANY, L, TAANY |  |  |  |  | 2023 | 8936000 |  |  | 8936000
GUILFORD | MURROW BLVD | GREENSBORO | MURROW BOULEVARD BRIDGE OVER CHURCH STREET. REPAIR BRIDGE DECK AND COMPLETE GREENWAY ACROSS STRUCTURE. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | EL-5101DR | Division 7 | BGDA, L |  |  |  |  | 2023 | 1800000 |  |  | 1800000 | UNDER CONSTRUCTION
GUILFORD | VARIOUS | GREENSBORO | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532 | Division 7 | BGANY, BGDA, L, TAANY, TADA | 2021 | 748000 |  |  | 2021 | 16154000 | 2023 | 100000 | 17002000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | RUDD STATION ROAD | GREENSBORO | CONSTRUCT SIDEWALK FROM SCOTT ROAD TO TOWNSEND ROAD. | 0.63 | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532C | Division 7 | L(M), TAANY |  |  |  |  | 2025 | 370000 |  |  | 370000
GUILFORD | VARIOUS | GREENSBORO | BIG TREE WAY-WENDOVER AVENUE TO ELKHOUND TRAIL; SHELBY DRIVE-BIG TREE WAY TO EDITH LANE; HEWITT STREET-NORWOLK STREET TO MERRITT DRIVE; BRIDFORD PARKWAY AND HORNADAY ROAD-WENDOVER AVENUE TO EXISTING WEST OF NICHOLAS ROAD. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532E | Division 7 | L, TADA |  |  |  |  | 2023 | 2436000 |  |  | 2436000 | UNDER CONSTRUCTION
GUILFORD | VARIOUS | GREENSBORO | HOLDEN ROAD SIDEWALK (1) HOLDEN ROAD FROM WALKER AVENUE TO SPRING GARDEN STREET - BOTH SIDES, 2) HOLDEN ROAD FROM DARDEN ROAD TO VANDALIA ROAD - WEST SIDE, 3) HOLDEN ROAD FROM MADISON AVENUE TO WALKER AVENUE - BOTH SIDES, 4) RANKIN ROAD / MARTIN AVENUE SOUTH SIDE OF RANKIN ROAD FROM SUMMIT AVENUE TO MARTIN AVENUE. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532F | Division 7 | L, TADA |  |  |  |  | 2025 | 1898000 |  |  | 1898000
GUILFORD | VARIOUS | GREENSBORO | SIDEWALK IMPROVEMENTS AT VARIOUS LOCATIONS IN GREENSBORO. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532G | Division 7 | L, TADA | 2022 | 70000 | 2022 | 5000 | 2025 | 1150000 |  |  | 1225000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | VARIOUS | GREENSBORO | NORTH SIDE OF SEMINOLE DRIVE FROM JOSEPHINE BOYD STREET; NORTH SIDE OF WHIPPOORWILL DRIVE FROM PENNYDALE DRIVE TO JANE STREET; AND NORTH SIDE OF WEST BESSEMER AVENUE FROM GRECADE STREET TO HILL STREET |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532H | Division 7 | L, TADA |  |  |  |  | 2025 | 670000 |  |  | 670000
GUILFORD | VARIOUS | GREENSBORO | CONSTRUCT SIDEWALKS ON HOLDEN ROAD FROM MADISON AVENUE TO FRIENDLY AVENUE; COTSWOLD AVENUE FROM BATTLEGROUND AVENUE TO COTSWOLD TERRACE (NORTH SIDE); GREENBRIAR ROAD FROM CHURCH STREET TO ELM STREET (NORTH SIDE); AND SWING ROAD FROM MARKET STREET TO BURNT POPLAR ROAD; HILLTOP ROAD FROM FAIRFAX ROAD TO GATE CITY BLVD; AND ON MCCONNELL ROAD FROM ARBOR DRIVE TO BEAUMONT AVE. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-5532I | Division 7 | L, TADA | 2025 | 400000 |  |  | 2025 | 1168000 | 2024 | 90000 | 1658000
GUILFORD | VARIOUS | NCDOT | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | Bike & Ped | Locally Selected | 7 | Greensboro Urban Area MPO | U-6220 | Division 7 | TADA |  |  |  |  | 2024 | 5702000 |  |  | 5702000
GUILFORD | VARIOUS | GREENSBORO | PEDESTRIAN AND BICYCLE PROJECTS IN THE GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO). |  | Bike & Ped | Other | 7 | Greensboro Urban Area MPO | EL-5101 | Division 7 | [10 empty] | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS - IN PROGRESS
GUILFORD | VARIOUS | GREENSBORO | SIDEWALK PROJECTS AT SELECTED LOCATIONS IN GREENSBORO. |  | Bike & Ped | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | C-5555 | Exempt | [10 empty] | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | HOLDEN ROAD; EAST LINDSAY STREET | GREENSBORO | HOLDEN ROAD, SOUTH OF MEADOWVIEW ROAD TO SPRING GARDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK ON WEST SIDE. EAST LINDSAY STREET, MURROW BOULEVARD TO BESSEMER AVENUE IN GREENSBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.89 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5716 | Division 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 1278 (UNIVERSITY PARKWAY) | HIGH POINT | SR 1300 (EAST GREEN DRIVE) TO SR 1113 (EAST MARTIN LUTHER KING JUNIOR DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.6 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5873 | Division 7 | L, TA50200 |  |  |  |  | 2024 | 360000 |  |  | 360000
GUILFORD | NC 68 (EASTCHESTER DRIVE) | HIGH POINT | JOHNSON STREET TO SR 1278 (UNIVERSITY PARKWAY) IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.65 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5874 | Division 7 | L, TA50200 |  |  |  |  | 2024 | 630000 |  |  | 630000
GUILFORD | HOLDEN ROAD | GREENSBORO | SR 4121 (WEST GATE CITY BOULEVARD) TO NORTH OF SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.56 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5876 | Division 7 | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | FARMINGTON DRIVE | GREENSBORO | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.97 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5877 | Division 7 | L, TAANY | 2022 | 25000 |  |  | 2025 | 1200000 |  |  | 1225000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | WEST MEADOWVIEW ROAD | GREENSBORO | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.47 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5878 | Division 7 | L, TAANY | 2022 | 50000 |  |  | 2025 | 950000 |  |  | 1000000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | US 220 (WENDOVER AVENUE) | GREENSBORO | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 2.21 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5883 | Division 7 | L, TAANY | 2025 | 296000 |  |  | 2025 | 2811000 |  |  | 3107000
GUILFORD | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | JAMESTOWN | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 0.7 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5889 | Division 7 | L, TA50200 | 2025 | 2500000 | 2025 | 1900000 | 2025 | 4100000 |  |  | 8500000
GUILFORD | SUMMERFIELD SOUTH GREENWAY | SUMMERFIELD | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 2.58 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5900 | Division 7 | L, TAANY | 2025 | 390000 |  |  | 2025 | 3900000 |  |  | 4290000
GUILFORD | NC 68 (EASTCHESTER DRIVE) | HIGH POINT | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.41 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5922 | Division 7 | L, TA50200 | 2025 | 130000 | 2025 | 460000 | 2025 | 540000 |  |  | 1130000
GUILFORD | CONE BOULEVARD | GREENSBORO | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 3.08 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5985 | Division 7 | L, TAANY | 2025 | 78000 |  |  | 2025 | 471000 | 2022 | 150000 | 699000
GUILFORD | BENJAMIN PARKWAY | GREENSBORO | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5986 | Division 7 | L, TAANY | 2025 | 1700000 | 2025 | 720000 | 2026 | 5200000 | 2024 | 40000 | 7660000
GUILFORD | OLD BATTLEGROUND ROAD | GREENSBORO | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5987 | Division 7 | L(M), TAANY | 2025 | 870000 | 2025 | 1100000 | 2026 | 4300000 | 2024 | 99000 | 6369000
GUILFORD | CEDROW DRIVE | HIGH POINT | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | Bike & Ped | STI (Prioritization) | 7 | High Point Urban Area MPO | EB-5989 | Division 7 | L, TA50200 | 2029 | 160000 | 2029 | 180000 | 2031 | 3750000 | 2025 | 120000 | 4210000
GUILFORD | LAWNDALE DRIVE | GREENSBORO | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5995 | Division 7 | L, TAANY | 2025 | 360000 | 2025 | 920000 | 2026 | 1700000 | 2024 | 60000 | 3040000
GUILFORD | SR 1001 (NORTH CHURCH STREET) | GREENSBORO | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 1.2 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5996 | Division 7 | L, TAANY | 2024 | 100000 |  |  | 2025 | 830000 |  |  | 930000
GUILFORD | GREEN VALLEY ROAD | GREENSBORO | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | Bike & Ped | STI (Prioritization) | 7 | Greensboro Urban Area MPO | EB-5997 | Division 7 | L, TAANY | 2025 | 45000 | 2025 | 560000 | 2025 | 1800000 | 2023 | 70000 | 2475000
GUILFORD | NEW PEDESTRIAN BRIDGE AND APPROACHES | HIGH POINT | EXISTING SIDEWALK TO PIEDMONT ENVIRONMENTAL CENTER ENTRANCE IN HIGH POINT AND JAMESTOWN. CONSTRUCT PEDESTRIAN BRIDGE OVER EAST FORK OF DEEP RIVER. | 0.5 | Bike & Ped | Transition | 7 | High Point Urban Area MPO | EB-5517 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN
GUILFORD | LATHAM PARK GREENWAY | GREENSBORO | BATTLEGROUND AVENUE TO MENDENHALL STREET IN GREENSBORO. REMOVE THROUGH LANE ON HILL STREET AND CONSTRUCT MULTI-USE PATH. | 0.11 | Bike & Ped | Transition | 7 | Greensboro Urban Area MPO | EB-5518 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | SR 4121 (EAST MAIN STREET) | JAMESTOWN | EXISTING SIDEWALK NEAR JAMESTOWN MUNICIPAL BUILDING TO YORKLEIGH LANE NEAR GUILFORD TECHNICAL COMMUNITY COLLEGE JAMESTOWN CAMPUS/RAGSDALE HIGH SCHOOL COMPLEX IN JAMESTOWN. CONSTRUCT SIDEWALK. | 0.57 | Bike & Ped | Transition | 7 | High Point Urban Area MPO | EB-5519 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN
GUILFORD | SR 2128 (BUNCH ROAD) | NCDOT | REPLACE BRIDGE 400106 OVER REEDY FORK CREEK IN OAK RIDGE. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-4958 | Division 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | NCDOT | REPLACE BRIDGE 400299 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-5356 | Statewide Mobility | BFP |  |  |  |  | 2029 | 11700000 |  |  | 11700000 | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965
GUILFORD | WILLOW ROAD | NCDOT | REPLACE BRIDGE 400352 OVER I-40 / BUSINESS 85 IN GREENSBORO. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-5713 | Division 7 | BFP | 2028 | 510000 |  |  | 2031 | 15200000 |  |  | 15710000
GUILFORD | SR 4240 (GATE CITY BOULEVARD) | NCDOT | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-5717 | Division 7 | BFP, HF | 2021 | 710000 | 2021 | 165000 | 2022 | 8957000 |  |  | 9832000 | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING
GUILFORD | PATTON AVENUE | NCDOT | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO | B-5718 | Division 7 | BFP | 2027 | 218000 | 2027 | 74000 | 2028 | 3350000 |  |  | 3642000 | COORDINATEWITH I-5965
GUILFORD | SR 1158 (JACKSON LAKE ROAD) | NCDOT | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | 0.25 | Highway | Bridges | 7 | High Point Urban Area MPO | B-5723 | Division 7 | BGOFF | 2030 | 30000 | 2030 | 570000 | 2031 | 2100000 |  |  | 2700000
GUILFORD | TUSCALOOSA STREET | NCDOT | REPLACE BRIDGE 400302 OVER US 29/US 70/US 220. |  | Highway | Bridges | 7 | Greensboro Urban Area MPO | BR-0079 | Division 7 | BGOFF | 2025 | 1800000 | 2025 | 2000000 | 2027 | 6300000 |  |  | 10100000
GUILFORD | SULLIVAN STREET | NCDOT | REPLACE BRIDGE 400331 OVER US 29/US 70/ US 220. |  | Highway | Bridges | 7 | Greensboro Urban Area MPO | BR-0080 | Division 7 | BGOFF | 2025 | 805000 | 2025 | 100000 | 2026 | 7400000 |  |  | 8305000
GUILFORD | PHILLIPS AVENUE | NCDOT | BRIDGES 400283 AND 400342 OVER US 29 / US 70 / US 220. |  | Highway | Bridges | 7 | Greensboro Urban Area MPO | BR-0081 |  | BFP | 2025 | 1150000 |  |  | 2027 | 11500000 |  |  | 12650000
GUILFORD | VARIOUS | NCDOT | CONSTUCT ROAD IMPROVEMENTS AND WETLANDS MITIGATION AT THE PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. |  | Highway | Economic Development | 7 | Greensboro Urban Area MPO | HE-0005 | Exempt | HF | 2022 | 1000000 | 2022 | 500000 | 2023 | 30000000 |  |  | 31500000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION
GUILFORD | I-85 | NCDOT | RANDOLPH COUNTY LINE TO SR 1113 (KIVETT DRIVE). PAVEMENT REHABILITATION. | 4.5 | Highway | Interstate Maintenance | 7 | High Point Urban Area MPO | I-5821 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789
GUILFORD | I-73 | NCDOT | I-85 TO SR 2085 (BRYAN BOULEVARD) IN GREENSBORO. PAVEMENT AND BRIDGE REHABILITATION. | 10.7 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5852
GUILFORD | I-73 / US 421 | NCDOT | I-85 TO I-40 | 6.62 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5852A | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / I-840 | NCDOT | I-40 TO SR 2085 (BRYAN BOULEVARD) | 3.26 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5852B | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-785 / I-840 | NCDOT | I-85 TO US 70. PAVEMENT REHABILITATION. | 2.14 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5953 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 | NCDOT | SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. PAVEMENT REHABILITATION. | 5 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5955 | Statewide Mobility | NHPIM |  |  |  |  | 2023 | 13224000 |  |  | 13224000 | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356
GUILFORD | I-40 | NCDOT | SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. REHABILITATE BRIDGES 400678, 400367, 400364, 400357, 400349, 400348, 400340, 400339, 400336, 400329, 400327, 400299, 400291, AND 400285. | 5.01 | Highway | Interstate Maintenance | 7 | Greensboro Urban Area MPO | I-5955A | Statewide Mobility | NHPIM |  |  |  |  | 2024 | 10099000 |  |  | 10099000
GUILFORD | BOULEVARD) SR 4240 (EAST GATE CITY | GREENSBORO | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 0.91 | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0046 | Division 7 | BGDA, L(M), T(DA) | 2023 | 250000 |  |  | 2025 | 3560000 |  |  | 3810000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | GREENSBORO | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 0.86 | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0047 | Division 7 | BGDA, L | 2025 | 70000 |  |  | 2025 | 550000 | 2024 | 10000 | 630000
GUILFORD | VARIOUS | GREENSBORO | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 0.5 | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0048 | Division 7 | BGDA, BGDACV, L | 2025 | 10000 |  |  | 2025 | 1000000 | 2022 | 255000 | 1265000
GUILFORD | HIGH POINT | HIGH POINT | HIGH POINT SIGNAL SYSTEM RETIMING STUDY |  | Highway | Locally Selected | 7 | High Point Urban Area MPO | HL-0060 | Exempt | CMAQ, L(M) | [6 empty] | 2023 | 1523000 | 1523000
GUILFORD | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENSBORO PLANNING ORGANIZATION. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0098 | Exempt | CRPDA, L |  |  |  |  | 2025 | 1840000 |  |  | 1840000
GUILFORD | LINDLEY ROAD | GREENSBORO | LINDLEY ROAD MODERNIZATION. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | HL-0126 | Division 7 | BGANY, L(M) |  |  | 2024 | 10000 | 2025 | 2304000 | 2024 | 10000 | 2324000
GUILFORD | VARIOUS | NCDOT | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | U-5021 | Division 7 | BGANY, BGDA |  |  |  |  | 2025 | 71364000 |  |  | 71364000 | STBG-ANYAREA FUNDS PROVIDED AS PART OF FUNDING SWAP. STATE TRUST FUNDS COULD BE USED IN LIEU OF STBG-ANYAREA ON AN ELIGIBLE STI HIGHWAY PROJECT IF DESIRED.
GUILFORD | VARIOUS | NCDOT | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. |  | Highway | Locally Selected | 7 | Greensboro Urban Area MPO | U-6085 | Division 7 | BGDA, L | [6 empty] | 2022 | 8731000 | 8731000 | IN PROGRESS
GUILFORD | VARIOUS | HIGH POINT | CITY OF HIGH POINT SIGNAL SYSTEM EXPANSION AND UPGRADE. |  | Highway | Other | 7 | High Point Urban Area MPO | C-5558 | Exempt | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-85 | NCDOT | GUILFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS |  | Highway | Other | 7 | Greensboro Urban Area MPO | C-5600E | Exempt | CMAQ, T(M) |  |  |  |  | 2025 | 1661000 |  |  | 1661000
GUILFORD | I-85 |  | TRIAD TMC UPDGRADE. (TRIANGLE AND TRIAD PIEDMONT TRAFFIC MANAGEMENT). |  | Highway | Other | 7 | Greensboro Urban Area MPO | C-5600U | Exempt | CMAQ, T(M) |  |  |  |  | 2025 | 1648000 |  |  | 1648000
GUILFORD | VARIOUS | GREENSBORO | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | Highway | Other | 7 | Greensboro Urban Area MPO | C-5607 | Exempt | CMAQ, L | 2020 | 360000 |  |  | 2020 | 2154000 | 2020 | 1080000 | 3594000
GUILFORD | VARIOUS | JAMESTOWN | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. |  | Highway | Other | 7 | High Point Urban Area MPO | C-5609F | Exempt | CMAQ, L(M) | 2025 | 40000 |  |  | 2025 | 550000 |  |  | 590000
GUILFORD | VARIOUS | HIGH POINT | SIDEWALK IMPROVEMENTS. |  | Highway | Other | 7 | High Point Urban Area MPO | C-5609L | Exempt | CMAQ, L(M) |  |  |  |  | 2024 | 1860000 |  |  | 1860000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | US 421 | NCDOT | SR 3389 (WOODY MILL ROAD) AND SR 3418 (NEELLEY ROAD) SOUTH OF GREENSBORO. CONVERT AT-GRADE INTERSECTIONS TO INTERCHANGES. | 2 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | R-2612 | Exempt
GUILFORD | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | NCDOT | SR 4228 (VICKREY CHAPEL ROAD) TO SR 1424 (HILLTOP ROAD) | 4.35 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | U-2412B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 1546 (GUILFORD COLLEGE ROAD) | NCDOT | SOUTH OF SR 1541 (WENDOVER AVENUE) TO NORTH OF SR 1560 (SAPP ROAD) | 1.244 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524AA | [11 empty] | COMPLETE
GUILFORD | I-73 / US 421 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF I-85 NEAR SR 1129 (GROOMETOWN ROAD) TO NORTH OF SR 4121 (HIGH POINT ROAD) | 4.207 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524AB | [11 empty] | COMPLETE
GUILFORD | I-73 / US 421 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF SR 4121 (HIGH POINT ROAD) TO SOUTH OF I-40 | 3.471 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524AC | [11 empty] | COMPLETE
GUILFORD | I-73 / US 421 | NCDOT | GREENSBORO WESTERN LOOP, INTERCHANGE AT PROPOSED HIGH POINT ROAD RELOCATION | 1 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524AE | [11 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / I-840 | NCDOT | GREENSBORO WESTERN LOOP, SOUTH OF I-40 TO NORTH OF SR 2147 (WEST FRIENDLY AVENUE) | 2.429 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524BA | [11 empty] | COMPLETE
GUILFORD | I-73 / I-840 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF SR 2147 (WEST FRIENDLY AVENUE) TO NORTH OF SR 2176 (BRYAN BOULEVARD) | 1.872 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524BB | [11 empty] | COMPLETE
GUILFORD | FUTURE I-840 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF SR 2176 (BRYAN BOULEVARD) TO US 220 (BATTLEGROUND AVENUE) | 3.54 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524C | Pre-STI (Transition) | NHP |  |  |  |  | 2013 | 54285000 |  |  | 54285000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING $105.9 MILLION; PAYBACK FY 2013-2024
GUILFORD | I-73 / I-840 | NCDOT | GREENSBORO WESTERN LOOP, ITS INSTALLATION |  | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2524E | [11 empty] | COMPLETE
GUILFORD | I-785 / I-840 | NCDOT | GREENSBORO EASTERN LOOP, SOUTH OF SR 3041 (CLAPP FARMS ROAD) TO US 70 RELOCATION | 1.809 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-2525A | [11 empty] | COMPLETE
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | NCDOT | AIRPARK ROAD TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. |  | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO | U-4015B | [11 empty] | COMPLETE
GUILFORD | I-85 BUSINESS/US29/70 | NCDOT | I-85 BUSINESS/US 29/70 SOUTHBOUND AND NORTHBOUND FROM RANDOLPH COUNTY LINE TO NORTH OF SR 1145 (RIVERDALE DRIVE) IN HIGH POINT. INSTALL GUARDRAIL. | 6.52 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007A | Region D | HSIP |  |  |  |  | 2021 | 540000 |  |  | 540000 | UNDER CONSTRUCTION
GUILFORD | I-85 BUSINESS/US29/70 | NCDOT | I-85 BUSINESS/US 29/70 NORTHBOUND FROM NORTH OF SR 1145 (RIVERDALE DRIVE) TO I-85 IN HIGH POINT. INSTALL GUARDRAIL. | 3.13 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007B | Region D | HSIP |  |  |  |  | 2021 | 270000 |  |  | 270000 | UNDER CONSTRUCTION
GUILFORD | I-74 AND US 29/70 | NCDOT | I-74 AND US 29/70 (I-85 BUSINESS INTERCHANGE). UPGRADE SIGNALS, PAVEMENT MARKINGS, AND SIGNING. | 1 | Highway | Safety | 7 | High Point Urban Area MPO | HS-2007D | Statewide Mobility | HSIP |  |  |  |  | 2024 | 400000 |  |  | 400000 | UNDER CONSTRUCTION
GUILFORD | NC 62 | NCDOT | NC 62 FROM WEST OF SR 1138 (TOM BALL ROAD) TO WEST OF THE ALAMANCE COUNTY LINE. INSTALL PAVEMENT MARKINGS. | 20.69 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007E | Division 7 | HSIP |  |  |  |  | 2023 | 401000 |  |  | 401000 | UNDER CONSTRUCTION
GUILFORD | US 29 | NCDOT | US 29 AT LAKEVIEW MEMORIAL PARK CEMETERY ENTRANCE. CONSTRUCT DIRECTIONAL CROSSOVER. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007G | Statewide Mobility | HSIP |  |  |  |  | 2024 | 410000 |  |  | 410000
GUILFORD | SR 4240 (EAST GATE CITY BOULEVARD / LEE STREET) | NCDOT | SR 4240 (EAST GATE CITY BOULEVARD / LEE STREET) AT I-40 WESTBOUND RAMPS. INTERSECTION AND TURN LANE IMPROVEMENTS, AND TRAFFIC SIGNAL INSTALLATION. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007I | Statewide Mobility | HSIP |  |  | 2025 | 5000 | 2026 | 752000 |  |  | 757000
GUILFORD | I-40 | NCDOT | I-40 WEST MEDIAN FROM BUFFALO CREEK BRIDGE EAST FOR 1550 FEET AND I-40 EAST EXIT 219 TO US 29 SOUTH. INSTALL GUARDRAIL. | 0.4 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2007K | Statewide Mobility | HSIP |  |  |  |  | 2024 | 265000 |  |  | 265000
GUILFORD | SR 2526 (SUMMIT AVENUE) | NCDOT | TEXTILE DRIVE INTERSECTION. INSTALL PEDESTRIAN SIGNAL HEADS, CROSSWALK, AND OTHER INSTERSECTION IMPROVEMENTS. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2407A | Division 7 | HSIP |  |  | 2024 | 5000 | 2025 | 70000 |  |  | 75000
GUILFORD | SR 1007 (RANDLEMAN ROAD) | NCDOT | WEBSTER ROAD INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2407B | Division 7 | HSIP | 2025 | 5000 | 2025 | 40000 | 2026 | 145000 |  |  | 190000
GUILFORD | US 29 NORTHBOUND | NCDOT | SR 2613 (NORTH O'HENRY BOULEVARD) IN THE VICINITY OF JOE BROWN DRIVE; SR 2937 (NORTH O'HENRY BOULEVARD) IN THE VICINITY OF THE FLEA MARKET; SR 2622/SR 5235 (CORBIN ROAD). CLOSE DIRECTIONAL LEFTOVERS. | 0.9 | Highway | Safety | 7 | Greensboro Urban Area MPO | HS-2407C | Statewide Mobility | HSIP |  |  |  |  | 2027 | 615000 |  |  | 615000
GUILFORD | US 220 EASTBOUND | NCDOT | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | 0.5 | Highway | Safety | 7 | Greensboro Urban Area MPO | W-5807A | Region D | HSIP, VRU |  |  |  |  | 2024 | 450000 |  |  | 450000 | UNDER CONSTRUCTION
GUILFORD | I-40 / US 421 | NCDOT | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | I-5712 | Statewide Mobility | NHP | 2028 | 13900000 | 2028 | 1100000 | 2031 | 27600000 |  |  | 42600000
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | NCDOT | ELM-EUGENE STREET IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | I-5964 | Statewide Mobility | NHP |  |  |  |  | 2025 | 1100000 |  |  | 1100000
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | NCDOT | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | 2.87 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | I-5965 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3732000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 109201000 |  |  | 123933000 | COORDINATE WITH B-5356 AND B-5718
GUILFORD | I-40 / I-85 | NCDOT | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | I-6004 | Division 7 | NHP | 2027 | 5700000 | 2027 | 120000 | 2030 | 21300000 |  |  | 27120000
GUILFORD | US 29; SR 4771 (REEDY FORK PARKWAY) | NCDOT | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | R-4707 | Region D | T | 2019 | 5824000 |  |  | 2021 | 62104000 | 2019 | 4019000 | 71947000 | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE)
GUILFORD | NC 68; NC 150 | NCDOT | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | R-5725 | Region D | T | 2022 | 1380000 | 2022 | 500000 | 2023 | 7300000 |  |  | 9180000 | COORDINATE WITH U-6127. UNDER CONSTRUCTION
GUILFORD | US 29 (FUTURE I-785) | NCDOT | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 4.48 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | R-5889A | Region D | T | 2027 | 17066000 | 2027 | 1876000 | 2030 | 69701000 |  |  | 88643000
GUILFORD | SR 1486 (GREENSBORO ROAD) / SR 4121 (HIGH POINT RO | NCDOT | PROPOSED US 311 BYPASS IN HIGH POINT TO SR 1424 (HILLTOP ROAD) IN GREENSBORO. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 7.8 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO, Greensboro Urban Area MPO | U-2412
GUILFORD | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | NCDOT | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | 3.61 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-2412A | Division 7 | T |  |  |  |  | 2018 | 80599000 |  |  | 80599000 | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $28.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | I-73 / I-840 / FUTURE I-840 / US 421 | NCDOT | GREENSBORO WESTERN LOOP, NORTH OF I-85 TO LAWNDALE DRIVE IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 15 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2524 | [11 empty] | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
GUILFORD | FUTURE I-840 | NCDOT | GREENSBORO WESTERN LOOP, US 220 (BATTLEGROUND AVENUE) TO SR 2303 (LAWNDALE DRIVE) | 1.64 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2524D | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-785 / I-840; FUTURE I-785; FUTURE I-840 | NCDOT | GREENSBORO EASTERN LOOP, LAWNDALE DRIVE TO NORTH OF I-40 / I-85 IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 12.6 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2525
GUILFORD | FUTURE I-840 | NCDOT | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | 1.89 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2525C | Statewide Mobility | T |  |  |  |  | 2018 | 94831000 | 2021 | 8340000 | 103171000 | UNDER CONSTRUCTION; BUILD NC BONDS: $6.485 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | US 70 WENDOVER AVENUE | NCDOT | US 70 (WENDOVER AVENUE) AT US 29 INTERCHANGE. REPLACE AND UPGRADE OVERHEAD SIGNS. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2525CA | Statewide Mobility | T |  |  |  |  | 2025 | 1550000 | 2024 | 100000 | 1650000
GUILFORD | FUTURE I-840 | NCDOT | INTERCHANGE AT PROPOSED CONE BOULEVARD EXTENSION | 15.4 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2525D | Not Funded | T | NOT FUNDED |  | NOT FUNDED |  | NOT FUNDED | 15000000 | NOT FUNDED |  | 15000000
GUILFORD | US 70 | NCDOT | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 4.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581
GUILFORD | US 70 | NCDOT | SR 2851 (PENRY ROAD) TO SR 2828 (WILLOWLAKE ROAD) |  | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581A | [11 empty] | PROJECT COMPLETE
GUILFORD | US 70 | NCDOT | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | 1.15 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581BA | Division 7 | T | 2020 | 2618000 |  |  | 2020 | 15535000 | 2020 | 1609000 | 19762000 | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $150,209 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | US 70 | NCDOT | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) |  | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581BB | Not Funded | T | NOT FUNDED | 2113000 | NOT FUNDED | 626000 | NOT FUNDED | 8200000 | NOT FUNDED |  | 10939000
GUILFORD | US 70 | NCDOT | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) |  | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-2581BC | Not Funded | T | NOT FUNDED | 3040000 | NOT FUNDED | 901000 | NOT FUNDED | 11799000 | NOT FUNDED |  | 15740000
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | NCDOT | NC 68 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 1.6 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-4015
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | NCDOT | NC 68 TO AIRPARK ROAD IN GREENSBORO. WIDEN TO MULTILANES | 1.17 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-4015A | Division 7 | T |  |  |  |  | 2025 | 15200000 |  |  | 15200000 | RIGHT OF WAY IN PROGRESS
GUILFORD | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | NCDOT | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | 4.45 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-4758 | Division 7 | BGANY, HP, T(M) | 2022 | 13221000 | 2022 | 7200000 | 2025 | 48401000 |  |  | 68822000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | I-74 / US 311 | NCDOT | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. RECONSTRUCT INTERCHANGE AND APPROACHES. | 1 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-5169 | Region D | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION AND SIDEWALK IMPROVEMENTS AT CONE BOULEVARD-BENJAMIN PARKWAY, WESTRIDGE ROAD, NEW GARDEN ROAD, AND BRASSFIELD ROAD INTERSECTIONS IN GREENSBORO. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5306
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION WITH WESTRIDGE ROAD AND APPROACHES | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5306B | Region D | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 29 / US 70 / US 220 (O'HENRY BOULEVARD) | NCDOT | I-40 / BUSINESS 85 TO SOUTH OF FLORIDA STREET IN GREENSBORO. ADD LANE ON I-40 / BUSINESS 85 EASTBOUND RAMP ONTO NORTHBOUND US 29 / US 70 / US 220 AND EXTEND US 29 / US 70 / US 220 SOUTHBOUND RAMP ONTO SR 3762 (MARTIN LUTHER KING, JR. DRIVE) | 0.69 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5754 | Region D | T |  |  |  |  | 2022 | 6750000 |  |  | 6750000 | UNDER CONSTRUCTION
GUILFORD | FRIENDLY AVENUE | NCDOT | WEST OF GREEN VALLEY ROAD TO LINDELL ROAD IN GREENSBORO. WIDENING AND INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5841 | Division 7 | T |  |  |  |  | 2025 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION
GUILFORD | PISGAH CHURCH ROAD | GREENSBORO | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5842 | Division 7 | BGANY, L(M) | 2028 | 1800000 | 2028 | 1300000 | 2031 | 6400000 | 2024 | 750000 | 10250000 | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | SR 1007 (RANDLEMAN ROAD) | NCDOT | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | 0.36 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5850 | Division 7 | T | 2022 | 600000 | 2022 | 400000 | 2026 | 4300000 |  |  | 5300000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | SR 1001 (CHURCH STREET) | NCDOT | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | 1.65 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5851 | Division 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18900000 |  |  | 109000000
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | 1.42 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-5892 | Region D | NHP | 2025 | 7531000 | 2025 | 1472000 | 2028 | 12401000 |  |  | 21404000
GUILFORD | US 29 / US 70 / BUSINESS 85 | NCDOT | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-5896 | Division 7 | T | 2019 | 8834000 |  |  | 2022 | 15400000 | 2019 | 1820000 | 26054000 | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
GUILFORD | NC 68 | NCDOT | SR 1523 (HICKSWOOD ROAD) TO SR 1823 (WILLARD DAIRY ROAD) IN HIGH POINT. UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.92 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-5974 | Region D | T | 2027 | 10200000 | 2027 | 6600000 | 2029 | 52605000 |  |  | 69405000 | COORDINATE WITH U-6122. BUILD NC BONDS: $16M FOR CONSTRUCTION PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE)
GUILFORD | SR 2085 (BRYAN BOULEVARD) | NCDOT | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | 1 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6008 | Division 7 | T | 2029 | 1600000 | 2029 | 300000 | 2031 | 7700000 |  |  | 9600000
GUILFORD | SR 2124 (LEWISTON ROAD) | NCDOT | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6016 | Division 7 | T | 2022 | 836000 | 2022 | 302000 | 2025 | 2049000 |  |  | 3187000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | NC 62 | NCDOT | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | 1 | Highway | STI (Prioritization) | 7 | High Point Urban Area MPO | U-6018 | Division 7 | T | 2021 | 2600000 | 2021 | 2811000 | 2025 | 29355000 |  |  | 34766000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10M FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 6 SALE).
GUILFORD | SR 2334 (AIR HARBOR ROAD) | NCDOT | SR 2347 (LAKE BRANDT ROAD). CONSTRUCT TURN LANES AND SIDEWALKS. |  | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6019 | Division 7 | T |  |  |  |  | 2022 | 1586000 |  |  | 1586000 | UNDER CONSTRUCTION
GUILFORD | SR 1850 (SANDY RIDGE ROAD) | NCDOT | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTI-LANES. | 0.69 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6045 | Division 7 | T | 2029 | 9100000 | 2029 | 610000 | 2032 | 40100000 |  |  | 49810000
GUILFORD | US 29, US 70, US 220 | NCDOT | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRIDGES 400283 AND 400342. | 5.09 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO | U-6100 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28400000 |  |  | 36300000
GUILFORD | NC 68 | NCDOT | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO REDUCED CONFLICT INTERSECTIONS. | 2.12 | Highway | STI (Prioritization) | 7 | Greensboro Urban Area MPO, High Point Urban Area MPO | U-6122 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34200000 |  |  | 38300000 | COORDINATE WITH U-5974
GUILFORD | SR 3058 (JUDGE ADAMS ROAD) | NCDOT | REPLACE BRIDGE 400214 OVER LITTLE ALAMANCE CREEK. | 0.25 | Highway | Transition | 7 | Burlington-Graham MPO, Greensboro Urban Area MPO | B-4960 | Division 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | FUTURE I-73 | NCDOT | NC 68 TO GREENSBORO WESTERN LOOP. SIX-LANE FREEWAY ON NEW LOCATION. | 3 | Highway | Transition | 7 | Greensboro Urban Area MPO | I-5110 | Pre-STI (Transition) | [10 empty] | COMBINED WITH R-2413A AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | FUTURE I-73 | NCDOT | FOUR LANES AT SR 2011 (EDGEFIELD ROAD) TO SR 2127 (BROOK BANK ROAD) | 4 | Highway | Transition | 7 | Greensboro Urban Area MPO | R-2413A |  | T |  |  |  |  | 2024 | 55000 |  |  | 55000 | COMBINED WITH I-5110 AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | FUTURE I-73 | NCDOT | SR 2127 (BROOK BANK ROAD) TO HAW RIVER | 4.4 | Highway | Transition | 7 | Greensboro Urban Area MPO | R-2413B | [11 empty] | COMBINED WITH I-5110 AND R-2413A FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | US 421 | NCDOT | SR 3418 (NEELLEY ROAD) INTERSECTION SOUTH OF GREENSBORO | 0.901 | Highway | Transition | 7 | Greensboro Urban Area MPO | R-2612B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / I-840 | NCDOT | SR 2085 (BRYAN BOULEVARD) INTERCHANGE MODIFICATIONS, INCLUDING AUXILIARY LANES, ITS, AND INMAN ROAD BRIDGE REPLACEMENT. | 2 | Highway | Transition | 7 | Greensboro Urban Area MPO | U-2524BC | Pre-STI (Transition) | [10 empty] | COMPLETE
GUILFORD | FUTURE I-785 / FUTURE I-840 | NCDOT | GREENSBORO EASTERN LOOP, US 70 RELOCATION TO US 29 NORTH OF GREENSBORO | 4.59 | Highway | Transition | 7 | Greensboro Urban Area MPO | U-2525B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 1820 (SKEET CLUB ROAD) | NCDOT | EAST OF SR 1818 (JOHNSON STREET) TO WEST OF NC 68 (EASTCHESTER DRIVE). WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY. | 3.18 | Highway | Transition | 7 | High Point Urban Area MPO | U-3615B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION WITH BENJAMIN PARKWAY / CONE BOULEVARD AND APPROACHES | 0.5 | Highway | Transition | 7 | Greensboro Urban Area MPO | U-5306A | Pre-STI (Transition) | [10 empty] | PROJECT COMPLETE
GUILFORD | US 220 (BATTLEGROUND AVENUE) | NCDOT | INTERSECTION WITH NEW GARDEN ROAD AND APPROACHES | 0.5 | Highway | Transition | 7 | Greensboro Urban Area MPO | U-5306C | Pre-STI (Transition) | [10 empty] | PROJECT COMPLETE
GUILFORD | GTA | GTA | REPLACEMENT PARATRANSIT BUSES |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-4767 | Public Transit | 5309, L | [6 empty] | 2022 | 4844000 | 4844000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GTA | GTA | CLEAN DIESEL REPLACEMENT BUSES |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-4771 | Public Transit | 5307, CMAQ, L | [6 empty] | 2022 | 4457000 | 4457000
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE ONE EXPANSION 40-FT BUS. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-6679 | Region D | [10 empty] | IN ACQUISITION
GUILFORD | REGIONAL TRANSPORTATION PIEDMONT AUTHORITY FOR | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | REPLACEMENT VEHICLES. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-6690 | Public Transit | 5339, L | [6 empty] | 2024 | 251000 | 251000
GUILFORD | GTA | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-6714 | Public Transit | 5339, CMAQ, L, S | [6 empty] | 2023 | 5830000 | 5830000 | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT
GUILFORD | SYSTEM / HI-TRAN HIGH POINT TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | High Point Urban Area MPO | TA-6729 | Public Transit | 5307, CMAQ, L | [6 empty] | 2022 | 1250000 | 1250000
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | VEHICLE REPLACEMENT AND EXPANSION |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TA-6732 | Public Transit | 5339, L |  |  |  |  | 2020 | 8480000 |  |  | 8480000 | PROJECT ADDED AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TD-5279 | Public Transit | 5339, L, S | [6 empty] | 2020 | 2284000 | 2284000 | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | SYSTEM / HI-TRAN HIGH POINT TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | BUILDING / FACILITY RENOVATION AND UPGRADE FOR PARATRANSIT ADMINISTRATION. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | High Point Urban Area MPO | TD-5283 | Region D | [10 empty] | N PROGRESS
GUILFORD | HIGH POINT TRANSIT SYSTEM / HI-TRAN | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | High Point Urban Area MPO | TP-5104 | Public Transit | 5303, L, S | [6 empty] | 2020 | 176000 | 176000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 CAPITAL PROJECT. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TQ-6783 | Public Transit | 5310, L | [6 empty] | 2024 | 2000000 | 2000000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | SAFETY & SECURITY |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Greensboro Urban Area MPO | TS-4758 | Public Transit | 5307, L | [6 empty] | 2024 | 415000 | 415000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GTA |  | GTA ROUTE 15 NEW SERVICE |  | Public Transportation (Transit) | Locally Selected | 7 | Greensboro Urban Area MPO | TL-0048 | Public Transit | CMAQ, L | [6 empty] | 2023 | 1812000 | 1812000
GUILFORD | GTA |  | GTA NEW CROSSTOWN NEW ROUTE. |  | Public Transportation (Transit) | Locally Selected | 7 | Greensboro Urban Area MPO | TL-0050 | Public Transit | CMAQ, L | [6 empty] | 2024 | 7680000 | 7680000
GUILFORD | GTA | GTA | J. DOUGLAS GAYLON DEPOT RENOVATION PHASE 3 |  | Public Transportation (Transit) | Locally Selected | 7 | Greensboro Urban Area MPO | TL-0055 | Public Transit | 5339, BGDA, L(M) |  |  |  |  | 2025 | 3063000 |  |  | 3063000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Greensboro Urban Area MPO | TO-4971 | Public Transit | 5307, L, SMAP | [6 empty] | 2022 | 52649000 | 52649000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | High Point Urban Area MPO | TO-5134C | Public Transit | 5307, L | [6 empty] | 2023 | 9744000 | 9744000
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Greensboro Urban Area MPO | TO-5209 | Public Transit | 5307, L, SMAP | [6 empty] | 2024 | 8024000 | 8024000 | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY
GUILFORD | GUILFORD COUNTY TRANSPORTATION | GUILFORD COUNTY TRANSPORTATION | OPERATING FUNDING FOR GUILFORD COUNTY THROUGH HIGH-POINT MPO |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | High Point Urban Area MPO | TO-5216 | Public Transit | 5307, L | [6 empty] | 2020 | 1330000 | 1330000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GUILFORD COUNTY TRANSPORTATION | GUILFORD COUNTY TRANSPORTATION | OPERATING- RURAL TRANSIT |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Greensboro Urban Area MPO | TO-5221 | Public Transit | 5307, L | [6 empty] | 2024 | 350000 | 350000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 OPERATING. |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Greensboro Urban Area MPO | TO-6139 | Public Transit | 5310, L | [6 empty] | 2024 | 500000 | 500000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO
GUILFORD | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | OPERATING |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-6151 | Public Transit | 5307, L | [6 empty] | 2020 | 2016000 | 2016000
GUILFORD | AUTHORITY GREENSBORO TRANSIT | AUTHORITY GREENSBORO TRANSIT | OPERATING-ADA PARATRANSIT SERVICE. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TG-4957 | Public Transit | 5307, L | [6 empty] | 2024 | 6620000 | 6620000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GUILFORD COUNTY TRANSPORTATION | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TK-6132 | Public Transit | 5311, L, S | [6 empty] | 2020 | 908000 | 908000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GTA | GTA | EXPANDED SUNDAY SERVICE, NEW SERVICE OPERATIONAL FUNDING |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TL-0012 | Public Transit | CMAQ, L | [6 empty] | 2021 | 2705000 | 2705000
GUILFORD | GTA |  | OPERATING MICROSTRANSIT. |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TM-0053 | Public Transit | 5307, L | [6 empty] | 2024 | 5470000 | 5470000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 PROGRAM ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Greensboro Urban Area MPO | TQ-7000 | Public Transit | 5310 | [6 empty] | 2024 | 205000 | 205000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303. |  | Public Transportation (Transit) | Planning | 7 | Greensboro Urban Area MPO | TP-5101 | Public Transit | 5303, L, SMAP | [6 empty] | 2024 | 1355000 | 1355000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GTA | GTA | THE CITY OF GREENSBORO WILL RECEIVE FUNDING TO PREPARE A TECHNICAL PLAN TO ESTABLISH WHAT WILL BE REQUIRED TO PROVIDE FREE BROADBAND INTERNET ACCESS IN LOW - INCOME AREAS USING TRANSIT, TRANSPORTATION AND OTHER PUBLIC INFRASTRUCTURE. |  | Public Transportation (Transit) | Planning | 7 | Greensboro Urban Area MPO | TU-0002 | Public Transit | 5305, L | [6 empty] | 2021 | 260000 | 260000
GUILFORD | GTA | GREENSBORO TRANSIT AUTHORITY | J.DOUGLAS GALYON DEPOT AREA TRANSIT ORIENTED DEVELOPMENT STUDY |  | Public Transportation (Transit) | Planning | 7 | Greensboro Urban Area MPO | TU-0018 | Public Transit | 20005(b) | [6 empty] | 2025 | 500000 | 500000
GUILFORD | GTA | GTA | ROUTINE CAPITAL: FAREBOXES, CAMERA SYSTEMS, APCs, AND DELIVERY FOR ASSET TRANSFER OF USED BUSES; DEPOT TICKET MACHINES: REALTIME SHELTER SIGNAGE; AND BUS SHELTERS. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Greensboro Urban Area MPO | TG-0019 | Public Transit | 5309, L | [6 empty] | 2024 | 3350000 | 3350000
GUILFORD | HIGH POINT TRANSIT SYSTEM | NT TRANSIT SYSTEM | MAINTENANCE FACILITY RENOVATION. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | High Point Urban Area MPO | TG-0022 | Public Transit | 5339, L |  |  |  |  | 2024 | 1500000 |  |  | 1500000
GUILFORD | HIGH POINT TRANSIT SYSTEM |  | REPLACEMENT PARATRANSIT BUSES. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | High Point Urban Area MPO | TG-0024 | Public Transit | 5307, L | [6 empty] | 2024 | 1375000 | 1375000
GUILFORD | HIGH POINT TRANSIT SYSTEM |  | NEW SPARE PARATRANSIT BUSES. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | High Point Urban Area MPO | TG-0025 | Public Transit | 5307, L | [6 empty] | 2024 | 275000 | 275000
GUILFORD | GREENSBORO TRANSIT AGENCY | GREENSBORO TRANSIT AGENCY | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Greensboro Urban Area MPO | TG-4759 | Public Transit | 5307, L | [6 empty] | 2022 | 27153000 | 27153000
GUILFORD | AUTHORITY GREENSBORO TRANSIT | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Greensboro Urban Area MPO | TG-5105 | Public Transit | 5307, 5339, L | [6 empty] | 2024 | 350000 | 350000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PREVENTIVE MAINTENANCE, SECURITY AND PESSENGER AMENITIES. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | High Point Urban Area MPO | TG-6173B | Public Transit | 5307, L | [6 empty] | 2023 | 858000 | 858000
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Greensboro Urban Area MPO | TG-6185 | Public Transit | 5307, L | [6 empty] | 2024 | 975000 | 975000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | LOWDERMILK STREET SYKES AVENUE | NCDOT | PINE STREET CROSSING CLOSURE (722957L) AND LOWDERMILK STREET / SYKES AVENUE (722958T) REALIGNMENT IN GREENSBORO. |  | Rail | Rail-Highway Grade Crossing Closure | 7 | Greensboro Urban Area MPO | Y-4807B | Division 7 | RR |  |  |  |  | 2024 | 5000000 |  |  | 5000000 | UNDER CONSTRUCTION
GUILFORD | SR 2748 (SPRINGWOOD AVENUE) | GIBSONVILLE | NORFOLK SOUTHERN RAILROAD CROSSING 722990L IN GIBSONVILLE. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Burlington-Graham MPO | RX-2007A | Division 7 | RR |  |  |  |  | 2023 | 500000 |  |  | 500000 | UNDER CONSTRUCTION
GUILFORD | SR 2531 (HILLCROFT ROAD) | GREENSBORO | NORFOLK SOUTHERN RAILROAD CROSSING 722545Y NEAR GREENSBORO. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Greensboro Urban Area MPO | RX-2007C | Division 7 | RR |  |  |  |  | 2024 | 800000 |  |  | 800000
GUILFORD | NORFOLK SOUTHERN MAINLINE | NSR RR | NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5700 | Division 7 | O, T |  |  |  |  | 2026 | 1700000 |  |  | 1700000 | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION
GUILFORD | NORFOLK SOUTHERN H LINE | NCDOT | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5709 | Region D | O, T | 2022 | 3484000 | 2022 | 1566000 | 2026 | 26800000 |  |  | 31850000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS
GUILFORD | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | NCDOT | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5713 | Statewide Mobility | O, T | 2025 | 3431000 | 2025 | 952000 | 2026 | 17800000 |  |  | 22183000 | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION
GUILFORD | NCRR NORFOLK SOUTHERN | NCDOT | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5714 | Region D | O, T |  |  |  |  | 2027 | 3100000 |  |  | 3100000 | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN | JAMESTOWN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. |  | Rail | STI (Prioritization) | 7 | High Point Urban Area MPO | P-5721 | Statewide Mobility | O, T |  |  |  |  | 2026 | 4070000 |  |  | 4070000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN MAIN LINE | NCDOT | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5735 | Region D | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12700000 |  |  | 16200000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD
GUILFORD | NCRR NORFOLK SOUTHERN H LINE | NCDOT | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | P-5747 | Region D | O, T | 2026 | 2300000 |  |  | 2028 | 24900000 |  |  | 27200000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NCRR / NS NC LINE | NCDOT | SR 1549 (MACKAY ROAD) INTERSECTION IN GREENSBORO (CROSSING #722359X). CONSTRUCT MACKAY ROAD GRADE SEPARATION. INCLUDES RELOCATING ATWATER DRIVE. |  | Rail | STI (Prioritization) | 7 | Greensboro Urban Area MPO | RP-0003 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21000000 |  |  | 30400000
GUILFORD | NCRR / NS MAIN LINE | NCDOT | SR 1332 (SCIENTIFIC STREET) INTERSECTION IN JAMESTOWN. CONSTRUCT GRADE SEPARATION AND CLOSURE OF EXISTING AT-GRADE CROSSING (#722352A). |  | Rail | STI (Prioritization) | 7 | High Point Urban Area MPO | RP-0004 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17000000 |  |  | 22200000
GUILFORD | NCRR/NS MAINLINE | NCDOT | SR 1352 (OAKDALE ROAD). CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING #722355V. |  | Rail | STI (Prioritization) | 7 | High Point Urban Area MPO | RP-0007 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30000000 |  |  | 43400000
GUILFORD, ALAMANCE | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION |  | CAPITAL |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Burlington-Graham MPO, High Point Urban Area MPO | TG-0014B | Public Transit | 5339, L | [6 empty] | 2024 | 1248000 | 1248000
GUILFORD, ALAMANCE, FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 7, 9 | Winston-Salem Area TPO | TS-5115 | Public Transit | 5307 | [6 empty] | 2020 | 8000 | 8000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD, DAVIDSON, RANDOLPH | SYSTEM / HI-TRAN HIGH POINT TRANSIT | SYSTEM / HI-TRAN HIGH POINT TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC ($40K CAPITAL COST OF CONTRACTING). |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7, 8, 9 | High Point Urban Area MPO | TG-4814 | Public Transit | 5307, L | [6 empty] | 2024 | 2124000 | 2124000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918 | Exempt | CMAQ, HF | [6 empty] | 2021 | 26618000 | 26618000 | "HF" FUNDING REFLECTS STATE RAIL FUNDS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | EQUIPMENT REBUILD - 2 F59PHI LOCOMOTIVES |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918A | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | PURCHASE 2 USED LOCOMOTIVES |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918B | [11 empty] | COMPLETE
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | EQUIPMENT REHABILITATION - 3 LOCOMOTIVES |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918C | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | EQUIPMENT REHABILITATION - 3 PASSENGER CARS |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918D | [11 empty] | COMPLETE
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | PASSENGER TRAIN SECURITY SYSTEM, CCTV DATA NETWORK AND GENERATORS |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918E | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | PURCHASE 4 USED PASSENGER CARS AND REHABILITATE 7 PASSENGER CARS |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918G | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | EQUIP 9 STATIONS AND PLATFORMS WITH ADA/FRA PIDS |  | Rail | Other | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-2918I | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | NCDOT | PURCHASE AND REFURBISH RAIL CARS FOR PIEDMONT SERVICE EXPANSION. |  | Rail | STI (Prioritization) | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-5719 | [11 empty] | "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP FOR STATE OF GOOD REPAIR GRANT
GUILFORD, FORSYTH | US 158 | NCDOT | NORTH OF SR 1969 (PINEY GROVE ROAD) / SR 1962 (KERNERSVILLE ROAD) IN FORSYTH COUNTY TO US 220 IN GUILFORD COUNTY. WIDEN TO MULTI-LANES. | 5.89 | Highway | STI (Prioritization) | 7, 9 | Greensboro Urban Area MPO, Winston-Salem Area TPO | R-2577C | Not Funded | T | NOT FUNDED | 74608000 | NOT FUNDED | 625000 | NOT FUNDED | 48400000 | NOT FUNDED |  | 123633000
GUILFORD, ORANGE | VARIOUS | BURLINGTON | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | Highway | Other | 7 | Burlington-Graham MPO | C-5602 | Exempt | CMAQ, L | 2020 | 18000 |  |  | 2020 | 99000 | 2020 | 54000 | 171000
GUILFORD, ROCKINGHAM | FUTURE I-73 | NCDOT | NC 68 AT SR 2011 (EDGEFIELD ROAD) IN GUILFORD COUNTY TO US 220-NC 68 INTERSECTION IN ROCKINGHAM COUNTY. FOUR-LANE FREEWAY, ON NEW LOCATION, NC 68 TO US 220 AND FOUR LANES ALONG US 220 TO NC 68 IN ROCKINGHAM COUNTY. | 12.1 | Highway | Pre-STI (Historic) | 7 | Greensboro Urban Area MPO, Piedmont Triad RPO | R-2413 | Pre-STI (Transition)
GUILFORD, WAKE, MECKLENBURG | PIEDMONT CORRIDOR | NCDOT | ACQUIRE AND REBUILD 2 ADDITIONAL LOCOMOTIVES. |  | Rail | STI (Prioritization) | 5, 7, 10 | Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-5719A | Exempt | [10 empty] | COMPLETE
GUILFORD, WAKE, MECKLENBURG | PIEDMONT CORRIDOR | NCDOT | ACQUIRE AND REFURBISH 2 COACH AND 1 LOUNGE/BAGGAGE RAIL CARS. |  | Rail | STI (Prioritization) | 5, 7, 10 | Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | P-5719B | Exempt | [10 empty] | IN PROGRESS
HALIFAX | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | CONSTRUCT TAXI LANE AND PREPARATION FOR ADDITIONAL T-HANGARS. |  | Aviation | STI (Prioritization) | 4 | Peanut Belt RPO | AV-5822 | Division 4 | T |  |  |  |  | 2024 | 1400000 |  |  | 1400000
HALIFAX | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. |  | Aviation | STI (Prioritization) | 4 | Peanut Belt RPO | AV-5833 | Division 4 | T |  |  |  |  | 2026 | 2500000 | 2025 | 221000 | 2721000
HALIFAX | NC 561 | NCDOT | REPLACE BRIDGE 410093 OVER CONOCONNARA SWAMP. | 0.25 | Highway | Bridges | 4 | Peanut Belt RPO | B-5662 | Highway Fund | HFB |  |  |  |  | 2021 | 2581000 |  |  | 2581000 | COMPLETE.
HALIFAX | SR 1601 (SLEDGE ROAD) | NCDOT | REPLACE BRIDGE 410115 OVER ROCKY SWAMP. | 0.25 | Highway | Bridges | 4 | Peanut Belt RPO | BR-0113 | Division 4 | DP, HFB | 2020 | 130000 |  |  | 2021 | 796000 |  |  | 926000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
HALIFAX | SR 1710 (GRACE DRIVE/ WATKINS DRIVE) AND SR 1737 | NCDOT | FROM US-158 TO NORTH OF SR 1734 (KENNAMETAL DRIVE). WIDEN TO FOUR LANES. REALIGN SR 1737 (POWER PLACE) AND US-158 INTERSECTION. | 0.72 | Highway | Economic Development | 4 | Peanut Belt RPO | HE-0003 | Division 4 | T |  |  |  |  | 2022 | 2050000 |  |  | 2050000 | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR ROSEBURG FOREST PRODUCTS.
HALIFAX | I-95 | NCDOT | NC 481 (MILE MARKER 154) TO MILE MARKER 167. PAVEMENT REHABILITATION. | 18 | Highway | Interstate Maintenance | 4 | Peanut Belt RPO | I-5932
HALIFAX | I-95 | NCDOT | NC 561 (MILE MARKER 160) TO MILE MARKER 167. | 7.19 | Highway | Interstate Maintenance | 4 | Peanut Belt RPO | I-5932A | Statewide Mobility | BGLT5 |  |  |  |  | 2021 | 9593000 |  |  | 9593000 | UNDER CONSTRUCTION.
HALIFAX | I-95 | NCDOT | NC 481 (MILE MARKER 154) TO NC 561 (MILE MARKER 160). | 6.83 | Highway | Interstate Maintenance | 4 | Peanut Belt RPO | I-5932B | Statewide Mobility | BGLT5 |  |  |  |  | 2021 | 8223000 |  |  | 8223000 | UNDER CONSTRUCTION.
HALIFAX | NC 48 | NCDOT | INSTALL ALL WAY STOP AND REVISE EXISTING OVERHEAD AND SHOULDER-MOUNTED FLASHERS AT NC 48 AND NC 903. | 0.5 | Highway | Safety | 4 | Peanut Belt RPO | HS-2004G | Region A | HSIP |  |  |  |  | 2022 | 50000 |  |  | 50000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004H.
HALIFAX | US 158 | NCDOT | US 158 FROM EASTERN LITTLETON TOWN LIMITS AND 0.15 MILES WEST OF SR 1432 (EVERETTS SCHOOL ROAD). INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | 9.41 | Highway | Safety | 4 | Peanut Belt RPO | HS-2004T | Region A | HSIP |  |  |  |  | 2024 | 2474000 |  |  | 2474000 | UNDER CONSTRUCTION.
HALIFAX | NEW ROUTE | NCDOT | NC 125 TO SOUTH OF US 158. CONSTRUCT THREE LANE FACILITY ON NEW LOCATION. | 1.49 | Highway | STI (Prioritization) | 4 | Peanut Belt RPO | R-3822 | Division 4 | [10 empty] | COMPLETE. COMBINED FOR LETTING WITH U-5725. CONSTRUCTION FUNDS SHOWN UNDER U-5725.
HALIFAX | NC 125 | NCDOT | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO FOUR LANES. | 1.63 | Highway | STI (Prioritization) | 4 | Peanut Belt RPO | U-5725 | Division 4 | T |  |  |  |  | 2019 | 27240000 | 2021 | 2130000 | 29370000 | COMPLETE. COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3).
HALIFAX, JOHNSTON | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 4 | Peanut Belt RPO, Upper Coastal Plain RPO | HS-2004J | Division 4 | HSIP |  |  |  |  | 2022 | 5246000 |  |  | 5246000 | UNDER CONSTRUCTION.
HARNETT | HRJ | HRJ | HARNETT COUNTY AIRPORT. WIDEN EXISTING RUNWAY FROM 75' TO 100'. |  | Aviation | STI (Prioritization) | 6 | Mid-Carolina RPO | AP-0005 | Division 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3697000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 370000 | 4067000
HARNETT | EAST MCIVER STREET, SOUTH WILMA STREET | ANGIER | EAST MCIVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 0.37 | Bike & Ped | Locally Selected | 6 | Capital Area MPO | BL-0090 | Division 6 | BGDA, L(M) | 2025 | 50000 |  |  | 2025 | 898000 | 2024 | 150000 | 1098000
HARNETT | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | ANGIER | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 0.73 | Bike & Ped | Locally Selected | 6 | Capital Area MPO | EB-6020 | Division 6 | BGDA, L | 2024 | 150000 |  |  | 2025 | 1457000 | 2021 | 175000 | 1782000
HARNETT | CAMPBELL UNIVERSITY SIDEWALK | BUIES CREEK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 0.81 | Bike & Ped | STI (Prioritization) | 6 | Mid-Carolina RPO | EB-6014 | Division 6 | L, TAANY | 2021 | 35000 |  |  | 2021 | 630000 |  |  | 665000 | UNDER CONSTRUCTION.
HARNETT | SR 1210 (HOOVER ROAD) | NCDOT | REPLACE BRIDGE 420234 OVER BARBEQUE SWAMP. | 0.25 | Highway | Bridges | 6 | Mid-Carolina RPO | B-6005 | Division 6 | [10 empty] | COMPLETED.
HARNETT | CHURCH ROAD) SR 1214 (MOUNT PISGAH | NCDOT | REPLACE BRIDGE 420034 OVER UPPER LITTLE RIVER. | 0.25 | Highway | Bridges | 6 | Mid-Carolina RPO | HB-0008 | Division 6 | BGOFF | 2026 | 330000 |  |  | 2028 | 1900000 |  |  | 2230000
HARNETT | SR 1115 (BUFFALO LAKE ROAD) | FAYETTEVILLE | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0146 | Division 6 | BGDA, HF(M) | 2026 | 300000 | 2026 | 160000 | 2028 | 2500000 | 2025 | 500000 | 3460000
HARNETT | (NEW ROUTE) HIGHLAND SCHOOL ROAD | HARNETT COUNTY | CONNECTING SR 1115 (BUFFALO LAKE ROAD) TO SR 1139 (TINGEN ROAD) SOUTH OF HIGHLAND ELEMENTARY AND MIDDLE SCHOOL CAMPUSES. CONSTRUCT TWO-LANE MINOR THOROUGHFARE PARTIALLY ON NEW GROUND. |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0155 | Division 6 | T(DA) |  |  |  |  | 2026 | 2658000 | 2025 | 125000 | 2783000
HARNETT | I-95 | NCDOT | CUMBERLAND COUNTY LINE TO THE JOHNSTON COUNTY LINE. PAVEMENT REPAIR. | 8.8 | Highway | Pre-STI (Historic) | 6 | Mid-Carolina RPO | I-4906 | Pre-STI (Transition) | [10 empty] | COMPLETED. GARVEE BOND FUNDING $3.15 MILLION; PAYBACK FY 2008 - FY 2019.
HARNETT | NC 27 | NCDOT | NC 24/27 FROM THE MOORE COUNTY LINE AND THE NC 24/27 SPLIT, NC 27 FROM NC 24 TO LILLINGTON, NC 27 FROM US 421 TO COATS, AND NC 27 FROM COATS TO THE JOHNSTON COUNTY LINE. INSTALL RUMBLE STRIPES, RUMBLE STRIPS, AND LONG-LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2006H | Region C | HSIP |  |  |  |  | 2024 | 1065000 |  |  | 1065000 | UNDER CONSTRUCTION.
HARNETT | SR 1441 (CHALYBEATE SPRINGS ROAD) | NCDOT | FROM NC 55 TO US 401. CURVE AND PAVEMENT MARKING IMPROVEMENTS. | 4.23 | Highway | Safety | 6 | Capital Area MPO | HS-2006K | Division 6 | HSIP | 2024 | 45000 | 2025 | 25000 | 2025 | 1150000 |  |  | 1220000
HARNETT | SR 1532 (LANGDON ROAD) | NCDOT | SR 1532 (LANGDON ROAD) AT BRIDGE 420015. UPGRADE GUARDRAIL. | 0.5 | Highway | Safety | 6 | Mid-Carolina RPO | HS-2006Q | Division 6 | HSIP | 2023 | 40000 |  |  | 2023 | 1767000 |  |  | 1807000 | UNDER CONSTRUCTION.
HARNETT | SR 1115 (BUFFALO LAKE ROAD) | NCDOT | FROM NC 27 TO NC 87. INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS. | 4.57 | Highway | Safety | 6 | Fayetteville Area MPO | HS-2006Y | Division 6 | HSIP |  |  |  |  | 2024 | 235000 |  |  | 235000 | UNDER CONSTRUCTION.
HARNETT | NC 27 | NCDOT | CONSTRUCT ROUNDABOUT AT SR 2084 (LESLIE CAMPBELL AVENUE) INTERSECTION. | 0.5 | Highway | Safety | 6 | Mid-Carolina RPO | W-5706L | Region C | HF, HSIP |  |  | 2024 | 278000 | 2024 | 3150000 |  |  | 3428000 | RIGHT-OF-WAY IN PROGRESS.
HARNETT | SR 1117, SR 3242, SR 1615 | NCDOT | SR 1117 (NURSERY ROAD) FROM NC 27 TO SR 3242 (OVERHILLS ROAD). SR 3242 (OVERHILLS ROAD) FROM NC 24/87 TO SR 1117 (NURSERY ROAD). SR 1121 (RAY ROAD) FROM SR 1117 (NURSERY ROAD) TO SR 3242 (OVERHILLS ROAD). WIDEN CURVES AND INSTALL RUMBLE STRIPS. | 11.01 | Highway | Safety | 6 | Fayetteville Area MPO, Mid-Carolina RPO | W-5806B | Division 6 | HSIP |  |  |  |  | 2022 | 400000 |  |  | 400000 | UNDER CONSTRUCTION.
HARNETT | NC 27, SR 1581 | NCDOT | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Safety | 6 | Mid-Carolina RPO | W-5806D | Region C | HSIP | 2021 | 100000 |  |  | 2022 | 606000 |  |  | 706000 | UNDER CONSTRUCTION.
HARNETT | NC 24 / NC 87 | NCDOT | SR 1117 (NURSERY ROAD) INTERSECTION IN FAYETTEVILLE. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | HP-0011 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33400000 |  |  | 34200000
HARNETT | NC 55 | NCDOT | NC 210 INTERSECTION IN ANGIER. CONSTRUCT TURN LANES. | 0.1 | Highway | STI (Prioritization) | 6 | Capital Area MPO | HP-0033 | Division 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 |  |  | 3800000
HARNETT | NC 55 | NCDOT | AT NORTH BROAD STREET IN ANGIER. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | STI (Prioritization) | 6 | Capital Area MPO | HP-0034 | Division 6 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4400000 |  |  | 7700000
HARNETT | I-95 | NCDOT | SR 1811 (BUD HAWKINS ROAD) (EXIT 70) AND SR 1001 (LONG BRANCH ROAD) (EXIT 71). IMPROVE INTERCHANGES. | 1 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | I-5877 | Statewide Mobility | T | 2023 | 3304000 |  |  | 2020 | 69733000 |  |  | 73037000 | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION.
HARNETT | I-95 | NCDOT | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). IMPROVE INTERCHANGES. | 1 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | I-5878 | Statewide Mobility | T |  |  |  |  | 2022 | 78860000 |  |  | 78860000 | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION.
HARNETT | I-95 | NCDOT | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). CLEARING FOR UTILITIES. |  | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | I-5878A | Statewide Mobility | T |  |  |  |  | 2020 | 139000 |  |  | 139000 | COMPLETED.
HARNETT | I-95 | NCDOT | SR 1808 (JONESBORO ROAD) (EXIT 75) AND SR 1709 (HODGES CHAPEL ROAD) (EXIT 77). IMPROVE INTERCHANGES. | 1 | Highway | STI (Prioritization) | 6 | Mid-Carolina RPO | I-5883 | Statewide Mobility | T |  |  |  |  | 2022 | 100613000 |  |  | 100613000 | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION.
HARNETT | NC 55 | NCDOT | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | 4.02 | Highway | STI (Prioritization) | 6 | Capital Area MPO | R-5705A | Division 6 | T | 2021 | 36835000 | 2021 | 3800000 | 2024 | 56316000 |  |  | 96951000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE).
HARNETT | NC 87/24 | NCDOT | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-5933 | Statewide Mobility | BGDA, T, T(M) | 2023 | 17000 | 2023 | 23000 | 2023 | 3345000 |  |  | 3385000 | UNDER CONSTRUCTION.
HARNETT | HARNETT COUNTY | HARNETT COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Mid-Carolina RPO | TK-6133 | Public Transit | 5311, L, S | [6 empty] | 2020 | 880000 | 880000 | FUNDS AUTHORIZED IN PROGRESS
HARNETT | HARNETT AREA RURAL TRANSIT SYSTEM | HARNETT AREA RURAL TRANSIT SYSTEM | SYSTEMWIDE. PURCHASE TWO EXPANSION VEHICLES TO SUPPORT ON DEMAND SERVICES. |  | Public Transportation (Transit) | STI (Prioritization) | 6 | Mid-Carolina RPO | TP-0006 | Division 6 | T | [6 empty] | 2028 | 260000 | 260000
HARNETT | HARNETT STREET | NCDOT | CSX CROSSING 629751J IN DUNN. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO | RX-2006C | Division 6 | RR |  |  |  |  | 2025 | 446000 |  |  | 446000
HARNETT | EDGERTON STREET | NCDOT | CSX CROSSING 629752R IN DUNN. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO | RX-2006D | Division 6 | RR |  |  |  |  | 2025 | 446000 |  |  | 446000
HARNETT | US 401 (MAIN STREET) | NCDOT | RFR CROSSING 465860F IN LILLINGTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Mid-Carolina RPO | RX-2006F | Division 6 | RR |  |  |  |  | 2026 | 345000 |  |  | 345000
HARNETT | US 401 | NCDOT | RFCC CROSSING 465843P IN ANGIER. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 6 | Capital Area MPO | RX-2406B | Division 6 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
HARNETT, BLADEN, CUMBERLAND, COLUMBUS | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS AT VARIOUS LOCATIONS. |  | Highway | Safety | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO | HS-2006E | Division 6 | HSIP |  |  |  |  | 2022 | 4715000 |  |  | 4715000 | UNDER CONSTRUCTION.
HARNETT, CUMBERLAND | US 401 | NCDOT | BETWEEN FAYETTEVILLE AND HARNETT COUNTY (MILEPOST 20 - 27.7), BETWEEN CUMBERLAND COUNTY AND LILLINGTON (MILEPOST 0 - 9.5), AND BETWEEN LILLINGTON AND WAKE COUNTY (MILEPOST 12.5 - 22.1). INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS. |  | Highway | Safety | 6 | Mid-Carolina RPO, Capital Area MPO, Fayetteville Area MPO | HS-2006W | Region C | HSIP |  |  |  |  | 2024 | 975000 |  |  | 975000 | UNDER CONSTRUCTION.
HARNETT, CUMBERLAND | US 301 | NCDOT | MILEPOST 0 TO 1.674 IN CUMBERLAND COUNTY AND MILEPOST 6.171 TO 9.703 IN HARNETT COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | Highway | Safety | 6 | Mid-Carolina RPO | HS-2406K | Region C | HSIP |  |  |  |  | 2025 | 280000 |  |  | 280000
HARNETT, JOHNSTON | I-95 | NCDOT | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 10.72 | Highway | STI (Prioritization) | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | I-5986B | Statewide Mobility | T | 2020 | 42100000 | 2020 | 700000 | 2022 | 92456000 |  |  | 135256000 | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883.
HARNETT, JOHNSTON | I-95 | NCDOT | SR 1001 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). CLEARING FOR UTILITIES. | 10.72 | Highway | STI (Prioritization) | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | I-5986BA | Statewide Mobility | T |  |  |  |  | 2020 | 144000 |  |  | 144000 | UNDER CONSTRUCTION.
HARNETT, WAKE | NC 55 | NCDOT | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 42 IN FUQUAY-VARINA. WIDEN TO MULTI-LANES. PART ON NEW LOCATION. | 10 | Highway | STI (Prioritization) | 5, 6 | Capital Area MPO | R-5705
HAYWOOD | HAZELWOOD AVENUE (PLOTT CREEK ROAD) | NCDOT | HAZELWOOD AVENUE (PLOTT CREEK ROAD), RICHLAND CREEK BRIDGE TO WILL HYATT ROAD. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.56 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | EB-5859 | Division 14 | [10 empty] | UNDER CONSTRUCTION
HAYWOOD | US 19 (SOCO ROAD) | NCDOT | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. |  | Bike & Ped | Locally Selected | 14 | French Broad River MPO | EB-5926 | Division 14 | BGANY, BGDA, L |  |  |  |  | 2022 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP
HAYWOOD | TOWN OF CANTON | CANTON | CHAMPION DRIVE, NORTH CANTON ROAD TO THICKETY ROAD. CONSTRUCT MULTI-USE PATH. | 0.68 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | EB-5945 | Division 14 | BGDA, L | 2023 | 384000 | [6 empty] | 384000 | RIGHT-OF-WAY IN PROGRESS.
HAYWOOD | US 23/US 74 | NCDOT | REPLACE BRIDGE 430155, AND BRIDGE 430158 OVER RICHLAND CREEK. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | B-3186 | Statewide Mobility | BG5T50 | 2021 | 800000 |  |  | 2024 | 29145000 |  |  | 29945000 | UNDER CONSTRUCTION. TO BE LET WITH B-5898.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430236 OVER SR 1513. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | B-5541 | Highway Fund | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY.
HAYWOOD | US 23/ US 74 | NCDOT | REPLACE BRIDGE 430168 OVER US 19 AND US 23. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | B-5898 | Statewide Mobility | BG5T50 | 2021 | 150000 |  |  | 2024 | 20253000 |  |  | 20403000 | UNDER CONSTRUCTION. TO BE LET WITH B-3186.
HAYWOOD | SR 1216 (STEEL BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 430246 OVER WEST FORK PIGEON CREEK. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | B-5920 | Division 14 | BGOFF | 2025 | 30000 |  |  | 2026 | 1800000 |  |  | 1830000
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGES (430057, 430159, 430171, 430124, AND 430142) ON I-40 IN HAYWOOD COUNTY. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054 | Statewide Mobility
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430057 OVER US FOREST SERVICE ROAD/COLD SPRINGS CREEK AT HARMON'S DEN. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054A | Statewide Mobility | T |  |  |  |  | 2022 | 22898000 | 2020 | 500000 | 23398000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054B | Statewide Mobility | T |  |  | 2022 | 5000 | 2023 | 25000000 | 2020 | 500000 | 25505000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054C | Statewide Mobility | T | 2022 | 47000 | 2022 | 5000 | 2022 | 79725000 | 2020 | 2500000 | 82277000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054D | Statewide Mobility | T | 2024 | 5000 | 2024 | 5000 | 2024 | 20800000 | 2021 | 500000 | 21310000
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | B-6054E | Statewide Mobility | T | 2023 | 50000 | 2023 | 5000 | 2024 | 34400000 | 2021 | 2000000 | 36455000 | RIGHT-OF-WAY IN PROGRESS.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0002 | Statewide Mobility | BFP, HIB | 2023 | 2000000 | 2024 | 390000 | 2024 | 38276000 |  |  | 40666000 | RIGHT-OF-WAY IN PROGRESS.
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430239 OVER SR 1550 (INCINERATOR ROAD). | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0003 | Statewide Mobility | BFP, HFB | 2023 | 1000000 | 2024 | 30000 | 2024 | 27600000 |  |  | 28630000
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGE 430243 OVER NC 215 (CHAMPION DRIVE). | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0004 | Statewide Mobility | BFP, HFB | 2024 | 1100000 | 2024 | 360000 | 2024 | 26100000 |  |  | 27560000
HAYWOOD | I-40 | NCDOT | REPLACE BRIDGES 430205 AND 430208 OVER SR 1364 (COLEMAN MOUNTAIN ROAD). | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | HB-0005 | Statewide Mobility | BFP | 2025 | 2000000 | 2025 | 170000 | 2030 | 17850000 |  |  | 20020000
HAYWOOD | US 74 | NCDOT | REPLACE BRIDGE 430126 OVER I-40. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0006 | Statewide Mobility | BFP | 2025 | 1000000 |  |  | 2033 | 9000000 |  |  | 10000000
HAYWOOD | US 19/23/74 | NCDOT | REPLACE BRIDGE 430133 OVER JONES COVE ROAD (SR 1527). | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0015 | Highway Fund | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY
HAYWOOD | SR 1876 (SONOMA ROAD/ MAX THOMPSON ROAD) | NCDOT | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. REPLACE BRIDGE 430170 OVER EAST FORK PIGEON RIVER. | 0.25 | Highway | Bridges | 14 | French Broad River MPO | HB-0023 | Division 14 | BGOFF | 2024 | 320000 | 2025 | 300000 | 2025 | 5000000 |  |  | 5620000
HAYWOOD | SR 1355 (PANTHER CREEK ROAD) | NCDOT | REPLACE BRIDGE 430206 OVER FINES CREEK. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | HB-0027 | Division 14 | BGOFF | 2025 | 50000 | 2025 | 50000 | 2028 | 1000000 |  |  | 1100000
HAYWOOD | I-40 | NCDOT | MILE MARKER 27 TO MILE MARKER 34. PAVEMENT REHABILITATION. | 7 | Highway | Interstate Maintenance | 14 | French Broad River MPO, Land-of-Sky RPO | I-5834 | [11 empty] | 6-13-2022: $2.566M IN NHPIM FUNDS SWITCHED WITH $2.566M IN BGDA AS PART OF FUND SWAP.
HAYWOOD | I-40 | NCDOT | MILE MARKER 27 TO MILE MARKER 30. PAVEMENT REHABILITATION. | 3 | Highway | Interstate Maintenance | 14 | French Broad River MPO, Land-of-Sky RPO | I-5834A | Statewide Mobility | BGDA, NHPIM |  |  |  |  | 2021 | 7299000 |  |  | 7299000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | MILE MARKER 30 TO MILE MARKER 34. PAVEMENT REHABILITATION. | 4 | Highway | Interstate Maintenance | 14 | French Broad River MPO | I-5834B | Statewide Mobility | NHPIM, PROTCT |  |  |  |  | 2022 | 13958000 |  |  | 13958000 | UNDER CONSTRUCTION.
HAYWOOD | I-40 | NCDOT | MILE MARKER 15 TO MILE MARKER 20.5. PAVEMENT REHABILITATION. | 5.5 | Highway | Interstate Maintenance | 14 | Land-of-Sky RPO | I-5924 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 10899000 |  |  | 10899000
HAYWOOD | I-40 | NCDOT | MILE MARKER 34 TO BUNCOMBE COUNTY LINE. PAVEMENT REHABILITATION. | 2.74 | Highway | Interstate Maintenance | 14 | French Broad River MPO | I-5928 | Statewide Mobility | NHPIM |  |  |  |  | 2030 | 8750000 |  |  | 8750000
HAYWOOD | CANTON | NCDOT | NC 110 (PISGAH DRIVE) AT LOCUST STREET. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 14 | French Broad River MPO | U-6055 | Exempt | [10 empty] | UNDER CONSTRUCTION. STBGDA FUNDS ARE EXEMPT BECAUSE THEY ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE IS PAYING MATCH BECAUSE PROJECT CAME IN RANK ORDER OFF P3.0 PRIORITIZATION LIST
HAYWOOD | WAYNESVILLE (DEPOT STREET) | WAYNESVILLE | REPLACE BRIDGE 430262 OVER RICHLAND CREEK. | 0.25 | Highway | Municipal Bridge | 14 | French Broad River MPO | B-5013 | Division 14 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY THE TOWN OF WAYNESVILLE - MUNICIPAL BRIDGE
HAYWOOD | GREAT SMOKY MOUNTAINS NATIONAL PARK | NCDOT | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. |  | Highway | Other | 14 | Land-of-Sky RPO | HO-0003 | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 250000 | 250000 | IN PROGRESS
HAYWOOD | US 19 | NCDOT | HOLSTON VILLAGE ROAD AND SR 1197 (GOLF COURSE ROAD). UPGRADE INTERSECTIONS. | 0.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014K | Region G | HSIP |  |  |  |  | 2025 | 110000 |  |  | 110000 | UNDER CONSTRUCTION.
HAYWOOD | US 19 | NCDOT | JACKSON COUNTY TO MAGGIE VALLEY. INSTALL LONG LIFE PAVEMENT MARKINGS. | 3.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014S | Region G | HSIP |  |  |  |  | 2024 | 263000 |  |  | 263000
HAYWOOD | US 19 (DELLWOOD ROAD) | NCDOT | NORTH LAKESHORE DRIVE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014Y | Region G | HSIP |  |  |  |  | 2025 | 210000 |  |  | 210000
HAYWOOD | US 276 | NCDOT | CONSTRUCT LEFT TURN LANE 0.3 MILES SOUTH OF SR 1326 (BOB BOYD ROAD). | 0.5 | Highway | Safety | 14 | Land-of-Sky RPO | W-5814A | Region G | HSIP |  |  |  |  | 2022 | 380000 |  |  | 380000 | UNDER CONSTRUCTION.
HAYWOOD | US 276 (JONATHAN CREEK) | NCDOT | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | 5.87 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO, French Broad River MPO | R-5921 | Division 14 | BGANY | 2023 | 8400000 | 2023 | 3200000 | 2025 | 42000000 |  |  | 53600000 | RIGHT-OF-WAY IN PROGRESS. FUND CONSTRUCTION WITH TOLL CREDITS.
HAYWOOD | US 23 BUSINESS (SOUTH MAIN STREET) | NCDOT | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | 2.09 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-4712 | Division 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25502000 |  |  | 57402000
HAYWOOD | US 276 (RUSS AVENUE) | NCDOT | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | 1.06 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5839 | Division 14 | T | 2019 | 6830000 | 2020 | 750000 | 2024 | 58577000 | 2020 | 3330000 | 69487000 | ROW IN PROGRESS. BUILD NC BOND FUNDING: $2.585M FOR PE, PAYBACK FY 20-34 (FY 19 / YR 1 SALE); $2.16M FOR ROW, PAYBACK FY 20-34 (FY 19 / YR 1 SALE). $17,693,719 FOR CON, PAYBACK FY 25-39 (FY 25 / YR 5 SALE); TO BE LET WITH U-5888.
HAYWOOD | US 23 BUSINESS | NCDOT | INTERSECTION OF US 23 BUSINESS (NORTH MAIN STREET) AND WALNUT STREET. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5888 | Division 14 | T |  |  |  |  | 2022 | 8751000 |  |  | 8751000 | UNDER CONSTRUCTION. TO BE LET WITH U-5839.
HAYWOOD | US 276 | NCDOT | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | 0.5 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-6158 | Division 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 |  |  | 6700000
HAYWOOD | US 276 (RUSS AVENUE) | NCDOT | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | 1.32 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-6159 | Division 14 | BG5T50 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25200000 |  |  | 38900000
HAYWOOD | MOUNTAIN PROJECTS, INC. | MOUNTAIN PROJECTS, INC. | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 |  | TK-6149 | Public Transit | 5311, L, S | [6 empty] | 2020 | 932000 | 932000 | FUNDS AUTHORIZED IN PROGRESS
HAYWOOD | HAYWOOD COUNTY |  | HAYWOOD COUNTY OPERATING ASSISTANCE |  | Public Transportation (Transit) | Operations and Maintenance | 14 | French Broad River MPO | TM-0054 | Public Transit | 5307, L | [6 empty] | 2024 | 984000 | 984000
HAYWOOD | WAYNESVILLE | CITY OF ASHEVILLE | MOUNTAIN PROJECTS ( HAYWOOD COUNTY) DEVIATED FIXED ROUTE CAPITAL AND CARES FUNDS. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 14 | French Broad River MPO | TG-6788 | Public Transit | 5307, L | [6 empty] | 2024 | 1034000 | 1034000
HAYWOOD | NC 215 (BLACKWELL DRIVE) | NCDOT | BLU CROSSING 720349K IN CANTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2014A | Division 14 | RR |  |  |  |  | 2026 | 345000 |  |  | 345000
HAYWOOD | NC 215 (BLACKWELL DRIVE) | NCDOT | BLU CROSSING 720349K IN CANTON. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414D | Division 14 | RR |  |  |  |  | 2025 | 345000 |  |  | 345000
HAYWOOD | HAZELWOOD AVENUE | NCDOT | BLU CROSSING 720305K IN WAYNESVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414K | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
HAYWOOD, BUNCOMBE | US 19, US 23 | NCDOT | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | 3.85 | Highway | STI (Prioritization) | 13, 14 | French Broad River MPO | U-6048 | Division 13, 14 | T | 2030 | 300000 | 2030 | 700000 | 2033 | 48600000 |  |  | 49600000
HAYWOOD, HENDERSON, JACKSON, POLK, TRANSYLVANIA | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS PRIMARY AND SECONDARY ROUTES. |  | Highway | Safety | 14 | Foothills RPO, French Broad River MPO, Land-of-Sky RPO, Southwestern RPO | HS-2014R | Region G | HSIP |  |  |  |  | 2023 | 1225000 |  |  | 1225000 | UNDER CONSTRUCTION.
HAYWOOD, HENDERSON, MACON, POLK, SWAIN | VARIOUS | NCDOT | INSTALL SNOWPLOWABLE MARKERS AND PAVEMENT MARKINGS FOR WRONG WAY RAMP ARROWS ON VARIOUS FREEWAY RAMPS. | 0.5 | Highway | Safety | 14 | Southwestern RPO, Foothills RPO, French Broad River MPO | HS-2014C | Statewide Mobility | HSIP |  |  |  |  | 2023 | 50000 |  |  | 50000 | UNDER CONSTRUCTION.
HAYWOOD, JACKSON | US 74 | NCDOT | IMPROVE PAVEMENT FROM SR 1392 TO EAST OF SR 1388 AND FROM JACKSON COUNTY LINE TO BRIDGES 107 AND 110. | 9.77 | Highway | Safety | 14 | French Broad River MPO, Southwestern RPO | HS-2014E | Statewide Mobility | HSIP |  |  |  |  | 2023 | 975000 |  |  | 975000 | UNDER CONSTRUCTION.
HAYWOOD, POLK | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS SECONDARY ROUTES. |  | Highway | Safety | 14 | French Broad River MPO, Foothills RPO, Land-of-Sky RPO | HS-2014J | Division 14 | HSIP |  |  |  |  | 2023 | 2570000 |  |  | 2570000 | UNDER CONSTRUCTION.
HAYWOOD, ROBESON | I-40 AND I-95 | NCDOT | I-40 FROM TENNESSEE STATE LINE TO MM 20 AND I-95 FROM EXIT 13 TO SOUTH OF PROPOSED I-295. IMPLEMENT SYSTEM TO PROVIDE REAL TIME ALERTS IN VEHICLES WHEN DRIVERS ENCOUNTER A ROAD ANOMALY REQUIRING THEM TO TAKE DRIVING ACTION. | 40 | Highway | Other | 6, 14 | Land-of-Sky RPO, Lumber River RPO | HO-0011 | Statewide Mobility | DP, O | [6 empty] | 2024 | 1972000 | 1972000 | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH.
HAYWOOD, SWAIN | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | Highway | Other | 14 | Land-of-Sky RPO, Southwestern RPO | C-5612 | Exempt | CMAQ, L | 2020 | 4000 |  |  | 2020 | 19000 | 2020 | 12000 | 35000 | IN PROGRESS
HENDERSON | ECUSTA RAIL-TRAIL | NCDOT | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | BL-0007 | Division 14 | BGDA, CRPDA, DP, L, TADA |  |  |  |  | 2023 | 15025000 | 2022 | 683000 | 15708000 | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS.
HENDERSON | CLEAR CREEK GREENWAY/ HENDERSONVILLE | HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | BL-0008 | Division 14 | BGANY, BGDA, L |  |  |  |  | 2025 | 3314000 | 2022 | 1403000 | 4717000 | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23.
HENDERSON | ECUSTA TRAIL | HENDERSON COUNTY | US 64 TO TRANSYLVANIA COUNTY LINE. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 14 | French Broad River MPO | BL-0078 | Division 14 | BGDA, L |  |  |  |  | 2027 | 11283000 | 2024 | 1800000 | 13083000
HENDERSON | TOWN OF MILLS RIVER | MILLS RIVER | NC 280, FRENCH BROAD RIVER TO HAYWOOD ROAD (NC 191). CONSTRUCT MULTI-USE PATH. | 3.09 | Bike & Ped | Locally Selected | 14 | French Broad River MPO | EB-5946 | Division 14 | L, TADA | [6 empty] | 2026 | 375000 | 375000
HENDERSON | BLYTHE STREET | NCDOT | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | Bike & Ped | STI (Prioritization) | 14 | French Broad River MPO | EB-5860 | Division 14 | L, TAANY | 2026 | 45000 | 2026 | 35000 | 2030 | 1153000 | 2024 | 267000 | 1500000
HENDERSON | GROVE STREET | NCDOT | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | Bike & Ped | STI (Prioritization) | 14 | French Broad River MPO | EB-5963 | Division 14 | L, TAANY | 2025 | 800000 | 2025 | 95000 | 2027 | 900000 | 2024 | 157000 | 1952000
HENDERSON | SR 1970 (COMMERCIAL BLVD) | NCDOT | CONSTRUCT ROADWAY EXTENSION TO INDUSTRIAL PARK. | 0.38 | Highway | Appalachian Development Highway System | 14 | French Broad River MPO | HA-0003 | Exempt | ADHSL | 2021 | 70000 |  |  | 2021 | 1830000 |  |  | 1900000 | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000
HENDERSON | I-26 | NCDOT | MILE MARKER 50 TO POLK COUNTY LINE. PAVEMENT REHABILITATION. | 7.96 | Highway | Interstate Maintenance | 14 | French Broad River MPO | I-5925 | Statewide Mobility | NHPIM |  |  |  |  | 2027 | 15200000 |  |  | 15200000
HENDERSON | TRACY GROVE ROAD | NCDOT | REPLACE BRIDGE 440350 OVER DEVILS FORK CREEK. | 0.25 | Highway | Municipal Bridge | 14 | French Broad River MPO | B-5929 | Division 14 | BGOFF |  |  |  |  | 2025 | 2100000 | 2025 | 125000 | 2225000 | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE
HENDERSON | US 25 BUSINESS (ASHEVILLE HIGHWAY) | NCDOT | HENDERSONVILLE CITY LIMIT TO SR 1534. INSTALL RUMBLE STRIPS WITH LONG LIFE PAVEMENT MARKINGS. | 4.3 | Highway | Safety | 14 | French Broad River MPO | HS-2014I | Region G | HSIP |  |  |  |  | 2024 | 349000 |  |  | 349000
HENDERSON | US 64 | NCDOT | SR 1574 (FRUITLAND ROAD), SR 1006 (HOWARD GAP ROAD), SR 1519 (THOMPSON STREET)/ SR 1751 (FREEMAN STREET), SR 1749 (ORR'S CAMP ROAD)/ SR 1634 (CAROLINA AVENUE). UPGRADE INTERSECTIONS. | 0.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014L | Region G | HSIP |  |  |  |  | 2023 | 570000 |  |  | 570000 | UNDER CONSTRUCTION.
HENDERSON | US 64 | NCDOT | SR 1586 (SOUTH MILLS GAP ROAD)/ TUTTLE ROAD. INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 14 | French Broad River MPO | HS-2014O | Region G | HSIP | 2023 | 20000 |  |  | 2023 | 75000 |  |  | 95000
HENDERSON | US 64, US 25 BUSINESS | NCDOT | UPGRADE SIGNAL SYSTEM AT 33 INTERSECTIONS ALONG US 64 AND US 25 BUSINESS. |  | Highway | Safety | 14 | French Broad River MPO | HS-2014Q | Region G | HSIP |  |  |  |  | 2023 | 225000 |  |  | 225000 | UNDER CONSTRUCTION.
HENDERSON | US 64 (6TH AVENUE W.) | NCDOT | NORTH OAK STREET INTERSECTION IN HENDERSONVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACON WITH ADVANCED FLASHERS AND ACTUATED CROSSWALK LIGHTING. |  | Highway | Safety | 14 | French Broad River MPO | HS-2414C | Region G | HSIP |  |  |  |  | 2025 | 50000 |  |  | 50000
HENDERSON | NC 191 (HAYWOOD ROAD) | NCDOT | RIDGEWOOD BOULEVARD / WHITMIRE STREET INTERSECTION IN HENDERSONVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACON AND ACTUATED CROSSWALK LIGHTING. |  | Highway | Safety | 14 | French Broad River MPO | HS-2414F | Region G | HSIP |  |  |  |  | 2025 | 43000 |  |  | 43000
HENDERSON | I-26 | NCDOT | US 25 TO US 64 | 4.64 | Highway | STI (Prioritization) | 14 | French Broad River MPO | I-4400A | Not Funded | NHP | NOT FUNDED | 1600000 | NOT FUNDED | 500000 | NOT FUNDED | 114800000 | NOT FUNDED |  | 116900000
HENDERSON | I-26 | NCDOT | US 64 INTERCHANGE IMPROVEMENTS | 1 | Highway | STI (Prioritization) | 14 | French Broad River MPO | I-4400BA | Division 14 | T |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 143200000 |  |  | 143600000
HENDERSON | I-26 | NCDOT | US 64 TO US 25 BUSINESS | 5.73 | Highway | STI (Prioritization) | 14 | French Broad River MPO | I-4400BB | Statewide Mobility | NHP |  |  |  |  | 2019 | 52752000 |  |  | 52752000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $43,911,307 FOR CONSTRUCTION, PAYBACK FY 2019-2033
HENDERSON | NC 191 | NCDOT | US 25 IN HENDERSONVILLE TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | 7.2 | Highway | STI (Prioritization) | 14 | French Broad River MPO | R-2588
HENDERSON | NC 191 | NCDOT | US 25 TO SR 1381 (MOUNTAIN ROAD). WIDEN TO MULTI-LANES. |  | Highway | STI (Prioritization) | 14 | French Broad River MPO | R-2588A | Not Funded | BGANY | NOT FUNDED | 15200000 | NOT FUNDED | 1800000 | NOT FUNDED | 18800000 | NOT FUNDED |  | 35800000
HENDERSON | NC 191 | NCDOT | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | 4.41 | Highway | STI (Prioritization) | 14 | French Broad River MPO | R-2588B | Division 14 | NHP, T | 2021 | 9500000 | 2022 | 15500000 | 2029 | 148300000 |  |  | 173300000 | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901).
HENDERSON | NC 191 | NCDOT | SR 1381 (MOUNTAIN ROAD) TO NC 280. CLEARING FOR UTILITIES. WIDEN TO MULTI-LANES. |  | Highway | STI (Prioritization) | 14 | French Broad River MPO | R-2588BA | Division 14 | T |  |  |  |  | 2025 | 556000 |  |  | 556000
HENDERSON | US 64 | NCDOT | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). MODERNIZE ROADWAY WITH BIKE LANES AND PAVED SHOULDERS. | 0.99 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5783 | Region G | T | 2022 | 19900000 | 2022 | 3900000 | 2025 | 26000000 |  |  | 49800000 | RIGHT-OF-WAY IN PROGRESS.
HENDERSON | SR 1547 (OLD AIRPORT ROAD) | NCDOT | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | 0.89 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5840 | Division 14 | T | 2020 | 855000 |  |  | 2020 | 12150000 | 2020 | 1575000 | 14580000 | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE).
HENDERSON | SR 1170 (WHITE STREET) | NCDOT | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | 0.42 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5886 | Division 14 | T | 2023 | 18700000 | 2023 | 2600000 | 2028 | 18200000 |  |  | 39500000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-6049.
HENDERSON | SR 1783 (HIGHLAND LAKE ROAD) | NCDOT | NC 225 TO US 176. UPGRADE ROADWAY. | 1.07 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-5887 | Division 14 | T | 2020 | 2295000 |  |  | 2021 | 7676000 |  |  | 9971000 | UNDER CONSTRUCTION.
HENDERSON | NC 225 (SOUTH MAIN STREET) | NCDOT | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | 0.24 | Highway | STI (Prioritization) | 14 | French Broad River MPO | U-6049 | Region G | BGANY, T | 2023 | 3400000 | 2023 | 400000 | 2028 | 4000000 |  |  | 7800000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5886
HENDERSON | NC 225 SR 1164 (ERKWOOD DRIVE) | NCDOT | NC 225/SR 1164 (ERKWOOD DRIVE)/SR 1779(SHEPHERD STREET) IN HENDERSONVILLE. IMPROVE INTERSECTION. | 0.5 | Highway | Transition | 14 | French Broad River MPO | U-5105 | Pre-STI (Transition) | [10 empty] | DIVISION PROJECT - UNDER CONSTRUCTION
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | REPLACEMENT TRANSIT VEHICLE ACQUISITION |  | Public Transportation (Transit) | Capital (Non-STI) | 14 | French Broad River MPO | TA-5229 | Public Transit | 5307, L | [6 empty] | 2024 | 578000 | 578000
HENDERSON | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 14 | French Broad River MPO | TS-5101 | Public Transit | 5307, L | [6 empty] | 2020 | 11000 | 11000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 14 | French Broad River MPO | TO-6106 | Public Transit | 5307, 5311, L | [6 empty] | 2024 | 474000 | 474000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING |  | Public Transportation (Transit) | Operations and Maintenance | 14 | French Broad River MPO | TG-4951 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 1921000 | 1921000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 | French Broad River MPO | TK-5176 | Public Transit | 5311, L, S | [6 empty] | 2020 | 540000 | 540000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | PROGRAM SUPPORT. |  | Public Transportation (Transit) | Planning | 14 | French Broad River MPO | TU-0010 | Public Transit | 5307, L | [6 empty] | 2022 | 600000 | 600000
HENDERSON | CITY OF ASHEVILLE | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 14 | French Broad River MPO | TG-6143 | Public Transit | 5307, 5311, L | [6 empty] | 2021 | 202000 | 202000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | APPLE COUNTRY TRANSIT | TRANSIT ROUTINE CAPITAL COST OF CONTRACTING |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 14 | French Broad River MPO | TG-6181 | Public Transit | 5307, L | [6 empty] | 2024 | 630000 | 630000
HENDERSON | FIFTH AVENUE | NCDOT | BLU CROSSING 720654V IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414A | Division 14 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
HENDERSON | SR 1633 (INDUSTRIAL PARK ROAD) | NCDOT | BLU CROSSING 729533D IN BALFOUR. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414B | Division 14 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
HENDERSON | RAY AVENUE | NCDOT | BLU CROSSING 729542C IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414C | Division 14 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
HENDERSON | SEVENTH AVENUE | NCDOT | BLU CROSSING 720651A IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414E | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
HENDERSON | SR 1527 (JONES COVE ROAD) | NCDOT | BLU CROSSING 720335C IN CLYDE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414G | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
HENDERSON | SR 1503 (MAIN STREET) | NCDOT | BLU CROSSING 729541V IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414H | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
HENDERSON | SR 1695 (NAPLES ROAD) | NCDOT | BLU CROSSING 720650T IN NAPLES. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414I | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
HENDERSON | FOURTH AVENUE | NCDOT | BLU CROSSING 720655C IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | French Broad River MPO | RX-2414J | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
HENDERSON, BUNCOMBE | I-26 | NCDOT | US 25 TO NC 280. WIDEN TO ADD ADDITIONAL LANES. | 13.6 | Highway | STI (Prioritization) | 13, 14 | French Broad River MPO | I-4400
HENDERSON, BUNCOMBE | I-26 | NCDOT | US 25 BUSINESS TO NC 280 | 3.29 | Highway | STI (Prioritization) | 13, 14 | French Broad River MPO | I-4400C | Region G | NHP |  |  |  |  | 2019 | 61776000 |  |  | 61776000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035
HENDERSON, TRANSYLVANIA | ECUSTA TRAIL | NCDOT | BREVARD BIKE PATH IN BREVARD TO KANUGA ROAD IN HENDERSONVILLE. CONSTRUCT MULTI-USE PATH. | 19.57 | Bike & Ped | Locally Selected | 14 | French Broad River MPO, Land-of-Sky RPO | EB-6037B | Division 14 | L, TAANY | 2021 | 8000000 | [6 empty] | 8000000 | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE.
HERTFORD | SR 1179 (UNION STREET) | CHOWAN UNIVERSITY | NORTH OF SEWELL STREET TO HAWKS DRIVE IN MURFREESBORO. CONSTRUCT SIDEWALK ON WEST SIDE. |  | Bike & Ped | Locally Selected | 1 | Peanut Belt RPO | BN-0018 | Exempt | CRPLT5, L(M) |  |  |  |  | 2025 | 326000 | 2025 | 10000 | 336000
HERTFORD | NC 11 | NCDOT | SR 1212 (SHORT CUT ROAD) TO US 158. INSTALL RUMBLE STRIPS AND PAVEMENT MARKERS. |  | Highway | Safety | 1 | Peanut Belt RPO | HS-2401D | Region A | HSIP |  |  |  |  | 2025 | 300000 |  |  | 300000
HERTFORD | US 158 / 258 | NCDOT | AT SR 1157 (POWELL ROAD) NEAR MURFREESBORO. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. |  | Highway | Safety | 1 | Peanut Belt RPO | HS-2401P | Region A | HF, HSIP |  |  |  |  | 2026 | 1900000 |  |  | 1900000 | HF FUNDS REPRESENT HIGH IMPACT-LOW COST DIVISION FUNDS.
HERTFORD | US 13/NC 11 | NCDOT | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. WIDEN TO MULTI-LANES. | 7.8 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5311
HERTFORD | US 13/NC 11 | NCDOT | WEST OF MODLIN ROAD TO EAST OF NC 11/SR 1213 (OLD NC 11 ROAD). CONSTRUCT GRADE SEPARATION AT SR 1130 (MODLIN ROAD) AND INTERCHANGE AT OLD NC 11/SR 1213 (OLD NC 11 ROAD). | 1 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5311A | Statewide Mobility | [10 empty] | COMPLETED.
HERTFORD | US 13/NC 11 | NCDOT | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | 7.77 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5311B | Region A | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6301000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 193400000 |  |  | 202701000
HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | NCDOT | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 0.78 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5796 | Region A | T | 2024 | 2574000 | 2024 | 2000000 | 2026 | 17900000 |  |  | 22474000 | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605.
HERTFORD | NC 461 | NCDOT | NC 45 TO END OF STATE MAINTENANCE. MODERNIZE ROADWAY. | 4.05 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5811 | Division 1 | T |  |  |  |  | 2023 | 5252000 |  |  | 5252000 | UNDER CONSTRUCTION.
HERTFORD | SR 1409 (HALL SIDING ROAD) | NCDOT | NCVA CROSSING 642347G IN AHOSKIE. |  | Rail | Rail-Highway Grade Crossing Improvement | 1 | Peanut Belt RPO | RX-2001A | Division 1 | RR |  |  |  |  | 2025 | 355000 | 2025 | 20000 | 375000 | UNDER CONSTRUCTION.
HERTFORD | SR 1101 (MAIN STREET) | NCDOT | NCVA CROSSING 629828U IN AHOSKIE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 1 | Peanut Belt RPO | RX-2401A | Division 1 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
HERTFORD, CURRITUCK, MARTIN, DARE, GATES, BERTIE, NORTHAMPTON, CAMDEN | VARIOUS | NCDOT | PRIMARY ROUTES IN DIVISION 1. UPGRADE GUARDRAIL END UNITS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2401B | Region A | HSIP |  |  |  |  | 2025 | 491000 |  |  | 491000
HOKE | HOKE TRAIL | FAYETTEVILLE | NEAR JAMES A. LEACH AQUATIC & RECREATION CENTER. CONSTRUCT COUNTY-OPERATED TRAIL SYSTEM IN HOKE COUNTY. |  | Bike & Ped | Locally Selected | 8 | Fayetteville Area MPO | BL-0135 | Division 8 | CRPDA, L(M) |  |  |  |  | 2025 | 429000 |  |  | 429000
HOKE | US 401 | HOKE COUNTY | WALMART TO JAMES A. LEACH AQUATIC & RECREATION CENTER IN RAEFORD. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 8 | Fayetteville Area MPO | BL-0136 | Division 8 | BGDA, L(M) |  |  |  |  | 2025 | 343000 | 2025 | 202000 | 545000
HOKE | US 401; NC 211 | HOKE COUNTY | VARIOUS LOCATIONS ALONG ROUTES IN RAEFORD. INSTALL AND MAINTAIN 5 ELECTRIC VEHICLE DC FAST CHARGERS. |  | Highway | Locally Selected | 8 | Fayetteville Area MPO | HL-0142 | Region E | CRPDA, L(M) |  |  |  |  | 2026 | 580000 | 2025 | 50000 | 630000
HOKE | NC 211 | NCDOT | 0.40 MILES NORTH OF SR 1225 (ASHEMONT ROAD) TO EAST OF SR 1244 (WEST PALMER STREET)/SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTI-LANES. | 9.46 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-5709C | Region E | T |  |  |  |  | 2025 | 139700000 |  |  | 139700000
HOKE | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | NCDOT | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTI-LANES. | 4.5 | Highway | STI (Prioritization) | 8 | Fayetteville Area MPO | U-5753 | Division 8 | BGANY, T | 2022 | 42100000 | 2022 | 5000000 | 2026 | 68210000 |  |  | 115310000 | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE)
HOKE | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | NCDOT | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3.19 | Highway | STI (Prioritization) | 8 | Fayetteville Area MPO | U-5857 | Division 8 | T | 2030 | 38200000 | 2030 | 4600000 | 2034 | 86400000 |  |  | 129200000 | COORDINATE WITH U-5753 AND U-5798.
HOKE | HOKE COUNTY | HOKE COUNTY | OPERATING ASSISTANCE FY20-21 |  | Public Transportation (Transit) | Miscellaneous/Other | 8 | Fayetteville Area MPO | TO-6157 | Public Transit | 5307, L | [6 empty] | 2020 | 932000 | 932000
HOKE | SR 1003 (ARABIA ROAD) | NCDOT | AR CROSSING 847348H IN DUNDARRACH. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO | RX-2008D | Division 8 | RR |  |  |  |  | 2025 | 345000 |  |  | 345000
HOKE, MOORE | NC 211 | NCDOT | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTI-LANES. | 15.36 | Highway | STI (Prioritization) | 8 | Lumber River RPO, Sandhills MPO | R-5709 | Region E | T | 2021 | 59423000 | 2021 | 4976000 |  |  |  |  | 64399000 | RIGHT-OF-WAY IN PROGRESS
HOKE, MOORE | NC 211 | NCDOT | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. CLEARING, GRUBBING, AND EROSION CONTROL. | 15.36 | Highway | STI (Prioritization) | 8 | Lumber River RPO, Sandhills MPO | R-5709A | Region E | T |  |  |  |  | 2022 | 30625000 |  |  | 30625000 | UNDER CONSTRUCTION.
HOKE, MOORE | NC 211 | NCDOT | US 15/US 501 IN ABERDEEN TO 0.40 MILES NORTH OF SR 1225 (ASHEMONT ROAD). WIDEN TO MULTI-LANES. | 5.9 | Highway | STI (Prioritization) | 8 | Lumber River RPO, Sandhills MPO | R-5709B | Region E | T |  |  |  |  | 2029 | 114200000 |  |  | 114200000
HYDE | HYDE COUNTY AIRPORT (7W6) | HYDE COUNTY AIRPORT (7W6) | EXTEND RUNWAY TO 5000 FEET. |  | Aviation | STI (Prioritization) | 1 | Albemarle RPO | AV-5812 | Division 1 | T |  |  |  |  | 2023 | 1800000 |  |  | 1800000 | UNDER CONSTRUCTION.
HYDE | NC 12 | NCDOT | OCRACOKE PEDESTRIAN WAITING AND ACCESS ACCOMMODATIONS |  | Ferry | Other | 1 | Albemarle RPO | F-5702B | Division 1 | [10 empty] | COMPLETED.
HYDE | HYDE COUNTY NON-PROFIT | HYDE COUNTY NON-PROFIT | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 1 | Albemarle RPO | TK-6135 | Public Transit | 5311, L, S | [6 empty] | 2020 | 400000 | 400000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | STATESVILLE REGIONAL AIRPORT (SVH) | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. |  | Aviation | STI (Prioritization) | 12 | Charlotte Regional TPO | AV-5896 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5610000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3725000 |  |  | 9335000
IREDELL | NC 152 (NORTH MAIN STREET) | MOORESVILLE | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.68 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0009 | Division 12 | BGDA, L | 2025 | 617000 |  |  | 2027 | 729000 | 2025 | 138000 | 1484000
IREDELL | MOORE AVENUE | MOORESVILLE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.22 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0013 | Division 12 | L, TAANY |  |  |  |  | 2025 | 1990000 | 2024 | 10000 | 2000000 | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23
IREDELL | MOORESVILLE | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0055 | Division 12 | L, TAANY |  |  |  |  | 2026 | 2081000 | 2025 | 363000 | 2444000 | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23
IREDELL | SR 2162 (WHITE OAK ROAD); MAPLE AVENUE; McNEELY AV | MOORESVILLE | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 0.69 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0056 | Division 12 | BGDA, L | 2027 | 104000 |  |  | 2029 | 1972000 | 2024 | 563000 | 2639000
IREDELL | NC 115 | MOORESVILLE | FAIRVIEW ROAD TO WATERLYNN ROAD. CONSTRUCT SHARED USE PATH. | 0.55 | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0082 | Division 12 | L, TAANY, TADA | 2027 | 700000 |  |  | 2029 | 3829000 | 2025 | 344000 | 4873000 | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24.
IREDELL | PATTERSON HEIGHTS | MOORESVILLE | WEST MOORE AVENUE TO WEST IREDELL AVENUE IN MOORESVILLE. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | BL-0122 | Division 12 | BGDA, L |  |  |  |  | 2028 | 3148000 | 2025 | 10000 | 3158000
IREDELL | MOORESVILLE | MOORESVILLE | KISTLER FARM-BRIARCLIFF-BELLINGHAM-WHITE OAK SIDEWALK NETWORK IN MOORESVILLE. CONSTRUCT SIDEWALKS IN VARIOUS LOCATIONS. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | C-5531 | Exempt | BGDA, L |  |  |  |  | 2020 | 801000 |  |  | 801000 | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES.
IREDELL | MOORESVILLE | MOORESVILLE | BELLINGHAM PARK GREENWAY EXTENSION TO JOHNSON DAIRY ROAD. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5787 | Division 12 | L, TADA |  |  |  |  | 2023 | 4444000 |  |  | 4444000 | UNDER CONSTRUCTION.
IREDELL | STATESVILLE | STATESVILLE | SHELTON AVENUE MULTI-USE PATH, GARNER BAGNAL BOULEVARD TO AMITY HILL ROAD. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5788 | Division 12 | BGDA, L | 2023 | 251000 | [6 empty] | 251000 | RIGHT-OF-WAY IN PROGRESS
IREDELL | STATESVILLE | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5818 | Division 12 | BGDA, L, TAANY |  |  |  |  | 2024 | 3060000 |  |  | 3060000 | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23
IREDELL | TROUTMAN | TROUTMAN | RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. DOWNTOWN TROUTMAN SIDEWALK IMPROVEMENTS. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5930 | Division 12 | L, TADA | 2024 | 199000 |  |  | 2024 | 1623000 | 2021 | 312000 | 2134000
IREDELL | TROUTMAN | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 12 | Charlotte Regional TPO | EB-5932 | Division 12 | L, TADA | 2024 | 217000 |  |  | 2025 | 1250000 | 2021 | 122000 | 1589000
IREDELL | SR 2402 (HOOVER ROAD) | NCDOT | REPLACE BRIDGE 480020 OVER I-L CREEK. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | B-5843 | Division 12 | BGOFF | 2028 | 67000 |  |  | 2030 | 675000 |  |  | 742000
IREDELL | SR 1892 (JENNINGS ROAD) | NCDOT | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | B-5846 | Division 12 | BGOFF | 2022 | 85000 | 2022 | 325000 | 2023 | 5495000 |  |  | 5905000 | RIGHT-OF-WAY IN PROGRESS.
IREDELL | SR 1639 (MEACHAM RD) | NCDOT | REPLACE BRIDGE 480118 OVER I-40. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0025 | Division 12 | BFP | 2027 | 80000 | 2027 | 20000 | 2029 | 4200000 |  |  | 4300000
IREDELL | SR 1577 | NCDOT | REPLACE BRIDGE 480131 OVER UT TO SNOW CREEK. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0107 | Highway Fund | HFB |  |  |  |  | 2022 | 800000 |  |  | 800000 | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT.
IREDELL | SR 1601 (BRANTON ROAD) | NCDOT | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0114 | Division 12 | DP, HFB | 2020 | 150000 |  |  | 2021 | 1150000 |  |  | 1300000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
IREDELL | SR 1595 (COOLBROOK ROAD) | NCDOT | REPLACE BRIDGE 480166 ON SR 1595 OVER ROCKY CREEK. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0115 | Division 12 | DP, HFB | 2020 | 170000 |  |  | 2021 | 1600000 |  |  | 1770000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
IREDELL | SR 1892 | NCDOT | REPLACE BRIDGE 480212 OVER PATTERSON CREEK. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0202 | Highway Fund | HFB |  |  |  |  | 2021 | 1250000 |  |  | 1250000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.49
IREDELL | SR 1896 | NCDOT | REPLACE BRIDGE 480214 OVER PATTERSON CREEK | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0203 | Highway Fund | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.50
IREDELL | SR 1892 | NCDOT | REPLACE BRIDGE 480219 OVER OLIN CREEK. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | BR-0204 | Highway Fund | HFB |  |  |  |  | 2021 | 900000 |  |  | 900000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.51
IREDELL | I-40 | NCDOT | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | HB-0018 | Statewide Mobility | BFP | 2026 | 700000 | 2026 | 700000 | 2028 | 59900000 |  |  | 61300000
IREDELL | SR 1004 (HUDSON CHAPEL ROAD) | NCDOT | REPLACE BRIDGE 480081 CATAWBA RIVER. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | HB-0032 | Division 12 | BGOFF | 2025 | 100000 | 2025 | 250000 | 2028 | 20400000 |  |  | 20750000
IREDELL | I-77 | NCDOT | REPLACE BRIDGES 480133 AND 480128 OVER THIRD CREEK. | 0.25 | Highway | Bridges | 12 | Charlotte Regional TPO | HB-0041 | Statewide Mobility | BFP | 2026 | 500000 | 2026 | 500000 | 2028 | 10000000 |  |  | 11000000
IREDELL | I-40 | NCDOT | SR 2158 (OLD MOCKSVILLE ROAD) TO DAVIE COUNTY LINE. PAVEMENT REHABILITATION. | 8.26 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO | I-5805 | Statewide Mobility | NHPIM |  |  |  |  | 2030 | 70501000 |  |  | 70501000
IREDELL | I-77 | NCDOT | MILEMARKER 36.5 TO MILEMARKER 50.0. PAVEMENT REHABILITATION. | 13.55 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO | I-5918 | Statewide Mobility | NHFP, NHPIM, PROTCT |  |  |  |  | 2024 | 30201000 |  |  | 30201000
IREDELL | I-77 | NCDOT | MILEMARKER 53.7 TO MILEMARKER 56.8. PAVEMENT REHABILITATION. | 3.1 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO | I-5919 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2025 | 12300000 |  |  | 12300000
IREDELL | I-77 | NCDOT | MILE MARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | 10.41 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO | I-5920 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2028 | 19274000 |  |  | 19274000
IREDELL | MOORESVILLE | MOORESVILLE | NC 115 AND NC 150 IN MOORESVILLE. CONSTRUCT SOUTHBOUND NC 115 RIGHT TURN LANE AT NC 150 AND WESTBOUND NC 150 SHARED THROUGH-RIGHT LANE AT NC 115. |  | Highway | Locally Selected | 12 | Charlotte Regional TPO | C-5200 | Exempt | BGDA, L |  |  |  |  | 2020 | 1514000 |  |  | 1514000 | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES.
IREDELL | MOORESVILLE | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 0.5 | Highway | Locally Selected | 12 | Charlotte Regional TPO | C-5529 | Exempt | BGDA, L |  |  |  |  | 2023 | 1128000 | 2023 | 259000 | 1387000 | UNDER CONSTRUCTION
IREDELL | MOORESVILLE | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 12 | Charlotte Regional TPO | C-5701 | Region F | BA, BGDA, CMAQ, L | 2020 | 324000 |  |  | 2020 | 3236000 |  |  | 3560000 | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
IREDELL | VARIOUS | NCDOT | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING AND PAVEMENT RESTRIPING. |  | Highway | Locally Selected | 12 | Charlotte Regional TPO | HL-0037 | Division 12 | BGDACV |  |  |  |  | 2023 | 975000 |  |  | 975000
IREDELL | LANGTREE ROAD | MOORESVILLE | PIN OAK LANE TO MOUNT MOURNE LOOP. WIDEN ROADWAY. | 1.21 | Highway | Locally Selected | 12 | Charlotte Regional TPO | HL-0114 | Division 12 | L, T(DA) | [6 empty] | 2024 | 1091000 | 1091000 | $873K IN STBG-DA FUNDS SWAPPED FOR $873K IN STATE FUNDS ON 5-17-23
IREDELL | US 21 / NC 115 (MAIN STREET) | TROUTMAN | MURDOCK ROAD / OLD MOUNTAIN ROAD INTERSECTION IN TROUTMAN; CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 12 | Charlotte Regional TPO | HL-0134 | Region F | BGANY, L | 2027 | 1582000 |  |  | 2029 | 3295000 | 2025 | 580000 | 5457000 | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24.
IREDELL | STATESVILLE | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | 0.09 | Highway | Locally Selected | 12 | Charlotte Regional TPO | U-6054 | Division 12 | BG5T50, BGDA, L | 2025 | 1540000 |  |  | 2026 | 2218000 | 2020 | 326000 | 4084000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.975M IN BGANY USED AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS.
IREDELL | STATESVILLE | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | 0.76 | Highway | Locally Selected | 12 | Charlotte Regional TPO | U-6153 | Division 12 | BA, O, T |  |  |  |  | 2026 | 4648000 |  |  | 4648000 | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT.
IREDELL | MOORESVILLE | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | 0.84 | Highway | Locally Selected | 12 | Charlotte Regional TPO | U-6239 | Division 12 | BGDA, DP, L | 2022 | 6149000 |  |  | 2023 | 28492000 | 2021 | 525000 | 35166000 | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE
IREDELL | NC 115 | MOORESVILLE | SR 1102 (LANGTREE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 12 | Charlotte Regional TPO | U-6249 | Exempt | BGDA, L, L(M), T(DA) | 2024 | 500000 |  |  | 2026 | 4006000 | 2021 | 560000 | 5066000 | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. $3.605M IN STBG-DA FUNDS SWAPPED FOR $3.605M IN STATE FUNDS ON 5-17-23
IREDELL | I-40/I-77 | NCDOT | INITIAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 1 | Highway | Pre-STI (Historic) | 12 | Charlotte Regional TPO | I-3819A | Pre-STI (Transition) | NHP |  |  |  |  | 2012 | 4388000 |  |  | 4388000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
IREDELL | I-77 | NCDOT | MILE MARKER 57.83 TO MILE POST 61.74. PAVEMENT REHABILITATION. | 3.9 | Highway | Pre-STI (Historic) | 12 | Charlotte Regional TPO | I-5106 | Pre-STI (Transition) | NHP |  |  |  |  | 2009 | 439000 |  |  | 439000 | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | NCDOT | SR 1177 (CHUCKWOOD ROAD) TO SR 1109 (CENTRE CHURCH ROAD). WIDEN TO MULTI-LANES. | 3.9 | Highway | Pre-STI (Historic) | 12 | Charlotte Regional TPO | R-3833A | [11 empty] | COMPLETE
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | NCDOT | SR 1109 (CENTRE CHURCH ROAD) TO I-77. WIDEN TO MULTI-LANES. | 1.1 | Highway | Pre-STI (Historic) | 12 | Charlotte Regional TPO | R-3833B | [11 empty] | COMPLETE
IREDELL | SR 1125 (SHEARERS ROAD) | NCDOT | SR 1147 (ROCKY RIVER ROAD) INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 12 | Charlotte Regional TPO | HS-2012C | Division 12 | HSIP |  |  |  |  | 2023 | 205000 | 2022 | 20000 | 225000 | UNDER CONSTRUCTION.
IREDELL | NC 150 | NCDOT | MILE MARKER 11.4 TO MILE MARKER 11.9. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | Highway | Safety | 12 | Charlotte Regional TPO | HS-2012K | Region F | HSIP |  |  |  |  | 2024 | 25000 |  |  | 25000
IREDELL | SR 1303 (PERTH ROAD) | NCDOT | INSTALL SIGNAL AT SR 1303 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | 0.5 | Highway | Safety | 12 | Charlotte Regional TPO | W-5212JA | Division 12 | BGANY, BGDA, HF(M) | 2020 | 25000 |  |  | 2022 | 125000 |  |  | 150000 | $62K IN BGANY USED AS PART OF FUND SWAP. UNDER CONSTRUCTION.
IREDELL | SR 1303 (PERTH ROAD) | NCDOT | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | 0.5 | Highway | Safety | 12 | Charlotte Regional TPO | W-5212JB | Division 12 | BGANY, HF(M) | 2022 | 125000 |  |  | 2023 | 1091000 |  |  | 1216000 | UNDER CONSTRUCTION. $460K IN BGANY USED AS PART OF FUND SWAP.
IREDELL | NC 150 | NCDOT | NC 150 AT NC 152 (WESTERN INTERSECTION) | 0.5 | Highway | Safety | 12 | Charlotte Regional TPO | W-5601U | Region F | HF, HSIP | 2022 | 472000 |  |  | 2025 | 1965000 |  |  | 2437000 | RIGHT-OF-WAY IN PROGRESS.
IREDELL | I-40/I-77 | NCDOT | STATESVILLE, MODIFICATION OF I-40/I-77 INTERCHANGE AREA. | 1 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | I-3819 | [11 empty] | GARVEE BOND FUNDING - SEGMENT A: $10M FOR CONSTRUCTION, PAYBACK FY 2012-2023
IREDELL | I-40/I-77 | NCDOT | FINAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 1 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | I-3819B | Statewide Mobility | T | 2025 | 840000 |  |  | 2019 | 360365000 |  |  | 361205000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
IREDELL | I-77 | NCDOT | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | I-5962 | Statewide Mobility | NHP, O | 2028 | 3000000 | 2028 | 500000 | 2031 | 61199000 |  |  | 64699000 | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE
IREDELL | NC 150 | NCDOT | GOOD LUCK LANE TO MORRISON PLANTATION PARKWAY. EXTEND EASTBOUND RIGHT AND THROUGH LANE. | 0.28 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-2307BA | Region F | T |  |  |  |  | 2023 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION.
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | NCDOT | SR 1177 (CHUCKWOOD ROAD) TO US 21. WIDEN TO MULTI-LANES WITH INTERCHANGE AT I-77. | 5.9 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-3833 | [11 empty] | $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE.
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | NCDOT | I-77 TO US 21. WIDEN TO MULTI-LANES. | 1 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-3833C | Division 12 | L, T | 2019 | 5610000 | 2019 | 1950000 | 2024 | 46762000 |  |  | 54322000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE);
IREDELL | SR 1109 (WILLIAMSON ROAD) | NCDOT | I-77 TO NC 150. WIDEN TO FOUR LANES. | 3.2 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-5100 | [11 empty] | COORDINATE WITH U-5817.
IREDELL | SR 1109 (WILLIAMSON ROAD) | NCDOT | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 2.35 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-5100A | Division 12 | T | 2020 | 11700000 | 2022 | 5300000 | 2027 | 68409000 | 2020 | 600000 | 86009000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $22M CON PAYBACK FY 28-44 (FY 28/YR 8 SALE).
IREDELL | SR 1109 (WILLIAMSON ROAD) | NCDOT | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 0.87 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-5100B | Division 12 | BGANY, T | 2019 | 9515000 | 2022 | 1300000 | 2026 | 9600000 |  |  | 20415000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE).
IREDELL | US 21 | NCDOT | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | 0.5 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | R-5711 | Region F | T | 2024 | 100000 |  |  | 2025 | 2950000 |  |  | 3050000 | RIGHT-OF-WAY IN PROGRESS
IREDELL | NC 150 | NCDOT | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5780 | Region F | T | 2019 | 605000 | 2025 | 750000 | 2025 | 3500000 |  |  | 4855000 | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U.
IREDELL | US 21 | NCDOT | US 21, SR 1933 (PUMP STATION ROAD) TO FORT DOBBS ROAD. WIDEN TO FOUR LANES. REALIGN OFFSET INTERSECTIONS OF SR 1922 (SHUMAKER DRIVE) AND SR 2171 (JANE SOWERS ROAD). | 0.81 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5799 | Region F | T | 2020 | 22360000 | 2023 | 4000000 | 2030 | 29400000 | 2020 | 2265000 | 58025000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE)
IREDELL | SR 1305 (OATES ROAD - MIDNIGHT LANE) | NCDOT | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | 1.56 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5816 | Division 12 | T | 2026 | 22800000 | 2026 | 3200000 | 2029 | 56405000 |  |  | 82405000 | NC BUILD BONDS: $16M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
IREDELL | SR 1246 (FAIRVIEW ROAD) | NCDOT | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | 0.11 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5817 | Division 12 | BA, BGANY, BGDA | 2019 | 5800000 | 2019 | 1900000 | 2027 | 25200000 |  |  | 32900000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100.
IREDELL | US 64 (DAVIE AVENUE) | NCDOT | US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | 0.5 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-5964 | Region F | T | 2024 | 3800000 | 2024 | 700000 | 2026 | 3299000 |  |  | 7799000
IREDELL | US 21 (CHARLOTTE HIGHWAY) | NCDOT | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | 2.64 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-6037 | Division 12 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 77000000 |  |  | 95000000
IREDELL | SR 2321 (EAST BROAD STREET) | NCDOT | VINE STREET TO SR 2422 (SIGNAL HILL DRIVE). UPGRADE ROADWAY AND IMPLEMENT ACCESS MANAGEMENT SOLUTIONS. | 0.68 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO | U-6039 | Division 12 | T |  |  |  |  | 2019 | 5350000 |  |  | 5350000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B
IREDELL | SR 1303 (PERTH ROAD) | NCDOT | SR 1303 (PERTH ROAD) AT SR 1378 (JUDAS ROAD) AND SR1302 (CORNELIUS ROAD) INTERSECTIONS. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Transition | 12 | Charlotte Regional TPO | W-5212J | Division 12 | BGANY, HF(M) | [6 empty] | 2020 | 356000 | 356000 | $178K IN BGANY USED AS PART OF FUND SWAP.
IREDELL | IREDELL COUNTY | IREDELL COUNTY | OPERATING ASSISTANCE FOR THE IREDELL COUNTY AREA TRANSPORTATION SYSTEM (ICATS) |  | Public Transportation (Transit) | Miscellaneous/Other | 12 | Charlotte Regional TPO | TO-5149 | Public Transit | 5307, L | [6 empty] | 2020 | 687000 | 687000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | IREDELL COUNTY | IREDELL COUNTY | OPERATION FOR FY20-21 |  | Public Transportation (Transit) | Miscellaneous/Other | 12 | Charlotte Regional TPO | TO-6158 | Public Transit | 5307, L | [6 empty] | 2020 | 2372000 | 2372000 | ADDING FUNDS FOR FFY2020
IREDELL | IREDELL COUNTY | IREDELL COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 12 |  | TK-6179 | Public Transit | 5311 | [6 empty] | 2020 | 1040000 | 1040000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | SR 2395 (MAZEPPA ROAD) | NCDOT | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | Rail | Locally Selected | 12 | Charlotte Regional TPO | RL-0001 | Region F | BGDA, DP, L | 2025 | 320000 |  |  | 2025 | 12633000 |  |  | 12953000 | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT.
IREDELL | WALL STREET | NCDOT | NSR CROSSING 729686G IN STATESVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Charlotte Regional TPO | RX-2012B | Division 12 | RR |  |  |  |  | 2025 | 474000 |  |  | 474000
IREDELL | OPAL STREET | NCDOT | NSR CROSSING 729684T IN STATESVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 12 | Charlotte Regional TPO | RX-2012D | Division 12 | RR |  |  |  |  | 2025 | 474000 |  |  | 474000
IREDELL | SR 1639 (MEACHAM ROAD) | NCDOT | ARC CROSSING 865740U IN STATESVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 12 | Charlotte Regional TPO | RX-2412A | Division 12 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
IREDELL, CATAWBA | I-40 | NCDOT | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT AND BRIDGE REHABILITATION. | 19.5 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO, Greater Hickory MPO | I-5915
IREDELL, CATAWBA | I-40 | NCDOT | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT REHABILITATION. | 32.62 | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO, Greater Hickory MPO | I-5915A | Statewide Mobility | [10 empty] | COMPLETE
IREDELL, CATAWBA | I-40 | NCDOT | BRIDGE REHABILITATION. |  | Highway | Interstate Maintenance | 12 | Charlotte Regional TPO, Greater Hickory MPO | I-5915B | Statewide Mobility | BGDA, NHPIM, T(M) |  |  |  |  | 2023 | 11840000 |  |  | 11840000 | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION.
IREDELL, CATAWBA | VARIOUS | NCDOT | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. |  | Highway | Safety | 12 | Charlotte Regional TPO, Greater Hickory MPO | W-5212DIV | Division 12 | HSIP | 2020 | 50000 |  |  | 2020 | 2500000 |  |  | 2550000 | IN PROGRESS.
IREDELL, CATAWBA | NC 150 | NCDOT | SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | 6.9 | Highway | STI (Prioritization) | 12 | Charlotte Regional TPO, Greater Hickory MPO | R-2307B | Region F | T |  |  |  |  | 2025 | 327336000 |  |  | 327336000 | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION FUNDED WITH TOLL CREDITS. BUILD NC BONDS: $50M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); $22.5M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE)
IREDELL, MECKLENBURG | ICATS INTERCOUNTY EXPRESS BUS | ICATS INTERCOUNTY EXPRESS BUS | PURCHASE 3 OVER-THE-ROAD COACH BUSES AND 5 SETS OF BUS STOP SHELTERS TO EXPAND INTERCOUNTY SERVICE BETWEEN STATESVILLE, TROUTMAN, MOORESVILLE, AND CATS ROUTES BETWEEN HUNTERSVILLE AND CHARLOTTE. |  | Public Transportation (Transit) | STI (Prioritization) | 10, 12 | Charlotte Regional TPO | TA-6713 | Region E, F | T |  |  |  |  | 2021 | 1000000 |  |  | 1000000
JACKSON | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | NCDOT | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. |  | Bike & Ped | Federal Lands Access Program | 14 | Southwestern RPO | BF-0001 | Exempt | FLAP, HF(M) |  |  |  |  | 2022 | 190000 | 2022 | 10000 | 200000 | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION.
JACKSON | MONTEITH GREENWAY | NCDOT | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD AND GREENWAY. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | BN-0003 | Exempt | CRP550, L, O |  |  |  |  | 2025 | 125000 | 2024 | 300000 | 425000 | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY.
JACKSON | MONTEITH GREENWAY | NCDOT | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | BN-0003A | Exempt | CRP550, L, O |  |  |  |  | 2025 | 575000 |  |  | 575000
JACKSON | NC 107 | JACKSON COUNTY | SR 1330 (FOREST HILLS ROAD/NORTH COUNTRY CLUB ROAD) TO THE JACKSON COUNTY RECREATION COMPLEX NEAR THE INTERSECTION OF SR 1545 (WISDOM DRIVE) AND CULLOWHEE MOUNTAIN ROAD. CONSTRUCT MULTI-USE PATH ON WEST SIDE. | 0.3 | Bike & Ped | NCDOT Selected (Other Selection Process) | 14 | Southwestern RPO | BN-0015 | Exempt | CRP550, L(M) |  |  |  |  | 2026 | 1647000 | 2025 | 440000 | 2087000
JACKSON | SR 1432 (SKYLAND DRIVE) | NCDOT | SR 1429 (CHIPPER CURVE ROAD) TO US 23 BUSINESS. CONSTRUCT SIDEWALK. | 0.72 | Bike & Ped | STI (Prioritization) | 14 | Southwestern RPO | EB-5923 | Division 14 | L, TALT5 |  |  |  |  | 2023 | 960000 |  |  | 960000 | UNDER CONSTRUCTION.
JACKSON | SR 1120 (CEDAR CREEK ROAD) | NCDOT | REPLACE BRIDGE 490008 CEDAR CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-5921 | Division 14 | BGOFF | 2024 | 410000 |  |  | 2025 | 400000 |  |  | 810000
JACKSON | SR 1300 (PUMPKINTOWN ROAD) | NCDOT | REPLACE BRIDGE 490069 OVER SAVANNAH CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6031 | Division 14 | BGOFF | 2024 | 80000 |  |  | 2025 | 800000 |  |  | 880000
JACKSON | SR 1397 (THOMAS VALLEY ROAD) | NCDOT | REPLACE BRIDGE 490144 OVER NATIONS CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6032 | Division 14 | BGOFF | 2021 | 50000 |  |  | 2022 | 983000 |  |  | 1033000 | UNDER CONSTRUCTION. 80 2019 BGOFF R 0
JACKSON | SR 1445 (LEE BUMGARNER ROAD) | NCDOT | REPLACE BRIDGE 490129 OVER SCOTT CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6033 | Division 14 | BGOFF |  |  |  |  | 2029 | 2700000 |  |  | 2700000 | RIGHT-OF-WAY IN PROGRESS
JACKSON | SR 1300 (PUMPKINTOWN ROAD) | NCDOT | REPLACE BRIDGE 490065 OVER SAVANNAH CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6034 | Division 14 | BGOFF | 2024 | 70000 |  |  | 2027 | 1500000 |  |  | 1570000
JACKSON | SR 1738 (HOOPER CEMETERY ROAD) | NCDOT | REPLACE BRIDGE 490203 OVER CANEY FORK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6035 | Division 14 | BGOFF | 2021 | 70000 |  |  | 2022 | 1495000 |  |  | 1565000 | UNDER CONSTRUCTION.
JACKSON | SR 1737 (CANEY FORK ROAD) | NCDOT | REPLACE BRIDGE 490081 OVER JOHNS CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6036 | Division 14 | BGOFF | 2026 | 410000 |  |  | 2027 | 1500000 |  |  | 1910000
JACKSON | SR 1356 (SAVANNAH DRIVE) | NCDOT | US 23 BUSINESS TO NICOL ARMS ROAD. CONSTRUCT SIDEWALK. | 0.12 | Highway | Safety | 14 | Southwestern RPO | HS-2014AD | Division 14 | HSIP |  |  |  |  | 2025 | 110000 |  |  | 110000
JACKSON | SR 1157 (CULLOWHEE MOUNTAIN ROAD) | NCDOT | INSTALL GUARDRAIL FROM MILEPOST 2.6 TO 6.6, NEAR CULLOWHEE. | 4.02 | Highway | Safety | 14 | Southwestern RPO | HS-2014B | Division 14 | HSIP |  |  |  |  | 2022 | 110000 |  |  | 110000 | UNDER CONSTRUCTION.
JACKSON | SR 1325 (CENTENNIAL DRIVE) | NCDOT | INSTALL RECTANGULAR RAPID FLASHING BEACONS (RRFB) AT THREE MIDBLOCK CROSSINGS NEAR SR 1169 (CENTRAL DRIVE). | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014D | Division 14 | HSIP |  |  |  |  | 2022 | 59000 |  |  | 59000 | UNDER CONSTRUCTION.
JACKSON | VARIOUS | NCDOT | US 23 BUSINESS (HAYWOOD ROAD) AT CHURCH STREET AND SR 1557 (FRONT STREET) AT SR 1558 (DEPOT STREET). INSTALL RECTANGULAR RAPID FLASHING BEACON (RRFB) AND UPGRADE CURB RAMPS. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014H | Region G | HSIP |  |  |  |  | 2023 | 96000 |  |  | 96000
JACKSON | US 64 | NCDOT | SR 1119 (SAPPHIRE POSTOFFICE ROAD) AT CHRYSLER CURVE NEAR SAPPHIRE. CONSTRUCT SAFETY IMPROVEMENTS. | 0.68 | Highway | Safety | 14 | Southwestern RPO | W-5714E | Region G | HSIP |  |  |  |  | 2024 | 975000 |  |  | 975000
JACKSON | NC 107 | NCDOT | SR 1002 TO NC 281. UPGRADE EXISTING ROADWAY. | 4.01 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-4753 | Division 14 | [10 empty] | UNDER CONSTRUCTION
JACKSON | NC 107 (US 23 BUSINESS) | NCDOT | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.85 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5600 | Region G | BG5T50, T | 2022 | 70440000 | 2022 | 7200000 | 2025 | 101900000 |  |  | 179540000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE).
JACKSON | US 64 | NCDOT | NC 107 INTERSECTION. IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5881 | Region G | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 |  |  | 21300000
JACKSON | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | NCDOT | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | 2.81 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5907 | Division 14 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35000000 |  |  | 38700000
JACKSON | JACKSON COUNTY | JACKSON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6137 | Public Transit | 5311, L, S | [6 empty] | 2020 | 752000 | 752000 | FUNDS AUTHORIZED IN PROGRESS
JACKSON, SWAIN | VARIOUS | NCDOT | INDIAN RESERVATION ROAD (IRR) PROGRAM. ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED BY EASTERN BAND OF CHEROKEE INDIANS. |  | Highway | Other | 14 | Southwestern RPO | R-5500 | Exempt | [10 empty] | PROGRAM IN PROGRESS
JOHNSTON | JOHNSTON COUNTY AIRPORT (JNX) | JOHNSTON COUNTY AIRPORT (JNX) | LAND ACQUISITION & CLEARING PROJECT. |  | Aviation | STI (Prioritization) | 4 | Upper Coastal Plain RPO | AV-5745 | Division 4 | T |  |  |  |  | 2023 | 2664000 | 2024 | 195000 | 2859000
JOHNSTON | SR 1004 (EAST MAIN STREET) | CLAYTON | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 0.35 | Bike & Ped | Locally Selected | 4 | Capital Area MPO | BL-0050 | Exempt | CMAQ, L | 2024 | 200000 |  |  | 2025 | 440000 | 2024 | 10000 | 650000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | MAIN STREET | CLAYTON | MOORE STREET TO SMITH STREET IN CLAYTON. CONSTRUCT SIDEWALK ON BOTH SIDES OF MAIN STREET FROM ROBERTSON STREET TO MOORE STREET. ADD CROSSWALKS, CURB EXTENSIONS, AND PEDESTRIAN SIGNALS FROM MOORE STREET TO SMITH STREET. | 1 | Bike & Ped | Locally Selected | 4 | Capital Area MPO | BL-0125 | Division 4 | L, L(M), TADA | 2025 | 50000 |  |  | 2025 | 1500000 |  |  | 1550000
JOHNSTON | NEUSE RIVER | JOHNSTON COUNTY | FROM PROPOSED RESIDENTIAL DEVELOPMENT TO FUTURE SCHOOL COMPLEX NEAR SR 2589 (CLEARWATER DRIVE) IN WILSON'S MILLS. CONSTRUCT MULTI-USE PATH ALONG NEUSE RIVER. |  | Bike & Ped | Locally Selected | 4 | Upper Coastal Plain RPO | BN-0024 | Exempt | CRPANY, L(M) |  |  |  |  | 2026 | 4011000 | 2025 | 200000 | 4211000
JOHNSTON | SR 2130 (WEST MAIN STREET) | MICRO | SOUTH OF FAYETTEVILLE STREET TO DWIGHT DRIVE IN MICRO. CONSTRUCT SIDEWALK. | 0.3 | Bike & Ped | Locally Selected | 4 | Upper Coastal Plain RPO | BN-0025 | Exempt | CRP550, L(M) | 2025 | 175000 |  |  | 2026 | 870000 | 2025 | 175000 | 1220000
JOHNSTON | (WEST MARKET STREET) US 70 BUSINESS | SMITHFIELD | FROM SR 1913 (WILSON'S MILLS ROAD) TO NEUSE RIVER BRIDGE IN SMITHFIELD. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 1 | Bike & Ped | NCDOT Selected (Other Selection Process) | 4 | Upper Coastal Plain RPO | BN-0001 | Exempt | CMAQ, CRP550, L | 2024 | 100000 |  |  | 2026 | 2344000 | 2024 | 225000 | 2669000 | WEST MARKET STREET MULTI-USE PATH
JOHNSTON | EAST CLAYTON CONNECTOR GREENWAY | CLAYTON | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | Bike & Ped | STI (Prioritization) | 4 | Capital Area MPO | EB-6016 | Division 4 | L, TAANY | 2029 | 780000 | 2029 | 2900000 | 2031 | 5300000 | 2027 | 258000 | 9238000
JOHNSTON | MOUNTAINS TO SEA TRAIL | CLAYTON | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | Bike & Ped | STI (Prioritization) | 4 | Capital Area MPO | EB-6017 | Division 4 | L, TAANY | 2030 | 10000 | 2030 | 10000 | 2032 | 2300000 | 2028 | 83000 | 2403000
JOHNSTON | SR 2143 (BEULAHTOWN ROAD) | NCDOT | REPLACE BRIDGE 500216 OVER LITTLE BUFFALO CREEK. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-4562 | Division 4 | [10 empty] | UNDER CONSTRUCTION. DESIGN BUILD PROJECT.
JOHNSTON | I-95 | NCDOT | REPLACE BRIDGE 500118 AND 500119 OVER CSX RAILROAD. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-4937 | Statewide Mobility | T | 2027 | 9399000 | 2027 | 300000 | 2031 | 34400000 |  |  | 44099000
JOHNSTON | SR 1555 (BARBOUR MILL ROAD) | NCDOT | REPLACE BRIDGE 500145 OVER SWIFT CREEK. | 0.25 | Highway | Bridges | 4 | Capital Area MPO | B-5664 | Division 4 | [10 empty] | UNDER CONSTRUCTION.
JOHNSTON | I-95 | NCDOT | REPLACE BRIDGE 500082 AND 500085 OVER BLACK CREEK AND BRIDGE 500100 AND 500101 OVER NEUSE RIVER. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-6044 | Statewide Mobility | BFP, HFB | 2023 | 110000 |  |  | 2029 | 53899000 |  |  | 54009000
JOHNSTON | SR 2137 (PITTMAN ROAD) SR 2130 (EAST MAIN STREET) | NCDOT | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-6050 | Division 4 | BFP | 2025 | 1500000 | 2025 | 3800000 | 2029 | 45200000 |  |  | 50500000
JOHNSTON | I-95 | NCDOT | I-95 FROM MILE MARKER 97 TO MILE MARKER 101. PAVEMENT REHABILITATION. | 4.01 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | HI-0008 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 7229000 |  |  | 7229000 | UNDER CONSTRUCTION.
JOHNSTON | I-95 | NCDOT | US 70 (EXIT 97) TO US 301 (EXIT 107). PAVEMENT AND BRIDGE REHABILITATION. | 10.7 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-3318
JOHNSTON | I-95 | NCDOT | US 70 (EXIT 97) TO NORTH OF SR 1001 (MILE MARKER 100). | 2.859 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-3318A | [11 empty] | COMPLETED.
JOHNSTON | I-95 | NCDOT | SOUTH OF SR 1001 (LIZZIE MILL ROAD) TO THE JOHNSTON/WILSON COUNTY LINE NORTH OF NC 222. PAVEMENT REHABILITATION. | 11.75 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-5786 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION.
JOHNSTON | I-95 | NCDOT | REPLACE BRIDGE 500117 ON SR 2399 (TRUCK STOP ROAD) OVER I-95 AND ADJUST SERVICE ROADS AND APPROACHES. |  | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-5786A | Statewide Mobility
JOHNSTON | US 70 (FUTURE I-42) | NCDOT | SR 1003 (BUFFALO ROAD) TO WAYNE COUNTY LINE. PAVEMENT REHABILITATION. | 13.32 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-6044 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 6090000 |  |  | 6090000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132 FOR CONSTRUCTION, PAYBACK FY 2019-2033.
JOHNSTON | US 70 BUSINESS | NCDOT | INTERSECTION OF US 70 BUSINESS AND SR 1553 (SHOTWELL ROAD). IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 4 | Capital Area MPO | HL-0127 | Exempt | CRPDA, HF(M) |  |  |  |  | 2024 | 5751000 |  |  | 5751000 | HF(M) REPRESENTS HIGH-IMPACT LOW-COST FUNDS
JOHNSTON | SOUTH ROBERTSON STREET MAIN STREET |  | SOUTH ROBERTSON STREET AND AMELIA CHURCH ROAD FROM MAIN STREET TO KENMORE DRIVE. MAIN STREET FROM SOUTH ROBERTSON STREET TO SOUTH MOORE STREET IN CLAYTON. INSTALL CURB AND GUTTER, CONSTRUCT SIDEWALKS, AND IMPROVE INTERSECTION. |  | Highway | Locally Selected | 4 | Capital Area MPO | HL-0129 | Division 4 | L, TADA | 2025 | 550000 |  |  |  |  | 2024 | 700000 | 1250000
JOHNSTON | SR 1560 (RANCH ROAD EXTENSION) | NCDOT | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | 0.4 | Highway | Locally Selected | 4 | Capital Area MPO | U-6223 | Division 4 | BGDA, HF, HF(M), L(M) | 2021 | 2169000 |  |  | 2022 | 11250000 |  |  | 13419000 | UNDER CONSTRUCTION. "S" FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS. HF FUNDING REFLECTS HIGH IMPACT-LOW COST HIGHWAY FUNDS.
JOHNSTON | NC 42 | NCDOT | US 70 AT CLAYTON TO EAST OF SR 1902 (GLEN LAUREL ROAD). | 1.5 | Highway | Pre-STI (Historic) | 4 | Capital Area MPO | R-3825A | [11 empty] | COMPLETED.
JOHNSTON | NC 39 | NCDOT | FROM US 301 NORTH OF SELMA TO THE WAKE COUNT LINE. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 18.5 | Highway | Safety | 4 | Capital Area MPO, Upper Coastal Plain RPO | HS-2004AD | Region A | HSIP |  |  |  |  | 2024 | 490000 |  |  | 490000
JOHNSTON | NC 242 | NCDOT | CURVE IMPROVEMENTS BETWEEN 0.08 MILES AND 0.31 MILES NORTH OF SR 1116 (GODWIN LAKE ROAD). | 0.23 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004L | Region A | HSIP | 2023 | 272000 |  |  | 2023 | 685000 |  |  | 957000 | UNDER CONSTRUCTION.
JOHNSTON | US 301 (BRIGHTLEAF BOULEVARD) | NCDOT | US 301 (BRIGHTLEAF BOULEVARD) AT NORTH STREET IN SMITHFIELD. INSTALL / UPGRADE HIGH VISIBILITY CROSSWALKS, AUDIBLE COUNTDOWN PEDESTRIAN SIGNAL HEADS, PEDESTRIAN IMPROVEMENTS, TRAFFIC SIGNAL, AND TRAFFIC SIGNAL SYSTEM. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004P | Region A | HSIP |  |  |  |  | 2023 | 350000 |  |  | 350000 | UNDER CONSTRUCTION.
JOHNSTON | SR 1902 (GLEN LAUREL ROAD) | NCDOT | SR 1902 (GLEN LAUREL ROAD) AT SR 1903 (VINSON ROAD). TRAFFIC SIGNAL INSTALLATION. | 0.5 | Highway | Safety | 4 | Capital Area MPO | HS-2004S | Division 4 | HSIP |  |  |  |  | 2023 | 350000 |  |  | 350000 | UNDER CONSTRUCTION.
JOHNSTON | US 70 | NCDOT | US 70 AT US 70A/SR 2532 (WEST EDWARDS STREET) AND US 70 AT SR 2314 (PONDFIELD ROAD). INSTALL REDUCED CONFLICT INTERSECTION WITH WESTBOUND U-TURN AT SR 2314 (PONDFIELD ROAD). | 0.38 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004W | Statewide Mobility | HSIP |  |  |  |  | 2024 | 754000 |  |  | 754000
JOHNSTON | NC 210 | NCDOT | HARNETT COUNTY LINE TO NC 50 AND SR 1382 (NORTH PLEASANT-COATES ROAD) TO SR 1010 (CLEVELAND ROAD). INSTALL RUMBLE STRIPS AND SNOWPLOWABLE PAVEMENT MARKERS. | 17 | Highway | Safety | 4 | Capital Area MPO, Upper Coastal Plain RPO | HS-2404B | Region A | HSIP |  |  |  |  | 2025 | 567000 |  |  | 567000
JOHNSTON | SR 1524 (OLD DRUG STORE ROAD) | NCDOT | IMPROVE SUPERELEVATION IN CURVE ON SR 1524 (OLD DRUG STORE ROAD) SOUTH OF SR 1525 (CORNWALLIS ROAD). INSTALL SIGNAL AT INTERSECTION OF SR 1524 (OLD DRUG STORE ROAD) AND SR 1525 (CORNWALLIS ROAD). | 0.5 | Highway | Safety | 4 | Capital Area MPO | W-5204E | Division 4 | HSIP | 2023 | 200000 |  |  | 2024 | 972000 |  |  | 1172000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | SR 1700 (COVERED BRIDGE ROAD) | NCDOT | SAFETY IMPROVEMENTS FROM 0.1 MILES EAST OF SR 1003 (BUFFALO ROAD) TO 0.1 MILES WEST OF SR 2685 (HELENA LANE). | 1.41 | Highway | Safety | 4 | Capital Area MPO | W-5704E | Division 4 | HSIP, T | 2023 | 1800000 |  |  | 2026 | 12600000 |  |  | 14400000
JOHNSTON | I-40 | NCDOT | ACCESS IMPROVEMENTS IN THE VICINITY OF EXISTING I-40/NC 42 INTERCHANGE (EXIT 312). | 1 | Highway | STI (Prioritization) | 4 | Capital Area MPO | I-4739 | Statewide Mobility | NHP | 2019 | 19305000 |  |  | 2018 | 40137000 |  |  | 59442000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033.
JOHNSTON | I-40 | NCDOT | WAKE COUNTY LINE TO NC 42. | 1.55 | Highway | STI (Prioritization) | 4 | Capital Area MPO | I-5111REG | Region A | NHP | 2019 | 3479000 |  |  | 2018 | 23795000 |  |  | 27274000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
JOHNSTON | I-95 | NCDOT | US 70 BUSINESS. UPGRADE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | I-5972 | Region A | NHP |  |  |  |  | 2024 | 43182000 |  |  | 43182000 | RIGHT-OF-WAY IN PROGRESS
JOHNSTON | I-95 | NCDOT | US 701/NC 96. CONSTRUCT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | I-5974 | Region A | NHP | 2026 | 7276000 | 2026 | 1400000 | 2029 | 73500000 |  |  | 82176000
JOHNSTON | I-95 | NCDOT | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | I-6061 | Division 4 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1999000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26300000 |  |  | 30299000
JOHNSTON | NC 42 | NCDOT | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 8.64 | Highway | STI (Prioritization) | 4 | Capital Area MPO | R-3410 | Region A | BGANY, T | 2027 | 66400000 | 2027 | 10500000 | 2031 | 156900000 |  |  | 233800000 | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
JOHNSTON | NC 42 | NCDOT | US 70 TO SR 1003 (BUFFALO ROAD). WIDEN TO MULTI-LANES. | 6.1 | Highway | STI (Prioritization) | 4 | Capital Area MPO | R-3825
JOHNSTON | NC 42 | NCDOT | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | 4.35 | Highway | STI (Prioritization) | 4 | Capital Area MPO | R-3825B | Division 4 | T |  |  |  |  | 2019 | 68448000 |  |  | 68448000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
JOHNSTON | SR 1003 (BUFFALO ROAD) | NCDOT | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 1.27 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5718 | Division 4 | T | 2022 | 8537000 | 2022 | 1190000 | 2026 | 20621000 |  |  | 30348000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE).
JOHNSTON | NC 242 | NCDOT | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | 0.65 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5761 | Division 4 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 740000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20800000 |  |  | 23740000
JOHNSTON | US 70 | NCDOT | US 301 TO I-95. ACCESS MANAGEMENT. | 0.69 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5795 | Region A | T | 2030 | 2800000 | 2030 | 7200000 | 2033 | 13400000 |  |  | 23400000
JOHNSTON | SR 1501 (SWIFT CREEK ROAD) | NCDOT | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | 0.29 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | R-5950 | Division 4 | T | 2029 | 2000000 | 2029 | 1700000 | 2031 | 5600000 |  |  | 9300000
JOHNSTON | US 301/NC 39/NC 96 | NCDOT | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.58 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-5726 | Division 4 | BG5T50 | 2026 | 13901000 | 2026 | 4300000 | 2029 | 29100000 |  |  | 47301000
JOHNSTON | CLAYTON | NCDOT | CLAYTON SIGNAL SYSTEM. | 6.2 | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-5943 | Region A | BG50200 |  |  | 2025 | 260000 | 2025 | 4500000 |  |  | 4760000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | NC 42 | NCDOT | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | 11.43 | Highway | STI (Prioritization) | 4 | Capital Area MPO, Upper Coastal Plain RPO | U-5998 | Division 4 | BGANY, T | 2025 | 3300000 | 2025 | 2100000 | 2027 | 32155000 |  |  | 37555000 | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE).
JOHNSTON | NC 210 | NCDOT | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.06 | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-6203 | Division 4 | T | 2027 | 12801000 | 2027 | 4000000 | 2030 | 71600000 |  |  | 88401000
JOHNSTON | NEW ROUTE | NCDOT | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.46 | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-6208 | Division 4 | T | 2029 | 19500000 | 2029 | 3900000 | 2032 | 33100000 |  |  | 56500000
JOHNSTON | SR 1010 (CLEVELAND ROAD) | NCDOT | NORTH OF SR 2231 (SOUTHFORT DRIVE) TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | 4.2 | Highway | STI (Prioritization) | 4 | Capital Area MPO | U-6216 | Division 4 | BGANY | 2030 | 36600000 | 2030 | 6300000 | 2034 | 100900000 |  |  | 143800000
JOHNSTON | US 70 | NCDOT | US 70 BUSINESS TO NEUSE RIVER BRIDGE. CONVERT TO FREEWAY WITH INTERCHANGES AT SR 1501 (SWIFT CREEK ROAD) AND SR 1919 (WILSON'S MILLS ROAD). | 5.63 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | W-5600 | Region A | NHP |  |  |  |  | 2021 | 87693000 |  |  | 87693000 | UNDER CONSTRUCTION.
JOHNSTON | I-95 | NCDOT | REPLACE BRIDGE NO. 114 AND BRIDGE NO. 116 AND APPROACHES OVER LITTLE RIVER. |  | Highway | Transition | 4 | Upper Coastal Plain RPO | I-3318BB | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION.
JOHNSTON | JOHNSTON COUNTY | JOHNSTON COUNTY (JCATS) | PURCHASE ELECTRIC TRANSIT VEHICLES. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 4 | Upper Coastal Plain RPO | TN-6132 | Division 4 | CRPANY, L(M) |  |  |  |  | 2025 | 500000 | 2025 | 10000 | 510000
JOHNSTON | JOHNSTON COUNTY COUNCIL ON AGING, INC. | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Upper Coastal Plain RPO | TK-6138 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1176000 | 1176000 | FUNDS AUTHORIZED IN PROGRESS
JOHNSTON | JOHNSTON COUNTY | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. |  | Public Transportation (Transit) | STI (Prioritization) | 4 | Upper Coastal Plain RPO, Capital Area MPO | TA-6720 | Division 4 | 5311, L, T |  |  |  |  | 2026 | 330000 |  |  | 330000
JOHNSTON | SR 2383 (PRESTON STREET) | NCDOT | CLOSURE OF SR 2383 (PRESTON STREET) AT CSX (CROSSING 629 950L) IN SELMA. |  | Rail | Rail-Highway Grade Crossing Closure | 4 | Upper Coastal Plain RPO | RC-2004B | Division 4 | RR | 2025 | 50000 | 2025 | 20000 | 2026 | 500000 |  |  | 570000
JOHNSTON | SR 1357 (GILBERT ROAD) | NCDOT | CSX CROSSING 629731X NEAR BENSON. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004C | Division 4 | RR |  |  |  |  | 2024 | 600000 |  |  | 600000
JOHNSTON | PARRISH DRIVE | NCDOT | CSX CROSSING 629739C IN BENSON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004D | Division 4 | RR |  |  |  |  | 2025 | 500000 |  |  | 500000
JOHNSTON | SR 2130 (MAIN STREET) | NCDOT | CSX CROSSING 629943B IN MICRO. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004G | Division 4 | RR |  |  |  |  | 2025 | 417000 |  |  | 417000
JOHNSTON | SR 1709 (STALLINGS STREET) | NCDOT | NORFOLK SOUTHERN CROSSING 735396M IN CLAYTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Capital Area MPO | RX-2004H | Division 4 | RR |  |  |  |  | 2025 | 475000 |  |  | 475000
JOHNSTON | SR 2339 (BAGLEY ROAD) | NCDOT | CSX CROSSING 629939L IN KENLY. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004J | Division 4 | RR |  |  |  |  | 2026 | 434000 |  |  | 434000
JOHNSTON | LEE STREET | NCDOT | CSX CROSSING 629964U IN SMITHFIELD. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004K | Division 4 | RR |  |  |  |  | 2027 | 388000 |  |  | 388000
JOHNSTON | SR 2500 (WALLPAT ROAD) | NCDOT | CSX CROSSING 629966H IN SMITHFIELD. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004L | Division 4 | RR |  |  |  |  | 2027 | 388000 |  |  | 388000
JOHNSTON, EDGECOMBE, NASH | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | Highway | Other | 4 | Upper Coastal Plain RPO | C-5619 | Exempt | CMAQ, L | 2020 | 420000 |  |  | 2020 | 2495000 | 2020 | 1260000 | 4175000
JOHNSTON, NASH, WAYNE, WILSON, EDGECOMBE, HALIFAX | VARIOUS | NCDOT | 194 FREEWAY RAMPS. INSTALL WRONG WAY PAVEMENT MARKINGS AND SIGNS | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | HS-2004Y | Statewide Mobility | HSIP |  |  |  |  | 2024 | 650000 |  |  | 650000
JOHNSTON, WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 15.03 | Public Transportation (Transit) | STI (Prioritization) | 4, 5 | Capital Area MPO | TO-6166D | Region A, C | L, T | 2030 | 34345000 | 2030 | 3988000 | 2033 | 75426000 | 2031 | 1500000 | 115259000
JOHNSTON, WILSON | VARIOUS | NCDOT | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 4 | Capital Area MPO, Upper Coastal Plain RPO | W-5204DIV | Division 4
JOHNSTON, WILSON | VARIOUS | NCDOT | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 4 | Capital Area MPO, Upper Coastal Plain RPO | W-5204REG | Region A
JONES | US 17 BUSINESS (MAIN STREET) |  | FROM NC 58 TO SR 1366 (EAST STREET) IN POLLOCKSVILLE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.83 | Bike & Ped | NCDOT Selected (Other Selection Process) | 2 | Down East RPO | BN-0005 | Exempt | CRPLT5, L, O |  |  |  |  | 2025 | 475000 | 2024 | 75000 | 550000
JONES | US 70 | NCDOT | AT SR 1002 (WYSE FORK ROAD) / SR 1309 (CASWELL STATION ROAD). CONSTRUCT A REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | Safety | 2 | Down East RPO | HS-2002AG | Region B | HSIP |  |  | 2024 | 30000 | 2024 | 965000 |  |  | 995000
JONES | US 17 | NCDOT | NORTH OF MAYSVILLE TO SOUTH OF NC 58. | 5.66 | Highway | Transition | 2 | Down East RPO | R-2514C | Pre-STI (Transition) | [10 empty] | COMPLETED.
JONES | US 17 | NCDOT | SOUTH OF NC 58 TO THE NEW BERN BYPASS. | 5.8 | Highway | Transition | 2 | Down East RPO | R-2514D | Pre-STI (Transition) | [10 empty] | COMPLETED.
JONES, LENOIR, CARTERET | NC 58 | NCDOT | NORTHWEST OF SR 1109 (PELETIER LOOP ROAD) SOUTHERN INTERSECTION IN CARTERET COUNTY TO SOUTHEASTERN MUNICIPAL LIMIT OF MAYSVILLE IN JONES COUNTY; EAST OF SR 1338 (GOSHEN LANE) TO SOUTHERN MUNICIPAL LIMIT OF TRENTON IN JONES COUNTY; EAST OF SR 1124 (GREENTOWN ROAD) IN JONES COUNTY TO SR 1900 (COLLIER LOFTIN ROAD) IN LENOIR COUNTY. INSTALL RUMBLE STRIPES. |  | Highway | Safety | 2 |  | HS-2402S | Region B | HSIP |  |  |  |  | 2025 | 1115000 |  |  | 1115000
JONES, ONSLOW | US 17 | NCDOT | MULTI-LANES NORTH OF JACKSONVILLE TO NEW BERN BYPASS. WIDEN TO MULTI-LANES WITH BYPASSES OF BELGRADE, MAYSVILLE AND POLLOCKSVILLE ON NEW LOCATION. | 22.1 | Highway | Pre-STI (Historic) | 2, 3 | Down East RPO, Jacksonville Urban Area MPO | R-2514
LEE | RALEIGH EXECUTIVE SANFORD - LEE COUNTY AIRPORT (TT | RALEIGH EXECUTIVE SANFORD - LEE COUNTY AIRPORT (TT | CONSTRUCT CORPORATE AREA APRON PHASE I. |  | Aviation | STI (Prioritization) | 8 | Central Pines RPO | AV-5762 | Division 8 | [10 empty] | UNDER CONSTRUCTION; INCLUDES $1.5 M IN ECONOMIC DEVELOPMENT FUNDING
LEE | RALEIGH EXECUTIVE JETPORT (TTA) | RALEIGH EXECUTIVE JETPORT (TTA) | RUNWAY 21 AND RUNWAY 3 BYPASS TAXIWAY. CONSTRUCT AIRPLANE RUN-UP LANE AT EACH END OF TAXIWAY. |  | Aviation | STI (Prioritization) | 8 | Central Pines RPO | AV-5899 | Division 8 | T |  |  |  |  | 2024 | 2600000 |  |  | 2600000
LEE | NC 42 (WICKER STREET) | SANFORD | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 0.42 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5742 | Division 8 | L, TA5T50 |  |  |  |  | 2026 | 1011000 | 2022 | 77000 | 1088000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS
LEE | US 1 BUSINESS (CARTHAGE STREET) | SANFORD | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.85 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5863 | Division 8 | L, TA5T50 | 2026 | 150000 |  |  | 2027 | 1469000 | 2021 | 295000 | 1914000
LEE | SR 1107 (FIELDS DRIVE) | SANFORD | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5867 | Division 8 | L, TA5T50 | 2025 | 102000 | 2025 | 90000 | 2026 | 1015000 | 2024 | 149000 | 1356000
LEE | WOODLAND STREET | SANFORD | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-5868 | Division 8 | L, TA5T50 | 2025 | 111000 | 2025 | 100000 | 2025 | 1105000 | 2023 | 116000 | 1432000
LEE | SR 1002 (CHARLOTTE AVENUE) | SANFORD | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 0.95 | Bike & Ped | STI (Prioritization) | 8 | Central Pines RPO | EB-6002 | Division 8 | L, TA5T50 |  |  |  |  | 2025 | 1400000 | 2023 | 191000 | 1591000
LEE | SR 1400 (CUMNOCK ROAD) | NCDOT | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | Highway | Bridges | 8 | Central Pines RPO | B-5976 | Division 8 | BGOFF | 2025 | 210000 | 2025 | 510000 | 2028 | 11500000 |  |  | 12220000
LEE | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NCDOT | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | 5.57 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-3830 | Division 8 | T | 2019 | 10228000 |  |  | 2023 | 74099000 |  |  | 84327000 | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE)
LEE | NC 42 | NCDOT | RAILROAD MITIGATION |  | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-3830A | Division 8 | T |  |  |  |  | 2021 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION
LEE | SR 1521 (KELLY DRIVE) | NCDOT | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | 0.5 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5959 | Division 8 | T | 2025 | 1900000 | 2025 | 660000 | 2026 | 7100000 |  |  | 9660000 | RIGHT-OF-WAY IN PROGRESS
LEE | SR 1237 (CARTHAGE STREET) | NCDOT | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY TO A TWO LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 0.85 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5709 | Division 8 | T | 2022 | 3427000 | 2022 | 1700000 | 2026 | 25195000 |  |  | 30322000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BONDS: $8,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE).
LEE | US 421 BUSINESS / NC 87 | NCDOT | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | 3.4 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5722 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19501000 |  |  | 56901000
LEE | US 1 / US 15 / US 501 | NCDOT | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO REDUCED CONFLICT INTERSECTION. | 0.8 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5727 | Region E | NHP, T | 2023 | 12300000 | 2023 | 1500000 | 2026 | 36000000 |  |  | 49800000 | COORDINATE WITH U-5975. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $12M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE);
LEE | US 1 / US 15 / US 501 | NCDOT | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 2.17 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-5975 | Region E | T | 2023 | 4100000 | 2023 | 3300000 | 2026 | 47240000 |  |  | 54640000 | COORDINATE WITH U-5727. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $15.5M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE);
LEE | LEE COUNTY | LEE COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 8 | Central Pines RPO | TK-6140 | Public Transit | 5311, L, S | [6 empty] | 2020 | 632000 | 632000 | FUNDS AUTHORIZED IN PROGRESS
LEE | US 1 BUSINESS (CARTHAGE STREET / CHARLOTTE AVENUE) | NCDOT | ATW CROSSING 721059F IN SANFORD. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Central Pines RPO | RX-2008E | Division 8 | RR |  |  |  |  | 2025 | 450000 |  |  | 450000
LENOIR | KINSTON RIVERWALK | KINSTON | CASWELL MEMORIAL PARK TO ATLANTIC AVENUE ALONG NEUSE RIVER IN KINSTON. CONSTRUCT 10 FOOT MULTI-USE PATH. | 1.58 | Bike & Ped | NCDOT Selected (Other Selection Process) | 2 | Eastern Carolina RPO | BN-0008 | Exempt | CRP550, L(M) | 2025 | 5000 |  |  | 2027 | 3040000 | 2024 | 305000 | 3350000 | KINSTON RIVERWALK PHASE 2
LENOIR | NC 903 | NCDOT | REPLACE BRIDGE 530045 OVER NEUSE RIVER. | 0.25 | Highway | Bridges | 2 | Eastern Carolina RPO | B-4566 | Region B | BFP | 2026 | 262000 | 2026 | 129000 | 2028 | 6500000 |  |  | 6891000
LENOIR | SR 1389 (HARDY BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 530052 OVER NEUSE RIVER AND 530152 OVER NEUSE RIVER OVERFLOW. | 0.25 | Highway | Bridges | 2 | Eastern Carolina RPO | B-5619 | Division 2 | BGOFF | 2020 | 500000 |  |  | 2021 | 9170000 |  |  | 9670000 | UNDER CONSTRUCTION.
LENOIR | US 70 / US 258 (WEST VERNON AVENUE) | NCDOT | 630 FEET EAST OF US 258 IN KINSTON. REMOVE EASTBOUND LEFT-OVER. | 0.5 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002AE | Region B | HSIP |  |  |  |  | 2024 | 205000 |  |  | 205000
LENOIR | US 70 | NCDOT | INSTALL RESTRICTED CROSSING INTERSECTIONS AT US 70 AND SR 1324 (KENNEDY HOME ROAD) / SR 1519 (EASON ROAD) AND AT ADJACENT CROSSOVER TO THE WEST. | 0.5 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002C | Statewide Mobility | HSIP |  |  | 2022 | 20000 | 2022 | 250000 |  |  | 270000 | UNDER CONSTRUCTION.
LENOIR | NC 11 | NCDOT | NC 11 AT SR 1716 (HARVEY ROUSE ROAD), NC 11 AT NC 118/SR 1091 (GRIFTON-HUGO ROAD), AND NC 11 AT SR 1714 (CREEK ROAD). CONVERT MEDIAN OPENINGS TO REDUCED CONFLICT INTERSECTIONS. | 0.68 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002K | Region B | HSIP |  |  | 2023 | 80000 | 2023 | 1235000 |  |  | 1315000 | UNDER CONSTRUCTION.
LENOIR | US 258 | NCDOT | US 258 AT SR 1342 (WILL BAKER ROAD / CENTRAL AVENUE). INSTALL FLASHER AND UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002N | Region B | HSIP |  |  |  |  | 2023 | 87000 |  |  | 87000 | UNDER CONSTRUCTION.
LENOIR | US 258 | NCDOT | US 258 AT SR 1120 (NOBLES MILL ROAD) AND US 258 AT SR 1908 (BILL STROUD ROAD). CONSTRUCT TURN LANES. | 0.5 | Highway | Safety | 2 | Eastern Carolina RPO | HS-2002P | Region B | HSIP |  |  | 2024 | 150000 | 2024 | 661000 |  |  | 811000 | UTILITY RELOCATION IN PROGRESS.
LENOIR | SR 1395 (VERNON AVENUE) | NCDOT | GREENBRIAR ROAD INTERSECTION IN KINSTON. INSTALL / UPGRADE PEDESTRIAN SIGNALS AND OTHER PEDESTRIAN ACCOMMODATIONS. |  | Highway | Safety | 2 | Eastern Carolina RPO | HS-2402J | Division 2 | HSIP | 2025 | 8000 |  |  | 2025 | 113000 |  |  | 121000
LENOIR | NC 148 (CF HARVEY PARKWAY) | NCDOT | NC 58 TO NC 11. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 4.07 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5703 | Region B | T |  |  |  |  | 2018 | 74609000 |  |  | 74609000 | COMPLETE. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
LENOIR | SR 1569 (CAREY ROAD EXTENSION) | NCDOT | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | 1.81 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | U-3618 | Division 2 | BGANY | 2028 | 7701000 | 2028 | 2700000 | 2031 | 50300000 |  |  | 60701000
LENOIR | LENOIR COUNTY | LENOIR COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Eastern Carolina RPO | TK-6178 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1048000 | 1048000 | FUNDS AUTHORIZED IN PROGRESS
LENOIR | LINCOLN STREET | NCDOT | NORFOLK SOUTHERN CROSSING 722766G IN KINSTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Eastern Carolina RPO | RX-2002D | Division 2 | RR |  |  |  |  | 2025 | 411000 |  |  | 411000
LENOIR, GREENE | US 258 | NCDOT | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | 4.79 | Highway | STI (Prioritization) | 2 | Eastern Carolina RPO | R-5814 | Division 2 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 61700000 |  |  | 77000000
LENOIR, ONSLOW, JONES | US 258 | NCDOT | US 258 BETWEEN NC 24 IN RICHLANDS AND US 70 IN KINSTON. INSTALL RUMBLES STRIPES. | 25.07 | Highway | Safety | 2, 3 | Eastern Carolina RPO, Jacksonville Urban Area MPO, Down East RPO | HS-2002Q | Region B | HSIP |  |  |  |  | 2025 | 585000 |  |  | 585000
LENOIR, WAYNE | NC 55 | NCDOT | FROM .86 MILES WEST OF NC 903 TO NC 11. INSTALL RUMBLE STRIPS. | 11.76 | Highway | Safety | 2, 4 | Eastern Carolina RPO | HS-2002AD | Region A, B | HSIP |  |  |  |  | 2025 | 380000 |  |  | 380000
LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | VARIOUS |  | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | Bike & Ped | Other | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | BO-2419 | Division 2, 4, 5, 6, 8, 9 | DP, HF, HSIP | 2025 | 122000 | 2025 | 122000 | 2025 | 10647000 | 2024 | 1409000 | 12300000 | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS.
LINCOLN | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | OBSTRUCTION REMOVAL IN RUNWAY 5 APPROACH. |  | Aviation | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | AV-5753 | Division 12 | T | 2024 | 295000 | [6 empty] | 295000
LINCOLN | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LAND ACQUISITION FOR RUNWAY 5 APPROACH. |  | Aviation | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | AV-5755 | Division 12 | T | 2024 | 176000 | [6 empty] | 176000
LINCOLN | NC 27 | LINCOLNTON | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 0.09 | Bike & Ped | Locally Selected | 12 | Gaston-Cleveland-Lincoln MPO | C-5606I | Exempt | CMAQ, HF, L(M) |  |  |  |  | 2024 | 700000 |  |  | 700000 | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000.
LINCOLN | SR 1360 (BETH HAVEN CHURCH ROAD) | NCDOT | SR 1373 (WINGATE HILL ROAD/ FORNEY HILL ROAD). INSTALL ALL WAY STOP, UPGRADE SIGNS AND PAVEMENT MARKINGS, AND IMPROVE SHOULDERS. | 0.5 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012F | Division 12 | HSIP |  |  |  |  | 2023 | 25000 |  |  | 25000 | UNDER CONSTRUCTION.
LINCOLN | SR 1003 (BUFFALO SHOALS ROAD) | NCDOT | SR 1343 (IVEY CHURCH ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | W-5712R | Division 12 | HSIP | 2024 | 42000 | 2024 | 5000 | 2025 | 610000 |  |  | 657000
LINCOLN | NC 16 BUSINESS | NCDOT | SR 1439 (UNITY CHURCH ROAD)/SR 1387 (TRIANGLE CIRCLE). ADD TURN LANES. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | R-5712 | Region F | T |  |  | 2025 | 1200000 | 2025 | 2300000 |  |  | 3500000 | RIGHT-OF-WAY IN PROGRESS
LINCOLN | NC 16 BUSINESS | NCDOT | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | 0.5 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-5962 | Region F | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16800000 |  |  | 35500000 | OTHER FUNDING PROVIDED BY LINCOLN COUNTY
LINCOLN | NC 16 BYPASS | NCDOT | SR 1380 (OPTIMIST CLUB ROAD). UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 12 | Gaston-Cleveland-Lincoln MPO | U-6134 | Region F | BGLT5 | 2024 | 500000 | 2024 | 100000 | 2031 | 46800000 |  |  | 47400000
LINCOLN | LINCOLN COUNTY | LINCOLN COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 12 | Eastern Carolina RPO | TK-6141 | Public Transit | 5311, L, S | [6 empty] | 2020 | 876000 | 876000 | FUNDS AUTHORIZED IN PROGRESS
LINCOLN, CLEVELAND, GASTON | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ON APPROXIMATELY 59 SECONDARY ROADS. |  | Highway | Safety | 12 | Gaston-Cleveland-Lincoln MPO | HS-2012E | Division 12 | HSIP |  |  |  |  | 2023 | 2675000 |  |  | 2675000 | UNDER CONSTRUCTION.
LINCOLN, MECKLENBURG | NC 73 | NCDOT | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. WIDEN TO MULTI-LANES. | 5.57 | Highway | STI (Prioritization) | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO | R-5721A | Region E, F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 69900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 189600000 |  |  | 268800000
MACON | MACON COUNTY AIRPORT | MACON COUNTY AIRPORT | EXTEND RUNWAY. |  | Aviation | STI (Prioritization) | 14 | Southwestern RPO | AV-5850 | Division 14 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 166000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4834000 |  |  | 5000000
MACON | SR 1729 (DEPOT STREET) | NCDOT | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 0.63 | Bike & Ped | STI (Prioritization) | 14 | Southwestern RPO | EB-5756 | Division 14 | L, TAANY |  |  |  |  | 2023 | 294000 | 2022 | 18000 | 312000 | UNDER CONSTRUCTION.
MACON | EAST MAIN STREET/ US 441 BUS | NCDOT | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 0.83 | Bike & Ped | STI (Prioritization) | 14 | Southwestern RPO | EB-5964 | Division 14 | L, TA5T50 | 2025 | 20000 |  |  | 2025 | 650000 | 2024 | 20000 | 690000
MACON | US 441 | NCDOT | SR 1515 (HYATT ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND RIGHT-IN/RIGHT-OUT AT INGLES DEVELOPMENT SITE. | 0.5 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | HA-0004 | Exempt | ADHSL |  |  |  |  | 2022 | 1900000 |  |  | 1900000 | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,900,000. UNDER CONSTRUCTION.
MACON | SR 1114 (SHOPE ROAD) | NCDOT | REPLACE BRIDGE 550244 OVER NORTH FORK COWEETA CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6025 | Division 14 | BGOFF |  |  |  |  | 2024 | 1700000 |  |  | 1700000 | UNDER CONSTRUCTION.
MACON | SR 1500 (WATAUGA ROAD) | NCDOT | REPLACE BRIDGE 550214 OVER WATAUGA CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6026 | Division 14 | BGOFF | 2024 | 50000 |  |  | 2028 | 500000 |  |  | 550000
MACON | SR 1528 (LITTLE ELLIJAY ROAD) | NCDOT | REPLACE BRIDGE 550150 OVER ELLIJAY CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6028 | Division 14 | BGOFF |  |  |  |  | 2022 | 2600000 |  |  | 2600000 | UNDER CONSTRUCTION.
MACON | SR 1001 (ELLIJAY ROAD) | NCDOT | REPLACE BRIDGE 550009 OVER NORTH PRONG ELLIJAY CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6029 | Division 14 | BGOFF |  |  |  |  | 2025 | 2000000 |  |  | 2000000 | UNDER CONSTRUCTION.
MACON | SR 1351 (MATLOCK CREEK ROAD) | NCDOT | REPLACE BRIDGE 550220 OVER MATLOCK CREEK. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | B-6030 | Division 14 | BGOFF |  |  |  |  | 2029 | 625000 |  |  | 625000 | RIGHT-OF-WAY IN PROGRESS
MACON | SR 1679 (PEEKS CREEK ROAD) | NCDOT | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | HB-0030 | Division 14 | BGOFF | 2025 | 480000 | 2025 | 360000 | 2026 | 2700000 |  |  | 3540000
MACON | SR 1679 (GOLD MINE ROAD) | NCDOT | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | 0.25 | Highway | Bridges | 14 | Southwestern RPO | HB-0037 | Division 14 | BGOFF | 2026 | 50000 | 2026 | 50000 | 2027 | 1000000 |  |  | 1100000
MACON | US 64 | NCDOT | DRY FALLS RECREATION AREA. IMPROVE PARKING AREA, CONSTRUCT PEDESTRIAN BRIDGE, AND CONSTRUCT OBSERVATION PLATFORM. | 0.2 | Highway | Federal Lands Access Program | 14 | Southwestern RPO | HF-0006 | Exempt | FLAP | [6 empty] | 2023 | 1000000 | 1000000 | FLAP PROJECT NC 64. AWARDED $1.0M.
MACON | US 64/NC 28 | NCDOT | INSTALL CENTERLINE RUMBLESTRIPS, LONG LIFE PAVEMENT MARKINGS, AND INTERMITTMENT PAVED SHOULDERS FROM SR 1560 TO SR 1533, NEAR FRANKLIN. | 5.76 | Highway | Safety | 14 | Southwestern RPO | HS-2014A | Region G | HSIP |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | UNDER CONSTRUCTION.
MACON | US 19 | NCDOT | CHEROKEE COUNTY TO SWAIN COUNTY. INSTALL RUMBLE STRIPES AND LONG LIFE PAVEMENT MARKINGS. | 2.61 | Highway | Safety | 14 | Southwestern RPO | HS-2014U | Statewide Mobility | HSIP |  |  |  |  | 2024 | 175000 |  |  | 175000
MACON | US 64 (MURPHY ROAD) | NCDOT | SR 1146 (PATTON ROAD); SR 1442 (OLD MURPHY ROAD) NEAR FRANKLIN. CONSTRUCT DIRECTIONAL LEFTOVER WITH U-TURN BULBOUTS. |  | Highway | Safety | 14 | Southwestern RPO | HS-2014W | Region G | HSIP |  |  |  |  | 2025 | 955000 |  |  | 955000
MACON | SR 1668 (FULTON ROAD) | NCDOT | US 64 TO SR 1667 NEAR FRANKLIN. INSTALL GUARDRAIL. |  | Highway | Safety | 14 | Southwestern RPO | HS-2414D | Division 14 | HSIP |  |  |  |  | 2025 | 190000 |  |  | 190000
MACON | SR 1372 (LOWER BURNINGTOWN ROAD) | NCDOT | SR 1474 (SALDEER MOUNTAIN ROAD) TO SR 1392 (MIDDLE BURNINGTOWN ROAD) NEAR FRANKLIN. INSTALL GUARDRAIL. |  | Highway | Safety | 14 | Southwestern RPO | HS-2414E | Division 14 | HSIP |  |  |  |  | 2025 | 375000 |  |  | 375000
MACON | US 23/US 441 | NCDOT | US 64 TO SR 1649 (PRENTISS BRIDGE ROAD). IMPLEMENT ACCESS MANAGEMENT STRATEGIES. | 3.2 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5734 | [11 empty] | SEGMENT A INCLUDES THE REPLACEMENT OF BRIDGE 314 FORMERLY SCHEDULED TO BE REPLACED UNDER 17BP.14.R.154
MACON | US 23/US 441 | NCDOT | US 64 TO SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE). | 0.82 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5734A | Division 14 | T |  |  |  |  | 2021 | 12600000 | 2021 | 2310000 | 14910000 | COMPLETE; BUILD NC BOND FUNDING: $1.788 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $9.797 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
MACON | US 23/US 441 | NCDOT | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | 2.42 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5734B | Not Funded | T | NOT FUNDED | 13800000 | NOT FUNDED | 3200000 | NOT FUNDED | 26600000 | NOT FUNDED |  | 43600000
MACON | US 23/US 441 | NCDOT | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | 9 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5734C | Not Funded | T | NOT FUNDED | 5000000 | NOT FUNDED | 600000 | NOT FUNDED | 53600000 | NOT FUNDED |  | 59200000
MACON | US 441 BUSINESS | NCDOT | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | 1.4 | Highway | STI (Prioritization) | 14 | Southwestern RPO | U-5604 | Region G | T |  |  |  |  | 2020 | 7080000 | 2021 | 1830000 | 8910000 | COMPLETE - BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE).
MACON | MACON COUNTY | MACON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6142 | Public Transit | 5311, L, S | [6 empty] | 2020 | 764000 | 764000 | FUNDS AUTHORIZED IN PROGRESS
MACON | INTEGRATED MOBILITY DIVISION |  | MACON COUNTY AREAS OF PERSISTENT POVERTY (AoPP) GRANT. |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TM-0049 | Public Transit | DP, L | [6 empty] | 2024 | 525000 | 525000
MACON, CHEROKEE, JACKSON | VARIOUS | NCDOT | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS PRIMARY AND SECONDARY ROUTES. |  | Highway | Safety | 14 | Southwestern RPO | HS-2014P | Region G | HSIP |  |  |  |  | 2024 | 2955000 |  |  | 2955000 | UNDER CONSTRUCTION.
MADISON | MARSHALL | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL, AND PEDESTRIAN REFUGE. | 0.14 | Bike & Ped | STI (Prioritization) | 13 | Land-of-Sky RPO | EB-5918 | Division 13 | L(M), TALT5 |  |  |  |  | 2026 | 150000 | 2023 | 45000 | 195000
MADISON | I-26 (US 19/US 23) | NCDOT | NORTH OF NC 213 TO NORTH OF US 19 | 1.762 | Highway | Appalachian Development Highway System | 13 | Land-of-Sky RPO | A-0010BB | [11 empty] | COMPLETE
MADISON | I-26 (US 19/US 23) | NCDOT | NORTH OF US 19 TO SR 1318 (BIG LAUREL ROAD) AT LAUREL CREEK | 6.08 | Highway | Appalachian Development Highway System | 13 | Land-of-Sky RPO | A-0010C | [11 empty] | COMPLETE
MADISON | I-26 (US 19/US 23) | NCDOT | SR 1318 (BIG LAUREL ROAD) AT LAUREL CREEK TO THE TENNESSEE STATE LINE AT SAMS GAP | 2.98 | Highway | Appalachian Development Highway System | 13 | Land-of-Sky RPO | A-0010D | [11 empty] | COMPLETE
MADISON | SR 1503 (LAUREL VALLEY) | NCDOT | REPLACE BRIDGE 560246 OVER LAUREL CREEK. | 0.25 | Highway | Bridges | 13 | French Broad River MPO, Land-of-Sky RPO | B-4182 | Division 13 | [10 empty] | CONSTRUCTION FUNDED WITH STATE LEGISLATIVE BRIDGE PROGRAM FUNDS (17BP.13.R.105)
MADISON | SR 1395 (WALNUT CREEK ROAD) | NCDOT | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | 0.25 | Highway | Bridges | 13 | Land-of-Sky RPO | B-5989 | Division 13 | BGOFF | 2022 | 13000 | 2023 | 130000 | 2023 | 7406000 |  |  | 7549000 | UNDER CONSTRUCTION.
MADISON | SR 1341 (FOSTER CREEK ROAD) | NCDOT | REPLACE BRIDGE 560073 OVER FOSTER CREEK. | 0.25 | Highway | Bridges | 13 | French Broad River MPO | B-6012 | Division 13 | T |  |  |  |  | 2019 | 4828000 |  |  | 4828000 | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
MADISON | I-26 | NCDOT | TENNESSEE STATE LINE TO MILE MARKER 9. PAVEMENT AND BRIDGE REHABILITATION. | 9 | Highway | Interstate Maintenance | 13 | Land-of-Sky RPO | I-5831
MADISON | I-26 | NCDOT | TENNESSEE STATE LINE TO MILE MARKER 9. REPLACE CURB AND DRAINAGE BOXES, AND REHABILITATE BRIDGES. | 9.04 | Highway | Interstate Maintenance | 13 | Land-of-Sky RPO | I-5831A | Statewide Mobility | BGLT5 |  |  |  |  | 2022 | 10054000 |  |  | 10054000 | UNDER CONSTRUCTION.
MADISON | I-26 | NCDOT | TENNESSEE STATE LINE TO MILE MARKER 9. REHABILITATE PAVEMENT. | 9.04 | Highway | Interstate Maintenance | 13 | Land-of-Sky RPO | I-5831B | Statewide Mobility | BGLT5 |  |  |  |  | 2025 | 18900000 |  |  | 18900000
MADISON | SR 1318 (BIG LAUREL ROAD) | NCDOT | SR 1340 TO SR 1636 NEAR MARS HILL. INSTALL GUARDRAIL. | 8.59 | Highway | Safety | 13 | Land-of-Sky RPO | HS-2013I | Division 13 | HSIP |  |  |  |  | 2024 | 507000 |  |  | 507000
MADISON | SR 1631 (CROSSROADS PARKWAY) | NCDOT | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | 0.31 | Highway | STI (Prioritization) | 13 | French Broad River MPO | R-5779 | Division 13 | ADHSL, O, T |  |  |  |  | 2021 | 4071000 |  |  | 4071000 | COMPLETE. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170)
MADISON | US 25 / US 70 | MADISON COUNTY TRANSPORTATION | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 13 | Land-of-Sky RPO | TN-6128 | Exempt | CRPLT5, L(M) |  |  |  |  | 2026 | 376000 | 2025 | 28000 | 404000
MADISON | MADISON COUNTY TRANSPORTATION | MADISON COUNTY TRANSPORTATION | PURCHASE TWO TRANSIT VEHICLES |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 13 | Land-of-Sky RPO | TN-6130 | Exempt | CRPLT5, L(M) | [6 empty] | 2025 | 246000 | 246000
MADISON | MADISON COUNTY TRANSPORTATION | MADISON COUNTY TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 13 |  | TK-6143 | Public Transit | 5311, L, S | [6 empty] | 2020 | 548000 | 548000 | FUNDS AUTHORIZED IN PROGRESS
MARTIN | MARTIN COUNTY AIRPORT (MCZ) | MARTIN COUNTY AIRPORT (MCZ) | CONSTRUCT TAXILANES AND APRON. |  | Aviation | STI (Prioritization) | 1 | Mid-East RPO | AV-5788 | Division 1 | T |  |  |  |  | 2023 | 1250000 |  |  | 1250000 | UNDER CONSTRUCTION.
MARTIN | EAST MAIN STREET | WILLIAMSTON | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 0.33 | Bike & Ped | STI (Prioritization) | 1 | Mid-East RPO | EB-5979 | Division 1 | L, TAANY |  |  |  |  | 2027 | 280000 | 2025 | 10000 | 290000
MARTIN | SR 1142 (PRISON CAMP ROAD) | NCDOT | REPLACE BRIDGE 570053 OVER COLLIE SWAMP. | 0.25 | Highway | Bridges | 1 | Mid-East RPO | B-5503 | Division 1 | [10 empty] | COMPLETED.
MARTIN | US 13/US 64 (FUTURE I-87) | NCDOT | EDGECOMBE COUNTY LINE TO US 13/17 AND US 64 INTERCHANGE. PAVEMENT REHABILITATION. | 18.56 | Highway | Interstate Maintenance | 1 | Mid-East RPO | I-6028 | Statewide Mobility | [10 empty] | "A" BREAK DELETED, WORK WAS COMPLETED WITH CONTRACT RESURFACING.
MARTIN | US 64 (FUTURE I-87) | NCDOT | US 64 ALTERNATE TO NC 125. | 4.7 | Highway | Interstate Maintenance | 1 | Mid-East RPO | I-6028B | Statewide Mobility | NHPIM |  |  |  |  | 2020 | 6073000 |  |  | 6073000 | COMPLETED.
MARTIN | US 64 (FUTURE I-87) | NCDOT | NC 125 TO US 13/17 AND US 64 INTERCHANGE. | 4.11 | Highway | Interstate Maintenance | 1 | Mid-East RPO | I-6028C | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 6000000 |  |  | 6000000 | UNDER CONSTRUCTION.
MARTIN | US 17 BUSINESS | NCDOT | SR 1001 (BEAR GRASS ROAD) AND US 13 / US 64 EASTBOUND RAMP INTERSECTIONS IN WILLIAMSTON. CONSTRUCT REDUCED CONFLICT INTERSECTION. |  | Highway | Safety | 1 | Mid-East RPO | HS-2401H | Region A | HSIP | 2026 | 100000 | 2026 | 30000 | 2027 | 1050000 |  |  | 1180000
MARTIN | SR 1142 (PRISON CAMP ROAD) | NCDOT | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | 9.58 | Highway | STI (Prioritization) | 1 | Mid-East RPO | R-4705 | Division 1 | BGANY | 2022 | 200000 | 2023 | 2100000 | 2022 | 48147000 |  |  | 50447000 | UNDER CONSTRUCTION.
MARTIN | US 17 | NCDOT | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | 2.01 | Highway | STI (Prioritization) | 1 | Mid-East RPO | R-5810 | Division 1 | BGANY, T | 2025 | 250000 | 2025 | 80000 | 2027 | 13300000 |  |  | 13630000
MARTIN | US 13/US 17 | NCDOT | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 1 | Mid-East RPO | R-5879 | Region A | NHP | 2028 | 140000 | 2028 | 970000 | 2031 | 5000000 |  |  | 6110000
MARTIN | MARTIN COUNTY | MARTIN COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 1 | Mid-East RPO | TK-6144 | Public Transit | 5311, L, S | [6 empty] | 2020 | 724000 | 724000 | FUNDS AUTHORIZED IN PROGRESS
MARTIN, BEAUFORT | US 17 | NCDOT | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | 10.01 | Highway | STI (Prioritization) | 1, 2 | Mid-East RPO | R-2511 | Division 1, 2 | T | 2019 | 10471000 | 2019 | 2200000 | 2022 | 99343000 |  |  | 112014000 | UNDER CONSTRUCTION.
MARTIN, BERTIE | US 13, US 17, NC 171 | NCDOT | UPGRADE CURVE WARNING SIGNS AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Mid-East RPO, Peanut Belt RPO | HS-2001B | Region A | HSIP |  |  |  |  | 2023 | 35000 |  |  | 35000 | UNDER CONSTRUCTION.
MARTIN, EDGECOMBE, WASHINGTON, DARE, TYRRELL, NASH | US 64 | NCDOT | BROADBAND AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | 145.54 | Highway | Other | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | HB-0001A | Statewide Mobility | DP, HSIP, T(M) |  |  |  |  | 2027 | 26500000 |  |  | 26500000
McDOWELL | SR 1703 (BALDWIN AVENUE) | MARION | PERRY STREET TO US 70 (EAST COURT STREET). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 0.56 | Bike & Ped | STI (Prioritization) | 13 | Foothills RPO | EB-5753 | Division 13 | L, TA5T50, TAANY | 2026 | 100000 |  |  | 2027 | 147000 | 2024 | 190000 | 437000
McDOWELL | FONTA FLORA TRAIL | MCDOWELL COUNTY | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | Bike & Ped | STI (Prioritization) | 13 | Foothills RPO | EB-5916 | Division 13 | L, TA5200, TAANY | 2025 | 75000 |  |  | 2025 | 3063000 | 2021 | 560000 | 3698000
McDOWELL | NEW ROUTE | NCDOT | CONSTRUCT ACCESS ROAD TO UNIVERSAL PROPERTY. | 0.17 | Highway | Appalachian Development Highway System | 13 | Foothills RPO | R-5964 | Exempt | ADHSL |  |  |  |  | 2021 | 922000 |  |  | 922000 | UNDER CONSTRUCTION. ARC # 19098; AWARD AMOUNT = $987,112
McDOWELL | SR 1781 (POLLY SPOUT ROAD) | NCDOT | REPLACE BRIDGE 580312 OVER SECOND BROAD RIVER. | 0.25 | Highway | Bridges | 13 | Foothills RPO | B-6014 | Division 13 | BGOFF | 2022 | 100000 |  |  | 2022 | 4831000 |  |  | 4931000 | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION.
McDOWELL | I-40 | NCDOT | SR 1001 (SUGAR HILL ROAD)/MILE MARKER 81 TO NC 226/MILE MARKER 86. PAVEMENT REHABILITATION. | 4.97 | Highway | Interstate Maintenance | 13 | Foothills RPO | HI-0009 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 14900000 |  |  | 14900000
McDOWELL | I-40 | NCDOT | MILE MARKER 67 TO MILE MARKER 73 (OLD FORT MOUNTAIN). CONSTRUCT SAFETY AND DRAINAGE IMPROVEMENTS, REHABILITATE PAVEMENT, AND RECONSTRUCT MEDIAN BARRIER. | 5.95 | Highway | Interstate Maintenance | 13 | Foothills RPO | HI-0010 | Statewide Mobility | PROTCT |  |  |  |  | 2023 | 17600000 |  |  | 17600000 | UNDER CONSTRUCTION.
McDOWELL | I-40 | NCDOT | MILE MARKER 73 TO MILE MARKER 81. PAVEMENT REHABILITATION. | 12.99 | Highway | Interstate Maintenance | 13 | Foothills RPO | I-5900 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2027 | 25100000 |  |  | 25100000
McDOWELL | US 221 - NC 226 | NCDOT | SR 1434 NORTH OF MARION TO US 221-NC 226 BUSINESS |  | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-0204A | [11 empty] | COMPLETE
McDOWELL | US 221 (MARION BYPASS) | NCDOT | US 221-NC 226 BUSINESS TO SOUTH OF SOUTHERN RAILWAY. |  | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-0204B | [11 empty] | COMPLETE
McDOWELL | US 221 (MARION BYPASS) | NCDOT | SOUTH OF SOUTHERN RAILWAY TO US 221-NC 226 INTERSECTION SOUTH OF MARION | 0.5 | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-0204C | [11 empty] | COMPLETE
McDOWELL | US 221 | NCDOT | NC 226/ US 221 BUS TO US 70. IMPROVE PAVEMENT. | 2.49 | Highway | Safety | 13 | Foothills RPO | HS-2013H | Statewide Mobility | HSIP |  |  |  |  | 2023 | 530000 |  |  | 530000 | UNDER CONSTRUCTION.
McDOWELL | SR 1135 (OLD FORT/ SUGARHILL ROAD) | NCDOT | SR 1103 TO SR 1001 NEAR OLD FORT. INSTALL GUARDRAIL. | 8.95 | Highway | Safety | 13 | Foothills RPO | HS-2013M | Division 13 | HSIP |  |  |  |  | 2023 | 890000 |  |  | 890000
McDOWELL | US 221 | NCDOT | US 221 BUSINESS TO NORTH OF NC 226 NEAR MARION. INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 13 | Foothills RPO | HS-2413C | Statewide Mobility | HSIP |  |  |  |  | 2026 | 445000 |  |  | 445000
McDOWELL | US 70 | NCDOT | MILE MARKER 7.424 TO MILE MARKER 15.422 AND MILE MARKER 20.237 TO MILE MARKER 27.443 NEAR MARION. INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 13 | Foothills RPO | HS-2413D | Region G | HSIP |  |  |  |  | 2026 | 690000 |  |  | 690000
McDOWELL | I-40 | NCDOT | BUNCOMBE COUNTY LINE TO BURKE COUNTY LINE. UPGRADE GUARDRAIL END UNITS. |  | Highway | Safety | 13 | Foothills RPO | HS-2413L | Statewide Mobility | HSIP |  |  |  |  | 2025 | 200000 |  |  | 200000
McDOWELL | US 221 | NCDOT | RUTHERFORD COUNTY LINE TO AVERY COUNTY LINE. UPGRADE GUARDRAIL END UNITS. |  | Highway | Safety | 13 | Foothills RPO | HS-2413M | Statewide Mobility | HSIP |  |  |  |  | 2025 | 645000 |  |  | 645000
McDOWELL | US 221 - NC 226 | NCDOT | SR 1434 TO SR 1153. WIDEN TO MULTI-LANES, WITH A BYPASS OF MARION. | 12.4 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-0204
McDOWELL | US 221 | NCDOT | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | 0.5 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-0204D | Not Funded | T | NOT FUNDED | 3000000 | NOT FUNDED | 500000 | NOT FUNDED | 32500000 | NOT FUNDED |  | 36000000
McDOWELL | US 221 | NCDOT | I-40 INTERCHANGE. IMPROVE INTERCHANGE. | 2.13 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-0204EA | Division 13 | BGANY | 2026 | 20100000 | 2026 | 1600000 | 2029 | 42700000 |  |  | 64400000
McDOWELL | US 221 | NCDOT | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | 2.13 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-0204EB | Division 13 | BGANY | 2030 | 4000000 | 2030 | 2200000 | 2033 | 33400000 |  |  | 39600000
McDOWELL | SR 1001 (SUGAR HILL ROAD) | NCDOT | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | 0.36 | Highway | STI (Prioritization) | 13 | Foothills RPO | U-5818 | Division 13 | T | 2020 | 75000 |  |  | 2020 | 13230000 | 2020 | 1710000 | 15015000 | UNDER CONSTRUCTION. BUILD NC BOND: $1.206M FOR PE, $55,995 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $6.005M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
McDOWELL | US 221 BUSINESS | NCDOT | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | 1.48 | Highway | STI (Prioritization) | 13 | Foothills RPO | U-5835 | Division 13 | BGANY | 2024 | 6600000 | 2024 | 2000000 | 2031 | 26300000 |  |  | 34900000 | RIGHT-OF-WAY IN PROGRESS.
McDOWELL, RUTHERFORD | US 221 | NCDOT | (1) US 221 IN RUTHERFORD COUNTY FROM US 64 TO THE MCDOWELL COUNTY LINE. (2) US 221 IN MCDOWELL COUNTY ROM THE RUTHERFORD COUNTY LINE TO I-40. INSTALL SINUSIODAL CENTERLINE RUMBLESTRIPES WITH LONG-LIFE PAVEMENT MARKINGS. | 18.99 | Highway | Safety | 13 | Foothills RPO | W-5813J | Statewide Mobility | HSIP |  |  |  |  | 2022 | 501000 |  |  | 501000 | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | CONSTRUCT END AROUND TAXIWAY ON WEST SIDE OF PROPOSED FOURTH PARALLEL RUNWAY. |  | Aviation | STI (Prioritization) | 10 | Charlotte Regional TPO | AP-0001 | Statewide Mobility | T |  |  |  |  | 2029 | 2000000 |  |  | 2000000
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. |  | Aviation | STI (Prioritization) | 10 | Charlotte Regional TPO | AV-5879 | Statewide Mobility | O, T |  |  |  |  | 2025 | 607500000 |  |  | 607500000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND WEST RAMP NEAR CONCOURSE A - PHASE II. |  | Aviation | STI (Prioritization) | 10 | Charlotte Regional TPO | AV-5881 | Statewide Mobility | O, T |  |  |  |  | 2021 | 40100000 |  |  | 40100000 | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). |  | Aviation | STI (Prioritization) | 10 | Charlotte Regional TPO | AV-5893 | Region E | O, T |  |  |  |  | 2025 | 202500000 |  |  | 202500000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | DAVIDSON | DAVIDSON | WEST BRANCH NATURE PRESERVE. CONSTRUCT GREENWAY. | 0.77 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0003 | Division 10 | L, TADA | [6 empty] | 2023 | 151000 | 151000
MECKLENBURG | THE PARK - HUNTERSVILLE GREENWAY | HUNTERSVILLE | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 1.55 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0010 | Division 10 | BGDA, L, TAANY, TADA | 2025 | 516000 |  |  | 2026 | 2600000 | 2023 | 376000 | 3492000 | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23
MECKLENBURG | IRWIN CREEK GREENWAY | MECKLENBURG COUNTY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 1.3 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0057 | Division 10 | BGDA, CMAQ, L |  |  |  |  | 2030 | 6081000 | 2024 | 10000 | 6091000 | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | RAIL TRAIL PEDESTRIAN BRIDGE | CHARLOTTE | SR 3815 (EAST MOREHEAD STREET) TO BROOKLYN VILLAGE LIGHT RAIL STATION. CONSTRUCT RAIL TRAIL PEDESTRIAN BRIDGE OVER I-277 (BELK FREEWAY). | 0.11 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0058 | Division 10 | L, TAANY |  |  |  |  | 2025 | 6343000 |  |  | 6343000 | $1.903M IN STBG-DA FUNDS SWAPPED FOR $1.903M IN TAP-ANYAREA FUNDS ON 5-17-23
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | CONSTRUCT GREENWAY CULVERT UNDER US 21. | 0.21 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0080 | Division 10 | L, TADA |  |  |  |  | 2025 | 3240000 | 2024 | 10000 | 3250000
MECKLENBURG | LEBANON ROAD AND MARGARET WALLACE ROAD | MINT HILL | MARGARET WALLACE ROAD TO GRISTMILL LANE. CONSTRUCT SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. CONSTRUCT SIDEWALK. | 0.99 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0081 | Division 10 | L, TADA | 2026 | 133000 |  |  | 2027 | 1081000 | 2024 | 434000 | 1648000
MECKLENBURG | SUGAR CREEK ROAD | CHARLOTTE | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0083 | Division 10 | DP, L, TADA | 2025 | 686000 |  |  | 2027 | 20262000 | 2025 | 10000 | 20958000 | DP REPRESENTS FY 23 RAISE GRANT FUNDS.
MECKLENBURG | ALBEMARLE ROAD AND WILORA LAKE ROAD | CHARLOTTE | REDMAN ROAD TO CENTRAL AVENUE. INSTALL SIDEWALK. ALBEMARLE ROAD TO 100 FEET NORTH OF BARR DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN IMPROVEMENTS AT VARIOUS INTERSECTIONS. | 0.93 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0084 | Division 10 | L, TADA |  |  |  |  | 2027 | 3182000 | 2025 | 10000 | 3192000
MECKLENBURG | BEATY STREET | DAVIDSON | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED-USE PATH. | 0.91 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0085 | Division 10 | L, TADA | 2027 | 601000 |  |  | 2029 | 2561000 | 2025 | 330000 | 3492000
MECKLENBURG | BEATY STREET | DAVIDSON | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). CONSTRUCT SHARED USE PATH. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0096 | Division 10 | L, TADA | 2026 | 601000 |  |  | 2028 | 2561000 | 2024 | 330000 | 3492000
MECKLENBURG | MCDOWELL CREEK GREENWAY | NCDOT | NC 73 IN HUNTERSVILLE. CONSTRUCT PEDESTRIAN BRIDGE OVER NC 73 NEAR LINDHOLM DRIVE. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0119 | Division 10 | BGDA, L(M) |  |  |  |  | 2027 | 5159000 |  |  | 5159000
MECKLENBURG | BAIN SCHOOL ROAD | MINT HILL | GAIT DRIVE TO PHILADELPHIA CHURCH ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0120 | Division 10 | BGDA, L | 2028 | 220000 |  |  | 2030 | 1100000 | 2026 | 469000 | 1789000
MECKLENBURG | LAWYERS ROAD | MINT HILL | PIAFFE AVENUE TO THOMPSON ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0121 | Division 10 | BGDA, L | 2028 | 236000 |  |  | 2030 | 774000 | 2026 | 319000 | 1329000
MECKLENBURG | ROCKY RIVER ROAD | CHARLOTTE | ROCKLAND DRIVE TO OLD CONCORD ROAD IN CHARLOTTE. CONSTRUCT SHARED-USE PATH. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0123 | Division 10 | BGDA, L |  |  |  |  | 2027 | 3952000 | 2025 | 10000 | 3962000
MECKLENBURG | TRUELIGHT CHURCH ROAD | MINT HILL | WILGROVE-MINT ROAD TO HEATHER NICOLE LANE IN MINT HILL. CONSTRUCT SIDEWALK. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0124 | Division 10 | BGDA, L | 2028 | 124000 |  |  | 2030 | 1216000 | 2026 | 500000 | 1840000
MECKLENBURG | CHARLOTTE | CHARLOTTE | TOBY CREEK GREENWAY, ROCKLAND DRIVE TO BLUE ROCK DRIVE. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | C-5225B | Exempt | [10 empty] | COMPLETE
MECKLENBURG | CORNELIUS | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY, SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY CONSTRUCT GREENWAY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5777 | Division 10 | CMAQ, L | 2021 | 960000 |  |  | 2026 | 2040000 |  |  | 3000000 | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | MATTHEWS | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5783 | Division 10 | BGANY, BGDA, L | 2022 | 335000 |  |  | 2025 | 1526000 | 2018 | 381000 | 2242000 | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | UPPER MCDOWELL CREEK GREENWAY, CHILGROVE LANE TO NC 73. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5785 | Division 10 | CMAQ, L |  |  |  |  | 2025 | 5339000 |  |  | 5339000 | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | CORNELIUS | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5817 | Division 10 | BGDA, L, TADA |  |  |  |  | 2020 | 3882000 |  |  | 3882000 | COMPLETE.
MECKLENBURG | CHARLOTTE | CHARLOTTE | CHARLOTTE BICYCLE EXPANSION. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5820 | Division 10 | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | MATTHEWS | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5829 | Division 10 | L, TADA |  |  |  |  | 2022 | 2899000 |  |  | 2899000 | UNDER CONSTRUCTION.
MECKLENBURG | SOUTH MCDOWELL STREET | CHARLOTTE | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5929 | Division 10 | BGANY, BGDA, L, TADA | 2021 | 517000 |  |  | 2026 | 1669000 | 2019 | 265000 | 2451000 | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE.
MECKLENBURG | DAVIDSON | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5933 | Division 10 | L, TAANY |  |  |  |  | 2025 | 878000 | 2024 | 219000 | 1097000 | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23
MECKLENBURG | PINEVILLE | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 0.06 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5949 | Division 10 | BGDA, L, O |  |  |  |  | 2022 | 4404000 |  |  | 4404000 | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH
MECKLENBURG | SUNSET ROAD | CHARLOTTE | OAKDALE ROAD / MIRANDA ROAD TO KIEV DRIVE. CONSTRUCT SIDEWALKS ON NORTH SIDE. | 2.83 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-6036 | Division 10 | BGDA, L |  |  |  |  | 2025 | 3158000 |  |  | 3158000
MECKLENBURG | LAWYERS ROAD; WILGROVE-MINT HILL ROAD; WILSON GROV | MINT HILL | EXTEND EXISTING SIDEWALKS. | 2.26 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-6051 | Division 10 | L, TADA | 2025 | 60000 |  |  | 2028 | 2574000 | 2022 | 376000 | 3010000
MECKLENBURG | W.T. HARRIS BOULEVARD | CHARLOTTE | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 0.32 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-6052 | Division 10 | L, TADA | 2025 | 400000 |  |  | 2026 | 1252000 | 2023 | 10000 | 1662000
MECKLENBURG | NORTH DAVIDSON STREET | NCDOT | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | 0.59 | Bike & Ped | Other | 10 | Charlotte Regional TPO | U-5008A | Pre-STI (Transition) | DP | 2022 | 1000000 | 2022 | 25000 | 2023 | 1200000 |  |  | 2225000 | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | CHARLOTTE | TOBY CREEK GREENWAY, UNIVERSTIY CITY BOULEVARD TO ROCKLAND DRIVE. |  | Bike & Ped | Pre-STI (Historic) | 10 | Charlotte Regional TPO | C-5225A | Exempt | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | CHARLOTTE | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. |  | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5781 | Division 10 | BGDA, CMAQ, L |  |  |  |  | 2021 | 3159000 |  |  | 3159000 | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | GREENWAY MCALPINE CREEK | MECKLENBURG COUNTY | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | 1.65 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5782 | Division 10 | L, TAANY, TADA |  |  |  |  | 2023 | 7218000 |  |  | 7218000
MECKLENBURG | CHARLOTTE | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 0.62 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5832 | Division 10 | BGDA, L, TAANY |  |  |  |  | 2022 | 1678000 |  |  | 1678000 | UNDER CONSTRUCTION.
MECKLENBURG | NC 51 MULTI-USE PATH | NCDOT | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5969 | Division 10 | L, TAANY, TADA | 2029 | 960000 |  |  | 2031 | 1300000 | 2023 | 464000 | 2724000
MECKLENBURG | IRWIN CREEK GREENWAY EASTERN EXTENSION | MECKLENBURG COUNTY | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | 0.55 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5970 | Division 10 | L, TAANY |  |  |  |  | 2028 | 4637000 |  |  | 4637000
MECKLENBURG | JETTON STREET | DAVIDSON | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | 0.66 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5971 | Division 10 | L, TAANY |  |  |  |  | 2026 | 900000 | 2025 | 10000 | 910000
MECKLENBURG | SR 1138 (W. ARROWOOD ROAD) WESTBOUND | NCDOT | REPLACE BRIDGES 590001 AND 590513 WITH A NEW SINGLE STRUCTURE OVER SUGAR CREEK. | 0.25 | Highway | Bridges | 10 | Charlotte Regional TPO | B-5990 | Division 10 | BFP | 2025 | 174000 | 2025 | 174000 | 2029 | 4000000 |  |  | 4348000
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NCDOT | NC 16 (BROOKSHIRE BOULEVARD) AT SR 2004 (MOUNT HOLLY HUNTERSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Economic Development | 10 | Charlotte Regional TPO | U-6084 | Region E | T |  |  |  |  | 2018 | 1963000 |  |  | 1963000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CORNING OPTICAL COMMUNICATIONS - COMPLETE.
MECKLENBURG | I-277 | NCDOT | I-77 TO EAST 10TH STREET. RESURFACING AND BRIDGE REHABILITATION. | 3.5 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5746
MECKLENBURG | I-277 (BELK FREEWAY) | NCDOT | I-77 TO EAST STONEWALL STREET. BRIDGE REHABILITATION. |  | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5746A | Statewide Mobility | [10 empty] | COMPLETE
MECKLENBURG | I-277 (BELK FREEWAY) | NCDOT | EAST STONEWALL STREET TO EAST 10TH STREET. BRIDGE REHABILITATION. |  | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5746B | Statewide Mobility | [10 empty] | COMPLETE
MECKLENBURG | I-277 (BROOKSHIRE FREEWAY) | NCDOT | I-77 TO EAST 10TH STREET. RESURFACE ROADWAY AND REHABILITATE BRIDGES FROM JOHNSON STREET TO EAST 10TH STREET. | 1.75 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5746C | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 29400000 |  |  | 29400000 | UNDER CONSTRUCTION.
MECKLENBURG | I-77 | NCDOT | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5769 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 17532000 |  |  | 17532000 | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-85 | NCDOT | 0.1 MILE NORTH OF SR 5901 (BILLY GRAHAM PKWY) TO 0.3 MILE SOUTH OF NC 16 AT MILE MARKER 35.93. PAVEMENT REHABILITATION. | 2.92 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5796 | Statewide Mobility | [10 empty] | TO BE LET WITH I-5770 - UNDER CONSTRUCTION
MECKLENBURG | I-85 | NCDOT | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | 13.93 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5826 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 8940000 |  |  | 8940000 | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-485 | NCDOT | I-77 TO NC 49. PAVEMENT REHABILITATION. REHABILITATE BRIDGES 590661, 590662, 590663, 590664, AND 590643. | 56.03 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5828 | Statewide Mobility | HFB, NHPIM |  |  |  |  | 2029 | 11950000 |  |  | 11950000 | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS
MECKLENBURG | I-85 | NCDOT | REHABIILITATE BRIDGES 590203 (I-85 NB) AND 590204 (I-85 SB) OVER SEABOARD COASTLINE RAILROAD. | 0.5 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5838 | Statewide Mobility | NHPIM |  |  |  |  | 2023 | 1031000 |  |  | 1031000 | UNDER CONSTRUCTION.
MECKLENBURG | I-485 | NCDOT | PAVEMENT AND BRIDGE REHABILITATION AT OAKDALE ROAD INTERCHANGE AT MILEMARKER 17.2. | 1 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5861 | Statewide Mobility | NHPIM |  |  |  |  | 2023 | 1256000 |  |  | 1256000 | UNDER CONSTRUCTION.
MECKLENBURG | I-485 | NCDOT | SR 1786 TO NC 27. BRIDGE REHABILITATION. | 0.65 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5902 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 1600000 |  |  | 1600000
MECKLENBURG | I-485 | NCDOT | BLAIR ROAD TO IDLEWILD ROAD. PAVEMENT REHABILITATION | 6.19 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5904 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 9801000 |  |  | 9801000 | COMPLETED - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-85 | NCDOT | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | 2 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-5905 | Statewide Mobility | BGDA, NHPIM, T(M) |  |  |  |  | 2021 | 19588000 |  |  | 19588000 | COMBINED WITH I-5906. UNDER CONSTRUCTION.
MECKLENBURG | I-277 (BROOKSHIRE FREEWAY) | NCDOT | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | 0.32 | Highway | Interstate Maintenance | 10 | Charlotte Regional TPO | I-6052 | Statewide Mobility | BGDA, NHPIM, T(M) |  |  |  |  | 2023 | 16045000 |  |  | 16045000 | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5538 | Division 10 | CMAQ, L |  |  |  |  | 2021 | 3676000 |  |  | 3676000 | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | SR 1138 (ARROWOOD ROAD) | CHARLOTTE | NC 49 (SOUTH TRYON) TO SOUTH BOULEVARD. ITS UPGRADES. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5613BD | Exempt | CMAQ, L(M) |  |  |  |  | 2022 | 614000 |  |  | 614000 | UNDER CONSTRUCTION.
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | CHARLOTTE | NC 24 (HARRIS BOULEVARD) TO GOVERNOR HUNT ROAD. ITS AND TRAFFIC MANAGEMENT UPGRADES. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5613BE | Exempt | CMAQ, L(M) |  |  |  |  | 2023 | 200000 |  |  | 200000 | UNDER CONSTRUCTION.
MECKLENBURG | NC 115 | NCDOT | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5613J | Exempt | BGDA, CMAQ, L(M) | 2022 | 75000 |  |  | 2025 | 3469000 |  |  | 3544000 | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265
MECKLENBURG | US 21 | NCDOT | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | C-5621 | Region E | BA, BGDA, CMAQ, L, T(M) | 2020 | 6183000 |  |  | 2024 | 23823000 | 2020 | 1916000 | 31922000 | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | REA ROAD | CHARLOTTE | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 0.73 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0023 | Division 10 | BA, O, T(DA) | 2023 | 820000 |  |  | 2025 | 6182000 | 2024 | 24000 | 7026000 | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23.
MECKLENBURG | SR 3468 (WEDDINGTON ROAD) | NCDOT | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0024 | Division 10 | BA, T(DA) | 2024 | 2300000 | 2024 | 1200000 | 2027 | 4723000 | 2021 | 1211000 | 9434000 | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | GREYLOCK RIDGE ROAD | NCDOT | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.25 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0025 | Division 10 | BA, BGDA, L(M), T(DA) | 2023 | 701000 | 2024 | 500000 | 2025 | 7322000 | 2022 | 1040000 | 9563000 | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23.
MECKLENBURG | VARIOUS | NCDOT | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, PAVEMENT RESTRIPING AND MARKERS, AND SIGN REPLACEMENT. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038 |  | BGDACV | [6 empty] | 2022 | 5000 | 5000
MECKLENBURG | US 29/74 (WILKINSON BLVD) AND US 29 (N TRYON ST) | NCDOT | US 29/74 (WILKINSON BLVD) FROM GASTON COUNTY LINE TO FIELD RIDGE ROAD AND US 29 (NORTH TRYON STREET) FROM WEST SUGAR CREEK ROAD TO OLD CONCORD ROAD. RESURFACE ROADWAYS. | 3.46 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038A | Exempt | BGDACV |  |  |  |  | 2022 | 2596000 |  |  | 2596000 | COMPLETE.
MECKLENBURG | VARIOUS | NCDOT | REPLACE PAVEMENT MARKINGS AND SNOW PLOWABLE MARKERS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038B | Exempt | BGDACV |  |  |  |  | 2022 | 2318000 |  |  | 2318000 | UNDER CONSTRUCTION.
MECKLENBURG | VARIOUS | NCDOT | REPLACE TRAFFIC SIGNAL LOOPS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038C | Exempt | BGDACV |  |  |  |  | 2022 | 90000 |  |  | 90000 | COMPLETE.
MECKLENBURG | I-485 | NCDOT | REPLACE OVERHEAD SIGNS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0038D | Exempt | BGDACV |  |  |  |  | 2022 | 705000 |  |  | 705000 | UNDER CONSTRUCTION.
MECKLENBURG | SR 2822 (ROBINSON CHURCH ROAD) | CHARLOTTE | NC 24 TO PLOTT ROAD. WIDEN TO THREE LANES. | 0.58 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0053 | Division 10 | L, T(DA) |  |  |  |  | 2027 | 12444000 | 2026 | 10000 | 12454000 | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG | NC 115 | HUNTERSVILLE | HARVEST POINT DRIVE TO SAM FURR ROAD. IMPROVE CORRIDOR. | 0.43 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0056 | Exempt | L, T(DA) | 2025 | 2852000 |  |  | 2027 | 4938000 | 2024 | 751000 | 8541000 | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP.
MECKLENBURG | NC 24 (WT HARRIS BOULEVARD) | CHARLOTTE | SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO I-85 NORTH RAMP. INSTALL OVERHEAD STREET LIGHTS. | 7.92 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0057 | Exempt | BA, L, T(DA) |  |  |  |  | 2025 | 1515000 | 2024 | 10000 | 1525000 | $981,000 IN I-5507 BONUS ALLOCATION (BA) FUNDS SWITCHED TO T(DA) FUNDS FROM U-5907 TO ENSURE BA FUNDS ARE AUTHORIZED BY JUNE 30, 2024.
MECKLENBURG | BEATY STREET | DAVIDSON | MAIN STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0111 | Exempt | CMAQ, L(M) | 2027 | 339000 |  |  | 2029 | 2742000 | 2025 | 358000 | 3439000
MECKLENBURG | DEARMON ROAD | CHARLOTTE | BENFIELD ROAD TO BROWNE ROAD. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 0.78 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0112 | Division 10 | L, T(DA) |  |  |  |  | 2026 | 15665000 | 2024 | 10000 | 15675000 | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23
MECKLENBURG | LANCASTER HIGHWAY | CHARLOTTE | PROVIDENCE ROAD W. INTERSECTION. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0113 | Exempt | CMAQ, L(M) |  |  |  |  | 2026 | 1683000 | 2025 | 10000 | 1693000
MECKLENBURG | STUMPTOWN ROAD | HUNTERSVILLE | ABERFELD ROAD TO NC 115. WIDEN ROADWAY. | 0.154 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0118 | Region E | L, T(DA) | 2025 | 1980000 |  |  | 2027 | 4280000 | 2025 | 185000 | 6445000 | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23
MECKLENBURG | WT HARRIS BOULEVARD | CHARLOTTE | SUGAR CREEK INTERSECTION IN CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0137 | Exempt | BGANY, L |  |  |  |  | 2028 | 1901000 | 2025 | 10000 | 1911000 | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24.
MECKLENBURG | BROWN-GRIER ROAD; SANDY PORTER ROAD | CHARLOTTE | NC 160 TO I-485; WILLIAM GLEN TO BROWN-GRIER ROAD. IMPROVE CORRIDORS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0138 | Division 10 | BGANY, L |  |  |  |  | 2026 | 31751000 | 2025 | 10000 | 31761000 | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24.
MECKLENBURG | VARIOUS | CHARLOTTE | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0152 | Exempt | CRPANY, CRPDA, L |  |  |  |  | 2027 | 4040000 | 2025 | 857000 | 4897000 | $3.606M IN CRPDA FUNDS SWITCHED WITH $3.606M IN CRPANY FUNDS AS PART OF FUND SWAP 8-12-24.
MECKLENBURG | SR 3156 (MARGARET WALLACE ROAD) | NCDOT | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-2509EA | Division 10 | L, T(DA) | 2025 | 8568000 | 2025 | 910000 | 2028 | 4887000 |  |  | 14365000 | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP.
MECKLENBURG | CORNELIUS NC 115 | NCDOT | POTTS STREET. CONSTRUCT IMPROVEMENTS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5873 | Exempt | BA, BGDA, CMAQ, L, L(M), T(DA), T(M) | 2018 | 4254000 |  |  | 2024 | 16992000 | 2020 | 504000 | 21750000 | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | CHARLOTTE | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | 0.3 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5874 | Division 10 | BGANY, BGDA, L | 2020 | 3500000 |  |  | 2022 | 19883000 |  |  | 23383000 | UNDER CONSTRUCTION; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES.
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | CHARLOTTE | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | 2.1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5905 | [11 empty] | SEGMENTS A AND B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | CHARLOTTE | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | 1.72 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5905A | Division 10 | BA, BGDA |  |  |  |  | 2021 | 8661000 |  |  | 8661000 | RIGHT-OF-WAY IN PROGRESS
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | CHARLOTTE | IMPROVE INTERSECTIONS OF SR 2112 (LAKEVIEW ROAD)/NC 24 (HARRIS BOULEVARD) AND SR 2112 (LAKEVIEW ROAD)/US 21 (STATESVILLE ROAD). | 1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5905B | Exempt | BA, BGDA |  |  |  |  | 2021 | 3162000 |  |  | 3162000
MECKLENBURG | CHAPEL ROAD) SR 2195 (TORRENCE | NCDOT | SR 5544 (WEST CATAWBA AVENUE) IN CORNELIUS. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5906 | Division 10 | BA, BGDA, L, T, T(DA) | 2020 | 11153000 |  |  | 2025 | 19193000 | 2017 | 2041000 | 32387000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | DAVIDSON | NCDOT | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.73 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5907 | Division 10 | BA, L, T(DA) | 2020 | 1048000 |  |  | 2024 | 10504000 | 2021 | 766000 | 12318000 | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. $981K OF T(DA) FUNDS SWITCHED FOR $981K IN BA FUNDS ON U-5907.
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5908 | [11 empty] | RIGHT-OF-WAY IN PROGRESS; SEGMENTS A & B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADD'L FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | 1.02 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5908A | Division 10 | BGANY, BGDA, L | 2020 | 825000 |  |  | 2021 | 4075000 | 2021 | 12000 | 4912000 | UNDER CONSTRUCTION.
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-5908B | Exempt | BGANY, BGDA, L | 2020 | 2895000 |  |  | 2021 | 12249000 |  |  | 15144000 | UNDER CONSTRUCTION.
MECKLENBURG | NC 51 | NCDOT | PARK ROAD TO CARMEL ROAD IN PINEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.46 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6086 | Exempt | BGANY, L(M) |  |  |  |  | 2026 | 7553000 |  |  | 7553000 | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP
MECKLENBURG | DAVIDSON | NCDOT | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6092 | Exempt | BGDA, CMAQ, L | 2022 | 795000 |  |  | 2025 | 2472000 | 2020 | 150000 | 3417000 | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | CORNELIUS | NCDOT | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.35 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6105 | Division 10 | BGANY, BGDA, L | 2023 | 2064000 |  |  | 2025 | 4632000 |  |  | 6696000 | RIGHT-OF-WAY IN PROGRESS. $3M IN BGANY USED AS PART OF FUND SWAP
MECKLENBURG | HUNTERSVILLE | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | 0.47 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6106 | Division 10 | BGANY, BGDA, L | 2022 | 3134000 |  |  | 2025 | 10684000 |  |  | 13818000 | RIGHT-OF-WAY IN PROGRESS. $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP.
MECKLENBURG | SARDIS LANE | CHARLOTTE | REPLACE BRIDGE 590433 OVER MCALPINE CREEK. | 0.25 | Highway | Municipal Bridge | 10 | Charlotte Regional TPO | B-5930 | Division 10 | BGOFF, L |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | PROJECT ADMINISTERED BY CITY OF CHARLOTTE
MECKLENBURG | MORRIS FIELD DRIVE | CHARLOTTE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | Highway | Municipal Bridge | 10 | Charlotte Regional TPO | B-5931 | Division 10 | BGDA, BGOFF, L |  |  |  |  | 2025 | 6204000 | 2024 | 20000 | 6224000 | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE.
MECKLENBURG | VARIOUS | CHARLOTTE | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | Highway | Other | 10 | Charlotte Regional TPO | HO-0016 | Exempt | CRPDA, L |  |  |  |  | 2026 | 4040000 | 2025 | 857000 | 4897000
MECKLENBURG | I-85 | NCDOT | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. CLEARING ONLY. | 1 | Highway | Other | 10 | Charlotte Regional TPO | I-6016A | Highway Fund | HF |  |  |  |  | 2024 | 200000 |  |  | 200000
MECKLENBURG | NC 73 | NCDOT | NC 73 AT NC 115. CONVERT RIGHT TURN LANE ON NC 115 SOUTHBOUND TO A THROUGH LANE AND WIDEN FOR MERGING TAPER. |  | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | R-2632AC | Pre-STI (Transition) | [10 empty] | COMPLETE
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | BROOKSHIRE FREEWAY TO IDLEWILD ROAD IN CHARLOTTE. ADD ADDITIONAL LANES AND CONSTRUCT INTERCHANGES WITH SHARON AMITY ROAD AND IDLEWILD ROAD AND SAFETY IMPROVEMENTS. | 1.4 | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | U-0209 | [11 empty] | COMPLETE - GARVEE BOND FUNDING: $50M FOR RIGHT-OF-WAY, PAYBACK FY 2010-2021; $2M FOR CONSTRUCTION, PAYBACK FY 2013-2024
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | NC 24/NC 27 (ALBEMARLE ROAD) TO IDLEWILD ROAD |  | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | U-0209B | Pre-STI (Transition) | NHP | 2010 | 10968000 |  |  | 2013 | 1025000 |  |  | 11993000 | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS.
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | SEPARATE ITS CONTRACT FOR U-209 B |  | Highway | Pre-STI (Historic) | 10 | Charlotte Regional TPO | U-0209BA | Pre-STI (Transition) | [10 empty] | WORK TO BE CONSTRUCTED BY PROJECT U-6103
MECKLENBURG | NC 24, NC 27 | NCDOT | SR 3110 (ARLINGTON CHURCH ROAD) NEAR CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010A | Region E | HSIP | 2022 | 4000 |  |  | 2023 | 1900000 |  |  | 1904000 | UNDER CONSTRUCTION.
MECKLENBURG | I-277 | NCDOT | INSTALL SMART CUSHIONS AT VARIOUS EXITS. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010B | Statewide Mobility | HSIP |  |  |  |  | 2021 | 144000 |  |  | 144000
MECKLENBURG | NC 49 (SOUTH TRYON STREET) | NCDOT | NC 49 (SOUTH TRYON STREET) AT GENERAL DRIVE; AND, NC 49 (SOUTH TRYON STREET) AT SR 1347 (NEVADA BOULEVARD). INSTALL TRAFFIC SIGNAL AT NC 49 AND GENERAL DRIVE, AND CONVERT NC 49 AT SR 1347 (NEVADA BOULEVARD) TO A DIRECTIONAL CROSSOVER. | 0.42 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010E | Region E | HSIP |  |  | 2025 | 25000 | 2025 | 720000 |  |  | 745000
MECKLENBURG | NC 51 | NCDOT | NC 51 AND POLK STREET. INSTALL PEDESTRIAN SIGNALS AND ACCOMMODATIONS. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010G | Region E | HSIP | 2025 | 70000 |  |  | 2025 | 360000 |  |  | 430000
MECKLENBURG | NC 73 (SAM FURR ROAD) | NCDOT | SR 5544 (CATAWBA AVENUE) AND GLENFURNESS DRIVE INTERSECTIONS IN HUNTERSVILLE. INSTALL PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010J | Region E | HSIP |  |  |  |  | 2024 | 865000 |  |  | 865000 | UNDER CONSTRUCTION.
MECKLENBURG | SR 5901 (BILLY GRAHAM PARKWAY) | NCDOT | NC 49 (TRYON ROAD) TO I-85. INSTALL GUARDRAIL. | 5.1 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010L | Statewide Mobility | HSIP |  |  |  |  | 2023 | 960000 |  |  | 960000
MECKLENBURG | SR 3300 (7TH STREET) | NCDOT | BASCOM STREET / CAMERON AVENUE IN CHARLOTTE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410B | Division 10 | HSIP | 2026 | 25000 |  |  | 2028 | 233000 |  |  | 258000
MECKLENBURG | SR 3624 (REA ROAD) | NCDOT | PIPER GLEN DRIVE AND BEVINGTON PLACE INTERSECTIONS IN CHARLOTTE. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN ACCOMMODATIONS. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410C | Division 10 | HSIP | 2026 | 1000 |  |  | 2028 | 317000 |  |  | 318000
MECKLENBURG | SR 3687 (PARK ROAD) | NCDOT | JIM HYNES CIRCLE INTERSECTION IN CHARLOTTE. INSTALL PEDESTRIAN SIGNAL. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410E | Division 10 | HSIP |  |  |  |  | 2025 | 36000 |  |  | 36000
MECKLENBURG | SR 2935 | NCDOT | COVE CREEK DRIVE INTERSECTION IN CHARLOTTE. CONSTRUCT DIRECTIONAL CROSSVER. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410G | Division 10 | HSIP |  |  |  |  | 2025 | 482000 |  |  | 482000
MECKLENBURG | NC 51 | NCDOT | PALOMINO DRIVE/ HOODS VILLAGE DRIVE INTERSECTION IN MINT HILL. CONSTRUCT DIRECTIONAL CROSSOVER. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410H | Region E | HSIP | 2026 | 260000 | 2026 | 15000 | 2028 | 848000 |  |  | 1123000
MECKLENBURG | NC 51; SR 3468 (WEDDINGTON ROAD) | NCDOT | FULLWOOD LANE INTERSECTION IN MATTHEWS; SOCRATES ACADEMY. CONSTRUCT SIDEWALKS AND INSTALL PEDESTRIAN IMPROVEMENTS. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410J | Region E | HSIP | 2025 | 15000 | 2026 | 5000 | 2027 | 277000 |  |  | 297000
MECKLENBURG | SR 3448 (PLEASANT PLAINS ROAD) | NCDOT | SQUIRREL LAKE PARK ENTRANCE INTERSECTION IN MATTHEWS. CONSTRUCT SIDEWALKS AND INSTALL PEDESTRIAN IMPROVEMENTS. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410K | Division 10 | HSIP |  |  | 2025 | 10000 | 2026 | 101000 |  |  | 111000
MECKLENBURG | VARIOUS | NCDOT | INSTALL SIGNAL AT VARIOUS LOCATION ON SECONDARY ROUTES. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410L | Division 10 | HSIP |  |  |  |  | 2025 | 1153000 |  |  | 1153000
MECKLENBURG | MECKLENBURG COUNTY | NCDOT | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710X | Division 10 | BGANY, CMAQ, HSIP, L, L(M), T(M) | 2021 | 2288000 |  |  | 2026 | 6501000 | 2021 | 788000 | 9577000 | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP.
MECKLENBURG | I-485 |  | I-77 TO I-85 IN SOUTHWEST CHARLOTTE. CONSTRUCT ONE EXPRESS LANE IN EACH DIRECTION. TOLL PROJECT. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | HP-0002 | Statewide Mobility | BOND R, NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 23700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 246200000 |  |  | 271500000
MECKLENBURG | I-85 |  | SR 1291 (BILLY GRAHAM PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | HP-0004 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6567000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30532000 |  |  | 37599000
MECKLENBURG | I-485 | NCDOT | I-485, I-77 SOUTH OF CHARLOTTE TO US 74 (INDEPENDENCE BOULEVARD). ADD ONE EXPRESS LANE IN EACH DIRECTION. TOLL PROJECT. | 16.62 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5507 | Statewide Mobility | T |  |  |  |  | 2019 | 458656000 |  |  | 458656000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT
MECKLENBURG | I-77 | NCDOT | SR 2136 (GILEAD ROAD) INTERCHANGE. UPGRADE EXISTING INTERCHANGE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5714 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | I-77 | NCDOT | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5715 | Statewide Mobility | NHP | 2023 | 19000000 | 2023 | 3000000 | 2027 | 79901000 |  |  | 101901000 | RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | I-77 | NCDOT | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT I-277 INTERCHANGES. TOLL PROJECT. | 11.2 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5718 | Statewide Mobility | BOND R, NHP | 2029 | 1508000000 | 2029 | 42000000 | 2029 | 2704567000 |  |  | 4254567000 | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049.
MECKLENBURG | I-485 | NCDOT | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-5973 | Region E | T |  |  | 2022 | 195000 | 2023 | 6460000 |  |  | 6655000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE)
MECKLENBURG | I-85 | NCDOT | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6012 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 47000000 |  |  | 52100000
MECKLENBURG | I-85 | NCDOT | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6013 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16000000 |  |  | 17100000
MECKLENBURG | I-485 | NCDOT | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6015 | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9999000 |  |  | 19499000
MECKLENBURG | I-85 | NCDOT | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6016 | Statewide Mobility | HF, T | 2024 | 2000000 | 2024 | 970000 | 2026 | 46600000 |  |  | 49570000 | HF FUNDS ARE CONTINGENCY FUNDS.
MECKLENBURG | I-485 | NCDOT | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6019 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20701000 |  |  | 40301000
MECKLENBURG | I-85 | NCDOT | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6020 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 72900000 |  |  | 132100000
MECKLENBURG | I-85 | NCDOT | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | I-6053 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26973000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 655000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24300000 |  |  | 51928000
MECKLENBURG | I-485 | NCDOT | SR 3468 (WEDDINGTON ROAD). CONSTRUCT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-0211EC | Division 10 | T |  |  |  |  | 2019 | 9000000 |  |  | 9000000
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NCDOT | NC 73 (SAM FURR ROAD) TO EAST OF SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | 3.4 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2555
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NCDOT | SR 2151 (JETTON ROAD) TO SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | 0.9 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2555A | [11 empty] | COMPLETE
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NCDOT | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 2.35 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2555B | Division 10 | L, T | 2026 | 5000000 | 2026 | 4000000 | 2027 | 39855000 |  |  | 48855000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE).
MECKLENBURG | NC 73 | NCDOT | US 21 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 4.3 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2632 | [11 empty] | COORDINATE WITH R-5706A & B. $7.273M IN NHP FUNDS SWITCHED WITH $7.237M IN BGDA AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | NC 73 | NCDOT | US 21 TO NC 115. WIDEN TO MULTI-LANES. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2632AA | [11 empty] | COMPLETE
MECKLENBURG | NC 73 | NCDOT | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 2.67 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-2632AB | Region E | BGDA, NHP, T(M) | 2023 | 8300000 | 2023 | 5100000 | 2026 | 70700000 |  |  | 84100000 | RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | NC 73 | NCDOT | VANCE ROAD EXTENSION/ BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). WIDEN TO MULTI-LANES. | 1.88 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | R-5721B | Region E | BA, T | 2024 | 15401000 | 2024 | 3000000 | 2029 | 59299000 |  |  | 77700000 | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22.
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | WEST OF IDLEWILD ROAD TO I-485. UPGRADE ROADWAY TO EXPRESSWAY WITH EXPRESS LANES AND CONSTRUCT IMPROVEMENTS ON PARALLEL ROUTES. | 6.62 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509
MECKLENBURG | US 74 | NCDOT | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509AA | Statewide Mobility | NHP | 2026 | 85100000 | 2026 | 6500000 | 2031 | 78500000 |  |  | 170100000 | SEGMENTS C1, C2
MECKLENBURG | US 74 | NCDOT | SARDIS ROAD AND SR 3473 (SAM NEWELL ROAD) INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROAD NORTH EXTENSION TO SAM NEWELL ROAD. | 0.59 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509AB | Statewide Mobility | NHP | 2026 | 40700000 | 2026 | 5700000 | 2030 | 76000000 |  |  | 122400000 | SEGMENTS C6, C7A, C8
MECKLENBURG | US 74 | NCDOT | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 0.7 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509AC | Statewide Mobility | NHP | 2030 | 5799000 | 2030 | 3500000 | 2033 | 20000000 |  |  | 29299000 | 0
MECKLENBURG | US 74 | NCDOT | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | 0.23 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509AD | Statewide Mobility | NHP | 2026 | 46800000 | 2026 | 2600000 | 2029 | 35700000 |  |  | 85100000 | SEGMENT C10, C13
MECKLENBURG | US 74 | NCDOT | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | 0.95 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509B | Statewide Mobility | NHP | 2030 | 8499000 | 2030 | 2100000 | 2033 | 75100000 |  |  | 85699000 | SEGMENT M1
MECKLENBURG | US 74 | NCDOT | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | 2.45 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509C | Not Funded | NHP | NOT FUNDED | 39199000 | NOT FUNDED | 5600000 | NOT FUNDED | 70349000 | NOT FUNDED |  | 115148000 | SEGMENT M2
MECKLENBURG | US 74 | NCDOT | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | 3.23 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509D | Not Funded | NHP | NOT FUNDED | 92299000 | NOT FUNDED | 10300000 | NOT FUNDED | 202205000 | NOT FUNDED |  | 304804000 | SEGMENTS C14, M3
MECKLENBURG | US 74 PARALLEL ROUTES | NCDOT | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | 3.39 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509E | Not Funded | T | NOT FUNDED | 43200000 | NOT FUNDED | 3500000 | NOT FUNDED | 61200000 | NOT FUNDED |  | 107900000 | SEGMENTS C3, C4, C5, C7B, C12
MECKLENBURG | INDEPENDENCE POINTE PARKWAY | NCDOT | SARDIS ROAD TO SR 3474 (SAM NEWELL ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.63 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-2509EB | Division 10 | T | 2028 | 1201000 | 2028 | 190000 | 2031 | 12000000 |  |  | 13391000 | SEGMENT C9
MECKLENBURG | NEW ROUTE | NCDOT | SR 3457 (CAMPUS RIDGE ROAD) TO SR 3448 (PLEASANT PLAINS ROAD) IN MATTHEWS. CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 1.1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4713 | [11 empty] | LOCAL FUNDS PROVIDED BY TOWN OF MATTHEWS.
MECKLENBURG | SR 3440 (MCKEE ROAD) EXTENSION | NCDOT | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1010 (EAST JOHN STREET). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 0.75 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4713A | Division 10 | L, T | 2020 | 2680000 | 2021 | 1100000 | 2025 | 15605000 | 2020 | 1155000 | 20540000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CON, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE).
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | 1.01 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714AA | Not Funded | BGANY, T | NOT FUNDED | 19301000 | NOT FUNDED | 1600000 | NOT FUNDED | 30600000 | NOT FUNDED |  | 51501000
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | I-485. IMPROVE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714AB | Division 10 | [10 empty] | LET WITH I-5507
MECKLENBURG | SR 3174 (IDLEWILD ROAD) | NCDOT | SR 3175 (STALLINGS ROAD) TO I-485. WIDEN TO FOUR LANES. | 0.26 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4913A | Division 10 | T | 2025 | 750000 | 2025 | 250000 | 2026 | 18705000 |  |  | 19705000 | BUILD NC BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 6 SALE).
MECKLENBURG | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | NCDOT | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN TO SIX LANES. | 0.75 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5763 | Region E | T | 2030 | 40100000 | 2030 | 5800000 | 2033 | 43000000 |  |  | 88900000
MECKLENBURG | NC 73 (SAM FURR ROAD) | NCDOT | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN TO SIX LANES. | 1.12 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5765 | Region E | T | 2023 | 58430000 | 2023 | 7500000 | 2027 | 53750000 |  |  | 119680000 | COORDINATE WITH R-5721. RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $18M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE);
MECKLENBURG | NC 160 | NCDOT | SOUTH CAROLINA LINE TO I-485. WIDEN TO MULTI-LANES. | 6.8 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5766 | [11 empty] | "O" FUNDS REPRESENT CITY OF CHARLOTTE
MECKLENBURG | NC 160 | NCDOT | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | 2.04 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5766A | Region E | T | 2025 | 26600000 | 2025 | 10700000 | 2030 | 35600000 |  |  | 72900000
MECKLENBURG | NC 160 | NCDOT | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | 4.31 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5766B | Region E | O, T | 2026 | 58200000 | 2026 | 42200000 | 2029 | 137400000 |  |  | 237800000
MECKLENBURG | US 21 (STATESVILLE ROAD) | NCDOT | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | 1.22 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5767 | Region E | T | 2030 | 35700000 | 2030 | 2700000 | 2034 | 44300000 |  |  | 82700000
MECKLENBURG | NC 49 & BACK CREEK CHURCH ROAD | NCDOT | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN TO SIX LANES. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | 2.13 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5768 | Region E | L, T | 2030 | 29400000 | 2030 | 7500000 | 2034 | 80400000 |  |  | 117300000 | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE
MECKLENBURG | US 21 | NCDOT | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO FOUR LANES. | 2.21 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5771 | Region E | BA, L, T, T(DA) | 2022 | 53050000 | 2022 | 1600000 | 2027 | 43185000 |  |  | 97835000 | RIGHT-OF-WAY IN PROGRESS. BL-0080 INCORPORATED INTO U-5771. FUND SWAP OF $2.56M OF TAP-DA FOR $2.56M OF T(DA). NC BUILD BOND $15M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE);
MECKLENBURG | NC 115 (OLD STATESVILLE ROAD) | NCDOT | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | 2.16 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5772 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 85900000 |  |  | 119700000
MECKLENBURG | SR 2940 (EASTWAY DRIVE) | NCDOT | SHAMROCK DRIVE IN CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5803 | Division 10 | BGANY, L(M) | 2025 | 3000000 |  |  | 2026 | 25638000 |  |  | 28638000 | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STBG-ANYAREA FUNDS AS PART OF FUND SWAP.
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | NCDOT | FULLWOOD LANE TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5804
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | NCDOT | FULLWOOD LANE TO FOUR MILE CREEK. WIDEN TO FOUR-LANES. | 0.43 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5804A | [11 empty] | COMPLETE - BY TOWN OF MATTHEWS USING TOWN FUNDS.
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | NCDOT | FOUR MILE CREEK TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | 0.13 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5804B | Division 10 | T |  |  |  |  | 2019 | 1470000 |  |  | 1470000 | COMPLETE. BUILD NC BOND FUNDING: $1.134 M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE).
MECKLENBURG | SR 1009 (MONROE ROAD) | NCDOT | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5805 | Division 10 | BGANY, L(M), T, T(M) | 2020 | 1386000 |  |  | 2025 | 7440000 |  |  | 8826000 | RIGHT-OF-WAY IN PROGRESS. $4.24M IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NCDOT | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. IMPROVE I-85 NORTHBOUND RAMP TO EASTBOUND NC 16. | 0.38 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5955 | Region E
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NCDOT | IMPROVE I-85 NORTHBOUND RAMP TO EASTBOUND NC 16. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5955A | Region E | T |  |  |  |  | 2023 | 3000000 |  |  | 3000000 | UNDER CONSTRUCTION.
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NCDOT | IDAHO DRIVE INTERSECTION. CONVERT INTERSECTION TO AN INTERCHANGE. | 0.38 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5955B | Region E | NHP | 2030 | 4300000 | 2030 | 345000 | 2033 | 12700000 |  |  | 17345000
MECKLENBURG | NC 27 (FREEDOM DRIVE) | NCDOT | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | 1.25 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5957 | Region E | T | 2030 | 15900000 | 2030 | 1750000 | 2033 | 28800000 |  |  | 46450000
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | NCDOT | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | 1.48 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6028 | Division 10 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26300000 |  |  | 48700000
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NCDOT | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | 4.85 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6103 | Statewide Mobility | NHP | 2030 | 12000000 | 2030 | 8100000 | 2033 | 248500000 |  |  | 268600000
MECKLENBURG | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | NCDOT | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTI-LANES. | 2.95 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6109 | Region E | NHP | 2030 | 11900000 | 2030 | 2100000 | 2033 | 52900000 |  |  | 66900000
MECKLENBURG | CHARLOTTE | CHARLOTTE | SR 4979 (BALLANTYNE COMMONS PARKWAY-MCKEE ROAD) AND NC 16 (PROVIDENCE ROAD) IN CHARLOTTE. CONSTRUCT AN ADDITIONAL LEFT TURN LANE ON SR 4979 AND A SECOND LEFT TURN LANE ON SOUTHBOUND NC 16. |  | Highway | Transition | 10 | Charlotte Regional TPO | C-5534 | Exempt | BGDA |  |  |  |  | 2020 | 640000 |  |  | 640000 | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES.
MECKLENBURG | CHARLOTTE | CHARLOTTE | MECKLENBURG COUNTY AIR QUALITY -GRADE (GRANTS TO REPLACE AGING DIESEL ENGINES). REPLACE, REPOWER OR RETROFIT AGING DIESEL VEHICLES AND EQUIPMENT. |  | Highway | Transition | 10 | Charlotte Regional TPO | C-5536 | Exempt | CMAQ |  |  |  |  | 2021 | 139000 |  |  | 139000 | COMPLETE.
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | NCDOT | SR 2480 (SUGAR CREEK ROAD) TO SR 2665 (HARRIS BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 2.37 | Highway | Transition | 10 | Charlotte Regional TPO | U-2507A | Pre-STI (Transition) | [10 empty] | COMPLETE
MECKLENBURG | NEW ROUTE | NCDOT | SR 2467 (MALLARD CREEK ROAD) TO IBM DRIVE. CONSTRUCT NEW CONNECTOR ROAD AND MULTI-USE PATH. |  | Highway | Transition | 10 | Charlotte Regional TPO | U-2507AA | Pre-STI (Transition) | [10 empty] | IMPROVEMENTS CONSTRUCTED UNDER U-2507A
MECKLENBURG | CAMPUS RIDGE ROAD REALIGNMENT | NCDOT | SR 1009 (JOHN STREET) TO SR 3457 (CAMPUS RIDGE ROAD). CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | 1.1 | Highway | Transition | 10 | Charlotte Regional TPO | U-4713B | Pre-STI (Transition) | [10 empty] | COMPLETE
MECKLENBURG | SR 2975 (SUGAR CREEK ROAD) | NCDOT | CONSTRUCT GRADE SEPARATION OVER NORTH CAROLINA RAILROAD/NORFOLK SOUTHERN RAILWAY CROSSING 715 352H AND THE CLOSURE OF CRAIGHEAD ROAD CROSSING 715 355D. |  | Highway | Transition | 10 | Charlotte Regional TPO | U-5008 | [11 empty] | DP ARE FEDERAL RAILROAD ADMINISTRATION (FRA) PRIIA GRANT, NCRR, NSR AND CITY OF CHARLOTTE FUNDS
MECKLENBURG | NORTHCROSS DRIVE EXTENSION | NCDOT | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | 0.97 | Highway | Transition | 10 | Charlotte Regional TPO | U-5108 | Pre-STI (Transition) | BA, BGANY, BGDA, L, T(M) | 2020 | 3500000 |  |  | 2024 | 17642000 | 2020 | 960000 | 22102000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | HUNTERSVILLE | NCDOT | INTERSECTION OF US 21 AND GILEAD ROAD IN HUNTERSVILLE. CONSTRUCT INTERSECTION IMPROVEMENTS, INCLUDING BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Transition | 10 | Charlotte Regional TPO | U-5114 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TA-4710 | Public Transit | 5307, 5339, L, S | [6 empty] | 2021 | 27252000 | 27252000 | "L" REFLECTS CATS CAPITAL PROGRAM
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TA-4711 | Public Transit | 5307, L, S | [6 empty] | 2020 | 11762000 | 11762000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TA-4960 | Public Transit | 5307, L, S | [6 empty] | 2020 | 3279000 | 3279000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE REGIONAL | CHARLOTTE REGIONAL | INNOVATIVE COORDINATED ACCESS AND MOBILITY PILOT PROGRAM VEHICLES |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TA-6706 | Public Transit | 5310, L | [6 empty] | 2020 | 140000 | 140000 | ADD PROJECT TA-6706 TO STIP FOR FY 20. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF CRTPO MPO
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | EXPANSION VANPOOL |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TC-0014 | Public Transit | 5307, L, S | [6 empty] | 2021 | 174000 | 174000 | "L" REFLECTS CATS CAPITAL FUND
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | CITY LYNX GOLD LINE - AMERICAN RESCUE PLAN SMALL STARTS |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TC-0024 | Public Transit | 5309 | [6 empty] | 2022 | 11122000 | 11122000
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM |  | ACQUIRE BATTERY-ELECTRIC BUSES, HYBRID BUSES, BUS CHARGERS, MANAGEMENT SYSTEMS, TRAINING, AND EQUIPMENT. |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TC-0035 | Public Transit | 5339(b), L | [6 empty] | 2024 | 57599000 | 57599000
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TD-4701 | Public Transit | 5307, L, S |  |  |  |  | 2020 | 21961000 |  |  | 21961000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | FACILITY - TRANSIT CENTER - UPGRADES |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TD-4702 | Public Transit | 5307, L, S |  |  |  |  | 2020 | 720000 |  |  | 720000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TE-4901 | Public Transit | 5309, L, S |  |  |  |  | 2020 | 66328000 |  |  | 66328000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | RAPID TRANSIT CORRIDOR STUDIES |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TE-4902 | Public Transit | 5307, FED, L, S |  |  |  |  | 2021 | 200000 |  |  | 200000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | ADD A LIGHT RAIL STATION ON THE LYNX BLUE LINE NEAR IVERSON WAY IN SOUTH CHARLOTTE |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TP-5156 | Public Transit | L | [6 empty] | 2021 | 7582000 | 7582000 | "L" REFLECTS CATS CAPITAL FUND, CITY OF CHARLOTTE CAPITAL FUNDS, PRIVATE DEVELOPER PARTICIPATION.
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TQ-9033 | Public Transit | 5310, L, S | [6 empty] | 2020 | 5292000 | 5292000 | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TS-5107 | Public Transit | 5307, L | [6 empty] | 2020 | 3710000 | 3710000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | NCDOT | STATE OF GOOD REPAIR - BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TW-4901 | Public Transit | 5337, FMOD, L, S | [6 empty] | 2020 | 7854000 | 7854000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | NCDOT | BRIDGE INSPECTIONS AND REPAIRS |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TW-5102A | Public Transit | 5307, L, S |  |  |  |  | 2020 | 1800000 |  |  | 1800000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | NCDOT | FIXED GUIDEWAY MODERNIZATION - BRIDGE INSPECTION & EMERGENCY REPAIRS |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TW-5102B | Public Transit | FMOD, L |  |  |  |  | 2020 | 1160000 |  |  | 1160000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | NCDOT | STATE OF GOOD REPAIR - BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TW-5104B | Public Transit | 5307, 5337, L, S | [6 empty] | 2020 | 13890000 | 13890000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | INSTALL ELECTRIC BUS CHARGERS AT NORTH DAVIDSON AND SOUTH TRYON BUS GARAGES. |  | Public Transportation (Transit) | Locally Selected | 10 | Charlotte Regional TPO | TL-0032 | Exempt | CRPDA, L |  |  |  |  | 2023 | 8183000 |  |  | 8183000
MECKLENBURG | CATS | CHARLOTTE | BALLANTYNE I-485 SERVICE. PURCHASE TWO BATTERY ELECTRIC BUSES. |  | Public Transportation (Transit) | Locally Selected | 10 | Charlotte Regional TPO | TL-0056 | Exempt | CRPDA, L |  |  |  |  | 2026 | 2188000 |  |  | 2188000
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 10 | Charlotte Regional TPO | TO-5137 | Public Transit | SMAP | [6 empty] | 2020 | 75312000 | 75312000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | MECKLENBURG TRANSPORTATION | MECKLENBURG TRANSPORTATION | OPERATING ASSISTANCE FY20-21 (20-LU-051) |  | Public Transportation (Transit) | Miscellaneous/Other | 10 | Charlotte Regional TPO | TO-6159 | Public Transit | 5307, L | [6 empty] | 2020 | 3074000 | 3074000 | ADDING CURRENT YEAR TO THE STIP
MECKLENBURG | MECKLENBURG TRANSPORTATION | MECKLENBURG TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TK-6145 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1020000 | 1020000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE TRANSIT AREA | CHARLOTTE AREA TRANSIT SYSTEM | FIRST MILE-LAST MILE PROJECT WILL PLAN NEW AND REPLACEMENT CIRCULATOR ROUTES WITH A NEW ON-DEMAND STRATEGY OF MICRO-TRANSIT ZONES TO REDUCE TRAVEL TIMES AND IMPROVE CONNECTIVITY TO HIGH-FREQUENCY ROUTES AT MOBILITY HUBS. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0040 | Public Transit | ARP | [6 empty] | 2023 | 750000 | 750000
MECKLENBURG | CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0041 | Public Transit | CMAQ, DP, L |  |  |  |  | 2024 | 85718000 | 2023 | 2708000 | 88426000 | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000.
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0042 | Public Transit | CMAQ, L, S | [6 empty] | 2023 | 2739000 | 2739000
MECKLENBURG | MECKLENBURG TRANSIT SYSTEM |  | CAPITAL COST FOR CONTRACTING RELATED TO DEMAND RESPONSE VENDOR TRIPS, PREVENTATIVE MAINTENANCE EXPENSES AND SECURITY RELATED SOFTWARE. |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0056 | Public Transit | 5307, L | [6 empty] | 2024 | 1243000 | 1243000
MECKLENBURG | CHARLOTTE REGIONAL | CHARLOTTE REGIONAL | OPERATING PROJECTS FOR ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TQ-6597 | Public Transit | 5310, L | [6 empty] | 2020 | 2790000 | 2790000 | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING PROJECT FOR ENHANCED MOBILITY OF SENIORS AND INDIVIDUALS WITH DISABILITIES |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TQ-6957 | Public Transit | 5310, L | [6 empty] | 2020 | 2790000 | 2790000 | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | ADMINISTRATIVE OVERSIGHT FOR 5310 |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TQ-7009 | Public Transit | 5310 | [6 empty] | 2020 | 463000 | 463000 | CORRECTED FUNDING LEVEL TO FY 20-25 FOR THE ADMINISTRATIVE OVERSIGHT OF THE 5310 PROGRAM AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE |  | Public Transportation (Transit) | Planning | 10 | Charlotte Regional TPO | TP-5114 | Public Transit | 5303, L, S | [6 empty] | 2020 | 2598000 | 2598000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE TOD PLANNING IN COOPERATION WITH CATS, CRTPO AND GCLMPO. |  | Public Transportation (Transit) | Planning | 10 | Charlotte Regional TPO | TP-5159 | Public Transit | 5303, L | [6 empty] | 2023 | 507000 | 507000
MECKLENBURG | CATS | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE LIGHT RAIL PROJECT | 28.84 | Public Transportation (Transit) | Planning | 10 | Charlotte Regional TPO | TU-0001 | Public Transit | 5307, L | [6 empty] | 2020 | 50000000 | 50000000
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE BATTERY ELECTRIC BUSES, CHARGING STATIONS, ONSITE TRAINING AND STARTUP SUPPORT AND TESTING |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-0010 | Public Transit | 5339, L | [6 empty] | 2021 | 7448000 | 7448000
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-4726 | Public Transit | 5307, FMOD, L | [6 empty] | 2020 | 17699000 | 17699000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | ROUTINE CAPITAL - SERVICE VEHICLE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-4827 | Public Transit | 5307, L | [6 empty] | 2020 | 2661000 | 2661000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - RAIL |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-5118A | Public Transit | 5337, L, S | [6 empty] | 2020 | 55592000 | 55592000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | LIGHT RAIL VEHICLE OVERHAUL |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-5118B | Public Transit | 5307, 5337, L | [6 empty] | 2020 | 14178000 | 14178000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | CHARLOTTE AREA TRANSIT SYSTEM | PREVENTIVE MAINTENANCE - RAIL, BUS AND FACILITIES |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-5119 | Public Transit | 5307, L | [6 empty] | 2020 | 47589000 | 47589000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | MECKLENBURG TRANSPORTATION | MECKLENBURG TRANSPORTATION | 5307 FUNDING FOR FY20-21 (20-LU-051) |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 10 | Charlotte Regional TPO | TG-6790 | Public Transit | 5307, L | [6 empty] | 2020 | 1580000 | 1580000 | ADDING FFY20-21
MECKLENBURG | MECKLENBURG COUNTY | MECKLENBURG COUNTY | EXPAND PARATRANSIT FLEET BY PURCHASING ADDITIONAL BUSES. |  | Public Transportation (Transit) | STI (Prioritization) | 10 | Charlotte Regional TPO | TA-6673 | Division 10 | O, T | [6 empty] | 2021 | 2500000 | 2500000 | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | CHARLOTTE AREA TRANSIT SYSTEM | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | Public Transportation (Transit) | STI (Prioritization) | 10 | Charlotte Regional TPO | TA-6724 | Division 10 | BGDA, CMAQ, L(M), T(M) | 2022 | 1257000 |  |  | 2023 | 9905000 | 2022 | 1510000 | 12672000 | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS
MECKLENBURG | CHARLOTTE RAILYARD PINEVILLE RAILYARD | NCDOT | GRANTS TO REPLACE AGING DIESEL ENGINES (GRADE). |  | Rail | Locally Selected | 10 | Charlotte Regional TPO | RL-0002 | Exempt | CMAQ, L |  |  |  |  | 2025 | 5450000 |  |  | 5450000
MECKLENBURG | PIEDMONT CORRIDOR | NCDOT | CRISP CHARLOTTE MAINTENANCE FACILITY - TRACK EXTENSION AND SHOP BUILDING |  | Rail | Other | 10 | Charlotte Regional TPO | P-2918F | [11 empty] | IN PROGRESS
MECKLENBURG | P & N CORRIDOR REACTIVATION | NCDOT | THRIFT DEPOT RELOCATION. |  | Rail | Other | 10 | Charlotte Regional TPO | P-5200EA | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | P & N CORRIDOR REACTIVATION | NCDOT | THRIFT DEPOT STABILIZATION. |  | Rail | Other | 10 | Charlotte Regional TPO | P-5200EB | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | SR 2623 (TRAILER DRIVE) | NCDOT | IMPROVE AT-GRADE CROSSING WITH NORFOLK SOUTHERN RAILROAD (CROSSING NUMBER 910 618A, MP O4.11) |  | Rail | Other | 10 | Charlotte Regional TPO | P-5754 | Exempt | O |  |  |  |  | 2022 | 1200000 | 2020 | 50000 | 1250000 | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN
MECKLENBURG | PECAN AVENUE | NCDOT | CSX CROSSING 631391N IN CHARLOTTE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2010D | Division 10 | RR |  |  |  |  | 2026 | 388000 |  |  | 388000
MECKLENBURG | INDUSTRIAL DRIVE | NCDOT | NSR CROSSING 716055T IN PINEVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2010E | Division 10 | RR |  |  |  |  | 2027 | 451000 |  |  | 451000
MECKLENBURG | SR 2940 (EASTWAY DRIVE) | NCDOT | ACWR CROSSING 726797N IN CHARLOTTE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2410B | Division 10 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
MECKLENBURG | SR 2805 (HARRISBURG HIGHWAY) | NCDOT | ACWR CROSSING 726808Y IN CHARLOTTE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2410C | Division 10 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
MECKLENBURG | TIPPERARY PLACE | NCDOT | ACWR CROSSING 726798V IN CHARLOTTE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2410D | Division 10 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
MECKLENBURG | CHARLOTTE | NCDOT | CHARLOTTE GATEWAY STATION. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705 | [11 empty] | DP REPRESENTS FEDERAL PRIIA GRANT AWARD = $2,578,000
MECKLENBURG | CHARLOTTE | NCDOT | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705A | Statewide Mobility | DP, T | 2021 | 500000 |  |  | 2023 | 13000000 |  |  | 13500000 | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | NCDOT | CHARLOTTE GATEWAY STATION - RIGHT-OF-WAY |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705B | Region E | [10 empty] | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | NCDOT | CHARLOTTE GATEWAY STATION - TRACK, STRUCTURE, AND SIGNALS |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705BA | Region E | [10 empty] | UNDER CONSTRUCTION.
MECKLENBURG | CHARLOTTE | NCDOT | CHARLOTTE GATEWAY STATION - PLATFORM AND CANOPY |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5705BB | Region E | [10 empty] | UNDER CONSTRUCTION.
MECKLENBURG | CLANTON ROAD | NCDOT | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5730 | Region E | O, T | 2030 | 13600000 |  |  | 2033 | 28300000 |  |  | 41900000 | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN.
MECKLENBURG, ALAMANCE, CABARRUS, CUMBERLAND, DAVIDSON, GUILFORD, HARNETT, HOKE, IREDELL, ORANGE, UNION | STATEWIDE | NCDOT | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS – CAPITAL PROGRAM |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 6, 7, 8, 9, 10, 12 | Charlotte Regional TPO, Cabarrus-Rowan MPO, Burlington-Graham MPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO | TG-6187 | Public Transit | 5307, L | [6 empty] | 2020 | 2438000 | 2438000
MECKLENBURG, CABARRUS | VARIOUS | NCDOT | I-85, I-77, I-277, I-485, AND US 74. INSTALL WRONG WAY PAVEMENT MARKINGS AND SIGNS. |  | Highway | Safety | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | HS-2010M | Statewide Mobility | HSIP |  |  |  |  | 2024 | 783000 |  |  | 783000
MECKLENBURG, CABARRUS | NC 73 (DAVIDSON HIGHWAY) | NCDOT | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | 2.35 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | R-5706A | Region E | NHP | 2025 | 12000000 | 2025 | 6200000 | 2029 | 53100000 |  |  | 71300000
MECKLENBURG, CABARRUS | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | NCDOT | I-485 TO SR 2894 (CONCORD MILLS BOULEVARD). WIDEN TO SIX LANES. | 0.87 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | U-6032 | Division 10 | T | 2022 | 11500000 | 2022 | 2600000 | 2029 | 49278000 |  |  | 63378000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $15M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
MECKLENBURG, CABARRUS | CHARLOTTE AREA TRANSIT SYSTEM | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE 6 BUSES FOR THE UNIVERSITY TO CONCORD MILLS BUS ROUTE. |  | Public Transportation (Transit) | STI (Prioritization) | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | TA-6672 | Region E | O, T | [6 empty] | 2020 | 3000000 | 3000000 | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS
MECKLENBURG, IREDELL | I-77 | NCDOT | MILE MARKER 11 TO MILE MARKER 20 AND MILE MARKER 24.5 TO MILE MARKER 37. REHABILITATE PAVEMENT. | 21.27 | Highway | Interstate Maintenance | 10, 12 | Charlotte Regional TPO | I-5992 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG, IREDELL | I-77 | NCDOT | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | I-6065 | Exempt | BA, BGDA, T(DA), T(M) | 2025 | 100000 |  |  | 2027 | 45080000 | 2020 | 1820000 | 47000000 | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG, IREDELL, UNION | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | C-5613 | Exempt | CMAQ, L(M) | 2020 | 518000 |  |  | 2020 | 3108000 | 2020 | 1554000 | 5180000 | IN PROGRESS.
MECKLENBURG, LINCOLN | NC 73 | NCDOT | NC 16 IN LINCOLN COUNTY TO SR 5544 (WEST CATAWBA AVENUE) IN MECKLENBURG COUNTY. WIDEN TO MULTI-LANES. | 9.7 | Highway | STI (Prioritization) | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | R-5721 | [11 empty] | COORDINATE WITH U-5765.
MECKLENBURG, UNION, IREDELL | VARIOUS | NCDOT | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. |  | Bike & Ped | Locally Selected | 10, 12 | Charlotte Regional TPO | U-5544 | Division 10, 12 | L, TADA |  |  |  |  | 2024 | 22423000 |  |  | 22423000
MECKLENBURG, UNION, IREDELL | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION. |  | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | HL-0092 | Exempt | CRPDA, L |  |  |  |  | 2024 | 1414000 |  |  | 1414000
MECKLENBURG, UNION, IREDELL | VARIOUS | NCDOT | STBG-DA IN CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO). |  | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | U-4744 | Division 10, 12 | BGDA, L |  |  |  |  | 2024 | 210346000 |  |  | 210346000
MECKLENBURG, UNION, IREDELL | VARIOUS | NCDOT | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. |  | Highway | Locally Selected | 10, 12 | Charlotte Regional TPO | U-4950 | Division 10, 12 | BGDA, L | [6 empty] | 2024 | 17873000 | 17873000 | FORMERLY U-9999C - IN PROGRESS
MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, LINCOLN, NASH, CHATHAM, DAVIE, EDGECOMBE, FRANKLIN, GRANVILLE, HAYWOOD, PERSON, SWAIN | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NCDOT | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. |  | Highway | Other | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban | HO-0009 | Exempt | CMAQ, L(M), O | [6 empty] | 2022 | 1604000 | 1604000 | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS
MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, NASH, DAVIE, EDGECOMBE, GRANVILLE, HAYWOOD | VARIOUS | NCDOT | NCDOT TRAFFIC SYSTEMS OPERATIONS. INSTALL STATEWIDE ITS DEVICE OPERATIONS. |  | Highway | Other | 4, 5, 7, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Winston-Salem Area TPO, Greensboro Urban Area MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Rocky Mount Urban Area MPO, Ker | HO-0005 | Exempt | CMAQ, T(M) |  |  |  |  | 2022 | 21605000 |  |  | 21605000 | UNDER CONSTRUCTION.
MITCHELL | SR 1193 (LEDGER SCHOOL ROAD) | MITCHELL COUNTY | NC 226 TO MITCHELL HIGH SCHOOL. CONSTRUCT SIDEWALK. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 13 | High Country RPO | BN-0016 | Exempt | CRPLT5, HF(M) | 2025 | 10000 |  |  | 2026 | 510000 | 2025 | 180000 | 700000 | HIGHWAY FUNDS ARE CONTIGENCY FUNDS
MITCHELL | SR 1260 | BAKERSVILLE | NORTH OF SR 1278 (BAKERS LANE) TO WILLIS COVE ROAD. CONSTRUCT SIDEWALK. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 13 | High Country RPO | BN-0017 | Exempt | CRPLT5, HF(M) |  |  |  |  | 2025 | 943000 | 2025 | 94000 | 1037000 | HIGHWAY FUNDS ARE CONTIGENCY FUNDS
MITCHELL | SR 1106 (LYNN GAP ROAD) | NCDOT | REPLACE BRIDGE 600207 OVER GRASSY CREEK. | 0.25 | Highway | Bridges | 13 | High Country RPO | B-6013 | Division 13 | BGOFF | 2022 | 40000 |  |  | 2022 | 800000 |  |  | 840000 | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016
MITCHELL | NC 226 | NCDOT | US 19E TO SR 1250 (SNOW CREEK ROAD). UPGRADE GUARDRAIL. | 6.04 | Highway | Safety | 13 | High Country RPO | HS-2013B | Region G | HSIP |  |  |  |  | 2021 | 290000 |  |  | 290000 | COMPLETE
MITCHELL | NC 226 | NCDOT | SR 1250 (SNOW CREEK ROAD) TO NC 261. UPGRADE GUARDRAIL. | 3.36 | Highway | Safety | 13 | High Country RPO | HS-2013D | Region G | HSIP |  |  |  |  | 2021 | 272000 |  |  | 272000 | COMPLETE
MITCHELL | NC 226 | NCDOT | US 19E TO NC 261 NEAR SPRUCE PINE. INSTALL GUARDRAIL. | 9.4 | Highway | Safety | 13 | High Country RPO | HS-2013L | Region G | HSIP |  |  |  |  | 2023 | 590000 |  |  | 590000
MITCHELL | NC 226 | NCDOT | BAKERSVILLE AND SPRUCE PINE. INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 13 | High Country RPO | HS-2413F | Region G | HSIP |  |  |  |  | 2026 | 350000 |  |  | 350000
MITCHELL | MITCHELL COUNTY TRANSPORTATION | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 13 | High Country RPO | TK-6146 | Public Transit | 5311, L, S | [6 empty] | 2020 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
MONTGOMERY | NC 731 (EAST ALLENTON STREET) | MOUNT GILEAD | EXISTING SIDEWALK ON NC 731 TO STANBECK PARK IN MT. GILEAD. CONSTRUCT SIDEWALK. | 0.19 | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-5899 | Division 8 | L, TALT5 |  |  |  |  | 2023 | 277000 |  |  | 277000
MONTGOMERY | NC 134 (NORTH MAIN STREET); SR 1005 (SOUTH MAIN ST | TROY | SR 1323 (OKEEWEMEE ROAD) TO BARNHILL STREET IN TROY. CONSTRUCT SIDEWALKS. | 2.37 | Bike & Ped | Transition | 8 | Piedmont Triad RPO | EB-5521 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF TROY
MONTGOMERY | I-73 / I-74 / US 220 | NCDOT | MONTGOMERY COUNTY LINE TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | 24.5 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5947
MONTGOMERY | I-73/74 | NCDOT | MONTGOMERY COUNTY LINE TO NC 211. PAVEMENT REHABILITATION. | 8.92 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5947A | Statewide Mobility | BGIM |  |  |  |  | 2027 | 19300000 |  |  | 19300000
MONTGOMERY | I-73/74 | NCDOT | NC 211 TO NC 24/27. PAVEMENT REHABILITATION. | 5.05 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5947B | Statewide Mobility | BGIM |  |  |  |  | 2023 | 6900000 |  |  | 6900000 | UNDER CONSTRUCTION - LET WITH I-5946A
MONTGOMERY | I-73/74 | NCDOT | NC 24/27 TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | 10.51 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5947C | Statewide Mobility | BGIM |  |  |  |  | 2028 | 17600000 |  |  | 17600000
MONTGOMERY | NC 24 / NC 27 | NCDOT | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 9.1 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-2527 | Region E | BGLT5, T | 2019 | 854000 |  |  | 2027 | 131500000 | 2019 | 7802000 | 140156000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
MONTGOMERY | NC 109 | NCDOT | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO NC 24 / NC 27. UPGRADE ROADWAY, INCLUDING PAVED SHOULDERS, TURN LANES AND SIGNALS. | 8 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5826
MONTGOMERY | NC 109 | NCDOT | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). |  | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5826A | Not Funded | T | NOT FUNDED | 3700000 | NOT FUNDED | 250000 | NOT FUNDED | 9200000 | NOT FUNDED |  | 13150000
MONTGOMERY | NC 109 | NCDOT | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | 2.61 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5826B | Division 8 | BGLT5, T | 2023 | 438000 | 2024 | 240000 | 2026 | 13200000 |  |  | 13878000 | RIGHT-OF-WAY IN PROGRESS
MONTGOMERY | NC 109 | NCDOT | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. |  | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5826C | Not Funded | T | NOT FUNDED | 3000000 | NOT FUNDED | 299000 | NOT FUNDED | 18000000 | NOT FUNDED |  | 21299000
MONTGOMERY | NC 24 / NC 27 | NCDOT | TROY BYPASS, WEST OF SR 1138 (DAIRY ROAD) TO EAST OF LITTLE RIVER. FOUR LANES, PART ON NEW LOCATION. | 5.42 | Highway | Transition | 8 | Piedmont Triad RPO | R-0623 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
MONTGOMERY | RANDOLPH- MONTGOMERY RESTORE | RANDOLPH- MONTGOMERY RESTORE | PURCHASE 20-FT LIGHT TRANSIT VEHICLES FOR SERVICE EXPANSION. |  | Public Transportation (Transit) | Capital (Non-STI) | 8 | Piedmont Triad RPO | TA-6671 | Region E | [10 empty] | IN ACQUISITION
MONTGOMERY | US 220 ALT (MAIN STREET) | NCDOT | IMPROVEMENTS TO ACWR CROSSING 466027X IN STAR. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Piedmont Triad RPO | RX-2408A | Division 8 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
MONTGOMERY | ELDORADO STREET | NCDOT | IMPROVEMENTS TO ACWR CROSSING 728934A IN TROY. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Piedmont Triad RPO | RX-2408B | Division 8 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
MONTGOMERY, RANDOLPH | REGIONAL COORDINATED AREA TRANSPORTION | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 8 | Piedmont Triad RPO | TK-6156 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1392000 | 1392000 | FUNDS AUTHORIZED IN PROGRESS
MOORE | MOORE COUNTY AIRPORT (SOP) | MOORE COUNTY AIRPORT (SOP) | CONSTRUCT HANGAR TAXIWAYS AND INTERNAL AIRFIELD SERVICE ROAD. |  | Aviation | STI (Prioritization) | 8 | Sandhills MPO | AV-5855 | Division 8 | T |  |  |  |  | 2021 | 2900000 |  |  | 2900000 | UNDER CONSTRUCTION
MOORE | US 1 / US 15 / US 501 (SANDHILLS BOULEVARD) | NCDOT | MAPLE AVENUE IN ABERDEEN. CONSTRUCT MID-BLOCK CROSSWALK, MEDIAN REFUGE ISLAND, AND INSTALL PEDESTRIAN SIGNAL. | 0.26 | Bike & Ped | STI (Prioritization) | 8 | Sandhills MPO | EB-5741 | Division 8 | L, TA50200 |  |  |  |  | 2023 | 312000 |  |  | 312000
MOORE | KNOLL ROAD | SOUTHERN PINES | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 1.44 | Bike & Ped | STI (Prioritization) | 8 | Sandhills MPO | EB-5864 | Division 8 | L, TA50200 |  |  |  |  | 2025 | 3600000 | 2023 | 190000 | 3790000
MOORE | SR 1203 (JOHNSON STREET) | ABERDEEN | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 0.39 | Bike & Ped | STI (Prioritization) | 8 | Sandhills MPO | EB-5869 | Division 8 | L, TA50200 | 2023 | 30000 |  |  | 2026 | 300000 |  |  | 330000
MOORE | SR 2055 (NORTH POPLAR STREET) | ABERDEEN | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 0.36 | Bike & Ped | STI (Prioritization) | 8 | Sandhills MPO | EB-6001 | Division 8 | L, TA50200 | 2024 | 34000 |  |  | 2025 | 340000 | 2023 | 26000 | 400000 | COORDINATE WITH U-5815
MOORE | NC 22 | NCDOT | REPLACE BRIDGE 620062 OVER NICKS CREEK IN CARTHAGE. | 0.25 | Highway | Bridges | 8 | Sandhills MPO | BR-0035 | Region E | NHPB |  |  |  |  | 2022 | 4100000 |  |  | 4100000 | PROJECT WILL BE COMPLETED UNDER THE STATE BRIDGE PROGRAM. PROJECT TO NO LONGER UTILIZE BUILD NC BONDS. UNDER CONSTRUCTION
MOORE | NC 5 | NCDOT | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | Highway | Safety | 8 | Sandhills MPO | HS-2008F | Region E | HSIP, T | 2026 | 500000 | 2027 | 250000 | 2028 | 3550000 |  |  | 4300000
MOORE | US 1 | NCDOT | SR 2026 (YOUNGS ROAD) INTERSECTION. INSTALL REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | Safety | 8 | Central Pines RPO | HS-2408B | Statewide Mobility | HSIP | 2025 | 25000 | 2025 | 25000 | 2026 | 825000 |  |  | 875000
MOORE | SR 2055 (NORTH POPLAR STREET) | NCDOT | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | 0.5 | Highway | Safety | 8 | Sandhills MPO | W-5808C | Division 8 | HSIP | 2021 | 2000 |  |  | 2021 | 15000 |  |  | 17000 | UNDER CONSTRUCTION.
MOORE | NC 211 | NCDOT | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 4.09 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5726 | Region E | T |  |  |  |  | 2025 | 49200000 |  |  | 49200000 | UNDER CONSTRUCTION
MOORE | NC 211 | NCDOT | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). CLEARING, GRUBBING, AND EROSION CONTROL. | 4.09 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5726A | Region E | T |  |  |  |  | 2022 | 5679000 |  |  | 5679000
MOORE | NC 690 (LOBELIA ROAD) | NCDOT | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | 11.75 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5824 | Region E | BGLT5 | 2025 | 1800000 | 2026 | 900000 | 2030 | 12000000 |  |  | 14700000
MOORE | US 15 / US 501 / NC 211 | NCDOT | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 8 | Sandhills MPO | R-5891 | Region E | BG50200 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39400000 |  |  | 44200000
MOORE | NC 5 (BEULAH HILL ROAD) | NCDOT | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | 2.76 | Highway | STI (Prioritization) | 8 | Sandhills MPO | R-5892 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1892000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 43200000 |  |  | 53292000
MOORE | US 15 / US 501 | NCDOT | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | 3.7 | Highway | STI (Prioritization) | 8 | Sandhills MPO, Central Pines RPO | R-5927 | Division 8 | T | 2027 | 1300000 | 2027 | 3900000 | 2031 | 48100000 |  |  | 53300000
MOORE | NC 24 / NC 27 | NCDOT | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | 0.5 | Highway | STI (Prioritization) | 8 | Central Pines RPO | R-5929 | Division 8 | T | 2026 | 280000 | 2026 | 280000 | 2028 | 4800000 |  |  | 5360000 | COORDINATE WITH U-3628
MOORE | NC 24 / NC 27 | NCDOT | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 1.35 | Highway | STI (Prioritization) | 8 | Central Pines RPO | U-3628 | Region E | NHP, T | 2023 | 2275000 |  |  | 2025 | 6900000 |  |  | 9175000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929
MOORE | NC 5 | NCDOT | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO FOUR LANE DIVIDED FACILITY FROM US 1 TO LINDEN ROAD AND A THREE LANE FACITILTY FROM LINDEN ROAD TO TROTTER DRIVE. | 3.94 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5756 | Region E | T | 2023 | 8600000 | 2023 | 13200000 | 2025 | 119700000 |  |  | 141500000 | RIGHT-OF-WAY IN PROGRESS
MOORE | US 15 / US 501 / NC 211 | NCDOT | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 1.24 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5814 | Region E | T | 2023 | 11500000 | 2023 | 1250000 |  |  |  |  | 12750000 | RIGHT-OF-WAY IN PROGRESS; CONSTRUCTION COMBINED WITH U-5815B - SEE U--5815B FOR FUNDING.
MOORE | US 1 (SANDHILLS BOULEVARD) | NCDOT | SR 1112 (ROSELAND ROAD) IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | 2.9 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5815 | Region E
MOORE | US 1 (SANDHILLS BOULEVARD) | NCDOT | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | 0.58 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5815A | Region E | BGANY | 2025 | 4700000 | 2025 | 3200000 | 2027 | 12700000 |  |  | 20600000
MOORE | US 1 (SANDHILLS BOULEVARD) | NCDOT | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US 1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | 2.36 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5815B | Region E | T | 2023 | 6650000 |  |  | 2025 | 154300000 |  |  | 160950000 | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION INCLUDES U-5814.
MOORE | US 1 (SANDHILLS BOULEVARD) | NCDOT | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. RELOCATE WATER TRANSMISSION LINE. | 2.36 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5815BA | Region E | T |  |  |  |  | 2023 | 17900000 |  |  | 17900000 | UNDER CONSTRUCTION
MOORE | US 15 / US 501 | NCDOT | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 (PAGE ROAD) IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | 2.3 | Highway | STI (Prioritization) | 8 | Sandhills MPO | U-5976 | Division 8 | T | 2027 | 25800000 | 2027 | 970000 | 2031 | 51100000 |  |  | 77870000
MOORE | MOORE COUNTY | MOORE COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 8 | Central Pines RPO, Sandhills MPO | TK-6147 | Public Transit | 5311, L, S | [6 empty] | 2020 | 964000 | 964000 | FUNDS AUTHORIZED IN PROGRESS
MOORE | LS (SOUTH STREET) | NCDOT | ACWR CROSSING 722526U IN ABERDEEN. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Sandhills MPO | RX-2008B | Division 8 | RR |  |  |  |  | 2025 | 1832000 |  |  | 1832000
MOORE, HOKE, LEE | VARIOUS | NCDOT | VARIOUS NHS AND PRIMARY ROUTES IN DIVISION 8, DISTRICT 2. UPGRADE GUARDRAIL. |  | Highway | Safety | 8 | Central Pines RPO, Lumber River RPO, Sandhills MPO | HS-2008B | Region E | HSIP |  |  |  |  | 2021 | 250000 |  |  | 250000 | UNDER CONSTRUCTION
NASH | ROCKY MOUNT | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 2.27 | Bike & Ped | Locally Selected | 4 | Rocky Mount Urban Area MPO | C-5549 | Exempt | CMAQ, CRPDA, L(M) | 2025 | 200000 |  |  | 2026 | 1373000 |  |  | 1573000
NASH | US 64 BUSINESS (SUNSET AVENUE) | ROCKY MOUNT | SR 1836 (MAY DRIVE) TO US 301 BUSINESS, NORTH BOUND (CHURCH STREET). INSTALL PEDESTRIAN SIGNALS. | 1.7 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5711 | Division 4 | L(M), TA50200 |  |  |  |  | 2024 | 580000 |  |  | 580000
NASH | US 301 BUSINESS (CHURCH STREET) | ROCKY MOUNT | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 1.69 | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5761 | Division 4 | L, TA50200, TA5200 | 2025 | 1600000 |  |  | 2026 | 6000000 | 2023 | 200000 | 7800000
NASH | US 64 BUSINESS (THOMAS STREET) | ROCKY MOUNT | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. |  | Bike & Ped | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | EB-5905 | Division 4 | BG50200, L(M) |  |  |  |  | 2027 | 1400000 |  |  | 1400000
NASH | NC 581 | NCDOT | REPLACE BRIDGE 630091 OVER TAR RIVER. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5947 | Region A | NHPB | 2021 | 400000 | 2021 | 138000 | 2023 | 7162000 |  |  | 7700000 | UNDER CONSTRUCTION.
NASH | SR 1522 (HALIFAX ROAD) | NCDOT | REPLACE BRIDGE 630203 OVER I-95. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5980 | Statewide Mobility | NHPB | 2020 | 2100000 |  |  | 2021 | 18000000 |  |  | 20100000 | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039.
NASH | NC 33 | NCDOT | REPLACE BRIDGE 630041 OVER I-95. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0036 | Highway Fund | HFB |  |  |  |  | 2021 | 4700000 |  |  | 4700000 | UNDER CONSTRUCTION.
NASH | SR 1510 | NCDOT | REPLACE BRIDGE 630224 OVER I-95. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0039 | Highway Fund | HFB |  |  |  |  | 2021 | 5200000 |  |  | 5200000 | UNDER CONSTRUCTION.
NASH | SR 1403 (COOPER ROAD) | NCDOT | REPLACE BRIDGE 630080 OVER GIDEON SWAMP. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | BR-0116 | Highway Fund | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION.
NASH | SR 1745 (BEND OF THE RIVER ROAD) | NCDOT | REPLACE BRIDGE 630110 OVER TAR RIVER RESERVOIR. | 0.25 | Highway | Bridges | 4 | Rocky Mount Urban Area MPO | HB-0038 | Division 4 | BGOFF | 2026 | 80000 |  |  | 2027 | 6500000 |  |  | 6580000
NASH | I-95 | NCDOT | SR 1770 (SUNSET AVENUE) (MILE MARKER 137.4) TO SR 1544 (NORTH HALIFAX ROAD) (MILE MARKER 142.1). PAVEMENT AND BRIDGE REHABILITATION. | 3.92 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | I-5934 | Statewide Mobility | NHPIM |  |  |  |  | 2026 | 9000000 |  |  | 9000000
NASH | US 64 (FUTURE I-87) | NCDOT | SR 1306 (SOUTH OLD FRANKLIN ROAD) TO SR 1603 (OLD CARRIAGE ROAD). PAVEMENT REHABILITATION. | 11.12 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | I-6045 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2023 | 16660000 |  |  | 16660000 | UNDER CONSTRUCTION.
NASH | US 64 (FUTURE I-87) | NCDOT | BRIDGE REHABILITATION FOR 630072 AND 630074. |  | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | I-6045A | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 520000 |  |  | 520000 | UNDER CONSTRUCTION.
NASH | US 64 | NCDOT | US 64 BUSINESS (SUNSET AVENUE) AT RIVER DRIVE/LAKE DRIVE IN ROCKY MOUNT. CONSTRUCT PEDESTRIAN CROSSING INCLUDING REFUGE ISLAND, SIDEWALK, RECTANGULAR RAPID-FLASHING BEACONS, AND CONVERSION OF FULL MOVEMENT MEDIAN OPENING TO LEFT-OVER INTO LAKE DRIVE AND REVERSING ONE-WAY TRAFFIC FLOW ON RIVER DRIVE. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004AA | Region A | HSIP |  |  |  |  | 2025 | 215000 |  |  | 215000
NASH | NC 97 | NCDOT | INSTALL LEFT TURN LANE AT NC 97 AND SR 1603 (OLD CARRIAGE ROAD). | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004B | Region A | HSIP | 2022 | 86000 |  |  | 2022 | 205000 |  |  | 291000 | UNDER CONSTRUCTION.
NASH | SR 1001 (OLD BAILEY HIGHWAY) | NCDOT | INSTALL ALL WAY STOP AT SR 1001 (OLD BAILEY HIGHWAY) AND SR 1717 (MACEDONIA ROAD / SANDY CROSS ROAD). | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004H | Division 4 | HSIP |  |  |  |  | 2022 | 25000 |  |  | 25000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004G.
NASH | NC 48 | NCDOT | INSTALL MINI ROUNDABOUTS ALONG NC 48 (GOLDROCK ROAD) AT WATERLOO DRIVE / ROUNDTREE DRIVE AND AT GREYSON ROAD / CUNNINGHAM DRIVE. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004M | Region A | HSIP |  |  |  |  | 2023 | 441000 |  |  | 441000 | UNDER CONSTRUCTION.
NASH | SR 1700 (OAK LEVEL ROAD) | NCDOT | SR 1700 (OAK LEVEL ROAD) AT SR 1603 (OLD CARRIAGE ROAD). REVISE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 4 | Rocky Mount Urban Area MPO | HS-2004N | Division 4 | HSIP |  |  |  |  | 2023 | 351000 |  |  | 351000 | UNDER CONSTRUCTION.
NASH | US 64 | NCDOT | US 64 AT BRIDGES 630019 AND 630020 OVER TAR RIVER. PAVEMENT IMPROVEMENTS. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004Q | Region A | HSIP |  |  |  |  | 2023 | 900000 |  |  | 900000 | UNDER CONSTRUCTION.
NASH | VARIOUS | NCDOT | SECONDARY ROADS IN NASH COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | HS-2404E | Division 4
NASH | NC 43 | NCDOT | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | 0.75 | Highway | Safety | 4 | Upper Coastal Plain RPO | W-5804B | Region A | HSIP | 2023 | 45000 |  |  | 2023 | 892000 |  |  | 937000 | UNDER CONSTRUCTION.
NASH | SR 1770 (EASTERN AVENUE) | NCDOT | SR 1003 (RED OAK ROAD) TO SR 1603 (OLD CARRIAGE ROAD) IN ROCKY MOUNT. WIDEN TO MULTI-LANES. | 2.41 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | R-5720 | Division 4 | T | 2020 | 12252000 | 2020 | 1470000 |  |  |  |  | 13722000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTION FUNDS SHOWN UNDER U-5026.
NASH | NC 43 | NCDOT | SR 1613 (WOODRUFF AVENUE) TO I-95. WIDEN TO MULTI-LANES. | 0.61 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-2561 | Division 4
NASH | NC 43 | NCDOT | SR 1613 (WOODRUFF AVENUE) TO I-95. | 1.65 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-2561C | Division 4 | BGLT5 | 2026 | 4400000 | 2026 | 3100000 | 2028 | 13600000 |  |  | 21100000
NASH | I-95 | NCDOT | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | 1 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-5026 | Division 4 | L, T | 2020 | 34686000 | 2020 | 336000 | 2020 | 87636000 |  |  | 122658000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $20,595,497.59 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
NASH | NC 48 | NCDOT | NC 4 INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.42 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-5911 | Division 4 | BGANY | 2025 | 30000 | 2025 | 360000 | 2027 | 3900000 |  |  | 4290000
NASH | NC 43 (BENVENUE ROAD) | NCDOT | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | 1 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-5947 | Region A | T | 2022 | 80000 | 2022 | 800000 | 2022 | 5725000 |  |  | 6605000 | UNDER CONSTRUCTION.
NASH | SR 1603 (OLD CARRIAGE ROAD) | NCDOT | WIDEN TO FOUR LANES FROM GREEN HILLS ROAD THROUGH US 64 BRIDGE. WIDEN TO THREE LANES FROM SOUTH OF US 64 BRIDGE TO SR 1770 (EASTERN AVENUE). | 1.33 | Highway | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | U-5996 | Division 4 | T | 2020 | 529000 |  |  | 2022 | 23940000 |  |  | 24469000 | UNDER CONSTRUCTION.
NASH | ROCKY MOUNT | ROCKY MOUNT | BENVENUE ROAD (NC 43/NC 48) AT JEFFREYS ROAD. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Transition | 4 | Rocky Mount Urban Area MPO | C-5546 | Exempt | CMAQ |  |  |  |  | 2025 | 130000 |  |  | 130000
NASH | TAR RIVER TRANSIT | TAR RIVER TRANSIT | ENLARGE DRIVERS BREAKROOM |  | Public Transportation (Transit) | STI (Prioritization) | 4 | Rocky Mount Urban Area MPO | TD-5281 | Division 4 | T | [6 empty] | 2025 | 15000 | 15000
NASH, EDGECOMBE, WILSON | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE ROCKY MOUNT PLANNING ORGANIZATION. |  | Highway | Locally Selected | 4 | Rocky Mount Urban Area MPO | HL-0106 | Exempt | BGANY, CRPDA, L |  |  |  |  | 2023 | 1306000 |  |  | 1306000
NASH, HALIFAX | NC 43 | NCDOT | NC 43 FROM 0.5 MILES NORTH OF SR 1425 (CASTALIA ROAD) IN NASH COUNTY TO NC 561 IN HALIFAX COUNTY. INSTALL RUMBLE STRIPS. | 13.51 | Highway | Safety | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | HS-2004X | Region A | HSIP |  |  |  |  | 2024 | 2474000 |  |  | 2474000 | UNDER CONSTRUCTION.
NASH, WAKE, JOHNSTON | US 264 | NCDOT | US 264 FROM THE US 64 / US 264 SPLIT TO THE WILSON COUNTY LINE. PAVEMENT REHABILITATION. | 14.27 | Highway | Interstate Maintenance | 4, 5 | Upper Coastal Plain RPO, Capital Area MPO | HI-0013 | Statewide Mobility | NHPIM |  |  |  |  | 2027 | 16500000 |  |  | 16500000
NASH, WILSON | NC 58 | NCDOT | NC 58 FROM NORTHERN STATONSBURG TOWN LIMITS TO 0.3 MILES NORTH OF SR 1622 (EVANSDALE ROAD) IN WILSON COUNTY. NC 58 FROM SOUTH OF SR 1314 (THOMPSON CHAPEL CHURCH ROAD) IN WILSON COUNTY TO SOUTHERN NASHVILLE TOWN LIMIT IN NASH COUNTY. NC 58 FROM SOUTH OF SR 1004 (TAYLORS STORE ROAD) TO SOUTHERN CASTALIA TOWN LIMIT IN NASH COUNTY. INSTALL RUMBLE STRIPS WITH SIX-INCH PAVEMENT MARKINGS. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | HS-2004U | Region A | HSIP |  |  |  |  | 2024 | 2474000 |  |  | 2474000 | UNDER CONSTRUCTION.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | TAXIWAY IMPROVEMENTS. |  | Aviation | STI (Prioritization) | 3 | Wilmington Urban Area MPO | AV-5798 | Statewide Mobility | O, T |  |  |  |  | 2028 | 5600000 |  |  | 5600000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | EXPANSION OF AIR CARRIER APRON. |  | Aviation | STI (Prioritization) | 3 | Wilmington Urban Area MPO | AV-5801 | Statewide Mobility | O, T |  |  |  |  | 2021 | 3940000 |  |  | 3940000 | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL AIRPORT (ILM) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. |  | Aviation | STI (Prioritization) | 3 | Wilmington Urban Area MPO | AV-5885 | Statewide Mobility | O, T |  |  |  |  | 2027 | 7500000 |  |  | 7500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | VARIOUS | NEW HANOVER COUNTY | MIDDLE SOUND LOOP CONNECTOR CONSTRUCTION AND PORTERS NECK WALMART CONNECTOR. CONSTRUCT MULTI-USE PATH. |  | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0040 | Division 3 | BGDA, L(M) |  |  |  |  | 2025 | 692000 |  |  | 692000
NEW HANOVER | WILMINGTON | WILMINGTON | WILMINGTON RAIL TRAIL. CONSTRUCT MULTI-USE PATH FROM 3RD STREET IN DOWNTOWN WILMINGTON TO THE LOVE GROVE BRIDGE MULTI-USE PATH FACILITY. | 1.36 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0045 | Division 3 | BGDACV | [6 empty] | 2022 | 680000 | 680000
NEW HANOVER | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | KURE BEACH | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 0.2 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0059 | Division 3 | BGDACV, L(M), TADA | 2025 | 53000 |  |  | 2025 | 302000 | 2023 | 57000 | 412000
NEW HANOVER | WRIGHTSVILLE BEACH | WRIGHTSVILLE BEACH | INSTALLATION OF ON-STREET BICYCLE LANES AND PEDESTRIAN CROSSWALKS ALONG US 76 (CAUSEWAY DRIVE) AND US 74 (WEST SALISBURY STREET) IN WRIGHTSVILLE BEACH. | 2.1 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0075 | Division 3 | BGDA, L |  |  |  |  | 2024 | 2291000 | 2024 | 10000 | 2301000
NEW HANOVER | US 117 (COLLEGE ROAD) | BELVILLE | SR 2048 (GORDON ROAD) TO SR 2206 (NORTHCHASE PARKWAY). CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 2.5 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0118 | Division 3 | BGDA, L | 2025 | 513000 |  |  | 2026 | 1787000 |  |  | 2300000
NEW HANOVER | SR 1403 (MIDDLE SOUND LOOP) | New Hanover County | CONSTRUCT MULTI-USE PATH SOUTH OF MARKET STREET FROM RED CEDAR ROAD TO EXISTING TRAIL AT CORNER OF MARKET STREET AND MIDDLE SOUND LOOP ROAD. | 6.73 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6027 | Division 3 | L | 2021 | 500000 |  |  | 2025 | 1000000 |  |  | 1500000 | RIGHT OF WAY IN PROGRESS.
NEW HANOVER | WILMINGTON | WILMINGTON | CONSTRUCT SIGNALIZED PEDESTRIAN CROSSING AT US 17 BUSINESS (MARKET STREET) AND 21ST STREET. | 0 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6028 | Division 3 | L, TADA |  |  |  |  | 2023 | 164000 |  |  | 164000 | UNDER CONSTRUCTION
NEW HANOVER | CAROLINA BEACH | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | EB-6039 | Division 3 | BGDA, L, TADA | 2025 | 60000 |  |  | 2025 | 1231000 | 2021 | 747000 | 2038000
NEW HANOVER | SR 1219 (SOUTH 17TH STREET) | WILMINGTON | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | Bike & Ped | STI (Prioritization) | 3 | Wilmington Urban Area MPO | EB-5600 | Division 3 | BGANY, BGDA, L(M) | 2024 | 30000 |  |  | 2025 | 3738000 | 2022 | 150000 | 3918000 | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON.
NEW HANOVER | US 76 AND US 74 | NCDOT | REPLACE BRIDGES 640021, 640022, AND 640024 IN NEW HANOVER COUNTY. | 0.9 | Highway | Bridges | 3 | Wilmington Urban Area MPO | HB-0040 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
NEW HANOVER | NEW ROUTE | NCDOT | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. | 0.61 | Highway | Economic Development | 3 | Wilmington Urban Area MPO | U-5926 | Division 3 | L, T | 2024 | 840000 | 2024 | 344000 |  |  |  |  | 1184000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SALVATION ARMY/AAI. CONSTRUCTION IS BEING ACCOMPLISHED UNDER U-4434.
NEW HANOVER | I-140 | NCDOT | US 421 TO I-40. PAVEMENT AND BRIDGE REHABILITATION. | 6.79 | Highway | Interstate Maintenance | 3 | Wilmington Urban Area MPO | I-6037 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 7300000 |  |  | 7300000
NEW HANOVER | WILMINGTON | WILMINGTON | CONSTRUCT A NEW NORTH GATE ON NORTH CAROLINA PORTS AUTHORITY PROPERTY. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0040 | Division 3 | BGDA, L | [6 empty] | 2022 | 313000 | 313000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY.
NEW HANOVER | SOUTH 3RD STREET | WILMINGTON | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 0.5 | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0109 | Division 3 | BGDA, L | 2025 | 61000 |  |  | 2025 | 664000 | 2024 | 489000 | 1214000
NEW HANOVER | SOUTH 3RD STREET | WILMINGTON | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0110 | Division 3 | BGDA, HF | 2025 | 296000 |  |  | 2025 | 274000 | 2023 | 69000 | 639000 | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY.
NEW HANOVER | GREENVILLE AVENUE | NCDOT | SR 1411 (WRIGHTSVILLE AVENUE) TO HINTON AVENUE IN WILMINGTON. REALIGN INTERSECTION AND CONSTRUCT BIKE LANES AND SIDEWALK ALONG GREENVILLE AVENUE. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534C | Division 3 | BGDA |  |  |  |  | 2025 | 861000 |  |  | 861000
NEW HANOVER | HOOKER ROAD | NCDOT | SR 1411 (WRIGHTSVILLE AVENUE) TO MALLARD DRIVE / ROSE AVENUE INTERSECTION IN WILMINGTON. CONSTRUCT A 10 FOOT MULTI-USE PATH. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534G | Division 3 | BGDA |  |  |  |  | 2025 | 1916000 |  |  | 1916000
NEW HANOVER | HINTON AVENUE | NCDOT | PARK AVENUE TO GREENVILLE AVENUE IN WILMINGTON. CONSTRUCT A 10 FOOT MULTI-USE PATH. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534H | Division 3 | BGDA |  |  |  |  | 2025 | 786000 |  |  | 786000
NEW HANOVER | CAROLINA BEACH | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | 0.5 | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-6233 | Division 3 | BGDA, HF | 2022 | 40000 |  |  | 2024 | 256000 | 2021 | 18000 | 314000 | RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS.
NEW HANOVER | WILMINGTON | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-6235 | Division 3 | BGDA, L(M) |  |  |  |  | 2025 | 1030000 | 2020 | 487000 | 1517000
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | WEST OF US 421 NORTH OF WILMINGTON TO WEST OF NC 133. | 3.6 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633CA | [11 empty] | COMPLETED.
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | WEST OF NC 133 TO US 117. | 3.544 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633CB | [11 empty] | COMPLETED.
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NCDOT | US 117 TO EAST OF I-40 SOUTH OF CASTLE HAYNE. | 0.85 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633CC | [11 empty] | COMPLETED.
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | SR 1272 (NEW CENTRE DRIVE) TO MARTIN LUTHER KING JR., BOULEVARD. | 0.089 | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | U-4902A | [11 empty] | COMPLETED.
NEW HANOVER | SR 1217 (17TH STREET) | NCDOT | INSTALL NEAR SIDE SIGNAL HEADS ON PEDESTAL ON BOTH SIDES OF SR 1217 (17TH STREET) AT DOCK STREET IN WILMINGTON. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003A | Division 3 | HSIP |  |  |  |  | 2025 | 34000 |  |  | 34000
NEW HANOVER | US 117/NC 132 (COLLEGE ROAD) | NCDOT | AT CREWS DRIVE. UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AD | Region B | HSIP |  |  |  |  | 2024 | 123000 |  |  | 123000
NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) | NCDOT | AT SR 1411 (WRIGHTSVILLE AVENUE) IN WILMINGTON. INSTALL CROSSWALKS AND PEDESTRIAN COUNTDOWN HEADS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AE | Statewide Mobility | HSIP |  |  |  |  | 2024 | 110000 |  |  | 110000
NEW HANOVER | US 117/NC 132 (COLLEGE ROAD) | NCDOT | AT SR 2160 (LONG RIDGE ROAD). INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AI | Region B | HSIP |  |  |  |  | 2025 | 575000 |  |  | 575000
NEW HANOVER | SR 1301 (PRINCESS PLACE DRIVE) | NCDOT | AT NORTH 30TH STREET IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND PAVEMENT MARKINGS, AND INSTALL PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AK | Division 3 | HSIP | 2024 | 15000 |  |  | 2025 | 151000 |  |  | 166000
NEW HANOVER | US 17/76 (DAWSON STREET AND WOOSTER STREET) | NCDOT | AT SR 1216 (16TH STREET) AND SR 1217 (17TH STREET) IN WILMINGTON. UPGRADE TRAFFIC SIGNALS, AND INSTALL CROSSWALKS AND PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AN | Region B | HSIP |  |  |  |  | 2025 | 147000 |  |  | 147000
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | AT SR 2048 (GORDON ROAD)/SR 1327 (FARLEY DRIVE). UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AO | Division 3 | HSIP |  |  |  |  | 2024 | 33000 |  |  | 33000
NEW HANOVER | SR 1302 (23RD STREET) | NCDOT | AT SR 1301 (PRINCESS PLACE DRIVE) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AP | Region B | HSIP |  |  |  |  | 2025 | 195000 |  |  | 195000
NEW HANOVER | SR 2817 (17TH STREET) | NCDOT | AT CASTLE STREET IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND SIGNS, AND INSTALL PEDESTRIAN SIGNALS AND CURB BUMP OUTS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003AQ | Division 3 | HSIP |  |  |  |  | 2025 | 141000 |  |  | 141000
NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) | NCDOT | US 117 / NC 132 (COLLEGE ROAD) AT LAKE AVENUE-HUGH MCRAE PARK IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003H | Statewide Mobility | HSIP |  |  |  |  | 2025 | 66000 |  |  | 66000
NEW HANOVER | US 17 (OLEANDER DRIVE) | NCDOT | US 17 (OLEANDER DRIVE) AT 42ND STREET IN WILMINGTON. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003J | Statewide Mobility | HSIP |  |  |  |  | 2025 | 59000 |  |  | 59000
NEW HANOVER | US 74 WESTBOUND ON-RAMP | NCDOT | US 74 WESTBOUND ON-RAMP AND SR 1627 (3RD STREET / MARTIN LUTHER KING JUNIOR BOULEVARD) IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003K | Statewide Mobility | HSIP |  |  |  |  | 2025 | 16000 |  |  | 16000
NEW HANOVER | US 17-76 (OLEANDER DRIVE) | NCDOT | US 17-76 (OLEANDER DRIVE) AND SR 1421 (GREENVILLE LOOP ROAD) / GREENVILLE AVENUE IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003L | Region B | HSIP |  |  |  |  | 2025 | 84000 |  |  | 84000
NEW HANOVER | US 117 (SHIPYARD BOULEVARD) | NCDOT | US 117 (SHIPYARD BOULEVARD) AT CONVERSE ROAD / LONGSTREET DRIVE IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND ADD PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003P | Statewide Mobility | HSIP | 2025 | 30000 |  |  | 2026 | 271000 |  |  | 301000
NEW HANOVER | US 17 (DAWSON STREET) | NCDOT | US 17 (DAWSON STREET) AT US 421 (3RD STREET) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL, UPGRADE PAVEMENT MARKINGS, AND ADD PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003Q | Region B | HSIP |  |  |  |  | 2026 | 184000 |  |  | 184000
NEW HANOVER | US 421 | NCDOT | US 421 AT SR 1573 (DOW ROAD) IN CAROLINA BEACH. UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003R | Region B | HSIP |  |  |  |  | 2026 | 23000 |  |  | 23000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | US 17 BUSINESS (MARKET STREET) AND SR 1272 (NEW CENTRE DRIVE). INSTALL CROSSWALKS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003S | Region B | HSIP | 2025 | 58000 |  |  | 2026 | 114000 |  |  | 172000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | US 17 BUSINESS (MARKET STREET) AT SR 2219 (GREEN MEADOWS DRIVE) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003T | Statewide Mobility | HSIP |  |  |  |  | 2026 | 32000 |  |  | 32000
NEW HANOVER | SR 2048 (GORDON ROAD) | NCDOT | SR 2048 (GORDON ROAD) JUST WEST OF I-40. INSTALL SIX INCH PAVEMENT MARKINGS. |  | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003U | Division 3 | HSIP |  |  |  |  | 2023 | 37000 |  |  | 37000 | UNDER CONSTRUCTION.
NEW HANOVER | US 17/76 (OLEANDER DRIVE) | NCDOT | US 17/76 (OLEANDER DRIVE) AT SR 1209 (INDEPENDENCE BOULEVARD) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003V | Statewide Mobility | HSIP | 2025 | 30000 |  |  | 2026 | 23000 |  |  | 53000
NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) | NCDOT | AT SR 2313 (WILSHIRE BOULEVARD) IN WILMINGTON. INSTALL PEDESTRIAN COUNTDOWN HEADS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003Y | Statewide Mobility | HSIP |  |  |  |  | 2026 | 63000 |  |  | 63000
NEW HANOVER | US 17/76 (WOOSTER STREET) | NCDOT | AT SR 1217 (17TH STREET) IN WILMINGTON. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN COUNTDOWN HEADS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2003Z | Region B | HSIP |  |  |  |  | 2026 | 114000 |  |  | 114000
NEW HANOVER | SR 1216 (16TH STREET); SR 1217 (17TH STREET) | NCDOT | QUEEN STREET AND CASTLE STREET INTERSECTIONS; QUEEN STREET INTERSECTION IN WILMINGTON. INSTALL CROSSWALKS AND OTHER PEDESTRIAN IMPROVEMENTS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403A | Division 3 | HSIP |  |  |  |  | 2025 | 403000 |  |  | 403000
NEW HANOVER | US 17/76 (OLEANDER DRIVE) | NCDOT | AT COUNTRY CLUB ROAD IN WILMINGTON. INSTALL NEAR SIDE SIGNAL HEAD AND UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403G | Region B | HSIP |  |  |  |  | 2025 | 36000 |  |  | 36000
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NCDOT | US 421 (CAROLINA BEACH ROAD) FROM US 117 / NC 132 (COLLEGE ROAD) TO NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | 0.71 | Highway | Safety | 3 | Wilmington Urban Area MPO | W-5703C | Region B | BGDA, HSIP, L, L(M), T | 2023 | 600000 | 2023 | 127000 | 2025 | 4278000 |  |  | 5005000 | RIGHT-OF-WAY IN PROGRESS. BG-DA FUNDS USED FOR CONSTRUCTION OF MULTI-USE PATH EXTENSION FOR MONKEY JUNCTION PEDESTRIAN IMPROVEMENT PROJECT.
NEW HANOVER | US 74 | NCDOT | US 74 (EASTWOOD ROAD) AT US 17 (MILITARY CUTOFF ROAD), AND US 74 (EASTWOOD ROAD) AT CAVALIER DRIVE IN WILMINGTON. UPGRADE PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | W-5803A | Region B | HSIP |  |  |  |  | 2023 | 170000 |  |  | 170000 | UNDER CONSTRUCTION.
NEW HANOVER | US 17/76/421 | NCDOT | REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. TOLL PROJECT. | 0.8 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | HB-0039 | Statewide Mobility | BOND R, DP, NHP | 2029 | 48515000 | 2029 | 3688000 | 2029 | 530595000 |  |  | 582798000 | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2033-2047.
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. WIDEN TO MULTI-LANES. | 3.2 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-3338
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | SR 1175 (KERR AVENUE) INTERCHANGE AT US 74 (MARTIN LUTHER KING, JR. PARKWAY). | 1 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-3338C | Region B | BGANY |  |  |  |  | 2030 | 39600000 |  |  | 39600000 | RIGHT-OF-WAY IN PROGRESS.
NEW HANOVER | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | NCDOT | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 1.81 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4434 | Division 3 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 88702000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 288800000 |  |  | 379802000
NEW HANOVER | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | NCDOT | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | 3.61 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4751 | Statewide Mobility | T | 2009 | 355000 |  |  | 2018 | 85750000 | 2021 | 14850000 | 100955000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
NEW HANOVER | LENDIRE ROAD | NCDOT | LENDIRE ROAD, WEST OF US 17 BUSINESS (MARKET STREET) TO US 17 BUSINESS (MARKET STREET)/SR 1403 (MIDDLE SOUND LOOP ROAD). REALIGN ROADWAY. | 0.31 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4751A | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION.
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | COLONIAL DRIVE TO SR 1402 (PORTERS NECK ROAD). ACCESS MANAGEMENT IMPROVEMENTS. | 8.6 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4902
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | 1.4 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4902B | Not Funded | T | NOT FUNDED | 10000000 | NOT FUNDED | 2900000 | NOT FUNDED | 9700000 | NOT FUNDED |  | 22600000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | 2.19 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4902C | Statewide Mobility | T | 2030 | 50357000 | 2030 | 5862000 | 2033 | 112900000 |  |  | 169119000 | INCLUDES U-5880.
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NCDOT | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | 1.66 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-4902D | Statewide Mobility | T |  |  |  |  | 2019 | 27609000 | 2021 | 4290000 | 31899000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
NEW HANOVER | NC 132 (COLLEGE ROAD) | NCDOT | SR 1272 (NEW CENTRE DRIVE) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 9.7 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5702
NEW HANOVER | NC 132 (COLLEGE ROAD) | NCDOT | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 2.64 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5702A | Statewide Mobility | NHP | 2030 | 56100000 | 2030 | 13900000 | 2033 | 24500000 |  |  | 94500000 | PLANNING/DESIGN IN PROGRESS.
NEW HANOVER | NC 132 (COLLEGE ROAD) | NCDOT | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | 4.23 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5702B | Not Funded | NHP | NOT FUNDED | 30600000 | NOT FUNDED | 15000000 | NOT FUNDED | 50400000 | NOT FUNDED |  | 96000000
NEW HANOVER | US 74 (EASTWOOD ROAD) | NCDOT | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5710 | Statewide Mobility | NHP | 2023 | 16900000 | 2025 | 4000000 | 2026 | 60500000 |  |  | 81400000 | RIGHT-OF-WAY IN PROGRESS.
NEW HANOVER | NEW LOCATION | NCDOT | FROM SR 1409 (MILITARY CUTOFF ROAD) AT DRYSDALE DRIVE TO US 74 (EASTWOOD ROAD). ROADWAY ON NEW LOCATION. | 0.3 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5710A | Statewide Mobility | BGANY, T | 2019 | 2575000 |  |  | 2022 | 8200000 |  |  | 10775000 | UNDER CONSTRUCTION.
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NCDOT | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 1.6 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5729
NEW HANOVER | US 421 | NCDOT | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | 1.54 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5729REG | Region B | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18480000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6560000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28640000 |  |  | 53680000
NEW HANOVER | US 421 | NCDOT | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5729SW | Statewide Mobility | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4620000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1640000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7160000 |  |  | 13420000
NEW HANOVER | US 74 | NCDOT | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5731 | Statewide Mobility | BGLT5 | 2028 | 6099000 | 2028 | 540000 | 2030 | 48200000 |  |  | 54839000
NEW HANOVER | US 421 (SOUTH FRONT STREET) | NCDOT | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | 0.99 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5734 | Region B | BGANY | 2025 | 35799000 | 2025 | 3200000 | 2029 | 37500000 |  |  | 76499000
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NCDOT | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | 1.03 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5790 | Division 3 | T | 2027 | 12500000 | 2027 | 3200000 | 2029 | 39300000 |  |  | 55000000
NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) | NCDOT | US 17 BUSINESS (MARKET STREET) TO SR 2048 (GORDON ROAD). UPGRADE ROADWAY. | 1.9 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5792 | Division 3 | T | 2026 | 29100000 | 2026 | 2800000 | 2029 | 202050000 |  |  | 233950000 | BUILD NC BOND FUNDING: $30,000,000 FOR CONSTRUCTION PAYBACK 2030 - 2044 (YR 10 / 2030 SALE).
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | NCDOT | NORTH 23RD STREET. CONSTRUCT ROUNDABOUT. | 1 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5954 | Region B | BGANY | 2025 | 970000 | 2025 | 600000 | 2027 | 5799000 |  |  | 7369000
NEW HANOVER | US 76 (OLEANDER DRIVE) | NCDOT | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-6128 | Region B | BGANY | 2027 | 3700000 | 2027 | 600000 | 2030 | 6800000 |  |  | 11100000
NEW HANOVER | WILMINGTON | NCDOT | WILMINGTON CITYWIDE SIGNAL SYSTEM. | 39.2 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-6199 | Division 3 | T | 2028 | 10000 | 2028 | 1100000 | 2030 | 15500000 |  |  | 16610000
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.3 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-6201 | Division 3 | T | 2028 | 6300000 | 2028 | 1200000 | 2030 | 7400000 |  |  | 14900000
NEW HANOVER | SR 2048 (GORDON ROAD) | NCDOT | US 17 BUSINESS (MARKET STREET) TO I-40. WIDEN TO FOUR LANES. | 2.49 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-6202 | Division 3 | T | 2022 | 17835000 | 2024 | 6651000 | 2025 | 73685000 |  |  | 98171000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE); $13,000,000 FOR CONSTRUCTION PAYBACK 2025-2039 (FY 2025 / YR 5 SALE), $15,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 S.
NEW HANOVER | SR 1175 (KERR AVENUE) | NCDOT | RANDALL PARKWAY TO US 74 (MARTIN LUTHER KING, JR. PARKWAY). | 1.49 | Highway | Transition | 3 | Wilmington Urban Area MPO | U-3338B | Pre-STI (Transition) | [10 empty] | COMPLETED.
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TA-5221 | Public Transit | 5307, L, S | [6 empty] | 2020 | 365000 | 365000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TA-5222 | Public Transit | 5309, 5339, L, S | [6 empty] | 2020 | 1301000 | 1301000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TA-5223 | Public Transit | 5339, L, S | [6 empty] | 2020 | 3234000 | 3234000
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT TROLLEY |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TA-5224 | Public Transit | 5339 | [6 empty] | 2020 | 700000 | 700000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TC-0027 | Public Transit | 5309, 5339, BGDA, L | [6 empty] | 2023 | 664000 | 664000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY |  | SUPPORT VEHICLES AND EQUIPMENT: ACQUIRE OR REPLACE VEHICLES, EQUIPMENT, AND ELECTRONICS THAT SUPPORT THE OPERATION OF FIXED ROUTE BUS AND PARATRANSIT SERVICES AND PASSENGER FACILITIES. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TM-0050 | Public Transit | 5309, L | [6 empty] | 2024 | 311000 | 311000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TP-5110 | Public Transit | 5307, L, S | [6 empty] | 2023 | 190000 | 190000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | MOBILITY MANAGER PROVIDES OVERSIGHT AND MANAGEMENT OF SECTION 5310 FUNDS AND ADMINISTERS THE PROGRAMS AND PROJECTS SUPPORTED BY THESE FUNDS. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TQ-8019 | Public Transit | 5310, L | [6 empty] | 2023 | 371000 | 371000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECTS FULFILLS THE ALLOCATION FOR NON-TRADITIONAL TRANSPORTATION PROJECTS AS DEFINED IN THE GRANT. THE PROJECT SUPPORTS THE COMMUNITY GRANT OFFERING TO NON-PROFITS AND GOVERNMENTAL ORGANIZAIONS TO REMOVE TRANSPORTATION BARRIERS AND CONNECT ELDERS AND INDIVIDUALS WITH DISABILITIES TO NEEDED RESOURCES. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TQ-9001 | Public Transit | 5310, L | [6 empty] | 2022 | 568000 | 568000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Wilmington Urban Area MPO | TS-5103 | Public Transit | 5307, L | [6 empty] | 2020 | 96000 | 96000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADA |  | Public Transportation (Transit) | Locally Selected | 3 | Wilmington Urban Area MPO | TA-6700 | Division 3 | BGDA, L |  |  |  |  | 2020 | 180000 |  |  | 180000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Locally Selected | 3 | Wilmington Urban Area MPO | TG-6784 | Division 3 | BGDA, L |  |  |  |  | 2020 | 420000 |  |  | 420000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPITAL IMPROVEMENT PROJECT TO SECURE AUTOMATIC PASSENGER COUNTER (APC) TECHNOLOGY FOR THE PURPOSE OF COLLECTING STOP LEVEL BOARDINGS AND ALIGHTINGS FOR FIXED ROUTE PUBLIC TRANSPORTATION SERVICES. |  | Public Transportation (Transit) | Locally Selected | 3 | Wilmington Urban Area MPO | TL-0017 | Division 3 | BGDA, L | [6 empty] | 2022 | 200000 | 200000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 3 | Wilmington Urban Area MPO | TO-4751 | Public Transit | 5307, L, SMAP | [6 empty] | 2022 | 17437000 | 17437000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Wilmington Urban Area MPO | TK-6176 | Public Transit | 5311, L, S | [6 empty] | 2020 | 872000 | 872000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT PROVIDES OPERATING SUPPORT FOR FIXED BUS ROUTE 205 LONG LEAF PARK WHICH SERVICES NOVANT HOSPITAL AND THE MEDICAL CENTER. THIS ROUTE CARRIES A HIGH CONCENTRATION OF INDIVIDUALS WITH DISABILITIES AS IDENTIFIED THROUGH AN EXTENSIVE ONBOARD SURVEY EFFORT CONDUCTED IN FY17. A SURVEY EFFORT IS SLATED FOR FY23. |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Wilmington Urban Area MPO | TQ-6513 | Public Transit | 5310, L | [6 empty] | 2023 | 866000 | 866000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT IS FOR ADMINISTRATIVE SUPPORT REQUIRED TO EFFECTVELY MANAGE THE SECTION 5310 PROGRAM AND ANNUAL FUNDING ALLOCATION FROM FTA. |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Wilmington Urban Area MPO | TQ-7005 | Public Transit | 5310 | [6 empty] | 2021 | 180000 | 180000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Planning | 3 | Wilmington Urban Area MPO | TP-5111 | Public Transit | 5303, L, S | [6 empty] | 2020 | 1648000 | 1648000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY |  | BUS FACILITIES CAPITAL IMPROVEMENTS - ACQUIRE OR REPLACE EQUIPMENT AND SUSTEMS IN THE WAVE TRANSIT OPERATIONS AND MAINTENANCE FACILITY. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-0020 | Public Transit | 5309, L | [6 empty] | 2024 | 239000 | 239000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PURCHASE CNG BUSES. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-0026 | Public Transit | 5339(b), L | [6 empty] | 2025 | 3432000 | 3432000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE PREVENTATIVE MAINTENACE PROJECT WILL ENSURE THE FTA FUNDED ASSESTS ARE MAINTAINED TO THE FTA STATE OF GOOD REPAIR REQUIREMENTS AND THAT SERVICE CONTINUES WITHOUT DISRUPTION. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-5243 | Public Transit | 5307, L | [6 empty] | 2023 | 1125000 | 1125000
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Wilmington Urban Area MPO | TG-5245 | Public Transit | 5307, L | [6 empty] | 2020 | 2464000 | 2464000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS |  | Public Transportation (Transit) | STI (Prioritization) | 3 | Wilmington Urban Area MPO | TG-6177 | Public Transit | 5307, L, T |  |  |  |  | 2023 | 66000 |  |  | 66000
NEW HANOVER | CSX SE LINE | NCDOT | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. |  | Rail | STI (Prioritization) | 3 | Wilmington Urban Area MPO | P-5740B | Statewide Mobility | DP, T | 2023 | 2600000 |  |  | 2025 | 4350000 |  |  | 6950000 | RIGHT-OF-WAY IN PROGRESS.
NEW HANOVER, BRUNSWICK | I-140/US 17 WILMINGTON BYPASS | NCDOT | SR 1430 (CEDAR HILL ROAD) TO WEST OF US 421 NORTH OF WILMINGTON. |  | Highway | Pre-STI (Historic) | 3 | Wilmington Urban Area MPO | R-2633BB | Pre-STI (Transition) | NHP |  |  |  |  | 2013 | 51250000 |  |  | 51250000 | COMPLETED. GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK 2013 - 2024.
NEW HANOVER, BRUNSWICK | CSX SE LINE | CSXT RR | WILMINGTON BELTLINE SPEED IMPROVEMENT PROJECT. | 13 | Rail | STI (Prioritization) | 3 | Wilmington Urban Area MPO | P-5740 | Statewide Mobility | [10 empty] | DP FUNDS REPRESENT FEDERAL CRISI GRANT.
NEW HANOVER, BRUNSWICK | CSX SE LINE | WILMINGTON | TIE AND RAIL REHABILITATION, CURVE REALIGNMENT, AND UPGRADE RAIL BRIDGES. |  | Rail | STI (Prioritization) | 3 | Wilmington Urban Area MPO | P-5740A | Statewide Mobility | DP, T |  |  |  |  | 2023 | 33000000 |  |  | 33000000 | UNDER CONSTRUCTION.
NEW HANOVER, BRUNSWICK | CSX SE LINE | WILMINGTON | INSTALLATION OF RAILROAD GRADE CROSSING SIGNALS AND GATES AT VARIOUS AT-GRADE CROSSINGS. |  | Rail | STI (Prioritization) | 3 | Wilmington Urban Area MPO | P-5740C | Statewide Mobility | DP, T |  |  |  |  | 2025 | 9900000 |  |  | 9900000
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | WILMINGTON URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. |  | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | U-5527 | Division 3 | TADA |  |  |  |  | 2022 | 17206000 |  |  | 17206000 | IN PROGRESS.
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WILMINGTON PLANNING ORGANIZATION. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | HL-0107 | Exempt | CRPDA, L |  |  |  |  | 2023 | 4363000 |  |  | 4363000
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5525 | Division 3 | BGDA, L | [6 empty] | 2020 | 19840000 | 19840000
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5534 | Division 3 | BGANY, BGDA, BGDACV, L, L(M) | 2022 | 220000 | 2024 | 420000 | 2020 | 15260000 |  |  | 15900000 | IN PROGRESS
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | NCDOT | WILMINGTON URBAN METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | Highway | Locally Selected | 3 | Wilmington Urban Area MPO | U-5989 | Division 3 | BGANY, BGDA |  |  |  |  | 2022 | 105116000 |  |  | 105116000
NEW HANOVER, PENDER | I-40 | NCDOT | I-40 FROM END I-40 (MILE MARKER 420) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | 11.88 | Highway | Interstate Maintenance | 3 | Wilmington Urban Area MPO | I-6039 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2023 | 23004000 |  |  | 23004000 | UNDER CONSTRUCTION.
NEW HANOVER, PENDER | SR 1336 (SIDBURY ROAD) | NCDOT | SR 1318 (BLUE CLAY ROAD) TO US 17 NORTH OF WILMINGTON. INSTALL CENTERLINE AND SHOULDER SINUSOIDAL RUMBLE STRIPS WITH BICYCLE PATTERN. | 7.2 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403D | Division 3 | HSIP |  |  |  |  | 2025 | 421000 |  |  | 421000
NEW HANOVER, PENDER | US 17 (HAMPSTEAD BYPASS) | NCDOT | US 17 BYPASS SOUTH OF HAMPSTEAD TO US 17 NORTH OF HAMPSTEAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 12.3 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | R-3300
NORTHAMPTON | NC 186 | NCDOT | GARYSBURG TO THE VIRGINIA STATE LINE, EXCLUDING THE SEABOARD TOWN LIMITS. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | Highway | Safety | 1 | Peanut Belt RPO | HS-2401E | Region A | HSIP |  |  |  |  | 2025 | 500000 |  |  | 500000
NORTHAMPTON | US 158/NC 46 | NCDOT | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. WIDEN TO MULTI-LANES WITH BYPASS OF JACKSON, SOME NEW LOCATION. | 15.2 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-2582
NORTHAMPTON | US 158/NC 46 | NCDOT | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 7.94 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-2582A | Division 1 | T | 2020 | 3345000 |  |  | 2020 | 106809000 | 2020 | 8820000 | 118974000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
NORTHAMPTON | US 158/NC 46 | NCDOT | SR 1312 (ST. JOHN CHURCH ROAD) TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. | 7.4 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-2582B | Not Funded | T | NOT FUNDED | 5400000 | NOT FUNDED |  | NOT FUNDED | 61400000 | NOT FUNDED |  | 66800000
NORTHAMPTON | NC 46 | NCDOT | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 10.41 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5739 | Division 1 | T | 2022 | 5065000 | 2022 | 2300000 | 2025 | 39499000 |  |  | 46864000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE).
NORTHAMPTON | NC 305 | NCDOT | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | 24.3 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5757 | Division 1 | BGLT5 | 2023 | 3200000 | 2024 | 4122000 |  |  |  |  | 7322000 | RIGHT-OF-WAY IN PROGRESS.
NORTHAMPTON | NC 305 | NCDOT | HERTFORD COUNTY LINE TO NORTH OF SR 1503 (LASKER ROAD). UPGRADE ROADWAY. | 10.33 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5757A | Division 1 | BGLT5 |  |  |  |  | 2026 | 25600000 |  |  | 25600000
NORTHAMPTON | NC 305 | NCDOT | NORTH OF SR 1503 (LASKER ROAD) TO SEABOARD TOWN LIMITS. UPGRADE ROADWAY. | 13.97 | Highway | STI (Prioritization) | 1 | Peanut Belt RPO | R-5757B | Division 1 | BGLT5 |  |  |  |  | 2026 | 29100000 |  |  | 29100000
NORTHAMPTON, CHOWAN, GATES, TYRRELL | US 64; US 158; NC 32 | NCDOT | VARIOUS LOCATIONS. INSTALL RUMBLE STRIPES AND SNOW PLOWABLE PAVEMENT MARKERS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO | HS-2401Q | Region A | HSIP |  |  |  |  | 2025 | 1950000 |  |  | 1950000
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ALBERT J. ELLIS AIRPORT (OAJ) | DESIGN AND CONSTRUCT RUNWAY 23 HOLDING APRON. |  | Aviation | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | AV-5733 | Region B | O, T |  |  |  |  | 2022 | 750000 |  |  | 750000 | UNDER CONSTRUCTION.
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR ROADWAY RELOCATION, RPZ AND RUNWAY EXTENSION. |  | Aviation | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | AV-5804 | Region B | O, T | 2023 | 697000 | [6 empty] | 697000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS.
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR RUNWAY EXTENSION AND ROADWAY RELOCATION. |  | Aviation | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | AV-5805 | Region B | O, T | 2024 | 361000 | [6 empty] | 361000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS.
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. |  | Aviation | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | AV-5806 | Region B | O, T |  |  |  |  | 2026 | 12880000 | 2025 | 300000 | 13180000 | OTHER FUNDS ARE AIRPORT FUNDS
ONSLOW | SR 1308 (GUM BRANCH ROAD) | JACKSONVILLE | CONSTRUCT PEDESTRIAN IMPROVEMENTS ALONG GUM BRANCH ROAD FROM ONSVILLE DRIVE TO ONSVILLE DRIVE. | 1.49 | Bike & Ped | Locally Selected | 3 | Jacksonville Urban Area MPO | BL-0073 | Exempt | CRPDA, L(M) | [6 empty] | 2024 | 320000 | 320000
ONSLOW | DOWNTOWN GREENWAY | JACKSONVILLE | CHANEY AVENUE TO WARDOLA DRIVE IN JACKSONVILLE. CONSTRUCT MULTI-USE PATH. | 0.58 | Bike & Ped | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | EB-6012 | Division 3 | L, TA50200 |  |  |  |  | 2022 | 1367000 |  |  | 1367000 | UNDER CONSTRUCTION.
ONSLOW | SR 1509 (QUEENS CREEK ROAD) | NCDOT | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | 0.25 | Highway | Bridges | 3 | Jacksonville Urban Area MPO | B-5944 | Division 3 | BFP | 2028 | 500000 | 2028 | 1200000 | 2030 | 30100000 |  |  | 31800000
ONSLOW | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE JACKSONVILLE PLANNING ORGANIZATION. |  | Highway | Locally Selected | 3 | Jacksonville Urban Area MPO | HL-0102 | Exempt | CRPDA, L |  |  |  |  | 2023 | 2902000 |  |  | 2902000
ONSLOW | US 17 | NCDOT | MULTI-LANE SECTION NORTH OF JACKSONVILLE TO SOUTH OF BELGRADE. | 6.17 | Highway | Pre-STI (Historic) | 3 | Jacksonville Urban Area MPO | R-2514A | Pre-STI (Transition) | [10 empty] | COMPLETED.
ONSLOW | SR 1702 (WEST HUFF DRIVE) | NCDOT | SR 1308 (BELL FORK ROAD) TO EAST OF SR 1470 (WESTERN BOULEVARD). | 1.4 | Highway | Pre-STI (Historic) | 3 | Jacksonville Urban Area MPO | U-4007A | [11 empty] | COMPLETED.
ONSLOW | JACKSONVILLE PARKWAY | NCDOT | COUNTRY CLUB ROAD TO SR 1470 (WESTERN BOULEVARD). | 0 | Highway | Pre-STI (Historic) | 3 | Jacksonville Urban Area MPO | U-4007B | [11 empty] | COMPLETED.
ONSLOW | SR 1308 (BELL FORK ROAD) | NCDOT | AT BRYNN MARR ROAD. UPGRADE TRAFFIC SIGNAL, SIGNING, AND PAVEMENT MARKINGS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AA | Division 3 | HSIP | 2024 | 126000 |  |  | 2025 | 246000 |  |  | 372000
ONSLOW | SR 1428 (RIGGS ROAD) | NCDOT | FROM NAUTICAL WAVE ROAD TO SR 1744 (HUBERT BOULEVARD). INSTALL PAVEMENT MARKINGS. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AB | Division 3 | HSIP |  |  |  |  | 2024 | 53000 |  |  | 53000
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | NCDOT | AT SR 1308 (GUM BRANCH ROAD / BELL FORK ROAD) IN JACKSONVILLE. UPDATE / INSTALL TRAFFIC SIGNAL, PAVEMENT MARKINGS, CURB RAMPS, AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AF | Region B | HSIP |  |  |  |  | 2025 | 82000 |  |  | 82000
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | NCDOT | AT SR 1336 (ONSLOW DRIVE) IN JACKSONVILLE. UPDATE / INSTALL TRAFFIC SIGNAL, PAVEMENT MARKINGS, AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AG | Region B | HSIP |  |  |  |  | 2025 | 144000 |  |  | 144000
ONSLOW | US 17 (MARINE BOULEVARD) | NCDOT | AT US 17 BUSINESS (MARINE BOULEVARD) AND HENDERSON DRIVE IN JACKSONVILLE. UPGRADE TRAFFIC SIGNAL AND PAVEMENT MARKINGS, AND INSTALL PEDESTRIAN IMPROVEMENTS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AJ | Region B | HSIP | 2025 | 51000 |  |  | 2025 | 159000 |  |  | 210000
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | AT FORUM ROAD/MARTY GOLDMAN WAY IN JACKSONVILLE. INSTALL CROSSWALKS AND PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AM | Region B | HSIP |  |  |  |  | 2025 | 178000 |  |  | 178000
ONSLOW | NC 24 | NCDOT | AT SR 1445 (NORRIS ROAD) IN SWANSBORO. INSTALL CROSSWALKS, RAMPS, PEDESTRIAN SIGNALS, AND 100 FEET OF SIDEWALK. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003AT | Region B | HSIP | 2025 | 125000 |  |  | 2025 | 325000 |  |  | 450000
ONSLOW | NC 24 | NCDOT | AT SR 1514 (PHILLIPS LOOP ROAD) IN SWANSBORO. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNALS AND ADVANCE FLASHERS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2003X | Statewide Mobility | HSIP | 2026 | 184000 |  |  | 2026 | 202000 |  |  | 386000
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | AT CAROLINA FOREST BOULEVARD AND NORTH PLAIN ROAD IN JACKSONVILLE. INSTALL NEAR SIDE SIGNAL HEADS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403F | Region B | HSIP |  |  |  |  | 2025 | 35000 |  |  | 35000
ONSLOW | US 17 BUSINESS (NORTH MARINE BOULEVARD) | NCDOT | AT MCDANIEL DRIVE AND WORKSHOP LANE IN JACKSONVILLE. INSTALL NEAR SIDE SIGNAL HEADS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403H | Region B | HSIP |  |  |  |  | 2025 | 23000 |  |  | 23000
ONSLOW | NC 172 | NCDOT | AT SR 1500 (STARLING ROAD) NEAR HUBERT. INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403I | Region B | HSIP | 2026 | 10000 | 2026 | 2000 | 2026 | 378000 |  |  | 390000
ONSLOW | SR 1403 (COUNTRY CLUB ROAD) | NCDOT | AT ACADEMIC DRIVE IN JACKSONVILLE. INSTALL TRAFFIC SIGNAL, PEDESTRIAN SIGNALS, AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | HS-2403J | Division 3 | HSIP | 2026 | 10000 | 2026 | 2000 | 2026 | 505000 |  |  | 517000
ONSLOW | VARIOUS | NCDOT | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5203REG | Region B
ONSLOW | NC 172 | NCDOT | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | 3.74 | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5602 | Region B | T |  |  |  |  | 2019 | 12183000 |  |  | 12183000 | COMPLETE. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
ONSLOW | US 17 BUSINESS | NCDOT | US 17 BUSINESS (MARINE BOULEVARD) AND SR 1402 (OLD BRIDGE STREET). UPGRADE TRAFFIC SIGNAL, PAVEMENT MARKINGS, AND IMPROVE SIGHT DISTANCE. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5803C | Region B | HSIP |  |  |  |  | 2023 | 85000 |  |  | 85000 | UNDER CONSTRUCTION.
ONSLOW | NC 24 | NCDOT | NC 24 (WEST CORBETT AVENUE) AND SR 1512 (OLD HAMMOCKS ROAD). UPGRADE PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5803D | Statewide Mobility | HSIP |  |  |  |  | 2022 | 17000 |  |  | 17000 | COMPLETED.
ONSLOW | NC 53 | NCDOT | NC 53 (WESTERN BOULEVARD) AND CENTER STREET / LIBERTY DRIVE. UPGRADE TRAFFIC SIGNAL AND ADD ADDITIONAL SPEED LIMIT SIGNS. | 0.5 | Highway | Safety | 3 | Jacksonville Urban Area MPO | W-5803E | Region B | HSIP |  |  |  |  | 2022 | 57000 |  |  | 57000 | COMPLETED.
ONSLOW | NC 24 (WEST CORBETT AVENUE) | NCDOT | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.91 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | R-5885 | Not Funded | NHP | NOT FUNDED | 61900000 | NOT FUNDED | 5200000 | NOT FUNDED | 47400000 | NOT FUNDED |  | 114500000
ONSLOW | NC 24 (WEST CORBETT AVENUE) | NCDOT | REPLACE CULVERT EAST OF WEST SHORE DRIVE. |  | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | R-5885A | Region B | NHP | 2025 | 115000 | 2025 | 84000 | 2027 | 1500000 |  |  | 1699000
ONSLOW | US 17 | NCDOT | US 17 BUSINESS TO SR 1326 (DRUMMER KELLUM ROAD) IN JACKSONVILLE. ADD ADDITIONAL LANES AND CONSTRUCT ROUTES ON NEW LOCATION. | 1.4 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-4007
ONSLOW | US 17 | NCDOT | WESTERN BOULEVARD TO FAIRWAY DRIVE. | 0 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-4007C | Not Funded | NHP | NOT FUNDED | 34775000 | NOT FUNDED |  | NOT FUNDED | 26300000 | NOT FUNDED |  | 61075000
ONSLOW | US 17 | NCDOT | FAIRWAY DRIVE TO DRUMMER KELLUM ROAD. | 0 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-4007D | Not Funded | NHP | NOT FUNDED | 32345000 | NOT FUNDED |  | NOT FUNDED | 16600000 | NOT FUNDED |  | 48945000
ONSLOW | NC 53 | NCDOT | FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | 0.7 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-4007E | Statewide Mobility | BG50200 | 2028 | 8899000 | 2028 | 420000 | 2031 | 12601000 |  |  | 21920000 | COMBINED WITH U-5736.
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NCDOT | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5508 | Statewide Mobility | BG50200 | 2028 | 1100000 | 2028 | 280000 | 2030 | 3100000 |  |  | 4480000
ONSLOW | NC 24 | NCDOT | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5716 | Statewide Mobility | T | 2028 | 42556000 | 2028 | 2900000 | 2031 | 49599000 |  |  | 95055000 | PROJECT BEING LET WITH U-5739.
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | NCDOT | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5728 | Region B | BG50200, T | 2024 | 590000 |  |  | 2026 | 6500000 |  |  | 7090000 | RIGHT-OF-WAY IN PROGRESS.
ONSLOW | US 17 (WILMINGTON HIGHWAY) | NCDOT | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | 1 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5735 | Region B | BG50200 | 2028 | 38102000 | 2028 | 6300000 | 2032 | 96000000 |  |  | 140402000
ONSLOW | US 17 (WILMINGTON HIGHWAY) | NCDOT | ROADWAY IMPROVEMENTS TO DOUGLAS GATE ENTRANCE. |  | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5735A | Exempt | O |  |  |  |  | 2021 | 1075000 |  |  | 1075000 | COMPLETED. OTHER FUNDS REPRESENT DEPARTMENT OF DEFENSE FUNDS.
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 2.55 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5736 | Region B | BG50200 | 2028 | 16099000 | 2028 | 1600000 | 2031 | 54700000 |  |  | 72399000 | COMBINED WITH U-4007E.
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | NCDOT | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.16 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5739 | Region B | T | 2028 | 2599000 | 2028 | 3200000 | 2031 | 31600000 |  |  | 37399000 | PROJECT BEING LET WITH WITH U-5716.
ONSLOW | SR 2715 (TRADE STREET) | NCDOT | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.28 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5787 | Division 3 | T | 2026 | 2599000 | 2026 | 890000 | 2029 | 7600000 |  |  | 11089000
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5789 | Region B | BG50200 |  |  |  |  | 2025 | 8000000 |  |  | 8000000 | RIGHT-OF-WAY IN PROGRESS.
ONSLOW | SR 2714 (JACKSONVILLE PARKWAY EXTENSION) | NCDOT | NC 53 (WESTERN BOULEVARD) TO US 17 (NEW BERN HIGHWAY). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | 3.83 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5791 | Division 3
ONSLOW | SR 2714 (JACKSONVILLE PARKWAY) | NCDOT | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | 1.55 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5791A | Division 3 | T | 2027 | 16300000 | 2027 | 1200000 | 2029 | 81500000 |  |  | 99000000 | PLANNING/DESIGN IN PROGRESS.
ONSLOW | SR 2714 (JACKSONVILLE PARKWAY) | NCDOT | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). |  | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5791B | Not Funded | T | NOT FUNDED | 15500000 | NOT FUNDED | 4100000 | NOT FUNDED | 34800000 | NOT FUNDED |  | 54400000
ONSLOW | COMMERCE DRIVE EXTENSION | NCDOT | COMMERCE DRIVE TO SR 1406 (PINEY GREEN ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | 0.24 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5878 | Division 3 | T |  |  |  |  | 2022 | 3698000 |  |  | 3698000 | UNDER CONSTRUCTION.
ONSLOW | SR 1336 (HENDERSON ROAD) | NCDOT | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO REDUCED CONFLICT INTERSECTIONS. | 1.13 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5903 | Division 3 | T | 2028 | 6600000 | 2028 | 4200000 | 2030 | 38500000 |  |  | 49300000
ONSLOW | NC 210 | NCDOT | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | 5.76 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5949 | Region B | T | 2030 | 28700000 | 2030 | 15400000 | 2034 | 115400000 |  |  | 159500000
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | NCDOT | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5950 | Region B | BG50200 | 2025 | 100000 | 2025 | 200000 | 2027 | 1500000 |  |  | 1800000
ONSLOW | US 17 | NCDOT | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | 1 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-5951 | Region B | BG50200 | 2027 | 350000 | 2027 | 80000 | 2029 | 24000000 |  |  | 24430000
ONSLOW | US 17 | NCDOT | NC 172 (SNEADS FERRY ROAD) AND SR 1518 (OLD FOLKSTONE ROAD) INTERSECTIONS. CONSTRUCT REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-6065 | Statewide Mobility | BGLT5, HSIP |  |  |  |  | 2028 | 2200000 |  |  | 2200000
ONSLOW | SR 1308 (BELL FORK ROAD) | NCDOT | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | 1 | Highway | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | U-6082 | Division 3 | BG50200 | 2025 | 2800000 | 2025 | 870000 | 2028 | 10500000 |  |  | 14170000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | NCDOT | WEST OF SR 1313 (MILLS FIELDS ROAD) TO EAST OF SR 1324 (RAMSEY ROAD) IN JACKSONVILLE. MODERNIZE ROADWAY, PROVIDE PAVED SHOULDERS, AND INTERSECTION IMPROVEMENTS. | 7.42 | Highway | Transition | 3 | Jacksonville Urban Area MPO | U-4906 | Pre-STI (Transition) | BGANY |  |  |  |  | 2021 | 16095000 |  |  | 16095000 | UNDER CONSTRUCTION.
ONSLOW | NC 53 (WESTERN BOULEVARD) | NCDOT | NC 53 (WESTERN BOULEVARD) AT SR 1336 (HENDERSON DRIVE). INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Transition | 3 | Jacksonville Urban Area MPO | W-5203U | Region B | HF(M), HSIP |  |  | 2023 | 61000 | 2023 | 2363000 |  |  | 2424000 | UNDER CONSTRUCTION.
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TA-4943 | Public Transit | 5307, L, S | [6 empty] | 2020 | 1587000 | 1587000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | REPLACEMENT BUS - FIXED ROUTE |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TA-4944 | Public Transit | 5307, L | [6 empty] | 2020 | 2516000 | 2516000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | CONSTRUCT AN URBAN FIXED-ROUTE SATELLITE TRANSFER FACILITY FOR JACKSONVILLE TRANSIT TO INCLUDE PUBLIC PARKING, SHELTERS, RESTROOMS AND PESSENGER TERMINAL |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TL-0001 | Public Transit | 5307 |  |  |  |  | 2020 | 1000000 |  |  | 1000000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | CONSTRUCT PEDESTRIAN ACCESS AND SAFETY IMPROVEMENTS FOR JACKSONVILLE TRANSIT WITHIN 1/2 MILE OF HIGH VOLUME URBAN FIXED ROUTE BUS STOPS. IMPROVEMENTS WILL INCLUDE NEW SIDE WALK CONNECTIONS, ADA RETROFIT OF EXISTING SIDE WALKS AND CONSTRUCTION OF HIGH VISIBILITY CROSSWALKS AT KEY ROADWAY INTERSECTIONS. |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TL-0002 | Public Transit | 5307 |  |  |  |  | 2020 | 900000 |  |  | 900000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TS-5114 | Public Transit | 5307 | [6 empty] | 2020 | 116000 | 116000 | FUNDS AUTHORIZED IN PROGRESS
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | TECHNOLOGY - VEHICLE TRACKING, FARE COLLECTION, PASSENGER INFORMATION, DATA COMMUNICATIONS, TRAFFIC SIGNAL PRIORITY |  | Public Transportation (Transit) | Capital (Non-STI) | 3 | Jacksonville Urban Area MPO | TT-4907 | Public Transit | 5307, L | [6 empty] | 2020 | 1140000 | 1140000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 3 | Jacksonville Urban Area MPO | TO-4923 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 7990000 | 7990000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 |  | Public Transportation (Transit) | Planning | 3 | Jacksonville Urban Area MPO | TP-4908 | Public Transit | 5307, L, S | [6 empty] | 2020 | 745000 | 745000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Planning | 3 | Jacksonville Urban Area MPO | TP-5102 | Public Transit | 5303, L, S | [6 empty] | 2020 | 335000 | 335000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | NON-FIXED ROUTE ADA PARATRANSIT |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-4952 | Public Transit | 5307, L | [6 empty] | 2020 | 761000 | 761000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-5109 | Public Transit | 5307, L | [6 empty] | 2020 | 2076000 | 2076000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-5220 | Public Transit | 5307, L, S | [6 empty] | 2020 | 312000 | 312000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | ROUTINE CAPITAL-BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-5225 | Public Transit | 5307, L | [6 empty] | 2020 | 149000 | 149000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | MOBILITY MANAGEMENT |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 3 | Jacksonville Urban Area MPO | TG-5225C | Public Transit | 5307, L | [6 empty] | 2020 | 653000 | 653000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN |  | Public Transportation (Transit) | STI (Prioritization) | 3 | Jacksonville Urban Area MPO | TD-4904 | Division 3 | 5307, 5309, L, T |  |  |  |  | 2020 | 11359000 |  |  | 11359000
ONSLOW, BRUNSWICK, NEW HANOVER | VARIOUS | NCDOT | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO, Grand Strand Area Transportation Study, Wilmington Urban Area MPO | W-5203DIV | Division 3
ONSLOW, DUPLIN, BRUNSWICK, NEW HANOVER, PENDER, SAMPSON | US 17 ; US 258 ; US 421 ; NC 24 ; NC 87 | NCDOT | VARIOUS LOCATIONS IN DIVISION 3. UPGRADE GUARDRAIL END UNITS. |  | Highway | Safety | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Cape Fear RPO, Mid-Carolina RPO, Grand Strand Area Transportation Study | HS-2403E | Region B | HSIP |  |  |  |  | 2025 | 306000 |  |  | 306000
ONSLOW, JONES | US 17 | NCDOT | SOUTH OF BELGRADE TO NORTH OF MAYSVILLE. | 4.36 | Highway | Transition | 2, 3 | Jacksonville Urban Area MPO, Down East RPO | R-2514B | Pre-STI (Transition) | T |  |  |  |  | 2023 | 6000 |  |  | 6000 | COMPLETED.
ONSLOW, PENDER | US 17 | NCDOT | US 17 BETWEEN NEW HANOVER / PENDER COUNTY LINE AND MILE POST 19.3 IN ONSLOW COUNTY. INSTALL SHOULDER RUMBLE STRIPS. | 34.89 | Highway | Safety | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Cape Fear RPO | W-5803B | Statewide Mobility | HSIP |  |  |  |  | 2023 | 476000 |  |  | 476000 | COMPLETED.
ONSLOW, PENDER, SAMPSON, DUPLIN, NEW HANOVER | NC 53; US 117; NC 111 | NCDOT | VARIOUS LOCATIONS ALONG ROUTES. INSTALL CENTER AND EDGELINE SINUSOIDAL RUMBLE STRIPS. | 63.83 | Highway | Safety | 3 | Cape Fear RPO, Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO | HS-2403B | Region B | HSIP |  |  |  |  | 2026 | 6230000 |  |  | 6230000
ORANGE | NC 54 | NCDOT | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 1.55 | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | BL-0044 | Division 7 | BGDA, HF, L(M) |  |  |  |  | 2025 | 1311000 | 2022 | 175000 | 1486000 | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION.
ORANGE | CAMERON AVENUE | CHAPEL HILL | SOUTH MERRITT MILL ROAD TO NC 86 (SOUTH COLUMBIA STREET) IN CHAPEL HILL. CONSTRUCT BIKE LANES AND CYCLE PATH. |  | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | BL-0101 | Division 7 | BGDA, L(M) | 2026 | 175000 |  |  | 2027 | 725000 | 2024 | 50000 | 950000
ORANGE | ORANGE GROVE ROAD |  | CONSTRUCT TRANSIT ACCESS SIDEWALK | 0.5 | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | BL-0139 | Division 7 | L(M), TADA | [6 empty] | 2025 | 250000 | 250000
ORANGE | SHELTON STREET; EAST POPLAR AVENUE; MAPLE AVENUE; | CARRBORO | CONSTRUCT CONTRAFLOW/CYCLE TRACK AND INSTALL PAVEMENT MARKINGS ON SHELTON STREET. CONSTRUCT PEDESTRIAN LANE ON EAST POPLAR AVENUE. CONSTRUCT CONTRAFLOW LANE ON MAPLE AVENUE. |  | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | BL-0149 | Division 7 | BGDA, L(M) |  |  |  |  | 2025 | 1112000 |  |  | 1112000
ORANGE | VARIOUS | CHAPEL HILL | ROUTES IN CHAPEL HILL. CONSTRUCT SIDEWALKS TO FILL IN GAPS. |  | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | BL-0150 | Division 7 | L(M), TADA | 2027 | 176000 |  |  | 2027 | 2935000 | 2026 | 359000 | 3470000
ORANGE | BOLIN CREEK GREENWAY PHASE TWO | CARRBORO | LAKE HOGAN GREENWAY TO JONES CREEK/TWIN CREEKS GREENWAYS. CONSTRUCT GREENWAY. |  | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | BL-0151 | Division 7 | L(M), TADA | [6 empty] | 2027 | 400000 | 400000
ORANGE | SR 1750 (NORTH ESTES DRIVE) | CHAPEL HILL | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 0.73 | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | C-5179 | Exempt | BGDA, BGDACV, CMAQ, L, L(M) |  |  |  |  | 2020 | 6433000 |  |  | 6433000 | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
ORANGE | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | CARRBORO | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | C-5650 | Division 7 | BGANY, CMAQ, L | 2025 | 125000 |  |  | 2026 | 2676000 | 2023 | 10000 | 2811000
ORANGE | VARIOUS | DURHAM | BICYCLE DETECTION AT SIGNALIZED INTERSECTIONS. |  | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | U-4726DF | Exempt | BGDA, CMAQ, L |  |  |  |  | 2024 | 156000 |  |  | 156000
ORANGE | SR 1777 (HOMESTEAD ROAD) | DURHAM | SR 1843 (SEAWELL SCHOOL ROAD) TO SR 1733 (WEAVER DAIRY ROAD EXTENSION). |  | Bike & Ped | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | U-4726IK | Division 7 | BGDA, L |  |  |  |  | 2023 | 2000000 |  |  | 2000000
ORANGE | MORGAN CREEK GREENWAY | CHAPEL HILL | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. |  | Bike & Ped | Other | 7 | Durham-Chapel Hill-Carrboro MPO | BO-2415 | Division 7 | BGDA, L, TADA | 2023 | 1173000 |  |  | 2024 | 1197000 |  |  | 2370000
ORANGE | EPHESUS CHURCH ROAD | TOWN OF CHAPEL HILL | US 15 / US 501 BYPASS (FORDHAM BOULEVARD) TO POPE ROAD. CONSTRUCT SIDEWALKS AND BIKE LANES TO FILL IN GAPS. | 1.6 | Bike & Ped | Other | 7 | Durham-Chapel Hill-Carrboro MPO | BO-2421 | Exempt | HP, L | 2026 | 70000 | 2026 | 150000 | 2026 | 800000 | 2025 | 80000 | 1100000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204.
ORANGE | MORGAN CREEK GREENWAY (CARRBORO) | CARRBORO | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 0.29 | Bike & Ped | Pre-STI (Historic) | 7 | Durham-Chapel Hill-Carrboro MPO | EL-4828A | Pre-STI (Transition) | BGDA, L, TADA |  |  |  |  | 2025 | 1992000 |  |  | 1992000
ORANGE | ORANGE COUNTY BICYCLE ROUTE 1 | CHAPEL HILL | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | 0.67 | Bike & Ped | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | EB-5721 | Division 7 | BGDA, L, TADA |  |  |  |  | 2025 | 2700000 |  |  | 2700000
ORANGE | SR 1005 (JONES FERRY ROAD) | CARRBORO | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | Bike & Ped | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | EB-5880 | Division 7 | L, TAANY | 2026 | 80000 | 2026 | 180000 | 2027 | 690000 | 2025 | 89000 | 1039000
ORANGE | SR 1780 (ESTES DRIVE) | CHAPEL HILL | SR 1772 (NORTH GREENSBORO STREET) IN CARRBORO TO NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.7 | Bike & Ped | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | EB-5886 | Division 7
ORANGE | SR 1780 (ESTES DRIVE) | CHAPEL HILL | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | Bike & Ped | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | EB-5886A | Division 7 | L(M), TAANY | 2026 | 7600000 | 2026 | 480000 | 2028 | 848000 | 2025 | 170000 | 9098000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7.
ORANGE | SR 1780 (ESTES DRIVE) | CHAPEL HILL | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.29 | Bike & Ped | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | EB-5886B | Division 7 | L(M), TAANY | 2026 | 864000 |  |  | 2027 | 3104000 | 2022 | 534000 | 4502000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7.
ORANGE | BARNES STREET | CARRBORO | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | Bike & Ped | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | EB-5890 | Division 7 | L, TAANY | 2026 | 50000 | 2026 | 340000 | 2027 | 350000 | 2025 | 46000 | 786000
ORANGE | US 15 / US 501 | CHAPEL HILL | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | Bike & Ped | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | EB-5998 | Division 7 | L, TAANY | 2025 | 480000 | 2025 | 1100000 | 2026 | 7200000 | 2023 | 204000 | 8984000 | COORDINATE WITH U-5304
ORANGE | JONES CREEK GREENWAY | CARRBORO | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 0.12 | Bike & Ped | Transition | 7 | Durham-Chapel Hill-Carrboro MPO | C-5181 | Exempt | BGDA, CMAQ, L |  |  |  |  | 2025 | 910000 | 2022 | 12000 | 922000
ORANGE | RIVERWALK TRAIL | HILLSBOROUGH | RIVERWALK TRAIL, PHASE III IN HILLSBOROUGH. CONSTRUCT A PAVED OFF-ROAD TAIL ALONG ENO RIVER CONNECTING RIVER PARK, GOLD PARK AND THE OCCONEECHEE MOUNTAIN STATE NATURAL AREA, AND CONSTRUCT SIDEWALK TO PROVIDE PEDESTRIAN AND BICYCLE CONNECTIONS TO THE GREE | 2.17 | Bike & Ped | Transition | 7 | Durham-Chapel Hill-Carrboro MPO | C-5184 | Exempt | [10 empty] | UNDER CONSTRUCTION BY TOWN OF HILLSBOROUGH
ORANGE | MORGAN CREEK GREENWAY | CARRBORO | WESTERN SECTION, SR 1919 (SMITH LEVEL ROAD) TO UNIVERSITY LAKE IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 1.7 | Bike & Ped | Transition | 7 | Durham-Chapel Hill-Carrboro MPO | EL-4828 | Pre-STI (Transition) | [10 empty] | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY TOWN OF CARRBORO
ORANGE | NC 86 | NCDOT | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILROAD. | 0.25 | Highway | Bridges | 7 | Durham-Chapel Hill-Carrboro MPO | B-6037 | Region D | BFP | 2025 | 2700000 |  |  | 2027 | 10600000 |  |  | 13300000
ORANGE | SR 1146 (WEST TEN ROAD) | NCDOT | SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1137 (BUSHY COOK ROAD). CONSTRUCT OVERLAY, PAVED SHOULDERS AND TURN LANES. | 1.68 | Highway | Economic Development | 7 | Durham-Chapel Hill-Carrboro MPO | U-6245 | Division 7 | T |  |  |  |  | 2021 | 829000 | 2020 | 109000 | 938000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MEDLINE
ORANGE | I-40 / I-85 | NCDOT | WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1006 (ORANGE GROVE ROAD). PAVEMENT REHABILITATION. | 6.74 | Highway | Interstate Maintenance | 7 | Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO | I-5958 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2027 | 9500000 |  |  | 9500000
ORANGE | EXCHANGE PARK LANE | HILLSBOROUGH | SOUTH CHURTON STREET TO FARIBAULT LANE IN HILLSBOROUGH. REPAIR BRIDGE 670241 OVER ENO RIVER. | 0.13 | Highway | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | HL-0045 | Division 7 | BGDA, L |  |  |  |  | 2025 | 158000 |  |  | 158000
ORANGE | CHAPEL HILL |  | FRANKLIN STREET AND ROSEMARY STREET, AND THE STREETS IN BETWEEN FROM MERRITT MILL ROAD TO HENDERSON STREET IN DOWNTOWN CHAPEL HILL. INSTALL NEW MAST ARM AND CURB AND SIDEWALK IMPROVEMENTS. | 2 | Highway | Other | 7 | Durham-Chapel Hill-Carrboro MPO | HO-0013 | Exempt | DP, L | 2025 | 250000 | 2026 | 550000 | 2026 | 1300000 | 2024 | 400000 | 2500000 | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M.
ORANGE | US 15 / US 501 | NCDOT | SR 1742 (EPHESUS CHURCH ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Pre-STI (Historic) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5304C | [11 empty] | WORK COMPLETED UNDER U-5550.
ORANGE | SR 1009 (OLD NC 86) | NCDOT | SR 1727 (EUBANKS ROAD) NEAR CHAPEL HILL. MODIFY RIGHT TURN LANE. | 0.5 | Highway | Safety | 7 | Durham-Chapel Hill-Carrboro MPO | HS-2007H | Division 7 | HSIP | 2025 | 10000 | 2025 | 5000 | 2025 | 137000 |  |  | 152000
ORANGE | NC 86 | NCDOT | NC 86 (MARTIN LUTHER KING BOULEVARD) AT CRITZ DRIVE. INSTALL PEDISTRIAN IMPROVEMENTS. | 0.5 | Highway | Safety | 7 | Durham-Chapel Hill-Carrboro MPO | HS-2007J | Region D | HSIP |  |  |  |  | 2025 | 530000 |  |  | 530000
ORANGE | I-85 | NCDOT | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | I-0305B | Statewide Mobility | NHP | 2030 | 52800000 | 2030 | 1200000 | 2033 | 101000000 |  |  | 155000000 | SCOPE PREVIOUSLY INCLUDED UNDER I-5967.
ORANGE | I-85 | NCDOT | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | I-0305C | Not Funded | NHP | NOT FUNDED | 11800000 | NOT FUNDED | 3100000 | NOT FUNDED | 56500000 | NOT FUNDED |  | 71400000 | SCOPE PREVIOUSLY INCLUDED UNDER I-5984.
ORANGE | I-40 | NCDOT | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 11.73 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | I-3306A | Statewide Mobility | NHP, T(M) | 2021 | 10724000 | 2021 | 628000 | 2021 | 303565000 |  |  | 314917000 | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035
ORANGE | I-40 | NCDOT | NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTIONS FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | 0.47 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | I-3306AC | Region D | NHP | 2025 | 1400000 | 2025 | 670000 | 2026 | 8900000 |  |  | 10970000
ORANGE | I-40 | NCDOT | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. TOWING CONTRACT FOR I-3306A CONSTRUCTION. |  | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | I-3306AD | Statewide Mobility | T |  |  |  |  | 2023 | 2280000 |  |  | 2280000 | UNDER CONSTRUCTION
ORANGE | NC 54 | NCDOT | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS, AND IMPROVE SR 1006 INTERSECTION. | 6.1 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO, Central Pines RPO | R-5821
ORANGE | NC 54 | NCDOT | SR 1006 (ORANGE GROVE ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | R-5821B | Division 7 | [10 empty] | UNDER CONSTRUCTION
ORANGE | US 15 / US 501 | NCDOT | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5304A | Not Funded | T | NOT FUNDED | 10000000 | NOT FUNDED | 1040000 | NOT FUNDED | 22001000 | NOT FUNDED |  | 33041000
ORANGE | US 15 / US 501 | NCDOT | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 2.13 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5304B | Not Funded | T | NOT FUNDED | 6000000 | NOT FUNDED | 285000 | NOT FUNDED | 22001000 | NOT FUNDED |  | 28286000
ORANGE | US 15 / US 501 | NCDOT | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | 1.92 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5304D | Not Funded | T | NOT FUNDED | 5000000 | NOT FUNDED | 344000 | NOT FUNDED | 30001000 | NOT FUNDED |  | 35345000
ORANGE | US 15 / US 501 | NCDOT | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5304E | Not Funded | T | NOT FUNDED | 12000000 | NOT FUNDED | 446000 | NOT FUNDED | 25000000 | NOT FUNDED |  | 37446000
ORANGE | US 15 / US 501 (FORDHAM BOULEVARD) | NCDOT | SR 1742 (EPHESUS CHURCH ROAD) IN CHAPEL HILL. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5550 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
ORANGE | NC 54 | NCDOT | US 15 / US 501. UPGRADE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5774A | Not Funded | T | NOT FUNDED | 2800000 | NOT FUNDED | 140000 | NOT FUNDED | 16100000 | NOT FUNDED |  | 19040000
ORANGE | SR 1009 (SOUTH CHURTON STREET) | NCDOT | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTI-LANES. | 2.22 | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5845 | Division 7 | T | 2030 | 19700000 | 2030 | 7200000 | 2033 | 50500000 |  |  | 77400000
ORANGE | SR 1772 (GREENSBORO STREET) | NCDOT | SR 1780 (ESTES DRIVE) IN CARRBORO. CONSTRUCT ROUNDABOUT. |  | Highway | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | U-5846 | Division 7 | [10 empty] | UNDER CONSTRUCTION
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT BUSES |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Durham-Chapel Hill-Carrboro MPO | TA-4726 | Public Transit | 5307, 5339, L, S | [6 empty] | 2020 | 9692000 | 9692000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | 3 REPLACEMENT BUSES. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Durham-Chapel Hill-Carrboro MPO | TA-4726A | Division 7 | [10 empty] | IN PROGRESS BY CHAPEL HILL TRANSIT
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT - PARATRANSIT VEHICLE |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Durham-Chapel Hill-Carrboro MPO | TA-4748 | Public Transit | 5307 | [6 empty] | 2020 | 788000 | 788000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | REPLACEMENT VAN |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Durham-Chapel Hill-Carrboro MPO | TA-4979 | Public Transit | 5307 | [6 empty] | 2023 | 792000 | 792000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | ORANGE PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | PURCHASE NEW BUS < 30'. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Durham-Chapel Hill-Carrboro MPO | TA-6731 | Public Transit | FED, L | [6 empty] | 2020 | 56000 | 56000
ORANGE | GO TRIANGLE | GO TRIANGLE | TOWN OF HILLSBOROUGH. CONSTRUCT PARK-AND-RIDE LOT. |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Durham-Chapel Hill-Carrboro MPO | TD-5295 | Region D | L, S |  |  |  |  | 2023 | 920000 |  |  | 920000 | UNDER CONSTRUCTION BY GO TRIANGLE
ORANGE | GOTRIANGLE | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE |  | Public Transportation (Transit) | Capital (Non-STI) | 7 | Durham-Chapel Hill-Carrboro MPO | TL-0018 | Public Transit | CMAQ, L |  |  |  |  | 2023 | 400000 | 2023 | 100000 | 500000
ORANGE | ORANGE PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | 1 REPLACEMENT LTV (25') AND RADIO, VEHICLE LETTERING AND LOGOS, AND ON-BOARD CAMERA. |  | Public Transportation (Transit) | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | TD-5155 | Division 7 | BGDA, L | [6 empty] | 2022 | 77000 | 77000 | IN PROGRESS BY ORANGE PUBLIC TRANSIT
ORANGE | ORANGE COUNTY | ORANGE COUNTY | UPDATE THREE BUS SHELTERS IN ORANGE COUNTY ON GOVERNMENT PROPERTY. |  | Public Transportation (Transit) | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | TL-0026 | Division 7 | BGDA, L, L(M), TADA |  |  |  |  | 2023 | 155000 |  |  | 155000
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | THE TOWN OF CHAPEL HILL. ACQUIRE FIVE (5) ELECTRIC TRANSIT BUSES. |  | Public Transportation (Transit) | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | TL-0034 | Exempt | CMAQ, L(M) | [6 empty] | 2024 | 2708000 | 2708000
ORANGE | TOWN OF CHAPEL HILL | TOWN OF CHAPEL HILL | NORTH-SOUTH BUS RAPID TRANSIT CORRIDOR (NSBRT). | 8.2 | Public Transportation (Transit) | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | TL-0035 | Public Transit | 5307, L |  |  |  |  | 2027 | 172263000 | 2024 | 10737000 | 183000000
ORANGE | VARIOUS |  | MOBILITY ON-DEMAND - 2 ADA ACCESSIBLE MINIVANS. |  | Public Transportation (Transit) | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | TL-0049 | Exempt | CMAQ, L | [6 empty] | 2024 | 187000 | 187000
ORANGE | GOTRIANGLE |  | IMPROVE (3) BUS STOPS IN ORANGE COUNTY AT SITES 701, 705, AND 706. |  | Public Transportation (Transit) | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | TL-0051 | Public Transit | CMAQ, L(M) |  |  |  |  | 2024 | 250000 |  |  | 250000
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | IMPROVE BUS STOPS AT VARIOUS LOCATIONS IN DOWNTOWN CHAPEL HILL. |  | Public Transportation (Transit) | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | TL-0062 | Division 7 | BGDA, L(M) |  |  |  |  | 2025 | 451000 |  |  | 451000
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | PURCHASE ELECTRIC BUS |  | Public Transportation (Transit) | Locally Selected | 7 | Durham-Chapel Hill-Carrboro MPO | TL-0066 | Division 7 | BGDA, L(M) | [6 empty] | 2027 | 1150000 | 1150000
ORANGE | ORANGE COUNTY TRANSIT |  | ORANGE COUNTY MOBILITY ON DEMAND - PURCHASE 2 ADA ACCESSIBLE MINI-VANS. EXPAND MICRO-TRANSIT ZONES. |  | Public Transportation (Transit) | Locally Selected | 7 | Central Pines RPO | TN-6126 | Exempt | CMAQ, L | [6 empty] | 2024 | 188000 | 188000
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Durham-Chapel Hill-Carrboro MPO | TO-5133 | Public Transit | SMAP | [6 empty] | 2020 | 14280000 | 14280000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | DURHAM | DURHAM | 5307 OPERATING FUNDS NC 2019-060-01-P11 |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Durham-Chapel Hill-Carrboro MPO | TO-5206 | Public Transit | 5307 | [6 empty] | 2020 | 311000 | 311000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
ORANGE | BURLINGTON -GRAHAM | BURLINGTON -GRAHAM | 5307 OPERATING FUNDS NC-2019-060-01-P10 |  | Public Transportation (Transit) | Miscellaneous/Other | 7 | Burlington-Graham MPO | TO-5220 | Public Transit | 5307 | [6 empty] | 2020 | 282000 | 282000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY 2020 GRANTS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | PURCHASE FIVE ELECTRIC TRANSIT BUSES. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 7 | Durham-Chapel Hill-Carrboro MPO | TN-6133 | Exempt | CMAQ, L, L(M) | [6 empty] | 2025 | 2708000 | 2708000
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Durham-Chapel Hill-Carrboro MPO | TG-4731B | Public Transit | 5307, L | [6 empty] | 2020 | 5372000 | 5372000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | ORANGE PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Central Pines RPO | TK-6151 | Public Transit | 5311, L, S | [6 empty] | 2020 | 744000 | 744000
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | ALTERNATIVE ANALYSIS - ENVIRONMENTAL ASSESSMENT, DESIGN, AND ENGINEERING |  | Public Transportation (Transit) | Planning | 7 | Durham-Chapel Hill-Carrboro MPO | U-5119A | Public Transit | FED, L | [6 empty] | 2020 | 200000 | 200000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Durham-Chapel Hill-Carrboro MPO | TG-4732A | Public Transit | 5307, S | [6 empty] | 2020 | 1080000 | 1080000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 7 | Durham-Chapel Hill-Carrboro MPO | TG-4732B | Public Transit | 5307, L | [6 empty] | 2023 | 196000 | 196000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | ORANGE PUBLIC TRANSIT | ORANGE PUBLIC TRANSIT | PURCHASE TWO (2) LIGHT TRANSIT VEHICLES |  | Public Transportation (Transit) | STI (Prioritization) | 7 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO | TA-6721 | Division 7 | BGANY, L | [6 empty] | 2022 | 109000 | 109000
ORANGE | GO TRIANGLE | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX |  | Public Transportation (Transit) | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | TD-5284 | Region D | 5307, L, T |  |  |  |  | 2024 | 360000 |  |  | 360000
ORANGE | SR 1120 (MOUNT WILLING ROAD) | NCDOT | NORFOLK SOUTHERN RAILROAD CROSSING 735145T NEAR EFLAND. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 7 | Durham-Chapel Hill-Carrboro MPO | RX-2007B | Division 7 | RR |  |  |  |  | 2025 | 800000 |  |  | 800000
ORANGE | NORFOLK SOUTHERN H LINE | NCDOT | MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PLATFORM, PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. |  | Rail | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | P-5701 | Division 7 | [10 empty] | UNDER CONSTRUCTION. "OTHER" FUNDING REFLECTS PARTICIPATION BY TRIANGLE TRANSIT.
ORANGE | NORFOLK SOUTHERN H LINE | NCDOT | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. |  | Rail | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | P-5701A | Division 7 | O, T |  |  |  |  | 2022 | 6860000 |  |  | 6860000
ORANGE | NORFOLK SOUTHERN H LINE | NCDOT | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT STATION PLATFORM AND REALIGN CURVE AT MILEPOST 41.4. |  | Rail | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | P-5701B | Division 7 | T |  |  |  |  | 2025 | 1000000 |  |  | 1000000
ORANGE | NC RR / NS NC LINE | NCDOT | SR 1120 (MT. WILLING ROAD) INTERSECTION IN EFLAND. REALING SR 1120 (MT. WILLING ROAD) TO LINE UP WITH EFLAND CEDAR GROVE ROAD AT US 70 AND CLOSE AT-GRADE CROSSING (CROSSING NUMBER 735145T) AND CONSTRUCT BRIDGE OVER THIS LINE. |  | Rail | STI (Prioritization) | 7 | Durham-Chapel Hill-Carrboro MPO | RP-0005 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3920000 |  |  | 8220000
ORANGE, DURHAM | CHAPEL HILL CARRBORO | NCDOT | IMPLEMENT AN IMPROVED SIGNAL SYSTEM FOR THE TOWN OF CHAPEL HILL AND TOWN OF CARRBORO. | 14.79 | Highway | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | HP-0006 | Region C, D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13910000 |  |  | 15610000
ORANGE, DURHAM | I-85 | NCDOT | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES AND UPGRADE INTERCHANGES. | 7.8 | Highway | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | I-0305 | [11 empty] | COORDINATE WITH U-5845
ORANGE, DURHAM | I-85 | NCDOT | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | 7.81 | Highway | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | I-0305A | Not Funded | NHP | NOT FUNDED | 17900000 | NOT FUNDED | 1200000 | NOT FUNDED | 120898000 | NOT FUNDED |  | 139998000 | PROJECT FUNDED FOR PRELIMINARY ENGINEERING ONLY.
ORANGE, DURHAM | I-40 | NCDOT | I-85 IN ORANGE COUNTY TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM COUNTY. WIDEN TO SIX LANES AND INSTALL ITS. | 20.7 | Highway | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | I-3306
ORANGE, DURHAM | US 15 / US 501 (FORDHAM BOULEVARD) | NCDOT | NC 86 (SOUTH COLUMBIA STREET) TO I-40 IN CHAPEL HILL. UPGRADE CORRIDOR. | 6 | Highway | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | U-5304 | [11 empty] | COORDINATE WITH EB-5998 AND U-5774
ORANGE, DURHAM | US 15 / US 501 | NCDOT | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | 1.75 | Highway | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | U-5304F | Region C, D | T | 2028 | 3700000 | 2028 | 1700000 | 2030 | 73100000 |  |  | 78500000
ORANGE, DURHAM | NC 54 | NCDOT | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | 1.22 | Highway | STI (Prioritization) | 5, 7 | Durham-Chapel Hill-Carrboro MPO | U-5774B | Not Funded | T | NOT FUNDED | 43000000 | NOT FUNDED | 74000 | NOT FUNDED | 23300000 | NOT FUNDED |  | 66374000
ORANGE, DURHAM | SR 1838 / SR 2220 | NCDOT | US 15 / US 501 IN ORANGE COUNTY TO SR 1113 (POPE ROAD) IN DURHAM COUNTY | 1 | Highway | Transition | 5, 7 | Durham-Chapel Hill-Carrboro MPO | EB-4707A | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
PAMLICO | NC 55 | NCDOT | REPLACE BRIDGE 680038 OVER TRENT CREEK. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-4593 | Region B | NHPB |  |  |  |  | 2022 | 6137000 |  |  | 6137000 | UNDER CONSTRUCTION.
PAMLICO | SR 1302 (JANIERO ROAD) | NCDOT | REPLACE BRIDGE 680057 OVER DAWSON CREEK. | 0.25 | Highway | Bridges | 2 | Down East RPO | B-5995 | Division 2 | BGOFF | 2022 | 600000 |  |  | 2026 | 5900000 |  |  | 6500000
PASQUOTANK | ELIZABETH CITY |  | WEEKSVILLE ROAD ACCESSIBILITY AND CONNECTIVITY PLAN. | 3.6 | Bike & Ped | Locally Selected | 1 | Albemarle RPO | BO-2420 | Exempt | DP | [6 empty] | 2024 | 2000000 | 2000000 | 'DP' FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS.
PASQUOTANK | US 17 (FUTURE I-87) | NCDOT | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | 10.29 | Highway | Interstate Maintenance | 1 | Albemarle RPO | I-6029 | Statewide Mobility | NHP, NHPIM, T(M) |  |  |  |  | 2020 | 11886000 |  |  | 11886000 | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034.
PASQUOTANK | SR 1354 (MILLPOND ROAD) | NCDOT | SR 1354 (MILLPOND ROAD) BETWEEN US 158 AND SR 1001 (TURNPIKE ROAD). UPGRADE PAVEMENT MARKINGS. | 4.42 | Highway | Safety | 1 | Albemarle RPO | HS-2001C | Division 1 | HSIP |  |  |  |  | 2024 | 40000 |  |  | 40000
PASQUOTANK | NC 344 | NCDOT | FROM SOUTH OF AIRPORT ENTRANCE TO SR 1100 (SAWMILL ROAD). INSTALL RUMBLE STRIPES AND PAVEMENT MARKERS. | 3.72 | Highway | Safety | 1 | Albemarle RPO | HS-2001I | Region A | HSIP |  |  |  |  | 2024 | 160000 |  |  | 160000
PASQUOTANK | US 17 BUSINESS (EHRINGHAUS STREET) | NCDOT | NC 344 (HALSTEAD BOULEVARD) INTERSECTION IN ELIZABETH CITY. INSTALL AUDIBLE PEDESTRIAN SIGNALS. |  | Highway | Safety | 1 | Albemarle RPO | HS-2401F | Region A | HSIP |  |  |  |  | 2025 | 12000 |  |  | 12000
PASQUOTANK | NC 344 | NCDOT | TANGLEWOOD PARKWAY TO MOUNT EVEREST DRIVE IN ELIZABETH CITY. REMOVE PORTION OF MEDIAN ISLAND AND INSTALL PEDESTRIAN ACCOMMODATIONS. | 0.36 | Highway | Safety | 1 | Albemarle RPO | HS-2401M | Region A | HSIP |  |  |  |  | 2025 | 90000 |  |  | 90000
PASQUOTANK | SR 1333 (WEST MAIN STREET EXTENSION) | NCDOT | FROM 0.6 MILES NORTH OF SR 1338 (BEREA CHURCH ROAD) TO 0.2 MILES SOUTH OF SR 1338 (BEREA CHURCH ROAD). IMPROVE HORIZONTAL ALIGNMENT WITH VARIOUS CURVE IMPROVEMENTS. | 0.8 | Highway | Safety | 1 | Albemarle RPO | W-5701C | Division 1 | HSIP | 2024 | 170000 |  |  | 2025 | 2165000 |  |  | 2335000 | RIGHT-OF-WAY IN PROGRESS.
PASQUOTANK | US 17 BUSINESS | NCDOT | AT SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 1 | Albemarle RPO | U-5939 | Region A | BG5T50, T | 2025 | 5400000 | 2025 | 530000 | 2028 | 22555000 |  |  | 28485000 | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
PASQUOTANK | US 17 (HUGHES BOULEVARD) | NCDOT | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | 1.49 | Highway | STI (Prioritization) | 1 | Albemarle RPO | U-5940 | Region A | NHP, T | 2027 | 23955000 | 2027 | 4700000 | 2030 | 21100000 |  |  | 49755000 | BUILD NC BOND FUNDING: $10,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
PASQUOTANK | ELIZABETH CITY | NCDOT | ELIZABETH CITY SIGNAL SYSTEM. | 20 | Highway | STI (Prioritization) | 1 | Albemarle RPO | U-5942 | Region A | BG5T50, HP |  |  |  |  | 2021 | 5359000 |  |  | 5359000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368.
PASQUOTANK, CAMDEN, PERQUIMANS | VARIOUS | NCDOT | UPGRADE WARNING SIGNS AT CURVES AT VARIOUS LOCATIONS. |  | Highway | Safety | 1 | Albemarle RPO | HS-2001D | Division 1 | HSIP |  |  |  |  | 2023 | 41000 |  |  | 41000 | UNDER CONSTRUCTION.
PENDER | HENDERSON FIELD (ACZ) | HENDERSON FIELD (ACZ) | LAND ACQUISTION PHASE IV FOR ROADWAY RELOCATION, SR 1307 (WALLACE AIRPORT ROAD) AND SR 1306 (OLD MILL ROAD) ROADWAY RELOCATION, RUNWAY EXTENSION - PHASE 1 (850 LF) | 0 | Aviation | STI (Prioritization) | 3 | Cape Fear RPO | AV-5744 | Division 3 | T | 2022 | 2113000 |  |  | 2024 | 8700000 |  |  | 10813000 | RIGHT-OF-WAY IN PROGRESS.
PENDER | HENDERSON FIELD (ACZ) | HENDERSON FIELD (ACZ) | EXTEND RUNWAY 5500 FEET. |  | Aviation | STI (Prioritization) | 3 | Cape Fear RPO | AV-5744A | Division 3 | T |  |  |  |  | 2026 | 4405000 |  |  | 4405000
PENDER | HENDERSON FIELD (ACZ) | HENDERSON FIELD (ACZ) | APRON EXPANSION. |  | Aviation | STI (Prioritization) | 3 | Cape Fear RPO | AV-5815 | Division 3 | T |  |  |  |  | 2027 | 6100000 |  |  | 6100000
PENDER | COUNTRY CLUB MULTI-USE PATH | PENDER COUNTY | ADJACENT TO COUNTRY CLUB DRIVE AND JENKINS ROAD FROM SLOOP POINT LOOP ROAD TO NORTH ST. JOHNS CHURCH ROAD. CONSTRUCT MULTI-USE PATH. | 3.91 | Bike & Ped | Locally Selected | 3 | Wilmington Urban Area MPO | BL-0154 | Division 3 | BGDA, L(M) | [6 empty] | 2025 | 1108000 | 1108000
PENDER | SR 1510 (EAST WILMINGTON STREET) |  | FROM US 117 BUSINESS TO US 117 BYPASS CORRIDOR IN BURGAW. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 0.67 | Bike & Ped | NCDOT Selected (Other Selection Process) | 3 | Cape Fear RPO | BN-0007 | Exempt | CRPLT5, L |  |  |  |  | 2024 | 867000 | 2024 | 50000 | 917000
PENDER | I-40 | NCDOT | WEST OF US 117 (MILE MARKER 388) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | 15.05 | Highway | Interstate Maintenance | 3 | Cape Fear RPO | I-6040 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 19768000 |  |  | 19768000 | UNDER CONSTRUCTION.
PENDER | US 117 | NCDOT | AT SR 1411 (ASHTON ROAD / OLD RIVER ROAD). INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Cape Fear RPO | HS-2003AC | Region B | HSIP |  |  |  |  | 2025 | 325000 |  |  | 325000
PENDER | US 117 | NCDOT | AT NC 53 IN BURGAW. UPGRADE TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Cape Fear RPO | HS-2003AL | Region B | HSIP |  |  |  |  | 2024 | 12000 |  |  | 12000
PENDER | US 17 | NCDOT | NC 210 INTERSECTION IN SURF CITY. REVISE TRAFFIC SIGNAL AND INSTALL BE PREPARED TO STOP SIGNS. | 0.5 | Highway | Safety | 3 | Cape Fear RPO | HS-2003F | Statewide Mobility | HSIP |  |  |  |  | 2024 | 271000 |  |  | 271000
PENDER | US 17 | NCDOT | AT SR 1561 (SLOOP POINT ROAD) NORTHEAST OF HAMPSTEAD. INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 3 | Wilmington Urban Area MPO | HS-2403K | Statewide Mobility | HSIP | 2026 | 10000 | 2026 | 2000 | 2026 | 223000 |  |  | 235000
PENDER | US 17 | NCDOT | NC 210 TO US 17 NORTH OF HAMPSTEAD. | 5.45 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | R-3300B | Region B | T | 2025 | 5000000 |  |  | 2022 | 229552000 |  |  | 234552000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE).
PENDER | NC 53 | NCDOT | US 117 BUSINESS (WALKER STREET / WILMINGTON STREET). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Cape Fear RPO | R-5701 | Region B | L, T | 2025 | 210000 | 2025 | 180000 | 2027 | 2800000 |  |  | 3190000 | L FUNDS REPRESENT PROPERTY DONATED BY THE TOWN OF BURGAW.
PENDER | NC 210 | NCDOT | SR 1560 (WATTS LANDING ROAD). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Cape Fear RPO | R-5899 | Division 3 | BGANY | 2025 | 1200000 | 2025 | 210000 | 2027 | 5600000 |  |  | 7010000
PENDER | NC 50/NC 210 | NCDOT | SR 1534 (BELT ROAD). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 3 | Cape Fear RPO | R-5900 | Division 3 | T | 2025 | 4600000 | 2025 | 310000 | 2028 | 23695000 |  |  | 28605000 | BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE).
PENDER | US 17 | NCDOT | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 5.51 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5732 | Statewide Mobility | T | 2024 | 19586000 | 2029 | 2400000 | 2032 | 56101000 |  |  | 78087000
PENDER | DAN OWEN DRIVE EXTENSION | NCDOT | SR 1570 (FACTORY ROAD) TO DAN OWEN DRIVE. |  | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | U-5732A | Region B | [10 empty] | COMPLETED.
PENDER | PENDER ADULT SERVICES, INC. | PENDER ADULT SERVICES, INC. | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Cape Fear RPO | TK-6152 | Public Transit | 5311, L, S | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
PENDER, NEW HANOVER | US 17 | NCDOT | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | 6.87 | Highway | STI (Prioritization) | 3 | Wilmington Urban Area MPO | R-3300A | Region B | T | 2025 | 10000000 |  |  | 2026 | 259087000 |  |  | 269087000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE).
PENDER, ONSLOW | SURF CITY | SURF CITY | PURCHASE TWO ELECTRIC VEHICLES. |  | Public Transportation (Transit) | Locally Selected | 3 | Cape Fear RPO, Jacksonville Urban Area MPO | TN-6131 | Exempt | CRPANY, L(M) | [6 empty] | 2025 | 100000 | 100000
PERQUIMANS | SR 1338 (WYNNE FORK ROAD) | NCDOT | REPLACE BRIDGE 710011 OVER RACOON CREEK. | 0.25 | Highway | Bridges | 1 | Albemarle RPO | B-5606 | Division 1 | T |  |  |  |  | 2021 | 1545000 |  |  | 1545000 | COMPLETED. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
PERQUIMANS | US 17 | NCDOT | BRIDGES 710014 AND 710080 OVER PERQUIMANS RIVER TO SR 1304 (CARTWRIGHT SWAMP ROAD). REHABILITATE PAVEMENT. | 4.38 | Highway | Interstate Maintenance | 1 | Albemarle RPO | HI-0026 | Statewide Mobility | NHPIM |  |  |  |  | 2029 | 4400000 |  |  | 4400000
PERQUIMANS | US 17 | NCDOT | SR 1304 (CARTWRIGHT SWAMP ROAD) TO PASQUOTANK COUNTY LINE. REHABILITATE PAVEMENT. | 4.17 | Highway | Interstate Maintenance | 1 | Albemarle RPO | HI-0027 | Statewide Mobility | NHPIM |  |  |  |  | 2030 | 4200000 |  |  | 4200000
PERQUIMANS | US 17 | NCDOT | US 17 BUSINESS TO BRIDGES 710014 AND 710080 OVER PERQUIMANS RIVER. REHABILITATE PAVEMENT. | 1.74 | Highway | Interstate Maintenance | 1 | Albemarle RPO | HI-0028 | Statewide Mobility | NHPIM |  |  |  |  | 2030 | 2000000 |  |  | 2000000
PERQUIMANS | US 17 BUSINESS/ NC 37 | NCDOT | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 0.82 | Highway | Pre-STI (Historic) | 1 | Albemarle RPO | R-4467 | Region A | T |  |  |  |  | 2019 | 65512000 | 2021 | 2415000 | 67927000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
PERQUIMANS | US 17 | NCDOT | CHOWAN COUNTY LINE TO SR 1101 (BEAR SWAMP ROAD). INSTALL RUMBLE STRIPS. | 4 | Highway | Safety | 1 | Albemarle RPO | HS-2401G | Statewide Mobility | HSIP |  |  |  |  | 2025 | 160000 |  |  | 160000
PERQUIMANS | SR 1329 (WOODVILLE ROAD) | NCDOT | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 4.39 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5740 | Division 1 | T | 2019 | 765000 | 2023 | 140000 | 2021 | 5841000 | 2020 | 1035000 | 7781000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
PERQUIMANS | SR 1336 (HARVEY POINT ROAD) | NCDOT | US 17 TO SR 1350 (CHURCHES LANE). MODERNIZE ROADWAY. | 6.13 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5806 | Division 1 | BGLT5 |  |  |  |  | 2022 | 5170000 |  |  | 5170000 | UNDER CONSTRUCTION.
PERQUIMANS | US 17 | NCDOT | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY AND CONVERT INTERSECTIONS TO INTERCHANGES. | 6 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5869
PERQUIMANS | US 17 | NCDOT | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5869A | Division 1 | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 58074000 |  |  | 89974000
PERQUIMANS | US 17 | NCDOT | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5869B | Division 1 | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5301000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 880000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 53900000 |  |  | 60081000
PERQUIMANS | US 17 | NCDOT | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. |  | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5869C | Not Funded | NHP | NOT FUNDED | 3500000 | NOT FUNDED | 1000000 | NOT FUNDED | 135000000 | NOT FUNDED |  | 139500000 | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY.
PERQUIMANS | SR 1300 (NEW HOPE ROAD) | NCDOT | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | 4.38 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5939 | Division 1 | T | 2028 | 1400000 | 2028 | 1700000 | 2030 | 26000000 |  |  | 29100000
PERSON | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). |  | Aviation | STI (Prioritization) | 5 | Kerr-Tar RPO | AV-5818 | Division 5 | T |  |  |  |  | 2026 | 15200000 |  |  | 15200000
PERSON | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | ROXBORO | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 0.44 | Bike & Ped | Locally Selected | 5 | Kerr-Tar RPO | BL-0061 | Exempt | CMAQ, L | 2025 | 65000 |  |  | 2025 | 450000 | 2023 | 130000 | 645000
PERSON | SR 1605 (NORTH MAIN STREET) | ROXBORO | CONSTRUCT SIDEWALK FROM US 501 (VIRGILINA ROAD) TO SCHOOL STREET. | 0.75 | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Kerr-Tar RPO | BN-0013 | Exempt | CRP550, L(M) | [6 empty] | 2025 | 150000 | 150000
PERSON | US 501 | NCDOT | US 501 AT NC 57 (HILLSBOROUGH ROAD). INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2005P | Region C | HSIP |  |  |  |  | 2025 | 260000 |  |  | 260000
PERSON | VARIOUS | NCDOT | VARIOUS INTERSECTIONS IN ROXBORO. UPGRADE PEDESTRIAN IMPROVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, SIDEWALK, LEADING PEDESRIAN INTERVAL, AND/OR TRAFFIC SIGNAL UPGRADES. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AO | Division 5 | HSIP | 2026 | 10000 | 2026 | 20000 | 2027 | 943000 |  |  | 973000
PERSON | US 501 | NCDOT | SOUTH OF US 158 TO SR 1601 (NORTH MAIN STREET) IN ROXBORO. CONVERT TO 4-LANE MEDIAN DIVIDED FACILITY, IMPROVE VARIOUS INTERSECTIONS WITH SOME CONSOLIDATION OF INTERSECTIONS, AND FILL IN SIDEWALK GAPS. | 3 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5969
PERSON | US 501 | NCDOT | SOUTH OF US 158 TO NC 157. | 0.88 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5969A | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1288000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6400000 |  |  | 14888000
PERSON | US 501 | NCDOT | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | 1.03 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5969B | Region C | T | 2029 | 10700000 | 2029 | 1500000 | 2031 | 14500000 |  |  | 26700000
PERSON | US 501 / NC 49 | NCDOT | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | 1.11 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5969C | Not Funded | T | NOT FUNDED | 6300000 | NOT FUNDED | 1346000 | NOT FUNDED | 6599000 | NOT FUNDED |  | 14245000
PERSON | PERSON COUNTY | PERSON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Kerr-Tar RPO | TK-6153 | Public Transit | 5311, L, S | [6 empty] | 2020 | 664000 | 664000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE | GREENVILLE | CONSTRUCT MULTI-USE PATH AT VARIOUS LOCATIONS INCLUDING ALONG THE TAR RIVER, MOYE BOULEVARD, THE NORFOLK SOUTHERN RAIL CORRIDOR, AND TOWN CREEK IN GREENVILLE. | 2.27 | Bike & Ped | Locally Selected | 2 | Greenville Urban Area MPO | EB-6042 | Exempt | DP, L |  |  |  |  | 2022 | 8291000 |  |  | 8291000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | NORTH-SOUTH CONNECTOR |  | CONSTRUCT GREENWAY / SIDEPATH USING EXISTING ROAD AND SIDEWALK ALONG NORTH GREENE STREET FROM 1ST STREET TO MUMFORD ROAD IN GREENVILLE. | 1.1 | Bike & Ped | Other | 2 | Greenville Urban Area MPO | BO-2418 | Exempt | HP, L, L(M) | 2026 | 25000 | 2026 | 100000 | 2026 | 3285000 | 2025 | 590000 | 4000000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199.
PITT | GREENVILLE | GREENVILLE | SOUTH TAR RIVER GREENWAY. PHASE 3: PITT STREET TO NASH STREET. CONSTRUCT GREENWAY USING EXISTING SIDEWALKS, ROADS AND ON NEW LOCATION ALONG THE RIVER. | 0.89 | Bike & Ped | Transition | 2 | Greenville Urban Area MPO | EB-5539 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION.
PITT | US 13 | NCDOT | REPLACE BRIDGE 730038 OVER TAR RIVER IN GREENVILLE. | 0.25 | Highway | Bridges | 2 | Greenville Urban Area MPO | B-4786 | Region B | NHPB |  |  |  |  | 2022 | 9700000 |  |  | 9700000 | UNDER CONSTRUCTION.
PITT | NC 222 | NCDOT | REPLACE BRIDGE 730024 OVER TAR RIVER. | 0.25 | Highway | Bridges | 2 | Mid-East RPO | B-5612 | Region B | T | 2019 | 950000 |  |  | 2029 | 14000000 |  |  | 14950000 | RIGHT-OF-WAY IN PROGRESS.
PITT | US 264/US 258 (FUTURE I-587) | NCDOT | GREENE COUNTY LINE TO SR 1467 (STANTONSBURG ROAD) INTERCHANGE (GREENVILLE SOUTHWEST BYPASS). PAVEMENT REHABILITATION. | 13.19 | Highway | Interstate Maintenance | 2 | Mid-East RPO, Greenville Urban Area MPO | I-6035 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 14420000 |  |  | 14420000 | COMPLETE. LET WITH I-6032. GARVEE BOND FUNDING $12M FOR CON, PAYBACK FY 2019-2033.
PITT | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENVILLE PLANNING ORGANIZATION. |  | Highway | Locally Selected | 2 | Greenville Urban Area MPO | HL-0099 | Exempt | CRPDA, L |  |  |  |  | 2023 | 3621000 |  |  | 3621000
PITT | SR 1571 (WEST 5TH STREET) | GREENVILLE | FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. ROAD REHABILITATION AND REALIGNMENT. | 1.07 | Highway | Locally Selected | 2 | Greenville Urban Area MPO | U-6240 | Exempt | DP, L |  |  |  |  | 2022 | 34077000 |  |  | 34077000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | OXFORD ROAD | NCDOT | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | 0.25 | Highway | Municipal Bridge | 2 | Greenville Urban Area MPO | HB-0021 | Division 2 | BFPOFF | 2024 | 50000 | 2024 | 143000 | 2024 | 1900000 |  |  | 2093000 | RIGHT-OF-WAY IN PROGRESS
PITT | ROCK SPRINGS ROAD | NCDOT | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | 0.25 | Highway | Municipal Bridge | 2 | Greenville Urban Area MPO | HB-0022 | Division 2 | BFPOFF | 2029 | 100000 | 2029 | 126000 | 2030 | 2277000 |  |  | 2503000
PITT | NC 11/NC 903 (GREENVILLE SOUTHWEST BYPASS) | NCDOT | NC 11 TO US 264 (GREENVILLE BYPASS). CONSTRUCT FOUR LANE DIVIDED FACILITY ON NEW LOCATION WITH BYPASS OF WINTERVILLE. | 11.25 | Highway | Pre-STI (Historic) | 2 | Greenville Urban Area MPO | R-2250 | Pre-STI (Transition) | T |  |  |  |  | 2023 | 750000 |  |  | 750000 | UNDER CONSTRUCTION.
PITT | SR 1703 (14TH STREET) | NCDOT | INSTALL CROSSWALK, WHEELCHAIR RAMPS, SIDEWALK, AND FENCING ALONG SR 1703 (14TH STREET) FROM HASKETT WAY AND BERKLEY ROAD. REMOVE TWO EXISTING OBSOLETE CROSSWALKS. | 0.09 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002A | Division 2 | HSIP |  |  |  |  | 2021 | 50000 |  |  | 50000 | COMPLETED.
PITT | US 264 ALTERNATE (GREENVILLE BOULEVARD) | NCDOT | FROM 200 FEET SOUTH OF LUCI DRIVE AND NC 33 (10TH STREET) IN GREENVILLE. CONSTRUCT PEDESTRIAN IMPORVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, AND SIDEWALK. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002AH | Region B | HSIP |  |  | 2024 | 125000 | 2024 | 320000 |  |  | 445000
PITT | US 264 ALTERNATE | NCDOT | US 264 ALTERNATE (GREENVILLE BOULEVARD) AT SR 1534 (OLD PACTOLUS ROAD). CONSTRUCT RESTRICTED-CROSSING INTERSECTION. | 0.48 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002E | Region B | HSIP |  |  |  |  | 2023 | 882000 |  |  | 882000 | UNDER CONSTRUCTION.
PITT | NC 33 | NCDOT | NC 33 FROM US 13/NC 11 (MEMORIAL DRIVE) TO DAUGHTRIDGE DRIVE IN GREENVILLE. INSTALL MEDIAN ISLAND AND REVISE PAVEMENT MARKINGS. | 0.07 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002J | Region B | HSIP |  |  |  |  | 2023 | 120000 |  |  | 120000 | UNDER CONSTRUCTION.
PITT | US 264 ALTERNATE | NCDOT | US 264 ALTERNATE/NC 43 (GREENVILLE BOULEVARD) AT NC 11/NC 43/NC 903 (MEMORIAL DRIVE) AND NC 11/NC 903 (MEMORIAL DRIVE) AT MALL DRIVE IN GREENVILLE. REVISE AND CONSTRUCT TURN LANES. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002L | Region B | HSIP |  |  |  |  | 2024 | 896000 |  |  | 896000
PITT | SR 1598 (10TH STREET) | NCDOT | AT COLLEGE HILL DRIVE AND AT ELM STREET IN GREENVILLE. UPGRADE TRAFFIC SIGNALS. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002M | Division 2 | HSIP |  |  |  |  | 2024 | 55000 |  |  | 55000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1702 (EVANS STREET) | NCDOT | SR 1702 (EVANS STREET) AT HOWELL STREET IN GREENVILLE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002R | Division 2 | HSIP |  |  | 2023 | 65000 | 2023 | 400000 |  |  | 465000 | UNDER CONSTRUCTION.
PITT | SR 1725 (COUNTY HOME ROAD) | NCDOT | AT EXISTING CROSSWALK JUST SOUTH OF DISTRICT PARK DRIVE IN GREENVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002X | Division 2 | HSIP |  |  |  |  | 2024 | 35000 |  |  | 35000 | UNDER CONSTRUCTION.
PITT | SR 1131 (REEDY BRANCH ROAD) | NCDOT | SR 1131 (REEDY BRANCH ROAD) AT BULLDOG RUN AND EDDIE SMITH STREET IN WINTERVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2002Z | Division 2 | HSIP |  |  |  |  | 2024 | 55000 |  |  | 55000
PITT | US 258 BUSINESS | NCDOT | COOPERATIVE WAY / SHARON LANE INTERSECTION IN FARMVILLE. INSTALL ALL WAY STOP. |  | Highway | Safety | 2 | Mid-East RPO | HS-2402A | Region B | HSIP |  |  |  |  | 2024 | 125000 |  |  | 125000
PITT | SR 1598 (10TH STREET) | NCDOT | ANDERSON STREET INTERSECTION IN GREENVILLE. INSTALL A PEDESTRIAN HYBRID BEACON. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402D | Division 2 | HSIP |  |  |  |  | 2025 | 175000 |  |  | 175000
PITT | NC 43 | NCDOT | SR 2241 (IVY ROAD) AND SR 1753 (STOKESTOWN - ST. JOHN ROAD) INTERSECTIONS SOUTH OF GREENVILLE. INSTALL TRAFFIC SIGNALS AT BOTH INTERSECTIONS AND CONSTRUCT LEFT TURN LANES ON SR 2241 (IVY ROAD). |  | Highway | Safety | 2 | Greenville Urban Area MPO, Mid-East RPO | HS-2402F | Region B | HSIP | 2025 | 100000 | 2025 | 500000 | 2026 | 736000 |  |  | 1336000
PITT | US 13 / US 264 | NCDOT | SR 1124 (SPEIGHT SPEED FARM ROAD) / SR 1207 (NASH JOYNER ROAD) INTERSECTION IN GREENVILLE. CONSTRUCT REDUCED CONFLICT INTERSECTION WITH RIGHT TURN LANES. |  | Highway | Safety | 2 | Greenville Urban Area MPO, Mid-East RPO | HS-2402G | Region B | HSIP | 2025 | 150000 | 2025 | 300000 | 2026 | 950000 |  |  | 1400000
PITT | NC 102 (THIRD STREET) ; SR 1149 (LEE STREET) | NCDOT | SR 1149 (LEE STREET) INTERSECTION IN AYDEN ; SECOND STREET INTERSECTION IN AYDEN. UPGRADE TRAFFIC SIGNALS AND INSTALL / UPGRADE PEDESTRIAN SIGNALS AND OTHER ACCOMMODATIONS. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402H | Region B | HSIP |  |  |  |  | 2025 | 72000 |  |  | 72000
PITT | SR 1598 (10TH STREET) | NCDOT | 5TH STREET INTERSECTION IN GREENVILLE. INSTALL / UPGRADE TRAFFIC SIGNALS, PAVEMENT MARKINGS, PEDESTRIAN SIGNALS, AND OTHER ACCOMMODATIONS. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402N | Division 2 | HSIP | 2025 | 3000 |  |  | 2025 | 253000 |  |  | 256000
PITT | NC 43 | NCDOT | US 264 INTERCHANGE RAMPS. CONSTRUCT ROUNDABOUTS. |  | Highway | Safety | 2 |  | HS-2402O | Region B | HSIP |  |  | 2025 | 200000 | 2025 | 388000 |  |  | 588000
PITT | NC 11/43/903 (MEMORIAL DRIVE) | NCDOT | ARLINGTON BOULEVARD INTERSECTION. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND SIDEWALK. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402Q | Region B | HSIP | 2025 | 6000 |  |  | 2025 | 142000 |  |  | 148000
PITT | US 258 (WESLEY CHURCH ROAD) | NCDOT | US 264 TO I-587 EASTBOUND RAMPS. INSTALL RUMBLE STRIPES. |  | Highway | Safety | 2 | Greenville Urban Area MPO | HS-2402R | Region B | HSIP |  |  |  |  | 2025 | 80000 |  |  | 80000
PITT | SR 1700 (EVANS STREET/ OLD TAR ROAD) | NCDOT | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO FOUR LANES. | 3.68 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-2817 | Division 2 | BG5200, T | 2019 | 22800000 | 2019 | 3972000 | 2026 | 149560000 |  |  | 176332000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDS: $25,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $25,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE).
PITT | SR 1598 (DICKINSON AVENUE) | NCDOT | NC 11 TO READE CIRCLE. IMPROVE ROADWAY. | 1.34 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5606 | Division 2 | BG50200 |  |  |  |  | 2022 | 18365000 |  |  | 18365000 | UNDER CONSTRUCTION.
PITT | US 13 (MEMORIAL DRIVE) | NCDOT | NC 43 (5TH STREET). UPGRADE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5730 | Region B | T |  |  | 2023 | 125000 | 2026 | 1400000 |  |  | 1525000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1726 (PORTERTOWN ROAD) SR 1708 (FIRETOWER ROAD) | NCDOT | WEST OF EAST ARLINGTON BOULEVARD TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO FOUR LANES. | 3.4 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5785 | Division 2 | T | 2024 | 58200000 | 2024 | 7500000 | 2030 | 109400000 |  |  | 175100000 | INCLUDES SCOPE OF U-5870.
PITT | SR 1203 (ALLEN ROAD) | NCDOT | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO FOUR LANES. | 2.33 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5875 | Division 2 | T | 2024 | 485000 | 2024 | 650000 | 2026 | 70105000 |  |  | 71240000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE).
PITT | SR 1704 (FOURTEENTH STREET) | NCDOT | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO ADD MEDIAN AND PROTECTED LEFT-TURN LANES. | 1.38 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5917 | Division 2 | T | 2019 | 952000 | 2024 | 2772000 | 2027 | 28645000 | 2020 | 1740000 | 34109000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $7,500,000 FOR CON PAYBACK 2028-2042 (FY 2028 / YR 8 SALE).
PITT | GREENVILLE | NCDOT | GREENVILLE SIGNAL SYSTEM. | 25 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5952 | Region B | BG50200 |  |  | 2027 | 750000 | 2030 | 13100000 |  |  | 13850000
PITT | NC 43 | NCDOT | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | 3.19 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-5991 | Division 2 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 57700000 |  |  | 100400000
PITT | SR 1711 (WORTHINGTON ROAD) | NCDOT | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 2 | Greenville Urban Area MPO | U-6197 | Division 2 | T | 2028 | 1300000 | 2028 | 730000 | 2030 | 3100000 |  |  | 5130000
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | FLEET SERVICE BUILDING EXPANSION. |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | Greenville Urban Area MPO | TL-0009 | Public Transit | CARES, L |  |  |  |  | 2021 | 976000 |  |  | 976000
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | SAFETY & SECURITY |  | Public Transportation (Transit) | Capital (Non-STI) | 2 | Greenville Urban Area MPO | TS-5112 | Public Transit | 5307 | [6 empty] | 2020 | 15000 | 15000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 2 | Greenville Urban Area MPO | TO-4726 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 5420000 | 5420000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Greenville Urban Area MPO | TG-5107B | Public Transit | 5307, L | [6 empty] | 2020 | 2700000 | 2700000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Greenville Urban Area MPO | TG-5107C | Public Transit | 5307, L | [6 empty] | 2020 | 600000 | 600000 | FUNDS AUTHORIZED IN PROGRESS
PITT | PITT COUNTY | PITT COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 2 | Mid-East RPO | TK-6154 | Public Transit | 5311, L, S | [6 empty] | 2020 | 720000 | 720000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Planning | 2 | Greenville Urban Area MPO | TP-5107 | Public Transit | 5303, L, S | [6 empty] | 2020 | 132000 | 132000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | GREENVILLE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 2 | Greenville Urban Area MPO | TG-4767 | Public Transit | 5307, L | [6 empty] | 2020 | 2404000 | 2404000 | FUNDS AUTHORIZED IN PROGRESS
PITT | EAST STREET | NCDOT | CLOSURE OF EAST STREET AT CSX (CROSSING 628 794Y) IN BETHEL. |  | Rail | Rail-Highway Grade Crossing Closure | 2 | Mid-East RPO | RC-2002A | Division 2 | RR |  |  |  |  | 2024 | 560000 |  |  | 560000
PITT | SR 1704 (FOURTEENTH STREET) | NCDOT | CLNA CROSSING 465488D IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Greenville Urban Area MPO | RX-2002B | Division 2 | RR |  |  |  |  | 2025 | 345000 |  |  | 345000
PITT | US 264 ALTERNATE (GREENVILLE BOULEVARD) | NCDOT | CLNA CROSSING 465489K IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Greenville Urban Area MPO | RX-2002C | Division 2 | RR |  |  |  |  | 2025 | 345000 |  |  | 345000
PITT | SR 1530 (AIRPORT ROAD) | NCDOT | CSX CROSSING 641860P IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 2 | Greenville Urban Area MPO | RX-2002E | Division 2 | RR |  |  |  |  | 2027 | 530000 |  |  | 530000
PITT | US 258 BUSINESS (MAIN STREET) | NCDOT | CLNA CROSSING 465540F IN FARMVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 2 | Mid-East RPO | RX-2402A | Division 2 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
PITT | SR 1139 (WILSON STREET / MOYE-TURNAGE ROAD) | NCDOT | CLNA CROSSING 465535J IN FARMVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 2 | Mid-East RPO | RX-2402B | Division 2 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
PITT | US 264 (MARLBORO ROAD) | NCDOT | CLNA CROSSING 465544H IN FARMVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 2 | Mid-East RPO | RX-2402C | Division 2 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
PITT, CRAVEN, EDGECOMBE | NC 43 | NCDOT | NC 43 BETWEEN NC 118 IN CRAVEN COUNTY AND SR 1730 (HERMAN GARRIS ROAD) IN PITT COUNTY, NC 43 BETWEEN SR 1205 (ROCK SPRING ROAD) AND THE SOUTHERN LIMITS OF FALKLAND, AND NC 43 BETWEEN THE NORTHERN LIMITS OF FALKLAND IN PITT COUNTY AND NC 42 IN EDGECOMBE COUNTY. INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | 33.01 | Highway | Safety | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Down East RPO, Upper Coastal Plain RPO | HS-2002S | Region A, B | HSIP |  |  |  |  | 2024 | 815000 |  |  | 815000
PITT, GREENE | US 264 | NCDOT | US 264 BETWEEN THE WILSON COUNTY LINE AND SR 1128 (DAVENPORT FARM ROAD) / SR 1206 (BELL ARTHUR ROAD) IN PITT COUNTY. INSTALL RUMBLE STRIPES. | 11.76 | Highway | Safety | 2 | Mid-East RPO, Eastern Carolina RPO, Greenville Urban Area MPO | HS-2002T | Region B | HSIP |  |  |  |  | 2024 | 378000 |  |  | 378000 | UNDER CONSTRUCTION.
PITT, GREENE, LENOIR | NC 903 | NCDOT | LAGRANGE TOWN LIMITS IN LENOIR COUNTY TO SR 1104 (HULL ROAD) IN GREENE COUNTY;US 13/258 IN GREENE COUNTY TO NC 11 IN PITT COUNTY; US 13/NC 11 TO MARTIN COUNTY LINE IN PITT COUNTY. INSTALL RUMBLE STRIPES. |  | Highway | Safety | 2 |  | HS-2402U | Region B | HSIP |  |  |  |  | 2025 | 950000 |  |  | 950000
POLK | SR 1004 (POORS FORD ROAD) | NCDOT | REPLACE BRIDGE 740087 OVER BROAD RIVER. | 0.25 | Highway | Bridges | 14 | Foothills RPO | HB-0025 | Division 14 | BGOFF | 2025 | 260000 | 2025 | 260000 | 2028 | 5200000 |  |  | 5720000
POLK | I-26 | NCDOT | HENDERSON COUNTY LINE TO MILE MARKER 65. PAVEMENT REHABILITATION. | 7.05 | Highway | Interstate Maintenance | 14 | Foothills RPO | I-5926 | Statewide Mobility | NHPIM |  |  |  |  | 2027 | 13998000 |  |  | 13998000
POLK | I-26 | NCDOT | MILE MARKER 65 TO SOUTH CAROLINA STATE LINE. PAVEMENT REHABILITATION. | 6.06 | Highway | Interstate Maintenance | 14 | Foothills RPO | I-5927 | Statewide Mobility | BGLT5 |  |  |  |  | 2023 | 21600000 |  |  | 21600000 | UNDER CONSTRUCTION.
POLK | NC 108 (MILLS STREET) | NCDOT | SR 1534 (PEAK STREET). INSTALL PEDESTRIAN SIGNALS AND UPGRADE CURB RAMP. | 0.5 | Highway | Safety | 14 | Foothills RPO | HS-2014AB | Region G | HSIP |  |  |  |  | 2024 | 168000 |  |  | 168000
POLK | US 74 WB | NCDOT | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | 12.65 | Highway | Safety | 14 | Foothills RPO | W-5814B | Statewide Mobility | HSIP |  |  |  |  | 2021 | 199000 |  |  | 199000 | COMPLETE
POLK | US 74 EB | NCDOT | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | 12.65 | Highway | Safety | 14 | Foothills RPO | W-5814C | Statewide Mobility | HSIP |  |  |  |  | 2021 | 179000 |  |  | 179000 | COMPLETE
POLK | I-26 | NCDOT | US 74/NC 108 INTERCHANGE (EXIT 67). REVISE INTERCHANGE AND CONSTRUCT IMPROVEMENTS TO NC 108. |  | Highway | STI (Prioritization) | 14 | Foothills RPO | I-4729
POLK | I-26 | NCDOT | REVISE THE I-26/US 74/NC 108 INTERCHANGE. CONSTRUCT RAMPS FROM I-26 WESTBOUND TO US 74 EASTBOUND, AND FROM US 74 WESTBOUND TO I-26 EASTBOUND. | 1 | Highway | STI (Prioritization) | 14 | Foothills RPO | I-4729A | Region G | [10 empty] | COMPLETE
POLK | I-26 | NCDOT | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. |  | Highway | STI (Prioritization) | 14 | Foothills RPO | I-4729B | Region G | T | 2030 | 5000000 | 2030 | 1000000 | 2033 | 33600000 |  |  | 45800000 | RIGHT-OF-WAY IN PROGRESS
POLK | NC 9 | NCDOT | US 74 TO NC 108. CONSTRUCT PAVED SHOULDERS. | 3.07 | Highway | STI (Prioritization) | 14 | Foothills RPO | R-5840 | Division 14 | T | 2022 | 2200000 | 2024 | 1300000 | 2029 | 13799000 |  |  | 17299000 | RIGHT-OF-WAY IN PROGRESS.
POLK | POLK COUNTY TRANSPORTATION | POLK COUNTY TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Foothills RPO | TK-6155 | Public Transit | 5311, L, S | [6 empty] | 2020 | 736000 | 736000 | FUNDS AUTHORIZED IN PROGRESS
RANDOLPH | SR 1950 (WEST ACADEMY STREET) | RANDLEMAN | SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN. CONSTRUCT SIDEWALK ON NORTH SIDE. | 1.04 | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-5744 | Division 8 | L, TA5T50 |  |  |  |  | 2026 | 800000 |  |  | 800000
RANDOLPH | INDUSTRIAL PARK AVENUE | ASHEBORO | RANDOLPH COMMUNITY COLLEGE ENTRANCE TO CONTINUING EDUCATION AND INDUSTRIAL CENTER IN ASHEBORO. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 0.26 | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-5862 | Division 8 | L, TA5T50 |  |  |  |  | 2022 | 147000 |  |  | 147000
RANDOLPH | SR 1950 (WEST NAOMI STREET) | RANDLEMAN | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. |  | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-5898 | Division 8 | L, TA5T50 | 2025 | 25000 |  |  | 2026 | 258000 |  |  | 283000
RANDOLPH | US 64 / NC 49 (EAST DIXIE DRIVE) | ASHEBORO | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | 0.15 | Bike & Ped | STI (Prioritization) | 8 | Piedmont Triad RPO | EB-6004 | Division 8 | L, TA5T50 | 2027 | 340000 | 2027 | 90000 | 2027 | 2100000 |  |  | 2530000
RANDOLPH | SR 2481 (LOW BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 750307 OVER MOUNT PLEASANT CREEK. | 0.25 | Highway | Bridges | 8 | Piedmont Triad RPO | B-5546 | Highway Fund | [10 empty] | UNDER CONSTRUCTION - LET WITH B-5360; CONSTRUCTION COST IS INCLUDED IN THAT PROJECT
RANDOLPH | SR 2207 (FAITH ROCK ROAD) | NCDOT | REPLACE BRIDGE 750176 OVER CREEK OFF DEEP RIVER. |  | Highway | Bridges | 8 | Piedmont Triad RPO | HB-0071 | Division 8 | BGOFF, HP, T(M) | 2025 | 20000 |  |  | 2026 | 800000 |  |  | 820000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114.
RANDOLPH | VARIOUS | NCDOT | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 3.18 | Highway | Economic Development | 8 | Piedmont Triad RPO | HE-0004 | Division 8 | HF, T | 2022 | 5000000 | 2022 | 2000000 | 2023 | 37000000 | 2023 | 1000000 | 45000000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
RANDOLPH | I-73 / US 220 | NCDOT | SR 1009 (OLD US HIGHWAY 311) TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | 7.69 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO, High Point Urban Area MPO | HI-0003 | Statewide Mobility | NHPIM |  |  |  |  | 2029 | 8121000 |  |  | 8121000
RANDOLPH | I-74 | NCDOT | SR 1928 (CEDAR SQUARE ROAD) TO I-73 / US 220. PAVEMENT REHABILITATION. | 7.58 | Highway | Interstate Maintenance | 8 | High Point Urban Area MPO, Piedmont Triad RPO | HI-0004 | Statewide Mobility | NHPIM |  |  |  |  | 2031 | 8140000 |  |  | 8140000
RANDOLPH | I-73 / I-74 / US 220 | NCDOT | MONTGOMERY COUNTY LINE TO NORTH OF SR 1462 (PARK DRIVE) IN ASHEBORO. PAVEMENT REHABILITATION. | 15.72 | Highway | Interstate Maintenance | 8 | Piedmont Triad RPO | I-5948 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 26700000 |  |  | 26700000
RANDOLPH | US 64 | NCDOT | ASHEBORO SOUTHERN BYPASS, US 64 WEST TO US 64 EAST. FOUR-LANE FREEWAY ON NEW LOCATION WITH INTERCHANGES AT US 220, NC 49 AND ZOO ACCESS AT NC 159. | 12.76 | Highway | Pre-STI (Historic) | 8 | Piedmont Triad RPO | R-2536 | Pre-STI (Transition) | [10 empty] | COMPLETE.
RANDOLPH | US 421 | NCDOT | CHATHAM COUNTY LINE TO THE GUILFORD COUNTY LINE. INSTALL 1 MILE AND .5 MILE MARKERS AND REVISE EXIT NUMBER SIGNS. | 9.98 | Highway | Safety | 8 | Piedmont Triad RPO | HS-2008D | Statewide Mobility | HSIP |  |  |  |  | 2023 | 50000 |  |  | 50000
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | NCDOT | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) FROM BEASLEY STREET TO BALFOUR AVENUE IN ASHEBORO. CONSTRUCT TWO-WAY LEFT TURN LANE. | 0.37 | Highway | Safety | 8 | Piedmont Triad RPO | W-5708L | Region E | HSIP | 2025 | 150000 |  |  | 2027 | 320000 |  |  | 470000
RANDOLPH | US 64 | NCDOT | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | 6.56 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-2220DA | Region E | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 117100000 |  |  | 133200000
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | NCDOT | SR 2269 (VISION DRIVE) ITO SR 2123 (CAUDLE ROAD) IN ASHEBORO. WIDEN TO MULTI-LANES. | 3.6 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5956 | Division 8 | [10 empty] | COORDINATE WITH U-6006
RANDOLPH | NC 159 (ZOO PARKWAY) | NCDOT | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | R-5958 | Division 8 | T | 2025 | 320000 | 2026 | 265000 | 2027 | 1900000 |  |  | 2485000
RANDOLPH | SR 1547 (FINCH FARM ROAD) | NCDOT | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTI-LANES. | 2.13 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-5308 | Division 8 | T | 2019 | 2459000 | 2026 | 3500000 | 2028 | 59500000 | 2020 | 2703000 | 68162000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) AND $15 MILLION FOR CONSTRUCTION - PAYBACK 2029-2043 (FY 2029 / YR 9 SALE)
RANDOLPH | SR 1712 (PINEVIEW STREET) | NCDOT | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO A THREE LANE FACILITY. | 0.61 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-5711 | Division 8 | BG5T50 |  |  |  |  | 2025 | 8800000 |  |  | 8800000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | NC 42 | NCDOT | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | 0.5 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-5743 | Region E | T | 2022 | 2006000 | 2022 | 897000 | 2025 | 13600000 |  |  | 16503000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | I-85 | NCDOT | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-5770 | Region E | T | 2022 | 6358000 | 2022 | 2200000 |  |  |  |  | 8558000 | “HF” FUNDING REFLECTS CONTRACT RESURFACING FUNDS. NC BUILD BOND $8M FOR CON, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE);
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | NCDOT | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | 1.07 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-5770A | Region E | HF, T |  |  |  |  | 2023 | 1693000 |  |  | 1693000 | UNDER CONSTRUCTION
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | NCDOT | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCI IMPROVEMENTS. | 0.99 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-5770B | Region E | T |  |  |  |  | 2027 | 29795000 |  |  | 29795000
RANDOLPH | US 64 | NCDOT | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO A FOUR LANE DIVIDED FACILITY, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | 2.31 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-5813 | Region E | NHP | 2021 | 7967000 | 2021 | 3000000 | 2024 | 62200000 |  |  | 73167000 | RIGHT OF WAY IN PROGRESS.
RANDOLPH | US 220 BUSINESS | NCDOT | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.72 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-6006 | Division 8 | BGANY, T | 2024 | 2050000 | 2024 | 2800000 | 2027 | 16000000 |  |  | 20850000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5956
RANDOLPH | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | NCDOT | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF SR 1453. | 0.47 | Highway | STI (Prioritization) | 8 | Piedmont Triad RPO | U-6007 | Division 8 | T |  |  | 2022 | 300000 | 2024 | 1400000 |  |  | 1700000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | NC 62 | NCDOT | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | 3.18 | Highway | STI (Prioritization) | 8 | High Point Urban Area MPO | U-6191 | Division 8 | T | 2028 | 21400000 | 2028 | 12400000 | 2031 | 30000000 |  |  | 63800000
RANDOLPH | RANDOLPH- MONTGOMERY RESTORE | RANDOLPH- MONTGOMERY RESTORE | PURCHASE ADDITIONAL 20-FOOT LIGHT TRANSIT VEHICLES. |  | Public Transportation (Transit) | Capital (Non-STI) | 8 | Piedmont Triad RPO | TA-6670 | Region E | [10 empty] | IN ACQUISITION
RANDOLPH | COORDINATED AREA TRANSPORTATION SYSTEM (RCATS) |  | ASHEBORO FLEXIBLE (DEVIATED) ROUTE TRANSIT LAUNCH. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 8 | Piedmont Triad RPO | TN-0001 | Exempt | CRPANY, L, L(M) | [6 empty] | 2024 | 733000 | 733000
RANDOLPH | SR 2502 (JULIAN AIRPORT ROAD) | NCDOT | NORFOLK SOUTHERN CROSSING 720943W IN LIBERTY. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Piedmont Triad RPO | RX-2008F | Division 8 | RR |  |  |  |  | 2026 | 411000 |  |  | 411000
RANDOLPH, DAVIDSON | I-85 | NCDOT | NC 109 IN THOMASVILLE TO SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. PAVEMENT REHABILITATION. | 7.61 | Highway | Interstate Maintenance | 8, 9 | High Point Urban Area MPO | HI-0002 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 15672000 |  |  | 15672000 | UNDER CONSTRUCTION
RANDOLPH, DAVIDSON | US 64 | NCDOT | NC 109 TO SR 1409 (LAKE PARK ROAD) |  | Highway | STI (Prioritization) | 8, 9 |  | R-2220C | Not Funded | T | NOT FUNDED | 13746000 | NOT FUNDED | 1650000 | NOT FUNDED | 56452000 | NOT FUNDED |  | 71848000
RANDOLPH, DAVIDSON, GUILFORD | HIGH POINT TRANSIT SYSTEM / HI-TRAN | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE. |  | Public Transportation (Transit) | Miscellaneous/Other | 7, 8, 9 | High Point Urban Area MPO | TO-4790 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 29675000 | 29675000 | FUNDS AUTHORIZED IN PROGRESS
RANDOLPH, GUILFORD | SR 1577 / SR 1004 (ARCHDALE ROAD) | NCDOT | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTI-LANES. | 3.09 | Highway | STI (Prioritization) | 7, 8 | High Point Urban Area MPO | U-3400 | Division 7, 8 | T | 2024 | 7901000 | 2026 | 6300000 | 2029 | 43600000 |  |  | 57801000
RANDOLPH, GUILFORD | SR 1595 / SR 4053 (SURRETT DRIVE) | NCDOT | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTI-LANES. | 3.22 | Highway | STI (Prioritization) | 7, 8 | High Point Urban Area MPO | U-5864 | Division 7, 8 | BGANY | 2026 | 28300000 | 2026 | 6700000 | 2029 | 44500000 |  |  | 79500000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | RICHMOND COUNTY AIRPORT (RCZ) | CLEAR OBSTRUCTIONS IN RUNWAY 14 APPROACH. |  | Aviation | STI (Prioritization) | 8 | Lumber River RPO | AV-5761 | Division 8 | T |  |  |  |  | 2026 | 570000 |  |  | 570000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | RICHMOND COUNTY AIRPORT (RCZ) | CONSTRUCT EAST RAMP EXPANSION. |  | Aviation | STI (Prioritization) | 8 | Lumber River RPO | AV-5853 | Division 8 | T |  |  |  |  | 2025 | 2000000 |  |  | 2000000
RICHMOND | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | HAMLET | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-6018 | Division 8 | L, TA5T50 | 2026 | 320000 | 2026 | 55000 | 2028 | 2400000 | 2024 | 28000 | 2803000
RICHMOND | I-73 / I-74 | NCDOT | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | 10.5 | Highway | Interstate Maintenance | 8 | Lumber River RPO | I-5946
RICHMOND | I-73/I-74 | NCDOT | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO SR 1455 (FIRE TOWER ROAD). PAVEMENT REHABILITATION. | 3.23 | Highway | Interstate Maintenance | 8 | Lumber River RPO | I-5946A | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION - LET WITH I-5947B
RICHMOND | I-73/I-74 | NCDOT | SR 1455 (FIRE TOWER ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | 6.86 | Highway | Interstate Maintenance | 8 | Lumber River RPO | I-5946B | Statewide Mobility | BGIM |  |  |  |  | 2022 | 6812000 |  |  | 6812000 | UNDER CONSTRUCTION
RICHMOND | US 74 / FUTURE I-74 | NCDOT | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 8 | Lumber River RPO | I-5979 | Division 8 | NHP | 2022 | 500000 | 2022 | 210000 | 2025 | 8800000 |  |  | 9510000 | RIGHT-OF-WAY IN PROGRESS
RICHMOND | US 1 | NCDOT | SOUTH CAROLINA STATE LINE TO SR 1001 (MARSTON ROAD). WIDEN TO FOUR LANES WITH VARIABLE WIDTH MEDIAN WITH BYPASS OF ROCKINGHAM ON NEW LOCATION. | 24.1 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501
RICHMOND | US 1 | NCDOT | SOUTH CAROLINA STATE LINE TO SR 1104 (OSBORNE ROAD) | 5.089 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501A | Not Funded | T | NOT FUNDED | 4500000 | NOT FUNDED |  | NOT FUNDED | 25700000 | NOT FUNDED |  | 30200000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | NCDOT | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | 5.282 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501BA | Not Funded | T | NOT FUNDED | 5519000 | NOT FUNDED | 908000 | NOT FUNDED | 40501000 | NOT FUNDED |  | 46928000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | NCDOT | US 74 BYPASS TO US 74 BUSINESS | 4.07 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501BB | Not Funded | T | NOT FUNDED | 13300000 | NOT FUNDED | 2523000 | NOT FUNDED | 67699000 | NOT FUNDED |  | 83522000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | NCDOT | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | 7.15 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501BC | Not Funded | T | NOT FUNDED | 24248000 | NOT FUNDED | 6950000 | NOT FUNDED | 101101000 | NOT FUNDED |  | 132299000 | COORDINATE WITH R-5928
RICHMOND | US 1 | NCDOT | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | 3.43 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-2501C | Division 8 | T |  |  |  |  | 2019 | 12975000 | 2021 | 217000 | 13192000 | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 220 / FUTURE I-73 / FUTURE I-74 | NCDOT | ROCKINGHAM BYPASS. FOUR LANES DIVIDED ON NEW LOCATION. | 10.5 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-3421 | [11 empty] | BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | NCDOT | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 2.61 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-3421A | Region E | T | 2020 | 5495000 |  |  | 2020 | 106857000 |  |  | 112352000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | NCDOT | ROCKINGHAM BYPASS, SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) TO SOUTHWEST OF SR 1304 (HARRINGTON ROAD) | 9.25 | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-3421B | Region E | T |  |  |  |  | 2020 | 83679000 |  |  | 83679000 | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 220/I-73/I-74 | NCDOT | SR 1336 (BILLY COVINGTON ROAD) |  | Highway | STI (Prioritization) | 8 | Lumber River RPO | R-3421CA | Statewide Mobility | T | 2023 | 75000 | 2023 | 25000 | 2024 | 532000 |  |  | 632000 | UNDER CONSTRUCTION
RICHMOND | VARIOUS | NCDOT | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | 4.01 | Highway | STI (Prioritization) | 8 | Lumber River RPO | U-5706 | Division 8 | T | 2029 | 18200000 | 2029 | 2500000 | 2033 | 64300000 |  |  | 85000000
RICHMOND | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | NCDOT | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | 0.54 | Highway | STI (Prioritization) | 8 | Lumber River RPO | U-6027 | Division 8 | T | 2025 | 1700000 | 2025 | 2000000 | 2028 | 8100000 |  |  | 11800000
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | NCDOT | ROCKINGHAM BYPASS, 0.2 MILES SOUTHWEST OF SR 1304 (HARRINGTON ROAD) TO I-73 / I-74 INTERCHANGE SOUTH OF ELLERBE | 0.84 | Highway | Transition | 8 | Lumber River RPO | R-3421C | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
RICHMOND | SR 1925 (BILTMORE DRIVE) | NCDOT | CSX CROSSING 630856U IN ROCKINGHAM. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 8 | Lumber River RPO | RX-2008C | Division 8 | RR |  |  |  |  | 2025 | 446000 |  |  | 446000
ROBESON | LUMBERTON REGIONAL AIRPORT (LBT) | LUMBERTON REGIONAL AIRPORT (LBT) | PARTIAL PARALLEL TAXIWAY RUNWAY 5. |  | Aviation | STI (Prioritization) | 6 | Lumber River RPO | AV-5747 | Division 6 | T |  |  |  |  | 2022 | 2600000 |  |  | 2600000 | UNDER CONSTRUCTION.
ROBESON | NC 711 (THIRD STREET) | PEMBROKE | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 1.52 | Bike & Ped | STI (Prioritization) | 6 | Lumber River RPO | EB-6013 | Division 6 | L, TAANY | 2028 | 168000 |  |  | 2029 | 2500000 | 2027 | 170000 | 2838000
ROBESON | NC 41/NC 72/SR 1600 | NCDOT | REPLACE BRIDGE 770125 AND 770175 OVER LUMBER RIVER. | 0.25 | Highway | Bridges | 6 | Lumber River RPO | B-5985 | Region C | NHPB | 2022 | 395000 | 2022 | 485000 |  |  |  |  | 880000 | RIGHT-OF-WAY IN PROGRESS.
ROBESON | NC 41/NC 72/SR 1600 | NCDOT | REPLACE BRIDGE 770125 OVER LUMBER RIVER. | 0.25 | Highway | Bridges | 6 | Lumber River RPO | B-5985A | Region C | BFP |  |  |  |  | 2023 | 7915000 |  |  | 7915000 | UNDER CONSTRUCTION.
ROBESON | NC 41/NC 72/SR 1600 | NCDOT | REPLACE BRIDGE 770175 OVER LUMBER RIVER. | 0.25 | Highway | Bridges | 6 | Lumber River RPO | B-5985B | Region C | BFP |  |  |  |  | 2025 | 9000000 |  |  | 9000000
ROBESON | CHURCH ROAD) SR 1529 (MOUNT OLIVE | NCDOT | REPLACE BRIDGE 770299 AND 770300 OVER SADDLE TREE SWAMP. | 0.5 | Highway | Bridges | 6 | Lumber River RPO | HB-0007 | Division 6 | BGOFF | 2023 | 77000 | 2023 | 185000 | 2024 | 1339000 |  |  | 1601000 | RIGHT-OF-WAY IN PROGRESS.
ROBESON | US 74 (FUTURE I-74) | NCDOT | 1 MILE EAST OF NC 41 TO 0.26 MILES EAST OF COLUMBUS COUNTY LINE. PAVEMENT REHABILITATION. | 10.93 | Highway | Interstate Maintenance | 6 | Lumber River RPO | HI-0016 | Statewide Mobility | NHPIM |  |  |  |  | 2024 | 10000000 |  |  | 10000000 | TO BE LET WITH HI-0017.
ROBESON | US 74 (FUTURE I-74) | NCDOT | US 74 (FUTURE I-74) FROM THE SCOTLAND COUNTY LINE TO I-74/US 74 BUSINESS. PAVEMENT REHABILITATION. | 3.44 | Highway | Interstate Maintenance | 6 | Lumber River RPO | HI-0017 | Statewide Mobility | NHPIM |  |  |  |  | 2024 | 6800000 |  |  | 6800000 | TO BE LET WITH HI-0016
ROBESON | I-95 | NCDOT | NORTH OF US 301 (MILE MARKER 22) TO CUMBERLAND COUNTY LINE (MILE MARKER 40). PAVEMENT REHABILITATION. | 15.7 | Highway | Interstate Maintenance | 6 | Lumber River RPO, Fayetteville Area MPO | I-5850 | Statewide Mobility
ROBESON | I-95 | NCDOT | BRIDGE REHABILITATION, MEDIAN DRAINAGE, AND CONTROL OF ACCESS FENCE. | 17.99 | Highway | Interstate Maintenance | 6 | Lumber River RPO, Fayetteville Area MPO | I-5850A | Statewide Mobility | [10 empty] | COMPLETED.
ROBESON | I-95 | NCDOT | PAVEMENT REHABILITATION. | 18.97 | Highway | Interstate Maintenance | 6 | Lumber River RPO, Fayetteville Area MPO | I-5850B | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | SOUTH CAROLINA STATE LINE (MILE MARKER 0.0) TO I-74 (MILE MARKER 13). PAVEMENT REHABILITATION. | 5.49 | Highway | Interstate Maintenance | 6 | Lumber River RPO | I-5939 | Statewide Mobility | BGIM |  |  |  |  | 2022 | 23898000 |  |  | 23898000 | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | MILE MARKER 13 TO MILE MARKER 22. PAVEMENT REHABILITATION. | 9 | Highway | Interstate Maintenance | 6 | Lumber River RPO | I-6064C | Statewide Mobility | NHPIM |  |  |  |  | 2021 | 131492000 |  |  | 131492000 | UNDER CONSTRUCTION.
ROBESON | PEMBROKE | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 0.17 | Highway | Locally Selected | 6 | Lumber River RPO | HL-0009 | Exempt | DP, HF, L | 2022 | 100000 | 2022 | 930000 | 2023 | 8810000 | 2021 | 350000 | 10190000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS.
ROBESON | NC 71 | FAYETTEVILLE | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | Highway | Locally Selected | 6 | Fayetteville Area MPO | HL-0144 | Region C | BGDA, HF(M) | 2026 | 150000 | 2026 | 100000 | 2028 | 900000 | 2025 | 200000 | 1350000
ROBESON | NC 71 |  | AT SR 1312 (OXENDINE SCHOOL ROAD/RED HILL ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Lumber River RPO | HN-0020 | Region C | CRPLT5, T(M) | 2025 | 150000 |  |  | 2026 | 2842000 | 2024 | 408000 | 3400000
ROBESON | NC 71 |  | AT SR 1001 (SHANNON ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Lumber River RPO | HN-0021 | Region C | CRPLT5, T(M) | 2025 | 150000 |  |  | 2026 | 2842000 | 2024 | 408000 | 3400000
ROBESON | NC 130 |  | AT NC 904. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 6 | Lumber River RPO | HN-0022 | Region C | CRPLT5, T(M) | 2025 | 150000 |  |  | 2026 | 2842000 | 2024 | 608000 | 3600000
ROBESON | NC 72 |  | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | Highway | Other | 6 | Lumber River RPO | HO-0014 | Region C | DP, HF, HSIP | 2025 | 120000 | 2025 | 110000 | 2026 | 9341000 | 2024 | 1430000 | 11001000 | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH.
ROBESON | US 74 (FUTURE I-74) | NCDOT | BRIDGES 770466 AND 770118 OVER THE LUMBER RIVER. REINFORCE SHOULDER EMBANKMENTS. |  | Highway | Other | 6 | Lumber River RPO | HO-0021 | Exempt | DP, HF(M) |  |  |  |  | 2025 | 1950000 | 2025 | 305000 | 2255000 | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT.
ROBESON | I-95 | NCDOT | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 9.01 | Highway | Other | 6 | Lumber River RPO | I-6064D | Statewide Mobility | DP, T | [6 empty] | 2022 | 315000 | 315000
ROBESON | SR 1340 (ODOM STREET / PROSPECT ROAD) | NCDOT | AT NC 711 (THIRD STREET) IN PEMBROKE. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNAL HEADS AND PEDESTRIAN REFUGE ISLAND, AND UPGRADE TRAFFIC SIGNAL. FROM NC 711 (THIRD STREET) TO SR 1566 (CORINTH ROAD). INSTALL RECTANGUAR RAPID FLASHING BEACONS. | 0.89 | Highway | Safety | 6 | Lumber River RPO | HS-2006AA | Region C | HSIP |  |  |  |  | 2025 | 835000 |  |  | 835000
ROBESON | NC 71 | NCDOT | FROM LUMBER BRIDGE CITY LIMITS TO PARKTON CITY LIMITS AND FROM PARKTON CITY LIMITS TO US 301. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | Highway | Safety | 6 | Lumber River RPO, Fayetteville Area MPO | HS-2006AD | Region C | HSIP |  |  |  |  | 2024 | 320000 |  |  | 320000
ROBESON | SR 1561 (UNIVERSITY ROAD) | NCDOT | FROM NC 711 TO HAWK DRIVE IN PEMBROKE. INSTALL PEDESTRIAN SIGNALS AND CROSS WALKS AT FIVE LOCATIONS. | 0.51 | Highway | Safety | 6 | Lumber River RPO | HS-2006AE | Division 6 | HSIP |  |  |  |  | 2025 | 300000 |  |  | 300000
ROBESON | SR 1935 (HOWELL ROAD) | NCDOT | CONVERT INTERSECTION OF SR 1924 (BARKER TEN MILE ROAD) AND SR 1935 (HOWELL ROAD) TO AN ALL WAY STOP. REALIGN NORTH LEG OF SR 1005 (TOLARSVILLE ROAD) AT SR 1935 (HOWELL ROAD) AND REMOVE SOUTH LEG. | 0.5 | Highway | Safety | 6 | Lumber River RPO | HS-2006D | Division 6 | HSIP | 2022 | 25000 |  |  | 2024 | 566000 |  |  | 591000 | UNDER CONSTRUCTION.
ROBESON | NC 710 | NCDOT | NC 710 AT SR 1340 (PROSPECT ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | Highway | Safety | 6 | Lumber River RPO | HS-2006I | Region C | HSIP | 2024 | 250000 |  |  | 2025 | 2262000 |  |  | 2512000
ROBESON | US 501/NC 130 | NCDOT | US 501/NC 130 NEAR SR 1134 (KITCHEN ROAD). CURVE IMPROVEMENTS. | 0.14 | Highway | Safety | 6 | Lumber River RPO | HS-2006J | Region C | HSIP | 2024 | 25000 | 2024 | 1000 | 2025 | 410000 |  |  | 436000
ROBESON | I-95 | NCDOT | I-95 FROM MILEMARKER 2.0 TO MILEMARKER 12.45. INSTALL CABLE MEDIAN BARRIER. | 10.45 | Highway | Safety | 6 | Lumber River RPO | HS-2006R | Statewide Mobility | HSIP |  |  |  |  | 2024 | 815000 |  |  | 815000
ROBESON | US 501 | NCDOT | FROM NC 130 TO THE SCOTLAND COUNTY LINE. INSTALL RUMBLE STRIPES. | 5.41 | Highway | Safety | 6 | Lumber River RPO | HS-2006S | Region C | HSIP |  |  |  |  | 2023 | 1051000 |  |  | 1051000 | UNDER CONSTRUCTION.
ROBESON | NC 72 | NCDOT | FROM US 74 TO NC 41 / NC 211. INSTALL RUMBLE STRIPES AND RAISED PAVEMENT MARKERS. | 11.84 | Highway | Safety | 6 | Lumber River RPO | HS-2006T | Region C | HSIP |  |  |  |  | 2023 | 1051000 |  |  | 1051000 | UNDER CONSTRUCTION.
ROBESON | NC 72 | NCDOT | FROM NC 711 TO NC 710. INSTALL RUMBLE STRIPES AND RAISED PAVEMENT MARKERS. | 14.42 | Highway | Safety | 6 | Lumber River RPO | HS-2006U | Region C | HSIP |  |  |  |  | 2023 | 1051000 |  |  | 1051000 | UNDER CONSTRUCTION.
ROBESON | US 501 | NCDOT | NC 130 INTERSECTION IN RAEMON. REALIGN INTERSECTION, REMOVE SLIP LANES, AND ADD RIGHT TURN LANE. |  | Highway | Safety | 6 | Lumber River RPO | HS-2406B | Region C | HSIP | 2025 | 30000 | 2025 | 5000 | 2026 | 1075000 |  |  | 1110000
ROBESON | US 301 | NCDOT | MILEPOST 24.42 TO 32.52 AND MILEPOST 33.865 TO 40.92. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | Highway | Safety | 6 | Lumber River RPO | HS-2406L | Region C | HSIP |  |  |  |  | 2025 | 670000 |  |  | 670000
ROBESON | NC 130 | NCDOT | MILEPOST 10.14 TO 22.23; MILEPOST 5.785 TO 19.004. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | Highway | Safety | 6 | Lumber River RPO | HS-2406M | Region C | HSIP |  |  |  |  | 2026 | 1110000 |  |  | 1110000
ROBESON | NC 710 | NCDOT | AT SR 1339 (DEEP BRANCH ROAD) IN PEMBROKE. CONVERT SIGNALIZED INTERSECTION TO A ROUNDABOUT. | 0.5 | Highway | Safety | 6 | Lumber River RPO | W-5706N | Region C | CRPLT5, HF, L, T(M) |  |  |  |  | 2024 | 4221000 |  |  | 4221000 | RIGHT-OF-WAY IN PROGRESS.
ROBESON | NC 41 (MARTIN LUTHER KING JR DRIVE) | NCDOT | NC 41 (MARTIN LUTHER KING JR DRIVE) AT NC 72 (WEST SECOND STREET) AND SR 1599 (MARTIN LUTHER KING JR DRIVE). CONSTRUCT SIGNALIZED PEDESTRIAN CROSSINGS. | 0.5 | Highway | Safety | 6 | Lumber River RPO | W-5806E | Region C | HSIP |  |  |  |  | 2022 | 315000 |  |  | 315000 | UNDER CONSTRUCTION.
ROBESON | NC 211 (NORTH ROBERTS AVENUE) | NCDOT | AT SR 1531 (SADDLETREE ROAD / CLYBOURN CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | Highway | STI (Prioritization) | 6 | Lumber River RPO | HP-0019 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 |  |  | 4000000
ROBESON | I-95 | NCDOT | SR 1536 (CARTHAGE ROAD/WEST CARTHAGE ROAD) (EXIT 19). IMPROVE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-5879 | Division 6 | NHP |  |  |  |  | 2021 | 15028000 |  |  | 15028000 | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C.
ROBESON | I-95 | NCDOT | SOUTH OF US 301 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 15.7 | Highway | STI (Prioritization) | 6 | Lumber River RPO, Fayetteville Area MPO | I-5987 | Region C | [10 empty] | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. AA BREAK: O FUNDS REPRESENT WEIGH STATION FUNDING.
ROBESON | I-95 | NCDOT | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 10.24 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-5987A | Region C | T | 2021 | 3395000 | 2022 | 3075000 | 2023 | 338809000 |  |  | 345279000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE)
ROBESON | I-95 | NCDOT | CONSTRUCT WEIGH IN MOTION STATION. | 2 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-5987AA | Region C | O |  |  |  |  | 2027 | 4800000 |  |  | 4800000 | O FUNDS REPRESENT STATE PRIMARY MAINTENANCE FUNDS FOR WEIGH STATIONS.
ROBESON | I-95 | NCDOT | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6.28 | Highway | STI (Prioritization) | 6 | Lumber River RPO, Fayetteville Area MPO | I-5987B | Region C | T | 2021 | 3581000 | 2021 | 2624000 | 2023 | 382396000 |  |  | 388601000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE)
ROBESON | I-95 | NCDOT | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 16.52 | Highway | STI (Prioritization) | 6 | Lumber River RPO, Fayetteville Area MPO | I-5987C | Region C | DP, T | [6 empty] | 2022 | 315000 | 315000
ROBESON | US 74 | NCDOT | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | 0.5 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-6011A | Division 6 | BGLT5 | 2025 | 150000 | 2025 | 200000 | 2027 | 8900000 |  |  | 9250000
ROBESON | I-95 | NCDOT | MILE MARKER 13 TO MILE MARKER 22. WIDEN TO EIGHT LANES AND PAVEMENT REHABILITATION. | 9 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-6064 | [11 empty] | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. PROJECT LET WITH I-5879.
ROBESON | I-95 | NCDOT | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 5.75 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-6064A | Region C | DP, T | 2021 | 3087000 | 2021 | 6450000 | 2021 | 218371000 |  |  | 227908000 | UNDER CONSTRUCTION.
ROBESON | I-95 | NCDOT | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN TO EIGHT LANES. | 2.79 | Highway | STI (Prioritization) | 6 | Lumber River RPO | I-6064B | Statewide Mobility | T | 2022 | 8688000 | 2022 | 3425000 | 2022 | 85946000 |  |  | 98059000 | UNDER CONSTRUCTION.
ROBESON | US 74 | NCDOT | NC 72/NC 130. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 6 | Lumber River RPO | R-5751 | Region C | T | 2021 | 325000 |  |  | 2023 | 28286000 |  |  | 28611000 | UNDER CONSTRUCTION.
ROBESON | NC 41 (EAST ELIZABETHTOWN ROAD) | NCDOT | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | 1.85 | Highway | STI (Prioritization) | 6 | Lumber River RPO | R-5888 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 |  |  | 7000000
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | NCDOT | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO SIX LANES AND MODERNIZE ROADWAY. | 1.26 | Highway | STI (Prioritization) | 6 | Lumber River RPO | U-5797 | Division 6 | T | 2023 | 8200000 | 2024 | 2600000 | 2025 | 46045000 |  |  | 56845000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $14,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE).
ROBESON | ROBESON COUNTY | ROBESON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 6 | Lumber River RPO | TK-6158 | Public Transit | 5311, L, S | [6 empty] | 2020 | 800000 | 800000 | FUNDS AUTHORIZED IN PROGRESS
ROBESON | SR 1154 (UNION SCHOOL ROAD) | NCDOT | CSX CROSSING 629606K NEAR PEMBROKE. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Lumber River RPO | RX-2006B | Division 6 | RR |  |  |  |  | 2024 | 1450000 |  |  | 1450000
ROBESON | NC 41 (MARTIN LUTHER KING JR. DRIVE) | NCDOT | CSX CROSSING 631029P IN LUMBERTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Lumber River RPO | RX-2006E | Division 6 | RR |  |  |  |  | 2026 | 446000 |  |  | 446000
ROBESON | SR 1748 (CRENSHAW ROAD) | NCDOT | CSX CROSSING 629581S IN REX. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 6 | Lumber River RPO | RX-2006G | Division 6 | RR |  |  |  |  | 2027 | 417000 |  |  | 417000
ROBESON, CUMBERLAND | I-295 | NCDOT | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | 1.88 | Highway | STI (Prioritization) | 6 | Fayetteville Area MPO | U-2519AA | Region C | NHP, T(M) |  |  |  |  | 2018 | 260442000 |  |  | 260442000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING: $111M FOR CONSTRUCTION, PAYBACK 2018 - 2032.
ROBESON, CUMBERLAND, JOHNSTON, NASH, HALIFAX, WILSON, HARNETT, NORTHAMPTON | I-95 | NCDOT | INSTALL BROADBAND FIBER ALONG I-95 FROM SOUTH CAROLINA LINE TO VIRGINIA STATE LINE. | 181.34 | Highway | Other | 1, 4, 6 | Upper Coastal Plain RPO, Lumber River RPO, Peanut Belt RPO, Fayetteville Area MPO, Mid-Carolina RPO, Rocky Mount Urban Area MPO | I-5986C | Statewide Mobility | DP, T |  |  |  |  | 2021 | 42167000 |  |  | 42167000 | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
ROBESON, HARNETT | VARIOUS | NCDOT | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 6 | Lumber River RPO, Mid-Carolina RPO | W-5206REG | Region C
ROCKINGHAM | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | CONSTRUCT T-HANGAR TAXILANES FOR ADDITION OF T-HANGARS. |  | Aviation | STI (Prioritization) | 7 | Piedmont Triad RPO | AV-5898 | Division 7 | T |  |  |  |  | 2024 | 810000 |  |  | 810000
ROCKINGHAM | SR 1747 (EAST STADIUM DRIVE) | NCDOT | SR 1962 (NORTH PIERCE STREET) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | 0.57 | Bike & Ped | STI (Prioritization) | 7 | Piedmont Triad RPO | EB-5888 | Division 7 | L, TA5T50 |  |  |  |  | 2024 | 1600000 |  |  | 1600000
ROCKINGHAM | US 220 BUSINESS | MAYODAN | EAST JACKSON STREET IN MAYODAN TO MAYO RIVER STATE PARK. CONSTRUCT MULTI-USE PATH. | 1.37 | Bike & Ped | STI (Prioritization) | 7 | Piedmont Triad RPO | EB-5891 | Division 7 | L, TALT5 |  |  |  |  | 2026 | 652000 |  |  | 652000
ROCKINGHAM | SR 2351 (WITTY ROAD) | NCDOT | REPLACE BRIDGE 780017 OVER HAW RIVER. | 0.25 | Highway | Bridges | 7 | Greensboro Urban Area MPO, Piedmont Triad RPO | B-5715 | Division 7 | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | SR 1138 (LINDSEY BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 780140 OVER DAN RIVER. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-5716 | Division 7 | BGOFF | 2023 | 610000 |  |  | 2025 | 12299000 |  |  | 12909000 | RIGHT-OF-WAY IN PROGRESS
ROCKINGHAM | SR 2177 (DAN VALLEY ROAD) | NCDOT | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-5721 | Division 7 | BGLT5 | 2022 | 188000 | 2022 | 336000 | 2023 | 4853000 |  |  | 5377000 | UNDER CONSTRUCTION
ROCKINGHAM | SR 1169 (ISLAND DRIVE) | NCDOT | REPLACE BRIDGE 780277 OVER BEAVER CREEK. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-5722 | Division 7 | BGOFF | 2023 | 200000 |  |  | 2025 | 2000000 |  |  | 2200000
ROCKINGHAM | NC 14 / NC 87 | NCDOT | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | B-6038 | Region D | BFP, NHPB | 2027 | 400000 | 2027 | 740000 | 2028 | 7603000 |  |  | 8743000
ROCKINGHAM | SR 1700 (FISHER HILL ROAD) | NCDOT | REPLACE BRIDGE 780176 OVER NC 14/NC 87. |  | Highway | Bridges | 7 | Piedmont Triad RPO | BR-0096 | Division 7 | BGOFF |  |  |  |  | 2026 | 2700000 |  |  | 2700000 | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM
ROCKINGHAM | SR 2150 (RIVER ROAD) | NCDOT | REPLACE BRIDGE 780123 OVER US 220/US 311. |  | Highway | Bridges | 7 | Piedmont Triad RPO | BR-0141 | Division 7 | BGOFF |  |  |  |  | 2026 | 4100000 |  |  | 4100000 | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM
ROCKINGHAM | SR 1535 (PRICE ROAD) | NCDOT | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | 0.25 | Highway | Bridges | 7 | Piedmont Triad RPO | HB-0035 | Division 7 | BGOFF | 2025 | 410000 | 2025 | 300000 | 2026 | 4500000 |  |  | 5210000
ROCKINGHAM | US 220 / FUTURE I-73 | NCDOT | NC 68 INTERSECTION - CONVERT AT-GRADE INTERSECTION TO INTERCHANGE | 1 | Highway | Pre-STI (Historic) | 7 | Piedmont Triad RPO | R-2413CA | Pre-STI (Transition) | [10 empty] | IN PROGRESS
ROCKINGHAM | FUTURE I-73 / US 220 | NCDOT | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | 1 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO | I-5898 | Region D | T | 2022 | 1500000 | 2022 | 1600000 | 2025 | 23000000 |  |  | 26100000 | RIGHT-OF-WAY IN PROGRESS
ROCKINGHAM | NC 87 | NCDOT | SR 1998 (WENTWORTH STREET) / SR 1001 (SANDY CROSS ROAD). INTERSECTION REALIGNMENT. | 0.5 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO | R-5704 | Region D | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | NC 65 / NC 87 | NCDOT | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO US 158 / US 29 BUSINESS (FREEWAY DRIVE) IN REIDSVILLE. UPGRADE ROADWAY. |  | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO | R-5766 | Division 7 | BGANY | 2030 | 18600000 | 2030 | 4800000 | 2033 | 34400000 |  |  | 57800000
ROCKINGHAM | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 7 | Piedmont Triad RPO | TK-6159 | Public Transit | 5311, L, S | [6 empty] | 2020 | 708000 | 708000 | FUNDS AUTHORIZED IN PROGRESS
ROCKINGHAM, GUILFORD | US 220 / FUTURE I-73 | NCDOT | HAW RIVER TO NC 68-US 220 INTERSECTION | 5.071 | Highway | Pre-STI (Historic) | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | R-2413C | [11 empty] | UNDER CONSTRUCTION
ROCKINGHAM, GUILFORD | NC 65 / NC 68 | NCDOT | US 158 IN STOKESDALE IN GUILFORD COUNTY TO I-73 / US 220 IN ROCKINGHAM COUNTY. MULTIPLE INTERSECTION IMPROVEMENTS ALONG CORRIDOR. | 3.61 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | R-5823 | Division 7 | BGLT5 | 2030 | 10500000 | 2030 | 424000 | 2032 | 29200000 |  |  | 40124000
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | NCDOT | NORTH OF I-785 IN GREENSBORO TO US 158 / NC 14 IN REIDSVILLE. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 15.59 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | R-5889 | Region D
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | NCDOT | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE TO INTERSTATE STANDARDS. | 11.12 | Highway | STI (Prioritization) | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | R-5889B | Not Funded | T | NOT FUNDED | 9364000 | NOT FUNDED | 5430000 | NOT FUNDED | 116450000 | NOT FUNDED |  | 131244000
ROWAN | GRANITE QUARRY VARIOUS | GRANITE QUARRY | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | BL-0088 | Region D | L, TADA | 2025 | 90000 | 2025 | 10000 | 2026 | 380000 | 2024 | 70000 | 550000
ROWAN | VARIOUS | SALISBURY | CONSTRUCT SIDEWALKS AT SELECTED LOCATIONS IN SALISBURY. |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | C-4908 | Exempt
ROWAN | ARLINGTON AVENUE | SALISBURY | ARLINGTON AVENUE TO WALMART PARKING LOT |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | C-4908D | Exempt | [10 empty] | COMPLETE
ROWAN | NEWSOME ROAD | SALISBURY | SR 1002 (BRINGLE FERRY ROAD) TO SR 1004 (STOKES FERRY ROAD) |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | C-4908F | Exempt | [10 empty] | PROJECT DELETED AT MPO REQUEST
ROWAN | MAIN STREET | SALISBURY | "D" AVENUE TO SUNSET DRIVE | 0.43 | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | C-4908H | Exempt | [10 empty] | UNDER CONSTRUCTION
ROWAN | GRANTS CREEK GREENWAY | SALISBURY | VICINITY OF FORESTDALE DRIVE TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT LOW-WATER BRIDGE GREENWAY CONNECTION. |  | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | EB-5619A | Division 9 | [10 empty] | COMPLETE
ROWAN | GRANTS CREEK GREENWAY | SALISBURY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO 1000 FEET SOUTH OF STATESVILLE BOULEVARD. CONSTRUCT MULTI-USE PATH. | 0.61 | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | EB-5619B | Division 9 | BGDA, L | 2020 | 825000 |  |  | 2025 | 1735000 |  |  | 2560000 | RIGHT-OF-WAY IN PROGRESS
ROWAN | GRANTS CREEK GREENWAY | SALISBURY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | Bike & Ped | Locally Selected | 9 | Cabarrus-Rowan MPO | EB-5619C | Division 9 | BGDA, L, TADA | 2025 | 65000 | 2025 | 45000 | 2026 | 2044000 | 2024 | 675000 | 2829000
ROWAN | GRANTS CREEK GREENWAY | SALISBURY | KELSEY SCOTT PARK TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT MULTI-USE PATH. |  | Bike & Ped | Other | 9 | Cabarrus-Rowan MPO | EB-5619 | Division 9 | [10 empty] | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SALISBURY
ROWAN | VARIOUS | SALISBURY | SPORTS COMPLEX, RYAN STREET TO CELEBRATION DRIVE AND SOUTH BOUNDARY STREET, HILLBORO STREET TO HILLS STREET |  | Bike & Ped | Pre-STI (Historic) | 9 | Cabarrus-Rowan MPO | C-4908B | Exempt | [10 empty] | COMPLETE
ROWAN | VARIOUS | SALISBURY | SALISBURY HIGH SCHOOL, ON VARIOUS STREETS AROUND HIGH SCHOOL |  | Bike & Ped | Pre-STI (Historic) | 9 | Cabarrus-Rowan MPO | C-4908C | Exempt | [10 empty] | COMPLETE
ROWAN | THIRD STREET GREENWAY | SPENCER | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 5.77 | Bike & Ped | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | EB-5861 | Division 9 | L(M), TAANY |  |  |  |  | 2026 | 4287000 | 2024 | 185000 | 4472000
ROWAN | SR 2739 (NORTH MAIN STREET) | KANNAPOLIS | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 0.92 | Bike & Ped | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | EB-5921 | Division 9 | L, TAANY | 2030 | 1600000 |  |  | 2033 | 2600000 | 2026 | 450000 | 4650000 | COORDINATE WITH U-6062
ROWAN | SR 1724 (HURLEY SCHOOL ROAD) | NCDOT | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | Highway | Bridges | 9 | Cabarrus-Rowan MPO | B-5772 | Division 9 | BGOFF | 2021 | 77000 | 2021 | 31000 | 2022 | 3009000 |  |  | 3117000 | UNDER CONSTRUCTION
ROWAN | NC 152 | NCDOT | WIDEN PAVEMENT AND CONSTRUCT ROUNDABOUT AT THE INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. |  | Highway | Economic Development | 9 | Cabarrus-Rowan MPO | HE-0009 | Division 9 | T |  |  |  |  | 2025 | 5411000 | 2022 | 1489000 | 6900000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS.
ROWAN | NC 152 | NCDOT | NC 152, INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. INTERMEDIATE INTERSECTION IMPROVEMENTS. WIDEN PAVEMENT AND CONSTRUCT TURN LANES FOR PHASE I OF ROADWAY IMPROVEMENTS. | 0.4 | Highway | Economic Development | 9 | Cabarrus-Rowan MPO | HE-0009A | Division 9 | T |  |  |  |  | 2023 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION. CONSTRUCTION BY STATE FORCES. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS.
ROWAN | SR 2120 (LONG FERRY ROAD) | NCDOT | SR 2182 (I-85 SERVICE ROAD) NEAR SPENCER. CONSTRUCT RIGHT-TURN LANE ON SR 2120, AND CONSTRUCT CUL-DE-SAC, REMOVE RESIDUAL PAVEMENT AND STRENGTHEN REMAINING PAVEMENT ON SR 2182. | 0.6 | Highway | Economic Development | 9 | Cabarrus-Rowan MPO | U-6237 | Division 9 | T |  |  | 2021 | 50000 | 2021 | 365000 |  |  | 415000 | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHEWY.COM
ROWAN | I-85 | NCDOT | US 29 / US 601 IN CHINA GROVE TO US 601 (JAKE ALEXANDER BOULEVARD) IN SALISBURY AND FROM SOUTH OF US 52 IN SALISBURY TO NORTH OF SR 2120 (LONG FERRY ROAD) IN SPENCER. PAVEMENT REHABILITATION. | 1.08 | Highway | Interstate Maintenance | 9 | Cabarrus-Rowan MPO | I-5858 | Statewide Mobility | NHPIM |  |  |  |  | 2019 | 12012000 |  |  | 12012000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033
ROWAN | VARIOUS | SALISBURY | CITY OF SALISBURY SIGNAL SYSTEM UPGRADE. |  | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | HL-0005 | Division 9 | BGDA, L |  |  |  |  | 2022 | 429000 |  |  | 429000
ROWAN | BRENNER AVENUE | SALISBURY | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 0.21 | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | HL-0049 | Division 9 | BGDA, L | 2025 | 14000 |  |  | 2025 | 791000 | 2023 | 220000 | 1025000
ROWAN | US 29 MAIN STREET | SALISBURY | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 0.52 | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | HL-0064 | Division 9 | BGDA, L |  |  | 2024 | 3261000 | 2025 | 6011000 | 2024 | 10000 | 9282000
ROWAN | NEW ROUTE | NCDOT | SR 1211 (KIMBALL ROAD) EXTENSION, NORTH CHAPEL STREET TO SR 1221 (BOSTIAN ROAD) IN LANDIS. CONSTRUCT TWO-LANE CONNECTOR ON NEW LOCATION. | 0.27 | Highway | Locally Selected | 9 | Cabarrus-Rowan MPO | U-5608 | Division 9 | [10 empty] | PROJECT COMPLETED
ROWAN | EAST FISHER STREET | SALISBURY | REPLACE 790138 OVER NORFOLK SOUTHERN RAILROAD BETWEEN SOUTH LONG STREET AND SOUTH LEE STREET IN SALISBURY. | 0.25 | Highway | Municipal Bridge | 9 | Cabarrus-Rowan MPO | HM-0001 | Division 9 | BFPOFF |  |  |  |  | 2024 | 2000000 |  |  | 2000000
ROWAN | HORAH STREET | SALISBURY | BRENNER AVENUE TO PARTEE STREET |  | Highway | Other | 9 | Cabarrus-Rowan MPO | C-4908A | Exempt | [10 empty] | PROJECT DELETED AT MPO REQUEST
ROWAN | OLD CONCORD ROAD | SALISBURY | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | Highway | Other | 9 | Cabarrus-Rowan MPO | C-5603D | Exempt | CMAQ, L(M) | 2024 | 15000 |  |  | 2025 | 1950000 |  |  | 1965000
ROWAN | BRENNER AVENUE | SALISBURY | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | Highway | Other | 9 | Cabarrus-Rowan MPO | C-5603H | Exempt | CMAQ, CRPANY, L, L(M) |  |  |  |  | 2025 | 1869000 |  |  | 1869000 | $676,032 IN CMAQ TRANSFERRED FROM BL-0034
ROWAN | SR 1007 (JAKE ALEXANDER BOULEVARD) | NCDOT | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | 0.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2009D | Division 9 | HSIP | 2022 | 50000 | 2022 | 20000 | 2023 | 520000 |  |  | 590000 | UNDER CONSTRUCTION
ROWAN | SR 1002 (OLD CONCORD ROAD) | NCDOT | SR 1002 (OLD CONCORD ROAD) FROM JAKE ALEXANDER BOULEVARD IN SALISBURY TO THE CABARRUS COUNTY LINE. INSTALL PAVEMENT MARKINGS. | 10.94 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2009E | Division 9 | HSIP |  |  |  |  | 2023 | 396000 |  |  | 396000
ROWAN | NC 152 | NCDOT | NC 152 AT NC 153 NEAR CHINA GROVE. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2009I | Region D | HSIP | 2024 | 20000 |  |  | 2024 | 350000 |  |  | 370000
ROWAN | SR 1002 (OLD CONCORD ROAD) | NCDOT | MARTIN LUTHER KING JR. AVENUE SOUTH INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL/UPGRADE PEDESTRIAN SIGNALS AND OTHER PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | HS-2409B | Division 9 | HSIP |  |  | 2025 | 30000 | 2026 | 160000 |  |  | 190000
ROWAN | NC 153 (RICE STREET) | NCDOT | NC 153 (RICE STREET) AT SR 1197 (CANNON FARM ROAD / MT MORIAH CHURCH ROAD) IN CHINA GROVE. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | Safety | 9 | Cabarrus-Rowan MPO | W-5709E | Region D | BGANY |  |  |  |  | 2024 | 2500000 |  |  | 2500000 | RIGHT-OF-WAY IN PROGRESS
ROWAN | NC 152 | NCDOT | SR 1509 (MILLER ROAD) INTERSECTION IN CHINA GROVE. CONSTRUCT ROUNDABOUT. |  | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | HP-0028 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 |  |  | 6100000
ROWAN | NC 150 | NCDOT | SR 1526 (ROWAN MILL ROAD) AND SR 1526 (SHERRILLS FORD ROAD) INTERSECTIONS IN SHERRILLS FORD AND SALISBURY. ADD STORAGE AND TURN LANES PER THE ROAD PLANS FOR U-5900 TIP PROJECT |  | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | HP-0029 | Region D | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 |  |  | 4100000
ROWAN | I-85 | NCDOT | SR 2180 (LANE STREET) IN CABARRUS COUNTY TO US 29 / US 601 CONNECTOR IN ROWAN COUNTY | 6.49 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | I-3802B | Statewide Mobility | [10 empty] | COMPLETE - DESIGN-BUILD PROJECT
ROWAN | I-85 | NCDOT | SR 1221 (OLD BEATTY FORD ROAD) NEAR LANDIS. CONVERT GRADE SEPARATION TO INTERCHANGE. | 1 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | I-3804 | Division 9 | [10 empty] | INCLUDED IN I-3802B - DESIGN-BUILD PROJECT
ROWAN | US 52 | NCDOT | PROPOSED ROCKWELL BYPASS. CONSTRUCT 3-LANE FACILITY ON NEW LOCATION. | 3.63 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | R-5860B | Not Funded | NHP | NOT FUNDED | 8200000 | NOT FUNDED | 500000 | NOT FUNDED | 22300000 | NOT FUNDED |  | 31000000
ROWAN | US 52 | NCDOT | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT 3-LANE FACILITY ON NEW LOCATION. | 4.63 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | R-5860C | Not Funded | NHP | NOT FUNDED | 5500000 | NOT FUNDED | 900000 | NOT FUNDED | 36500000 | NOT FUNDED |  | 42900000
ROWAN | SR 2528 (JULIAN ROAD) | NCDOT | US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2667 (SUMMIT PARK DRIVE) IN SALISBURY. WIDEN TO FOUR LANE DIVIDED FACILITY WITH BIKE-PED ACCOMMODATIONS. | 1.28 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5738 | Division 9 | T |  |  |  |  | 2022 | 14995000 |  |  | 14995000 | UNDER CONSTRUCTION
ROWAN | NEW ROUTE | NCDOT | SR 2576 (BENDIX DRIVE) TO US 52 (EAST INNES STREET) AT NEWSOME ROAD IN SALISBURY. CONSTRUCT A NEW MULTI-LANE ROADWAY. | 0.6 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5820 | [11 empty] | FUNDING FOR PART B REFLECTS REIMBURSEMENT TO CITY OF SALISBURY
ROWAN | NEW ROUTE | NCDOT | SR 2576 (BENDIX DRIVE) TO SR 1006 (FAITH ROAD) IN SALISBURY. | 0.42 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5820A | Division 9 | T |  |  |  |  | 2019 | 2609000 |  |  | 2609000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.023 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
ROWAN | NEW ROUTE | NCDOT | SR 1006 (FAITH ROAD) TO US 52 (EAST INNES STREET) IN SALISBURY. | 0.1 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5820B | Division 9 | T |  |  |  |  | 2020 | 1100000 |  |  | 1100000
ROWAN | NEW ROUTE (AIRPORT PARKWAY) | NCDOT | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2538 (PEELER ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY. | 3.63 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-5901 | Division 9 | BGANY | 2030 | 19600000 | 2030 | 7900000 | 2033 | 52090000 |  |  | 79590000
ROWAN | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | NCDOT | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | 4.26 | Highway | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | U-6062 | Division 9 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35800000 |  |  | 80400000 | COORDINATE WITH EB-5921
ROWAN | SR 1002 (BRINGLE FERRY ROAD) | SALISBURY | LONG STREET TO NEWSOME ROAD |  | Highway | Transition | 9 | Cabarrus-Rowan MPO | C-4908E | Exempt | [10 empty] | COMPLETE
ROWAN | US 70 (STATESVILLE BOULEVARD) | SALISBURY | US 601 (JAKE ALEXANDER BOULEVARD) |  | Highway | Transition | 9 | Cabarrus-Rowan MPO | C-4908G | Exempt | [10 empty] | UNDER CONSTRUCTION
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | REPLACMENT BUSES |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Cabarrus-Rowan MPO | TA-5181 | Public Transit | 5307, L, S | [6 empty] | 2020 | 8235000 | 8235000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | EXPANSION VEHICLE (ADA PARATRANSIT, ADMINISTRATION) |  | Public Transportation (Transit) | Capital (Non-STI) | 9 |  | TA-5182 | Public Transit | 5339, L | [6 empty] | 2020 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | SALISBURY TRANSIT ( CITY OF SALISBURY) | SALISBURY TRANSIT ( CITY OF SALISBURY) | REPLACE FOUR TRANSIT BUSES THAT HAVE EXCEEDED THEIR USEFUL LIFE, AND REPLACE VEHICLE RELATED EQUIPMENT SUCH AS FARE BOXES, DESTINATION SIGNS, CAMERA SYSTEMS, AND AUTOMATED VOICE ANNUNCIATION SYSTEMS. |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Cabarrus-Rowan MPO | TC-0023 | Public Transit | 5339(b), L | [6 empty] | 2021 | 4560000 | 4560000
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | PREVENTIVE MAINTENANCE FOR BUS AND BUS FACILITY, FACILITY IMPROVEMENTS AND REPAIRS, AUTOMATIC BUS WASHER, SHOP EQUIPMENT, FUELING SYSTEM, SECURITY GATE UPGRADE, |  | Public Transportation (Transit) | Capital (Non-STI) | 9 |  | TD-5302 | Public Transit | 5339, L | [6 empty] | 2020 | 2025000 | 2025000
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | SAFETY & SECURITY MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 9 | Cabarrus-Rowan MPO | TS-5133 | Public Transit | 5307 | [6 empty] | 2020 | 28000 | 28000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | OPERATING |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Cabarrus-Rowan MPO | TO-5135 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 3560000 | 3560000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | OPERATING - FREE FARE |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Cabarrus-Rowan MPO | TO-5139 | Public Transit | CMAQ, L | [6 empty] | 2020 | 336000 | 336000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 9 | Cabarrus-Rowan MPO | TO-5201 | Public Transit | CMAQ, SMAP | [6 empty] | 2020 | 904000 | 904000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | ROWAN COUNTY | ROWAN COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 9 | Cabarrus-Rowan MPO | TK-6160 | Public Transit | 5311, L, S | [6 empty] | 2020 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Planning | 9 | Cabarrus-Rowan MPO | TP-5150 | Public Transit | 5303, L, S | [6 empty] | 2020 | 170000 | 170000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | PREVENTIVE MAINTENANCE - BUS, FACILITIES |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Cabarrus-Rowan MPO | TG-5232 | Public Transit | 5307, L | [6 empty] | 2020 | 3336000 | 3336000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Cabarrus-Rowan MPO | TG-5233 | Public Transit | 5307, L | [6 empty] | 2020 | 1120000 | 1120000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | ROUTINE CAPITAL - ADA SERVICES |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Cabarrus-Rowan MPO | TG-5260 | Public Transit | 5307, L | [6 empty] | 2020 | 704000 | 704000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | CITY OF SALISBURY | AVL SYSTEM |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 9 | Cabarrus-Rowan MPO | TG-6179 | Public Transit | 5339, L | [6 empty] | 2020 | 1400000 | 1400000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | HENDERSON GROVE CHURCH ROAD | NCDOT | CLOSE RAILROAD CROSSING #724 362M AND CONSTRUCT NEW LOCATION TO SR 2528 (JULIAN ROAD) IN SALISBURY. |  | Rail | Rail-Highway Grade Crossing Closure | 9 | Cabarrus-Rowan MPO | Y-5500IA | Division 9 | RR |  |  |  |  | 2024 | 4900000 |  |  | 4900000
ROWAN | RAILROAD NORFOLK SOUTHERN | NCDOT | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | P-5726 | Region D | T |  |  |  |  | 2026 | 13600000 |  |  | 13600000
ROWAN | NORFOLK SOUTHERN | NCDOT | SALISBURY TRAIN STATION SECOND PLATFORM AND PEDESTRIAN UNDERPASS. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | P-5726A | Region D | T |  |  |  |  | 2025 | 2500000 |  |  | 2500000
ROWAN | NORFOLK SOUTHERN | SALISBURY | SALISBURY NORFOLK SOUTHERN CROSSOVER RELOCATION. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | P-5726B | Region D | T |  |  |  |  | 2025 | 4000000 |  |  | 4000000
ROWAN | NORFOLK SOUTHERN | NCDOT | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | P-5733 | Division 9 | CMAQ, T | 2025 | 2000000 |  |  | 2026 | 8999000 | 2024 | 720000 | 11719000 | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0.
ROWAN | NCRR / NS MAIN LINE | NCDOT | SR 2120 (LONG FERRY RD). CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING #715307NR. |  | Rail | STI (Prioritization) | 9 | Cabarrus-Rowan MPO | RP-0006 | Region D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15000000 |  |  | 20200000
ROWAN, CABARRUS | US 52 | NCDOT | PROPOSED MISENHEIMER BYPASS TO GRANITE QUARRY BYPASS.WIDEN TO 3-LANE ROADWAY. | 4.54 | Highway | STI (Prioritization) | 9, 10 | Cabarrus-Rowan MPO | R-5860 | Division 9, 10
ROWAN, CABARRUS | US 52 | NCDOT | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. WIDEN TO 3-LANE ROADWAY. | 4.54 | Highway | STI (Prioritization) | 9, 10 | Cabarrus-Rowan MPO | R-5860A | Division 9, 10 | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 50500000 |  |  | 79800000
RUTHERFORD | THERMAL BELT RAIL TRAIL | NCDOT | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | 6.18 | Bike & Ped | STI (Prioritization) | 13 | Foothills RPO | EB-5915 | Division 13 | HF(M), L(M), TAANY |  |  |  |  | 2022 | 526000 |  |  | 526000 | UNDER CONSTRUCTION.
RUTHERFORD | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | NCDOT | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 2.78 | Bike & Ped | STI (Prioritization) | 13 | Foothills RPO | EB-5966 | Division 13 | L, TAANY | 2025 | 520000 |  |  | 2026 | 2100000 | 2024 | 150000 | 2770000
RUTHERFORD | NEW ROUTE | NCDOT | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | 0.14 | Highway | Appalachian Development Highway System | 13 | Foothills RPO | HA-0005 | Exempt | ADHSL | 2025 | 15000 |  |  | 2026 | 900000 | 2022 | 15000 | 930000 | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045
RUTHERFORD | SR 1306 (BILLS CREEK ROAD) | NCDOT | REPLACE BRIDGE 800628 OVER LAKE LURE DAM AND BROAD RIVER. | 0.25 | Highway | Bridges | 13 | Foothills RPO | B-5871 | Division 13 | BGOFF | 2025 | 4600000 |  |  | 2028 | 20800000 |  |  | 25400000 | RIGHT-OF-WAY IN PROGRESS.
RUTHERFORD | SR 2125 (HARRIS HENRIETTA ROAD) | NCDOT | REPLACE BRIDGE 800145 OVER FLOYDS CREEK. | 0.25 | Highway | Bridges | 13 | Foothills RPO | B-6047 | Division 13 | BGOFF | 2024 | 210000 |  |  | 2026 | 2700000 |  |  | 2910000 | RIGHT-OF-WAY IN PROGRESS.
RUTHERFORD | US-221A (CHARLOTTE ROAD / MAIN STREET) | NCDOT | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | Highway | Locally Selected | 13 | Foothills RPO | HL-0065 | Division 13 | 5311, DP, HF(M), HSIP, L | 2024 | 1050000 | 2024 | 2110000 | 2025 | 20110000 | 2023 | 1140000 | 24410000 | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT
RUTHERFORD | US 64/ US 74A |  | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 13 | Foothills RPO | HN-0019 | Region G | CRP550, T(M) | 2025 | 3300000 | 2025 | 250000 | 2026 | 2900000 | 2024 | 650000 | 7100000
RUTHERFORD | US 221 | NCDOT | SOUTH CAROLINA STATE LINE TO SOUTH OF FLOYD'S CREEK | 3.3 | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-2233AA | Division 13 | [10 empty] | COMPLETE
RUTHERFORD | US 221 | NCDOT | SOUTH OF FLOYD'S CREEK TO NORTH OF US 74 BYPASS | 6.2 | Highway | Pre-STI (Historic) | 13 | Foothills RPO | R-2233AB | [11 empty] | COMPLETE
RUTHERFORD | SR 1510 (HUDLOW ROAD) | NCDOT | US 221A TO NC 64. UPGRADE GUARDRAIL. | 5.39 | Highway | Safety | 13 | Foothills RPO | HS-2013G | Division 13 | HSIP |  |  |  |  | 2023 | 497000 |  |  | 497000 | UNDER CONSTRUCTION.
RUTHERFORD | SR 1006 (BOSTIC-SUNSHINE HIGHWAY) | NCDOT | SR 1007 TO NC 226 NEAR BOSTIC. INSTALL GUARDRAIL. | 9.78 | Highway | Safety | 13 | Foothills RPO | HS-2013N | Division 13 | HSIP |  |  |  |  | 2024 | 875000 |  |  | 875000
RUTHERFORD | US 221 | NCDOT | SOUTH CAROLINA STATE LINE TO NORTH OF SR 1366 (ROPER LOOP ROAD). WIDEN TO MULTI-LANES WITH BYPASS OF RUTHERFORDTON ON NEW LOCATION. | 18.2 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-2233
RUTHERFORD | US 221 | NCDOT | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 4.52 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-2233BA | Division 13 | T | 2025 | 18100000 | 2025 | 3000000 | 2028 | 160950000 |  |  | 182050000 | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
RUTHERFORD | US 221 | NCDOT | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | 3.51 | Highway | STI (Prioritization) | 13 | Foothills RPO | R-2233BB | Division 13 | T | 2021 | 20000000 |  |  | 2022 | 132797000 |  |  | 152797000 | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
RUTHERFORD | SR 2241 (OAK STREET) | NCDOT | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | 0.64 | Highway | STI (Prioritization) | 13 | Foothills RPO | U-5833 | Division 13 | T | 2020 | 450000 |  |  | 2020 | 7530000 | 2020 | 1050000 | 9030000 | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $347,260 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
RUTHERFORD | RUTHERFORDTON | RUTHERFORDTON | PURCHASE FOUR ELECTRIC VEHICLES. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 13 | Foothills RPO | TN-6127 | Exempt | CRP550, L(M) | [6 empty] | 2025 | 291000 | 291000
RUTHERFORD | RUTHERFORD COUNTY | RUTHERFORD COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 13 | Foothills RPO | TK-6161 | Public Transit | 5311, L, S | [6 empty] | 2020 | 788000 | 788000 | FUNDS AUTHORIZED IN PROGRESS
RUTHERFORD, BURKE | US 64 / NC 18; US 64 / US 74 | NCDOT | MORGANTON NORTHEAST MUNICIPAL LIMIT TO BURKE COUNTY LINE; SR 1008 (BILLS CREEK ROAD) TO RUTHERFORDTON WESTERN MUNICIPAL LIMIT. INSTALL LONG LIFE PAVEMENT MARKINGS. | 17.46 | Highway | Safety | 13 | Foothills RPO, Greater Hickory MPO | HS-2413A | Region G | HSIP |  |  |  |  | 2025 | 675000 |  |  | 675000
RUTHERFORD, BURKE, McDOWELL | US 64 | NCDOT | RUTHERFORDTON NORTHEAST MUNICIPAL LIMIT TO MORGANTON SOUTHWEST MUNICIPAL LIMIT. INSTALL LONG LIFE PAVEMENT MARKINGS. | 28.03 | Highway | Safety | 13 | Foothills RPO, Greater Hickory MPO | HS-2413B | Region G | HSIP |  |  |  |  | 2025 | 775000 |  |  | 775000
RUTHERFORD, BURKE, MITCHELL, YANCEY | VARIOUS | NCDOT | VARIOUS SR LOCATIONS. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 13 | Foothills RPO, Greater Hickory MPO, High Country RPO | W-5813B | Division 13 | HSIP |  |  |  |  | 2022 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION.
SAMPSON | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | REHABILITATE RUNWAY. |  | Aviation | STI (Prioritization) | 3 | Mid-Carolina RPO | AV-5823 | Division 3 | T |  |  |  |  | 2025 | 2200000 | 2024 | 232000 | 2432000
SAMPSON | US 13 | NCDOT | REPLACE BRIDGE 810009 OVER SOUTH RIVER OVERFLOW. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-4635 | Highway Fund | HFB |  |  |  |  | 2021 | 2250000 |  |  | 2250000 | UNDER CONSTRUCTION.
SAMPSON | NC 24 | NCDOT | REPLACE BRIDGE 810056 OVER SIX RUNS CREEK. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-4636 | Statewide Mobility | BFP, HFB | 2020 | 390000 |  |  | 2029 | 9900000 |  |  | 10290000 | RIGHT-OF-WAY IN PROGRESS.
SAMPSON | SR 1817 (BRADSHAW ROAD) | NCDOT | REPLACE BRIDGE 810188 OVER WARD SWAMP. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-5310 | Division 3 | BGOFF | 2023 | 100000 |  |  | 2024 | 1850000 |  |  | 1950000 | RIGHT-OF-WAY IN PROGRESS.
SAMPSON | SR 1904 (PINE RIDGE ROAD) | NCDOT | REPLACE BRIDGE 810248 OVER SIX RUNS CREEK. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-5621 | Division 3 | BGOFF | 2021 | 154000 |  |  | 2022 | 2500000 |  |  | 2654000 | UNDER CONSTRUCTION.
SAMPSON | SR 1206 (WRIGHT BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 810072 OVER GREAT COHARIE CREEK. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | B-6049 | Division 3 | BGOFF | 2023 | 340000 |  |  | 2024 | 1901000 |  |  | 2241000 | UNDER CONSTRUCTION.
SAMPSON | SR 1804 (HOUSES MILL ROAD) | NCDOT | REPLACE BRIDGE 810178 OVER SEVENMILE SWAMP. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | BR-0121 | Division 3 | DP |  |  |  |  | 2021 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
SAMPSON | SR 1703 (OLD GOLDSBORO ROAD) | NCDOT | REPLACE BRIDGE 810348 OVER BEAVERDAM CREEK. | 0.25 | Highway | Bridges | 3 | Mid-Carolina RPO | BR-0122 | Division 3 | DP |  |  |  |  | 2021 | 727000 |  |  | 727000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
SAMPSON | I-40 | NCDOT | I-40 FROM THE JOHNSTON COUNTY LINE (MILE MARKER 340) TO THE DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | 20.18 | Highway | Interstate Maintenance | 3 | Mid-Carolina RPO | HI-0011 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2028 | 22399000 |  |  | 22399000
SAMPSON | NC 24 | NCDOT | WEST OF SR 1262 (AIRPORT ROAD) TO EAST OF US 421. |  | Highway | Pre-STI (Historic) | 3 | Mid-Carolina RPO | R-2303DA | [11 empty] | COMPLETED.
SAMPSON | NC 24 | NCDOT | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 4.77 | Highway | STI (Prioritization) | 3 | Mid-Carolina RPO | R-2303E | Division 3 | T | 2020 | 4395000 |  |  | 2020 | 38396000 | 2020 | 5055000 | 47846000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
SAMPSON | NC 24 | NCDOT | SR 1404 (DOWDY ROAD) TO SR 1303 (MITCHELL LOOP ROAD). | 6.12 | Highway | Transition | 3 | Mid-Carolina RPO | R-2303C | Pre-STI (Transition) | [10 empty] | COMPLETED.
SAMPSON | NC 24 | NCDOT | SR 1303 (MITCHELL LOOP ROAD) TO US 421/US 701/SR 1296 (SUNSET AVENUE). | 6.9 | Highway | Transition | 3 | Mid-Carolina RPO | R-2303D | Pre-STI (Transition) | [10 empty] | COMPLETED.
SAMPSON | SAMPSON COUNTY | SAMPSON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 3 | Mid-Carolina RPO | TK-6162 | Public Transit | 5311, L, S | [6 empty] | 2020 | 632000 | 632000 | FUNDS AUTHORIZED IN PROGRESS
SAMPSON, CUMBERLAND | NC 24 | NCDOT | SR 1853 (JOHN NUNNERY ROAD) IN CUMBERLAND COUNTY TO SR 1404 (DOWDY ROAD) IN SAMPSON COUNTY. | 6.95 | Highway | Pre-STI (Historic) | 3, 6 | Mid-Carolina RPO | R-2303B | Pre-STI (Transition) | [10 empty] | COMPLETED.
SAMPSON, CUMBERLAND, DUPLIN | NC 24 | NCDOT | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO I-40 IN DUPLIN COUNTY AT WARSAW. FOUR LANES DIVIDED, PART ON NEW LOCATION. | 39.7 | Highway | STI (Prioritization) | 3, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Eastern Carolina RPO | R-2303
SAMPSON, DUPLIN | NC 24 | NCDOT | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | 9.61 | Highway | STI (Prioritization) | 3 | Mid-Carolina RPO, Eastern Carolina RPO | R-2303F | Not Funded | T | NOT FUNDED | 35700000 | NOT FUNDED | 2300000 | NOT FUNDED | 338100000 | NOT FUNDED |  | 376100000 | PLANNING/DESIGN IN PROGRESS.
SCOTLAND | SR 1108 (WEST BOULEVARD) | LAURINBURG | GLASGOW DRIVE TO EAST OF US 15 / US 401 / US 501 (MCCOLL ROAD) IN LAURINBURG. PROVIDE PEDESTRIAN ACCOMMODATIONS AT US 15 / US 401 / US 501 INTERSECTION AND ACROSS US 74. |  | Bike & Ped | Locally Selected | 8 | Lumber River RPO | EB-5872B | Exempt
SCOTLAND | SR 1107 (ATKINSON STREET) | NCDOT | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-5865 | Division 8 | L, TA5T50 | 2025 | 100000 | 2025 | 90000 | 2027 | 930000 | 2022 | 76000 | 1196000
SCOTLAND | SR 1108 (WEST BOULEVARD) | LAURINBURG | SR 1105 (TURNPIKE ROAD) TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE, AND PROVIDE PEDESTRIAN ACCOMMODATIONS AT US 15 / US 401 / US 501 INTERSECTION AND ACROSS US 74. | 1.2 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-5872 | Division 8 | [10 empty] | PROJECT LENGTH REFLECTS PARTS A ONLY- PART B IS NON-STI PROJECT; EB 5872C PROJECT BREAK DELETED WORK TO BE ACCOMPLISHED UNDER EB-5872A.
SCOTLAND | SR 1108 (WEST BOULEVARD) | NCDOT | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE. | 1.27 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-5872A | Division 8 | L, TA5T50 | 2026 | 166000 |  |  | 2028 | 436000 | 2024 | 87000 | 689000
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) | NCDOT | SR 1674 (LAUCHWOOD DRIVE) TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS. | 1 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-6015
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) | NCDOT | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.52 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-6015A | Division 8 | L(M), TA5T50 | 2025 | 76000 |  |  | 2027 | 660000 | 2022 | 66000 | 802000
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) | NCDOT | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.45 | Bike & Ped | STI (Prioritization) | 8 | Lumber River RPO | EB-6015B | Division 8 | L(M), TA5T50 | 2025 | 30000 |  |  | 2027 | 1300000 | 2025 | 70000 | 1400000
SCOTLAND | US 15/501 (ABERDEEN ROAD) | NCDOT | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE. |  | Highway | Economic Development | 8 | Lumber River RPO | HE-0013 | Division 8 | HF, T | 2024 | 150000 | 2024 | 470000 | 2025 | 7300000 | 2023 | 750000 | 8670000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT PUBLIC ACCESS AND ECONOMIC DEVELOPMENT FUNDS.
SCOTLAND | SCOTLAND COUNTY INDUSTRIAL PARK ACCESS ROAD | NCDOT | IMPROVE THE EXISTING ACCESS ROAD INTO THE SCOTLAND COUNTY INDUSTRIAL PARK. |  | Highway | Economic Development | 8 | Lumber River RPO | HE-0013A | Division 8 | T |  |  |  |  | 2023 | 333000 |  |  | 333000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO.
SCOTLAND | US 74 | NCDOT | RICHMOND COUNTY LINE TO SR 1363. UPGRADE GUARDRAIL. | 4.33 | Highway | Safety | 8 | Lumber River RPO | HS-2008A | Statewide Mobility | HSIP |  |  |  |  | 2021 | 360000 |  |  | 360000 | UNDER CONSTRUCTION
SCOTLAND | US 74 | NCDOT | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 0.5 | Highway | Safety | 8 | Lumber River RPO | HS-2008E | Statewide Mobility | HSIP, T | 2024 | 100000 | 2024 | 50000 | 2025 | 2600000 |  |  | 2750000
SCOTLAND | US 15 / US 501 | NCDOT | NC 144 INTERSECTION. CONSTRUCT ROUNDABOUT | 0.5 | Highway | Safety | 8 | Lumber River RPO | W-5208MA | Region E | [10 empty] | UNDER CONSTRUCTION
SCOTLAND | US 74 / FUTURE I-74 WESTBOUND | NCDOT | EXITS 183 AND 184 IN LAURINBURG. UPGRADE SIGNING AND PAVEMENT MARKINGS. |  | Highway | Safety | 8 | Lumber River RPO | W-5808A | Statewide Mobility | [10 empty] | PROJECT DELETED AT REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. PROJECT WILL UTILZE NON-STIP FUNDS.
SCOTLAND | US 15 / US 401 | NCDOT | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTI-LANES. | 3.44 | Highway | STI (Prioritization) | 8 | Lumber River RPO | U-5977 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22001000 |  |  | 32701000
SCOTLAND | COMMONWEALTH AVENUE | LAURINBURG | REPLACE BRIDGE 820081 OVER LEITH CREEK WITH CULVERT IN LAURINBURG. | 0.25 | Highway | Transition | 8 | Lumber River RPO | B-5003 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION BY CITY OF LAURINBURG - MUNICIPAL BRIDGE
SCOTLAND | SCOTLAND COUNTY | SCOTLAND COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 8 | Lumber River RPO | TK-6163 | Public Transit | 5311, L, S | [6 empty] | 2020 | 460000 | 460000 | FUNDS AUTHORIZED IN PROGRESS
SCOTLAND | CSX | CSXT RR | RAIL SPUR FOR INDUSTRIAL ACCESS. CONSTRUCT SPINE TRACK AND TURNOUTS, AND REHABILITATE EXISTING TRACK SECTIONS. |  | Rail | Economic Development | 8 | Lumber River RPO | P-5724 | Division 8 | [10 empty] | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CSX; "O" FUNDING INCLUDES PARTICIPATION BY NORTH CAROLINA RAILROAD, LAURINBURG-MAXTON AIRPORT, RAIL INDUSTRIIAL ACCESS PROGRAM, AND COMMUNITY DEVELOPMENT BLOCK GRANT PROGRAM
SCOTLAND, RICHMOND | US 74 / FUTURE I-74 | NCDOT | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 9.84 | Highway | STI (Prioritization) | 8 | Lumber River RPO | I-6055 | Region E | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 43000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 224100000 |  |  | 275600000
STANLY | STANLY COUNTY AIRPORT (VUJ) | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBBING LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. |  | Aviation | STI (Prioritization) | 10 | Rocky River RPO | AV-5817 | Division 10 | T | 2030 | 4400000 |  |  | 2032 | 2500000 |  |  | 6900000
STANLY | ALBEMARLE | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | Bike & Ped | STI (Prioritization) | 10 | Rocky River RPO | EB-5841 | Division 10 | L, TA5T50 | 2029 | 200000 | 2029 | 440000 | 2031 | 4600000 | 2024 | 1150000 | 6390000
STANLY | STANFIELD | NCDOT | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | Bike & Ped | STI (Prioritization) | 10 | Rocky River RPO | EB-5857 | Division 10 | HF(M), L(M), TALT5 | 2024 | 290000 |  |  | 2026 | 860000 | 2021 | 120000 | 1270000 | UNDER CONSTRUCTION.
STANLY | NORTH SECOND AVENUE | ALBEMARLE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | Bike & Ped | STI (Prioritization) | 10 | Rocky River RPO | EB-5972 | Division 10 | L, TA5T50 | 2026 | 342000 | 2026 | 81000 | 2027 | 1200000 | 2024 | 300000 | 1923000
STANLY | SALISBURY AVENUE | ALBEMARLE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | Bike & Ped | STI (Prioritization) | 10 | Rocky River RPO | EB-5973 | Division 10 | L, TA5T50 | 2025 | 378000 | 2025 | 60000 | 2025 | 3350000 | 2024 | 838000 | 4626000
STANLY | SR 1434 (ROGERS ROAD) | NCDOT | REPLACE BRIDGE 830042 OVER BIG BEAR CREEK. | 0.25 | Highway | Bridges | 10 | Rocky River RPO | B-5811 | Division 10 | BGOFF | 2028 | 15000 |  |  | 2030 | 600000 |  |  | 615000
STANLY | SR 1917 (BETHLEHEM CHURCH ROAD) | NCDOT | REPLACE BRIDGE 830102 OVER LONG CREEK. | 0.25 | Highway | Bridges | 10 | Rocky River RPO | B-6046 | Division 10 | BGOFF | 2022 | 145000 |  |  | 2024 | 1700000 |  |  | 1845000 | RIGHT-OF-WAY IN PROGRESS.
STANLY | VARIOUS | NCDOT | VARIOUS IMPROVEMENTS AROUND TOWN OF OAKBORO. | 3.4 | Highway | Economic Development | 10 | Rocky River RPO | R-5965 | [11 empty] | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. TOTAL AWARD AMOUNT = $4,400,279
STANLY | VARIOUS | NCDOT | NC 205/SR 1108 (LIGHTHOUSE ROAD)/SR 1109 (BUSTER ROAD) INTERSECTION AND SR 1110 (SWIFT ROAD) AT CHARLOTTE PIPE FACILITY. IMPROVE INTERSECTIONS. | 0.5 | Highway | Economic Development | 10 | Rocky River RPO | R-5965A | Division 10 | T | 2021 | 120000 |  |  | 2021 | 2405000 |  |  | 2525000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION.
STANLY | VARIOUS | NCDOT | SR 1107 (SILVER ROAD)/SR 1108 (LIGHTHOUSE ROAD) AND SR 1107 (SILVER ROAD)/SR 1110 (SWIFT ROAD) INTERSECTIONS. IMPROVE INTERSECTIONS. SR 1107 (SILVER ROAD), SR 1108 (LIGHTHOUSE ROAD) AND SR 1110 (SWIFT ROAD). VARIOUS ROADWAY IMPROVEMENTS INCLUDING FULL DEPTH RECLAMATION. |  | Highway | Economic Development | 10 | Rocky River RPO | R-5965B | Division 10 | T | 2021 | 250000 |  |  | 2023 | 1586000 |  |  | 1836000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION.
STANLY | US 52 | NCDOT | SR 1654 (MERNER TERRACE) INTERSECTION IN MISENHEIMER. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 10 | Rocky River RPO | HN-0032 | Exempt | CRPLT5, T(M) | 2025 | 194000 |  |  | 2026 | 2627000 | 2024 | 550000 | 3371000
STANLY | NC 24/NC 27 | NCDOT | LEONARD AVENUE. INSTALL AUDIBLE PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 10 | Rocky River RPO | HS-2010K | Region E | HSIP |  |  |  |  | 2024 | 15000 |  |  | 15000
STANLY | NC 73 | NCDOT | SR 1425 (NELSON MOUNTAIN ROAD)/ SR 1243 (CANE ROAD) INTERSECTION NEAR ALBEMARLE. REALIGN INTERSECTION AND CONSTRUCT TURN LANES. |  | Highway | Safety | 10 | Rocky River RPO | HS-2410I | Region E | HSIP | 2026 | 125000 | 2026 | 65000 | 2028 | 912000 |  |  | 1102000
STANLY | NC 24-27 | NCDOT | SR 1963 (ST. MARTIN ROAD) TO BIRD ROAD IN ALBEMARLE. |  | Highway | Safety | 10 | Rocky River RPO | R-2530A | [11 empty] | COMPLETE
STANLY | NC 24/NC 27 | NCDOT | SR 1963 (ST. MARTIN ROAD) IN ALBEMARLE TO NC 73. WIDEN TO MULTI- LANES. (COORDINATE WITH B-4974). | 8.9 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-2530
STANLY | NC 24-27 | NCDOT | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER. | 6.1 | Highway | STI (Prioritization) | 10 | Rocky River RPO | R-2530B | Region E | T | 2020 | 5700000 | 2020 | 3600000 | 2020 | 96961000 | 2020 | 8040000 | 114301000 | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
STANLY | SCUSA TRANSPORTATION | SCUSA TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Rocky River RPO | TK-6164 | Public Transit | 5311, L, S | [6 empty] | 2020 | 904000 | 904000 | FUNDS AUTHORIZED IN PROGRESS
STANLY | OLD CHARLOTTE HIGHWAY | NCDOT | WSS CROSSING 849910V IN ALBEMARLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 10 | Rocky River RPO | RX-2410A | Division 10 | RR |  |  |  |  | 2026 | 450000 |  |  | 450000
STANLY, ANSON | NC 740; US 52 | NCDOT | MILE MARKER 0 TO MILE MARKER 12.8 IN STANLY COUNTY; MILE MARKER 4.9 TO MILE MARKER 10.5 IN ANSON COUNTY. INSTALL RUMBLE STRIPS AND LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 10 | Rocky River RPO | HS-2010N | Region E | HSIP |  |  |  |  | 2024 | 636000 |  |  | 636000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE TRAINING, EDUCATION, AND WORKFORCE DEVELOPMENT. |  |  |  | 99 | STATEWIDE PROJECT | M-0426DIV | Division 99 | NHP | [6 empty] | 2024 | 1140000 | 1140000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE TRAINING, EDUCATION, AND WORKFORCE DEVELOPMENT. |  |  |  | 99 | STATEWIDE PROJECT | M-0426REG | Region SW | NHP | [6 empty] | 2024 | 1140000 | 1140000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE TRAINING, EDUCATION, AND WORKFORCE DEVELOPMENT. |  |  |  | 99 | STATEWIDE PROJECT | M-0426SW | Statewide Mobility | NHP | [6 empty] | 2024 | 1520000 | 1520000
STATEWIDE | VARIOUS | NCDOT | INTEGRATED MOBILITY DIVISION BICYCLE AND PEDESTRIAN COORDINATION ACTIVITIES. |  | Bike & Ped | Other | 99 | STATEWIDE PROJECT | BO-2424 | Division 99 | CMAQ, T(M) | [6 empty] | 2025 | 1100000 | 1100000
STATEWIDE | VARIOUS | NCDOT | SAFE ROUTES TO SCHOOL EDUCATION. |  | Bike & Ped | Other | 99 | STATEWIDE PROJECT | EB-6033 | Division 99 | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | RAILS TO TRAILS PROGRAM |  | Bike & Ped | Other | 99 | STATEWIDE PROJECT | EB-6037 | Division 99 | [10 empty] | LOCAL FUNDS REPRESENT LOCAL MATCH FOR RIGHT-OF-WAY AND CONSTRUCTION OF TRAILS BY LOCAL GOVERNMENTS.
STATEWIDE | VARIOUS |  | NATIONAL RECREATIONAL TRAILS. |  | Bike & Ped | Other | 99 | STATEWIDE PROJECT | M-0510 | Division 99 | TA |  |  |  |  | 2020 | 19200000 |  |  | 19200000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | SAFE ROUTES TO SCHOOL PROGRAM. PROJECTS TO IMPROVE SAFETY, REDUCE TRAFFIC, FUEL CONSUMPTION AND AIR POLLUTION IN VICINITY OF SCHOOLS. |  | Bike & Ped | Other | 99 | STATEWIDE PROJECT | SR-5001 | Division 99 | [10 empty] | IN PROGRESS - $200,800 IN STPDA FUNDS ALLOCATED TO SR-5001C
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PEDESTRIAN FACILITIES PROGRAM. |  | Bike & Ped | Pre-STI (Historic) | 99 | STATEWIDE PROJECT | EB-3314 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
STATEWIDE | VARIOUS | NCDOT | SIDEWALK PROGRAM IN ALL FOURTEEN HIGHWAY DIVISIONS. |  | Bike & Ped | Pre-STI (Historic) | 99 | STATEWIDE PROJECT | ER-2971 | Pre-STI (Transition) | [10 empty] | IN PROGRESS - $182,000 IN STPDA FUNDS ALLOCATED TO ER-2971E
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | B-8888 | Division 99 | BGOFF |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | B-8888DIV | Division 99 | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | B-8888REG | Region SW | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | B-8888SW | Statewide Mobility | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | NCDOT | ESTABLISH BRIDGE MANAGEMENT SYSTEM. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | BK-5100 | Division 99 | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | BP-5500DIV | Division 99
STATEWIDE | VARIOUS | NCDOT | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | BP-5500REG | Region SW
STATEWIDE | VARIOUS | NCDOT | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | BP-5500SW | Statewide Mobility
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0088 | Division 99 | BGOFF |  |  |  |  | 2025 | 218897000 |  |  | 218897000
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0088DIV | Division 99 | BFP |  |  |  |  | 2025 | 91692000 |  |  | 91692000
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0088REG | Region SW | BFP |  |  |  |  | 2025 | 91692000 |  |  | 91692000
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0088SW | Statewide Mobility | BFP |  |  |  |  | 2025 | 122255000 |  |  | 122255000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099A
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099ADIV | Division 99 | T | [6 empty] | 2025 | 85800000 | 85800000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099AREG | Region SW | T | [6 empty] | 2025 | 85800000 | 85800000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099ASW | Statewide Mobility | T | [6 empty] | 2025 | 114400000 | 114400000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099B
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099BDIV | Division 99 | T | [6 empty] | 2025 | 6600000 | 6600000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099C
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099CDIV | Division 99 | T | [6 empty] | 2025 | 8580000 | 8580000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099CREG | Region SW | T | [6 empty] | 2025 | 8580000 | 8580000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-0099CSW | Statewide Mobility | T | [6 empty] | 2025 | 11440000 | 11440000
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-8888 | Division 99 | BGOFF |  |  |  |  | 2024 | 6844000 |  |  | 6844000
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-8888DIV | Division 99 | BFP |  |  |  |  | 2024 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-8888REG | Region SW | BFP |  |  |  |  | 2024 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-8888SW | Statewide Mobility | BFP |  |  |  |  | 2024 | 0
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999A
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999ADIV | Division 99 | T | [6 empty] | 2021 | 31200000 | 31200000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999AREG | Region SW | T | [6 empty] | 2021 | 31200000 | 31200000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999ASW | Statewide Mobility | T | [6 empty] | 2021 | 41600000 | 41600000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999B
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999BDIV | Division 99 | T | [6 empty] | 2021 | 2400000 | 2400000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999C
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999CDIV | Division 99 | T | [6 empty] | 2021 | 3120000 | 3120000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999CREG | Region SW | T | [6 empty] | 2021 | 3120000 | 3120000
STATEWIDE | VARIOUS | NCDOT | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HB-9999CSW | Statewide Mobility | T | [6 empty] | 2021 | 4160000 | 4160000
STATEWIDE | VARIOUS |  | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | HM-9999 | Division 99 | BGOFF | [6 empty] | 2025 | 13000000 | 13000000
STATEWIDE | VARIOUS | NCDOT | SCOUR EVALUATION PROGRAM OF EXISTING BRIDGES. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | M-0379 | Division 99 | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | Highway | Bridges | 99 | STATEWIDE PROJECT | M-0414 | Division 99 | BGOFF, L | [6 empty] | 2020 | 5000000 | 5000000
STATEWIDE | VARIOUS | NCDOT | STORM WATER RUNOFF. RESEARCH, DESIGN, CONSTRUCT, MAINTAIN AND MONITOR STORM WATER DRAINAGE FROM 50 BRIDGES OVER WATERWAYS. (HB 2346, SECTION 25.18) |  | Highway | Bridges | 99 | STATEWIDE PROJECT | M-0418 | Division 99 | [10 empty] | UNDER CONSTRUCTION
STATEWIDE | VARIOUS | NCDOT | INTERSTATE MAINTENANCE PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Interstate Maintenance | 99 | STATEWIDE PROJECT | HI-9999 | Statewide Mobility | NHPIM |  |  |  |  | 2026 | 626273000 |  |  | 626273000
STATEWIDE | VARIOUS | NCDOT | CONSTRUCTION OF ELECTRIC VEHICLE SUPPLY EQUIPMENT ALONG NORTH CAROLINA'S ALTERNATIVE CORRIDORS AND NEVI PLANNING. |  | Highway | National Electric Vehicle Infrastructure | 99 | STATEWIDE PROJECT | HV-0001 | Division 99 | NEVI |  |  |  |  | 2024 | 95010000 | 2023 | 9371000 | 104381000
STATEWIDE | VARIOUS | NCDOT | NATIONAL ELECTRIC VEHICLE INFRASTRUCTURE PROGRAM (NEVI) - UNPROGRAMMED BALANCE. |  | Highway | National Electric Vehicle Infrastructure | 99 | STATEWIDE PROJECT | HV-9999 | Division 99 | NEVI |  |  |  |  | 2023 | 6925000 |  |  | 6925000
STATEWIDE | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY SOLAR CENTER CLEAN TRANSPORTATION PROGRAM. DEVELOP AND ADMINISTER A SEVEN YEAR CLEAN FUEL-ADVANCED TECHNOLOGY REBATE PROGRAM IN ALL CMAQ ELIGIBLE COUNTIES TO REDUCE EMISSIONS. |  | Highway | Other | 99 | STATEWIDE PROJECT | C-4902 | Exempt | [10 empty] | IN PROGRESS BY NORTH CAROLINA STATE UNIVERSITY
STATEWIDE | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY | PHASE 2 OF IMPLEMENTATION |  | Highway | Other | 99 | STATEWIDE PROJECT | C-4902A | Exempt
STATEWIDE | VARIOUS | NCDOT | STATEWIDE CMAQ PROJECTS TO IMPROVE AIR QUALITY WITHIN NONATTAINMENT AND MAINTENANCE AREAS. |  | Highway | Other | 99 | STATEWIDE PROJECT | C-5600 | Exempt
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM, INCLUDING EMISSIONS-REDUCING SUB-AWARDS, IN ALL CMAQ-ELIGIBLE COUNTIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | C-5702 | Exempt
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | C-5702A | Exempt | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | C-5702B | Exempt | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | C-5702C | Exempt
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | C-5702D | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 9093000 | 9093000
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | C-5702E | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 5584000 | 5584000
STATEWIDE | VARIOUS | NCDOT | VEGETATION MANAGEMENT - CLEAR ZONE IMPROVEMENT AND LANDSCAPING STATEWIDE. |  | Highway | Other | 99 | STATEWIDE PROJECT | ER-5600 | Division 99 | STPE |  |  |  |  | 2022 | 9000000 | 2022 | 700000 | 9700000 | IN PROGRESS
STATEWIDE | STATEWIDE TRAFFIC OPERATIONS | NCDOT | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT. |  | Highway | Other | 99 | STATEWIDE PROJECT | HO-0010
STATEWIDE | STATEWIDE TRAFFIC OPERATIONS | NCDOT | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT ACROSS THE ENTIRE STATE. |  | Highway | Other | 99 | STATEWIDE PROJECT | HO-0010B | Exempt | CMAQ | [6 empty] | 2024 | 93220000 | 93220000
STATEWIDE | VARIOUS | NCDOT | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0219 | Statewide Mobility
STATEWIDE | VARIOUS | NCDOT | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0219DIV | Division 99 | T | [6 empty] | 2020 | 1200000 | 1200000
STATEWIDE | VARIOUS | NCDOT | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0219REG | Region SW | T | [6 empty] | 2020 | 1200000 | 1200000
STATEWIDE | VARIOUS | NCDOT | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0219SW | Statewide Mobility | T | [6 empty] | 2020 | 1600000 | 1600000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0376 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0376DIV | Division 99 | T | [6 empty] | 2020 | 4320000 | 4320000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0376REG | Region SW | T | [6 empty] | 2020 | 4320000 | 4320000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0376SW | Statewide Mobility | T | [6 empty] | 2020 | 5670000 | 5670000
STATEWIDE | VARIOUS | NCDOT | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0391 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0391DIV | Division 99 | T | [6 empty] | 2020 | 1920000 | 1920000
STATEWIDE | VARIOUS | NCDOT | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0391REG | Region SW | T | [6 empty] | 2020 | 1920000 | 1920000
STATEWIDE | VARIOUS | NCDOT | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0391SW | Statewide Mobility | T | [6 empty] | 2020 | 2560000 | 2560000
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0392 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0392DIV | Division 99 | T | [6 empty] | 2020 | 768000 | 768000
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0392REG | Region SW | T | [6 empty] | 2020 | 768000 | 768000
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0392SW | Statewide Mobility | T | [6 empty] | 2020 | 1024000 | 1024000
STATEWIDE | VARIOUS |  | STATEWIDE TRAINING, EDUCATION, AND WORKFORCE DEVELOPMENT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0426 | [11 empty] | AUTHORIZED UNDER 23 U.S.C. 504e
STATEWIDE | VARIOUS | NCDOT | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0451
STATEWIDE | VARIOUS | NCDOT | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0451DIV | Division 99 | T | [6 empty] | 2020 | 1203000 | 1203000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0451REG | Region SW | T | [6 empty] | 2020 | 1203000 | 1203000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0451SW | Statewide Mobility | T | [6 empty] | 2020 | 1606000 | 1606000
STATEWIDE | VARIOUS | NCDOT | TOLLING/FINANCIAL FEASIBILITY STUDIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0452 | Statewide Mobility | T | [6 empty] | 2020 | 3200000 | 3200000
STATEWIDE | VARIOUS | NCDOT | NATIONAL SUMMER TRANSPORTATION INSTITUTE (NSTI). |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0460 | Exempt | O | [6 empty] | 2024 | 2400000 | 2400000
STATEWIDE | VARIOUS | NCDOT | ON-THE-JOB TRAINING PROGRAM. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0478 | Exempt | O | [6 empty] | 2024 | 6000000 | 6000000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479A
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479ADIV | Division 99 | T | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479AREG | Region SW | T | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479ASW | Statewide Mobility | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479B
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479BDIV | Division 99 | T | [6 empty] | 2020 | 2400000 | 2400000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479BREG | Region SW | T | [6 empty] | 2020 | 2400000 | 2400000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479BSW | Statewide Mobility | T | [6 empty] | 2020 | 3200000 | 3200000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479DIV | Division 99 | T | [6 empty] | 2020 | 24000000 | 24000000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479REG | Region SW | T | [6 empty] | 2020 | 24000000 | 24000000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0479SW | Statewide Mobility | T | [6 empty] | 2020 | 32000000 | 32000000
STATEWIDE | VARIOUS | NCDOT | DISADVANTAGED BUSINESS ENTERPRISE (DBE) TRAINING AND SUPPORTIVE SERVICES. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0480 | Exempt | O | [6 empty] | 2024 | 3600000 | 3600000
STATEWIDE | VARIOUS | NCDOT | FEDERAL STATE TRANSPORTATION INNOVATION COUNCIL (STIC) INCENTIVE FUNDED PROJECTS |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0482 | Exempt | DP, HF(M) | [6 empty] | 2023 | 500000 | 500000 | DP FUNDS REPRESENT FEDERAL STIC FUNDS.
STATEWIDE | VARIOUS | NCDOT | TRANSPORTATION PROGRAM MANAGEMENT UNIT (TPMU) OVERSIGHT FOR LOCALLY-ADMINISTERED PROJECTS INCLUDING PREPARATION OF AGREEMENTS AND FUNDING AUTHORIZATION REQUESTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0505 | Division 99 | T | [6 empty] | 2020 | 5000000 | 5000000
STATEWIDE | VARIOUS | NCDOT | RIGHT-OF-WAY BRANCH, REVIEW OF LOCAL PUBLIC AGENCY (LPA) PROJECTS BY THE APPRAISAL SECTION. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0515 | Division 99 | T | 2020 | 4000000 | [6 empty] | 4000000
STATEWIDE | VARIOUS | NCDOT | HYDRAULICS, PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0534 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0534DIV | Division 99 | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | NCDOT | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0534REG | Region SW | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | NCDOT | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0534SW | Statewide Mobility | T | [6 empty] | 2020 | 12800000 | 12800000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0539
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0539DIV | Division 99 | T | [6 empty] | 2020 | 43200000 | 43200000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0539REG | Region SW | T | [6 empty] | 2020 | 43200000 | 43200000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0539SW | Statewide Mobility | T | [6 empty] | 2020 | 57600000 | 57600000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552A
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552ADIV | Division 99 | T | [6 empty] | 2022 | 750000 | 750000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552AREG | Region SW | T | [6 empty] | 2022 | 750000 | 750000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552ASW | Statewide Mobility | T | [6 empty] | 2022 | 1000000 | 1000000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552B
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552BDIV | Division 99 | T | [6 empty] | 2022 | 924000 | 924000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552BREG | Region SW | T | [6 empty] | 2022 | 924000 | 924000
STATEWIDE | VARIOUS | NCDOT | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552BSW | Statewide Mobility | T | [6 empty] | 2022 | 1232000 | 1232000
STATEWIDE | VARIOUS | NCDOT | DIGITAL DELIVERY INITIATIVE. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552C
STATEWIDE | VARIOUS | NCDOT | DIGITAL DELIVERY INITIATIVE. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552CDIV | Division 99 | T | [6 empty] | 2023 | 150000 | 150000
STATEWIDE | VARIOUS | NCDOT | DIGITAL DELIVERY INITIATIVE. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552CREG | Region SW | T | [6 empty] | 2023 | 150000 | 150000
STATEWIDE | VARIOUS | NCDOT | DIGITAL DELIVERY INITIATIVE. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0552CSW | Statewide Mobility | T | [6 empty] | 2023 | 200000 | 200000
STATEWIDE | VARIOUS |  | TECHNICAL SERVICES. PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0553A
STATEWIDE | VARIOUS | NCDOT | INTEGRATED PROJECT DELIVERY. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0553ADIV | Exempt | T | [6 empty] | 2022 | 4350000 | 4350000
STATEWIDE | VARIOUS | NCDOT | INTEGRATED PROJECT DELIVERY. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0553AREG | Exempt | T | [6 empty] | 2022 | 4350000 | 4350000
STATEWIDE | VARIOUS | NCDOT | INTEGRATED PROJECT DELIVERY. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0553ASW | Exempt | T | [6 empty] | 2022 | 5800000 | 5800000
STATEWIDE | VARIOUS |  | TECHNICAL SERVICES. PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0553B
STATEWIDE | VARIOUS | NCDOT | TRAINING AND SPECIAL PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0553BDIV | Exempt | T | [6 empty] | 2022 | 3000000 | 3000000
STATEWIDE | VARIOUS | NCDOT | TRAINING AND SPECIAL PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0553BREG | Exempt | T | [6 empty] | 2022 | 3000000 | 3000000
STATEWIDE | VARIOUS | NCDOT | TRAINING AND SPECIAL PROJECTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0553BSW | Exempt | T | [6 empty] | 2022 | 4000000 | 4000000
STATEWIDE | VARIOUS | NCDOT | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0554
STATEWIDE | VARIOUS | NCDOT | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0554DIV | Division 99 | T | [6 empty] | 2022 | 105000000 | 105000000
STATEWIDE | VARIOUS | NCDOT | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0554REG | Region SW | T | [6 empty] | 2022 | 105000000 | 105000000
STATEWIDE | VARIOUS | NCDOT | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0554SW | Statewide Mobility | T | [6 empty] | 2022 | 140000000 | 140000000
STATEWIDE | VARIOUS | NCDOT | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0555
STATEWIDE | VARIOUS | NCDOT | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0555DIV | Division 99 | T |  |  | 2023 | 1365000 |  |  |  |  | 1365000
STATEWIDE | VARIOUS | NCDOT | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0555REG | Region SW | T |  |  | 2023 | 1365000 |  |  |  |  | 1365000
STATEWIDE | VARIOUS | NCDOT | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0555SW | Statewide Mobility | T |  |  | 2023 | 1820000 |  |  |  |  | 1820000
STATEWIDE | STATEWIDE | NCDOT | ADVANCED RIGHT-OF-WAY ACQUISITION ACCOUNT. REVOLVING ACCOUNT TO FUND ADVANCED RIGHT-OF-WAY ACQUISITION. FUNDS TO BE REPAID FROM THE STIP PROJECT AT THE TIME THE PROJECT IS FUNDED. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0556 | Statewide Mobility | T | 2023 | 6000000 | [6 empty] | 6000000
STATEWIDE | STATEWIDE |  | PROTECT FORMULA PLANNING FUNDING FOR RESILIENCE PROGRAM. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0563
STATEWIDE | STATEWIDE | NCDOT | HAZARD CHARACTERIZATION AND WARNING TOOLS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0563A | Statewide Mobility | PROTCT | [6 empty] | 2023 | 3360000 | 3360000
STATEWIDE | STATEWIDE | NCDOT | HAZARD CORRIDOR VULNERABILITY ASSESSMENTS. |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0563B | Statewide Mobility | PROTCT | [6 empty] | 2023 | 1400000 | 1400000
STATEWIDE | STATEWIDE | NCDOT | GEOTECHNICAL ASSET MANAGEMENT (GAM) DATABASE AND LANDSLIDE MITIGATION PLANNING |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0563C | Statewide Mobility | PROTCT | [6 empty] | 2023 | 2240000 | 2240000
STATEWIDE | STATEWIDE | NCDOT | RESILIENCE PROGRAM REPORTING, MANAGEMENT AND SUPPORT |  | Highway | Other | 99 | STATEWIDE PROJECT | M-0563E | Statewide Mobility | PROTCT | [6 empty] | 2024 | 2550000 | 2550000
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-4436DIV | Division 99 | BGANY |  |  |  |  | 2020 | 900000 |  |  | 900000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-4436REG | Region SW | BGANY |  |  |  |  | 2020 | 900000 |  |  | 900000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-4436SW | Statewide Mobility | BGANY |  |  |  |  | 2020 | 1200000 |  |  | 1200000 | IN PROGRESS
STATEWIDE | VARIOUS | FHWA | FEDERAL LANDS TRANSPORTATION PROGRAM (FLTP) AND EMERGENCY RELIEF FOR FEDERALLY OWNED ROADS (ERFO). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO FEDERAL LANDS. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-5753 | Exempt | ERFO, FLTP |  |  |  |  | 2020 | 103192000 |  |  | 103192000 | PROGRAM IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-5968
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-5968DIV | Division 99 | BGANY |  |  |  |  | 2020 | 14400000 |  |  | 14400000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-5968REG | Region SW | BGANY |  |  |  |  | 2020 | 14400000 |  |  | 14400000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-5968SW | Statewide Mobility | BGANY |  |  |  |  | 2020 | 19200000 |  |  | 19200000 | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-9999WM | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-9999WMDIV | Division 99 | NHP, T | [6 empty] | 2020 | 300000 | 300000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-9999WMREG | Region SW | NHP, T | [6 empty] | 2020 | 300000 | 300000
STATEWIDE | VARIOUS | NCDOT | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | Highway | Other | 99 | STATEWIDE PROJECT | R-9999WMSW | Statewide Mobility | NHP, T | [6 empty] | 2020 | 400000 | 400000
STATEWIDE | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2015
STATEWIDE | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2015DIV | Division 99 | VRU | [6 empty] | 2023 | 14205000 | 14205000
STATEWIDE | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2015REG | Region SW | VRU | [6 empty] | 2023 | 14205000 | 14205000
STATEWIDE | VARIOUS | NCDOT | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2015SW | Statewide Mobility | VRU | [6 empty] | 2023 | 18940000 | 18940000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2420
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2420DIV | Division 99 | T | [6 empty] | 2024 | 15300000 | 15300000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2420REG | Region SW | T | [6 empty] | 2024 | 15300000 | 15300000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2420SW | Statewide Mobility | T | [6 empty] | 2024 | 20400000 | 20400000
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2421
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2421DIV | Division 99 | T | [6 empty] | 2024 | 24000000 | 24000000
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2421REG | Region SW | T | [6 empty] | 2024 | 24000000 | 24000000
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2421SW | Statewide Mobility | T | [6 empty] | 2024 | 32000000 | 32000000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2422
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2422DIV | Division 99 | T | [6 empty] | 2024 | 15000000 | 15000000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2422REG | Region SW | T | [6 empty] | 2024 | 18500000 | 18500000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-2422SW | Statewide Mobility | T | [6 empty] | 2024 | 20000000 | 20000000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-9999
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-9999DIV | Division 99 | HSIP |  |  |  |  | 2024 | 276783000 |  |  | 276783000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-9999REG | Region SW | HSIP |  |  |  |  | 2024 | 276833000 |  |  | 276833000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE |  | Highway | Safety | 99 | STATEWIDE PROJECT | HS-9999SW | Statewide Mobility | HSIP |  |  |  |  | 2024 | 369110000 |  |  | 369110000
STATEWIDE | VARIOUS |  | SCHOOL TRAFFIC ANALYSIS FOR NEW, RELOCATED AND EXPANDING SCHOOLS. |  | Highway | Safety | 99 | STATEWIDE PROJECT | SM-6215
STATEWIDE | VARIOUS | NCDOT | SCHOOL TRAFFIC ANALYSIS FOR NEW, RELOCATED AND EXPANDING SCHOOLS. |  | Highway | Safety | 99 | STATEWIDE PROJECT | SM-6215DIV | Division 99 | T | [6 empty] | 2024 | 1800000 | 1800000
STATEWIDE | VARIOUS | NCDOT | SCHOOL TRAFFIC ANALYSIS FOR NEW, RELOCATED AND EXPANDING SCHOOLS. |  | Highway | Safety | 99 | STATEWIDE PROJECT | SM-6215REG | Region SW | T | [6 empty] | 2024 | 1800000 | 1800000
STATEWIDE | VARIOUS | NCDOT | SCHOOL TRAFFIC ANALYSIS FOR NEW, RELOCATED AND EXPANDING SCHOOLS. |  | Highway | Safety | 99 | STATEWIDE PROJECT | SM-6215SW | Statewide Mobility | T | [6 empty] | 2024 | 2400000 | 2400000
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5517DIV | Division 99
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5517REG | Region SW
STATEWIDE | VARIOUS | NCDOT | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5517SW | Statewide Mobility
STATEWIDE | VARIOUS | NCDOT | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5601 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON DIVISION CATEGORY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5601DIV | Division 99 | HSIP | 2021 | 68000 |  |  | 2020 | 3670000 |  |  | 3738000
STATEWIDE | VARIOUS | NCDOT | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON REGIONAL CATEGORY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5601REG | Region SW | HSIP | 2021 | 68000 |  |  | 2021 | 6170000 |  |  | 6238000
STATEWIDE | VARIOUS | NCDOT | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON STATWIDE CATEGORY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5601SW | Statewide Mobility | HSIP | 2021 | 90000 |  |  | 2021 | 3360000 |  |  | 3450000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5700DIV | Division 99
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5700REG | Region SW
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5700SW | Statewide Mobility
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5715
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5715DIV | Division 99 | HSIP | [6 empty] | 2020 | 4230000 | 4230000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5715REG | Region SW | HSIP | [6 empty] | 2020 | 4230000 | 4230000
STATEWIDE | VARIOUS | NCDOT | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5715SW | Statewide Mobility | HSIP | [6 empty] | 2020 | 5640000 | 5640000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5717
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5717DIV | Division 99 | HSIP | [6 empty] | 2020 | 1350000 | 1350000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5717REG | Region SW | HSIP | [6 empty] | 2020 | 1350000 | 1350000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SYSTEM DATA COLLECTION. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-5717SW | Statewide Mobility | HSIP | [6 empty] | 2020 | 1800000 | 1800000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-9999
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-9999DIV | Division 99 | HSIP |  |  |  |  | 2020 | 45163000 |  |  | 45163000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-9999REG | Region SW | HSIP |  |  |  |  | 2020 | 55935000 |  |  | 55935000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. |  | Highway | Safety | 99 | STATEWIDE PROJECT | W-9999SW | Statewide Mobility | HSIP |  |  |  |  | 2020 | 74580000 |  |  | 74580000
STATEWIDE | STATEWIDE | FTA | 5311 CAPITAL PROJECTS FOR RURAL AREAS |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TA-6665 | Public Transit | 5311, L, S | [6 empty] | 2023 | 92050000 | 92050000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5339 BUS AND BUS FACILITIES |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TA-6666 | Public Transit | 5339 | [6 empty] | 2021 | 6750000 | 6750000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | NCDOT | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0003 | Public Transit | 5311, L, S | [6 empty] | 2023 | 1371000 | 1371000
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0005 | Public Transit | 5339, L |  |  |  |  | 2022 | 3750000 |  |  | 3750000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0006 | Public Transit | 5339, L |  |  |  |  | 2021 | 1819000 |  |  | 1819000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR CONSTRUCTION PROJECT |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0007 | Public Transit | 5339, L | [6 empty] | 2021 | 3976000 | 3976000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0008 | Public Transit | 5339, L | [6 empty] | 2023 | 8325000 | 8325000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0010 | Public Transit | 5339, L |  |  |  |  | 2023 | 9500000 |  |  | 9500000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | NCDOT | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0011 | Public Transit | 5339, L |  |  |  |  | 2023 | 719000 | 2021 | 8689000 | 9408000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5339(b) DISCRETIONARY GRANT TO PURCHASE ELECTRIC BUSES AND CHARGING STATIONS. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0012 | Public Transit | 5339, L | [6 empty] | 2024 | 3125000 | 3125000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | MOBILITY FROM ALL GRANT OPPORTUNITY FROM THE FTA.5310 DISCRETIONARY GRANT AWARDED BY FTA. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0013 | Public Transit | 5310, S | [6 empty] | 2021 | 350000 | 350000
STATEWIDE | NCDOT | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL AND URBAN AREAS. |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0018 | Public Transit | 5310, L, S | [6 empty] | 2022 | 7955000 | 7955000
STATEWIDE | NCDOT | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0019 | Public Transit | 5311, L, S | [6 empty] | 2022 | 17147000 | 17147000
STATEWIDE | NCDOT | FTA | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON FY 24 GRANTS |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0020 | Public Transit | 5309, L, S | [6 empty] | 2023 | 425000 | 425000
STATEWIDE | NCDOT | NCDOT | 5339 STATEWIDE RURAL |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0021 | Public Transit | 5339, BGDA, L, S | [6 empty] | 2023 | 38025000 | 38025000
STATEWIDE | NCDOT | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0022 | Public Transit | ADTAP, L, S | [6 empty] | 2022 | 1880000 | 1880000
STATEWIDE | NCDOT | NCDOT | FEDERAL AMERICAN RESCUE PLAN (ARP) FUNDS FOR CAPITAL |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-0026 | Public Transit | ARP | [6 empty] | 2023 | 500000 | 500000
STATEWIDE | STATEWIDE | FTA | 5311 ADTAP |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TC-5004 | Public Transit | ADTAP | [6 empty] | 2021 | 3392000 | 3392000 | FUMODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | REGIONAL COORDINATED AREA TRANSPORTION | REGIONAL COORDINATED AREA TRANSPORTION | PLANNING ASSISTANCE - RESEARCH SUPPORT ACTIVITIES |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TP-4901 | Public Transit | FSPR, S | [6 empty] | 2020 | 720000 | 720000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | STATEWIDE | FTA | 5310 CAPITAL PROJECTS FOR RURAL AREAS AND SMALL URBAN AREAS |  | Public Transportation (Transit) | Capital (Non-STI) | 99 | STATEWIDE PROJECT | TQ-9038 | Public Transit | 5310 | [6 empty] | 2021 | 2850000 | 2850000 | MODIFYING THE FEDERAL FUND S RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIGNS OF HUMAN TRAFFICKING. THE DEPARTMENT ALSO WILL DEVELOP HUMAN TRAFFICKING AWARENESS EDUCATIONAL MATERIALS TO BE POSTED ON TRANSIT VEHICLES AND STATIONS. |  | Public Transportation (Transit) | Miscellaneous/Other | 99 | STATEWIDE PROJECT | TO-0003 | Public Transit | 5307, 5312 | [6 empty] | 2021 | 150000 | 150000
STATEWIDE | STATEWIDE | FTA | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | Public Transportation (Transit) | Miscellaneous/Other | 99 | STATEWIDE PROJECT | TO-0004 | Public Transit | S, SSO |  |  |  |  | 2025 | 3810000 | 2021 | 3280000 | 7090000 | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD.
STATEWIDE | STATEWIDE | FTA | 5311 OPERATING FUNDS FOR FTA GRANTS |  | Public Transportation (Transit) | Miscellaneous/Other | 99 | STATEWIDE PROJECT | TO-6135 | Public Transit | 5311 | [6 empty] | 2021 | 947000 | 947000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS - OPERATING |  | Public Transportation (Transit) | Miscellaneous/Other | 99 | Burlington-Graham MPO, Charlotte Regional TPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO | TO-6142 | Public Transit | 5307, L | [6 empty] | 2020 | 11230000 | 11230000
STATEWIDE | STATEWIDE | FTA | 5311 OPERATING AND 5311 OPERATING F |  | Public Transportation (Transit) | Miscellaneous/Other | 99 | STATEWIDE PROJECT | TO-6155 | Public Transit | 5311, L | [6 empty] | 2020 | 154320000 | 154320000
STATEWIDE | STATEWIDE | FTA | 5311(F) INTERCITY BUS FUNDS FOR FTA GANTS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TI-6109 | Public Transit | 5311 | [6 empty] | 2021 | 2698000 | 2698000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5311 STATE ADMINISTRATION AND 5311 STATE ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TK-4900Z | Public Transit | 5311 | [6 empty] | 2021 | 3080000 | 3080000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | STATE ADMINISTRATION OF APPALACHIAN DEVELOPMENT TRANSPORTATION ASSISTANCE PROGRAM |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TK-4902 | Public Transit | ADTAP | [6 empty] | 2021 | 235000 | 235000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5311 ADMINISTRATIVE |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TK-6181 | Public Transit | 5311 | [6 empty] | 2021 | 15025000 | 15025000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | NCDOT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311 ADMIN/OPERATING/CAPITAL AND 5311(F) |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0002 | Public Transit | 5311 | [6 empty] | 2023 | 3950000 | 3950000
STATEWIDE | NCDOT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311CAPITAL-ADTAP) |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0004 | Public Transit | 5311 | [6 empty] | 2023 | 150000 | 150000
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0010 | Public Transit | 5307 | [6 empty] | 2021 | 142000 | 142000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0012 | Public Transit | 5307 | [6 empty] | 2021 | 129000 | 129000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0014 | Public Transit | 5307 | [6 empty] | 2021 | 75000 | 75000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0015 | Public Transit | 5307 | [6 empty] | 2021 | 145000 | 145000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0020 | Public Transit | 5307, L | [6 empty] | 2021 | 2191000 | 2191000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | 5307 OPERATING FUNDS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0022 | Public Transit | 5307 | [6 empty] | 2021 | 18000 | 18000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | NCDOT | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5310 ADMIN/OPERATING/CAPITAL PURCHASE SERVICE) |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0023 | Public Transit | 5310 | [6 empty] | 2023 | 1022000 | 1022000
STATEWIDE | STATEWIDE | FTA | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0024 | Public Transit | 5312, L | [6 empty] | 2021 | 313000 | 313000
STATEWIDE | NCDOT | NCDOT | 5310 OPERATING PROJECTS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0025 | Public Transit | 5310, L | [6 empty] | 2022 | 4212000 | 4212000
STATEWIDE | NCDOT | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0027 | Public Transit | 5311, L, S | [6 empty] | 2023 | 51684000 | 51684000
STATEWIDE | NCDOT | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0028 | Public Transit | 5311, L, S | [6 empty] | 2023 | 15494000 | 15494000
STATEWIDE | NCDOT | NCDOT | 5311 STATE ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0029 | Public Transit | 5311 | [6 empty] | 2022 | 3361000 | 3361000
STATEWIDE | NCDOT | NCDOT | 5311 ADTAP STATE ADMINISTRATIVE FUNDS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0030 | Public Transit | ADTAP | [6 empty] | 2022 | 177000 | 177000
STATEWIDE | NCDOT | NCDOT | RTAP STATEWIDE FUNDS FOR FTA GRANTS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0031 | Public Transit | RTAP | [6 empty] | 2023 | 1348000 | 1348000
STATEWIDE | NCDOT | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0032 | Public Transit | 5311, S | [6 empty] | 2022 | 29441000 | 29441000
STATEWIDE | NCDOT | NCDOT | 5311(F) INTERCITY BUS - STATE ADMIN |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0033 | Public Transit | 5311 | [6 empty] | 2022 | 494000 | 494000
STATEWIDE | STATEWIDE | FTA | 5310 STATE ADMINISTRATIVE FUNDS. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0036 | Public Transit | 5310 | [6 empty] | 2022 | 567000 | 567000
STATEWIDE | NCDOT | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS. (ARP/CRRSAA 5301 OPERATING) |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-0038 | Public Transit | FEDT, S | [6 empty] | 2023 | 1501000 | 1501000
STATEWIDE | SUB REGIONAL | FTA | STATE ADMINISTRATION - JOB ACCESS NON-URBAN |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TM-5301 | Public Transit | 5316 | [6 empty] | 2020 | 500000 | 500000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | SUB REGIONAL | FTA | STATE ADMINISTRATION - NEW FREEDOM - 5317 |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TN-5112 | Public Transit | 5317 | [6 empty] | 2020 | 350000 | 350000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | STATEWIDE | FTA | 5317 NEW FREEDOM |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TN-6125 | Public Transit | FEP, L | [6 empty] | 2020 | 4272000 | 4272000
STATEWIDE | STATEWIDE | FTA | 5310 OPERATING PROJECTS FOR RURAL AREAS |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TQ-6954 | Public Transit | 5310, L | [6 empty] | 2021 | 8935000 | 8935000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | STATEWIDE RTAP |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TS-4900Z | Public Transit | RTAP | [6 empty] | 2021 | 480000 | 480000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FTA | 5329 STATE SAFETY AND OVERSIGHT |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TS-7001 | Public Transit | FED, L, S | [6 empty] | 2020 | 4676000 | 4676000
STATEWIDE | NCDOT | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TU-0011 | Public Transit | 5303, L | [6 empty] | 2023 | 2070000 | 2070000
STATEWIDE | SUB REGIONAL | FTA | 5310 STATE ADMIN |  | Public Transportation (Transit) | Operations and Maintenance | 99 | STATEWIDE PROJECT | TV-4903 | Public Transit | 5310 | [6 empty] | 2021 | 450000 | 450000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | STATEWIDE | FTA | 5304 PLANNING |  | Public Transportation (Transit) | Planning | 99 | STATEWIDE PROJECT | TP-5154 | Public Transit | 5303, L | [6 empty] | 2020 | 5136000 | 5136000
STATEWIDE | NCDOT | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. |  | Public Transportation (Transit) | Planning | 99 | STATEWIDE PROJECT | TU-0003 | Public Transit | 5303, 5312, S | [6 empty] | 2021 | 222000 | 222000 | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD.
STATEWIDE | NCDOT | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS |  | Public Transportation (Transit) | Planning | 99 | STATEWIDE PROJECT | TU-0005 | Public Transit | 5303, L, S | [6 empty] | 2022 | 10809000 | 10809000
STATEWIDE | NCDOT | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. |  | Public Transportation (Transit) | Planning | 99 | STATEWIDE PROJECT | TU-0008 | Public Transit | 5311, S | [6 empty] | 2022 | 588000 | 588000
STATEWIDE | NCDOT | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. |  | Public Transportation (Transit) | Planning | 99 | STATEWIDE PROJECT | TU-0009 | Public Transit | RTAP | [6 empty] | 2022 | 765000 | 765000
STATEWIDE | NCDOT | NCDOT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY. PLANNING STUDY ON THE TRANSITION TO ZERO EMISSIONS LIGHT AND HEAVY DUTY PASSENGER VEHICLES. THE TRANSITION PLAN IS AREQUIREMENT BY FTA TO APPLY FOR GRANT FUNDS SUPPORTING ANY ZEV PROJECTS, INCLUDING VEHICLES AND ALL RELATED INFRASTRUCTURE. |  | Public Transportation (Transit) | Planning | 99 | STATEWIDE PROJECT | TU-0012 | Public Transit | 5303, L | [6 empty] | 2023 | 100000 | 100000
STATEWIDE | NCDOT | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. |  | Public Transportation (Transit) | Planning | 99 | STATEWIDE PROJECT | TU-0014 | Public Transit | 5311, L | [6 empty] | 2023 | 634000 | 634000
STATEWIDE | NCDOT | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO THE DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. |  | Public Transportation (Transit) | Planning | 99 | STATEWIDE PROJECT | TU-0015 | Public Transit | RTAP | [6 empty] | 2023 | 73000 | 73000
STATEWIDE | STATEWIDE | FTA | FY21 5307 SBUS CAPITAL |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 99 | STATEWIDE PROJECT | TG-0002 | Public Transit | 5307 | [6 empty] | 2021 | 21000 | 21000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | FY21 5307 SBUS CAPITAL |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 99 | STATEWIDE PROJECT | TG-0004 | Public Transit | 5307 | [6 empty] | 2021 | 168000 | 168000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | FY21 5307 SBUS CAPITAL |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 99 | STATEWIDE PROJECT | TG-0005 | Public Transit | 5307 | [6 empty] | 2021 | 168000 | 168000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FTA | FY21 5307 SBUS CAPITAL |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 99 | STATEWIDE PROJECT | TG-0006 | Public Transit | 5307, L | [6 empty] | 2021 | 381000 | 381000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | QUEEN CITY EXPRESS | NCDOT | WILMINGTON TO CHARLOTTE. SUBSIDY FOR INTERMODAL RAIL SERVICE BETWEEN PORT OF WILMINGTON AND CHARLOTTE. |  | Rail | Other | 99 | STATEWIDE PROJECT | C-5600VA | Exempt | CMAQ | [6 empty] | 2025 | 250000 | 250000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE RAIL PRELIMINARY ENGINEERING |  | Rail | Other | 99 | STATEWIDE PROJECT | P-5602 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | STATEWIDE RAIL PRELIMINARY ENGINEERING |  | Rail | Other | 99 | STATEWIDE PROJECT | P-5602DIV | Division 99 | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE RAIL PRELIMINARY ENGINEERING |  | Rail | Other | 99 | STATEWIDE PROJECT | P-5602REG | Region SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | NCDOT | STATEWIDE RAIL PRELIMINARY ENGINEERING |  | Rail | Other | 99 | STATEWIDE PROJECT | P-5602SW | Statewide Mobility | T | [6 empty] | 2020 | 6400000 | 6400000
STATEWIDE | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES PROGRAM ADMINISTRATION |  | Rail | Rail-Highway Grade Crossing Closure | 99 | STATEWIDE PROJECT | RC-2000 | Statewide Mobility | [10 empty] | PROGRAMMED FOR PLANNING ONLY.
STATEWIDE | VARIOUS | NCDOT | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE |  | Rail | Rail-Highway Grade Crossing Closure | 99 | STATEWIDE PROJECT | Y-5500 | Division 99 | RR | 2021 | 1500000 |  |  | 2020 | 7560000 |  |  | 9060000 | RIGHT-OF-WAY IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS PROGRAM ADMINISTRATION. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | STATEWIDE PROJECT | RX-2000 | Statewide Mobility | [10 empty] | PROGRAMMED FOR PLANNING ONLY.
STATEWIDE | VARIOUS | NCDOT | PASSENGER RAIL CROSSING SAFETY IMPROVEMENT INVENTORY PROGRAM |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | STATEWIDE PROJECT | RX-2100 | Division 99 | RR | [6 empty] | 2021 | 2500000 | 2500000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY
STATEWIDE | VARIOUS | NCDOT | RAILWAY-HIGHWAY CROSSINGS PROGRAM - UNPROGRAMMED BALANCE |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | STATEWIDE PROJECT | RX-9999 | Division 99 | RR |  |  |  |  | 2024 | 85008000 |  |  | 85008000
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | STATEWIDE PROJECT | Z-5400 | Division 99 | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | STATEWIDE PROJECT | Z-5700 | Division 99 | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NCDOT | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 99 | STATEWIDE PROJECT | Z-5800 | Division 99 | RR | 2021 | 500000 |  |  | 2020 | 3280000 |  |  | 3780000
STOKES | SR 1112 (MAIN STREET) | KING | KIRBY ROAD TO KING CITY HALL. CONSTRUCT ADA-COMPLIANT SIDEWALK. |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0147 | Exempt | CRPDA, L(M) | 2026 | 98000 |  |  | 2027 | 323000 | 2025 | 10000 | 431000
STOKES | INGRAM DRIVE | KING | CAMPBELL DRIVE TO EAST OF 5 FORKS STREET. CONSTRUCT ADA-COMPLIANT SIDEWALK CONNECTING TO EXISTING SIDEWALKS |  | Bike & Ped | Locally Selected | 9 | Winston-Salem Area TPO | BL-0148 | Exempt | CRPDA, L(M) |  |  |  |  | 2027 | 213000 | 2025 | 38000 | 251000
STOKES | US 311 | NCDOT | NC 65 IN WALNUT COVE. UPGRADE INTERSECTION AND IMPROVE RAILROAD CROSSING. | 0.5 | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5768 | Division 9 | BGLT5, T |  |  |  |  | 2023 | 6963000 |  |  | 6963000 | UNDER CONSTRUCTION
STOKES | US 311 (NORTH MAIN STREET) | NCDOT | SR 1918 (FIRST STREET) IN WALNUT COVE. CONSTRUCT ROUNDABOUT. |  | Highway | STI (Prioritization) | 9 | Northwest Piedmont RPO | R-5828 | Division 9 | T |  |  |  |  | 2022 | 3050000 |  |  | 3050000 | UNDER CONSTRUCTION
SURRY | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | CONSTRUCT GENERAL AVIATION APRON AND AIRCRAFT STORAGE HANGARS. |  | Aviation | STI (Prioritization) | 11 | Northwest Piedmont RPO | AV-5859 | Division 11 | T |  |  |  |  | 2020 | 4000000 |  |  | 4000000 | COMPLETE.
SURRY | DOBSON SCHOOL GREENWAY |  | CENTRAL MIDDLE SCHOOL TO THE ELEMENTARY SCHOOL OF DOBSON. CONSTRUCT GREENWAY CONNECTOR. |  | Bike & Ped | NCDOT Selected (Other Selection Process) | 11 | Northwest Piedmont RPO | BN-0004 | Exempt | CRPLT5, L | 2025 | 50000 |  |  | 2026 | 1485000 |  |  | 1535000
SURRY | MOUNT AIRY | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 0.69 | Bike & Ped | STI (Prioritization) | 11 | Northwest Piedmont RPO | EB-5845 | Division 11 | L, TA5T50 | 2026 | 161000 |  |  | 2027 | 430000 |  |  | 591000
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | ELKIN | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 0.23 | Bike & Ped | STI (Prioritization) | 11 | Northwest Piedmont RPO | EB-5961 | Division 11 | L, TALT5 | 2026 | 53000 |  |  | 2027 | 175000 |  |  | 228000
SURRY | I-77 NORTHBOUND | NCDOT | REPLACE BRIDGE 850006 OVER NC 268, NORFOLK SOUTHERN RAILROAD, AND THE YADKIN RIVER. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5831 | Statewide Mobility | BFP | 2024 | 320000 |  |  | 2025 | 24000000 |  |  | 24320000
SURRY | SR 2080 (QUAKER CHURCH ROAD) | NCDOT | REPLACE BRIDGE 850152 OVER ARARAT RIVER. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5832 | Division 11 | BGOFF | 2029 | 250000 |  |  | 2030 | 4000000 |  |  | 4250000
SURRY | SR 1149 (ELK SPUR STREET) | NCDOT | REPLACE BRIDGE 850387 OVER ELKIN CREEK. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5971 | Division 11 | BGOFF | 2027 | 500000 |  |  | 2030 | 6500000 |  |  | 7000000
SURRY | SR 2081 | NCDOT | REPLACE BRIDGE 850153 OVER HOGAN CREEK. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0210 | Highway Fund | DP |  |  |  |  | 2020 | 875000 |  |  | 875000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING
SURRY | I-77 | NCDOT | MILE MARKER 91 TO MILE MARKER 95. PAVEMENT REHABILITATION. | 4.39 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5829 | [11 empty] | UNDER CONSTRUCTION
SURRY | I-77 | NCDOT | MILE MARKER 91 TO MILE MARKER 95. DIAMOND GRINDING | 4.39 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5829A | Statewide Mobility | T |  |  |  |  | 2022 | 3600000 |  |  | 3600000 | UNDER CONSTRUCTION.
SURRY | I-74 | NCDOT | I-77 TO US 601. PAVEMENT REHABILITATION. | 6.28 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5907 | Statewide Mobility | BGLT5 |  |  |  |  | 2022 | 5543000 |  |  | 5543000 | UNDER CONSTRUCTION.
SURRY | NC 89 (PINE STREET) | NCDOT | SR 1345 (BEULAH ROAD/ BEULAH CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | Highway | Safety | 11 | Northwest Piedmont RPO | HS-2011G | Region F | HF, HSIP | 2025 | 425000 | 2025 | 25000 | 2026 | 1250000 | 2023 | 100000 | 1800000 | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS.
SURRY | US 601 | NCDOT | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | 0.98 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5714 | Region F | T | 2019 | 10950000 | 2024 | 1200000 | 2030 | 29800000 |  |  | 41950000 | RIGHT-OF-WAY IN PROGRESS
SURRY | US 601 | NCDOT | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 7.19 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5836 | Division 11 | BGLT5, T | 2026 | 3100000 | 2026 | 1700000 | 2028 | 181835000 |  |  | 186635000 | NC BUILD BOND FUNDING: $35.5M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
SURRY | NC 89 (WEST PINE STREET) | NCDOT | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5901 | Region F | BGLT5 | 2024 | 370000 | 2024 | 410000 | 2025 | 7701000 |  |  | 8481000
SURRY | NC 89 (WEST PINE STREET) | NCDOT | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | 3.81 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5905 | Division 11 | BGLT5 | 2026 | 19400000 | 2026 | 28399000 | 2029 | 53401000 |  |  | 101200000
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | NCDOT | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | 0.5 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5910 | Division 11 | BGLT5 | 2022 | 900000 | 2022 | 400000 | 2023 | 1700000 |  |  | 3000000 | UNDER CONSTRUCTION.
SURRY | US 52 BYPASS (ANDY GRIFFITH PARKWAY) | NCDOT | YVRR CROSSING 721996Y IN MOUNT AIRY. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 11 | Northwest Piedmont RPO | RX-2411A | Division 11 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
SWAIN | NC 28 | NCDOT | SR 1121 (WATTIA ROAD) AT ALMONDS TO EXISTING US 19/NC 28 | 1.517 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009DA | [11 empty] | COMPLETE
SWAIN | GREAT SMOKY MOUNTAINS NATIONAL PARK | NCDOT | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. |  | Highway | Other | 14 | Southwestern RPO | HO-0004 | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 375000 | 375000 | IN PROGRESS
SWAIN | US 19 | NCDOT | SR 1336 TO JACKSON COUNTY. INSTALL RUMBLE STRIPES AND LONG LIFE PAVEMENT MARKINGS. | 5.15 | Highway | Safety | 14 | Southwestern RPO | HS-2014T | Region G | HSIP |  |  |  |  | 2024 | 364000 |  |  | 364000
SWAIN | SR 1337 (WEST DEEP CREEK ROAD) | NCDOT | SR 1338. INSTALL PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2014Z | Division 14 | HSIP |  |  |  |  | 2025 | 71000 |  |  | 71000
SWAIN | US 19 / US 74 | NCDOT | NANTAHALA OUTDOORS CENTER/ APPALACHIAN TRAIL NEAR SR 1103 NEAR WESSER. INSTALL PEDESTRIAN RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | Highway | Safety | 14 | Southwestern RPO | HS-2414A | Statewide Mobility | HSIP |  |  |  |  | 2025 | 48000 |  |  | 48000
SWAIN | NC 28 | NCDOT | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. |  | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5839A | Not Funded | T | NOT FUNDED | 1520000 | NOT FUNDED | 200000 | NOT FUNDED | 312700000 | NOT FUNDED |  | 314420000
SWAIN | SR 1321 (BRYSON WALK), SR 1336 (DEPOT STREET) | NCDOT | SR 1323 (SLOPE STREET) TO SR 1336 (DEEP CREEK ROAD). IMPROVE INTERSECTIONS. | 0.73 | Highway | STI (Prioritization) | 14 | Southwestern RPO | R-5843 | Division 14 | T |  |  |  |  | 2022 | 3629000 |  |  | 3629000 | UNDER CONSTRUCTION.
SWAIN | SWAIN COUNTY FOCAL POINT ON AGING, INC. | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 | Southwestern RPO | TK-6165 | Public Transit | 5311, L, S | [6 empty] | 2020 | 508000 | 508000 | FUNDS AUTHORIZED IN PROGRESS
SWAIN | SR 1176 (WHITTIER DEPOT ROAD) | NCDOT | GSM CROSSING 720218G IN WHITTIER. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | Rail | Rail-Highway Grade Crossing Improvement | 14 | Southwestern RPO | RX-2414F | Division 14 | RR |  |  |  |  | 2026 | 400000 |  |  | 400000
SWAIN, GRAHAM | NC 28 | NCDOT | EAST OF CALFPEN GAP IN GRAHAM COUNTY TO SR 1121 (WATTIA ROAD) AT ALMONDS IN SWAIN COUNTY | 2.381 | Highway | Appalachian Development Highway System | 14 | Southwestern RPO | A-0009DB | [11 empty] | COMPLETE
TRANSYLVANIA | ECUSTA TRAIL | NCDOT | TRANSYLVANIA COUNTY LINE TO LAMB CREEK. CONSTRUCT GREENWAY. | 8 | Bike & Ped | Federal Lands Access Program | 14 | Land-of-Sky RPO | BF-0002 | Exempt | FLAP | [6 empty] | 2023 | 1000000 | 1000000 | FLAP PROJECT NC 61. PE AWARDED $1.0M.
TRANSYLVANIA | ESTATOE TRAIL | NCDOT | CASHIERS VALLEY ROAD TO US HIGHWAY 64 IN BREVARD. CONSTRUCT MULTI-USE PATH. | 0.69 | Bike & Ped | NCDOT Selected (Other Selection Process) | 14 | Land-of-Sky RPO | BN-0011 | Exempt | CRP550, L(M) |  |  |  |  | 2025 | 560000 | 2024 | 100000 | 660000
TRANSYLVANIA | BREVARD | NCDOT | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | Bike & Ped | STI (Prioritization) | 14 | Land-of-Sky RPO | EB-5858 | Division 14 | L, TA5200 | 2022 | 20000 | 2022 | 140000 | 2022 | 1200000 | 2022 | 820000 | 2180000 | UNDER CONSTRUCTION.
TRANSYLVANIA | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | NCDOT | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | 0.41 | Highway | Appalachian Development Highway System | 14 | Land-of-Sky RPO | HA-0002 | Exempt | ADHSL | 2022 | 10000 |  |  | 2024 | 739000 | 2021 | 200000 | 949000 | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610
TRANSYLVANIA | SR 1533 (EVERETT ROAD) | NCDOT | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | 0.25 | Highway | Bridges | 14 | Land-of-Sky RPO | HB-0026 | Division 14 | BGOFF | 2025 | 200000 | 2025 | 200000 | 2028 | 4000000 |  |  | 4400000
TRANSYLVANIA | (FISH HATCHERY ROAD) SR 1408 | NCDOT | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 1.65 | Highway | Federal Lands Access Program | 14 | Land-of-Sky RPO | HF-0002 | Exempt | FLAP, HF(M) |  |  |  |  | 2023 | 230000 | 2022 | 10000 | 240000 | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS.
TRANSYLVANIA | US 276 | NCDOT | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 0.5 | Highway | Federal Lands Access Program | 14 | Land-of-Sky RPO | HF-0004 | Exempt | FLAP, HF(M) |  |  |  |  | 2026 | 495000 | 2022 | 30000 | 525000 | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. HF(M) ARE HIGHWAY FUNDS.
TRANSYLVANIA | US 276 | NCDOT | US 64 TO AVERY CREEK TRAIL HEAD. WIDEN TO 3-LANES WITH BICYCLE LANES. NC FLAP DOT 276(1). | 2.2 | Highway | Federal Lands Access Program | 14 | Land-of-Sky RPO | R-5865 | Exempt | FLAP, HF(M) | [6 empty] | 2023 | 3150000 | 3150000 | HF(M) FROM DIVISION 14 MAINTENANCE FUNDING; FLAP PROJECTS NC 35 AND NC 63.
TRANSYLVANIA | BREVARD | BREVARD | REPLACE BRIDGE 870102 ON RAILROAD AVENUE OVER KINGS CREEK. | 0.25 | Highway | Municipal Bridge | 14 | Land-of-Sky RPO | B-5550 | Division 14 | BFPOFF |  |  |  |  | 2023 | 1586000 |  |  | 1586000 | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF BREVARD
TRANSYLVANIA | US 276 | NCDOT | SR 1536 (CASCADE LAKE ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 14 | Land-of-Sky RPO | HN-0031 | Exempt | CRPLT5, T(M) | 2025 | 1320000 |  |  | 2026 | 4200000 | 2024 | 744000 | 6264000
TRANSYLVANIA | US 276 (GREENVILLE HIGHWAY) | NCDOT | SR 1118 (GALLIMORE ROAD). INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 14 | Land-of-Sky RPO | HS-2014AC | Region G | HSIP |  |  |  |  | 2024 | 200000 |  |  | 200000
TRANSYLVANIA | US 64 (ASHEVILLE HIGHWAY) | NCDOT | SR 1592 (HOSPITAL DRIVE)/ STRAUS PARKWAY. UPGRADE INTERSECTION. | 0.5 | Highway | Safety | 14 | Land-of-Sky RPO, French Broad River MPO | HS-2014M | Region G | HSIP |  |  |  |  | 2024 | 225000 |  |  | 225000
TRANSYLVANIA | SR 1512 (ECUSTA ROAD) | NCDOT | ECUSTA BYPASS INTERSECTION IN BREVARD. INSTALL RECTANGULAR RAPID FLASHING BEACON AND ACTUATED CROSSWALK LIGHTING. |  | Highway | Safety | 14 | Land-of-Sky RPO | HS-2414G | Division 14 | HSIP |  |  |  |  | 2025 | 35000 |  |  | 35000
TRANSYLVANIA | US 64 | NCDOT | MILE MARKER 5 TO MILE MARKER 13 AND MILE MARKER 25 TO MILE MARKER 31 NEAR BREVARD. INSTALL RUMBLE STRIPES WITH 6" LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 14 | Land-of-Sky RPO | HS-2414H | Region G | HSIP |  |  |  |  | 2025 | 580000 |  |  | 580000
TRANSYLVANIA | DAVIDSON RIVER VILLAGE CONNECTOR | NCDOT | US 64 TO US 276/US 64 IN PISGAH FOREST. | 0.75 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO | R-5605 | Division 14 | T |  |  |  |  | 2020 | 3345000 |  |  | 3345000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2.592M FOR CON, PAYBACK FY 2020-2034 (FY 2019/ YR 1 SALE)
TRANSYLVANIA | SR 1540 (WILSON ROAD) | NCDOT | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 3.67 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO | R-5763 | Division 14 | T | 2022 | 17400000 | 2022 | 1200000 | 2029 | 67451000 |  |  | 86051000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $17.8M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
TRANSYLVANIA | US 64 | NCDOT | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO | R-5799 | Region G | T | 2022 | 5890000 | 2022 | 600000 | 2024 | 23651000 |  |  | 30141000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
TRANSYLVANIA | US 64/ US 276 | NCDOT | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | 1.17 | Highway | STI (Prioritization) | 14 | Land-of-Sky RPO | R-5800 | Region G | BG5T50, T | 2023 | 14800000 | 2023 | 4400000 | 2030 | 32500000 |  |  | 51700000 | RIGHT-OF-WAY IN PROGRESS
TRANSYLVANIA | US 64 | NCDOT | WEST OF NC 281 N NEAR LAKE TOXAWAY TO INDIAN CREEK. WIDENING AND REALIGNMENT. | 1.44 | Highway | Transition | 14 | Land-of-Sky RPO | R-2409C | Pre-STI (Transition) | [10 empty] | COMPLETE
TRANSYLVANIA | TRANSYLVANIA COUNTY | TRANSYLVANIA COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 14 |  | TK-6167 | Public Transit | 5311, L, S | [6 empty] | 2020 | 644000 | 644000 | FUNDS AUTHORIZED IN PROGRESS
TYRRELL | US 64 | NCDOT | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | Highway | Bridges | 1 | Albemarle RPO | HB-0001 | Statewide Mobility | BFP, DP, HF(M), HFB, PROTCT, T | 2023 | 590000 | 2023 | 500000 | 2025 | 521740000 |  |  | 522830000 | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS.
TYRRELL | US 64 | NCDOT | FROM 0.85 MILES EAST OF SR 1326 (KEISER DRIVE) TO EASTERN INTERSECTION WITH SR 1229 (OLD HIGHWAY 64). INSTALL RUMBLE STRIPES. | 5.19 | Highway | Safety | 1 | Albemarle RPO | HS-2001H | Region A | HSIP |  |  |  |  | 2024 | 250000 |  |  | 250000
TYRRELL | US 64 | NCDOT | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | 14.34 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5940 | Division 1 | NHP | 2028 | 1400000 | 2028 | 6000000 | 2032 | 64900000 |  |  | 72300000
TYRRELL | TYRELL COUNTY | TYRELL COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 1 | Albemarle RPO | TK-6168 | Public Transit | 5311, L, S | [6 empty] | 2020 | 88000 | 88000 | FUNDS AUTHORIZED IN PROGRESS
UNION | MARSHVILLE | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 0.55 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0011 | Division 10 | BGDA, L |  |  |  |  | 2026 | 335000 | 2023 | 63000 | 398000
UNION | MARVIN LOOP TRAIL | MARVIN | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.16 | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | BL-0012 | Division 10 | BGDA, L, TADA | 2025 | 157000 |  |  | 2026 | 1309000 | 2023 | 244000 | 1710000
UNION | WAXHAW | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5819 | Division 10 | BGDA, L, TADA |  |  |  |  | 2022 | 1814000 | 2016 | 258000 | 2072000 | UNDER CONSTRUCTION.
UNION | INDIAN TRAIL | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). |  | Bike & Ped | Locally Selected | 10 | Charlotte Regional TPO | EB-5931 | Division 10 | BGDA, CMAQ, L, TADA | 2023 | 1509000 |  |  | 2025 | 5739000 | 2020 | 25000 | 7273000 | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22.
UNION | US 74 | INDIAN TRAIL | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 0.6 | Bike & Ped | STI (Prioritization) | 10 | Charlotte Regional TPO | EB-5723 | Division 10 | CMAQ, L(M), TAANY | 2025 | 125000 |  |  | 2026 | 3930000 |  |  | 4055000 | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | SR 1681 (OLD CAMDEN ROAD) | NCDOT | REPLACE BRIDGE 890021 OVER STEWART'S CREEK. | 0.25 | Highway | Bridges | 10 | Charlotte Regional TPO | B-5376 | Division 10 | BGOFF | 2024 | 210000 |  |  | 2028 | 3000000 |  |  | 3210000
UNION | NC 200 | NCDOT | REPLACE BRIDGE 890053 OVER STEWARTS CREEK. | 0.25 | Highway | Bridges | 10 | Charlotte Regional TPO | B-5949 | Region E | BFP | 2025 | 120000 |  |  | 2027 | 5400000 |  |  | 5520000
UNION | WAXHAW KENSINGTON DRIVE | WAXHAW | NC 16 TO SUNSET HILL ROAD. IMPROVE CORRIDOR. | 0.24 | Highway | Locally Selected | 10 | Charlotte Regional TPO | EB-5950 | Division 10 | BGANY, BGDA, L | 2022 | 591000 |  |  | 2025 | 3818000 |  |  | 4409000 | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23
UNION | VARIOUS | NCDOT | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, AND PAVEMENT RESTRIPING. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0039
UNION | NORTH CHARLOTTE AVENUE AND NEW TOWN ROAD | NCDOT | NORTH CHARLOTTE AVENUE FROM WALNUT STREET TO NC 200 AND NEW TOWN ROAD FROM CUTHBERTSON ROAD TO ENNIS ROAD. RESURFACE ROADWAYS. | 3.23 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0039A | Division 10 | BGDACV |  |  |  |  | 2022 | 938000 |  |  | 938000 | UNDER CONSTRUCTION.
UNION | VARIOUS | NCDOT | REPLACE PAVEMENT MARKINGS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0039B | Exempt | BGDACV |  |  |  |  | 2022 | 126000 |  |  | 126000 | COMPLETE.
UNION | VARIOUS | NCDOT | REPLACE TRAFFIC SIGNAL LOOPS. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0039C | Exempt | BGDACV |  |  |  |  | 2023 | 189000 |  |  | 189000 | UNDER CONSTRUCTION.
UNION | SR 1357 (POTTER ROAD) | NCDOT | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0055 | Division 10 | BGANY, HF, L, L(M), O, T(DA) | 2024 | 643000 |  |  | 2026 | 1773000 | 2023 | 475000 | 2891000 | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS.
UNION | STREET) NC 16 (NORTH BROOME | WAXHAW | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMPROVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 0.38 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0115 | Region E | BGANY, BGDA, L | 2027 | 517000 |  |  | 2028 | 3099000 | 2025 | 461000 | 4077000 | $1.605M IN BGDA FUNDS SWITCHED WITH $1.605M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24.
UNION | BONDS GROVE CHURCH ROAD | UNION COUNTY | WAXAHAW MARVIN ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0116 | Exempt | CMAQ, L(M) | 2026 | 595000 |  |  | 2028 | 4426000 | 2024 | 438000 | 5459000
UNION | NC 218 | UNION COUNTY | LOVE MILL ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0117 | Exempt | CMAQ, HF(M) | 2025 | 308000 |  |  | 2026 | 2349000 |  |  | 2657000 | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY)
UNION | NEW TOWN ROAD | NCDOT | CUTHBERTSON ROAD INTERSECTION IN WESLEY CHAPEL. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0135 | Division 10 | BGANY, HF(M), L | 2025 | 447000 |  |  | 2027 | 3646000 | 2024 | 407000 | 4500000 | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24.
UNION | INDIAN TRAIL | INDIAN TRAIL | INSTALL LEVEL 2 ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSING PATHS PARK. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | HL-0139 | Exempt | CRPDA, L |  |  |  |  | 2025 | 784000 | 2025 | 5000 | 789000
UNION | WESLEY CHAPEL | NCDOT | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6087 | Division 10 | BGDA, CMAQ, HF(M), L(M) |  |  |  |  | 2025 | 1880000 |  |  | 1880000 | UNDER CONSTRUCTION. HF(M) IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP.
UNION | MARVIN | NCDOT | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6088 | Division 10 | BGDA, CMAQ, HF(M), L(M) |  |  |  |  | 2023 | 1872000 |  |  | 1872000 | UNDER CONSTRUCTION. HF(M) FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP.
UNION | WEDDINGTON | NCDOT | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. |  | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6090 | Division 10 | CMAQ, HF(M), L(M) | 2020 | 261000 |  |  | 2022 | 2443000 | 2020 | 391000 | 3095000 | UNDER CONSTRUCTION. HF(M) IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | NC 84 | NCDOT | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6246 | Exempt | BGDA, HF(M), L, T(DA) | 2025 | 350000 |  |  | 2027 | 2080000 | 2022 | 200000 | 2630000 | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONROE AND $50K FROM UNION COUNTY. HF(M) IS SPOT MOBILITY FUNDS.
UNION | NC 84 | NCDOT | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6247 | Exempt | BGDA, HF(M), L, T(DA) | 2027 | 270000 |  |  | 2028 | 2555000 | 2021 | 363000 | 3188000 | "HF(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
UNION | NC 75 | NCDOT | SR 1111 (OLD PROVIDENCE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 10 | Charlotte Regional TPO | U-6248 | Exempt | L, T(DA) | 2025 | 1598000 |  |  | 2027 | 3544000 |  |  | 5142000 | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
UNION | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | Highway | Other | 10 | Rocky River RPO | C-5617 | Exempt | CMAQ, L | 2020 | 6000 |  |  | 2020 | 38000 | 2020 | 18000 | 62000
UNION | NC 16 (PROVIDENCE ROAD) | NCDOT | SR 1307 (BONDS GROVE CHURCH ROAD) INTERSECTION NEAR MARVIN. WIDEN ROAD, ADD TURN LANE, AND INSTALL TRAFFIC SIGNAL. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010I | Region E
UNION | SR 1313 (JOE KERR ROAD) AND SR 3486 (WHEATFIELD DR | NCDOT | INSTALL PEDESTRIAN SIGNS AND CROSSWALK. |  | Highway | Safety | 10 | Charlotte Regional TPO | HS-2410M | Division 10 | HSIP |  |  | 2025 | 10000 | 2026 | 90000 | 2025 | 30000 | 130000
UNION | VARIOUS | NCDOT | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN STATEWIDE CATEGORY. |  | Highway | Safety | 10 | Charlotte Regional TPO | W-5210SW | Statewide Mobility
UNION | SR 1005 (LANDSFORD ROAD) | NCDOT | SR 1937 (OLD PAGELAND MARSHVILLE ROAD). INSTALL AN ALL WAY STOP. |  | Highway | Safety | 10 | Charlotte Regional TPO | W-5710AD | Division 10 | HSIP |  |  |  |  | 2024 | 30000 |  |  | 30000
UNION | NC 200 (LANCASTER HIGHWAY) | NCDOT | SR 1137 (POTTER ROAD). CONSTRUCT SAFETY IMPROVEMENTS. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710AH | Region E | HF(M), HSIP | 2022 | 650000 |  |  | 2024 | 2914000 |  |  | 3564000
UNION | NC 218 | NCDOT | SR 1606 (SIKES MILLS ROAD) INTERSECTION NEAR FAIRVIEW. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710AI | Region E | HSIP |  |  |  |  | 2024 | 1217000 |  |  | 1217000
UNION | SR 1009 (OLD CHARLOTTE HIGHWAY) | NCDOT | WILLIAMS ROAD IN MONROE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Highway | Safety | 10 | Charlotte Regional TPO | W-5710AN | Division 10 | HSIP |  |  |  |  | 2024 | 952000 |  |  | 952000
UNION | UNION COUNTY | NCDOT | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710Y | Division 10 | BGANY, HF(M), HSIP |  |  |  |  | 2021 | 2581000 |  |  | 2581000 | COMPLETE. $1.385M IN BGANY USED AS PART OF FUND SWAP.
UNION | UNION COUNTY | NCDOT | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | 0.5 | Highway | Safety | 10 | Charlotte Regional TPO | W-5710Z | Region E | BGANY, BGDA, HF(M), HSIP, L(M) | 2020 | 35000 |  |  | 2022 | 2571000 | 2020 | 195000 | 2801000 | UNDER CONSTRUCTION. $1.486M IN BGANY USED AS PART OF FUND SWAP.
UNION | US 74 | NCDOT | INDIAN TRAIL-FAIRVIEW ROAD TO NORTH ROCKY RIVER ROAD IN MONROE. WIDEN ROADWAY TO SIX LANES. |  | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | HP-0001 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4650000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2250000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 84700000 |  |  | 91600000
UNION | NC 84 | NCDOT | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | 4.02 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-3467 | Region E | BGANY, T | 2024 | 41000000 | 2025 | 5700000 | 2028 | 129545000 |  |  | 176245000 | NC BUILD BOND $50M FOR CON, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE);
UNION | US 601 | NCDOT | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | 0.89 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4024 | Region E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1201000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 770000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27700000 |  |  | 29671000 | COORDINATE WITH U-5723
UNION | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD). | 3.16 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714B | Division 10 | BGANY, BGDA, O, T, T(M) | 2021 | 46000000 | 2021 | 4500000 | 2028 | 96630000 |  |  | 147130000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-4714AC. NC BUILD BONDS: $25M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
UNION | US 74 (ROOSEVELT BOULEVARD) | NCDOT | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5703 | [11 empty] | OTHER FUNDS PROVIDED BY THE CITY OF MONROE
UNION | US 74 (ROOSEVELT BLVD) | NCDOT | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5703A | Statewide Mobility | [10 empty] | COMPLETE
UNION | US 74 (ROOSEVELT BLVD) | NCDOT | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | 0.14 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5703B | Statewide Mobility | O, T | 2023 | 3457000 | 2023 | 325000 | 2026 | 1741000 |  |  | 5523000 | RIGHT-OF-WAY IN PROGRESS.
UNION | US 74 | NCDOT | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5723 | Statewide Mobility | T |  |  | 2025 | 500000 | 2030 | 23100000 |  |  | 23600000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024
UNION | US 74 | NCDOT | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN TO SIX LANES. | 2.8 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5764 | Region E | BGANY | 2025 | 48900000 | 2025 | 7400000 | 2030 | 74700000 |  |  | 131000000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | NCDOT | SR 1316 (REA ROAD EXTENSION) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 5.7 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5769
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | NCDOT | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH ROAD). WIDEN TO MULTI-LANES. | 4.05 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5769A | Region E | T | 2025 | 29801000 | 2025 | 10000 | 2030 | 71000000 |  |  | 100811000
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | NCDOT | SR 1307 (BONDS GROVE CHURCH ROAD) INTERSECTION. CONSTRUCT INTERIM SAFETY IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5769AA | Region E | HSIP, T | 2024 | 4000000 | 2024 | 1000000 | 2026 | 1100000 |  |  | 6100000
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | NCDOT | SR 1307 (BONDS GROVE CHURCH ROAD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | 1.73 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5769B | Region E | T | 2025 | 18200000 | 2025 | 10000 | 2030 | 80900000 |  |  | 99110000
UNION | SR 1362 (CHESTNUT LANE CONNECTOR) | NCDOT | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.39 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5808 | Division 10 | T | 2019 | 1615000 | 2019 | 1200000 | 2024 | 21211000 |  |  | 24026000 | RIGHT-OF-WAY IN PROGRESS. NC BUILD BOND $6M FOR CON, PAYBACK FY 2025-2039 (YR 5 SALE / FY 2025);
UNION | US 74 | NCDOT | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-5931 | Statewide Mobility | T | 2027 | 1031000 | 2027 | 520000 | 2030 | 8800000 |  |  | 10351000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764.
UNION | SR 1009 (CHARLOTTE AVENUE) | NCDOT | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | 0.37 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6031 | Division 10 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18100000 |  |  | 28900000
UNION | SR 1004 (LAWYERS ROAD) | NCDOT | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | 0.25 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-6170 | Division 10 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18700000 |  |  | 22600000
UNION | STALLINGS | NCDOT | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | 0.5 | Highway | Transition | 10 | Charlotte Regional TPO | U-5112 | Pre-STI (Transition) | BGANY, BGDA, CMAQ, HSIP, L, L(M), T(M) | 2021 | 676000 |  |  | 2024 | 10203000 |  |  | 10879000 | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | UNION COUNTY | UNION COUNTY | 5307 FUNDS TO REH/REN EQUIPMENT FFY20-21 (20-SU-089) |  | Public Transportation (Transit) | Capital (Non-STI) | 10 | Charlotte Regional TPO | TA-6149 | Public Transit | 5307, L | [6 empty] | 2020 | 17000 | 17000 | ADD FUNDING TO FY20
UNION | INDIAN TRAIL | INDIAN TRAIL | INSTALL TYPE TWO ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSINGS PATH PARK. |  | Public Transportation (Transit) | Locally Selected | 10 | Charlotte Regional TPO | TL-0030 | Exempt | CRPDA, L |  |  |  |  | 2023 | 585000 |  |  | 585000
UNION | UNION COUNTY TRANSPORTATION | UNION COUNTY TRANSPORTATION | LOW EMISSION ALTERNATIVE FUEL CONVERSION (MOTOR POOL FACILITY). |  | Public Transportation (Transit) | Locally Selected | 10 | Charlotte Regional TPO | TL-0031 | Exempt | CRPDA, L |  |  |  |  | 2024 | 200000 |  |  | 200000
UNION | UNION COUNTY | UNION COUNTY | 5307 OPERATIONS FOR FFY20-21 (20-LU-089) |  | Public Transportation (Transit) | Miscellaneous/Other | 10 | Charlotte Regional TPO | TO-6156 | Public Transit | 5307, L | [6 empty] | 2020 | 1566000 | 1566000 | ADDING FUNDS FOR FFY20-21
UNION | UNION COUNTY | UNION COUNTY TRANSPORTATION | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Rocky River RPO | TK-6169 | Public Transit | 5311, L, S | [6 empty] | 2020 | 732000 | 732000 | FUNDS AUTHORIZED IN PROGRESS
UNION | UNION COUNTY TRANSPORTATION |  | OPERATIONAL EXPENSES AND ROUTINE CAPITAL |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0052 | Public Transit | 5307, L(M) | [6 empty] | 2024 | 1942000 | 1942000
UNION | UNION COUNTY TRANSPORTATION | UNION COUNTY TRANSPORTATION | OPERATIONAL EXPENSES, ROUTINE CAPITAL, AND PLANNING |  | Public Transportation (Transit) | Operations and Maintenance | 10 | Charlotte Regional TPO | TM-0059 | Public Transit | 5307, L | [6 empty] | 2024 | 1938000 | 1938000
UNION | SR 1758, STEWART STREET, SR 1762 | NCDOT | IMPROVE CROSSINGS AT SR 1758 (NORTH MAIN STREET) AND SR 1762 ( BIVENS STREET). CLOSE THE STEWART STREET CROSSING. |  | Rail | Rail-Highway Grade Crossing Closure | 10 | Charlotte Regional TPO | RC-2010A | Division 10 | RR | 2025 | 500000 |  |  | 2025 | 3000000 |  |  | 3500000
UNION | SR 3522 (WEDDINGTON ROAD) | NCDOT | CSX CROSSING 631587H NEAR MONROE. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2010A | Division 10 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000 | UNDER CONSTRUCTION.
UNION | SR 1008 (INDIAN TRAIL ROAD) | NCDOT | CSX CROSSING 631928Y IN INDIAN TRAIL. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 10 | Charlotte Regional TPO | RX-2010C | Division 10 | RR |  |  |  |  | 2026 | 388000 |  |  | 388000
UNION | CSX SF LINE | NCDOT | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5744 | Statewide Mobility | DP, O, T | 2025 | 5851000 | 2025 | 826000 | 2028 | 23100000 |  |  | 29777000 | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX.
UNION | CSX SG LINE | NCDOT | CONSTRUCT RAIL SIDING AND GRADE SEPARATION IN VICINITY OF SR 1300 (HELMS ROAD) AND CLOSE AT-GRADE CROSSINGS AT SR 1300 (HELMS ROAD) AND SR 1432 (TORY PATH). |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5748 | [11 empty] | DP REPRESENTS FEDERAL CRISI GRANT FUNDS; OTHER FUNDING PROVIDED BY CSX.
UNION | CSX SG LINE | CSXT RR | CONSTRUCT RAIL SIDING IN WAXHAW |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5748A | Region E | T |  |  |  |  | 2022 | 5894000 |  |  | 5894000 | UNDER CONSTRUCTION.
UNION | CSX SG LINE | NCDOT | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | P-5748B | Region E | DP, O, T | 2023 | 5000000 | 2023 | 378000 | 2026 | 24202000 |  |  | 29580000 | RIGHT-OF-WAY IN PROGRESS.
UNION | CSX SF LINE | NCDOT | SR 1007 (ROCKY RIVER ROAD), SR 1009 (OLD CHARLOTTE HIGHWAY) IN MONROE. CONSTRUCT TWO RAIL-HIGHWAY GRADE SEPARATIONS. |  | Rail | STI (Prioritization) | 10 | Charlotte Regional TPO | RP-0001 | Statewide Mobility | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 210000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34000000 |  |  | 42010000
UNION, ANSON, MECKLENBURG | NC 218 | NCDOT | US 74 IN ANSON COUNTY TO US 601 IN UNION COUNTY, AND FROM MILL GROVE ROAD IN UNION COUNTY TO I-485 IN MECKLENBURG COUNTY. INSTALL MILLED RUMBLE STRIPS. | 27.51 | Highway | Safety | 10 | Charlotte Regional TPO | HS-2010C | Region E | HSIP |  |  |  |  | 2022 | 616000 |  |  | 616000 | UNDER CONSTRUCTION.
UNION, MECKLENBURG | VARIOUS | NCDOT | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN DIVISION CATEGORY. |  | Highway | Safety | 10 | Charlotte Regional TPO | W-5210DIV | Division 10
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | SR 3448-SR 3474 (TRADE STREET) TO SR 1377 (WESLEY CHAPEL-STOUTS ROAD). WIDEN TO MULTI-LANES. | 6.5 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714 | [11 empty] | OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL.
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | NCDOT | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE. | 2.02 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4714AC | Division 10 | BGANY, BGDA, T, T(DA), T(M) | 2019 | 11780000 | 2019 | 2200000 | 2026 | 33900000 |  |  | 47880000 | TO BE LET WITH U-4714B. $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. RIGHT-OF-WAY IN PROGRESS.
UNION, MECKLENBURG | SR 3174 / 1501 (IDLEWILD ROAD) | NCDOT | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY | 0.77 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4913 | [11 empty] | PROJECT BEING ACCELERATED BY A LOAN PROVIDED BY THE TOWN OF MATTHEWS. LOAN TO BE PAID BACK TO THE TOWN WITH ROW/UTIL IN 2025 AND CON IN 2026. NCDOT TO BEGIN ROW IN 2024 AND CON IN 2026.
UNION, MECKLENBURG | SR 3174 / SR 1501 (IDLEWILD ROAD) | NCDOT | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN TO SIX LANES. | 0.77 | Highway | STI (Prioritization) | 10 | Charlotte Regional TPO | U-4913B | Not Funded | T | NOT FUNDED | 14947000 | NOT FUNDED | 646000 | NOT FUNDED | 21500000 | NOT FUNDED |  | 37093000
VANCE | VARIOUS | NCDOT | VARIOUS INTERSECTIONS IN HENDERSON. UPGRADE VARIOUS INTERSECTIONS IN HENDERSON. PEDESTRIAN IMPROVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, SIDEWALK, LEADING PEDESRIAN INTERVAL, AND/OR TRAFFIC SIGNAL UPGRADES. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2405AP | Division 5 | HSIP | 2026 | 10000 | 2026 | 20000 | 2027 | 1255000 |  |  | 1285000
VANCE | SR 1001 (WARRENTON ROAD) | NCDOT | SR 1001 (WARRENTON ROAD) AT SR 1507 (BROOKSTON ROAD). SAFETY IMPROVEMENTS. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | W-5705G | Division 5 | HSIP |  |  |  |  | 2025 | 503000 |  |  | 503000
VANCE | US 1 | NCDOT | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | W-5805G | Statewide Mobility | CRPLT5, HSIP, T(M) | 2024 | 100000 |  |  | 2025 | 955000 |  |  | 1055000
VANCE | US 1 (RALEIGH ROAD) | NCDOT | BELMONT DRIVE (OLD COUNTY HOME ROAD) AND WELCOME AVENUE INTERSECTION IN HENDERSON. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | HP-0013 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 |  |  | 2800000
VANCE | HENDERSON CITYWIDE SIGNAL SYSTEM | NCDOT | INSTALL CITYWIDE SIGNAL SYSTEM. | 9.71 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | HP-0021 | Region C | BGANY |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4736000 |  |  | 5036000
VANCE | SR 1162 (DABNEY DRIVE) | NCDOT | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | 0.65 | Highway | STI (Prioritization) | 5 | Kerr-Tar RPO | U-5890 | Division 5 | T | 2027 | 43875000 | 2027 | 5000000 | 2030 | 48880000 |  |  | 97755000 | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT-OF-WAY PAYBACK 2030 - 2044 (FY 2030 / YR 10 SALE) AND BUILD NC BOND FUNDING: $19,000,000 FOR CONSTRUCTION PAYBACK 2030-2044 (FY2030/ YR 10 SALE).
VANCE | KERR AREA TRANSPORTATION AUTHORITY | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Kerr-Tar RPO | TA-6711 | Region C | FEDT, L, T | [6 empty] | 2020 | 56000 | 56000
VANCE | CSX S-LINE | NCDOT | BERT WINSTON ROAD AND CEDAR CREEK ROAD GRADE SEPARATION AND FRANKLINTON ROADWAY IMPROVEMENTS. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753BF | Statewide Mobility
VANCE | CSX S-LINE | NCDOT | SOUTH KITRELL ROADWAY IMPROVEMENTS. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753BG | Statewide Mobility
VANCE | CSX S-LINE | NCDOT | NORTH KITRELL ROADWAY IMPROVEMENTS INLCUDING MCCLANAHAN GRADE SEPARATION AND PETER GILL ROAD. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753BH | Statewide Mobility
VANCE | CSX S-LINE | NCDOT | FRANKLINTON TO RIDGEWAY - S-LINE RAIL IMPROVEMENTS. | 36.46 | Rail | Other | 5 | Kerr-Tar RPO | P-5753CA | Statewide Mobility
VANCE | CSX S-LINE | NCDOT | BEAR POND ROAD GRADE SEPARATION. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CD | Statewide Mobility
VANCE | CSX S-LINE | NCDOT | JP TAYLOR ROAD GRADE SEPARATION AND SOUTH HENDERSON ROADWAY IMPROVEMENTS. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CE | Statewide Mobility
VANCE | CSX S-LINE | NCDOT | ALEXANDER AVENUE GRADE SEPARATION AND DABNEY DRIVE ROADWAY IMPROVEMENTS. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CF | Region C | T | 2030 | 9000000 | 2030 | 800000 | 2033 | 20000000 |  |  | 28450000
VANCE | CSX S-LINE | NCDOT | ANDREWS GRADE SEPARATION AND DOWNTOWN ROADWAY IMPROVEMENTS. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CG | Statewide Mobility
VANCE | CSX S-LINE | NCDOT | WARRENTON ROAD IMPROVEMENTS AND GREYSTONE GRADE SEPARATION. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CH | Statewide Mobility
VANCE | CSX S-LINE | NCDOT | BROOKSTONE ROAD GRADE SEPARATION AND CARROLL STREET GRADE SEPARATION. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753CI | Statewide Mobility
VANCE, FRANKLIN, WAKE | NC 39 | NCDOT | NC 97 IN WAKE COUNTY TO VIRGINIA STATE LINE. INSTALL RUMBLE STRIPS. | 22.5 | Highway | Safety | 5 | Kerr-Tar RPO, Capital Area MPO | HS-2405AG | Region C | HSIP |  |  |  |  | 2025 | 1705000 |  |  | 1705000
VANCE, WARREN | I-85 | NCDOT | SOUTH OF US 158 IN VANCE COUNTY TO NORTH OF SR 1237 (MANSON DREWRY ROAD) IN WARREN COUNTY | 5.81 | Highway | Transition | 5 | Kerr-Tar RPO | I-0914BA | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
VANCE, WARREN | CSX S-LINE | NCDOT | FRANKLINTON TO RIDGEWAY. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753C | Statewide Mobility
WAKE | INTERNATIONAL AIRPORT (RDU) RALEIGH DURHAM | RALEIGH DURHAM INTERNATIONAL AIRPORT (RDU) | RECONSTRUCT RUNWAY 5L-23R. |  | Aviation | STI (Prioritization) | 5 | Capital Area MPO | AV-5700 | Statewide Mobility | O, T |  |  |  |  | 2024 | 104000000 |  |  | 104000000
WAKE | VARIOUS | FUQUAY-VARINA | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0022 | Division 5 | BGDA, L | 2023 | 187000 | 2023 | 75000 | 2024 | 1180000 | 2022 | 164000 | 1606000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | HOLLY SPRINGS | FLINT POINT LANE TO MIDDLECREST WAY IN HOLLY SPRINGS. ENHANCE PEDESTRIAN SAFETY. | 0.41 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0023 | Division 5 | BGDA, L |  |  |  |  | 2022 | 1115000 |  |  | 1115000 | UNDER CONSTRUCTION
WAKE | SR 3112 (NW CARY PARKWAY) | CARY | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0024 | Division 5 | BGDA, L | 2022 | 40000 | 2022 | 162000 | 2023 | 6744000 |  |  | 6946000 | UNDER CONSTRUCTION
WAKE | SR 2000 (WAKE FOREST ROAD) | RALEIGH | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 0.12 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0025 | Division 5 | BGANY, L | 2024 | 200000 |  |  | 2024 | 2679000 | 2022 | 150000 | 3029000 | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP
WAKE | LITTLE DRIVE | RALEIGH | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 0.24 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0026 | Division 5 | BGDA, L |  |  |  |  | 2025 | 1063000 | 2022 | 235000 | 1298000
WAKE | CRABTREE CREEK GREENWAY | RALEIGH | LASSITER MILL ROAD TO HERTFORD STREET IN RALEIGH. CONSTRUCT GREENWAY TRAIL. | 0.14 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0027 | Division 5 | BGDA, L |  |  |  |  | 2025 | 1689000 |  |  | 1689000
WAKE | CRABTREE CREEK GREENWAY | CARY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 0.53 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0036 | Exempt | CMAQ, L |  |  |  |  | 2024 | 1402000 | 2024 | 248000 | 1650000
WAKE | CRABTREE CREEK GREENWAY CONNECTOR | CARY | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | 0.21 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0037 | Exempt | CMAQ, L |  |  |  |  | 2025 | 2826000 | 2024 | 20000 | 2846000
WAKE | EAST JONES STREET | FUQUAY-VARINA | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0038 | Exempt | CMAQ, L | 2022 | 17000 | 2022 | 39000 | 2024 | 710000 | 2022 | 140000 | 906000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | CARY | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 0.71 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0039 | Exempt | CMAQ, L | 2024 | 167000 |  |  | 2024 | 1144000 | 2022 | 50000 | 1361000
WAKE | VARIOUS | APEX | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0047 | Division 5 | L, TADA | 2024 | 221000 |  |  | 2025 | 1524000 | 2024 | 20000 | 1765000
WAKE | SR 1616 (OLD APEX ROAD) | CARY | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | 1.29 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0048 | Division 5 | BGDA, L |  |  |  |  | 2025 | 1975000 | 2024 | 25000 | 2000000
WAKE | SR 1632 (LOUIS STEPHENS DRIVE) | MORRISVILLE | GRAY MARBLE ROAD TO ADDENBROCK DRIVE IN MORRISVILLE, AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | 0.63 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0049 | Exempt | CMAQ, L |  |  |  |  | 2026 | 550000 | 2025 | 10000 | 560000
WAKE | SR 1379 (PENNY ROAD) | NCDOT | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 0.28 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0051 | Exempt | CMAQ, HF(M) | 2025 | 50000 |  |  | 2025 | 350000 | 2023 | 50000 | 450000 | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS
WAKE | SR 6107 (NORTH MAIN STREET) | HOLLY SPRINGS | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 0.24 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0052 | Exempt | CMAQ, L | 2025 | 250000 |  |  | 2025 | 500000 | 2024 | 75000 | 825000
WAKE | SR 2768 (SOUTHEAST JUDD PARKWAY) | FUQUAY-VARINA | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 0.07 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0054 | Division 5 | BGDA, L |  |  |  |  | 2024 | 728000 | 2023 | 60000 | 788000
WAKE | US 401 (SOUTH SAUNDERS STREET) | RALEIGH | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | 0.12 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0089 | Exempt | CMAQ, L, L(M) |  |  |  |  | 2025 | 1095000 | 2024 | 10000 | 1105000
WAKE | HIGGINS GREENWAY | CARY | SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | 0.27 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0091 | Exempt | CMAQ, L |  |  |  |  | 2025 | 2450000 | 2024 | 10000 | 2460000
WAKE | ALSTON RIDGE GREENWAY | FUQUAY-VARINA | ALSTON RIDGE GREENWAY TO BASS LAKE GREENWAY IN FUQUAY-VARINA. COMPLETE A GAP OF GREENWAY TRAIL. | 0.41 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0092 | Exempt | CMAQ, L |  |  |  |  | 2025 | 1531000 | 2024 | 17000 | 1548000
WAKE | UTLEY CREEK GREENWAY WEST | HOLLY SPRINGS | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | 1.06 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0093 | Exempt | CMAQ, L, L(M) |  |  |  |  | 2025 | 2750000 | 2024 | 20000 | 2770000
WAKE | SAUNDERS STREET | APEX | SAUNDERS STREET AT WEST CHATHAM STREET TO HINTON STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS. | 0.4 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0095 | Division 5 | BGDA, L |  |  |  |  | 2025 | 1344000 | 2024 | 20000 | 1364000
WAKE | HIGGINS GREENWAY (PHASE IV) |  | KILDARE FARM ROAD TO HARRISON AVENUE IN CARY. CONSTRUCT MULTI-USE PATH. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0106 | Exempt | CMAQ, L |  |  |  |  | 2024 | 2951000 | 2024 | 10000 | 2961000
WAKE | ALSTON RIDGE GREENWAY |  | ALSTON RIDGE TO BASS LAKE GREEWAY IN FUQUAY VARINA. CONSTRUCT 2000 FEET OF GREENWAY. | 0.41 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0107 | Exempt | CMAQ, L |  |  |  |  | 2024 | 1548000 | 2024 | 10000 | 1558000
WAKE | UTLEY CREEK GREENWAY WEST |  | PARKWAY GREENWAY CONNECTION AND ALIGNMENT IN HOLLY SPRINGS. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0108 | Exempt | CMAQ, L |  |  |  |  | 2024 | 2749000 | 2024 | 10000 | 2759000
WAKE | SOUTHWEST DOWNTOWN BIKE AND PEDESTRIAN GATEWAY |  | LAKE WHEELER ROAD FROM CENTENNIAL PARKWAY TO WEST SOUTH STREET IN RALEIGH. CONSTRUCT SHARED USE PATH. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0109 | Exempt | CMAQ, L |  |  |  |  | 2024 | 1095000 | 2024 | 10000 | 1105000
WAKE | VANDORA SPRINGS ROAD; WOODLAND ROAD | NCDOT | VANDORA SPRINGS ELEMENTARY SCHOOL TO WOODLAND ROAD; VANDORA SPRINGS ROAD TO PINEVIEW DRIVE IN GARNER. CONSTRUCT SIDEWALK. | 0.15 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | BL-0128 | Division 5 | L(M), TADA | 2025 | 73000 |  |  |  |  | 2025 | 234000 | 307000
WAKE | CRABTREE CREEK GREENWAY | CARY | CONSTRUCT GREENWAY CONNECTING EXISTING GREENWAY IN CARY THROUGH MORRISVILLE, INCLUDING REPLACEMENT OF TRAIN TRESTLE. | 1.85 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | C-5168 | Exempt | [10 empty] | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE
WAKE | SR 1306 (LAURA DUNCAN ROAD) | APEX | APEX COMMUNITY PARK AND NORTH SALEM STREET IN APEX. IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6019 | Division 5 | BGDA, L |  |  |  |  | 2021 | 544000 |  |  | 544000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION.
WAKE | BEAVER CREEK GREENWAY EXTENSION | APEX | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | 1.21 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6021 | Division 5 | L, L(M), TADA |  |  |  |  | 2022 | 8201000 |  |  | 8201000
WAKE | (SR 1307) WEST CHATHAM STREET | APEX | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 0.31 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6046 | Division 5 | BGDA, L |  |  |  |  | 2024 | 953000 | 2024 | 10000 | 963000
WAKE | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | WENDELL | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 1.47 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6048 | Division 5 | BGDA, L | 2023 | 75000 |  |  | 2023 | 1575000 |  |  | 1650000 | UNDER CONSTRUCTION
WAKE | AVENT FERRY ROAD | HOLLY SPRINGS | GB ALFORD HIGHWAY TO NORTH OF OAK STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO GRIGSBY AVENUE VIA OAK STREET IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | 0.65 | Bike & Ped | Locally Selected | 5 | Capital Area MPO | EB-6049 | Division 5 | BGDA, L |  |  |  |  | 2024 | 1250000 | 2024 | 10000 | 1260000
WAKE | OPTIMIST FARM GREENWAY | CARY | EXISTING SEGMENT OF THE GREENWAY BEHIND TRUELOVE DRIVE SOUTH AND WEST TO WEST LAKE ROAD IN CARY. CONSTRUCT 10' WIDE GREENWAY AND .2 MILES OF SIDEWALK. INCLUDES PEDESTRIAN IMPROVEMENTS AT ONE INTERSECTION, AND MID-BLOCK CROSSINGS ON OPTIMIST FARM ROAD (RRFB OR PHB) AND ON HENDERSON ROAD (HIGH VISIBILITY CROSSWALK AND PED CROSSING SIGNS). | 1.2 | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | BL-0126 | Division 5 | CMAQ, L, L(M) |  |  |  |  | 2025 | 5000000 |  |  | 5000000
WAKE | SOUTH GARNER GREENWAY | GARNER | VANDORA SPRINGS ROAD AND BUFFALOE ROAD TO LAKE BENSON PARK IN GARNER. CONSTRUCT A MULTI-USE PATH ALONG THE WEST / SOUTH SIDE OF BUFFALOE ROAD. INCLUDES A PEDESTRIAN BRIDGE CROSSING AND BOARDWALK SEGMENTS. | 1.75 | Bike & Ped | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | BL-0129 | Division 5 | CMAQ, L, L(M) |  |  |  |  | 2025 | 5300000 | 2025 | 16000 | 5316000
WAKE | SR 1153 (TINGEN ROAD) |  | CONSTRUCT A PEDESTRIAN BRIDGE OVER CSX RAILROAD WITHIN THE EXISTING ALIGNMENT OF SR 1153 (TINGEN ROAD) IN APEX. | 0.25 | Bike & Ped | Other | 5 | Capital Area MPO | BO-2416 | Exempt | HP, L | 2025 | 48000 |  |  |  |  | 2024 | 640000 | 688000 | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME.
WAKE | SR 1011 (SOUTH SALEM STREET) | APEX | PLEASANT PLAINS ROAD TO CHATHAM STREET. CONSTRUCT BICYCLE LANES AND INSTALL SHARED LANE MARKINGS. | 2.9 | Bike & Ped | Other | 5 | Capital Area MPO | BO-2422 | Exempt | HP, L, L(M) | 2026 | 890000 |  |  | 2027 | 2970000 | 2025 | 740000 | 4600000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206.
WAKE | WALNUT CREEK GREENWAY | CARY | DOWNTOWN CARY PARK TO BUCK JONES ROAD AT I-40. CONSTRUCT GREENWAY. | 2.6 | Bike & Ped | Other | 5 | Capital Area MPO | BO-2423 | Exempt | HP, L(M) | [6 empty] | 2025 | 625000 | 625000 | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC207.
WAKE | SR 1012 (WESTERN BOULEVARD) | NCDOT | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 0.06 | Bike & Ped | STI (Prioritization) | 5 | Capital Area MPO | EB-5718 | Division 5 | L(M), TAANY | 2028 | 6100000 | 2028 | 310000 | 2029 | 5600000 |  |  | 12010000 | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166
WAKE | SR 1637 (CHURCH STREET) | MORRISVILLE | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 2.97 | Bike & Ped | STI (Prioritization) | 5 | Capital Area MPO | EB-5838 | Division 5 | L, TAANY | 2025 | 250000 |  |  | 2025 | 1450000 | 2022 | 300000 | 2000000
WAKE | BLACK CREEK GREENWAY | CARY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 2.74 | Bike & Ped | STI (Prioritization) | 5 | Capital Area MPO | EB-5894 | Division 5 | CMAQ, L, TAANY |  |  |  |  | 2023 | 15121000 |  |  | 15121000 | UNDER CONSTRUCTION
WAKE | NC 55 (EAST WILLIAMS STREET) | HOLLY SPRINGS | SR 1301 (SUNSET LAKE ROAD) TO NC 55 IN HOLLY SPRINGS. CONSTRUCT SIDEWALK. | 0.9 | Bike & Ped | STI (Prioritization) | 5 | Capital Area MPO | EB-5895 | Division 5 | L, TAANY |  |  |  |  | 2021 | 500000 |  |  | 500000 | UNDER CONSTRUCTION
WAKE | NC 50 | NCDOT | REPLACE BRIDGE 910069 OVER US 70 IN GARNER. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-4654 | Region C | BFP |  |  |  |  | 2024 | 9000000 |  |  | 9000000
WAKE | US 70/US 401/NC 50 (CAPITAL BOULEVARD) | NCDOT | REPLACE BRIDGE 910227 OVER PEACE STREET AND BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH AND REVISE INTERCHANGE AT PEACE STREET. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5121 | Region C | BGDA, L, L(M) |  |  |  |  | 2024 | 7760000 |  |  | 7760000 | UNDER CONSTRUCTION; PARTICIPATION BY CITY OF RALEIGH; INCLUDES B-5317
WAKE | SR 1321 (AVENT FERRY ROAD) | NCDOT | REPLACE BRIDGE 910318 OVER LAKE JOHNSON IN RALEIGH. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5130 | Division 5 | BFP |  |  |  |  | 2029 | 3650000 |  |  | 3650000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 2044 (LIGON MILL ROAD) | NCDOT | REPLACE BRIDGE 910126 OVER SMITHS CREEK IN WAKE FOREST. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5318 | Division 5 | BFP |  |  |  |  | 2023 | 11000000 |  |  | 11000000 | UNDER CONSTRUCTION
WAKE | SR 1630 (GREEN LEVEL CHURCH ROAD) | NCDOT | REPLACE BRIDGE 910061 OVER KIT CREEK IN CARY. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5673 | Division 5 | HFB | 2024 | 290000 |  |  | 2029 | 6600000 |  |  | 6890000
WAKE | US 401 (CAPITAL BOULEVARD) | NCDOT | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5684 | Region C | BFP | 2029 | 6300000 | 2029 | 380000 | 2030 | 11600000 |  |  | 18280000
WAKE | NC 231 | NCDOT | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5986 | Region C | BFP, HFB | 2027 | 1104000 | 2027 | 352000 | 2028 | 5300000 |  |  | 6756000
WAKE | US 401 | NCDOT | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | B-5987 | Region C | NHPB | 2026 | 640000 | 2026 | 640000 | 2029 | 24500000 |  |  | 25780000 | RIGHT OF WAY IN PROGRESS.
WAKE | SR 1179 (BRIDGE STREET) | NCDOT | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | 0.25 | Highway | Bridges | 5 | Capital Area MPO | HB-0029 | Division 5 | BGOFF | 2027 | 100000 | 2027 | 100000 | 2029 | 2000000 |  |  | 2200000
WAKE | NEW ROUTE; SR 1152 (HOLLY SPRINGS - NEW HILL ROAD) | NCDOT | NEW ROUTE INTERSECTING GREEN OAKS PARKWAY BETWEEN THOMAS MILL ROAD AND NC 55, SR 1153 INTERSECTION WITH BENNET KNOLL PARKWAY, AND SR 1152 INTERSECTION WITH SR 1153 IN HOLLY SPRINGS. CONSTRUCT ACCESS ROAD AND INTERSECTION IMPROVEMENTS. | 1.55 | Highway | Economic Development | 5 | Capital Area MPO | HE-0002 | Division 5 | T |  |  |  |  | 2025 | 9691000 |  |  | 9691000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FUJIFILM DIOSYNTH BIOTECHNOLOGIES.
WAKE | VARIOUS | NCDOT | INTERCHANGE IMPROVEMENTS AT US 1 / SR 1127 (NEW HILL-HOLLEMANN ROAD), INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) / SR 1149 (FRIENDSHIP ROAD) AND SR 1149 (FRIENDSHIP ROAD) / SR 1152 (OLD HOLLY SPRINGS-NEW HILL ROAD). |  | Highway | Economic Development | 5 | Capital Area MPO | HE-0010 | Division 5 | T | 2026 | 200000 |  |  | 2027 | 9301000 | 2023 | 500000 | 10001000 | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN.
WAKE | SR 5220 (JONES SAUSAGE ROAD) | NCDOT | SR 1004 (EAST GARNER ROAD) TO I-40 IN GARNER. WIDEN ROADWAY FROM SOUTH OF SR 2585 (WILMINGTON ROAD) TO I-40, INCLUDING ACCESS POINT IMPROVEMENTS, AND CONSTRUCT IMPROVEMENTS AT SR 1004 INTERSECTION AND I-40 INTERCHANGE. | 1.44 | Highway | Economic Development | 5 | Capital Area MPO | U-6099 | Division 5 | [10 empty] | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMAZON
WAKE | I-40 | NCDOT | SR 1728 (WADE AVENUE) TO I-440 / US 1 IN RALEIGH. PAVEMENT AND BRIDGE REHABILITATION. | 3.84 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5943 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 18419000 |  |  | 18419000 | UNDER CONSTRUCTION
WAKE | I-87 / US 64 / US 264 | NCDOT | I-440 IN RALEIGH TO SR 1003 (ROLESVILLE ROAD). PAVEMENT REHABILITATION. | 9.91 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5944 | Statewide Mobility | NHPIM |  |  |  |  | 2031 | 28600000 |  |  | 28600000
WAKE | I-540 | NCDOT | TRIANGLE TOWNE CENTER BOULEVARD IN RALEIGH TO I-495 / US 64 / US 264 IN KNIGHTDALE. PAVEMENT REHABILITATION. | 8.97 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5945 | Statewide Mobility | NHPIM |  |  |  |  | 2031 | 27900000 |  |  | 27900000
WAKE | I-440 / US 1 | NCDOT | SR 1728 (WADE AVENUE) TO SR 2000 (WAKE FOREST ROAD) IN RALEIGH. PAVEMENT REHABILITATION. | 4.85 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5997 | Statewide Mobility | NHPIM |  |  |  |  | 2024 | 23100000 |  |  | 23100000
WAKE | I-540 | NCDOT | US 70 (GLENWOOD AVENUE) TO EAST OF TRIANGLE TOWN BOULEVARD IN RALEIGH. PAVEMENT REHABILITATION. | 12.53 | Highway | Interstate Maintenance | 5 | Capital Area MPO | I-5999 | Statewide Mobility | NHPIM |  |  |  |  | 2024 | 12511000 |  |  | 12511000 | COORDINATE WITH I-5998 AND I-6000;
WAKE | US 401 | NCDOT | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0006 | Exempt | NHPBA | 2024 | 2601000 | 2024 | 509000 | 2026 | 30500000 |  |  | 33610000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NC 55 | NCDOT | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | 1 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0007 | Exempt | BA, NHPBA | 2024 | 9100000 | 2024 | 2900000 | 2025 | 27099000 | 2021 | 2615000 | 41714000
WAKE | NC 50 (BENSON ROAD) | NCDOT | SR 2812 (TIMBER DRIVE) INTERSECTION IN GARNER. INTERSECTION IMPROVEMENTS | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008C | Exempt | BA | 2022 | 100000 |  |  | 2025 | 525000 |  |  | 625000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | NCDOT | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008D | Exempt | BA | 2024 | 1330000 | 2025 | 170000 | 2025 | 3400000 |  |  | 4900000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1010 (TEN TEN ROAD) |  | SR 1006 (OLD STAGE ROAD) AND SR 1010 (TEN TEN ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008F | Exempt | BGBA | 2025 | 510000 | 2025 | 50000 | 2026 | 2000000 |  |  | 2560000
WAKE | SR 1375 (LAKE WHEELER ROAD) | NCDOT | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008G | Exempt | BA, BGBA | 2023 | 790000 | 2024 | 240000 | 2025 | 2000000 |  |  | 3030000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | NCDOT | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008H | Exempt | BA | 2022 | 251000 | 2022 | 300000 | 2025 | 1750000 |  |  | 2301000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1006 (OLD STAGE ROAD) |  | SR 1006 (OLD STAGE ROAD) AND SR 2736 (ROCK SERVICE STATION ROAD) INTERSECTION IMPROVEMENTS | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008I | Exempt | BA | 2024 | 3100000 | 2025 | 350000 | 2025 | 9300000 |  |  | 12750000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NC 50 |  | NC 50 (BENSON ROAD) AT SR 2728 (RAND ROAD) AND SR 2711 (BUFFALOE ROAD). INTERSECTION IMPROVEMENTS, INCLUDING WIDENING OF BENSON ROAD BETWEEN RAND ROAD AND BUFFALOE ROAD. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008J | Exempt | BGBA | 2025 | 1000000 | 2026 | 600000 | 2026 | 14301000 | 2024 | 10000 | 15911000
WAKE | SR 1010 (TEN-TEN ROAD) | NCDOT | SR 1386 (BELLS LAKE ROAD) AND SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008L | Exempt | BA | 2023 | 300000 | 2025 | 225000 | 2025 | 3000000 |  |  | 3525000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NC 42 | NCDOT | SR 2735 (JOHNSON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008O | Exempt | BA | 2023 | 175000 | 2025 | 125000 | 2025 | 1300000 |  |  | 1600000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1010 (TEN-TEN ROAD) | NCDOT | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008P | Exempt | BA, HSIP | 2023 | 370000 | 2025 | 240000 | 2025 | 2700000 |  |  | 3310000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1390 (OPTIMIST FARM ROAD) | NCDOT | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008Q | Exempt | BA | 2024 | 360000 | 2025 | 60000 | 2025 | 3034000 | 2023 | 10000 | 3464000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1379 (PENNY ROAD) | NCDOT | SR 1382 (OLDE SOUTH ROAD) INTERSECTION IN RALIEGH. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0008S | Exempt | [10 empty] | DELETED
WAKE | SR 1301 (SUNSET LAKE ROAD) | FUQUAY-VARINA | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0027 | Division 5 | BGDA, L | 2023 | 385000 | 2023 | 575000 | 2025 | 578000 | 2022 | 62000 | 1600000 | RIGHT-OF-WAY IN PROGRESS
WAKE | US 401 | FUQUAY-VARINA | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0028 | Exempt | BGDA, L, L(M) |  |  |  |  | 2024 | 3202000 | 2022 | 134000 | 3336000 | UNDER CONSTRUCTION
WAKE | NC 55 | HOLLY SPRINGS | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 0.39 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0029 | Exempt | BGDA, L | 2023 | 102000 |  |  | 2024 | 914000 |  |  | 1016000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SOUTH MAIN STREET | HOLLY SPRINGS | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 0.12 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0030 | Division 5 | BGDA, L | 2023 | 451000 |  |  | 2024 | 749000 |  |  | 1200000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1007 (POOLE ROAD) | NCDOT | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0031 | Division 5 | BGDA, HF(M) | 2022 | 340000 | 2022 | 150000 | 2025 | 1700000 |  |  | 2190000 | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS
WAKE | LAKE BOONE TRAIL | RALEIGH | I-440 TO RIDGE ROAD IN RALEIGH. UPGRADE ROADWAY TO COMPLETE STREET. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0032 | Division 5 | BGDA, L |  |  |  |  | 2024 | 1264000 |  |  | 1264000
WAKE | (SR 3126) AIRPORT BOULEVARD | NCDOT | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.44 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0033 | Division 5 | BGDA, L | 2022 | 600000 |  |  | 2025 | 6474000 |  |  | 7074000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 2768 (JUDD PARKWAY) | FUQUAY-VARINA | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0041 | Exempt | CMAQ, HF(M) | 2022 | 63000 |  |  | 2023 | 2161000 | 2022 | 86000 | 2310000 | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. RIGHT-OF-WAY IN PROGRESS
WAKE | (JUDD PARKWAY) SR 1110 / SR 5056 | FUQUAY-VARINA | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0042 | Exempt | CMAQ, L | 2023 | 140000 | 2023 | 260000 | 2024 | 1274000 | 2022 | 253000 | 1927000 | RIGHT-OF-WAY IN PROGRESS
WAKE | (SIX FORKS ROAD) SR 1005 | NCDOT | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0043 | Exempt | CMAQ, HF | 2024 | 275000 |  |  | 2026 | 1040000 | 2022 | 190000 | 1505000 | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS
WAKE | SR 1349 (DILLARD DRIVE) | NCDOT | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0050 | Division 5 | BGDA, HF | 2023 | 650000 |  |  | 2025 | 623000 |  |  | 1273000 | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1319 (JONES FRANKLIN ROAD) | NCDOT | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0051 | Division 5 | BGDA, HF(M) | 2025 | 80000 |  |  | 2027 | 400000 | 2023 | 110000 | 590000 | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE.
WAKE | BLUE RIDGE ROAD | RALEIGH | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | 0.32 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0052 | Division 5 | BGANY, BGDA, L(M) |  |  |  |  | 2025 | 7997000 | 2024 | 10000 | 8007000 | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP.
WAKE | SR 1005 (SIX FORKS ROAD) | RALEIGH | ROWAN STREET TO SR 2018 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPARATED BIKEWAYS, PROTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 1.69 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0119 | Division 5 | BGANY, BGDA, L, L(M) |  |  |  |  | 2025 | 30998000 | 2025 | 51000 | 31049000 | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP
WAKE | NC 50 | CREEDMOOR | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0121 | Division 5 | BGDA, HF(M) | 2025 | 103000 |  |  | 2025 | 778000 | 2024 | 266000 | 1147000 | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS
WAKE | NC 50 | NCDOT | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0122 | Division 5 | BGDA, HF(M) | 2025 | 187000 |  |  | 2026 | 940000 | 2024 | 332000 | 1459000 | HF(M) REPRESENT SPOT MOBILITY FUNDING
WAKE | ROLESVILLE ROAD |  | INTERSECTION OF ROLESVILLE ROAD AND RILEY HILL ROAD. IMPROVE INTERSECTION. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0128 | Division 5 | BGDA, HF(M) | 2025 | 90000 |  |  |  |  | 2024 | 197000 | 287000
WAKE | VARIOUS | NCDOT | CONGESTION AND SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN WAKE COUNTY. |  | Highway | Locally Selected | 5 | Capital Area MPO | HL-0133 | Exempt | BA | [6 empty] | 2025 | 2500000 | 2500000
WAKE | SR 5220 JONES SAUSAGE ROAD | GARNER | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0140 | Division 5 | BGDA, L(M) | 2025 | 2000000 | 2025 | 500000 | 2026 | 7090000 | 2025 | 10000 | 9600000
WAKE | SR 2765 (OLD HONEYCUTT ROAD) | FUQUAY-VARINA | INTERSECTION OF OLD HONEYCUTT ROAD AND KENNEBEC ROAD (SR 2754). PROVIDE SIGNALIZATION AT THE INTERSECTION. ADD CURB, GUTTER, SIDEWALK AND ADA RAMPS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | HL-0141 | Division 5 | BGDA, L(M) |  |  |  |  | 2025 | 1212000 | 2025 | 15000 | 1227000
WAKE | NC 96 (ARENDELL AVENUE) | ZEBULON | NORTH OF PEARCES ROAD TO DOGWOOD DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.4 | Highway | Locally Selected | 5 | Capital Area MPO | U-5118FB | Region C | BGANY, BGDA, L(M) |  |  |  |  | 2025 | 1062000 |  |  | 1062000
WAKE | MORRISVILLE PARKWAY EXTENSION | CARY | WEST OF HIGHCROFT DRIVE TO EAST OF MILLS PARK DRIVE IN CARY. CONSTRUCT 2-LANE FACILITY ON 4-LANE RIGHT OF WAY. | 0.48 | Highway | Locally Selected | 5 | Capital Area MPO | U-5315A | Division 5 | [10 empty] | PROJECT COMPLETE.
WAKE | MORRISVILLE PARKWAY EXTENSION | CARY | NC 540 (TRIANGLE EXPRESSWAY / WESTERN WAKE FREEWAY). CONSTRUCT INTERCHANGE. | 1 | Highway | Locally Selected | 5 | Capital Area MPO | U-5315B | Division 5 | [10 empty] | PROJECT COMPLETE.
WAKE | SR 1650 (REEDY CREEK ROAD) | CARY | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | 1.2 | Highway | Locally Selected | 5 | Capital Area MPO | U-5501 | Division 5 | BGDA, L |  |  |  |  | 2020 | 7692000 |  |  | 7692000 | UNDER CONSTRUCTION BY TOWN OF CARY
WAKE | SR 1650 (REEDY CREEK ROAD) | CARY | SR 1652 (HARRISION AVENUE) TO SOUTH OF WATTS POND LANE IN CARY. WIDEN ROADWAY TO THREE LANES INSTALL ROUNDABOUTS AND PEDESTRIAN ENHANCEMENTS | 0.38 | Highway | Locally Selected | 5 | Capital Area MPO | U-5501A | Division 5
WAKE | WEST STREET | RALEIGH | CABARRUS STREET TO MARTIN STREET IN RALEIGH. EXTEND WEST STREET ON NEW LOCATION, WITH GRADE SEPARATION AT NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN "H" LINE. | 0.2 | Highway | Locally Selected | 5 | Capital Area MPO | U-5521 | Division 5 | BGDA, L | 2025 | 2387000 | [6 empty] | 2387000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY CITY OF RALEIGH - IN PROGRESS
WAKE | SR 1115 (AVENT FERRY ROAD) | HOLLY SPRINGS | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | 0.25 | Highway | Locally Selected | 5 | Capital Area MPO | U-5529 | Division 5 | BGDA, L |  |  |  |  | 2020 | 2330000 |  |  | 2330000 | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS
WAKE | SR 1521 (LAKE PINE DRIVE) | APEX | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTI-USE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | 0.31 | Highway | Locally Selected | 5 | Capital Area MPO | U-5537 | Division 5 | BGDA, L |  |  |  |  | 2021 | 585000 |  |  | 585000 | UNDER CONSTRUCTION BY TOWN OF APEX
WAKE | SR 3014 (MORRISVILLE- CARPENTER ROAD) | MORRISVILLE | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.2 | Highway | Locally Selected | 5 | Capital Area MPO | U-5618 | Division 5 | BGDA, HF, L, L(M) |  |  |  |  | 2020 | 8495000 |  |  | 8495000 | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "HF" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION
WAKE | APEX PEAKWAY | APEX | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | 0.25 | Highway | Locally Selected | 5 | Capital Area MPO | U-5928 | Division 5 | BGDA, L, RR |  |  |  |  | 2024 | 25000000 |  |  | 25000000
WAKE | SR 2542 (ROCK QUARRY ROAD) | RALEIGH | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | 0.83 | Highway | Locally Selected | 5 | Capital Area MPO | U-6093 | Division 5 | BGDA, L | 2021 | 1891000 |  |  | 2022 | 11062000 |  |  | 12953000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | HOLLY SPRINGS | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | 0.83 | Highway | Locally Selected | 5 | Capital Area MPO | U-6094 | Division 5 | BGDA, L | 2020 | 1480000 |  |  | 2025 | 1521000 |  |  | 3001000 | RIGHT-OF-WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS
WAKE | NC 98 | WAKE FOREST | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | 0.75 | Highway | Locally Selected | 5 | Capital Area MPO | U-6222 | Exempt | BGDA, HF |  |  |  |  | 2021 | 1050000 | 2020 | 150000 | 1200000 | "HF" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION
WAKE | SR 2700 (WHITE OAK RD) | GARNER | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTI-LANE ROUNDABOUT. | 1.06 | Highway | Locally Selected | 5 | Capital Area MPO | U-6225 | Division 5 | BGDA, L | 2021 | 75000 |  |  | 2024 | 3441000 |  |  | 3516000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS.
WAKE | SR 1624 (CARPENTER FIRE STATION ROAD) | CARY | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | 0.95 | Highway | Locally Selected | 5 | Capital Area MPO | U-6227 | Division 5 | BGANY, BGDA, L | 2021 | 5629000 |  |  | 2026 | 8100000 |  |  | 13729000 | RIGHT-OF-WAY IN PROGRESS. $3,645,000 IN STBG-ANYAREA FUNDS RESULTING FROM FUND SWAPS
WAKE | US 401 BUSINESS (SOUTH MAIN STREET) SR 2051 ROAD); | ROLESVILLE | SR 2051 (BURLINGTON MILLS ROAD), EAST OF ROLESVILLE MIDDLE SCHOOL TO US 401 BUSINESS (SOUTH MAIN STREET) IN ROLESVILLE. REALIGN ROADWAY AND CONSTRUCT NEW INTERSECTION WITH SOUTH MAIN STREET. US 401 BUSINESS (SOUTH MAIN STREET), SR 2051 (BURLINGTON MILLS ROAD) TO NORTH OF SR 1003 (EAST YOUNG STREET) / SR 1945 (WEST YOUNG STREET) IN ROLESVILLE. CONSTRUCT SIDEWALK EXTENSIONS AND COMPLETE STREET IMRPOVEMENTS. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | U-6241 | Division 5 | BGDA, L |  |  |  |  | 2022 | 20452000 |  |  | 20452000 | UNDER CONSTRUCTION
WAKE | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | RALEIGH | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | 1.44 | Highway | Locally Selected | 5 | Capital Area MPO | U-6242 | Division 5 | BGANY, BGDA, L(M) | 2023 | 1700000 | 2023 | 1100000 | 2025 | 11148000 |  |  | 13948000 | RIGHT-OF-WAY IN PROGRESS. $8,918,000 in STBG-ANY FUNDS IS FROM A FUND SWAP.
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | HOLLY SPRINGS | FLINT POINT LANE TO SR 1301 (SUNSET LAKE ROAD) IN HOLLY SPRINGS. WIDEN TO A FOUR-LANE MEDIAN-DIVIDED FACILITY AND CONSTRUCT SIDEWALK. | 1.52 | Highway | Locally Selected | 5 | Capital Area MPO | U-6243 | Division 5 | BGDA, L |  |  |  |  | 2022 | 18000000 |  |  | 18000000 | UNDER CONSTRUCTION
WAKE | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | WENDELL | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | 0.5 | Highway | Locally Selected | 5 | Capital Area MPO | U-6244 | Exempt | BGDA, L | 2022 | 110000 |  |  | 2024 | 649000 |  |  | 759000 | RIGHT-OF-WAY IN PROGRESS.
WAKE | SHELLEY ROAD | RALEIGH | REPLACE BRIDGE 910378 OVER MINE CREEK FROM SHADOWBROOK DRIVE TO FOREST LAWN COURT. | 0.25 | Highway | Municipal Bridge | 5 | Capital Area MPO | HM-0002 | Division 5 | BFPOFF | 2025 | 300000 | 2025 | 250000 | 2026 | 2500000 |  |  | 3050000
WAKE | CHESWICK DRIVE | RALEIGH | REPLACE BRIDGE 910627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 0.25 | Highway | Municipal Bridge | 5 | Capital Area MPO | HM-0003 | Division 5 | BFPOFF | 2025 | 250000 | 2025 | 250000 | 2025 | 1250000 | 2024 | 500000 | 2250000
WAKE | RALEIGH |  | NEW HOPE ROAD AND EVA MAE DRIVE. CONSTRUCT TURN LANES. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0012 | Exempt | CMAQ, T | 2025 | 63000 |  |  | 2026 | 676000 | 2024 | 161000 | 900000
WAKE | GLENWOOD AVENUE |  | SR 1728 (WADE AVENUE) EASTBOUND RAMPS / COLE STREET INTERSECTION. CONSTRUCT LEFT TURN LANE FROM WESTBOUND GLENWOOD AVENUE TO EASTBOUND WADE AVENUE LOOP. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0016 | Exempt | CMAQ, HF(M) | 2025 | 25000 |  |  | 2026 | 235000 | 2024 | 124000 | 384000 | HF(M) ARE SPOT SAFETY FUNDS.
WAKE | ZEBULON |  | PEARCES ROAD AND PROCTOR STREET. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0018 | Exempt | CMAQ, T | 2025 | 40000 |  |  | 2026 | 1400000 | 2024 | 118000 | 1558000
WAKE | CENTRAL PINES REGIONAL COUNCIL | CAMPO | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | Highway | NCDOT Selected (Other Selection Process) | 5 | Capital Area MPO | HN-0026A | Exempt | CMAQ, L(M) | [6 empty] | 2024 | 3146000 | 3146000
WAKE | MINGO CREEK GREENWAY | KNIGHTDALE | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE |  | Highway | Other | 5 | Capital Area MPO | C-5604HA | Exempt | CMAQ, L(M) | 2024 | 300000 |  |  | 2023 | 3431000 |  |  | 3731000 | UNDER CONSTRUCTION
WAKE | HIGGINS GREENWAY | CARY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 |  | Highway | Other | 5 | Capital Area MPO | C-5604ID | Exempt | CMAQ, L(M) |  |  |  |  | 2023 | 1249000 |  |  | 1249000
WAKE | VARIOUS | NCDOT | NCDOT MULTI-MODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. |  | Highway | Other | 5 | Capital Area MPO | HO-0001 | Exempt | DP, HF(M) |  |  |  |  | 2022 | 227000 | 2021 | 311000 | 538000 | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT. "HF(M)" FUNDS REFLECT SPOT MOBILITY MATCHING FUNDS.
WAKE | NCSU CAMPUS | NCDOT | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. |  | Highway | Other | 5 | Capital Area MPO | HO-0001AA | Exempt | DP, HF(M) |  |  |  |  | 2023 | 2981000 | 2021 | 369000 | 3350000 | UNDER CONSTRUCTION
WAKE | NCSU CAMPUS | NCDOT | FIBER OPTIC CABLE INSTALLATION. |  | Highway | Other | 5 | Capital Area MPO | HO-0001AB | Exempt | DP, HF(M) |  |  |  |  | 2024 | 168000 | 2022 | 150000 | 318000
WAKE | NCSU CAMPUS | NCDOT | ECO DRIVING APPLICATION |  | Highway | Other | 5 | Capital Area MPO | HO-0001AC | Exempt | DP, HF(M) |  |  |  |  | 2024 | 704000 | 2023 | 74000 | 778000 | PROJECT DELETED
WAKE | NCSU CAMPUS | NCDOT | SYSTEMS ENGINEERING, GRANT ADMINISTRATION |  | Highway | Other | 5 | Capital Area MPO | HO-0001B | Exempt | DP, HF(M) | [6 empty] | 2021 | 200000 | 200000
WAKE | NCSU CAMPUS | NCDOT | BEFORE & AFTER STUDY, EXPANSION FEASIBILITY STUDY |  | Highway | Other | 5 | Capital Area MPO | HO-0001C | Exempt | DP, HF(M) | [6 empty] | 2021 | 310000 | 310000
WAKE | I-40 | NCDOT | SR 1728 (WADE AVENUE) TO I-440 / US 1 / US 64. WIDEN TO SIX LANES. | 4 | Highway | Pre-STI (Historic) | 5 | Capital Area MPO | I-4744 | Pre-STI (Transition) | NHP |  |  |  |  | 2009 | 4635000 |  |  | 4635000 | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020
WAKE | US 401 | NCDOT | SR 2044 (LIGON MILL ROAD) TO NORTH OF SR 2225 (LOUISBURY ROAD) | 2.237 | Highway | Pre-STI (Historic) | 5 | Capital Area MPO | R-2814A | [11 empty] | COMPLETE
WAKE | US 401 | NCDOT | ROLESVILLE BYPASS, NORTH OF SR 2225 (LOUISBURY ROAD) TO NC 96 ON NEW LOCATION | 6.401 | Highway | Pre-STI (Historic) | 5 | Capital Area MPO | R-2814B | Pre-STI (Transition) | BGANY | 2009 | 1727000 |  |  | 2011 | 7083000 |  |  | 8810000 | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022
WAKE | VARIOUS | NCDOT | DOWNTOWN RALEIGH BUSINESS DISTRICT. TRAFFIC SIGNAL REVISIONS AT VARIOUS LOCATIONS. |  | Highway | Safety | 5 | Capital Area MPO | HS-2005F | Division 5 | HSIP |  |  |  |  | 2023 | 200000 |  |  | 200000 | UNDER CONSTRUCTION
WAKE | SR 2215 (BUFFALOE ROAD) | NCDOT | SR 2214 (SOUTHHALL ROAD)/BRINTONS COTTAGE STREET AND VALLEY STREAM DRIVE INTERSECTIONS IN RALEIGH. TRAFFIC SIGNALS REVISIONS, CURB RAMPS, AND PAVEMENT MARKINGS. | 0.33 | Highway | Safety | 5 | Capital Area MPO | HS-2005G | Division 5 | HSIP |  |  |  |  | 2024 | 147000 |  |  | 147000
WAKE | SR 1645 (LUMLEY ROAD) | NCDOT | I-540 WESTBOUND RAMP/ARCO CORPORATE DRIVE IN RALEIGH. WIDENING, TURN LANE CONSTRUCTION, TRAFFIC SIGNAL UPGRADE. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2005I | Division 5 | HSIP |  |  |  |  | 2025 | 240000 |  |  | 240000
WAKE | SR 2516 (HODGE ROAD) | NCDOT | THE MINGO CREEK TRAIL CROSSING. RELOCATE CROSSWALK. |  | Highway | Safety | 5 | Capital Area MPO | HS-2005J | Division 5 | HSIP |  |  |  |  | 2024 | 190000 |  |  | 190000
WAKE | US 401 | NCDOT | SR 2108/SR 2036 (NEW HOPE ROAD) AND US 401 AT CALVARY DRIVE. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2005K | Region C | HSIP |  |  |  |  | 2024 | 170000 |  |  | 170000 | UNDER CONSTRUCTION
WAKE | SR 1142 (HUMIE OLIVE ROAD) | NCDOT | SR 1142 (HUMIE OLIVE ROAD) AT BLAZING TRAIL DRIVE/DRIVEWAY ACCESS TO APEX FRIENDSHIP HIGH AND ELEMENTARY SCHOOLS. INSTALL TRAFFIC AND PEDESTRIAN SIGNALS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2005Q | Division 5 | HSIP |  |  |  |  | 2024 | 130000 |  |  | 130000
WAKE | US 70/US 401/NC 50 (WILMINGTON STREET) | NCDOT | SR 1370/SR 2684 (TRYON ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AA | Region C | HSIP |  |  | 2025 | 2000 | 2025 | 270000 |  |  | 272000
WAKE | SR 2000 (FALLS OF NEUSE ROAD) | NCDOT | NORTH BEND DRIVE INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AB | Division 5 | HSIP | 2025 | 2000 | 2025 | 3000 | 2025 | 114000 |  |  | 119000
WAKE | SR 2000 (FALLS OF NEUSE ROAD) | NCDOT | NEWTON ROAD INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AC | Division 5 | HSIP | 2025 | 2000 | 2025 | 3000 | 2025 | 135000 |  |  | 140000
WAKE | SR 3008 (EDENTON STREET) | NCDOT | HARRINGTON STREET INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS AND HIGH VISIBILITY CROSSWALKS AND CONNECT TO RALEIGH SIGNAL SYSTEM. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AI | Division 5 | HSIP | 2025 | 20000 | 2025 | 20000 | 2026 | 300000 |  |  | 340000
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | NCDOT | SR 4089 (WINDING OAK WAY)/YMCA DRIVEWAY. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AJ | Division 5 | HSIP | 2025 | 12000 | 2025 | 6000 | 2026 | 248000 |  |  | 266000
WAKE | SR 1004 (GARNER ROAD) | NCDOT | SR 2684 (TRYON ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL, AND INSTALL PEDESTRIAN SIGNALS, CURB RAMPS, AND CROSSWALKS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AK | Division 5 | HSIP |  |  | 2025 | 8000 | 2025 | 145000 |  |  | 153000
WAKE | SR 3009 (EDWARDS MILL ROAD) | NCDOT | SR 1728 (WADE AVENUE) RAMPS. UPGRADE TRAFFIC SIGNAL, INSTALL PEDESTRIAN SIGNALS, AND INSTALL RECTANGULAR RAPID FLASHING BEACONS AT SLIP RAMPS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AN | Division 5 | HSIP |  |  |  |  | 2026 | 185000 |  |  | 185000
WAKE | SR 1835 (PINECREST ROAD) | NCDOT | GROVE BARTON ROAD/TOSCANA DRIVE INTERSECTION. INSTALL TRAFFIC SIGNAL AND INTERSECTION PEDESTRIAN IMPROVEMENTS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AQ | Division 5 | HSIP | 2025 | 30000 | 2026 | 5000 | 2026 | 340000 |  |  | 375000
WAKE | VARIOUS | NCDOT | DOWNTOWN RALEIGH PEDESTRIAN STUDY PHASE II. PEDESTRIAN IMPROVEMENTS AT MULTIPLE EXISTING CROSSWALKS INCLUDING PEDESTRIAN CURB EXTENSIONS, RAISED CROSSWALKS, AND MEDIAN REFUGE ISLANDS. |  | Highway | Safety | 5 | Capital Area MPO | HS-2405AR | Division 5 | HSIP | 2026 | 5000 | 2026 | 5000 | 2026 | 1020000 |  |  | 1030000
WAKE | US 1 (CAPITAL BOULEVARD) | NCDOT | CALVARY DRIVE INTERSECTION. CONSTRUCT SIGNAL AND CROSSWALK UPGRADES AND INSTALL MEDIAN FENCE. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405AS | Statewide Mobility | HSIP |  |  |  |  | 2025 | 395000 |  |  | 395000
WAKE | SR 1656 (TRINITY ROAD) | NCDOT | SR 1656 (TRINITY ROAD) AT SR 3009 (EDWARDS MILL ROAD). UPGRADE TRAFFIC SIGNAL TO PROVIDE PEDESTRIAN ACCOMMODATIONS AND CROSSWALKS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405D | Division 5 | HSIP |  |  | 2025 | 16000 | 2025 | 125000 |  |  | 141000
WAKE | US 70 (GLENWOOD ROAD) | NCDOT | US 70 (GLENWOOD AVENUE) AT SR 1820 (LEAD MINE ROAD)/SR 1670 (BLUE RIDGE ROAD). UPGRADE TRAFFIC SIGNAL TO PROVIDE PEDESTRIAN ACCOMMODATIONS AND CROSSWALKS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405E | Statewide Mobility | HSIP |  |  |  |  | 2025 | 175000 |  |  | 175000
WAKE | SR 1349 (DILLARD DRIVE) | NCDOT | SR 1349 (DILLARD DRIVE) AT DILLARD DRVIE MIDDLE SCHOOL / ORABELLE COURT. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405G | Division 5 | HSIP | 2025 | 8000 | 2025 | 30000 | 2025 | 297000 |  |  | 335000
WAKE | SR 2049 (FORESTVILLE ROAD) | NCDOT | SR 2049 (FORESTVILLE ROAD) AT CASHEW DRIVE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405H | Division 5 | HSIP | 2024 | 2000 | 2024 | 20000 | 2025 | 243000 |  |  | 265000
WAKE | US 70-401 (SOUTH SAUNDERS STREET) | NCDOT | US 70-401 (SOUTH SAUNDERS STREET) AT I-440 / I-40 INTERCHANGE. UPGRADE RAMP TRAFFIC SIGNALS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405J | Region C | HSIP |  |  |  |  | 2025 | 360000 |  |  | 360000
WAKE | SR 2026 (NORTH PERSON STREET) | NCDOT | POLK STREET INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS AND HIGH VISIBILITY CROSSWALKS AND CONNECT TO THE RALEIGH SIGNAL SYSTEM. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405K | Division 5 | HSIP | 2025 | 2000 |  |  | 2026 | 150000 |  |  | 152000
WAKE | SR 2754 (KENNEBEC ROAD) | NCDOT | SR 2763 (MAUDE STEWART ROAD) INTERSECTION. INSTALL ROUNDABOUT. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405O | Division 5 | HSIP | 2025 | 50000 | 2025 | 50000 | 2025 | 560000 |  |  | 660000
WAKE | SR 5144 (HERITAGE LAKE ROAD) | NCDOT | HERITAGE HEIGHTS LANE INTERSECTION. CROSSWALK AND SIDEWALK IMPROVEMENTS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405Q | Division 5 | HSIP | 2025 | 2000 | 2025 | 2000 | 2025 | 130000 |  |  | 134000
WAKE | SR 3067 (TW ALEXANDER DRIVE) | NCDOT | BRIER CLUB LANE/SALEM GLEN LANE INTERSECTION. UPGRADE TRAFFIC SIGNAL AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405R | Division 5 | HSIP | 2025 | 8000 | 2025 | 3000 | 2025 | 125000 |  |  | 136000
WAKE | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | NCDOT | GARNER ROAD TO HAYWOOD STREET. UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.25 | Highway | Safety | 5 | Capital Area MPO | HS-2405S | Division 5 | HSIP | 2025 | 3000 | 2025 | 5000 | 2025 | 440000 |  |  | 448000
WAKE | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | NCDOT | SR 3670 (BLOUNT ST) TO SOUTH EAST STREET. UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.25 | Highway | Safety | 5 | Capital Area MPO | HS-2405T | Division 5 | HSIP | 2025 | 5000 | 2025 | 3000 | 2026 | 385000 |  |  | 393000
WAKE | SR 1652 (HARRISON AVENUE) | NCDOT | SR 3081 (CHAPEL HILL ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNAL AND OTHER PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405U | Division 5 | HSIP |  |  |  |  | 2025 | 80000 |  |  | 80000
WAKE | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | NCDOT | GREGG STREET TO ROCK QUARRY ROAD. INSTALL/UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405V | Division 5 | HSIP | 2025 | 15000 | 2025 | 5000 | 2025 | 405000 |  |  | 425000
WAKE | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | NCDOT | RALEIGH BOULEVARD TO POOLE ROAD. UPGRADE TRAFFIC SIGNALS, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS, AND INSTALL LIGHTING. | 1 | Highway | Safety | 5 | Capital Area MPO | HS-2405W | Division 5 | HSIP | 2025 | 5000 | 2025 | 10000 | 2026 | 470000 |  |  | 485000
WAKE | US 70 (GLENWOOD AVENUE) | NCDOT | HILBURN DRIVE / GLENWWOOD FOREST DRIVE INTERSECTION. INSTALL/UPGRADE CROSSWALKS, PEDESTRIAN SIGNALS, AND SIDEWALK. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405X | Region C | HSIP |  |  | 2025 | 2000 | 2025 | 227000 |  |  | 229000
WAKE | SR 2026 (HAMMOND ROAD) | NCDOT | RUSH STREET INTERSECTION. UPGRADE TRAFFIC SIGNALS AND INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405Y | Division 5 | HSIP |  |  |  |  | 2025 | 183000 |  |  | 183000
WAKE | US 70/401/NC 50 (WILMINGTON STREET) | NCDOT | CHAPANOKE ROAD INTERSECTION. UPGRADE TRAFFIC SIGNAL AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | HS-2405Z | Region C | HSIP |  |  |  |  | 2025 | 89000 |  |  | 89000
WAKE | VARIOUS | NCDOT | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS - REGIONAL IMPACT CATEGORY |  | Highway | Safety | 5 | Capital Area MPO | W-5205REG | Region C
WAKE | NC 42 | NCDOT | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | Safety | 5 | Capital Area MPO | W-5805A | Region C | HSIP | 2025 | 235000 |  |  | 2026 | 725000 |  |  | 960000
WAKE | NC 98 BUSINESS | NCDOT | US 1, CLOVERLEAF DRIVE, AND RETAIL DRIVE / HAMPTON WAY IN WAKE FOREST. REVISE TRAFFIC SIGNALS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | W-5805B | Region C | [10 empty] | PROJECT DELETED; WORK TO BE ACCOMPLISHED UNDER U-6023.
WAKE | SR 1820 (LEAD MINE ROAD) | NCDOT | SR 1827 (LYNN ROAD) INTERSECTION IN RALEIGH. CONSTRUCT PEDESTRIAN REFUGE ISLANDS, AND REVISE CURB RAMPS, CROSSWALKS, AND OTHER PAVEMENT MARKINGS. | 0.5 | Highway | Safety | 5 | Capital Area MPO | W-5805C | Division 5 | HSIP |  |  |  |  | 2022 | 292000 |  |  | 292000 | UNDER CONSTRUCTION
WAKE | NC 42 | NCDOT | BRIDGE 910023 OVER MIDDLE CREEK. INSTALL GUARDRAIL. | 0.5 | Highway | Safety | 5 | Capital Area MPO | W-5805D | Region C | HSIP |  |  |  |  | 2022 | 184000 |  |  | 184000 | UNDER CONSTRUCTION
WAKE | NC 98 | NCDOT | SR 2057 / SR 4465 (MOORES POND ROAD). CONSTRUCT ROUNDABOUT. |  | Highway | Safety | 5 | Capital Area MPO | W-5805E | Region C | HSIP | 2023 | 140000 | 2025 | 125000 | 2025 | 1540000 |  |  | 1805000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1004 (GARNER ROAD); TIMBER DRIVE EAST | NCDOT | SR 2539 (YEARGAN ROAD), SR 2564 (CREECH ROAD), AND SHENSTONE BOULEVARD INTERSECTIONS IN GARNER. UPGRADE TRAFFIC SIGNALS | 1 | Highway | Safety | 5 | Capital Area MPO | W-5805H | Division 5 | HSIP |  |  |  |  | 2021 | 75000 |  |  | 75000 | UNDER CONSTRUCTION
WAKE | I-40 |  | CARY TOWNE BOULEVARD TO WADE AVENUE. CONSTRUCT OPERATIONAL IMPROVEMENTS INCLUDING AUXILIARY LANES BETWEEN WADE AVENUE AND CARY TOWNE BOULEVARD AND INTERCHANGE IMPROVEMENTS AT CARY TOWNE BOULEVARD. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0003 | Statewide Mobility | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27500000 |  |  | 34000000
WAKE | VARIOUS | NCDOT | LOCATIONS IN DIVISION 5. PROVIDE COMMUNICATION AND CAMERAS TO IMPROVE SIGNAL TIMING. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0005 | Region C | T |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15596000 |  |  | 16796000
WAKE | US 70 BUSINESS | NCDOT | RAYNOR ROAD AND GUY ROAD INTERSECTION IN RALEIGH. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 1.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0007 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 |  |  | 11000000
WAKE | HOLLY SPRINGS | NCDOT | HOLLY SPRINGS CITYWIDE SIGNAL SYSTEM. INSTALL FIBER TO CONNECT EXISTING TOWN FIBER TO INTERSECTIONS, UPGRADE EXISTING INFRASTRUCTURE INCLUDING CABINETS, CONTROLLERS, AND SOFTWARE. | 4.58 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0008 | Region C | T |  |  |  |  | 2028 | 3085000 |  |  | 3085000
WAKE | US 401 / US 70 BUSINESS | NCDOT | TRYON ROAD INTERSECTION IN RALEIGH. IMPROVE INTERSECTION SIGNALS AND MERGING BETWEEN TRYON ROAD AND MECHANICAL BOULEVARD. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0009 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5500000 |  |  | 7500000
WAKE | TOWN OF CARY | NCDOT | TOWN OF CARY SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE, INSTALL NEW FIBER, CONTROLLERS, SIGNALS, CONNECTED VEHICLE TECHNOLOGY AND OTHER EQUIPMENT AS NECESSARY. | 7.94 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0010 | Region C | L, T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10000000 |  |  | 10000000
WAKE | US 401 | NCDOT | TRYON ROAD INTERSECTION IN RALEIGH. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0012 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 |  |  | 11000000
WAKE | NC 55 | NCDOT | SOUTH MAIN STREET TO HOLLY SPRINGS ROAD. UPGRADE CORRIDOR TO SIX LANE EXPRESSWAY. | 1.6 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0014 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 60000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 64000000 |  |  | 133000000
WAKE | US 70 (GLENWOOD AVENUE) | NCDOT | AT NC 50 (CREEDMOOR ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0016 | Region C | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 |  |  | 11000000
WAKE | NC 55 BYPASS | NCDOT | AT SR 1144 (MAIN STREET). UPGRADE EXISTING INTERSECTION TO INTERCHANGE. | 2 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0017 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24700000 |  |  | 55200000
WAKE | US 401 | NCDOT | SR 5056 / SR 2768 (JUDD PARKWAY) TO FIVE POINTS INTERCHANGE OF US 401, NC 55, AND NC 42. CONSTRUCT MEDIAN THROUGHOUT CORRIDOR WITH OTHER ACCESS MANAGEMENT IMPROVEMENTS. | 1.18 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0024 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 470000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 |  |  | 9770000
WAKE | NC 98 | NCDOT | SIX FORKS ROAD INTERSECTION IN RALEIGH. UPGRADE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0025 | Region C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 |  |  | 11000000
WAKE | US 1 | NCDOT | SR 1010 (TEN TEN ROAD) INTERCHANGE. RECONSTRUCT INTERCHANGE. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | HP-0032 | Region C | T | 2027 | 21300000 | 2027 | 3300000 | 2030 | 20600000 |  |  | 45200000
WAKE | I-40 | NCDOT | I-440 / US 64 (EXIT 301) TO JOHNSTON COUNTY LINE. | 9.18 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5111SW | Statewide Mobility | NHP | 2019 | 15826000 |  |  | 2018 | 128398000 |  |  | 144224000 | SEE PARENT PROJECT FOR GARVEE DETAILS.
WAKE | I-40 | NCDOT | SR 1002 (AVIATION PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 1002 TO SR 3015 (AIRPORT BOULEVARD). | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5506 | Statewide Mobility | [10 empty] | PROJECT COMPLETE.
WAKE | I-40 | NCDOT | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | 2.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5700 | Statewide Mobility | NHP, T(M) |  |  |  |  | 2020 | 51733000 |  |  | 51733000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034
WAKE | I-40 / US 64 | NCDOT | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | 4.44 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5701 | Statewide Mobility | NHP |  |  | 2027 | 3400000 | 2027 | 161000000 |  |  | 164400000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703.
WAKE | I-40 | NCDOT | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5703 | Statewide Mobility | NHP | 2027 | 35000000 | 2027 | 7200000 | 2027 | 322696000 |  |  | 364896000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043.
WAKE | I-440 / US 1 | NCDOT | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5708 | Statewide Mobility | NHP | 2019 | 1736000 | 2024 | 2000000 | 2026 | 20580000 |  |  | 24316000 | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033
WAKE | I-40 | NCDOT | NC 54 IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5873 | Region C | [10 empty] | UNDER CONSTRUCTION
WAKE | I-40 | NCDOT | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | 2.33 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5966 | Statewide Mobility | NHP | 2029 | 430000 | 2029 | 200000 | 2032 | 73700000 |  |  | 74330000
WAKE | I-540 | NCDOT | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | 2.53 | Highway | STI (Prioritization) | 5 | Capital Area MPO | I-5968 | Statewide Mobility | NHP | 2028 | 4700000 | 2028 | 20000 | 2031 | 34800000 |  |  | 39520000
WAKE | NEW ROUTE (FUTURE NC 540) | NCDOT | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), NC 55 (SOUTH) TO EAST OF US 401 SOUTH. FREEWAY ON NEW LOCATION. TOLL PROJECT. | 7.8 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2721 | Statewide Mobility | [10 empty] | COORDINATE WITH U-5746; NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT
WAKE | NC 540 | NCDOT | NC 55 BYPASS TO EAST OF SR 1152 (HOLLY SPRINGS ROAD). CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 2.84 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2721A | Statewide Mobility | NHP |  |  |  |  | 2019 | 79500000 |  |  | 79500000 | UNDER CONSTRUCTION
WAKE | NC 540 | NCDOT | EAST OF SR 1152 (HOLLY SPRINGS ROAD) TO EAST OF US 401. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 5.37 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2721B | Statewide Mobility | NHP |  |  |  |  | 2019 | 63000000 |  |  | 63000000 | UNDER CONSTRUCTION
WAKE | NEW ROUTE (FUTURE NC 540) | NCDOT | EASTERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), I-40 TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 10.8 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2829 | Statewide Mobility | T | 2025 | 1133000 | [6 empty] | 1133000
WAKE | NEW ROUTE (FUTURE NC 540) | NCDOT | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 6.42 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2829A | Statewide Mobility | BOND R, NHP, T(M) | 2025 | 41809000 | 2025 | 3544000 | 2025 | 419150000 |  |  | 464503000 | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039
WAKE | NEW ROUTE (FUTURE NC 540) | NCDOT | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 3.82 | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-2829B | Statewide Mobility | BOND R, NHP, T(M) | 2025 | 33806000 | 2025 | 500000 | 2025 | 509652000 |  |  | 543958000 | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039
WAKE | NC 55 | NCDOT | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | R-5705C | Not Funded | T | NOT FUNDED | 8170000 | NOT FUNDED | 1386000 | NOT FUNDED | 17900000 | NOT FUNDED |  | 27456000
WAKE | I-440/US-1 | NCDOT | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | 5.58 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-2719 | Statewide Mobility | NHP | 2019 | 34749000 |  |  | 2019 | 158558000 |  |  | 193307000 | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT-OF-WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033
WAKE | NC 55 (WILLIAMS STREET) | NCDOT | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD) IN APEX. WIDEN TO A MULTI-LANE CURB AND GUTTER FACILITY. | 2.8 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-2901 | [11 empty] | PROJECTS U-2901AA AND AB COMPLETE
WAKE | NC 55 (WILLIAMS STREET) | NCDOT | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | 1.73 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-2901B | Region C | T | 2027 | 12900000 | 2027 | 1700000 | 2030 | 40300000 |  |  | 54900000
WAKE | NC 55 (WILLIAMS STREET) | NCDOT | CSX RAILROAD BRIDGE OVER NC 55. REPLACE RAILROAD BRIDGE. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-2901BA | Region C | T | 2026 | 830000 | 2026 | 140000 | 2028 | 30600000 |  |  | 31570000
WAKE | NC 54 (HILLSBOROUGH STREET) | NCDOT | SR 1664 / SR 3074 (BLUE RIDGE ROAD) IN VICINITY OF NC RAILROAD (CSX CORPORATION AND NORFOLK SOUTHERN) IN RALEIGH. CONSTRUCT GRADE SEPARATIONS AND ACCESS ROAD BETWEEN NC 54 AND SR 1664 / SR 3074. | 3 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-4437 | Division 5 | [10 empty] | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT - LET WITH U-2719; INCLUDES $19.9 MILLION FEDERAL TIGER GRANT
WAKE | US 64 | NCDOT | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | 3.2 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5301 | Statewide Mobility | NHP | 2028 | 82201000 | 2028 | 4400000 | 2032 | 207100000 |  |  | 293701000
WAKE | US 64 | NCDOT | CSX RAILROAD BRIDGE OVER US 64. REPLACE RAILROAD BRIDGE. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5301A | Statewide Mobility | NHP | 2027 | 5600000 | 2027 | 104000 | 2029 | 32300000 |  |  | 38004000
WAKE | US 401 | NCDOT | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO REDUCED CONFLICT INTERSECTIONS. | 1.05 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5302 | Region C | T | 2019 | 9931000 |  |  | 2026 | 24700000 | 2019 | 1801000 | 36432000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
WAKE | US 1 | NCDOT | I-540 IN RALEIGH TO SR 1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. UPGRADE ROADWAY TO CONTROLLED ACCESS FACILITY. | 10 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307
WAKE | US 1 | NCDOT | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | 1.63 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307A | Statewide Mobility | NHP | 2028 | 128500000 | 2028 | 13400000 | 2031 | 374350000 |  |  | 516250000 | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $150M FOR CONSTRUCTION, PAYBACK FY 2033-2047.
WAKE | US 1 | NCDOT | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | 2.11 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307B | Statewide Mobility | NHP | 2028 | 119500000 | 2028 | 8200000 | 2031 | 164345000 |  |  | 292045000 | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2033-2047.
WAKE | US 1 | NCDOT | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | 3.83 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307C | Statewide Mobility | NHP | 2030 | 37700000 | 2030 | 6400000 | 2033 | 219445000 |  |  | 263545000 | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2033-2047.
WAKE | US 1 | NCDOT | SOUTH OF NC 98 BUSINESS TO SR 1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | 2.33 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5307D | Statewide Mobility | NHP | 2030 | 72000000 | 2030 | 10100000 | 2033 | 186745000 |  |  | 268845000 | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2035-2049.
WAKE | US 401 | NCDOT | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | 0.81 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5746 | Region C | T | 2022 | 2938000 | 2022 | 1310000 | 2025 | 5699000 |  |  | 9947000 | RIGHT-OF-WAY IN PROGRESS
WAKE | NC 54; SR 1635 (MCCRIMMON PARKWAY) | NCDOT | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET); NC 54 AT SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. WIDEN SR 1635 AND CONVERT NC 54 AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION | 2 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5747 |  | T | [6 empty] | 2019 | 3001000 | 3001000 | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
WAKE | SR 1635 (MCCRIMMON PARKWAY) | NCDOT | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | 1.07 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5747A | Division 5 | T | 2021 | 5000000 | 2021 | 500000 | 2026 | 38610000 |  |  | 44110000 | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966; BUILD NC BONDS: $10,000,000 FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE)
WAKE | NC 54 | NCDOT | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | 0.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5747B | Region C | T | 2019 | 2072000 | 2024 | 620000 | 2026 | 43455000 |  |  | 46147000 | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) AND $10,000,000 FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE)
WAKE | US 401 | NCDOT | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | 1.5 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5748 | Region C | T | 2019 | 6840000 | 2021 | 212000 | 2024 | 22500000 | 2019 | 1921000 | 31473000 | UNDER CONSTRUCTION. BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE).
WAKE | NC 54 | NCDOT | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | 1.29 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5750 | Region C | T | 2019 | 3468000 | 2022 | 1700000 | 2026 | 34655000 | 2019 | 1620000 | 41443000 | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE, $3,371 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR1 SALE), AND $10M IN CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR7 SALE); RIGHT-OF-WAY IN PROGRESS
WAKE | US 401 | NCDOT | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | 3 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5751 | Region C | T | 2028 | 59900000 | 2028 | 3300000 | 2031 | 113300000 |  |  | 176500000
WAKE | SR 1002 (AVIATION PARKWAY) | NCDOT | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTI-LANES. | 2.45 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5811 | Division 5 | T | 2026 | 16150000 | 2026 | 2100000 | 2030 | 49030000 |  |  | 67280000 | BUILD NC BONDS: $6M FOR RIGHT-OF-WAY PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE) AND $13M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE).
WAKE | SR 1010 (TEN-TEN ROAD) | NCDOT | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTI-LANES. | 3.3 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5825 | [11 empty] | COORDINATE WITH U-6066
WAKE | SR 1010 (TEN TEN ROAD) | NCDOT | APEX PEAKWAY TO SR 1306 (SCHIEFFELIN ROAD). WIDEN TO FOUR LANES WITH REDUCED CONFLICT INTERSECTIONS. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5825A | Not Funded | T | NOT FUNDED | 10000000 | NOT FUNDED | 3300000 | NOT FUNDED | 22000000 | NOT FUNDED |  | 35300000
WAKE | US 1 | NCDOT | US 1 / SR 1010 (TEN TEN ROAD) INTERCHANGE. RECONSTRUCT INTERCHANGE. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5825B | Region C | T | 2027 | 21300000 | 2027 | 3300000 | 2030 | 20600000 |  |  | 45200000
WAKE | SR 1010 (TEN TEN ROAD) | NCDOT | SR 4070 (RELIANCE AVENUE) TO SR 1300 (KILDAIRE FARM ROAD), WIDEN TO FOUR LANES WITH REDUCED CONFLICT INTERSECTIONS. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5825C | Not Funded | T | NOT FUNDED | 11500000 | NOT FUNDED | 3300000 | NOT FUNDED | 59500000 | NOT FUNDED |  | 74300000
WAKE | SR 2000 (FALLS OF NEUSE ROAD) | NCDOT | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | 0.89 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5826 | Division 5 | T | 2024 | 280000 |  |  | 2023 | 31105000 |  |  | 31385000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE).
WAKE | SR 1632 (LOUIS STEPHENS DRIVE) | NCDOT | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.55 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5827 | Division 5 | T | 2020 | 1340000 |  |  | 2020 | 7699000 | 2019 | 1231000 | 10270000 | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT-OF-WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
WAKE | MCCRIMMON PARKWAY | NCDOT | SR 3015 (AIRPORT BOULEVARD) TO SR 1002 (AVIATION PARKWAY) IN MORRISVILLE. WIDEN TO A FOUR LANE DIVIDED FACILITY, PART ON NEW LOCATION. | 1.42 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5828 | Division 5 | T |  |  |  |  | 2019 | 3097000 |  |  | 3097000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
WAKE | SR 1115 (AVENT FERRY ROAD) | HOLLY SPRINGS | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTI-LANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | 1.02 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5889 | Division 5 | T | 2027 | 1400000 | 2027 | 500000 | 2029 | 18385000 |  |  | 20285000 | BUILD NC BONDS: $5.5M FOR CONSTRUCTION PAYBACK 2030-2044 (FY 2030 / YR 10 SALE).
WAKE | NC 50 (CREEDMOOR ROAD) | NCDOT | I-540 TO NORTH OF NC 98. WIDEN TO MULTI-LANE DIVIDED ROADWAY. | 5.12 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5891 | Region C | T | 2030 | 143200000 | 2030 | 2200000 | 2034 | 104200000 |  |  | 249600000
WAKE | VARIOUS | NCDOT | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-5967 | Region C | BGANY, T |  |  | 2027 | 33000 | 2028 | 953000 |  |  | 986000
WAKE | VARIOUS | NCDOT | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6022 | Region C | BGANY |  |  | 2022 | 451000 | 2023 | 4092000 |  |  | 4543000 | UNDER CONSTRUCTION
WAKE | VARIOUS | NCDOT | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6023 | Division 5 | BGANY |  |  | 2022 | 250000 | 2023 | 4176000 |  |  | 4426000 | UNDER CONSTRUCTION
WAKE | VARIOUS | NCDOT | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6026 | Division 5 | BGANY |  |  | 2022 | 450000 | 2023 | 2320000 |  |  | 2770000 | FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION. UNDER CONSTRUCTION
WAKE | US 401 | NCDOT | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO REDUCED CONFLICT INTERSECTION. | 1 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6112 | Region C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30480000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6720000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33600000 |  |  | 70800000 | COORDINATE WITH R-2721 AND U-5746
WAKE | VARIOUS | NCDOT | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6117 | Division 5 | BGANY |  |  | 2027 | 360000 | 2028 | 6200000 |  |  | 6560000
WAKE | VARIOUS | NCDOT | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6119 | Division 5 | BGANY |  |  |  |  | 2030 | 4700000 |  |  | 4700000
WAKE | VARIOUS | NCDOT | GARNER CITYWIDE SIGNAL SYSTEM |  | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6194 | Division 5 | BGANY |  |  | 2030 | 480000 | 2031 | 6800000 |  |  | 7280000
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | NCDOT | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | 3.44 | Highway | STI (Prioritization) | 5 | Capital Area MPO | U-6217 | Division 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 49200000 |  |  | 68900000
WAKE | SR 2703 (NEW BETHEL CHURCH ROAD) | NCDOT | REPLACE BRIDGE 910248 OVER MAHLER'S CREEK IN GARNER. | 0.25 | Highway | Transition | 5 | Capital Area MPO | B-5237 | Division 5 | T |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | BUILD NC BONDS: $2.0 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
WAKE | GOTRIANGLE | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-4818A | Public Transit | 5307, 5339, L(M) | [6 empty] | 2024 | 962000 | 962000
WAKE | GORALEIGH | GORALEIGH | REPLACEMENT BUS AND BUS FACILITIES |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-4903 | Public Transit | 5339, L | [6 empty] | 2021 | 16417000 | 16417000
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-4903A | Public Transit | 5307, CMAQ, L, S | [6 empty] | 2020 | 1126000 | 1126000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH PARK AND RIDE AT POOLE ROAD. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-5116 | Public Transit | 5307 |  |  |  |  | 2021 | 455000 |  |  | 455000
WAKE | GOTRIANGLE | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-5123A | Public Transit | 5307, 5339, L, S | [6 empty] | 2024 | 3378000 | 3378000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | BUS REPLACEMENT |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-5140 | Public Transit | 5307, L, S | [6 empty] | 2021 | 4500000 | 4500000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GO RALEIGH | GO RALEIGH | SIX EXPANSION BUSES FOR ADDING ROUTE EXPANSION SERVICE. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-5186 | Division 5 | [10 empty] | ACQUISITION IN PROGRESS BY GO RALEIGH
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | ADA EXPANSION BUS |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TA-5202 | Public Transit | 5307, 5339, L | [6 empty] | 2020 | 1184000 | 1184000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | GORALEIGH CAPITAL PROJECTS (PASSENGER AMENITIES, PEDESTRIAN CONNECTIONS, FACILITY MAINTENANCE, UPGRADE AND UPKEEPS ETC) |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0015 | Public Transit | 5307, L | [6 empty] | 2021 | 10922000 | 10922000
WAKE | GOTRIANGLE | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0016 | Public Transit | BGDA, L | 2022 | 12000 |  |  | 2022 | 550000 | 2022 | 110000 | 672000
WAKE | GOTRIANGLE | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TC-0017 | Public Transit | BGDA, L | 2022 | 14000 |  |  | 2022 | 330000 | 2022 | 130000 | 474000
WAKE | GO TRIANGLE | GO TRIANGLE | EXPAND EXISTING GARAGE FACILITY IN MORRISVILLE. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5285 | Public Transit | 5339(b), L |  |  |  |  | 2025 | 815000 | 2024 | 120000 | 935000 | IN PROGRESS
WAKE | GO TRIANGLE | GO TRIANGLE | PARK AND RIDE LOT AT SR 1774 (DISTRICT DRIVE). ADD SPACES, IMPROVE LIGHTING AND CONSTRUCT SHELTERS. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5287 | Region C | [10 empty] | IN PROGRESS
WAKE | GO RALEIGH | GO RALEIGH | INTERSECTION OF SR 2298 (EDENTON STREET) AND NORTH SALISBURY STREET IN RALEIGH. CONSTRUCT BUS STOP SHELTER. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5293 | Region C | [10 empty] | UNDER CONSTRUCTION BY GO TRIANGLE
WAKE | GORALEIGH | GORALEIGH | BUS STOP IMPROVEMENTS |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5304 | Public Transit | L | [6 empty] | 2022 | 3273000 | 3273000
WAKE | CARY TRANSIT/C-TRAN | CARY TRANSIT/C-TRAN | DOWNTOWN CARY MULTI-MODAL FACILITY. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5305 | Public Transit | L |  |  |  |  | 2022 | 44200000 |  |  | 44200000
WAKE | GORALEIGH | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5308 | Public Transit | DP, L | 2022 | 2750000 |  |  | 2023 | 23766000 | 2022 | 4000000 | 30516000 | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH.
WAKE | GOTRIANGLE | GOTRIANGLE | EXISTING PARK AND RIDE IMPROVEMENTS |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5314 | Public Transit | L | [6 empty] | 2022 | 1105000 | 1105000
WAKE | GOTRIANGLE | GOTRIANGLE | BUILD NEW PARK AND RIDE AT HILLSBOROUGH ST AND I-440 IN RALEIGH. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5315 | Public Transit | L |  |  |  |  | 2023 | 5200000 | 2022 | 2220000 | 7420000
WAKE | GOTRIANGLE | GOTRIANGLE | BUILD NEW PARK AND RIDE AT CREEDMOOR AND I-540 OR AT FALLS OF NEUSE AND I-540 IN RALEIGH. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5316 | Public Transit | L |  |  |  |  | 2024 | 1500000 | 2023 | 1100000 | 2600000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH CONSTRUCTION OF PARK AND RIDE IN ROLESVILLE. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5317 | Public Transit | L |  |  |  |  | 2021 | 55000 |  |  | 55000
WAKE | GORALEIGH | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5318 | Public Transit | L | 2024 | 2249000 |  |  | 2025 | 2989000 | 2024 | 547000 | 5785000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT CRABTREE VALLEY MALL |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5319 | Public Transit | L |  |  |  |  | 2022 | 324000 |  |  | 324000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT TRIANGLE TOWNE CENTER |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TD-5320 | Public Transit | L |  |  |  |  | 2022 | 324000 |  |  | 324000
WAKE | GOTRIANGLE | GOTRIANGLE | FIXED GUIDEWAY - COMMUTER RAIL SERVICE- DURHAM/RALEIGH |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TE-4903B | Public Transit | FED |  |  |  |  | 2020 | 222000 |  |  | 222000
WAKE | GO RALEIGH | GO RALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT WESTERN CORRIDOR (DOWNTOWN RALEIGH TO DOWNTOWN CARY). |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TL-0006 | Public Transit | L |  |  |  |  | 2022 | 45168000 | 2022 | 1500000 | 46668000
WAKE | GORALEIGH | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT SOUTHERN CORRIDOR ( DOWNTOWN RALEIGH TO DOWNTOWN GARNER) |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TL-0013 | Public Transit | L |  |  |  |  | 2022 | 27777000 | 2022 | 1500000 | 29277000
WAKE | GOCARY | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TL-0019 | Exempt | CMAQ, L | 2022 | 167000 |  |  | 2022 | 1144000 | 2022 | 51000 | 1362000
WAKE | GORALEIGH | GORALEIGH | BUILD PARK AND RIDE FACILITY AT GORMAN STREET AT I-40 IN RALEIGH |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TL-0023 | Public Transit | L |  |  |  |  | 2027 | 1614000 | 2025 | 1432000 | 3046000
WAKE | GORALEIGH | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TM-0039 | Public Transit | 5307, L |  |  |  |  | 2022 | 2000000 |  |  | 2000000
WAKE | GO RALEIGH | GO RALEIGH | CONSTRUCT BUS RAPID TRANSIT ON NEW BERN CORRIDOR. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TP-5160 | Public Transit
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT NEW BERN CORRIDOR | 3.54 | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TP-5160A | Division 5 | 5309, ARP, FUZ, L | 2021 | 3086000 |  |  | 2021 | 68507000 | 2020 | 20841000 | 92434000
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT NEW BERN CORRIDOR, BETTERMENT FUNDING | 3.54 | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TP-5160B | Division 5 | L |  |  |  |  | 2023 | 814000 |  |  | 814000
WAKE | GORALEIGH | GORALEIGH | 5310 CAPITAL AND ADMIN |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TQ-9037 | Public Transit | 5310, L | [6 empty] | 2021 | 938000 | 938000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO | TS-5104 | Public Transit | 5307, L | [6 empty] | 2021 | 542000 | 542000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SITES IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE PE |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TD-5309 | Division 5 | BGDA, L | [6 empty] | 2020 | 752000 | 752000
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOPS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE ROW |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TD-5309A | Division 5 | BGDA, L | 2020 | 250000 | [6 empty] | 250000
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SIGHTS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE CON |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TD-5309B | Division 5 | BGDA, L |  |  |  |  | 2020 | 1500000 |  |  | 1500000
WAKE | GOTRIANGLE | GOTRIANGLE | PURCHASE AND INSTALL SIGNAGE AT DESIGNATED LOCATIONS ALONG I-540 AND I-40 FOR BUS ON SHOULDER SYSTEM. (BOSS) UTILIZE EASTBOUND SHOULDER OF I-540 BETWEEN NC-147 AND CAPITAL BLVD AND EASTBOUND ON I-40 BETWEEN WADE AVENUE AND S SAUNDERS STREET. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TG-6814 | Exempt | BGDA, L | [6 empty] | 2021 | 454000 | 454000
WAKE | GOTRIANGLE | GOTRIANGLE | DESIGN, PURCHASE, AND INSTALL NEW AMENITIES AT 13 BUS STOP LOCATIONS ALONG ROUTES IN WAKE COUNTY,UPGRADES INCLUDE SHELTERS, BENCH, PAD, OR SOME COMBINATIONS |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TG-6815 | Division 5 | BGDA, L | [6 empty] | 2021 | 907000 | 907000
WAKE | GORALEIGH | GORALEIGH | DEVELOPED ENHANCED TRANSFER POINTS THROUGHOUT GO RALEIGH SYSTEM IN LOCATION WITH HIGH RIDERSHIP (75 + BOARDINGS PER DAY) |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TG-6816 | Division 5 | BGDA, L | [6 empty] | 2021 | 1185000 | 1185000
WAKE | GOTRIANGLE | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0011 | Public Transit | BGDA, L | 2022 | 18000 |  |  | 2022 | 252000 | 2022 | 64000 | 334000
WAKE | GORALEIGH | GORALEIGH | RALEIGH UNION STATION BUS FACILITY INTER-CITY/COMMUTER RAIL PARK AND RIDE |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0020 | Public Transit | CMAQ, L |  |  |  |  | 2022 | 5625000 |  |  | 5625000
WAKE | GOTRIANGLE | GOTRIANGLE | ADD A WAITING PAD AND LANDING PAD AT 5 STOPS ON THE 305. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0046 | Division 5 | BGDA, L | 2024 | 15000 |  |  | 2024 | 250000 | 2024 | 60000 | 325000
WAKE | GOTRIANGLE | GOTRIANGLE | ADD A LANDING PAD AT 24 STOPS BETWEEN EXISTING SIDEWALK AND BACK OF CURB. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. ROUTE 305. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0053 | Division 5 | BGDA, L |  |  |  |  | 2024 | 240000 | 2024 | 100000 | 340000
WAKE | GOTRIANGLE | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0057 | Division 5 | L(M), TADA | 2025 | 18000 |  |  | 2025 | 438000 | 2025 | 72000 | 528000
WAKE | GOTRIANGLE | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0058 | Division 5 | L(M), TADA | 2025 | 27000 |  |  | 2025 | 405000 | 2025 | 108000 | 540000
WAKE | GOCARY | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TL-0059 | Division 5 | BGDA, L, L(M) |  |  |  |  | 2024 | 339000 | 2025 | 949000 | 1288000
WAKE | GOAPEX | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 |  | Public Transportation (Transit) | Locally Selected | 5 | Capital Area MPO | TM-0026 | Division 5 | BGDA, L | [6 empty] | 2021 | 610000 | 610000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-0002 | Public Transit | 5307, L | [6 empty] | 2021 | 1368000 | 1368000
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-5128 | Public Transit | 5307, L, SMAP | [6 empty] | 2021 | 152980000 | 152980000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-5129 | Public Transit | 5307, L, SMAP | [6 empty] | 2021 | 19401000 | 19401000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GOTRIANGLE | GOTRIANGLE | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-5131 | Public Transit | L, SMAP | [6 empty] | 2021 | 37855000 | 37855000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | TOWN OF WAKE FOREST REVERSE CIRCULATOR OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 5 | Capital Area MPO | TO-6168 | Public Transit | L | [6 empty] | 2021 | 2283000 | 2283000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH ADA PARATRANSIT SERVICE. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TG-4729B | Public Transit | 5307, L | [6 empty] | 2021 | 5000000 | 5000000
WAKE | GORALEIGH | GORALEIGH | ADA PARATRANSIT SERVICE |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TG-4792B | Public Transit | 5307, L | [6 empty] | 2021 | 10000000 | 10000000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TG-4935A | Public Transit | 5307, 5309, 5339, L | [6 empty] | 2023 | 17955000 | 17955000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | WAKE COORDINATED TRANSPORTATION SERVICE | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TK-6170 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1580000 | 1580000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GOTRIANGLE | GOTRIANGLE | OPERATING ASSISTANCE FOR TOWN OF MORRISVILLE NODE BASED SMART SHUTTLE. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TM-0035 | Public Transit | L | [6 empty] | 2021 | 3621000 | 3621000
WAKE | WAKE COORDINATED TRANSIT SERVICE | WAKE COORDINATED TRANSIT SERVICE | WAKE COORDINATED TRANSIT SERVICES OPERATING ASSISTANCE. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TN-6116 | Public Transit | L | [6 empty] | 2021 | 4070000 | 4070000
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | 5310 OPERATING |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TQ-6953 | Public Transit | 5310, L | [6 empty] | 2021 | 1200000 | 1200000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | 5310 ADMIN. |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TQ-7006 | Public Transit | 5310 | [6 empty] | 2020 | 65000 | 65000
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | 5310 ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 5 | Capital Area MPO | TQ9037 | Public Transit | 5310 | [6 empty] | 2020 | 65000 | 65000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN ON BUS RAPID TRANSIT IN WAKE TRANSIT PLAN NORTHERN CORRIDOR. |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TL-0007 | Public Transit | L | [6 empty] | 2020 | 5540000 | 5540000
WAKE | GOTRIANGLE | GOTRIANGLE | EARLY PROJECT DEVELOPMENT ACTIVITIES FOR COMMUTER RAIL FROM GARNER TO WESTERN DURHAM |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TL-0008 | Public Transit | L | [6 empty] | 2021 | 9200000 | 9200000
WAKE | GOTRIANGLE | GOTRIANGLE | PLANNING ASSISTANCE |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TP-4732B | Public Transit | 5307, L, S | [6 empty] | 2020 | 2952000 | 2952000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TP-5100A | Public Transit | 5303, L, S | [6 empty] | 2020 | 1872000 | 1872000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH | PLANNING ASSISTANCE - 5307 |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TP-5100B | Public Transit | 5307, L, S | [6 empty] | 2021 | 3826000 | 3826000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GOTRIANGLE | GOTRIANGLE | GOTRIANGLE WAKE COUNTY BUS PLAN UPDATE. |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TU-0006 | Public Transit | CMAQ, L | [6 empty] | 2021 | 740000 | 740000
WAKE | GORALEIGH | GORALEIGH | MAJOR INVESTMENT STUDY/ALTERNATIVES ANALYSIS FOR BUS RAPID TRANSIT EXTENSION TO RESEARCH TRIANGLE PARK AND CLAYTON. |  | Public Transportation (Transit) | Planning | 5 | Capital Area MPO | TU-0007 | Public Transit | L | [6 empty] | 2021 | 430000 | 430000
WAKE | GORALEIGH | GORALEIGH | FIXED ROUTE PREVENTATIVE MAINTENANCE |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Capital Area MPO | TG-0013 | Public Transit | 5307, L | [6 empty] | 2021 | 9600000 | 9600000
WAKE | GORALEIGH | GORALEIGH | GORALEIGH CAPITAL PROJECTS. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Capital Area MPO | TG-0015 | Public Transit | 5307 | [6 empty] | 2021 | 4401000 | 4401000
WAKE | GOTRIANGLE | GOTRIANGLE | CONSTRUCT 11 BUS STOPS. |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Capital Area MPO | TG-0027 | Public Transit | CPF, L | [6 empty] | 2025 | 1136000 | 1136000
WAKE | GORALEIGH | GORALEIGH | CAPITAL COST OF CONTRACTING |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5 | Capital Area MPO | TG-6791 | Public Transit | 5307, L | [6 empty] | 2021 | 5000000 | 5000000
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | US 64 BUSINESS (NEW HOPE ROAD) IN RALEIGH. CONSTRUCT TRANSFER FACILITY. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-4912 | Division 5 | [10 empty] | UNDER CONSTRUCTION BY GO RALEIGH
WAKE | GOCARY | CARY TRANSIT / C-TRAN | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-5264B | Division 5 | 5307, 5339(b), DP, L, T |  |  |  |  | 2023 | 76442000 | 2022 | 2500000 | 78942000 | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023
WAKE | GO TRIANGLE | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-5269 | Division 5 | 5339(b), DP, L, O, T |  |  |  |  | 2020 | 54185000 | 2024 | 130000 | 54315000 | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH
WAKE | GO RALEIGH TRANSIT | GO RALEIGH TRANSIT | SOUTH WILMINGTON STREET AT PECAN ROAD IN RALEIGH. CONSTRUCT OFF-STREET TRANSFER FACILITY. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-5272 | Division 5 | [10 empty] | UNDER CONSTRUCTION BY GO RALEIGH
WAKE | VARIOUS | GO RALEIGH | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. |  | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TD-5307 | Division 5 | L, O, T | 2027 | 1500000 |  |  | 2028 | 6658000 |  |  | 8158000
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 3.86 | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TO-6166A | Region C | L, T | 2030 | 94345000 | 2030 | 3988000 | 2033 | 75425000 | 2031 | 1500000 | 175258000
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, CARY TO RALEIGH. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 9.19 | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TO-6166B | Region C | 5309, L | [6 empty] | 2024 | 8134000 | 8134000
WAKE | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, RALEIGH TO GARNER. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 5.93 | Public Transportation (Transit) | STI (Prioritization) | 5 | Capital Area MPO | TO-6166C | Region C | 5309, L | [6 empty] | 2024 | 8134000 | 8134000
WAKE | PIEDMONT CORRIDOR | NCDOT | CAPITAL YARD PHASE 1 IMPROVEMENTS - EXTEND TRACKS 1 AND 2, MAJOR WORK TRACK 3 |  | Rail | Other | 5 | Capital Area MPO | P-2918H | [11 empty] | IN PROGRESS
WAKE | CSX S-LINE, CSX SA-LINE. | NCDOT | RALEIGH TO NC 98. |  | Rail | Other | 5 | Capital Area MPO | P-5753A | Statewide Mobility
WAKE | CSX S-LINE | NCDOT | RALEIGH UNION STATION TO NC 98 - S-LINE RAIL IMPROVEMENTS. | 28.66 | Rail | Other | 5 | Capital Area MPO | P-5753AA | Statewide Mobility
WAKE | CSX S-LINE | NCDOT | HARGETT STREET, MORGAN STREET AND CAPITAL BOULEVARD ROADWAY IMPROVEMENTS AND PEDESTRIAN OVERPASS AT JONES STREET. |  | Rail | Other | 5 | Capital Area MPO | P-5753AE | Statewide Mobility
WAKE | CSX S-LINE | NCDOT | WHITAKER MILL ROAD ROADWAY IMPROVEMENTS. |  | Rail | Other | 5 | Capital Area MPO | P-5753AF | Statewide Mobility
WAKE | CSX S-LINE | NCDOT | HIGHWOODS BOULEVARD GRADE SEPERATION. |  | Rail | Other | 5 | Capital Area MPO | P-5753AG | Statewide Mobility
WAKE | CSX S-LINE | NCDOT | GRESHAM LAKE AND LIGON MILL GRADE SEPARATIONS AND ROADWAY IMPROVEMENTS AT SEAWELL AND FRIENDSHIP CHAPEL ROAD. |  | Rail | Other | 5 | Capital Area MPO | P-5753AH | Statewide Mobility
WAKE | NCRR | NCDOT | RALEIGH UNION STATION PROJECT - PHASE I. CONSTRUCT RALEIGH TRAIN STATION AND ASSOCIATED RAIL TRACK AND SIDING IMPROVEMENTS TO INCREASE PASSENGER AND FREIGHT CAPACITY. |  | Rail | Pre-STI (Historic) | 5 | Capital Area MPO | P-5500 | Pre-STI (Transition) | [10 empty] | DP FUNDS - FEDERAL TIGER GRANT; O FUNDS - STATE LEGISLATIVE ALLOCATION FOR RAIL; PROJECT INCLUDES IN-KIND PROPERTY CONTRIBUTION BY TRIANGLE TRANSIT (CONTINGENT ON TT BOARD OF TRUSTEES APPROVAL) - 4 PARCELS TOTALING 3.5 ACRES WITH TAX VALUE OF $2.9 MILLION
WAKE | NCRR | NCDOT | STATION SITE WORK |  | Rail | Pre-STI (Historic) | 5 | Capital Area MPO | P-5500B | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
WAKE | NCRR | NCDOT | TRACK IMPROVEMENTS |  | Rail | Pre-STI (Historic) | 5 | Capital Area MPO | P-5500C | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
WAKE | FAYETTEVILLE STREET (SR 2513) | NCDOT | FAYETTEVILLE STREET AND THE CAROLINA COASTAL RAILWAY TRACKS CROSSING CLOSURE IN KNIGHTDALE. |  | Rail | Rail-Highway Grade Crossing Closure | 5 | Capital Area MPO | Y-4805F | Division 5 | RR |  |  |  |  | 2023 | 1600000 |  |  | 1600000
WAKE | CSX S LINE | NCDOT | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5707 | Region C | T | 2025 | 7000000 |  |  | 2025 | 42500000 |  |  | 49500000 | RIGHT-OF-WAY IN PROGRESS
WAKE | CSX | NCDOT | CROSSING 630607N AT NEW HOPE CHURCH ROAD IN RALEIGH. CONSTRUCT GRADE SEPARATION. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5715 | Region C | T |  |  |  |  | 2025 | 23700000 |  |  | 23700000 | RIGHT-OF-WAY IN PROGRESS
WAKE | CSX | NCDOT | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5718 | Region C | O, T | 2028 | 37300000 | 2028 | 4500000 | 2031 | 42000000 |  |  | 83800000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734.
WAKE | CSX | NCDOT | CROSSING 630601X AT SR 2006 (DURANT ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5720 | Region C | T |  |  |  |  | 2024 | 21914000 |  |  | 21914000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | NCDOT | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5734 | Statewide Mobility | O, T | 2028 | 23400000 | 2028 | 960000 | 2031 | 29600000 |  |  | 53960000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718.
WAKE | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | NCDOT | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5736 | Statewide Mobility | O, T | 2030 | 200000 |  |  | 2031 | 4900000 |  |  | 5100000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
WAKE | CSX S LINE | NCDOT | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. |  | Rail | STI (Prioritization) | 5 | Capital Area MPO | P-5737 | Statewide Mobility | DP, T | 2022 | 6111000 | 2022 | 1228000 | 2026 | 25100000 |  |  | 32439000 | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT.
WAKE | NCRR | NCDOT | CSXT S-LINE, TRACK AND SIGNAL IMPROVEMENTS - BOYLAN WYE CROSSOVER |  | Rail | Transition | 5 | Capital Area MPO | P-5500A | [11 empty] | DELETED - WORK TO BE ACCOMPLISHED UNDER P-5005D.
WAKE, DURHAM | I-40 | NCDOT | EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | 9.37 | Highway | Interstate Maintenance | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | I-5995 | Statewide Mobility | NHFP, NHPIM |  |  |  |  | 2026 | 54600000 |  |  | 54600000 | Combined with I-5996.
WAKE, DURHAM | I-540 | NCDOT | I-40 IN DURHAM TO US 70 IN RALEIGH. PAVEMENT REHABILITATION. | 4.25 | Highway | Interstate Maintenance | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | I-5998 | Statewide Mobility | NHPIM |  |  |  |  | 2026 | 24500000 |  |  | 24500000 | COORDINATE WITH I-5999 AND I-6000
WAKE, DURHAM | I-540 | NCDOT | I-40 IN DURHAM TO US 1 IN RALEIGH. BRIDGE PRESERVATION / REHABILITATION. | 16.34 | Highway | Interstate Maintenance | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | I-6000 | Statewide Mobility | NHPIM |  |  |  |  | 2029 | 7610000 |  |  | 7610000 | COORDINATE WITH I-5998 AND I-5999
WAKE, DURHAM | VARIOUS | NCDOT | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS - DIVISION NEEDS CATEGORY |  | Highway | Safety | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | W-5205DIV | Division 5
WAKE, DURHAM | US 70 (GLENWOOD AVENUE) | NCDOT | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | 1.26 | Highway | STI (Prioritization) | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | U-5518 | Statewide Mobility | NHP | 2030 | 153208000 | 2030 | 15714000 | 2030 | 230000000 |  |  | 398922000 | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT
WAKE, DURHAM | GOTRIANGLE | GOTRIANGLE | PURCHASE EXPANSION VEHICLES FOR DRX ROUTE. |  | Public Transportation (Transit) | Capital (Non-STI) | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | TA-6668 | Region C | [10 empty] | IN ACQUISITION
WAKE, DURHAM, ORANGE | CENTRAL PINES REGIONAL COUNCIL |  | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS. |  | Highway | NCDOT Selected (Other Selection Process) | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | HN-0026 | Exempt
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | TRIANGLE J COUNCIL OF GOVERNMENTS (COG) | TRIANGLE J COUNCIL OF GOVERNMENTS (COG). TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN TRIANGLE OZONE NON-ATTAINMENT AREA. |  | Highway | Other | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | C-4924 | Exempt
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | NCDOT | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | Highway | Other | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | C-4924A | Exempt | [10 empty] | IN PROGRESS
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | NCDOT | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | Highway | Other | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | C-4924B | Exempt | CMAQ, L(M) | [6 empty] | 2022 | 3025000 | 3025000 | IN PROGRESS
WAKE, DURHAM, ORANGE | GOTRIANGLE | GOTRIANGLE | FIXED GUIDEWAY - LIGHT RAIL SERVICE- CARY/RALEIGH |  | Public Transportation (Transit) | Capital (Non-STI) | 5, 7 | Capital Area MPO | TE-4903A | Public Transit | FED |  |  |  |  | 2020 | 1500000000 |  |  | 1500000000
WAKE, DURHAM, ORANGE | GOTRIANGLE | GOTRIANGLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | TG-4821B | Public Transit | 5307, 5339, L | [6 empty] | 2024 | 8441000 | 8441000 | FUNDS AUTHORIZED IN PROGRESS
WAKE, FRANKLIN | I-87 / FUTURE I-87 / US 64 / US 264 | NCDOT | SR 1003 (ROLESVILLE ROAD) TO NASH COUNTY LINE. PAVEMENT REHABILITATION. | 13.38 | Highway | Interstate Maintenance | 5 | Capital Area MPO, Kerr-Tar RPO | I-6001 | Statewide Mobility | NHPIM |  |  |  |  | 2025 | 40400000 |  |  | 40400000
WAKE, FRANKLIN | CSX S-LINE | NCDOT | NC 98 TO FRANKLINTON - S-LINE RAIL IMPROVEMENTS. | 16.88 | Rail | Other | 5 | Capital Area MPO | P-5753BA | Statewide Mobility
WAKE, FRANKLIN, GRANVILLE | VARIOUS | NCDOT | US 401 IN FRANKLIN COUNTY. NC 42 IN WAKE COUNTY. NC 56 IN FRANKLIN AND GRANVILLE COUNTY. NC 96 IN WAKE AND GRANVILLE COUNTY. SR 1006 IN WAKE COUNTY AND NC 50 IN WAKE AND GRANVILLE COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | Highway | Safety | 5 | Capital Area MPO, Kerr-Tar RPO | HS-2405C | Region C | HSIP |  |  |  |  | 2025 | 1315000 |  |  | 1315000
WAKE, FRANKLIN, VANCE | CSX S-LINE | NCDOT | NC 98 TO FRANKLINTON. |  | Rail | Other | 5 | Capital Area MPO, Kerr-Tar RPO | P-5753B | Statewide Mobility
WAKE, FRANKLIN, WARREN | VARIOUS | NCDOT | INSTALL LONG-LIFE PAVEMENT MARKINGS |  | Highway | Safety | 5 | Capital Area MPO, Kerr-Tar RPO | W-5805F | Division 5 | HSIP |  |  |  |  | 2021 | 2553000 |  |  | 2553000 | COMPLETE
WAKE, HARNETT | NC 55 | NCDOT | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | 4.99 | Highway | STI (Prioritization) | 5, 6 | Capital Area MPO | R-5705B | Region C | T | 2021 | 35171000 | 2021 | 1300000 | 2023 | 70722000 |  |  | 107193000 | UNDER CONSTRUCTION.
WAKE, IREDELL, MECKLENBURG, ROWAN, CLEVELAND, UNION, CABARRUS, GASTON, JOHNSTON, DURHAM, LINCOLN, FRANKLIN, ORANGE, CHATHAM, GRANVILLE, HARNETT | STATEWIDE TRAFFIC OPERATIONS | NCDOT | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT IN THE TRIANGLE AND METROLINA AREAS. |  | Highway | Other | 4, 5, 6, 7, 8, 9, 10, 12 | Capital Area MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO, Cabarrus-Rowan MPO, Durham-Chapel Hill-Carrboro MPO | HO-0010A | Statewide Mobility | CRPANY, HF(M) | [6 empty] | 2023 | 4000000 | 4000000
WAKE, JOHNSTON | I-40 | NCDOT | I-440 / US 64 (EXIT 301) TO NC 42 (EXIT 312). ADD 2 GENERAL-PURPOSE LANES IN EACH DIRECTION. | 10.71 | Highway | STI (Prioritization) | 4, 5 | Capital Area MPO | I-5111 | [11 empty] | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK 2019-2033.
WAKE, JOHNSTON | NEW ROUTE (FUTURE NC 540) | NCDOT | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), EAST OF US 401 TO I-40. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 8.64 | Highway | STI (Prioritization) | 4, 5 | Capital Area MPO | R-2828 | Statewide Mobility | NHP |  |  |  |  | 2019 | 135750000 |  |  | 135750000 | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT.
WAKE, JOHNSTON | VARIOUS | GO RALEIGH | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | 33.93 | Public Transportation (Transit) | STI (Prioritization) | 4, 5 | Capital Area MPO | TO-6166
WAKE, JOHNSTON, FRANKLIN, GRANVILLE | VARIOUS | NCDOT | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | Highway | Other | 4, 5 | Capital Area MPO | C-5604 | Exempt | BGDA, CMAQ, L | 2020 | 1188000 |  |  | 2020 | 23622000 | 2020 | 4081000 | 28891000 | IN PROGRESS
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. |  | Bike & Ped | Locally Selected | 4, 5, 6 | Capital Area MPO | U-5530 | Division 4, 5, 6 | BGDA, L, TADA |  |  |  |  | 2020 | 3500000 |  |  | 3500000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | Bike & Ped | Locally Selected | 4, 5, 6 | Capital Area MPO | U-6218 | Division 4, 5, 6 | TADA |  |  |  |  | 2024 | 26579000 |  |  | 26579000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | PEDESTRIAN, BICYCLE, AND TRANSIT PROJECTS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO). |  | Bike & Ped | Other | 4, 5, 6 | Capital Area MPO | EL-5100 | Division 4, 5, 6
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | INTERSECTION IMPROVEMENTS AT MULTIPLE LOCATIONS WITHIN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) BOUNDARY. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | HL-0008 | Exempt | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | HL-0105 | Exempt | CRPDA, L |  |  |  |  | 2024 | 6008000 |  |  | 6008000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | U-4735 | Division 4, 5, 6 | BGANY, BGDA |  |  |  |  | 2024 | 162642000 |  |  | 162642000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | U-4850 | Division 4, 5, 6 | BGDA, L | [6 empty] | 2022 | 20336000 | 20336000 | FORMERLY U-9999B - IN PROGRESS
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | NCDOT | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. |  | Highway | Locally Selected | 4, 5, 6 | Capital Area MPO | U-5118 | Division 4, 5, 6 | BGDA, L |  |  |  |  | 2020 | 4477000 |  |  | 4477000 | UNDER CONSTRUCTION. PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS. $24,867 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP.
WAKE, LEE, VANCE | CSX S-LINE | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. |  | Public Transportation (Transit) | Planning | 5, 8 | Capital Area MPO, Kerr-Tar RPO, Central Pines RPO | TU-0004 | Public Transit | FED, L, S | [6 empty] | 2021 | 1505000 | 1505000 | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS
WAKE, ORANGE | GOTRIANGLE | GOTRIANGLE | PURCHASE EXPANSION VEHICLES FOR CRX ROUTE. |  | Public Transportation (Transit) | Capital (Non-STI) | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | TA-6669 | Region C, D | [10 empty] | IN ACQUISITION
WARREN | NC 903 | NCDOT | NC 903 CAUSEWAY ON EATONS FERRY BRIDGE OVER LAKE GASTON. UPGRADE GUARDRAIL. | 0.85 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2005B | Region C | HSIP |  |  |  |  | 2021 | 130000 |  |  | 130000 | UNDER CONSTRUCTION
WARREN | US 1 / US 158 | NCDOT | US 1 / US 158 AT SR 1237 (MASON DREWRY ROAD). INTERSECTION REALIGNMENT. | 0.5 | Highway | Safety | 5 | Kerr-Tar RPO | HS-2005O | Region C | HSIP | 2025 | 31000 | 2025 | 80000 | 2025 | 335000 |  |  | 446000
WARREN | I-85 | NCDOT | NORTH OF SR 1237 (MANSON DREWRY ROAD) TO VIRGINIA STATE LINE | 7.72 | Highway | Transition | 5 | Kerr-Tar RPO | I-0914BB | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
WARREN | CSX S-LINE | NCDOT | MANSON AXTELL ROAD GRADE SEPARATION. |  | Rail | Other | 5 |  | P-5753CJ | Statewide Mobility
WARREN | CSX S-LINE | NCDOT | RIDGEWAY TO PASCHALL |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753D | Statewide Mobility
WARREN | CSX S-LINE | NCDOT | RIDGEWAY TO THE VA STATE LINE - S-LINE RAIL IMPROVEMENTS. | 13.51 | Rail | Other | 5 | Kerr-Tar RPO | P-5753DA | Statewide Mobility
WARREN | CSX S-LINE | NCDOT | SOUL CITY BOULEVARD ROADWAY IMPROVEMENTS INCLUDING DREWRY GRADE SEPARATION. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753DC | Statewide Mobility
WARREN | CSX S-LINE | NCDOT | NORLINA ROADWAY IMPROVEMENTS. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753DD | Statewide Mobility
WARREN | CSX S-LINE | NCDOT | WISE ROADWAY IMPROVEMENTS INCLUDING FELTS ROAD. |  | Rail | Other | 5 | Kerr-Tar RPO | P-5753DE | Statewide Mobility
WARREN, VANCE | I-85 | NCDOT | US 158 (MILE POST 213.5) IN VANCE COUNTY TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION AND SIGN UPGRADES. | 19 | Highway | Pre-STI (Historic) | 5 | Kerr-Tar RPO | I-0914 | Pre-STI (Transition)
WARREN, VANCE | I-85 | NCDOT | ITS DEPLOYMENT FOR PARTS BA AND BB |  | Highway | Pre-STI (Historic) | 5 | Kerr-Tar RPO | I-0914BC | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
WASHINGTON | NC 32 | NCDOT | PRESERVATION OF BRIDGE 930015 ON NC 32 OVER ALBEMARLE SOUND. | 3.5 | Highway | Bridges | 1 | Albemarle RPO | HB-0016 | Region A | BFP |  |  |  |  | 2027 | 50001000 |  |  | 50001000
WASHINGTON | SR 1126 (ROPER NEWLAND ROAD) | NCDOT | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | 4.19 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5936 | Division 1 | T | 2028 | 820000 | 2028 | 120000 | 2030 | 38000000 |  |  | 38940000
WASHINGTON | SR 1106 (MORATTOCK ROAD) | NCDOT | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | 2.12 | Highway | STI (Prioritization) | 1 | Albemarle RPO | R-5937 | Division 1 | T | 2028 | 1400000 | 2028 | 340000 | 2032 | 21600000 |  |  | 23340000
WASHINGTON | WASHINGTON COUNTY | WASHINGTON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 1 | Albemarle RPO | TK-6171 | Public Transit | 5311, L, S | [6 empty] | 2020 | 356000 | 356000 | FUNDS AUTHORIZED IN PROGRESS
WASHINGTON, MARTIN, PASQUOTANK, CHOWAN, TYRRELL, BERTIE, HERTFORD | US 64; US 17 BYPASS; US 17; NC 11; US 13 | NCDOT | INSTALL WRONG WAY PAVEMENT MARKINGS, MARKERS, AND SIGNS AT RAMPS. |  | Highway | Safety | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | HS-2401C | Region A | HSIP |  |  |  |  | 2025 | 170000 |  |  | 170000
WATAUGA | US 221 | BLOWING ROCK | MAIN STREET IN BLOWING ROCK TO MOSES H CONE MEMORIAL PARK AND BASS LAKE. CONSTRUCT SIDEWALK. | 0.6 | Bike & Ped | Locally Selected | 11 | High Country RPO | EB-5798 | Exempt | [10 empty] | UNDER CONSTRUCTION. PROJECT TO BE ADMINISTERED BY THE TOWN OF BLOWING ROCK
WATAUGA | TOWN OF BLOWING ROCK | BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). |  | Bike & Ped | Locally Selected | 11 | High Country RPO | EB-5924 | Exempt | FLAP, HF(M), L | 2023 | 90000 |  |  | 2024 | 2014000 |  |  | 2104000 | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF HF(M) IS CONTINGENCY FUNDS ON WBS 44607
WATAUGA | US 421/ US 321 (WEST KING STREET) |  | SR 1180 (POPLAR GROVE CONNECTOR ROAD) TO WESTWOOD APARTMENTS IN BOONE. CONSTRUCT SIDEWALK AND OTHER CORRIDOR IMPROVEMENTS. | 0.42 | Bike & Ped | NCDOT Selected (Other Selection Process) | 11 | High Country RPO | BN-0010 | Exempt | CRP550, L(M) | 2025 | 50000 |  |  | 2025 | 656000 | 2024 | 150000 | 856000
WATAUGA | US 421 (KING STREET) MULTI-USE PATH | BOONE | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 1.14 | Bike & Ped | STI (Prioritization) | 11 | High Country RPO | EB-5983 | Division 11 | L, TAANY | 2026 | 20000 |  |  | 2027 | 1865000 |  |  | 1885000
WATAUGA | (ALDRIDGE ROAD) SR 1594 | NCDOT | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0062 | Exempt | BGOFF, DP, HFB | 2025 | 500000 | 2025 | 60000 | 2026 | 2000000 | 2023 | 139000 | 2699000 | DP REPRESENTS RAISE GRANT FUNDS.
WATAUGA | HUNTING HILLS LANE | BOONE | REPLACE BRIDGE NO. 940346 OVER SOUTH FORK OF NEW RIVER IN BOONE. | 0.25 | Highway | Municipal Bridge | 11 | High Country RPO | B-5979 | Division 11 | BGOFF, L |  |  |  |  | 2025 | 4300000 |  |  | 4300000 | RIGHT-OF-WAY IN PROGRESS.
WATAUGA | US 221 / US 321 | NCDOT | DEERFIELD ROAD TO BOONE MALL. INSTALL PEDESTRIAN COUNTDOWN HEADS AND FLASHING YELLOW ARROWS AT VARIOUS INTERSECTIONS. | 0.99 | Highway | Safety | 11 | High Country RPO | HS-2011B | Statewide Mobility | HSIP |  |  |  |  | 2021 | 116000 |  |  | 116000 | UNDER CONSTRUCTION.
WATAUGA | NC 105 | NCDOT | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 5.49 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566B | Region F | NHP, T | 2022 | 13270000 | 2022 | 13700000 | 2030 | 117000000 |  |  | 143970000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
WATAUGA | NC 105 | NCDOT | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). |  | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566BA | Division 11 | T |  |  | 2019 | 2850000 | 2022 | 23680000 |  |  | 26530000 | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
WATAUGA | NC 105 | NCDOT | SR 1658 (OLD SHULLS MILL ROAD) INTERSECTION. REALIGN SR 1658 (OLD SHULLS MILL ROAD). | 0.5 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566BB | Region F | T |  |  |  |  | 2025 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION.
WATAUGA | US 421/US 321 | NCDOT | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | 3.55 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2615 | Region F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40901000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 78300000 |  |  | 122101000
WATAUGA | SR 1522 (DEERFIELD ROAD) | NCDOT | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 0.87 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5830 | Division 11 | T | 2025 | 3900000 | 2025 | 560000 | 2028 | 27660000 |  |  | 32120000 | BUILD NC BOND FUNDING: $8,500,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NCDOT | US 421/321 WEST OF BOONE TO US 421 EAST OF BOONE. CONSTRUCT FREEWAY ON NEW LOCATION SOUTH OF BOONE. | 10.42 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5915 | Division 11
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NCDOT | US 321/421 WEST OF BOONE TO NC 105 | 2.25 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5915A | Not Funded | NHP | NOT FUNDED | 81700000 | NOT FUNDED | 400000 | NOT FUNDED | 165600000 | NOT FUNDED |  | 247700000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NCDOT | NC 105 TO US 221/321 SOUTH OF BOONE | 3.62 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5915B | Division 11 | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 84801000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 346200000 |  |  | 431601000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NCDOT | US 221/321 TO US 221/421 EAST OF BOONE | 4.55 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5915C | Not Funded | NHP | NOT FUNDED | 133800000 | NOT FUNDED | 400000 | NOT FUNDED | 384600000 | NOT FUNDED |  | 518800000
WATAUGA | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | NCDOT | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | 1.88 | Highway | STI (Prioritization) | 11 | High Country RPO | U-5810 | Division 11 | BG5T50, T | 2022 | 19400000 | 2022 | 1500000 | 2025 | 42400000 |  |  | 63300000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
WATAUGA | APPALCART | APPALCART | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 11 | High Country RPO | TO-6101 | Public Transit | 5311, L | [6 empty] | 2020 | 9544000 | 9544000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA | APPALCART | APPALCART | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 11 | High Country RPO | TO-6104 | Public Transit | SMAP | [6 empty] | 2020 | 2632000 | 2632000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA | APPALCART | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | 11 | High Country RPO | TN-6129 | Exempt | CRPANY, T(M) | [6 empty] | 2025 | 5003000 | 5003000
WATAUGA | APPALCART | APPALCART | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 11 | High Country RPO | TK-6107 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1872000 | 1872000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA, AVERY | NC 105 | NCDOT | US 221 TO SR 1107 (NC 105 BYPASS) IN BOONE. WIDEN TO MULTI-LANES. | 14.8 | Highway | STI (Prioritization) | 11 | High Country RPO | R-2566
WAYNE | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | EXTEND RUNWAY TO 5500 FEET. |  | Aviation | STI (Prioritization) | 4 | Eastern Carolina RPO | AV-5811 | Division 4 | T |  |  |  |  | 2029 | 1200000 |  |  | 1200000
WAYNE | STONEY CREEK GREENWAY | GOLDSBORO | US 70 BYPASS TO SR 1560 (ROYALL AVENUE). CONSTRUCT 10 FOOT WIDE ASPHALT GREENWAY. | 0.39 | Bike & Ped | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | EB-5707 | Division 4 | L, SRTS |  |  |  |  | 2022 | 391000 |  |  | 391000 | UNDER CONSTRUCTION.
WAYNE | GOLDSBORO | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 0.33 | Bike & Ped | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | EB-5850 | Division 4 | L, TA50200 |  |  | 2026 | 200000 | 2026 | 1200000 | 2025 | 19000 | 1419000
WAYNE | SR 1958 (BENNETTS BRIDGE ROAD) | NCDOT | REPLACE BRIDGE 950117 OVER NE CAPE FEAR RIVER. | 0.25 | Highway | Bridges | 4 | Eastern Carolina RPO | B-4844 | Highway Fund | HFB |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS.
WAYNE | I-795 | NCDOT | WILSON COUNTY LINE TO SR 2075 (ASH STREET). UPGRADE GUARDRAIL, SHOULDER AND MEDIAN REPAIRS. | 13.55 | Highway | Interstate Maintenance | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | I-6047 | Statewide Mobility | NHPIM, T(M) |  |  |  |  | 2020 | 6893000 |  |  | 6893000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034.
WAYNE | US 117 (FUTURE I-795) | NCDOT | US 70 TO DUPLIN COUNTY LINE. PAVEMENT AND BRIDGE REHABILITATION. | 16.69 | Highway | Interstate Maintenance | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | I-6048 | Statewide Mobility | NHPIM |  |  |  |  | 2021 | 7942000 |  |  | 7942000 | UNDER CONSTRUCTION.
WAYNE | VARIOUS | NCDOT | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GOLDSBORO PLANNING ORGANIZATION. |  | Highway | Locally Selected | 4 | Goldsboro Urban Area MPO | HL-0097 | Exempt | CRPDA, L |  |  |  |  | 2023 | 1892000 |  |  | 1892000
WAYNE | NC 55 | DIVISION | SR 1744 (OLD SEVEN SPRINGS ROAD / INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. |  | Highway | Locally Selected | 4 | Upper Coastal Plain RPO | HN-0033 | Exempt | CRPANY, T(M) | 2026 | 662000 |  |  | 2026 | 6318000 | 2024 | 1100000 | 8080000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | FROM US 70 BYPASS TO THE GREENE COUNTY LINE. INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS. | 7.3 | Highway | Safety | 4 | Goldsboro Urban Area MPO | HS-2004AC | Division 4 | HSIP |  |  |  |  | 2024 | 210000 |  |  | 210000
WAYNE | SR 1537 (AIRPORT ROAD) | NCDOT | INSTALL ALL WAY STOP AT SR 1537 (AIRPORT ROAD) AND SR 1545 (MT. CARMEL CHURCH ROAD). | 0.5 | Highway | Safety | 4 | Goldsboro Urban Area MPO | HS-2004C | Division 4 | HSIP |  |  |  |  | 2022 | 66000 |  |  | 66000 | UNDER CONSTRUCTION.
WAYNE | SR 1002 (PIKEVILLE-PRINCETON ROAD) | NCDOT | INSTALL ALL WAY STOP WITH ISLAND AT SR 1002 (PIKEVILLE-PRINCETON ROAD) AND SR 1320 (HINNANT ROAD). | 0.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2004D | Division 4 | HSIP |  |  |  |  | 2022 | 65000 |  |  | 65000 | UNDER CONSTRUCTION.
WAYNE | NC 111 | NCDOT | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT NC 111 AND SR 1754 (ZION CHURCH ROAD). | 0.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2004E | Region A | HSIP |  |  |  |  | 2022 | 152000 |  |  | 152000 | UNDER CONSTRUCTION.
WAYNE | SR 1744 (INDIAN SPRINGS ROAD) | NCDOT | INSTALL ALL WAY STOP AT SR 1744 (INDIAN SPRINGS ROAD) AND SR 1941 (NORTHEAST CHURCH ROAD). | 0.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2004I | Division 4 | HSIP |  |  |  |  | 2022 | 65000 |  |  | 65000 | UNDER CONSTRUCTION.
WAYNE | NC 55 | NCDOT | SR 1006 (GRANTHAM SCHOOL ROAD) INTERSECTION. REALIGN INTERSECTION. | 0.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2404A | Region A | HSIP | 2025 | 75000 | 2025 | 96000 | 2026 | 524000 |  |  | 695000
WAYNE | NC 55 | NCDOT | 0.27 MILES WEST OF LENOIR COUNTY LINE TO MOUNT OLIVE CITY LIMITS AND SR 1135 (COUNTRY CLUB ROAD) TO SAMPSON COUNTY LINE. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 23.5 | Highway | Safety | 4 | Eastern Carolina RPO | HS-2404C | Region A | HSIP |  |  |  |  | 2025 | 806000 |  |  | 806000
WAYNE | US 70 BUSINESS / US 117 BUSINESS (ASH STREET) | NCDOT | SR 1925 (JOHN STREET) AND US 117 BUSINESS (WILLIAM STREET) INTERSECTIONS IN GOLDSBORO. INSTALL / REVISE PEDESTRIAN ACCOMODATIONS INCLUDING TRAFFIC SIGNALS, PEDESTRIAN SIGNALS, AND CROSSWALK IMPROVEMENTS. |  | Highway | Safety | 4 | Goldsboro Urban Area MPO | HS-2404D | Region A | HSIP |  |  |  |  | 2025 | 100000 |  |  | 100000
WAYNE | SR 1927 (GENOA ROAD) | NCDOT | SR 1927 (GENOA ROAD) AT CRESCENT DRIVE. INTERSECTION IMPROVEMENTS. | 0.5 | Highway | Safety | 4 | Goldsboro Urban Area MPO | W-5704K | Division 4 | HSIP | 2024 | 40000 |  |  | 2024 | 857000 |  |  | 897000 | UNDER CONSTRUCTION.
WAYNE | US 13 | NCDOT | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | 3.64 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | R-5853 | Division 4 | BGANY | 2025 | 3500000 | 2025 | 1900000 | 2027 | 8799000 |  |  | 14199000
WAYNE | US 117 BUS/US 117 (N. WILLIAMS STREET) | NCDOT | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN TO FOUR LANES AND MAKE SAFETY IMPROVEMENTS. | 0.96 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-2714 | Region A | L, T | 2020 | 3510000 |  |  | 2020 | 25087000 | 2020 | 4290000 | 32887000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,419 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
WAYNE | US 117 (FUTURE I-795) | NCDOT | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | 3.61 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO | U-3125C | Region A | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 90000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35500000 |  |  | 38690000
WAYNE | US 117 (FUTURE I-795) | NCDOT | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | 2.42 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3125D | Region A | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 103100000 |  |  | 117900000
WAYNE | US 117 (FUTURE I-795) | NCDOT | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | 1.82 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3125E | Not Funded | NHP | NOT FUNDED | 30500000 | NOT FUNDED | 2600000 | NOT FUNDED | 234400000 | NOT FUNDED |  | 267500000
WAYNE | US 117 (FUTURE I-795) | NCDOT | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | 3.48 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3125F | Not Funded | NHP | NOT FUNDED | 20200000 | NOT FUNDED | 1600000 | NOT FUNDED | 116400000 | NOT FUNDED |  | 138200000
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | SR 1560 (ROYAL AVENUE) TO NORTH OF SR 1572 (SAULSTON ROAD) IN GOLDSBORO. WIDEN TO MULTI-LANES. | 3 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3609
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENTS AT SR 1572 (SAULSTON ROAD). WIDEN TO FOUR LANES. | 3.46 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3609B | Region A | T | 2020 | 23339000 | 2020 | 3750000 | 2026 | 31900000 | 2020 | 2400000 | 61389000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); REMOVED $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE).
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | REALIGNMENT OF HOOD SWAMP ROAD. | 0.19 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-3609BA | Region A | T |  |  |  |  | 2022 | 2030000 |  |  | 2030000 | UNDER CONSTRUCTION.
WAYNE | US 70 BUSINESS (EAST ASH STREET) | NCDOT | SR 1711 (SOUTH OAK FOREST ROAD) TO US 70 BYPASS. WIDEN TO THREE LANES. | 1.88 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-4407 | Region A | T | 2026 | 4900000 | 2026 | 5300000 | 2029 | 39175000 |  |  | 49375000 | BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2029 - 2043 (FY 2029 / YR 9 SALE).
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | SR 1003 (NEW HOPE ROAD) TO US 70 IN GOLDSBORO. WIDEN TO FOUR LANES. | 0.87 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-4753 | Division 4 | T | 2019 | 6180000 |  |  | 2026 | 12300000 |  |  | 18480000 | RIGHT-OF-WAY IN PROGRESS.
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | REALIGNMENT OF SR 1709 (CENTRAL HEIGHTS ROAD) AT BERKELEY BOULEVARD IN GOLDSBORO. | 0.62 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-5724 | Region A | T | 2025 | 1322000 |  |  | 2023 | 19839000 |  |  | 21161000 | UNDER CONSTRUCTION.
WAYNE | US 117 | NCDOT | SR 1120 (O'BERRY ROAD) IN GOLDSBORO. CONSTRUCT INTERCHANGE. | 1 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-5796 | Division 4 | [10 empty] | UNDER CONSTRUCTION.
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | LOCKHAVEN DRIVE TO COUNTRY DAY ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.26 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-5994 | Division 4 | T |  |  |  |  | 2023 | 450000 |  |  | 450000 | UNDER CONSTRUCTION.
WAYNE | US 70 | NCDOT | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6110 | Region A | NHP | 2025 | 1300000 | 2025 | 280000 | 2027 | 14000000 |  |  | 15580000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | 1.08 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6204 | Division 4 | BG50200, T | 2025 | 4101000 | 2025 | 1400000 | 2028 | 30355000 |  |  | 35856000 | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | NCDOT | US 70 BYPASS TO SR 1547 (STONEY CREEK CHURCH ROAD). WIDEN ROADWAY. | 2.79 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6205 | Division 4 | T | 2027 | 1200000 | 2027 | 1600000 | 2029 | 4400000 |  |  | 7200000
WAYNE | SR 1713 (MILLER'S CHAPEL ROAD) | NCDOT | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | 1 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6206 | Division 4 | T | 2029 | 9200000 | 2029 | 2500000 | 2031 | 10900000 |  |  | 22600000
WAYNE | ARLINGTON BRIDGE ROAD) NC 581 (BILL LANE BOULEVARD | NCDOT | NEUSE RIVER JUST SOUTH OF SR 1919 (WESTBROOK ROAD) TO NC 111. MODERNIZE ROADWAY. | 4.5 | Highway | STI (Prioritization) | 4 | Goldsboro Urban Area MPO | U-6207 | Division 4 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 740000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 460000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22000000 |  |  | 23200000
WAYNE | US 13 (BERKELEY BOULEVARD) | NCDOT | SR 1560 (ROYAL AVENUE) TO SR 1003 (NEW HOPE ROAD). | 1 | Highway | Transition | 4 | Goldsboro Urban Area MPO | U-3609A | Pre-STI (Transition) | [10 empty] | COMPLETED.
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE |  | Public Transportation (Transit) | Capital (Non-STI) | 4 | Goldsboro Urban Area MPO | TP-5116 | Public Transit | 5303, L, S | [6 empty] | 2020 | 124000 | 124000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE |  | Public Transportation (Transit) | Capital (Non-STI) | 4 | Goldsboro Urban Area MPO | TS-5129 | Public Transit | 5307, L | [6 empty] | 2020 | 20000 | 20000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 4 | Goldsboro Urban Area MPO | TO-4719 | Public Transit | 5307, L, SMAP | [6 empty] | 2020 | 3360000 | 3360000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 4 | Goldsboro Urban Area MPO | TO-6107 | Public Transit | 5311, L | [6 empty] | 2020 | 168000 | 168000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | PREVENTIVE MAINTENANCE |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Goldsboro Urban Area MPO | TG-4752B | Public Transit | 5307, L | [6 empty] | 2020 | 1004000 | 1004000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Goldsboro Urban Area MPO | TG-4752C | Public Transit | 5307, L | [6 empty] | 2020 | 700000 | 700000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Goldsboro Urban Area MPO | TK-5179 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1224000 | 1224000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 4 | Goldsboro Urban Area MPO | TG-4752A | Public Transit | 5307, L | [6 empty] | 2020 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | 4 | Goldsboro Urban Area MPO | TG-6146 | Public Transit | 5311 | [6 empty] | 2020 | 176000 | 176000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | BAIN STREET | NCDOT | NORFOLK SOUTHERN CROSSING 722874X IN GOLDSBORO. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Goldsboro Urban Area MPO | RX-2004F | Division 4 | RR |  |  |  |  | 2025 | 417000 |  |  | 417000
WAYNE | JEFFERSON STREET | NCDOT | NORFOLK SOUTHERN CROSSING 722868U IN GOLDSBORO. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Goldsboro Urban Area MPO | RX-2004M | Division 4 | RR |  |  |  |  | 2027 | 411000 |  |  | 411000
WAYNE, DUPLIN | US 117 (FUTURE I-795) | NCDOT | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | 6.73 | Highway | STI (Prioritization) | 3, 4 | Eastern Carolina RPO | U-3125B | Not Funded | NHP | NOT FUNDED | 39400000 | NOT FUNDED | 5000000 | NOT FUNDED | 173000000 | NOT FUNDED |  | 217400000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
WAYNE, DUPLIN, SAMPSON | US 117 (FUTURE I-795) | NCDOT | I-40 TO I-795. UPGRADE ROADWAY TO INTERSTATE STANDARDS, PART ON NEW LOCATION. | 24.3 | Highway | STI (Prioritization) | 3, 4 | Goldsboro Urban Area MPO, Eastern Carolina RPO, Mid-Carolina RPO | U-3125
WAYNE, EDGECOMBE, WILSON | NC 111 | NCDOT | NC 111 FROM WAYNE/DUPLIN COUNTY LINE TO SR 1727 (DOLLARD TOWN ROAD). NC 111 FROM US 70 BYPASS OVERPASS TO NC 222. NC 111/NC 222 FROM FREMONT LIMITS TO SR 1513 (RED HILL ROAD). NC 111/NC 222 FROM STANTONSBURG LIMITS TO SARATOGA LIMITS. NC 111 FROM NC 222 IN WILSON COUNTY TO SR 1344 (SARA LEE ROAD) IN EDGECOMBE COUNTY. NC 111 FROM PRINCEVILLE TO EDGECOMBE/MARTIN COUNTY LINE. INSTALL RUMBLE STRIPS WITH SIX-INCH PAVEMENT MARKINGS. |  | Highway | Safety | 4 | Upper Coastal Plain RPO, Goldsboro Urban Area MPO | HS-2004V | Region A | HSIP |  |  |  |  | 2024 | 2474000 |  |  | 2474000 | UNDER CONSTRUCTION.
WILKES | WILKES COUNTY AIRPORT (UKF) | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. |  | Aviation | STI (Prioritization) | 11 | High Country RPO | AV-5894 | Division 11 | T | 2025 | 600000 |  |  | 2027 | 12300000 |  |  | 12900000
WILKES | SR 1001 (OAKWOODS ROAD) | NCDOT | REPLACE BRIDGE 960029 OVER CUB CREEK. |  | Highway | Bridges | 11 | High Country RPO | B-4676A | Division 11 | BGOFF |  |  |  |  | 2026 | 8000000 |  |  | 8000000 | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM
WILKES | SR 1313 | NCDOT | REPLACE BRIDGE 960075 OVER FISH DAM CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | B-4977 | Highway Fund | HFB |  |  |  |  | 2021 | 700000 |  |  | 700000 | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT
WILKES | SR 2418 | NCDOT | REPLACE BRIDGE 960004 OVER LITTLE HUNTING CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0108 | Highway Fund | HFB |  |  |  |  | 2022 | 1200000 |  |  | 1200000 | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT
WILKES | SR 1745 (SHUMATE MOUNTAIN ROAD) | NCDOT | REPLACE BRIDGE 960166 ON SR 1745 OVER WEST PRONG ROARING RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0124 | Highway Fund | DP, HFB | 2020 | 40000 |  |  | 2021 | 2900000 |  |  | 2940000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 1002 (TRAPHILL ROAD) | NCDOT | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0125 | Highway Fund | DP, HFB | 2020 | 280000 |  |  | 2021 | 2650000 |  |  | 2930000 | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 1749 (AUSTIN TRAPHILL ROAD) | NCDOT | REPLACE BRIDGE 960667 ON SR 1749 OVER SPARKS CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0126 | Highway Fund | DP, HFB | 2020 | 80000 |  |  | 2021 | 1550000 |  |  | 1630000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 2516 | NCDOT | REPLACE BRIDGE 960733 OVER CUB CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0208 | Highway Fund | HFB |  |  |  |  | 2022 | 600000 |  |  | 600000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.154
WILKES | SR 1148 | NCDOT | REPLACE BRIDGE 960419 OVER NAKED CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | BR-0209 | Highway Fund | HFB |  |  |  |  | 2021 | 650000 |  |  | 650000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.153
WILKES | ROAD) SR 1185 (CURTIS BRIDGE | NCDOT | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0020 | Exempt | BGOFF, DP, HFB | 2025 | 750000 | 2025 | 290000 | 2027 | 13800000 | 2023 | 1112000 | 15952000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | SR 1559 | NCDOT | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0063 | Exempt | BGOFF, DP, HFB | 2025 | 70000 | 2025 | 20000 | 2026 | 1600000 | 2023 | 139000 | 1829000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | (SHEETS GAP ROAD) SR 1567 | NCDOT | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0064 | Exempt | BGOFF, DP, HFB | 2025 | 129000 | 2025 | 40000 | 2026 | 1401000 | 2023 | 111000 | 1681000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | SR 1170 | NCDOT | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0065 | Exempt | BGOFF, DP, HFB | 2025 | 280000 | 2025 | 20000 | 2026 | 1900000 | 2023 | 125000 | 2325000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | SR 1355 | NCDOT | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0066 | Exempt | BGOFF, DP, HFB | 2025 | 130000 | 2025 | 60000 | 2026 | 2119000 | 2023 | 139000 | 2448000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | US 421 BUSINESS | NCDOT | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | Highway | Bridges | 11 | High Country RPO | HB-0069 | Exempt | BFP, DP, HFB | 2025 | 4000000 | 2025 | 1400000 | 2027 | 20700000 | 2023 | 1667000 | 27767000 | DP REPRESENTS RAISE GRANT FUNDS.
WILKES | VARIOUS | NCDOT | INSTALL RUMBLE STRIPES AND LONG LIFE PAVEMENT MARKINGS. INSTALL SHOULDER GUARDRAIL NEAR SR 2329. |  | Highway | Safety | 11 | High Country RPO | HS-2011F | Division 11 | HSIP |  |  |  |  | 2023 | 395000 |  |  | 395000
WILKES | SR 1143 (NEW BROWNS FORD ROAD) | NCDOT | BRIDGE 960093 OVER YADKIN RIVER. INSTALL GUARDRAIL. |  | Highway | Safety | 11 | High Country RPO | HS-2411A | Division 11 | HSIP |  |  |  |  | 2025 | 36000 |  |  | 36000
WILKES | NC 268 | NCDOT | SR 1966 (AIRPORT ROAD) TO SR 2026 (AUSTIN TRAPHILL ROAD). INSTALL GUARDRAIL AND PAVEMENT MARKINGS. | 13.75 | Highway | Safety | 11 | High Country RPO | W-5503A | Region F | HSIP |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | UNDER CONSTRUCTION.
WILKES | NC 115 | NCDOT | US 421 TO 2ND STREET. WIDEN TO TWO LANES WITH MEDIAN. CONSTRUCT BIKE LANES AND SIDEWALKS. | 2.98 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5759 | Division 11 | T | 2022 | 12615000 | 2022 | 900000 | 2026 | 57945000 | 2020 | 1365000 | 72825000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $14M FOR CON PAYBACK FY 2026-2042 (FY 2026 / YR6 SALE)
WILKES | SR 1001 (OAKWOODS ROAD) | NCDOT | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 1.27 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5772 | Division 11 | T | 2026 | 3500000 | 2026 | 1900000 | 2027 | 25925000 |  |  | 31325000 | BUILD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE).
WILKES | NC 268 | NCDOT | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | 13.52 | Highway | STI (Prioritization) | 11 | High Country RPO | R-5906 | Division 11 | BGLT5, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 60200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 118900000 |  |  | 187300000
WILKES | US 421 | NCDOT | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO REDUCED CONFLICT INTERSECTIONS AND ADD SERVICE ROADS. | 2.64 | Highway | STI (Prioritization) | 11 | High Country RPO | U-5312 | Region F | NHP | 2023 | 5100000 | 2023 | 1217000 | 2023 | 91349000 |  |  | 97666000 | UNDER CONSTRUCTION.
WILKES | NC 268 | NCDOT | NC 18 TO SR 1966 (AIRPORT ROAD). CONSTRUCT SIDEWALK FROM NC 18 TO SHAVER STREET. WIDEN TO FIVE-LANES FROM SHAVER STREET TO FAIRPLAINS ROAD. WIDEN TO FOUR-LANES DIVIDED FROM FAIRPLAINS ROAD TO SR 1966 (AIRPORT ROAD). | 3.27 | Highway | Transition | 11 | High Country RPO | R-2603 | Pre-STI (Transition) | [10 empty] | UNDER CONSTRUCTION
WILKES | NC 268 | NCDOT | NC 268 EAST OF NORTH WILKESBORO. WIDEN MULTIPLE SECTIONS, IMPROVE SHOULDERS, AND INSTALL GUARDRAIL, RUMBLE STRIPS, AND PAVEMENT MARKINGS. |  | Highway | Transition | 11 | High Country RPO | W-5503 | Region F | [10 empty] | PART COMPLETE
WILKES | WILKES TRANSPORTATION AUTHORITY | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 11 | High Country RPO | TK-6172 | Public Transit | 5311, L, S | [6 empty] | 2020 | 912000 | 912000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | WILSON | WILSON | HOMINY CREEK GREENWAY AND TRAIL NETWORK PLAN. | 3.8 | Bike & Ped | Other | 4 | Upper Coastal Plain RPO | BL-0069 | Exempt | DP | [6 empty] | 2023 | 950000 | 950000 | DP FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT.
WILSON | US 117 | NCDOT | REPLACE BRIDGE 970047 OVER SEABOARD COAST LINE RAILROAD. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5666 | Highway Fund | HFB |  |  |  |  | 2022 | 4469000 |  |  | 4469000 | UNDER CONSTRUCTION.
WILSON | SR 1339 (SHARPE SHORE ROAD) | NCDOT | REPLACE BRIDGE 970092 OVER TOWN SWAMP. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-5998 | Division 4 | [10 empty] | UNDER CONSTRUCTION
WILSON | SR 1400 (ROCK QUARRY ROAD) | NCDOT | REPLACE BRIDGE 970096 OVER TRIBUTARY OF TOWN CREEK. | 0.25 | Highway | Bridges | 4 | Upper Coastal Plain RPO | B-6000 | Division 4 | [10 empty] | UNDER CONSTRUCTION
WILSON | US 264 | NCDOT | US 264 FROM I-795 TO TOISNOT SWAMP. PAVEMENT REHABILITATION. | 7.05 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | HI-0006 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 13706000 |  |  | 13706000 | UNDER CONSTRUCTION.
WILSON | US 264 | NCDOT | US 264 FROM TOISNOT SWAMP TO THE GREENE COUNTY LINE. PAVEMENT REHABILITATION. | 8.23 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | HI-0007 | Statewide Mobility | NHPIM |  |  |  |  | 2022 | 11015000 |  |  | 11015000 | UNDER CONSTRUCTION.
WILSON | US 264 | NCDOT | US 264 FROM THE WILSON COUNTY LINE TO I-95. PAVEMENT REHABILITATION. | 4.55 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | HI-0014 | Statewide Mobility | NHPIM |  |  |  |  | 2026 | 6000000 |  |  | 6000000
WILSON | I-95 | NCDOT | JOHNSTON COUNTY LINE (MILE MARKER 108.2) TO NORTH OF SR 1116 (GOVERNOR HUNT ROAD) (MILE MARKER 114.5). PAVEMENT REHABILITATION. | 6.41 | Highway | Interstate Maintenance | 4 | Upper Coastal Plain RPO | I-5936 | Statewide Mobility | NHPIM |  |  |  |  | 2021 | 3303000 |  |  | 3303000 | UNDER CONSTRUCTION.
WILSON | SR 1356 (RALEIGH ROAD PARKWAY) | NCDOT | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | 0.47 | Highway | Locally Selected | 4 | Upper Coastal Plain RPO | HL-0034 | Exempt | BA |  |  | 2022 | 75000 | 2023 | 2357000 | 2021 | 45000 | 2477000 | UNDER CONSTRUCTION.
WILSON | SR 1103 (WIGGINS MILL ROAD) | NCDOT | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT SR 1103 (WIGGINS MILL ROAD) AND SR 1169 (RADFORD ROAD). | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004F | Division 4 | HSIP |  |  |  |  | 2022 | 30000 |  |  | 30000 | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004G AND HS-2004H.
WILSON | SR 1320 (AIRPORT BOULEVARD) | NCDOT | SR 1320 (AIRPORT BOULEVARD) AT CHELSEA DRIVE AND SR 1320 (AIRPORT BOULEVARD) AT JETSTREAM DRIVE IN WILSON. INSTALL TRAFFIC SIGNALS. | 0.5 | Highway | Safety | 4 | Upper Coastal Plain RPO | HS-2004O | Division 4 | HSIP |  |  | 2023 | 140000 | 2024 | 520000 |  |  | 660000 | UNDER CONSTRUCTION.
WILSON | US 301 | NCDOT | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | 1 | Highway | Safety | 4 | Upper Coastal Plain RPO | W-5804A | Region A | HSIP | 2021 | 100000 |  |  | 2022 | 2584000 |  |  | 2684000 | UNDER CONSTRUCTION.
WILSON | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | NCDOT | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | 1.12 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-5941 | Region A | BG5T50 | 2028 | 12600000 | 2028 | 4200000 | 2031 | 21300000 |  |  | 38100000
WILSON | WILSON | NCDOT | WILSON CITY SIGNAL SYSTEM. | 26.1 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-5945 | Division 4 | BG5T50 |  |  | 2024 | 2300000 | 2025 | 1700000 |  |  | 4000000
WILSON | NC 58 (NASH STREET NW) | NCDOT | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 4 | Upper Coastal Plain RPO | U-6111 | Region A | T | 2028 | 4800000 | 2028 | 720000 | 2031 | 8100000 |  |  | 13620000
WILSON | INTERGRATED MOBILITY DIVISION |  | COMMUNITY PROJECT FUNDING FOR CITY OF WILSON RIDE MICROTRANSIT EXPANSION. |  | Public Transportation (Transit) | Locally Selected | 4 | Upper Coastal Plain RPO | TL-0033 | Public Transit | CPF, L | [6 empty] | 2024 | 2500000 | 2500000
WILSON | CITY OF WILSON | CITY OF WILSON | OPERATING ASSISTANCE |  | Public Transportation (Transit) | Miscellaneous/Other | 4 | Upper Coastal Plain RPO | TO-4779 | Public Transit | 5311, L, SMAP | [6 empty] | 2020 | 4464000 | 4464000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | CITY OF WILSON | CITY OF WILSON | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Upper Coastal Plain RPO | TK-5178 | Public Transit | 5311, L, S | [6 empty] | 2020 | 1304000 | 1304000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | WILSON COUNTY | WILSON COUNTY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 4 | Upper Coastal Plain RPO | TK-6173 | Public Transit | 5311, L, S | [6 empty] | 2020 | 344000 | 344000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | SR 1163 (GOLDSBORO STREET) | NCDOT | AT-GRADE CROSSING IMPROVEMENTS AT CSX (CROSSING 629 847Y) IN WILSON. |  | Rail | Rail-Highway Grade Crossing Closure | 4 | Upper Coastal Plain RPO | RC-2004A | Division 4 | RR | 2024 | 50000 | 2025 | 50000 | 2026 | 1200000 |  |  | 1300000
WILSON | SR 1163 (GOLDSBORO STREET / HERRING AVENUE) | NCDOT | CSX CROSSING 629847Y IN WILSON. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004A | Division 4 | RR |  |  |  |  | 2025 | 800000 |  |  | 800000
WILSON | SR 1100 (CHICOPEE ROAD) | NCDOT | CSX CROSSING 629847Y IN WILSON. INSTALL ACTIVE WARNING DEVICES. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004B | Division 4 | RR |  |  |  |  | 2023 | 650000 |  |  | 650000 | UNDER CONSTRUCTION.
WILSON | SR 1329 (VAN SLYKE ROAD) | NCDOT | CSX CROSSING 629843W IN WILSON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004E | Division 4 | RR |  |  |  |  | 2025 | 650000 |  |  | 650000
WILSON | GREEN STREET | NCDOT | CSX CROSSING 629849M IN WILSON. CONSTRUCT SAFETY IMPROVEMENTS. |  | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2004I | Division 4 | RR |  |  |  |  | 2025 | 417000 |  |  | 417000
WILSON | NC 58 | NCDOT | CLNA CROSSING 465577V IN STANTONSBURG. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2404A | Division 4 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
WILSON | SR 1607 (CHARLESTON STREET) | NCDOT | CLNA CROSSING 465596A IN WILSON. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2404B | Division 4 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
WILSON | TARBORO STREET ANNEX | NCDOT | CLNA CROSSING 465604P IN WILSON. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | Rail | Rail-Highway Grade Crossing Improvement | 4 | Upper Coastal Plain RPO | RX-2404C | Division 4 | RR |  |  |  |  | 2027 | 400000 |  |  | 400000
WILSON, LEE, ROWAN, BRUNSWICK, NEW HANOVER, PENDER, JOHNSTON, ALAMANCE, ROCKINGHAM, McDOWELL, MONTGOMERY, EDGECOMBE, FRANKLIN, GRANVILLE, NASH, RANDOLPH, VANCE, WARREN | INTEGRATED MOBILITY DIVISION |  | THE PROJECT WILL EXPAND ON-DEMAND TRANSIT SERVICES FOR UP TO 11 RURAL COMMUNITIES ACROSS NORTH CAROLINA. THIS PROJECT WILL EMPLOY TWO PRIMARY ON-DEMAND SERVICE MODELS: SOFTWARE AS A SERVICE (SAAS) AND TURNKEY, ALSO REFERRED TO AS TRANSPORTATION AS A SERVICE (TAAS). |  | Public Transportation (Transit) | Capital (Non-STI) | 3, 4, 5, 7, 8, 9, 13 | Wilmington Urban Area MPO, Upper Coastal Plain RPO, Piedmont Triad RPO, Greensboro Urban Area MPO, Winston-Salem Area TPO, Kerr-Tar RPO, Foothills RPO | TC-0031 | Public Transit | L, RTAP, S | [6 empty] | 2024 | 25400000 | 25400000
YADKIN | US 21 BUS | NCDOT | REPLACE BRIDGE 980059 OVER JONESVILLE CREEK. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-4979 | Highway Fund | HFB |  |  |  |  | 2021 | 1600000 |  |  | 1600000 | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT.
YADKIN | NC 67 | NCDOT | REPLACE BRIDGE 980035 OVER YADKIN RIVER. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5825 | Region F | T |  |  |  |  | 2021 | 12440000 |  |  | 12440000 | UNDER CONSTRUCTION.
YADKIN | US 21 BUSINESS | NCDOT | REPLACE BRIDGE 980029 OVER I-77. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | B-5833 | Region F | BFP | 2021 | 1800000 |  |  | 2025 | 17300000 |  |  | 19100000 | RIGHT-OF-WAY IN PROGRESS.
YADKIN | SR 1512 | NCDOT | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0109 | Highway Fund | HFB | 2022 | 3000 | 2022 | 5000 | 2023 | 788000 |  |  | 796000 | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT
YADKIN | SR 1325 (MOUNTAIN VIEW CHURCH ROAD) | NCDOT | REPLACE BRIDGE 980189 ON SR 1325 OVER SOUTH DEEP CREEK. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0127 | Highway Fund | DP, HFB | 2020 | 45000 |  |  | 2021 | 850000 |  |  | 895000 | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
YADKIN | SR 1152 | NCDOT | REPLACE BRIDGE 980020 OVER SOUTH DEEP CREEK. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0200 | Highway Fund | HFB |  |  |  |  | 2019 | 850000 |  |  | 850000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENT HFB PROJECT NUMBER 17BP.11.R.183.
YADKIN | SR 1119 | NCDOT | REPLACE BRIDGE 980028 OVER NORTH LITTLE HUNTING CREEK. | 0.25 | Highway | Bridges | 11 | Northwest Piedmont RPO | BR-0205 | Highway Fund | HFB |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.130
YADKIN | I-77 | NCDOT | MILEMARKER 71.8 TO MILEMARKER 75.8. PAVEMENT REHABILITATION. | 2.08 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5864 | Statewide Mobility | NHPIM |  |  |  |  | 2028 | 6285000 |  |  | 6285000 | COMBINE WITH I-5865 FOR LETTING.
YADKIN | I-77 | NCDOT | MILEMARKER 75.8 TO US 21 (EXIT 79). PAVEMENT REHABILITATION. | 1.89 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5865 | Statewide Mobility | NHPIM |  |  |  |  | 2030 | 2990000 |  |  | 2990000 | COMBINE WITH I-5864 FOR LETTING.
YADKIN | US 421 | NCDOT | SR 1710 (SPEER BRIDGE ROAD) INTERCHANGE. CONSTRUCT ROUNDABOUTS AT RAMP TERMINALS. |  | Highway | NCDOT Selected (Other Selection Process) | 11 | Northwest Piedmont RPO | HN-0028 | Statewide Mobility | HSIP, T(M) |  |  |  |  | 2025 | 4000000 |  |  | 4000000
YADKIN | I-77 | NCDOT | SOUTH OF SR 1125 (ASHBURY CHURCH ROAD-MILEPOST 71) TO US 21 IN YADKIN COUNTY (EXIT 79) | 6.592 | Highway | Pre-STI (Historic) | 11 | Northwest Piedmont RPO | I-2808A | Pre-STI (Transition) | [10 empty] | COMPLETE
YADKIN | VARIOUS | NCDOT | DIVISION 11 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN REGIONAL CATEGORY. |  | Highway | Safety | 11 | Northwest Piedmont RPO | W-5211REG | Region F
YADKIN | SR 1605 (OLD US 421) | NCDOT | SR 1146 (SHACKTOWN ROAD) TO SR 1711 (SPEER BRIDGE ROAD). CONSTRUCT NEW ROADWAY TO REALIGN SR 1605 WITH SR 1711 AND CONSTRUCT A ROUNDABOUT AT THE INTERSECTION WITH SR 1146. | 0.18 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5730 | Division 11 | T |  |  |  |  | 2022 | 3216000 |  |  | 3216000 | UNDER CONSTRUCTION.
YADKIN | AVENUE) US 601 (CAROLINA | NCDOT | NC 67 (MAIN STREET) INTERSECTION. UPGRADE INTERSECTION. | 0.5 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5831 | Division 11 | T |  |  | 2023 | 650000 | 2025 | 3900000 |  |  | 4550000 | RIGHT-OF-WAY IN PROGRESS
YADKIN | SR 1314 (EAST MAIN STREET) | NCDOT | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 1.19 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5909 | Division 11 | T | 2027 | 1901000 | 2027 | 2300000 | 2030 | 13105000 |  |  | 17306000 | NC BUILD BONDS: $4M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030).
YADKIN | SR 1605 (OLD US 421) | NCDOT | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5912 | Division 11 | T | 2023 | 600000 | 2023 | 400000 | 2024 | 1500000 |  |  | 2500000 | RIGHT-OF-WAY IN PROGRESS.
YADKIN | NC 67 | NCDOT | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | 10.55 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5914 | Division 11 | BGLT5, T | 2028 | 9000000 | 2028 | 14800000 | 2031 | 92100000 |  |  | 115900000
YADKIN | US 601 (STATE STREET) | NCDOT | SR 1742 (SHARON DRIVE) TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | 0.68 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | U-5809 | Division 11 | BGLT5, T | 2023 | 1700000 | 2024 | 800000 | 2024 | 23035000 |  |  | 25535000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894.
YADKIN, SURRY | I-77 | NCDOT | SOUTH OF SR 1125 (MILE MARKER 71) IN YADKIN COUNTY TO US 21 BYPASS (MILE MARKER 83.5) IN SURRY COUNTY (EXIT 83). PAVEMENT REHABILITATION. | 12 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-2808 | [11 empty] | SECTION A - GARVEE BOND FUNDING $35 MILLION; PAYBACK FY 2007 - FY 2018. SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
YADKIN, SURRY | I-77 | NCDOT | US 21 IN YADKIN COUNTY (EXIT 79) TO US 21 BYPASS (EXIT 83) IN SURRY COUNTY | 0 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-2808B | [11 empty] | SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
YADKIN, SURRY | I-77 | NCDOT | US 21 IN YADKIN COUNTY (EXIT 79) TO MILEMARKER 83.4 IN SURRY COUNTY . PAVEMENT REHABILITATION. | 4.36 | Highway | Interstate Maintenance | 11 | Northwest Piedmont RPO | I-5912 | Statewide Mobility | [10 empty] | UNDER CONSTRUCTION
YADKIN, SURRY | I-77 | NCDOT | VARIOUS LOCATIONS. UPGRADE GUARDRAIL END UNITS. |  | Highway | Safety | 11 | Northwest Piedmont RPO | HS-2411B | Statewide Mobility | HSIP |  |  |  |  | 2025 | 152000 |  |  | 152000
YADKIN, SURRY | NC 67; US 21 BUSINESS | NCDOT | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN EXISTING TWO LANE ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS; REHABILITATE BRIDGE 850021 OVER YADKIN RIVER AND WIDEN SIDEWALKS. | 0.35 | Highway | STI (Prioritization) | 11 | Northwest Piedmont RPO | R-5913 | Division 11 | BGLT5, HFB | 2025 | 1100000 | 2025 | 280000 | 2027 | 5800000 |  |  | 7180000
YANCEY | US 19W | NCDOT | SR 1454 TO SR 1382 NEAR BURNSVILLE. INSTALL GUARDRAIL. | 5.07 | Highway | Safety | 13 | High Country RPO | HS-2013J | Region G | HSIP |  |  |  |  | 2024 | 731000 |  |  | 731000
YANCEY | NC 197 | NCDOT | NC 197 FROM SR 1338 TO THE MITCHELL COUNTY LINE, NEAR GREEN MOUNTAIN. INSTALL SHOULDER GUARDRAIL. | 3.74 | Highway | Safety | 13 | High Country RPO | W-5813H | Region G | HSIP |  |  |  |  | 2022 | 474000 |  |  | 474000 | COMPLETE
YANCEY | YANCEY COUNTY TRANSPORTATION AUTHORITY | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION |  | Public Transportation (Transit) | Operations and Maintenance | 13 | High Country RPO | TK-6175 | Public Transit | 5311, L, S | [6 empty] | 2020 | 580000 | 580000 | FUNDS AUTHORIZED IN PROGRESS
YANCEY | AUTHORITY YANCEY COUNTY TRANSPORTATION | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. |  | Public Transportation (Transit) | STI (Prioritization) | 13 | High Country RPO | TA-6723 | Division 13 | L, T |  |  |  |  | 2023 | 2345000 | 2023 | 155000 | 2500000 | LOCAL FUNDING PROVIDED BY YANCEY COUNTY

## 2026-2035 STIP Funding Details
2026-2035 DRAFT STATE TRANSPORTATION IMPROVEMENT PROGRAM Please note that ALL INFORMATION AND DATA is considered DRAFT and is SUBJECT TO CHANGE. | [15 empty] | 2026-2035 STIP WINDOW
PROJECT ID | MODE | FUNDING PROGRAM | ROUTE/CITY | DESCRIPTION | LENGTH (MILES) | COUNTY(S) | DIVISION(S) | MPOs/RPOs | COMMENT | CATEGORY FUNDED | FUNDING COMMENT | FUND SOURCE | ACTIVITY | TOTAL FUNDED (MAY INCLUDE PREVIOUSLY AUTHORIZED FUNDS) | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | FY 2035 | AFTER 2035
A-0009 | Highway | Appalachian Development Highway System | US 19, US 74, US 129, NC 28, NC 143 | CORRIDOR "K", ANDREWS TO NC 28 EAST OF ALMOND. UPGRADE ROADWAY TO INCLUDE EXISTING FACILITIES AND NEW LOCATION. | 27.1 | GRAHAM, SWAIN, CHEROKEE | 14 | Southwestern RPO | Use Toll Credits on A-0009CE
A-0009A | Highway | Appalachian Development Highway System | US 19, US 74, US 129 | US 19 BUSINESS IN ANDREWS TO US 129 SOUTH OF SR 1275 (FIVE POINT ROAD) IN ROBBINSVILLE, UPGRADE ROADWAY. | 7.71 | GRAHAM, CHEROKEE | 14 | Southwestern RPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 14300000 | [11 empty] | 14300000
A-0009A | Highway | Appalachian Development Highway System | US 19, US 74, US 129 | US 19 BUSINESS IN ANDREWS TO US 129 SOUTH OF SR 1275 (FIVE POINT ROAD) IN ROBBINSVILLE, UPGRADE ROADWAY. | 7.71 | GRAHAM, CHEROKEE | 14 | Southwestern RPO |  | Not Funded |  | NHP | UTILITIES | 925000 | [11 empty] | 925000
A-0009A | Highway | Appalachian Development Highway System | US 19, US 74, US 129 | US 19 BUSINESS IN ANDREWS TO US 129 SOUTH OF SR 1275 (FIVE POINT ROAD) IN ROBBINSVILLE, UPGRADE ROADWAY. | 7.71 | GRAHAM, CHEROKEE | 14 | Southwestern RPO |  | Not Funded |  | NHP | CONSTRUCTION | 366000000 | [11 empty] | 366000000
A-0009CA | Highway | Appalachian Development Highway System | US 129, NC 143 | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | 4.14 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | RIGHT-OF-WAY | 1900000
A-0009CA | Highway | Appalachian Development Highway System | US 129, NC 143 | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | 4.14 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | UTILITIES | 2030000
A-0009CA | Highway | Appalachian Development Highway System | US 129, NC 143 | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | 4.14 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | CONSTRUCTION | 54624000 | FY 2025: 12984000
A-0009CB | Highway | Appalachian Development Highway System | NC 143 | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | 3.91 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | RIGHT-OF-WAY | 3300000
A-0009CB | Highway | Appalachian Development Highway System | NC 143 | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | 3.91 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | UTILITIES | 1300000
A-0009CB | Highway | Appalachian Development Highway System | NC 143 | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | 3.91 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | CONSTRUCTION | 133871000 | FY 2025: 30799000; FY 2026: 19198000
A-0009CC | Highway | Appalachian Development Highway System | NC 143, NC 28 | NC 143 FROM NORTH OF APPALACHIAN TRAIL TO NC 28; NC 28 FROM NC 143 TO WEST OF SR 1228 (STECOAH ROAD). UPGRADE ROADWAY. | 2.4 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | RIGHT-OF-WAY | 2300000
A-0009CC | Highway | Appalachian Development Highway System | NC 143, NC 28 | NC 143 FROM NORTH OF APPALACHIAN TRAIL TO NC 28; NC 28 FROM NC 143 TO WEST OF SR 1228 (STECOAH ROAD). UPGRADE ROADWAY. | 2.4 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | UTILITIES | 550000
A-0009CC | Highway | Appalachian Development Highway System | NC 143, NC 28 | NC 143 FROM NORTH OF APPALACHIAN TRAIL TO NC 28; NC 28 FROM NC 143 TO WEST OF SR 1228 (STECOAH ROAD). UPGRADE ROADWAY. | 2.4 | GRAHAM | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Exempt |  | ADHS | CONSTRUCTION | 77500000 | FY 2025: 18413000; FY 2026: 13053000; FY 2027: 3622000
A-0009CD | Highway | Appalachian Development Highway System | NC 28 | WEST OF SR 1228 (STECOAH ROAD) TO SR 1235 (GUNTERS GAP ROAD). UPGRADE ROADWAY. | 1.42 | GRAHAM | 14 | Southwestern RPO |  |  |  | ADHS | CONSTRUCTION | 16000000 | FY 2025: 16000000
A-0009CD | Highway | Appalachian Development Highway System | NC 28 | WEST OF SR 1228 (STECOAH ROAD) TO SR 1235 (GUNTERS GAP ROAD). UPGRADE ROADWAY. | 1.42 | GRAHAM | 14 | Southwestern RPO |  |  |  | DP | CONSTRUCTION | 20000000 | FY 2025: 20000000
A-0009CE | Highway | NCDOT Selected (Other Selection Process) | NC 28 | SR 1238 (BILL CRISP ROAD) TO SR 1230 (HYDE TOWN ROAD). CONSTRUCT MULTI-USE PATH. |  | GRAHAM | 14 | Southwestern RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 5000000
A-0009DA | Highway | Appalachian Development Highway System | NC 28 | SR 1121 (WATTIA ROAD) AT ALMONDS TO EXISTING US 19/NC 28 | 1.517 | SWAIN | 14 | Southwestern RPO | COMPLETE
A-0009DB | Highway | Appalachian Development Highway System | NC 28 | EAST OF CALFPEN GAP IN GRAHAM COUNTY TO SR 1121 (WATTIA ROAD) AT ALMONDS IN SWAIN COUNTY | 2.381 | SWAIN, GRAHAM | 14 | Southwestern RPO | COMPLETE
A-0009DC | Highway | Appalachian Development Highway System | NC 28 | WEST OF SR 1231 (TOBACCO BRANCH ROAD) TO CALFPEN GAP | 2.337 | GRAHAM | 14 | Southwestern RPO | COMPLETE
A-0009DD | Highway | Appalachian Development Highway System | NC 28 | NC 28 AT STECOAH TO WEST OF SR 1231 (TOBACCO BRANCH ROAD) | 2.859 | GRAHAM | 14 | Southwestern RPO | COMPLETE
A-0010 | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) IN ASHEVILLE TO TENNESSEE STATE LINE AT SAMS GAP. MULTI-LANE FREEWAY, PART ON NEW LOCATION. | 28.3 | BUNCOMBE, MADISON | 13 | French Broad River MPO, Land-of-Sky RPO | COORDINATE WITH B-4442, B-4443, B-4444.
A-0010AA | Highway | STI (Prioritization) | I-26 (US 19/US 23) | BREAK NO LONGER USED. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G
A-0010AB | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251/SR 1781 (BROADWAY STREET) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 26499000
A-0010AB | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251/SR 1781 (BROADWAY STREET) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1800000
A-0010AB | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251/SR 1781 (BROADWAY STREET) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 34400000
A-0010AC | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1684 (ELK MOUNTAIN ROAD) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 22106000
A-0010AC | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1684 (ELK MOUNTAIN ROAD) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1697000
A-0010AC | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1684 (ELK MOUNTAIN ROAD) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 42700000
A-0010AD | Highway | STI (Prioritization) | I-26 (US 19/US 23) | US 25 (MERRIMON AVENUE) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 46300000
A-0010AD | Highway | STI (Prioritization) | I-26 (US 19/US 23) | US 25 (MERRIMON AVENUE) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 1600000
A-0010AD | Highway | STI (Prioritization) | I-26 (US 19/US 23) | US 25 (MERRIMON AVENUE) INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 74500000
A-0010AE | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1882 (NEW STOCK ROAD) INTERCHANGE. IMPROVE INTERCHANGE AREA INCLUDING WIDENING I-26 TO NORTH OF SR 1720 (AIKEN ROAD). |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | NHP | RIGHT-OF-WAY | 24100000 | FY 2028: 2410000; FY 2029: 8435000; FY 2030: 8435000; FY 2031: 2410000; FY 2032: 2410000
A-0010AE | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1882 (NEW STOCK ROAD) INTERCHANGE. IMPROVE INTERCHANGE AREA INCLUDING WIDENING I-26 TO NORTH OF SR 1720 (AIKEN ROAD). |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | NHP | UTILITIES | 2300000 | FY 2028: 767000; FY 2029: 767000; FY 2030: 766000
A-0010AE | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 1882 (NEW STOCK ROAD) INTERCHANGE. IMPROVE INTERCHANGE AREA INCLUDING WIDENING I-26 TO NORTH OF SR 1720 (AIKEN ROAD). |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | NHP | CONSTRUCTION | 93900000 | FY 2031: 23475000; FY 2032: 23475000; FY 2033: 23475000; FY 2034: 23475000
A-0010AF | Highway | STI (Prioritization) | I-26 (US 19/US 23) | US 25/US 70 INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4656000
A-0010AF | Highway | STI (Prioritization) | I-26 (US 19/US 23) | US 25/US 70 INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 737000
A-0010AF | Highway | STI (Prioritization) | I-26 (US 19/US 23) | US 25/US 70 INTERCHANGE. IMPROVE INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 36400000
A-0010AG | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251/SR 1728 (BROADWAY STREET) TO US 25/US 70. WIDEN ROADWAY TO EIGHT AND SIX LANES. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4600000
A-0010AG | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251/SR 1728 (BROADWAY STREET) TO US 25/US 70. WIDEN ROADWAY TO EIGHT AND SIX LANES. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 230000
A-0010AG | Highway | STI (Prioritization) | I-26 (US 19/US 23) | NC 251/SR 1728 (BROADWAY STREET) TO US 25/US 70. WIDEN ROADWAY TO EIGHT AND SIX LANES. |  | BUNCOMBE | 13 | French Broad River MPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 207600000
A-0010AJ | Highway | STI (Prioritization) | I-26 (US 19/US 23) | US 25/US 70 TO SR 2207 (N BUNCOMBE SCHOOL ROAD). UPGRADE TO ROADWAY TO INTERSTATE STANDARDS. |  | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5600000 | [11 empty] | 5600000
A-0010AJ | Highway | STI (Prioritization) | I-26 (US 19/US 23) | US 25/US 70 TO SR 2207 (N BUNCOMBE SCHOOL ROAD). UPGRADE TO ROADWAY TO INTERSTATE STANDARDS. |  | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 72001000 | [11 empty] | 72001000
A-0010AK | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 2207 (N BUNCOMBE SCHOOL ROAD) TO SOUTH OF SR 2148 (STOCKTON ROAD). UPGRADE ROADWAY TO INTERSTATE STANDARDS. |  | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 700000 | [11 empty] | 700000
A-0010AK | Highway | STI (Prioritization) | I-26 (US 19/US 23) | SR 2207 (N BUNCOMBE SCHOOL ROAD) TO SOUTH OF SR 2148 (STOCKTON ROAD). UPGRADE ROADWAY TO INTERSTATE STANDARDS. |  | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | T | CONSTRUCTION | 27001000 | [11 empty] | 27001000
A-0010BA | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | SOUTH OF SR 2148 IN BUNCOMBE COUNTY TO NORTH OF NC 213 | 2.975 | BUNCOMBE, MADISON | 13 | Land-of-Sky RPO, French Broad River MPO | COMPLETE
A-0010BB | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | NORTH OF NC 213 TO NORTH OF US 19 | 1.762 | MADISON | 13 | Land-of-Sky RPO | COMPLETE
A-0010C | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | NORTH OF US 19 TO SR 1318 (BIG LAUREL ROAD) AT LAUREL CREEK | 6.08 | MADISON | 13 | Land-of-Sky RPO | COMPLETE
A-0010D | Highway | Appalachian Development Highway System | I-26 (US 19/US 23) | SR 1318 (BIG LAUREL ROAD) AT LAUREL CREEK TO THE TENNESSEE STATE LINE AT SAMS GAP | 2.98 | MADISON | 13 | Land-of-Sky RPO | COMPLETE
A-0011 | Highway | Appalachian Development Highway System | US 64/NC 69 | NC 69, GEORGIA STATE LINE TO US 64. WIDEN TO FOUR LANES DIVIDED. US 64, NC 69 TO EAST OF NC 175. WIDEN TO MULTI-LANES. | 7.3 | CLAY | 14 | Southwestern RPO | APD FUNDS ARE 100% FEDERAL
A-0011A | Highway | Appalachian Development Highway System | NC 69 | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). UPGRADE EXISTING TWO-LANES | 3.51 | CLAY | 14 | Southwestern RPO | COMPLETE
A-0011BA | Highway | Appalachian Development Highway System | US 64 | NC 69 IN HAYESVILLE TO EAST OF THE HIWASSEE RIVER | 0.946 | CLAY | 14 | Southwestern RPO | COMPLETE
A-0011BB | Highway | Appalachian Development Highway System | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175 | 3.8 | CLAY | 14 | Southwestern RPO | COMPLETE
A-0011C | Highway | Appalachian Development Highway System | NC 69 | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). WIDEN TO FOUR-LANES | 3.51 | CLAY | 14 | Southwestern RPO | UNDER CONSTRUCTION | Exempt |  | ADHS | CONSTRUCTION | 52600000
A-0011D | Highway | Appalachian Development Highway System | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. |  | CLAY | 14 | Southwestern RPO |  | Not Funded |  | ADHS | RIGHT-OF-WAY | 20845000 | [11 empty] | 20845000
A-0011D | Highway | Appalachian Development Highway System | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. |  | CLAY | 14 | Southwestern RPO |  | Not Funded |  | ADHS | UTILITIES | 378000 | [11 empty] | 378000
A-0011D | Highway | Appalachian Development Highway System | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. |  | CLAY | 14 | Southwestern RPO |  | Not Funded |  | ADHS | CONSTRUCTION | 52800000 | [11 empty] | 52800000
AO-0001 | Aviation | Other | ASHEVILLE REGIONAL AIRPORT | MODERNIZE AIRPORT TERMINAL BUILDING. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "HF" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | Exempt |  | FED | CONSTRUCTION | 2884000
AO-0001 | Aviation | Other | ASHEVILLE REGIONAL AIRPORT | MODERNIZE AIRPORT TERMINAL BUILDING. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "HF" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | Exempt |  | L | CONSTRUCTION | 136674000
AO-0001 | Aviation | Other | ASHEVILLE REGIONAL AIRPORT | MODERNIZE AIRPORT TERMINAL BUILDING. |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. "FED" FUNDS ARE FAA FUNDS; "HF" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT | Exempt |  | HF | CONSTRUCTION | 14250000
AP-0001 | Aviation | STI (Prioritization) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | CONSTRUCT END AROUND TAXIWAY ON WEST SIDE OF PROPOSED FOURTH PARALLEL RUNWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | T | CONSTRUCTION | 2000000 | FY 2029: 500000; FY 2030: 500000; FY 2031: 500000; FY 2032: 500000
AP-0002 | Aviation | STI (Prioritization) | FAYETTEVILLE REGIONAL AIRPORT | EXTEND RUNWAY 10/28. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 300000 | FY 2030: 300000
AP-0002 | Aviation | STI (Prioritization) | FAYETTEVILLE REGIONAL AIRPORT | EXTEND RUNWAY 10/28. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 600000
AP-0002 | Aviation | STI (Prioritization) | FAYETTEVILLE REGIONAL AIRPORT | EXTEND RUNWAY 10/28. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1500000
AP-0003 | Aviation | STI (Prioritization) | FAYETTEVILLE REGIONAL AIRPORT | EXTEND RUNWAY 4/22. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 300000 | FY 2030: 300000
AP-0003 | Aviation | STI (Prioritization) | FAYETTEVILLE REGIONAL AIRPORT | EXTEND RUNWAY 4/22. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 600000
AP-0003 | Aviation | STI (Prioritization) | FAYETTEVILLE REGIONAL AIRPORT | EXTEND RUNWAY 4/22. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1500000
AP-0004 | Aviation | STI (Prioritization) | FAYETTEVILLE REGIONAL AIRPORT | UPGRADE PAVEMENT AND PAINT THE GENERAL AVIATION APRON ON CONTROL TOWER ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO | O FUNDS REPRESENT FUNDING FROM FAYETTEVILLE REGIONAL AIRPORT. | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 900000
AP-0004 | Aviation | STI (Prioritization) | FAYETTEVILLE REGIONAL AIRPORT | UPGRADE PAVEMENT AND PAINT THE GENERAL AVIATION APRON ON CONTROL TOWER ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO | O FUNDS REPRESENT FUNDING FROM FAYETTEVILLE REGIONAL AIRPORT. | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 1400000
AP-0005 | Aviation | STI (Prioritization) | HRJ | HARNETT COUNTY AIRPORT. WIDEN EXISTING RUNWAY FROM 75' TO 100'. |  | HARNETT | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 370000 | FY 2033: 370000
AP-0005 | Aviation | STI (Prioritization) | HRJ | HARNETT COUNTY AIRPORT. WIDEN EXISTING RUNWAY FROM 75' TO 100'. |  | HARNETT | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3697000
AP-0006 | Aviation | STI (Prioritization) | CPC | COLUMBUS COUNTY MUNICIPAL AIRPORT. EXTEND RUNWAY. |  | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 390000 | FY 2030: 390000
AP-0006 | Aviation | STI (Prioritization) | CPC | COLUMBUS COUNTY MUNICIPAL AIRPORT. EXTEND RUNWAY. |  | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 248000
AP-0006 | Aviation | STI (Prioritization) | CPC | COLUMBUS COUNTY MUNICIPAL AIRPORT. EXTEND RUNWAY. |  | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1838000
AP-0006 | Aviation | STI (Prioritization) | CPC | COLUMBUS COUNTY MUNICIPAL AIRPORT. EXTEND RUNWAY. |  | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1839000
AP-0007 | Aviation | STI (Prioritization) | CPC | COLUMBUS COUNTY MUNICIPAL AIRPORT. IMPROVE RUNWAY SAFETY AREA AND WIDEN RUNWAY. |  | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 1054000 | FY 2033: 1054000
AP-0007 | Aviation | STI (Prioritization) | CPC | COLUMBUS COUNTY MUNICIPAL AIRPORT. IMPROVE RUNWAY SAFETY AREA AND WIDEN RUNWAY. |  | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 10536000
AV-5700 | Aviation | STI (Prioritization) | INTERNATIONAL AIRPORT (RDU) RALEIGH DURHAM | RECONSTRUCT RUNWAY 5L-23R. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 4500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
AV-5700 | Aviation | STI (Prioritization) | INTERNATIONAL AIRPORT (RDU) RALEIGH DURHAM | RECONSTRUCT RUNWAY 5L-23R. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 99500000
AV-5701 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L EXTENSION PROGRAM |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2025: 500000; FY 2026: 500000; FY 2027: 500000
AV-5701 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L EXTENSION PROGRAM |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 19500000 | FY 2025: 19500000
AV-5707 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY G. |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2026: 500000; FY 2027: 500000; FY 2028: 500000
AV-5707 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY G. |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | O | CONSTRUCTION | 15400000 | FY 2026: 15400000
AV-5708 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY OVER FUTURE I-73 EAST OF SR 2085 (BRYAN BOULEVARD). |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | T | CONSTRUCTION | 1500000
AV-5711 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2026: 500000; FY 2027: 500000; FY 2028: 500000
AV-5711 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY | Statewide Mobility |  | O | CONSTRUCTION | 7500000 | FY 2026: 7500000
AV-5715 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2028: 500000; FY 2029: 500000; FY 2030: 500000
AV-5715 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 9500000 | FY 2028: 9500000
AV-5718 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | HIGH SPEED TAXIWAY TO RUNWAY 5R-23L. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2027: 500000; FY 2028: 500000; FY 2029: 500000
AV-5718 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | HIGH SPEED TAXIWAY TO RUNWAY 5R-23L. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 2500000 | FY 2027: 2500000
AV-5731 | Aviation | STI (Prioritization) | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Region E |  | T | CONSTRUCTION | 300000 | FY 2025: 300000
AV-5731 | Aviation | STI (Prioritization) | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Region E |  | O | CONSTRUCTION | 7617000 | FY 2025: 7617000
AV-5733 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | DESIGN AND CONSTRUCT RUNWAY 23 HOLDING APRON. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | T | CONSTRUCTION | 300000
AV-5733 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | DESIGN AND CONSTRUCT RUNWAY 23 HOLDING APRON. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | O | CONSTRUCTION | 450000
AV-5734 | Aviation | STI (Prioritization) | REGIONAL AIRPORT (FAY) FAYETTEVILLE | REPLACE PERIMETER FENCING AND ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | T | CONSTRUCTION | 300000 | FY 2026: 300000
AV-5734 | Aviation | STI (Prioritization) | REGIONAL AIRPORT (FAY) FAYETTEVILLE | REPLACE PERIMETER FENCING AND ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | O | CONSTRUCTION | 3140000 | FY 2026: 3140000
AV-5735 | Aviation | STI (Prioritization) | ASHEVILLE REGIONAL AIRPORT (AVL) | AIRFIELD IMPROVEMENTS PROGRAM - RUNWAY CONSTRUCTION |  | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION | Region G
AV-5736 | Aviation | STI (Prioritization) | SILER CITY MUNICIPAL AIRPORT (SCR) | ACQUIRE NAVIGATION EASEMENTS IN RUNWAY 4 AND RUNWAY 22 APPROACHES, AND REMOVE OBSTRUCTIONS IN EASEMENTS. |  | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | T | RIGHT-OF-WAY | 365000
AV-5737 | Aviation | STI (Prioritization) | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN THE RUNWAY 24 APPROACH. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | T | RIGHT-OF-WAY | 1080000 | FY 2027: 1080000
AV-5737 | Aviation | STI (Prioritization) | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN THE RUNWAY 24 APPROACH. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 120000 | FY 2027: 120000
AV-5738 | Aviation | STI (Prioritization) | SMITH REYNOLDS AIRPORT (INT) | ACQUIRE LAND AND CLEAR TERRAIN OBSTRUCTIONS EAST OF RUNWAY 15-33 TO DRAIN AND GRADE MATERIAL IN PLACE. |  | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS BY AIRPORT | Division 9 |  | T | CONSTRUCTION | 2450000 | FY 2031: 1225000; FY 2032: 1225000
AV-5739 | Aviation | STI (Prioritization) | CAPE FEAR REGIONAL (SUT) | APPROACH CLEARING AT RUNWAY 5 AND RUNWAY 23. | 0 | BRUNSWICK | 3 | Cape Fear RPO | COMPLETED. | Division 3
AV-5741 | Aviation | STI (Prioritization) | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. |  | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | T | CONSTRUCTION | 3460000 | FY 2029: 1730000; FY 2030: 1730000
AV-5741 | Aviation | STI (Prioritization) | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. |  | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | O | CONSTRUCTION | 384000 | FY 2029: 384000
AV-5743 | Aviation | STI (Prioritization) | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | 0 | BEAUFORT | 2 | Mid-East RPO |  | Division 2 |  | T | RIGHT-OF-WAY | 1635000 | FY 2030: 1635000
AV-5743 | Aviation | STI (Prioritization) | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | 0 | BEAUFORT | 2 | Mid-East RPO |  | Division 2 |  | T | CONSTRUCTION | 7100000 | FY 2032: 3550000; FY 2033: 3550000
AV-5744 | Aviation | STI (Prioritization) | HENDERSON FIELD (ACZ) | LAND ACQUISTION PHASE IV FOR ROADWAY RELOCATION, SR 1307 (WALLACE AIRPORT ROAD) AND SR 1306 (OLD MILL ROAD) ROADWAY RELOCATION, RUNWAY EXTENSION - PHASE 1 (850 LF) | 0 | PENDER | 3 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T | RIGHT-OF-WAY | 2113000
AV-5744 | Aviation | STI (Prioritization) | HENDERSON FIELD (ACZ) | LAND ACQUISTION PHASE IV FOR ROADWAY RELOCATION, SR 1307 (WALLACE AIRPORT ROAD) AND SR 1306 (OLD MILL ROAD) ROADWAY RELOCATION, RUNWAY EXTENSION - PHASE 1 (850 LF) | 0 | PENDER | 3 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | T | CONSTRUCTION | 8700000 | FY 2025: 6960000
AV-5744A | Aviation | STI (Prioritization) | HENDERSON FIELD (ACZ) | EXTEND RUNWAY 5500 FEET. |  | PENDER | 3 | Cape Fear RPO |  | Division 3 |  | T | CONSTRUCTION | 4405000 | FY 2026: 2205000; FY 2027: 2200000
AV-5745 | Aviation | STI (Prioritization) | JOHNSTON COUNTY AIRPORT (JNX) | LAND ACQUISITION & CLEARING PROJECT. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T | ENGINEERING | 195000
AV-5745 | Aviation | STI (Prioritization) | JOHNSTON COUNTY AIRPORT (JNX) | LAND ACQUISITION & CLEARING PROJECT. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T | CONSTRUCTION | 2664000
AV-5746 | Aviation | STI (Prioritization) | MICHAEL J. SMITH FIELD (MRH) | FULL PARALLEL TAXIWAY 8-26. |  | CARTERET | 2 | Down East RPO | COMPLETE | Division 2
AV-5747 | Aviation | STI (Prioritization) | LUMBERTON REGIONAL AIRPORT (LBT) | PARTIAL PARALLEL TAXIWAY RUNWAY 5. |  | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | T | CONSTRUCTION | 2600000
AV-5748 | Aviation | STI (Prioritization) | COLUMBUS COUNTY AIRPORT (CPC) | APRON EXPANSION. |  | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 |  | T | CONSTRUCTION | 3000000
AV-5753 | Aviation | STI (Prioritization) | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | OBSTRUCTION REMOVAL IN RUNWAY 5 APPROACH. |  | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | T | RIGHT-OF-WAY | 295000
AV-5755 | Aviation | STI (Prioritization) | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LAND ACQUISITION FOR RUNWAY 5 APPROACH. |  | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | T | RIGHT-OF-WAY | 176000
AV-5761 | Aviation | STI (Prioritization) | RICHMOND COUNTY AIRPORT (RCZ) | CLEAR OBSTRUCTIONS IN RUNWAY 14 APPROACH. |  | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | T | CONSTRUCTION | 570000 | FY 2026: 570000
AV-5762 | Aviation | STI (Prioritization) | RALEIGH EXECUTIVE SANFORD - LEE COUNTY AIRPORT (TT | CONSTRUCT CORPORATE AREA APRON PHASE I. |  | LEE | 8 | Central Pines RPO | UNDER CONSTRUCTION; INCLUDES $1.5 M IN ECONOMIC DEVELOPMENT FUNDING | Division 8
AV-5788 | Aviation | STI (Prioritization) | MARTIN COUNTY AIRPORT (MCZ) | CONSTRUCT TAXILANES AND APRON. |  | MARTIN | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | T | CONSTRUCTION | 1250000
AV-5798 | Aviation | STI (Prioritization) | WILMINGTON INTERNATIONAL (ILM) | TAXIWAY IMPROVEMENTS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | T | CONSTRUCTION | 500000 | FY 2028: 500000
AV-5798 | Aviation | STI (Prioritization) | WILMINGTON INTERNATIONAL (ILM) | TAXIWAY IMPROVEMENTS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | O | CONSTRUCTION | 5100000 | FY 2028: 5100000
AV-5800 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY J EXTENSION, TAXIWAY D TO TAXIWAY J2. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2026: 500000; FY 2027: 500000; FY 2028: 500000
AV-5800 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY J EXTENSION, TAXIWAY D TO TAXIWAY J2. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 5500000 | FY 2026: 5500000
AV-5801 | Aviation | STI (Prioritization) | WILMINGTON INTERNATIONAL (ILM) | EXPANSION OF AIR CARRIER APRON. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | T | CONSTRUCTION | 500000
AV-5801 | Aviation | STI (Prioritization) | WILMINGTON INTERNATIONAL (ILM) | EXPANSION OF AIR CARRIER APRON. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | O | CONSTRUCTION | 3440000
AV-5802 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT NORTHWEST APRON TO INCREASE CAPACITY FOR FUTURE EXPANSION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2028: 500000; FY 2029: 500000; FY 2030: 500000
AV-5802 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT NORTHWEST APRON TO INCREASE CAPACITY FOR FUTURE EXPANSION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 9500000 | FY 2028: 9500000
AV-5803 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1500000 | FY 2028: 500000; FY 2029: 500000; FY 2030: 500000
AV-5803 | Aviation | STI (Prioritization) | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | O | CONSTRUCTION | 26500000 | FY 2028: 26500000
AV-5804 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR ROADWAY RELOCATION, RPZ AND RUNWAY EXTENSION. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | Region B |  | T | RIGHT-OF-WAY | 300000
AV-5804 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR ROADWAY RELOCATION, RPZ AND RUNWAY EXTENSION. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | Region B |  | O | RIGHT-OF-WAY | 397000
AV-5805 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR RUNWAY EXTENSION AND ROADWAY RELOCATION. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | Region B |  | T | RIGHT-OF-WAY | 300000
AV-5805 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR RUNWAY EXTENSION AND ROADWAY RELOCATION. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDS ARE AIRPORT FUNDS. | Region B |  | O | RIGHT-OF-WAY | 61000
AV-5806 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | OTHER FUNDS ARE AIRPORT FUNDS | Region B |  | T | ENGINEERING | 300000 | FY 2025: 300000
AV-5806 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | OTHER FUNDS ARE AIRPORT FUNDS | Region B |  | T | CONSTRUCTION | 300000 | FY 2026: 300000
AV-5806 | Aviation | STI (Prioritization) | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | OTHER FUNDS ARE AIRPORT FUNDS | Region B |  | O | CONSTRUCTION | 12580000 | FY 2026: 12580000
AV-5811 | Aviation | STI (Prioritization) | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | EXTEND RUNWAY TO 5500 FEET. |  | WAYNE | 4 | Eastern Carolina RPO |  | Division 4 |  | T | CONSTRUCTION | 1200000 | FY 2029: 1200000
AV-5812 | Aviation | STI (Prioritization) | HYDE COUNTY AIRPORT (7W6) | EXTEND RUNWAY TO 5000 FEET. |  | HYDE | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | T | CONSTRUCTION | 1800000
AV-5815 | Aviation | STI (Prioritization) | HENDERSON FIELD (ACZ) | APRON EXPANSION. |  | PENDER | 3 | Cape Fear RPO |  | Division 3 |  | T | CONSTRUCTION | 6100000 | FY 2027: 4100000; FY 2028: 2000000
AV-5817 | Aviation | STI (Prioritization) | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBBING LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. |  | STANLY | 10 | Rocky River RPO |  | Division 10 |  | T | RIGHT-OF-WAY | 4400000 | FY 2030: 2200000; FY 2031: 2200000
AV-5817 | Aviation | STI (Prioritization) | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBBING LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. |  | STANLY | 10 | Rocky River RPO |  | Division 10 |  | T | CONSTRUCTION | 2500000 | FY 2032: 2500000
AV-5818 | Aviation | STI (Prioritization) | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). |  | PERSON | 5 | Kerr-Tar RPO |  | Division 5 |  | T | CONSTRUCTION | 15200000 | FY 2026: 6000000; FY 2027: 6000000; FY 2028: 3200000
AV-5819 | Aviation | STI (Prioritization) | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. |  | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | T | RIGHT-OF-WAY | 3100000 | FY 2026: 3100000
AV-5819 | Aviation | STI (Prioritization) | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. |  | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | T | CONSTRUCTION | 22700000 | FY 2031: 5675000; FY 2032: 5675000; FY 2033: 5675000; FY 2034: 5675000
AV-5822 | Aviation | STI (Prioritization) | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | CONSTRUCT TAXI LANE AND PREPARATION FOR ADDITIONAL T-HANGARS. |  | HALIFAX | 4 | Peanut Belt RPO |  | Division 4 |  | T | CONSTRUCTION | 1400000 | FY 2025: 490000
AV-5823 | Aviation | STI (Prioritization) | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | REHABILITATE RUNWAY. |  | SAMPSON | 3 | Mid-Carolina RPO |  | Division 3 |  | T | ENGINEERING | 232000
AV-5823 | Aviation | STI (Prioritization) | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | REHABILITATE RUNWAY. |  | SAMPSON | 3 | Mid-Carolina RPO |  | Division 3 |  | T | CONSTRUCTION | 2200000 | FY 2025: 2200000
AV-5826 | Aviation | STI (Prioritization) | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. |  | BLADEN | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | ENGINEERING | 920000 | FY 2032: 920000
AV-5826 | Aviation | STI (Prioritization) | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. |  | BLADEN | 6 | Mid-Carolina RPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9200000
AV-5831 | Aviation | STI (Prioritization) | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE AND STRENGTHEN RUNWAY TO ACCOMMODATE LARGER PRIVATE AIRCRAFT. |  | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. TO BE LET WITH AV-5900. | Division 9 |  | T | CONSTRUCTION | 14551000
AV-5832 | Aviation | STI (Prioritization) | SMITH REYNOLDS AIRPORT (INT) | CONSTRUCT NEW TAXILANE. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | T | CONSTRUCTION | 15700000 | FY 2027: 2000000; FY 2028: 7000000; FY 2029: 6700000
AV-5833 | Aviation | STI (Prioritization) | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. |  | HALIFAX | 4 | Peanut Belt RPO |  | Division 4 |  | T | ENGINEERING | 221000 | FY 2025: 221000
AV-5833 | Aviation | STI (Prioritization) | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. |  | HALIFAX | 4 | Peanut Belt RPO |  | Division 4 |  | T | CONSTRUCTION | 2500000 | FY 2026: 2500000
AV-5848 | Aviation | STI (Prioritization) | ASHE COUNTY AIRPORT (GEV) | CONSTRUCT APRON EXPANSONS. |  | ASHE | 11 | High Country RPO | UNDER CONSTRUCTION. | Division 11 |  | T | CONSTRUCTION | 2700000
AV-5850 | Aviation | STI (Prioritization) | MACON COUNTY AIRPORT | EXTEND RUNWAY. |  | MACON | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 166000
AV-5850 | Aviation | STI (Prioritization) | MACON COUNTY AIRPORT | EXTEND RUNWAY. |  | MACON | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4834000
AV-5851 | Aviation | STI (Prioritization) | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | CONSTRUCT 100 FT PAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | T | CONSTRUCTION | 2080000 | FY 2029: 2080000
AV-5853 | Aviation | STI (Prioritization) | RICHMOND COUNTY AIRPORT (RCZ) | CONSTRUCT EAST RAMP EXPANSION. |  | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | T | CONSTRUCTION | 2000000 | FY 2025: 1600000; FY 2026: 400000
AV-5855 | Aviation | STI (Prioritization) | MOORE COUNTY AIRPORT (SOP) | CONSTRUCT HANGAR TAXIWAYS AND INTERNAL AIRFIELD SERVICE ROAD. |  | MOORE | 8 | Sandhills MPO | UNDER CONSTRUCTION | Division 8 |  | T | CONSTRUCTION | 2900000
AV-5859 | Aviation | STI (Prioritization) | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | CONSTRUCT GENERAL AVIATION APRON AND AIRCRAFT STORAGE HANGARS. |  | SURRY | 11 | Northwest Piedmont RPO | COMPLETE. | Division 11 |  | T | CONSTRUCTION | 4000000
AV-5879 | Aviation | STI (Prioritization) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Statewide Mobility |  | T | CONSTRUCTION | 500000 | FY 2025: 500000
AV-5879 | Aviation | STI (Prioritization) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Statewide Mobility |  | O | CONSTRUCTION | 607000000 | FY 2025: 607000000
AV-5881 | Aviation | STI (Prioritization) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND WEST RAMP NEAR CONCOURSE A - PHASE II. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Statewide Mobility |  | T | CONSTRUCTION | 500000
AV-5881 | Aviation | STI (Prioritization) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND WEST RAMP NEAR CONCOURSE A - PHASE II. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Statewide Mobility |  | O | CONSTRUCTION | 39600000
AV-5885 | Aviation | STI (Prioritization) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | T | CONSTRUCTION | 500000 | FY 2027: 500000
AV-5885 | Aviation | STI (Prioritization) | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | OTHER FUNDS PROVIDED BY ILM. | Statewide Mobility |  | O | CONSTRUCTION | 7000000 | FY 2027: 7000000
AV-5890 | Aviation | STI (Prioritization) | CONCORD REGIONAL AIRPORT (JQF) | REHABILITATE APRON AND TAXIWAY PAVEMENT. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. | Region E |  | T | CONSTRUCTION | 300000
AV-5892 | Aviation | STI (Prioritization) | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT | Region E |  | T | CONSTRUCTION | 300000
AV-5892 | Aviation | STI (Prioritization) | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT | Region E |  | O | CONSTRUCTION | 1870000
AV-5893 | Aviation | STI (Prioritization) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). |  | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Region E |  | T | CONSTRUCTION | 500000 | FY 2025: 500000
AV-5893 | Aviation | STI (Prioritization) | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). |  | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT | Region E |  | O | CONSTRUCTION | 202000000 | FY 2025: 202000000
AV-5894 | Aviation | STI (Prioritization) | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. |  | WILKES | 11 | High Country RPO |  | Division 11 |  | T | RIGHT-OF-WAY | 600000 | FY 2025: 600000
AV-5894 | Aviation | STI (Prioritization) | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. |  | WILKES | 11 | High Country RPO |  | Division 11 |  | T | CONSTRUCTION | 12300000 | FY 2027: 3000000; FY 2028: 6000000; FY 2029: 3300000
AV-5896 | Aviation | STI (Prioritization) | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5610000
AV-5896 | Aviation | STI (Prioritization) | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 3725000
AV-5898 | Aviation | STI (Prioritization) | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | CONSTRUCT T-HANGAR TAXILANES FOR ADDITION OF T-HANGARS. |  | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | T | CONSTRUCTION | 810000
AV-5899 | Aviation | STI (Prioritization) | RALEIGH EXECUTIVE JETPORT (TTA) | RUNWAY 21 AND RUNWAY 3 BYPASS TAXIWAY. CONSTRUCT AIRPLANE RUN-UP LANE AT EACH END OF TAXIWAY. |  | LEE | 8 | Central Pines RPO |  | Division 8 |  | T | CONSTRUCTION | 2600000 | FY 2025: 2340000
AV-5900 | Aviation | STI (Prioritization) | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE TAXIWAY AND APRON. |  | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION, LET WITH AV-5831. FUNDING SHOWN UNDER PROJECT AV-5831 | Division 9
B-2500 | Highway | Pre-STI (Historic) | NC 12 | REPLACE BRIDGE 270011 (HERBERT C. BONNER BRIDGE) OVER OREGON INLET AND NC 12 IMPROVEMENTS. | 2.7 | DARE | 1 | Albemarle RPO |  | Pre-STI (Transition)
B-2500AB | Highway | Pre-STI (Historic) | NC 12 | PHASE II, SHORT-TERM IMPROVEMENTS AT PEA ISLAND. |  | DARE | 1 | Albemarle RPO | COMPLETED. | Pre-STI (Transition)
B-2500B | Highway | Transition | NC 12 | PHASE II, LONG-TERM IMPROVEMENTS AT RODANTHE. |  | DARE | 1 | Albemarle RPO | COMPLETED. | Pre-STI (Transition) |  | BGLT5 | CONSTRUCTION | 1300000
B-3159 | Highway | Transition | NC 8 | REPLACE BRIDGE 280027 OVER US 29 / US 64 / US 70 / I-85 BUSINESS IN LEXINGTON. | 0.25 | DAVIDSON | 9 | High Point Urban Area MPO | COMPLETE | Region D
B-3186 | Highway | Bridges | US 23/US 74 | REPLACE BRIDGE 430155, AND BRIDGE 430158 OVER RICHLAND CREEK. | 0.25 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-5898. | Statewide Mobility |  | BG5T50 | RIGHT-OF-WAY | 800000
B-3186 | Highway | Bridges | US 23/US 74 | REPLACE BRIDGE 430155, AND BRIDGE 430158 OVER RICHLAND CREEK. | 0.25 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-5898. | Statewide Mobility |  | BG5T50 | CONSTRUCTION | 29145000
B-4069 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 190159 OVER HANGING DOG CREEK. | 0.25 | CHEROKEE | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 295000 | FY 2025: 295000
B-4069 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 190159 OVER HANGING DOG CREEK. | 0.25 | CHEROKEE | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1800000 | FY 2027: 1800000
B-4182 | Highway | Bridges | SR 1503 (LAUREL VALLEY) | REPLACE BRIDGE 560246 OVER LAUREL CREEK. | 0.25 | MADISON | 13 | French Broad River MPO, Land-of-Sky RPO | CONSTRUCTION FUNDED WITH STATE LEGISLATIVE BRIDGE PROGRAM FUNDS (17BP.13.R.105) | Division 13
B-4410 | Highway | Bridges | SR 1627 (PINKSTON RIVER ROAD) | REPLACE BRIDGE 030307 OVER WSSB RAILROAD. | 0.25 | ANSON | 10 | Rocky River RPO | UNDER CONSTRUCTION. LOCAL FUNDING PROVIDED BY TOWN OF ANSONVILLE
B-4410A | Highway | Bridges | SR 1627 (PINKSTON RIVER ROAD) | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. |  | ANSON | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | T | RIGHT-OF-WAY | 25000
B-4410A | Highway | Bridges | SR 1627 (PINKSTON RIVER ROAD) | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. |  | ANSON | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | T | CONSTRUCTION | 945000
B-4410A | Highway | Bridges | SR 1627 (PINKSTON RIVER ROAD) | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. |  | ANSON | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | L | CONSTRUCTION | 68000
B-4439 | Highway | Bridges | SR 1342 (MAKATOKA ROAD NORTHWEST) | REPLACE BRIDGE 090100 OVER MUDDY BRANCH. | 0.25 | BRUNSWICK | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 550000
B-4439 | Highway | Bridges | SR 1342 (MAKATOKA ROAD NORTHWEST) | REPLACE BRIDGE 090100 OVER MUDDY BRANCH. | 0.25 | BRUNSWICK | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 1250000
B-4442 | Highway | Bridges | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100370, AND BRIDGE 100373 OVER REEMS CREEK. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | Statewide Mobility |  | NHPB | RIGHT-OF-WAY | 400000
B-4442 | Highway | Bridges | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100370, AND BRIDGE 100373 OVER REEMS CREEK. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH A-0010 A, UNDER CONSTRUCTION. | Statewide Mobility |  | NHPB | CONSTRUCTION | 29996000 | FY 2025: 7935000
B-4443 | Highway | Bridges | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 700000 | FY 2025: 700000
B-4443 | Highway | Bridges | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | BFP | UTILITIES | 700000 | FY 2025: 700000
B-4443 | Highway | Bridges | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH A-0010A | Statewide Mobility |  | BFP | CONSTRUCTION | 50100000 | FY 2029: 10020000; FY 2030: 21042000; FY 2031: 14529000; FY 2032: 4509000
B-4444 | Highway | Bridges | US 19/23/25/70 | REHABILITATE DECK ON BRIDGE 100353 OVER SR 1882. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | COORDINATE WITH A-0010A. | Statewide Mobility
B-4484 | Highway | Bridges | ROAD) SR 1470 (MAPLE CYPRESS | REPLACE BRIDGE 240138 AND 240139 OVER NEUSE RIVER. | 0.25 | CRAVEN | 2 | Down East RPO | UNDER CONSTRUCTION. | Division 2 |  | T | CONSTRUCTION | 18700000
B-4491 | Highway | Bridges | NC 59 | REPLACE BRIDGE 250022 OVER I-95 BUSINESS/US 301. | 0.25 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Region C |  | NHPB | CONSTRUCTION | 3533000
B-4562 | Highway | Bridges | SR 2143 (BEULAHTOWN ROAD) | REPLACE BRIDGE 500216 OVER LITTLE BUFFALO CREEK. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. | Division 4
B-4566 | Highway | Bridges | NC 903 | REPLACE BRIDGE 530045 OVER NEUSE RIVER. | 0.25 | LENOIR | 2 | Eastern Carolina RPO |  | Region B |  | BFP | RIGHT-OF-WAY | 262000 | FY 2026: 262000
B-4566 | Highway | Bridges | NC 903 | REPLACE BRIDGE 530045 OVER NEUSE RIVER. | 0.25 | LENOIR | 2 | Eastern Carolina RPO |  | Region B |  | BFP | UTILITIES | 129000 | FY 2026: 129000
B-4566 | Highway | Bridges | NC 903 | REPLACE BRIDGE 530045 OVER NEUSE RIVER. | 0.25 | LENOIR | 2 | Eastern Carolina RPO |  | Region B |  | BFP | CONSTRUCTION | 6500000 | FY 2028: 3250000; FY 2029: 3250000
B-4593 | Highway | Bridges | NC 55 | REPLACE BRIDGE 680038 OVER TRENT CREEK. | 0.25 | PAMLICO | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | NHPB | CONSTRUCTION | 6137000
B-4635 | Highway | Bridges | US 13 | REPLACE BRIDGE 810009 OVER SOUTH RIVER OVERFLOW. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 2250000
B-4636 | Highway | Bridges | NC 24 | REPLACE BRIDGE 810056 OVER SIX RUNS CREEK. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HFB | RIGHT-OF-WAY | 390000
B-4636 | Highway | Bridges | NC 24 | REPLACE BRIDGE 810056 OVER SIX RUNS CREEK. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | CONSTRUCTION | 9900000 | FY 2029: 1782000; FY 2030: 6336000; FY 2031: 1782000
B-4654 | Highway | Bridges | NC 50 | REPLACE BRIDGE 910069 OVER US 70 IN GARNER. | 0.25 | WAKE | 5 | Capital Area MPO |  | Region C |  | BFP | CONSTRUCTION | 9000000 | FY 2025: 8100000
B-4676A | Highway | Bridges | SR 1001 (OAKWOODS ROAD) | REPLACE BRIDGE 960029 OVER CUB CREEK. |  | WILKES | 11 | High Country RPO | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM | Division 11 |  | BGOFF | CONSTRUCTION | 8000000 | FY 2026: 3200000; FY 2027: 3200000; FY 2028: 1600000
B-4722 | Highway | Bridges | US 70 | REPLACE BRIDGE 150033 OVER NORTH RIVER AND REPAIRS TO EXISTING STRUCTURE TO SERVE AS DETOUR. | 0.25 | CARTERET | 2 | Down East RPO |  | Region B
B-4722B | Highway | Transition | US 70 | REPLACEMENT OF BRIDGE NO. 33 OVER NORTH RIVER. |  | CARTERET | 2 | Down East RPO | COMPLETED. | Region B
B-4786 | Highway | Bridges | US 13 | REPLACE BRIDGE 730038 OVER TAR RIVER IN GREENVILLE. | 0.25 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | NHPB | CONSTRUCTION | 9700000
B-4844 | Highway | Bridges | SR 1958 (BENNETTS BRIDGE ROAD) | REPLACE BRIDGE 950117 OVER NE CAPE FEAR RIVER. | 0.25 | WAYNE | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Highway Fund |  | HFB | CONSTRUCTION | 1200000
B-4863 | Highway | Bridges | SR 1335 (ISLAND ROAD) | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | 0.75 | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | Division 2 |  | T | BUILD NC CON | 21240000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000 | 1416000
B-4863 | Highway | Bridges | SR 1335 (ISLAND ROAD) | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | 0.75 | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | Division 2 |  | DP | CONSTRUCTION | 1000000
B-4863 | Highway | Bridges | SR 1335 (ISLAND ROAD) | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | 0.75 | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS. | Division 2 |  | T | CONSTRUCTION | 51495000 | FY 2025: 5998000
B-4931 | Highway | Bridges | US 258 | REPLACE BRIDGE 320022 OVER TOWN CREEK. | 0.25 | EDGECOMBE | 4 | Upper Coastal Plain RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 2129000
B-4933 | Highway | Bridges | NC 33 | REPLACE BRIDGE 320080 OVER TAR RIVER. REPLACE BRIDGE 320049 OVER TAR RIVER OVERFLOW. | 0.25 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Region A |  | BFP | RIGHT-OF-WAY | 860000 | FY 2025: 60000; FY 2026: 800000
B-4933 | Highway | Bridges | NC 33 | REPLACE BRIDGE 320080 OVER TAR RIVER. REPLACE BRIDGE 320049 OVER TAR RIVER OVERFLOW. | 0.25 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Region A |  | BFP | CONSTRUCTION | 16100000 | FY 2028: 5474000; FY 2029: 6762000; FY 2030: 3864000
B-4937 | Highway | Bridges | I-95 | REPLACE BRIDGE 500118 AND 500119 OVER CSX RAILROAD. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 9399000 |  |  | 334000 | 2005000 | 2005000 | 2005000 | 1170000 | 940000 | 940000
B-4937 | Highway | Bridges | I-95 | REPLACE BRIDGE 500118 AND 500119 OVER CSX RAILROAD. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | T | UTILITIES | 300000 | FY 2027: 300000
B-4937 | Highway | Bridges | I-95 | REPLACE BRIDGE 500118 AND 500119 OVER CSX RAILROAD. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | T | CONSTRUCTION | 34400000 | FY 2031: 8600000; FY 2032: 17200000; FY 2033: 8600000
B-4958 | Highway | Bridges | SR 2128 (BUNCH ROAD) | REPLACE BRIDGE 400106 OVER REEDY FORK CREEK IN OAK RIDGE. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7
B-4960 | Highway | Transition | SR 3058 (JUDGE ADAMS ROAD) | REPLACE BRIDGE 400214 OVER LITTLE ALAMANCE CREEK. | 0.25 | GUILFORD | 7 | Burlington-Graham MPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7
B-4977 | Highway | Bridges | SR 1313 | REPLACE BRIDGE 960075 OVER FISH DAM CREEK. | 0.25 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | Highway Fund |  | HFB | CONSTRUCTION | 700000
B-4979 | Highway | Bridges | US 21 BUS | REPLACE BRIDGE 980059 OVER JONESVILLE CREEK. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT. | Highway Fund |  | HFB | CONSTRUCTION | 1600000
B-5003 | Highway | Transition | COMMONWEALTH AVENUE | REPLACE BRIDGE 820081 OVER LEITH CREEK WITH CULVERT IN LAURINBURG. | 0.25 | SCOTLAND | 8 | Lumber River RPO | UNDER CONSTRUCTION BY CITY OF LAURINBURG - MUNICIPAL BRIDGE | Pre-STI (Transition)
B-5007 | Highway | Municipal Bridge | WEST FIRST STREET | REPLACE BRIDGE 330296 OVER NORFOLK SOUTHERN RAILWAY IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | RIGHT-OF-WAY | 600000
B-5007 | Highway | Municipal Bridge | WEST FIRST STREET | REPLACE BRIDGE 330296 OVER NORFOLK SOUTHERN RAILWAY IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | CONSTRUCTION | 6100000 | FY 2025: 6100000
B-5013 | Highway | Municipal Bridge | WAYNESVILLE (DEPOT STREET) | REPLACE BRIDGE 430262 OVER RICHLAND CREEK. | 0.25 | HAYWOOD | 14 | French Broad River MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY THE TOWN OF WAYNESVILLE - MUNICIPAL BRIDGE | Division 14
B-5121 | Highway | Bridges | US 70/US 401/NC 50 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910227 OVER PEACE STREET AND BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH AND REVISE INTERCHANGE AT PEACE STREET. | 0.25 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; PARTICIPATION BY CITY OF RALEIGH; INCLUDES B-5317 | Region C |  | BGDA | CONSTRUCTION | 5230000
B-5121 | Highway | Bridges | US 70/US 401/NC 50 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910227 OVER PEACE STREET AND BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH AND REVISE INTERCHANGE AT PEACE STREET. | 0.25 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; PARTICIPATION BY CITY OF RALEIGH; INCLUDES B-5317 | Region C |  | L | CONSTRUCTION | 1222000
B-5121 | Highway | Bridges | US 70/US 401/NC 50 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910227 OVER PEACE STREET AND BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH AND REVISE INTERCHANGE AT PEACE STREET. | 0.25 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; PARTICIPATION BY CITY OF RALEIGH; INCLUDES B-5317 | Region C |  | L(M) | CONSTRUCTION | 1308000
B-5123 | Highway | Bridges | US 29 | REPLACE BRIDGE 120014 AND 120019 OVER ROCKY RIVER AND ACCESS ROAD. | 0.322 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE | Region E
B-5130 | Highway | Bridges | SR 1321 (AVENT FERRY ROAD) | REPLACE BRIDGE 910318 OVER LAKE JOHNSON IN RALEIGH. | 0.25 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BFP | CONSTRUCTION | 3650000 | FY 2029: 2040000; FY 2030: 1610000
B-5136 | Highway | Transition | US 29/US 601 | REPLACE BRIDGE 120066 AND BRIDGE 120069 OVER SOUTHERN RAILROAD. | 0.25 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Region E |  | T | BUILD NC CON | 2790000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000 | 186000
B-5196 | Highway | Transition | MONTREAT (TEXAS ROAD) | REPLACE BRIDGE 100528 OVER FLAT CREEK. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | MUNICIPAL BRIDGE - COMPLETE | Division 13
B-5210 | Highway | Bridges | SR 1600 (EAST RIVER ROAD) | REPLACE BRIDGE 340076 OVER SYCAMORE CREEK. | 0.25 | FRANKLIN | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION - BRIDGE PURCHASE ORDER CONTRACT (BPOC) | Division 5
B-5237 | Highway | Transition | SR 2703 (NEW BETHEL CHURCH ROAD) | REPLACE BRIDGE 910248 OVER MAHLER'S CREEK IN GARNER. | 0.25 | WAKE | 5 | Capital Area MPO | BUILD NC BONDS: $2.0 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 5 |  | T | BUILD NC CON | 2000000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 138000
B-5310 | Highway | Bridges | SR 1817 (BRADSHAW ROAD) | REPLACE BRIDGE 810188 OVER WARD SWAMP. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 100000
B-5310 | Highway | Bridges | SR 1817 (BRADSHAW ROAD) | REPLACE BRIDGE 810188 OVER WARD SWAMP. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | CONSTRUCTION | 1850000 | FY 2025: 1425000
B-5318 | Highway | Bridges | SR 2044 (LIGON MILL ROAD) | REPLACE BRIDGE 910126 OVER SMITHS CREEK IN WAKE FOREST. | 0.25 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BFP | CONSTRUCTION | 11000000 | FY 2025: 2091000
B-5323 | Highway | Bridges | SR 1442 (DAVE WINSTON ROAD) | REPLACE BRIDGE 380143 OVER JOHNSON CREEK. | 0.25 | GRANVILLE | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Division 5 |  | BFPOFF | CONSTRUCTION | 4183000
B-5356 | Highway | Bridges | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | REPLACE BRIDGE 400299 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965 | Statewide Mobility |  | BFP | CONSTRUCTION | 11700000 | FY 2029: 6450000; FY 2030: 4201000; FY 2031: 1049000
B-5375 | Highway | Bridges | SR 1132 (MIAMI CHURCH ROAD) | REPLACE BRIDGE 120137 OVER DUTCH BUFFALO CREEK. | 0.25 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | Division 10 |  | BGOFF | CONSTRUCTION | 1573000
B-5376 | Highway | Bridges | SR 1681 (OLD CAMDEN ROAD) | REPLACE BRIDGE 890021 OVER STEWART'S CREEK. | 0.25 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | BGOFF | RIGHT-OF-WAY | 210000
B-5376 | Highway | Bridges | SR 1681 (OLD CAMDEN ROAD) | REPLACE BRIDGE 890021 OVER STEWART'S CREEK. | 0.25 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | BGOFF | CONSTRUCTION | 3000000 | FY 2028: 2250000; FY 2029: 750000
B-5503 | Highway | Bridges | SR 1142 (PRISON CAMP ROAD) | REPLACE BRIDGE 570053 OVER COLLIE SWAMP. | 0.25 | MARTIN | 1 | Mid-East RPO | COMPLETED. | Division 1
B-5541 | Highway | Bridges | I-40 | REPLACE BRIDGE 430236 OVER SR 1513. | 0.25 | HAYWOOD | 14 | French Broad River MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. | Highway Fund
B-5546 | Highway | Bridges | SR 2481 (LOW BRIDGE ROAD) | REPLACE BRIDGE 750307 OVER MOUNT PLEASANT CREEK. | 0.25 | RANDOLPH | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - LET WITH B-5360; CONSTRUCTION COST IS INCLUDED IN THAT PROJECT | Highway Fund
B-5550 | Highway | Municipal Bridge | BREVARD | REPLACE BRIDGE 870102 ON RAILROAD AVENUE OVER KINGS CREEK. | 0.25 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF BREVARD | Division 14 |  | BFPOFF | CONSTRUCTION | 1586000
B-5606 | Highway | Bridges | SR 1338 (WYNNE FORK ROAD) | REPLACE BRIDGE 710011 OVER RACOON CREEK. | 0.25 | PERQUIMANS | 1 | Albemarle RPO | COMPLETED. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE). | Division 1 |  | T | BUILD NC CON | 1545000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000 | 103000
B-5610 | Highway | Bridges | NC 12 | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS. | 0.25 | DARE | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | NHPB | RIGHT-OF-WAY | 520000
B-5610 | Highway | Bridges | NC 12 | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS. | 0.25 | DARE | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | NHPB | UTILITIES | 460000
B-5610 | Highway | Bridges | NC 12 | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS. | 0.25 | DARE | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | BGLT5 | CONSTRUCTION | 5220000 | FY 2025: 3360000; FY 2026: 384000
B-5612 | Highway | Bridges | NC 222 | REPLACE BRIDGE 730024 OVER TAR RIVER. | 0.25 | PITT | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | RIGHT-OF-WAY | 950000 | FY 2027: 950000
B-5612 | Highway | Bridges | NC 222 | REPLACE BRIDGE 730024 OVER TAR RIVER. | 0.25 | PITT | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Region B |  | T | CONSTRUCTION | 14000000 | FY 2029: 6028000; FY 2030: 5540000; FY 2031: 2432000
B-5614 | Highway | Bridges | SR 1112 (MOUTH OF THE CREEK ROAD) | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | 0.25 | BEAUFORT | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BGOFF | RIGHT-OF-WAY | 319000
B-5614 | Highway | Bridges | SR 1112 (MOUTH OF THE CREEK ROAD) | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | 0.25 | BEAUFORT | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BGOFF | UTILITIES | 750000
B-5614 | Highway | Bridges | SR 1112 (MOUTH OF THE CREEK ROAD) | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | 0.25 | BEAUFORT | 2 | Mid-East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | BGOFF | CONSTRUCTION | 17200000 | FY 2025: 3612000; FY 2026: 8772000; FY 2027: 4816000
B-5619 | Highway | Bridges | SR 1389 (HARDY BRIDGE ROAD) | REPLACE BRIDGE 530052 OVER NEUSE RIVER AND 530152 OVER NEUSE RIVER OVERFLOW. | 0.25 | LENOIR | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 2 |  | BGOFF | RIGHT-OF-WAY | 500000
B-5619 | Highway | Bridges | SR 1389 (HARDY BRIDGE ROAD) | REPLACE BRIDGE 530052 OVER NEUSE RIVER AND 530152 OVER NEUSE RIVER OVERFLOW. | 0.25 | LENOIR | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 2 |  | BGOFF | CONSTRUCTION | 9170000
B-5621 | Highway | Bridges | SR 1904 (PINE RIDGE ROAD) | REPLACE BRIDGE 810248 OVER SIX RUNS CREEK. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 154000
B-5621 | Highway | Bridges | SR 1904 (PINE RIDGE ROAD) | REPLACE BRIDGE 810248 OVER SIX RUNS CREEK. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 2500000
B-5629 | Highway | Bridges | SR 1515 (OLD MILL CREEK ROAD SE) | REPLACE BRIDGE 090040 OVER MILL CREEK. | 0.25 | BRUNSWICK | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 115000
B-5629 | Highway | Bridges | SR 1515 (OLD MILL CREEK ROAD SE) | REPLACE BRIDGE 090040 OVER MILL CREEK. | 0.25 | BRUNSWICK | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 2759000
B-5632 | Highway | Bridges | SR 1828 (CYPRESS CREEK ROAD) | REPLACE BRIDGE 300187 OVER BACK SWAMP. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 190000
B-5632 | Highway | Bridges | SR 1828 (CYPRESS CREEK ROAD) | REPLACE BRIDGE 300187 OVER BACK SWAMP. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 5186000 | FY 2025: 1348000
B-5639 | Highway | Bridges | NC 11 | REPLACE BRIDGE 300036 OVER MAXWELL CREEK. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | RIGHT-OF-WAY | 56000
B-5639 | Highway | Bridges | NC 11 | REPLACE BRIDGE 300036 OVER MAXWELL CREEK. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 3422000
B-5647 | Highway | Bridges | SR 1135 (PROVIDENCE CHURCH ROAD) | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 60000
B-5647 | Highway | Bridges | SR 1135 (PROVIDENCE CHURCH ROAD) | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | UTILITIES | 25000
B-5647 | Highway | Bridges | SR 1135 (PROVIDENCE CHURCH ROAD) | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | RIGHT-OF-WAY IN PROGRESS. | Division 3 |  | BGOFF | CONSTRUCTION | 1750000 | FY 2025: 1128000
B-5655 | Highway | Bridges | NC 111 / NC 122 | REPLACE BRIDGE 320011 OVER TOWN CREEK. | 0.25 | EDGECOMBE | 4 | Upper Coastal Plain RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 1950000
B-5662 | Highway | Bridges | NC 561 | REPLACE BRIDGE 410093 OVER CONOCONNARA SWAMP. | 0.25 | HALIFAX | 4 | Peanut Belt RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 2581000
B-5664 | Highway | Bridges | SR 1555 (BARBOUR MILL ROAD) | REPLACE BRIDGE 500145 OVER SWIFT CREEK. | 0.25 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. | Division 4
B-5666 | Highway | Bridges | US 117 | REPLACE BRIDGE 970047 OVER SEABOARD COAST LINE RAILROAD. | 0.25 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 4469000
B-5671 | Highway | Bridges | NC 97 | REPLACE BRIDGE 320087 OVER SWIFT CREEK. | 0.25 | EDGECOMBE | 4 | Upper Coastal Plain RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 2279000
B-5673 | Highway | Bridges | SR 1630 (GREEN LEVEL CHURCH ROAD) | REPLACE BRIDGE 910061 OVER KIT CREEK IN CARY. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HFB | RIGHT-OF-WAY | 290000
B-5673 | Highway | Bridges | SR 1630 (GREEN LEVEL CHURCH ROAD) | REPLACE BRIDGE 910061 OVER KIT CREEK IN CARY. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HFB | CONSTRUCTION | 6600000 | FY 2029: 6600000
B-5674 | Highway | Bridges | US 15 / US 501 NORTHBOUND | REPLACE BRIDGE 310080 OVER SR 1308 (CORNWALLIS ROAD) IN DURHAM. | 0.25 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | BFP | RIGHT-OF-WAY | 700000 | FY 2026: 700000
B-5674 | Highway | Bridges | US 15 / US 501 NORTHBOUND | REPLACE BRIDGE 310080 OVER SR 1308 (CORNWALLIS ROAD) IN DURHAM. | 0.25 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | BFP | CONSTRUCTION | 5449000 | FY 2028: 54000; FY 2029: 3595000; FY 2030: 1800000
B-5684 | Highway | Bridges | US 401 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | 0.25 | WAKE | 5 | Capital Area MPO |  | Region C |  | BFP | RIGHT-OF-WAY | 6300000 | FY 2029: 3600000; FY 2030: 1440000; FY 2031: 630000; FY 2032: 630000
B-5684 | Highway | Bridges | US 401 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | 0.25 | WAKE | 5 | Capital Area MPO |  | Region C |  | BFP | UTILITIES | 380000 | FY 2029: 380000
B-5684 | Highway | Bridges | US 401 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | 0.25 | WAKE | 5 | Capital Area MPO |  | Region C |  | BFP | CONSTRUCTION | 11600000 | FY 2030: 4735000; FY 2031: 5055000; FY 2032: 1810000
B-5713 | Highway | Bridges | WILLOW ROAD | REPLACE BRIDGE 400352 OVER I-40 / BUSINESS 85 IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BFP | RIGHT-OF-WAY | 510000 | FY 2028: 116000; FY 2029: 100000; FY 2030: 100000; FY 2031: 97000; FY 2032: 97000
B-5713 | Highway | Bridges | WILLOW ROAD | REPLACE BRIDGE 400352 OVER I-40 / BUSINESS 85 IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BFP | CONSTRUCTION | 15200000 | FY 2031: 7600000; FY 2032: 6080000; FY 2033: 1520000
B-5715 | Highway | Bridges | SR 2351 (WITTY ROAD) | REPLACE BRIDGE 780017 OVER HAW RIVER. | 0.25 | ROCKINGHAM | 7 | Greensboro Urban Area MPO, Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7
B-5716 | Highway | Bridges | SR 1138 (LINDSEY BRIDGE ROAD) | REPLACE BRIDGE 780140 OVER DAN RIVER. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGOFF | RIGHT-OF-WAY | 610000
B-5716 | Highway | Bridges | SR 1138 (LINDSEY BRIDGE ROAD) | REPLACE BRIDGE 780140 OVER DAN RIVER. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGOFF | CONSTRUCTION | 12299000 | FY 2025: 5640000; FY 2026: 4930000; FY 2027: 1729000
B-5717 | Highway | Bridges | SR 4240 (GATE CITY BOULEVARD) | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | Division 7 |  | HF | RIGHT-OF-WAY | 710000
B-5717 | Highway | Bridges | SR 4240 (GATE CITY BOULEVARD) | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | Division 7 |  | HF | UTILITIES | 165000
B-5717 | Highway | Bridges | SR 4240 (GATE CITY BOULEVARD) | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING | Division 7 |  | BFP | CONSTRUCTION | 8957000
B-5718 | Highway | Bridges | PATTON AVENUE | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  | BFP | RIGHT-OF-WAY | 218000 | FY 2027: 218000
B-5718 | Highway | Bridges | PATTON AVENUE | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  | BFP | UTILITIES | 74000 | FY 2027: 74000
B-5718 | Highway | Bridges | PATTON AVENUE | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | 0.25 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATEWITH I-5965 | Division 7 |  | BFP | CONSTRUCTION | 3350000 | FY 2028: 2636000; FY 2029: 714000
B-5721 | Highway | Bridges | SR 2177 (DAN VALLEY ROAD) | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | BGLT5 | RIGHT-OF-WAY | 188000
B-5721 | Highway | Bridges | SR 2177 (DAN VALLEY ROAD) | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | BGLT5 | UTILITIES | 336000
B-5721 | Highway | Bridges | SR 2177 (DAN VALLEY ROAD) | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | BGLT5 | CONSTRUCTION | 4853000 | FY 2025: 198000
B-5722 | Highway | Bridges | SR 1169 (ISLAND DRIVE) | REPLACE BRIDGE 780277 OVER BEAVER CREEK. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 200000
B-5722 | Highway | Bridges | SR 1169 (ISLAND DRIVE) | REPLACE BRIDGE 780277 OVER BEAVER CREEK. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2025: 502000; FY 2026: 1498000
B-5723 | Highway | Bridges | SR 1158 (JACKSON LAKE ROAD) | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | 0.25 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 30000 | FY 2030: 30000
B-5723 | Highway | Bridges | SR 1158 (JACKSON LAKE ROAD) | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | 0.25 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | BGOFF | UTILITIES | 570000 | FY 2030: 570000
B-5723 | Highway | Bridges | SR 1158 (JACKSON LAKE ROAD) | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | 0.25 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 2100000 | FY 2031: 2100000
B-5725 | Highway | Bridges | SR 1710 (GRIERS CHURCH ROAD) | REPLACE BRIDGE 160007 OVER HYCO CREEK. | 0.25 | CASWELL | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 30000 | FY 2030: 30000
B-5725 | Highway | Bridges | SR 1710 (GRIERS CHURCH ROAD) | REPLACE BRIDGE 160007 OVER HYCO CREEK. | 0.25 | CASWELL | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 1700000 | FY 2031: 850000; FY 2032: 850000
B-5770 | Highway | Bridges | SALISBURY RIDGE ROAD | REPLACE BRIDGE 330243 OVER NC 150 IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGOFF | CONSTRUCTION | 5501000
B-5770 | Highway | Bridges | SALISBURY RIDGE ROAD | REPLACE BRIDGE 330243 OVER NC 150 IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGOFF | CONSTRUCTION | 500000
B-5772 | Highway | Bridges | SR 1724 (HURLEY SCHOOL ROAD) | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | BGOFF | RIGHT-OF-WAY | 77000
B-5772 | Highway | Bridges | SR 1724 (HURLEY SCHOOL ROAD) | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | BGOFF | UTILITIES | 31000
B-5772 | Highway | Bridges | SR 1724 (HURLEY SCHOOL ROAD) | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | BGOFF | CONSTRUCTION | 3009000 | FY 2025: 1059000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | 0.25 | DAVIDSON | 9 | High Point Urban Area MPO |  | Region D |  | BFP | RIGHT-OF-WAY | 110000 | FY 2028: 110000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | 0.25 | DAVIDSON | 9 | High Point Urban Area MPO |  | Region D |  | BFP | UTILITIES | 350000 | FY 2028: 350000
B-5779 | Highway | Bridges | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | 0.25 | DAVIDSON | 9 | High Point Urban Area MPO |  | Region D |  | BFP | CONSTRUCTION | 11800000 | FY 2029: 3540000; FY 2030: 6136000; FY 2031: 2124000
B-5783 | Highway | Bridges | US 29 / US 70 / BUSINESS 85 | REPLACE BRIDGE 280164 AND BRIDGE 280168 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | BFP | CONSTRUCTION | 5778000 | FY 2025: 1619000
B-5808 | Highway | Bridges | US 29 US 601 | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | 0.25 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | Region E |  | NHPB | RIGHT-OF-WAY | 255000
B-5808 | Highway | Bridges | US 29 US 601 | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | 0.25 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | Region E |  | NHPB | UTILITIES | 1156000
B-5808 | Highway | Bridges | US 29 US 601 | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | 0.25 | CABARRUS | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. | Region E |  | BFP | CONSTRUCTION | 10100000 | FY 2025: 790000
B-5811 | Highway | Bridges | SR 1434 (ROGERS ROAD) | REPLACE BRIDGE 830042 OVER BIG BEAR CREEK. | 0.25 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | BGOFF | RIGHT-OF-WAY | 15000 | FY 2028: 15000
B-5811 | Highway | Bridges | SR 1434 (ROGERS ROAD) | REPLACE BRIDGE 830042 OVER BIG BEAR CREEK. | 0.25 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | BGOFF | CONSTRUCTION | 600000 | FY 2030: 600000
B-5825 | Highway | Bridges | NC 67 | REPLACE BRIDGE 980035 OVER YADKIN RIVER. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Region F |  | T | CONSTRUCTION | 12440000 | FY 2025: 275000
B-5831 | Highway | Bridges | I-77 NORTHBOUND | REPLACE BRIDGE 850006 OVER NC 268, NORFOLK SOUTHERN RAILROAD, AND THE YADKIN RIVER. | 0.25 | SURRY | 11 | Northwest Piedmont RPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 320000
B-5831 | Highway | Bridges | I-77 NORTHBOUND | REPLACE BRIDGE 850006 OVER NC 268, NORFOLK SOUTHERN RAILROAD, AND THE YADKIN RIVER. | 0.25 | SURRY | 11 | Northwest Piedmont RPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 24000000 | FY 2025: 2880000; FY 2026: 10080000; FY 2027: 7440000; FY 2028: 3600000
B-5832 | Highway | Bridges | SR 2080 (QUAKER CHURCH ROAD) | REPLACE BRIDGE 850152 OVER ARARAT RIVER. | 0.25 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGOFF | RIGHT-OF-WAY | 250000 | FY 2029: 250000
B-5832 | Highway | Bridges | SR 2080 (QUAKER CHURCH ROAD) | REPLACE BRIDGE 850152 OVER ARARAT RIVER. | 0.25 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGOFF | CONSTRUCTION | 4000000 | FY 2030: 2151000; FY 2031: 1849000
B-5833 | Highway | Bridges | US 21 BUSINESS | REPLACE BRIDGE 980029 OVER I-77. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | BFP | RIGHT-OF-WAY | 1800000 | FY 2025: 200000
B-5833 | Highway | Bridges | US 21 BUSINESS | REPLACE BRIDGE 980029 OVER I-77. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Region F |  | BFP | CONSTRUCTION | 17300000 | FY 2025: 5111000; FY 2026: 6850000; FY 2027: 4618000; FY 2028: 721000
B-5835 | Highway | Bridges | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO |  | Division 11 |  | BGOFF | RIGHT-OF-WAY | 150000 | FY 2025: 150000
B-5835 | Highway | Bridges | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO |  | Division 11 |  | BGOFF | UTILITIES | 160000 | FY 2025: 160000
B-5835 | Highway | Bridges | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO |  | Division 11 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2026: 1149000; FY 2027: 851000
B-5843 | Highway | Bridges | SR 2402 (HOOVER ROAD) | REPLACE BRIDGE 480020 OVER I-L CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | RIGHT-OF-WAY | 67000 | FY 2028: 67000
B-5843 | Highway | Bridges | SR 2402 (HOOVER ROAD) | REPLACE BRIDGE 480020 OVER I-L CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | CONSTRUCTION | 668000 | FY 2030: 352000; FY 2031: 316000
B-5843 | Highway | Bridges | SR 2402 (HOOVER ROAD) | REPLACE BRIDGE 480020 OVER I-L CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | CONSTRUCTION | 7000 | FY 2030: 4000; FY 2031: 3000
B-5846 | Highway | Bridges | SR 1892 (JENNINGS ROAD) | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGOFF | RIGHT-OF-WAY | 85000
B-5846 | Highway | Bridges | SR 1892 (JENNINGS ROAD) | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGOFF | UTILITIES | 325000
B-5846 | Highway | Bridges | SR 1892 (JENNINGS ROAD) | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Division 12 |  | BGOFF | CONSTRUCTION | 5495000
B-5847 | Highway | Bridges | SR 1709 (ROCK BARN ROAD) | REPLACE BRIDGE 170173 OVER I-40. | 0.25 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BFP | RIGHT-OF-WAY | 1400000 | FY 2025: 140000; FY 2026: 140000
B-5847 | Highway | Bridges | SR 1709 (ROCK BARN ROAD) | REPLACE BRIDGE 170173 OVER I-40. | 0.25 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BFP | CONSTRUCTION | 10300000 | FY 2030: 2022000; FY 2031: 4904000; FY 2032: 3374000
B-5858 | Highway | Bridges | SR 1607 (EASTRIDGE DRIVE) | REPLACE BRIDGE 220392 OVER BUFFALO CREEK. |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGOFF | RIGHT-OF-WAY | 20000 | FY 2027: 20000
B-5858 | Highway | Bridges | SR 1607 (EASTRIDGE DRIVE) | REPLACE BRIDGE 220392 OVER BUFFALO CREEK. |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGOFF | UTILITIES | 225000 | FY 2027: 225000
B-5858 | Highway | Bridges | SR 1607 (EASTRIDGE DRIVE) | REPLACE BRIDGE 220392 OVER BUFFALO CREEK. |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | BGOFF | CONSTRUCTION | 1500000 | FY 2029: 975000; FY 2030: 525000
B-5869 | Highway | Bridges | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 0.25 | BURKE | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  | BFP | RIGHT-OF-WAY | 640000
B-5869 | Highway | Bridges | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 0.25 | BURKE | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  | BGDA | RIGHT-OF-WAY | 2560000
B-5869 | Highway | Bridges | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 0.25 | BURKE | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  | BFP | UTILITIES | 270000
B-5869 | Highway | Bridges | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | 0.25 | BURKE | 13 | Greater Hickory MPO | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Region G |  | BFP | CONSTRUCTION | 25861000 | FY 2025: 6795000
B-5871 | Highway | Bridges | SR 1306 (BILLS CREEK ROAD) | REPLACE BRIDGE 800628 OVER LAKE LURE DAM AND BROAD RIVER. | 0.25 | RUTHERFORD | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 4600000 | FY 2025: 828000; FY 2026: 1104000; FY 2027: 1104000; FY 2028: 644000; FY 2029: 920000
B-5871 | Highway | Bridges | SR 1306 (BILLS CREEK ROAD) | REPLACE BRIDGE 800628 OVER LAKE LURE DAM AND BROAD RIVER. | 0.25 | RUTHERFORD | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGOFF | CONSTRUCTION | 20800000 | FY 2028: 3126000; FY 2029: 8462000; FY 2030: 6598000; FY 2031: 2614000
B-5898 | Highway | Bridges | US 23/ US 74 | REPLACE BRIDGE 430168 OVER US 19 AND US 23. | 0.25 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-3186. | Statewide Mobility |  | BG5T50 | RIGHT-OF-WAY | 150000
B-5898 | Highway | Bridges | US 23/ US 74 | REPLACE BRIDGE 430168 OVER US 19 AND US 23. | 0.25 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. TO BE LET WITH B-3186. | Statewide Mobility |  | BG5T50 | CONSTRUCTION | 20253000
B-5920 | Highway | Bridges | SR 1216 (STEEL BRIDGE ROAD) | REPLACE BRIDGE 430246 OVER WEST FORK PIGEON CREEK. | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 30000 | FY 2025: 30000
B-5920 | Highway | Bridges | SR 1216 (STEEL BRIDGE ROAD) | REPLACE BRIDGE 430246 OVER WEST FORK PIGEON CREEK. | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1800000 | FY 2026: 1173000; FY 2027: 627000
B-5921 | Highway | Bridges | SR 1120 (CEDAR CREEK ROAD) | REPLACE BRIDGE 490008 CEDAR CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 410000
B-5921 | Highway | Bridges | SR 1120 (CEDAR CREEK ROAD) | REPLACE BRIDGE 490008 CEDAR CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 400000 | FY 2026: 224000; FY 2027: 176000
B-5925 | Highway | Bridges | SR 1548 (OLD HIGHWAY 64) | REPLACE BRIDGE 190223 OVER HIWASSEE RIVER. | 0.25 | CHEROKEE | 14 | Southwestern RPO |  | Division 14 |  | BFP | RIGHT-OF-WAY | 660000 | FY 2025: 660000
B-5925 | Highway | Bridges | SR 1548 (OLD HIGHWAY 64) | REPLACE BRIDGE 190223 OVER HIWASSEE RIVER. | 0.25 | CHEROKEE | 14 | Southwestern RPO |  | Division 14 |  | BFP | UTILITIES | 320000 | FY 2025: 320000
B-5925 | Highway | Bridges | SR 1548 (OLD HIGHWAY 64) | REPLACE BRIDGE 190223 OVER HIWASSEE RIVER. | 0.25 | CHEROKEE | 14 | Southwestern RPO |  | Division 14 |  | BFP | CONSTRUCTION | 6500000 | FY 2026: 6500000
B-5929 | Highway | Municipal Bridge | TRACY GROVE ROAD | REPLACE BRIDGE 440350 OVER DEVILS FORK CREEK. | 0.25 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE | Division 14 |  | BGOFF | ENGINEERING | 125000 | FY 2025: 125000
B-5929 | Highway | Municipal Bridge | TRACY GROVE ROAD | REPLACE BRIDGE 440350 OVER DEVILS FORK CREEK. | 0.25 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE | Division 14 |  | BGOFF | CONSTRUCTION | 2100000 | FY 2025: 1522000; FY 2026: 578000
B-5930 | Highway | Municipal Bridge | SARDIS LANE | REPLACE BRIDGE 590433 OVER MCALPINE CREEK. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE | Division 10 |  | BGOFF | CONSTRUCTION | 1600000
B-5930 | Highway | Municipal Bridge | SARDIS LANE | REPLACE BRIDGE 590433 OVER MCALPINE CREEK. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | PROJECT ADMINISTERED BY CITY OF CHARLOTTE | Division 10 |  | L | CONSTRUCTION | 400000
B-5931 | Highway | Municipal Bridge | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | Division 10 |  | BGDA | ENGINEERING | 8000
B-5931 | Highway | Municipal Bridge | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | Division 10 |  | BGDA | ENGINEERING | 5000
B-5931 | Highway | Municipal Bridge | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | Division 10 |  | L | ENGINEERING | 5000
B-5931 | Highway | Municipal Bridge | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | Division 10 |  | L | ENGINEERING | 2000
B-5931 | Highway | Municipal Bridge | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | Division 10 |  | BGOFF | CONSTRUCTION | 2192000 | FY 2025: 2192000
B-5931 | Highway | Municipal Bridge | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | Division 10 |  | BGDA | CONSTRUCTION | 1732000 | FY 2025: 1732000
B-5931 | Highway | Municipal Bridge | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | Division 10 |  | L | CONSTRUCTION | 548000 | FY 2025: 548000
B-5931 | Highway | Municipal Bridge | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE. | Division 10 |  | L | CONSTRUCTION | 1732000 | FY 2025: 1732000
B-5937 | Highway | Bridges | US 158 | REHABILITATE BRIDGE 260016 OVER CURRITUCK SOUND. | 3.16 | CURRITUCK | 1 | Albemarle RPO | COMPLETED. | Statewide Mobility
B-5938 | Highway | Bridges | SR 1182 (ATLANTIC BEACH CAUSEWAY) | REHABILITATE BRIDGE 150068 OVER BOGUE SOUND. | 0.75 | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE) | Division 2 |  | T | BUILD NC CON | 6195000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000 | 413000
B-5938 | Highway | Bridges | SR 1182 (ATLANTIC BEACH CAUSEWAY) | REHABILITATE BRIDGE 150068 OVER BOGUE SOUND. | 0.75 | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE) | Division 2 |  | T | CONSTRUCTION | 1800000
B-5939 | Highway | Bridges | NC 58 | REHABILITATE BRIDGE 150006 OVER BOGUE SOUND. | 0.75 | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION | Region B |  | T | CONSTRUCTION | 3000000
B-5944 | Highway | Bridges | SR 1509 (QUEENS CREEK ROAD) | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | 0.25 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BFP | RIGHT-OF-WAY | 500000 | FY 2028: 500000
B-5944 | Highway | Bridges | SR 1509 (QUEENS CREEK ROAD) | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | 0.25 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BFP | UTILITIES | 1200000 | FY 2028: 1200000
B-5944 | Highway | Bridges | SR 1509 (QUEENS CREEK ROAD) | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | 0.25 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | BFP | CONSTRUCTION | 30100000 | FY 2030: 6622000; FY 2031: 16254000; FY 2032: 7224000
B-5947 | Highway | Bridges | NC 581 | REPLACE BRIDGE 630091 OVER TAR RIVER. | 0.25 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | NHPB | RIGHT-OF-WAY | 400000
B-5947 | Highway | Bridges | NC 581 | REPLACE BRIDGE 630091 OVER TAR RIVER. | 0.25 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | NHPB | UTILITIES | 138000
B-5947 | Highway | Bridges | NC 581 | REPLACE BRIDGE 630091 OVER TAR RIVER. | 0.25 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | NHPB | CONSTRUCTION | 7162000 | FY 2025: 1647000
B-5949 | Highway | Bridges | NC 200 | REPLACE BRIDGE 890053 OVER STEWARTS CREEK. | 0.25 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | BFP | RIGHT-OF-WAY | 120000 | FY 2025: 120000
B-5949 | Highway | Bridges | NC 200 | REPLACE BRIDGE 890053 OVER STEWARTS CREEK. | 0.25 | UNION | 10 | Charlotte Regional TPO |  | Region E |  | BFP | CONSTRUCTION | 5400000 | FY 2027: 54000; FY 2028: 4650000; FY 2029: 696000
B-5950 | Highway | Bridges | NC 67 (WESTBOUND SILAS CREEK PARKWAY) | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D |  | BFP | RIGHT-OF-WAY | 800000 | FY 2026: 800000
B-5950 | Highway | Bridges | NC 67 (WESTBOUND SILAS CREEK PARKWAY) | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D |  | BFP | UTILITIES | 3100000 | FY 2026: 3100000
B-5950 | Highway | Bridges | NC 67 (WESTBOUND SILAS CREEK PARKWAY) | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D |  | BFP | CONSTRUCTION | 8500000 | FY 2027: 1927000; FY 2028: 4571000; FY 2029: 2002000
B-5961 | Highway | Bridges | SR 1421 (MARYS GROVE ROAD) | REPLACE BRIDGE 350097 OVER UN-NAMED TRIBUTARY OF MUDDY FORK CREEK. | 0.25 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | BGOFF | RIGHT-OF-WAY | 67000
B-5961 | Highway | Bridges | SR 1421 (MARYS GROVE ROAD) | REPLACE BRIDGE 350097 OVER UN-NAMED TRIBUTARY OF MUDDY FORK CREEK. | 0.25 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | BGOFF | CONSTRUCTION | 705000
B-5971 | Highway | Bridges | SR 1149 (ELK SPUR STREET) | REPLACE BRIDGE 850387 OVER ELKIN CREEK. | 0.25 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGOFF | RIGHT-OF-WAY | 500000 | FY 2027: 500000
B-5971 | Highway | Bridges | SR 1149 (ELK SPUR STREET) | REPLACE BRIDGE 850387 OVER ELKIN CREEK. | 0.25 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGOFF | CONSTRUCTION | 6500000 | FY 2030: 65000; FY 2031: 4384000; FY 2032: 2051000
B-5976 | Highway | Bridges | SR 1400 (CUMNOCK ROAD) | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | RIGHT-OF-WAY | 210000 | FY 2025: 210000
B-5976 | Highway | Bridges | SR 1400 (CUMNOCK ROAD) | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | UTILITIES | 510000 | FY 2025: 510000
B-5976 | Highway | Bridges | SR 1400 (CUMNOCK ROAD) | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | CONSTRUCTION | 11500000 | FY 2028: 3229000; FY 2029: 6531000; FY 2030: 1740000
B-5979 | Highway | Municipal Bridge | HUNTING HILLS LANE | REPLACE BRIDGE NO. 940346 OVER SOUTH FORK OF NEW RIVER IN BOONE. | 0.25 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | BGOFF | CONSTRUCTION | 3440000 | FY 2025: 3440000
B-5979 | Highway | Municipal Bridge | HUNTING HILLS LANE | REPLACE BRIDGE NO. 940346 OVER SOUTH FORK OF NEW RIVER IN BOONE. | 0.25 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | L | CONSTRUCTION | 860000 | FY 2025: 860000
B-5980 | Highway | Bridges | SR 1522 (HALIFAX ROAD) | REPLACE BRIDGE 630203 OVER I-95. | 0.25 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | Statewide Mobility |  | NHPB | RIGHT-OF-WAY | 2100000
B-5980 | Highway | Bridges | SR 1522 (HALIFAX ROAD) | REPLACE BRIDGE 630203 OVER I-95. | 0.25 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039. | Statewide Mobility |  | NHPB | CONSTRUCTION | 18000000
B-5981 | Highway | Bridges | US 117 NBL | REPLACE BRIDGE 300016 OVER CSX RAILROAD. BRIDGE PRESERVATION OF BRIDGE 300017 OVER CSX. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | RIGHT OF WAY IN PROGRESS | Statewide Mobility |  | BGLT5 | RIGHT-OF-WAY | 443000
B-5981 | Highway | Bridges | US 117 NBL | REPLACE BRIDGE 300016 OVER CSX RAILROAD. BRIDGE PRESERVATION OF BRIDGE 300017 OVER CSX. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | RIGHT OF WAY IN PROGRESS | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 10866000 | FY 2025: 5107000; FY 2026: 652000
B-5985 | Highway | Bridges | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770125 AND 770175 OVER LUMBER RIVER. | 0.25 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | NHPB | RIGHT-OF-WAY | 395000
B-5985 | Highway | Bridges | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770125 AND 770175 OVER LUMBER RIVER. | 0.25 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | NHPB | UTILITIES | 485000
B-5985A | Highway | Bridges | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770125 OVER LUMBER RIVER. | 0.25 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | BFP | CONSTRUCTION | 7915000 | FY 2025: 2454000
B-5985B | Highway | Bridges | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770175 OVER LUMBER RIVER. | 0.25 | ROBESON | 6 | Lumber River RPO |  | Region C |  | BFP | CONSTRUCTION | 9000000 | FY 2025: 1980000; FY 2026: 5138000; FY 2027: 1882000
B-5986 | Highway | Bridges | NC 231 | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | 0.25 | WAKE | 5 | Capital Area MPO |  | Region C |  | HFB | RIGHT-OF-WAY | 1104000 | FY 2027: 1104000
B-5986 | Highway | Bridges | NC 231 | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | 0.25 | WAKE | 5 | Capital Area MPO |  | Region C |  | HFB | UTILITIES | 352000 | FY 2027: 352000
B-5986 | Highway | Bridges | NC 231 | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | 0.25 | WAKE | 5 | Capital Area MPO |  | Region C |  | BFP | CONSTRUCTION | 5300000 | FY 2028: 53000; FY 2029: 3496000; FY 2030: 1751000
B-5987 | Highway | Bridges | US 401 | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | 0.25 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | Region C |  | NHPB | RIGHT-OF-WAY | 640000 | FY 2026: 640000
B-5987 | Highway | Bridges | US 401 | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | 0.25 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | Region C |  | NHPB | UTILITIES | 640000 | FY 2026: 640000
B-5987 | Highway | Bridges | US 401 | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | 0.25 | WAKE | 5 | Capital Area MPO | RIGHT OF WAY IN PROGRESS. | Region C |  | NHPB | CONSTRUCTION | 24500000 | FY 2029: 5429000; FY 2030: 9668000; FY 2031: 6706000; FY 2032: 2697000
B-5989 | Highway | Bridges | SR 1395 (WALNUT CREEK ROAD) | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | 0.25 | MADISON | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 13000
B-5989 | Highway | Bridges | SR 1395 (WALNUT CREEK ROAD) | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | 0.25 | MADISON | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 13 |  | BGOFF | UTILITIES | 130000
B-5989 | Highway | Bridges | SR 1395 (WALNUT CREEK ROAD) | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | 0.25 | MADISON | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 7406000 | FY 2025: 1100000
B-5990 | Highway | Bridges | SR 1138 (W. ARROWOOD ROAD) WESTBOUND | REPLACE BRIDGES 590001 AND 590513 WITH A NEW SINGLE STRUCTURE OVER SUGAR CREEK. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BFP | RIGHT-OF-WAY | 174000 | FY 2025: 174000
B-5990 | Highway | Bridges | SR 1138 (W. ARROWOOD ROAD) WESTBOUND | REPLACE BRIDGES 590001 AND 590513 WITH A NEW SINGLE STRUCTURE OVER SUGAR CREEK. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BFP | UTILITIES | 174000 | FY 2025: 174000
B-5990 | Highway | Bridges | SR 1138 (W. ARROWOOD ROAD) WESTBOUND | REPLACE BRIDGES 590001 AND 590513 WITH A NEW SINGLE STRUCTURE OVER SUGAR CREEK. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BFP | CONSTRUCTION | 4000000 | FY 2029: 2788000; FY 2030: 1212000
B-5995 | Highway | Bridges | SR 1302 (JANIERO ROAD) | REPLACE BRIDGE 680057 OVER DAWSON CREEK. | 0.25 | PAMLICO | 2 | Down East RPO |  | Division 2 |  | BGOFF | RIGHT-OF-WAY | 600000
B-5995 | Highway | Bridges | SR 1302 (JANIERO ROAD) | REPLACE BRIDGE 680057 OVER DAWSON CREEK. | 0.25 | PAMLICO | 2 | Down East RPO |  | Division 2 |  | BGOFF | CONSTRUCTION | 5900000 | FY 2026: 1003000; FY 2027: 3894000; FY 2028: 1003000
B-5996 | Highway | Bridges | SR 1300 (ASH-LITTLE RIVER ROAD NORTHWEST) | REPLACE BRIDGE 090126 OVER CAWCAW SWAMP. | 0.25 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 100000
B-5996 | Highway | Bridges | SR 1300 (ASH-LITTLE RIVER ROAD NORTHWEST) | REPLACE BRIDGE 090126 OVER CAWCAW SWAMP. | 0.25 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 2100000
B-5998 | Highway | Bridges | SR 1339 (SHARPE SHORE ROAD) | REPLACE BRIDGE 970092 OVER TOWN SWAMP. | 0.25 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION | Division 4
B-6000 | Highway | Bridges | SR 1400 (ROCK QUARRY ROAD) | REPLACE BRIDGE 970096 OVER TRIBUTARY OF TOWN CREEK. | 0.25 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION | Division 4
B-6002 | Highway | Bridges | SR 1126 (FAITH BAPTIST CHURCH ROAD) | REPLACE BRIDGE 320064 OVER TOWN CREEK. | 0.25 | EDGECOMBE | 4 | Upper Coastal Plain RPO | COMPLETE. | Highway Fund |  | HFB | CONSTRUCTION | 1200000
B-6003 | Highway | Bridges | SR 1609 (BAPTIST CHURCH ROAD) | REPLACE BRIDGE 340078 OVER TAR RIVER | 0.25 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | RIGHT-OF-WAY | 430000 | FY 2029: 430000
B-6003 | Highway | Bridges | SR 1609 (BAPTIST CHURCH ROAD) | REPLACE BRIDGE 340078 OVER TAR RIVER | 0.25 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | CONSTRUCTION | 7600000 | FY 2031: 3268000; FY 2032: 3420000; FY 2033: 912000
B-6004 | Highway | Bridges | SR 1534 (OVER LYON ROAD) | REPLACE BRIDGE 080197 OVER KELLY CANAL. | 0.25 | BLADEN | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6
B-6005 | Highway | Bridges | SR 1210 (HOOVER ROAD) | REPLACE BRIDGE 420234 OVER BARBEQUE SWAMP. | 0.25 | HARNETT | 6 | Mid-Carolina RPO | COMPLETED. | Division 6
B-6006 | Highway | Bridges | SR 1159 (OLD TRAM ROAD) | REPLACE BRIDGE 230313 OVER BOOGY BRANCH. | 0.25 | COLUMBUS | 6 | Cape Fear RPO | COMPLETED. | Division 6
B-6008 | Highway | Bridges | SR 1536 (JAMES PORTER ROAD) | REPLACE BRIDGE 080198 OVER KELLY CANAL. | 0.25 | BLADEN | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6
B-6011 | Highway | Bridges | SR 1430 (HARLAND ROAD) | REPLACE BRIDGE 110145 OVER BRISTOL CREEK. | 0.25 | BURKE | 13 | Greater Hickory MPO | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 65000
B-6011 | Highway | Bridges | SR 1430 (HARLAND ROAD) | REPLACE BRIDGE 110145 OVER BRISTOL CREEK. | 0.25 | BURKE | 13 | Greater Hickory MPO | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 725000
B-6012 | Highway | Bridges | SR 1341 (FOSTER CREEK ROAD) | REPLACE BRIDGE 560073 OVER FOSTER CREEK. | 0.25 | MADISON | 13 | French Broad River MPO | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Division 13 |  | T | BUILD NC CON | 4440000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000 | 296000
B-6012 | Highway | Bridges | SR 1341 (FOSTER CREEK ROAD) | REPLACE BRIDGE 560073 OVER FOSTER CREEK. | 0.25 | MADISON | 13 | French Broad River MPO | COMPLETE - BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Division 13 |  | T | CONSTRUCTION | 388000
B-6013 | Highway | Bridges | SR 1106 (LYNN GAP ROAD) | REPLACE BRIDGE 600207 OVER GRASSY CREEK. | 0.25 | MITCHELL | 13 | High Country RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016 | Division 13 |  | BGOFF | RIGHT-OF-WAY | 40000
B-6013 | Highway | Bridges | SR 1106 (LYNN GAP ROAD) | REPLACE BRIDGE 600207 OVER GRASSY CREEK. | 0.25 | MITCHELL | 13 | High Country RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016 | Division 13 |  | BGOFF | CONSTRUCTION | 800000
B-6014 | Highway | Bridges | SR 1781 (POLLY SPOUT ROAD) | REPLACE BRIDGE 580312 OVER SECOND BROAD RIVER. | 0.25 | McDOWELL | 13 | Foothills RPO | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 100000
B-6014 | Highway | Bridges | SR 1781 (POLLY SPOUT ROAD) | REPLACE BRIDGE 580312 OVER SECOND BROAD RIVER. | 0.25 | McDOWELL | 13 | Foothills RPO | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 4831000
B-6015 | Highway | Bridges | SR 1913 (SUGAR LOAF ROAD) | REPLACE BRIDGE 110237 OVER ROCK CREEK. | 0.25 | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 100000
B-6015 | Highway | Bridges | SR 1913 (SUGAR LOAF ROAD) | REPLACE BRIDGE 110237 OVER ROCK CREEK. | 0.25 | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 1369000
B-6016 | Highway | Bridges | SR 2027 (MARTINS CREEK ROAD) | REPLACE BRIDGE 100142 OVER MARTIN CREEK. | 0.25 | BUNCOMBE | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014 | Division 13 |  | BGOFF | RIGHT-OF-WAY | 50000
B-6016 | Highway | Bridges | SR 2027 (MARTINS CREEK ROAD) | REPLACE BRIDGE 100142 OVER MARTIN CREEK. | 0.25 | BUNCOMBE | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014 | Division 13 |  | BGOFF | CONSTRUCTION | 700000
B-6018 | Highway | Bridges | SR 1296 (BROOKS BRANCH ROAD) | REPLACE BRIDGE 100536 OVER NEWFOUND CREEK. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 55000
B-6018 | Highway | Bridges | SR 1296 (BROOKS BRANCH ROAD) | REPLACE BRIDGE 100536 OVER NEWFOUND CREEK. | 0.25 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION. | Division 13 |  | BGOFF | CONSTRUCTION | 872000
B-6025 | Highway | Bridges | SR 1114 (SHOPE ROAD) | REPLACE BRIDGE 550244 OVER NORTH FORK COWEETA CREEK. | 0.25 | MACON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 1700000 | FY 2025: 501000
B-6026 | Highway | Bridges | SR 1500 (WATAUGA ROAD) | REPLACE BRIDGE 550214 OVER WATAUGA CREEK. | 0.25 | MACON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 50000
B-6026 | Highway | Bridges | SR 1500 (WATAUGA ROAD) | REPLACE BRIDGE 550214 OVER WATAUGA CREEK. | 0.25 | MACON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 500000 | FY 2028: 425000; FY 2029: 75000
B-6028 | Highway | Bridges | SR 1528 (LITTLE ELLIJAY ROAD) | REPLACE BRIDGE 550150 OVER ELLIJAY CREEK. | 0.25 | MACON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 2600000
B-6029 | Highway | Bridges | SR 1001 (ELLIJAY ROAD) | REPLACE BRIDGE 550009 OVER NORTH PRONG ELLIJAY CREEK. | 0.25 | MACON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2025: 1389000; FY 2026: 611000
B-6030 | Highway | Bridges | SR 1351 (MATLOCK CREEK ROAD) | REPLACE BRIDGE 550220 OVER MATLOCK CREEK. | 0.25 | MACON | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  | BGOFF | CONSTRUCTION | 625000 | FY 2029: 445000; FY 2030: 180000
B-6031 | Highway | Bridges | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490069 OVER SAVANNAH CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 80000
B-6031 | Highway | Bridges | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490069 OVER SAVANNAH CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 800000 | FY 2025: 473000; FY 2026: 327000
B-6032 | Highway | Bridges | SR 1397 (THOMAS VALLEY ROAD) | REPLACE BRIDGE 490144 OVER NATIONS CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. 80 2019 BGOFF R 0 | Division 14 |  | BGOFF | RIGHT-OF-WAY | 50000
B-6032 | Highway | Bridges | SR 1397 (THOMAS VALLEY ROAD) | REPLACE BRIDGE 490144 OVER NATIONS CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. 80 2019 BGOFF R 0 | Division 14 |  | BGOFF | CONSTRUCTION | 983000
B-6033 | Highway | Bridges | SR 1445 (LEE BUMGARNER ROAD) | REPLACE BRIDGE 490129 OVER SCOTT CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS | Division 14 |  | BGOFF | CONSTRUCTION | 2700000 | FY 2029: 1511000; FY 2030: 1189000
B-6034 | Highway | Bridges | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490065 OVER SAVANNAH CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 70000
B-6034 | Highway | Bridges | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490065 OVER SAVANNAH CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1500000 | FY 2027: 1065000; FY 2028: 435000
B-6035 | Highway | Bridges | SR 1738 (HOOPER CEMETERY ROAD) | REPLACE BRIDGE 490203 OVER CANEY FORK. | 0.25 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | RIGHT-OF-WAY | 70000
B-6035 | Highway | Bridges | SR 1738 (HOOPER CEMETERY ROAD) | REPLACE BRIDGE 490203 OVER CANEY FORK. | 0.25 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | BGOFF | CONSTRUCTION | 1495000
B-6036 | Highway | Bridges | SR 1737 (CANEY FORK ROAD) | REPLACE BRIDGE 490081 OVER JOHNS CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 410000 | FY 2026: 410000
B-6036 | Highway | Bridges | SR 1737 (CANEY FORK ROAD) | REPLACE BRIDGE 490081 OVER JOHNS CREEK. | 0.25 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1500000 | FY 2027: 15000; FY 2028: 1485000
B-6037 | Highway | Bridges | NC 86 | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILROAD. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | BFP | RIGHT-OF-WAY | 2700000 | FY 2026: 1440000; FY 2027: 720000; FY 2028: 270000; FY 2029: 270000
B-6037 | Highway | Bridges | NC 86 | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILROAD. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | BFP | CONSTRUCTION | 10600000 | FY 2027: 7621000; FY 2028: 2979000
B-6038 | Highway | Bridges | NC 14 / NC 87 | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Region D |  | NHPB | RIGHT-OF-WAY | 400000 | FY 2027: 400000
B-6038 | Highway | Bridges | NC 14 / NC 87 | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Region D |  | NHPB | UTILITIES | 740000 | FY 2027: 740000
B-6038 | Highway | Bridges | NC 14 / NC 87 | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Region D |  | BFP | CONSTRUCTION | 7603000 | FY 2028: 4151000; FY 2029: 3452000
B-6041 | Highway | Bridges | I-40 | REPLACE BRIDGE 170177 AND 170178 OVER LYLE CREEK. | 0.25 | CATAWBA | 12 | Greater Hickory MPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 290000 | FY 2026: 290000
B-6041 | Highway | Bridges | I-40 | REPLACE BRIDGE 170177 AND 170178 OVER LYLE CREEK. | 0.25 | CATAWBA | 12 | Greater Hickory MPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 26900000 | FY 2030: 8877000; FY 2031: 11029000; FY 2032: 6994000
B-6044 | Highway | Bridges | I-95 | REPLACE BRIDGE 500082 AND 500085 OVER BLACK CREEK AND BRIDGE 500100 AND 500101 OVER NEUSE RIVER. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 110000
B-6044 | Highway | Bridges | I-95 | REPLACE BRIDGE 500082 AND 500085 OVER BLACK CREEK AND BRIDGE 500100 AND 500101 OVER NEUSE RIVER. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | HFB | CONSTRUCTION | 53899000 | FY 2029: 16632000; FY 2030: 18588000; FY 2031: 12967000; FY 2032: 5712000
B-6046 | Highway | Bridges | SR 1917 (BETHLEHEM CHURCH ROAD) | REPLACE BRIDGE 830102 OVER LONG CREEK. | 0.25 | STANLY | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | BGOFF | RIGHT-OF-WAY | 145000
B-6046 | Highway | Bridges | SR 1917 (BETHLEHEM CHURCH ROAD) | REPLACE BRIDGE 830102 OVER LONG CREEK. | 0.25 | STANLY | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | BGOFF | CONSTRUCTION | 1700000 | FY 2025: 402000
B-6047 | Highway | Bridges | SR 2125 (HARRIS HENRIETTA ROAD) | REPLACE BRIDGE 800145 OVER FLOYDS CREEK. | 0.25 | RUTHERFORD | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGOFF | RIGHT-OF-WAY | 210000
B-6047 | Highway | Bridges | SR 2125 (HARRIS HENRIETTA ROAD) | REPLACE BRIDGE 800145 OVER FLOYDS CREEK. | 0.25 | RUTHERFORD | 13 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 13 |  | BGOFF | CONSTRUCTION | 2700000 | FY 2026: 864000; FY 2027: 1836000
B-6048 | Highway | Bridges | SR 1812 (DIGGS ROAD) | REPLACE BRIDGE 030039 OVER JONES CREEK. | 0.25 | ANSON | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | BGOFF | RIGHT-OF-WAY | 355000
B-6048 | Highway | Bridges | SR 1812 (DIGGS ROAD) | REPLACE BRIDGE 030039 OVER JONES CREEK. | 0.25 | ANSON | 10 | Rocky River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | BGOFF | CONSTRUCTION | 4100000 | FY 2027: 2091000; FY 2028: 2009000
B-6049 | Highway | Bridges | SR 1206 (WRIGHT BRIDGE ROAD) | REPLACE BRIDGE 810072 OVER GREAT COHARIE CREEK. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | RIGHT-OF-WAY | 340000
B-6049 | Highway | Bridges | SR 1206 (WRIGHT BRIDGE ROAD) | REPLACE BRIDGE 810072 OVER GREAT COHARIE CREEK. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | BGOFF | CONSTRUCTION | 1901000 | FY 2025: 684000
B-6050 | Highway | Bridges | SR 2137 (PITTMAN ROAD) SR 2130 (EAST MAIN STREET) | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BFP | RIGHT-OF-WAY | 1500000 | FY 2025: 439000; FY 2026: 351000; FY 2027: 410000; FY 2028: 150000; FY 2029: 150000
B-6050 | Highway | Bridges | SR 2137 (PITTMAN ROAD) SR 2130 (EAST MAIN STREET) | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BFP | UTILITIES | 3800000 | FY 2025: 1900000; FY 2026: 1900000
B-6050 | Highway | Bridges | SR 2137 (PITTMAN ROAD) SR 2130 (EAST MAIN STREET) | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | 0.25 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | BFP | CONSTRUCTION | 45200000 | FY 2029: 12969000; FY 2030: 15560000; FY 2031: 11004000; FY 2032: 5667000
B-6051 | Highway | Bridges | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 0.25 | GASTON, MECKLENBURG | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region E, F |  | BFP | RIGHT-OF-WAY | 1100000
B-6051 | Highway | Bridges | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 0.25 | GASTON, MECKLENBURG | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region E, F |  | HIB | RIGHT-OF-WAY | 4000000
B-6051 | Highway | Bridges | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 0.25 | GASTON, MECKLENBURG | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region E, F |  | BFP | UTILITIES | 1300000
B-6051 | Highway | Bridges | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 0.25 | GASTON, MECKLENBURG | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region E, F |  | HIB | CONSTRUCTION | 36168000 | FY 2025: 4765000; FY 2026: 12705000; FY 2027: 10469000; FY 2028: 7213000; FY 2029: 1016000
B-6051 | Highway | Bridges | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | 0.25 | GASTON, MECKLENBURG | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143. | Region E, F |  | BFP | CONSTRUCTION | 39832000 | FY 2025: 5248000; FY 2026: 13992000; FY 2027: 11530000; FY 2028: 7944000; FY 2029: 1118000
B-6054 | Highway | Bridges | I-40 | REPLACE BRIDGES (430057, 430159, 430171, 430124, AND 430142) ON I-40 IN HAYWOOD COUNTY. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility
B-6054A | Highway | Bridges | I-40 | REPLACE BRIDGE 430057 OVER US FOREST SERVICE ROAD/COLD SPRINGS CREEK AT HARMON'S DEN. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | ENGINEERING | 500000
B-6054A | Highway | Bridges | I-40 | REPLACE BRIDGE 430057 OVER US FOREST SERVICE ROAD/COLD SPRINGS CREEK AT HARMON'S DEN. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 22898000
B-6054B | Highway | Bridges | I-40 | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | ENGINEERING | 500000
B-6054B | Highway | Bridges | I-40 | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | UTILITIES | 5000
B-6054B | Highway | Bridges | I-40 | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 25000000 | FY 2025: 5004000
B-6054C | Highway | Bridges | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | ENGINEERING | 2500000
B-6054C | Highway | Bridges | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 47000
B-6054C | Highway | Bridges | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | UTILITIES | 5000
B-6054C | Highway | Bridges | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 79725000 | FY 2025: 15784000
B-6054D | Highway | Bridges | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T | ENGINEERING | 500000
B-6054D | Highway | Bridges | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 5000
B-6054D | Highway | Bridges | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T | UTILITIES | 5000
B-6054D | Highway | Bridges | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | T | CONSTRUCTION | 20800000 | FY 2025: 15041000; FY 2026: 5551000
B-6054E | Highway | Bridges | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | ENGINEERING | 2000000
B-6054E | Highway | Bridges | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 50000
B-6054E | Highway | Bridges | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | UTILITIES | 5000
B-6054E | Highway | Bridges | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 34400000 | FY 2025: 17008000; FY 2026: 8699000; FY 2027: 6360000; FY 2028: 1989000
B-8888 | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | CONSTRUCTION | 0
B-8888DIV | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BFP | CONSTRUCTION | 0
B-8888REG | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | BFP | CONSTRUCTION | 0
B-8888SW | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | BFP | CONSTRUCTION | 0
BF-0001 | Bike & Ped | Federal Lands Access Program | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. |  | JACKSON | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | FLAP | ENGINEERING | 8000
BF-0001 | Bike & Ped | Federal Lands Access Program | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. |  | JACKSON | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | HF(M) | ENGINEERING | 2000
BF-0001 | Bike & Ped | Federal Lands Access Program | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. |  | JACKSON | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | FLAP | CONSTRUCTION | 152000
BF-0001 | Bike & Ped | Federal Lands Access Program | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. |  | JACKSON | 14 | Southwestern RPO | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | HF(M) | CONSTRUCTION | 38000
BF-0002 | Bike & Ped | Federal Lands Access Program | ECUSTA TRAIL | TRANSYLVANIA COUNTY LINE TO LAMB CREEK. CONSTRUCT GREENWAY. | 8 | TRANSYLVANIA | 14 | Land-of-Sky RPO | FLAP PROJECT NC 61. PE AWARDED $1.0M. | Exempt |  | FLAP | ENGINEERING | 1000000
BK-5100 | Highway | Bridges | VARIOUS | ESTABLISH BRIDGE MANAGEMENT SYSTEM. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99
BL-0001 | Bike & Ped | Locally Selected | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BURKE | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 13 |  | BGDA | ENGINEERING | 64000
BL-0001 | Bike & Ped | Locally Selected | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BURKE | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 13 |  | L | ENGINEERING | 16000
BL-0001 | Bike & Ped | Locally Selected | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BURKE | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 13 |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2025: 80000
BL-0001 | Bike & Ped | Locally Selected | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BURKE | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 13 |  | L | RIGHT-OF-WAY | 20000 | FY 2025: 20000
BL-0001 | Bike & Ped | Locally Selected | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BURKE | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 13 |  | BGANY | CONSTRUCTION | 272000 | FY 2026: 272000
BL-0001 | Bike & Ped | Locally Selected | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BURKE | 13 | Greater Hickory MPO | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 13 |  | L | CONSTRUCTION | 68000 | FY 2026: 68000
BL-0002 | Bike & Ped | Locally Selected | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 0.23 | CALDWELL | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | BGDA | ENGINEERING | 64000
BL-0002 | Bike & Ped | Locally Selected | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 0.23 | CALDWELL | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | L(M) | ENGINEERING | 16000
BL-0002 | Bike & Ped | Locally Selected | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 0.23 | CALDWELL | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | BGDA | RIGHT-OF-WAY | 19000 | FY 2025: 19000
BL-0002 | Bike & Ped | Locally Selected | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 0.23 | CALDWELL | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2025: 5000
BL-0002 | Bike & Ped | Locally Selected | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 0.23 | CALDWELL | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | TAANY | CONSTRUCTION | 352000 | FY 2025: 4000; FY 2026: 348000
BL-0002 | Bike & Ped | Locally Selected | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | 0.23 | CALDWELL | 11 | Greater Hickory MPO | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN TAANY AS PART OF FUND SWAP 5-19-22. | Division 11 |  | L(M) | CONSTRUCTION | 88000 | FY 2025: 1000; FY 2026: 87000
BL-0003 | Bike & Ped | Locally Selected | DAVIDSON | WEST BRANCH NATURE PRESERVE. CONSTRUCT GREENWAY. | 0.77 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 121000
BL-0003 | Bike & Ped | Locally Selected | DAVIDSON | WEST BRANCH NATURE PRESERVE. CONSTRUCT GREENWAY. | 0.77 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 30000
BL-0005 | Bike & Ped | Locally Selected | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 0.23 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | BGDA | ENGINEERING | 3000
BL-0005 | Bike & Ped | Locally Selected | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 0.23 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | HF(M) | ENGINEERING | 1000
BL-0005 | Bike & Ped | Locally Selected | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 0.23 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | HSIP | CONSTRUCTION | 45000
BL-0005 | Bike & Ped | Locally Selected | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 0.23 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | BGDA | CONSTRUCTION | 749000
BL-0005 | Bike & Ped | Locally Selected | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 0.23 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | HF(M) | CONSTRUCTION | 188000
BL-0005 | Bike & Ped | Locally Selected | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | 0.23 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE. "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. "HF" FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID. | Division 13 |  | HF | CONSTRUCTION | 142000
BL-0006 | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | ENGINEERING | 60000 | FY 2026: 60000
BL-0006 | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | ENGINEERING | 15000 | FY 2026: 15000
BL-0006 | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 600000 | FY 2027: 600000
BL-0006 | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 150000 | FY 2027: 150000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | BGDA | ENGINEERING | 546000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | L | ENGINEERING | 137000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | DP | CONSTRUCTION | 5705000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | CRPDA | CONSTRUCTION | 1911000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | TADA | CONSTRUCTION | 2618000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | TADA | CONSTRUCTION | 2419000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | L | CONSTRUCTION | 605000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | L | CONSTRUCTION | 655000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | L | CONSTRUCTION | 478000
BL-0007 | Bike & Ped | Locally Selected | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | 5.79 | HENDERSON | 14 | French Broad River MPO | "DP" REPRESENTS NATIONALLY SIGNIFICANT FEDERAL LANDS AND TRIBAL PROJECTS GRANT FUNDS. | Division 14 |  | L | CONSTRUCTION | 634000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | BGDA | ENGINEERING | 484000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | BGDA | ENGINEERING | 638000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L | ENGINEERING | 160000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L | ENGINEERING | 121000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | BGANY | CONSTRUCTION | 1796000 | FY 2025: 1796000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | BGANY | CONSTRUCTION | 487000 | FY 2025: 487000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | BGANY | CONSTRUCTION | 78000 | FY 2025: 78000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L | CONSTRUCTION | 122000 | FY 2025: 122000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L | CONSTRUCTION | 20000 | FY 2025: 20000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L | CONSTRUCTION | 362000 | FY 2025: 362000
BL-0008 | Bike & Ped | Locally Selected | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | 1.39 | HENDERSON | 14 | French Broad River MPO | $78K IN BGANY USED AS PART OF FUND SWAP. $2.283M OF STBG-DA FUNDS SWAPPED FOR $2.283M IN STBG-ANYAREA FUNDS ON 6-9-23. | Division 14 |  | L | CONSTRUCTION | 449000 | FY 2025: 449000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.68 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | ENGINEERING | 110000 | FY 2025: 110000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.68 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | ENGINEERING | 28000 | FY 2025: 28000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.68 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 493000 | FY 2025: 493000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.68 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | RIGHT-OF-WAY | 124000 | FY 2025: 124000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.68 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | CONSTRUCTION | 583000 | FY 2027: 583000
BL-0009 | Bike & Ped | Locally Selected | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.68 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | CONSTRUCTION | 146000 | FY 2027: 146000
BL-0010 | Bike & Ped | Locally Selected | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 1.55 | MECKLENBURG | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TADA | ENGINEERING | 188000
BL-0010 | Bike & Ped | Locally Selected | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 1.55 | MECKLENBURG | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L | ENGINEERING | 188000
BL-0010 | Bike & Ped | Locally Selected | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 1.55 | MECKLENBURG | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGDA | RIGHT-OF-WAY | 77000 | FY 2025: 77000
BL-0010 | Bike & Ped | Locally Selected | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 1.55 | MECKLENBURG | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TAANY | RIGHT-OF-WAY | 181000 | FY 2025: 181000
BL-0010 | Bike & Ped | Locally Selected | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 1.55 | MECKLENBURG | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L | RIGHT-OF-WAY | 258000 | FY 2025: 258000
BL-0010 | Bike & Ped | Locally Selected | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 1.55 | MECKLENBURG | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGDA | CONSTRUCTION | 1300000 | FY 2026: 1300000
BL-0010 | Bike & Ped | Locally Selected | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | 1.55 | MECKLENBURG | 10 | Charlotte Regional TPO | $181K IN STBG-DA FUNDS SWAPPED FOR $181K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L | CONSTRUCTION | 1300000 | FY 2026: 1300000
BL-0011 | Bike & Ped | Locally Selected | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 0.55 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 50000
BL-0011 | Bike & Ped | Locally Selected | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 0.55 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 13000
BL-0011 | Bike & Ped | Locally Selected | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 0.55 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 268000 | FY 2026: 268000
BL-0011 | Bike & Ped | Locally Selected | MARSHVILLE | CROSS STREET, SR 1735 (EAST UNION STREET), NC 205 (NORTH ELM STREET) AND SR 1740 (MAIN STREET), NC 205 (NORTH ELM STREET) AND SR 1735 (EAST UNION STREET). CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | 0.55 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 67000 | FY 2026: 67000
BL-0012 | Bike & Ped | Locally Selected | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.16 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 146000
BL-0012 | Bike & Ped | Locally Selected | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.16 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 98000
BL-0012 | Bike & Ped | Locally Selected | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.16 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 94000 | FY 2025: 94000
BL-0012 | Bike & Ped | Locally Selected | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.16 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 63000 | FY 2025: 63000
BL-0012 | Bike & Ped | Locally Selected | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.16 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 785000 | FY 2026: 785000
BL-0012 | Bike & Ped | Locally Selected | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 1.16 | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 524000 | FY 2026: 524000
BL-0013 | Bike & Ped | Locally Selected | MOORE AVENUE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.22 | IREDELL | 12 | Charlotte Regional TPO | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | TAANY | ENGINEERING | 8000
BL-0013 | Bike & Ped | Locally Selected | MOORE AVENUE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.22 | IREDELL | 12 | Charlotte Regional TPO | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L | ENGINEERING | 2000
BL-0013 | Bike & Ped | Locally Selected | MOORE AVENUE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.22 | IREDELL | 12 | Charlotte Regional TPO | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | TAANY | CONSTRUCTION | 1192000 | FY 2025: 1192000
BL-0013 | Bike & Ped | Locally Selected | MOORE AVENUE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.22 | IREDELL | 12 | Charlotte Regional TPO | $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L | CONSTRUCTION | 798000 | FY 2025: 798000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | ENGINEERING | 83000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | ENGINEERING | 206000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | ENGINEERING | 21000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | ENGINEERING | 51000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | RIGHT-OF-WAY | 116000 | FY 2026: 116000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | RIGHT-OF-WAY | 29000 | FY 2026: 29000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | CONSTRUCTION | 1501000 | FY 2027: 1501000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | CONSTRUCTION | 305000 | FY 2027: 305000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | CONSTRUCTION | 375000 | FY 2027: 375000
BL-0014 | Bike & Ped | Locally Selected | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.4 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | CONSTRUCTION | 76000 | FY 2027: 76000
BL-0015 | Bike & Ped | Locally Selected | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 0.17 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 38000 | FY 2025: 38000
BL-0015 | Bike & Ped | Locally Selected | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 0.17 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 9000 | FY 2025: 9000
BL-0015 | Bike & Ped | Locally Selected | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 0.17 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 79000 | FY 2025: 79000
BL-0015 | Bike & Ped | Locally Selected | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 0.17 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 20000 | FY 2025: 20000
BL-0015 | Bike & Ped | Locally Selected | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 0.17 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 771000 | FY 2027: 771000
BL-0015 | Bike & Ped | Locally Selected | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | 0.17 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 193000 | FY 2027: 193000
BL-0016 | Bike & Ped | Locally Selected | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 8000
BL-0016 | Bike & Ped | Locally Selected | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 2000
BL-0016 | Bike & Ped | Locally Selected | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 64000 | FY 2025: 64000
BL-0016 | Bike & Ped | Locally Selected | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 15000 | FY 2025: 15000
BL-0016 | Bike & Ped | Locally Selected | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 15000 | FY 2025: 15000
BL-0016 | Bike & Ped | Locally Selected | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | UTILITIES | 4000 | FY 2025: 4000
BL-0016 | Bike & Ped | Locally Selected | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 277000 | FY 2025: 277000
BL-0016 | Bike & Ped | Locally Selected | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 69000 | FY 2025: 69000
BL-0017 | Bike & Ped | Locally Selected | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 0.13 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 117000 | FY 2025: 117000
BL-0017 | Bike & Ped | Locally Selected | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 0.13 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 29000 | FY 2025: 29000
BL-0017 | Bike & Ped | Locally Selected | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 0.13 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 40000 | FY 2026: 40000
BL-0017 | Bike & Ped | Locally Selected | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 0.13 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 10000 | FY 2026: 10000
BL-0017 | Bike & Ped | Locally Selected | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 0.13 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 681000 | FY 2027: 681000
BL-0017 | Bike & Ped | Locally Selected | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | 0.13 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 170000 | FY 2027: 170000
BL-0018 | Bike & Ped | Locally Selected | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.76 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | ENGINEERING | 164000
BL-0018 | Bike & Ped | Locally Selected | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.76 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | ENGINEERING | 41000
BL-0018 | Bike & Ped | Locally Selected | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.76 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGDA | RIGHT-OF-WAY | 410000 | FY 2025: 410000
BL-0018 | Bike & Ped | Locally Selected | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.76 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | RIGHT-OF-WAY | 103000 | FY 2025: 103000
BL-0018 | Bike & Ped | Locally Selected | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.76 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | BGANY | CONSTRUCTION | 1861000 | FY 2026: 1861000
BL-0018 | Bike & Ped | Locally Selected | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | 0.76 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Division 9 |  | L | CONSTRUCTION | 465000 | FY 2026: 465000
BL-0019 | Bike & Ped | Locally Selected | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.28 | FORSYTH | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | BGDA | ENGINEERING | 800000
BL-0019 | Bike & Ped | Locally Selected | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.28 | FORSYTH | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | L | ENGINEERING | 200000
BL-0019 | Bike & Ped | Locally Selected | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.28 | FORSYTH | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2025: 80000
BL-0019 | Bike & Ped | Locally Selected | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.28 | FORSYTH | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | L | RIGHT-OF-WAY | 20000 | FY 2025: 20000
BL-0019 | Bike & Ped | Locally Selected | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.28 | FORSYTH | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | DP | CONSTRUCTION | 6000000 | FY 2025: 6000000
BL-0019 | Bike & Ped | Locally Selected | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 25TH STREET IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.28 | FORSYTH | 9 | Winston-Salem Area TPO | DP REPRESENT RAISE GRANT FUNDS | Division 9 |  | L | CONSTRUCTION | 1500000 | FY 2025: 1500000
BL-0020 | Bike & Ped | Locally Selected | DEPOT STREET | US 311 (MAIN STREET) TO SR 1992 (SULLIVANTOWN ROAD) IN WALKERTOWN. CONSTRUCT SIDEWALK. | 0.22 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 849000 | FY 2025: 849000
BL-0020 | Bike & Ped | Locally Selected | DEPOT STREET | US 311 (MAIN STREET) TO SR 1992 (SULLIVANTOWN ROAD) IN WALKERTOWN. CONSTRUCT SIDEWALK. | 0.22 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 212000 | FY 2025: 212000
BL-0021 | Bike & Ped | Locally Selected | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION TRANSPORTATION ALTERNATIVES PROGRAM. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Division 3 |  | TADA | CONSTRUCTION | 1752000 | 275000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 378000
BL-0022 | Bike & Ped | Locally Selected | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | ENGINEERING | 131000
BL-0022 | Bike & Ped | Locally Selected | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | ENGINEERING | 33000
BL-0022 | Bike & Ped | Locally Selected | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 150000
BL-0022 | Bike & Ped | Locally Selected | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 37000
BL-0022 | Bike & Ped | Locally Selected | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | UTILITIES | 60000
BL-0022 | Bike & Ped | Locally Selected | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | UTILITIES | 15000
BL-0022 | Bike & Ped | Locally Selected | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 944000
BL-0022 | Bike & Ped | Locally Selected | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 236000
BL-0023 | Bike & Ped | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO MIDDLECREST WAY IN HOLLY SPRINGS. ENHANCE PEDESTRIAN SAFETY. | 0.41 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 558000
BL-0023 | Bike & Ped | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO MIDDLECREST WAY IN HOLLY SPRINGS. ENHANCE PEDESTRIAN SAFETY. | 0.41 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 557000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | RIGHT-OF-WAY | 20000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | RIGHT-OF-WAY | 20000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | UTILITIES | 81000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | UTILITIES | 81000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 3372000
BL-0024 | Bike & Ped | Locally Selected | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 3372000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 0.12 | WAKE | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | BGANY | ENGINEERING | 120000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 0.12 | WAKE | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | L | ENGINEERING | 30000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 0.12 | WAKE | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | BGANY | RIGHT-OF-WAY | 160000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 0.12 | WAKE | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | L | RIGHT-OF-WAY | 40000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 0.12 | WAKE | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | BGANY | CONSTRUCTION | 2411000 | FY 2025: 1351000; FY 2026: 1060000
BL-0025 | Bike & Ped | Locally Selected | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | 0.12 | WAKE | 5 | Capital Area MPO | $1,351,200 STBG-ANYAREA RESULTING FROM FUND SWAP | Division 5 |  | L | CONSTRUCTION | 268000
BL-0026 | Bike & Ped | Locally Selected | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 0.24 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 13000 | FY 2025: 13000
BL-0026 | Bike & Ped | Locally Selected | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 0.24 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 153000
BL-0026 | Bike & Ped | Locally Selected | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 0.24 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 66000
BL-0026 | Bike & Ped | Locally Selected | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 0.24 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 3000 | FY 2025: 3000
BL-0026 | Bike & Ped | Locally Selected | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 0.24 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 744000 | FY 2025: 744000
BL-0026 | Bike & Ped | Locally Selected | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | 0.24 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 319000 | FY 2025: 319000
BL-0027 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY | LASSITER MILL ROAD TO HERTFORD STREET IN RALEIGH. CONSTRUCT GREENWAY TRAIL. | 0.14 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1182000 | FY 2025: 1182000
BL-0027 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY | LASSITER MILL ROAD TO HERTFORD STREET IN RALEIGH. CONSTRUCT GREENWAY TRAIL. | 0.14 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 507000 | FY 2025: 507000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 4.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | CMAQ | ENGINEERING | 48000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 4.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGDA | ENGINEERING | 75000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 4.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | ENGINEERING | 52000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 4.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | CMAQ | CONSTRUCTION | 852000 | FY 2025: 9000; FY 2026: 843000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 4.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | CMAQ | CONSTRUCTION | 375000 | FY 2025: 4000; FY 2026: 371000
BL-0028 | Bike & Ped | Locally Selected | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 4.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CONSTRUCTION | 1338000 | FY 2025: 1105000; FY 2026: 180000
BL-0030 | Bike & Ped | Locally Selected | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 8.67 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGDA | ENGINEERING | 14000
BL-0030 | Bike & Ped | Locally Selected | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 8.67 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGDACV | ENGINEERING | 15000
BL-0030 | Bike & Ped | Locally Selected | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 8.67 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | ENGINEERING | 7000
BL-0030 | Bike & Ped | Locally Selected | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 8.67 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 143000 | FY 2025: 143000
BL-0030 | Bike & Ped | Locally Selected | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HILL BOULEVARD), NATION AVENUE TO SR 1183 (UNIVERSITY DRIVE) IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | 8.67 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CONSTRUCTION | 36000 | FY 2025: 36000
BL-0031 | Bike & Ped | Locally Selected | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STEPHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 8.23 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGDA | ENGINEERING | 40000
BL-0031 | Bike & Ped | Locally Selected | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STEPHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 8.23 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | ENGINEERING | 20000
BL-0031 | Bike & Ped | Locally Selected | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STEPHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 8.23 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 283000 | FY 2025: 243000
BL-0031 | Bike & Ped | Locally Selected | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB BOULEVARD TO ELLERBE CREEK TRAIL; CLEVELAND STREET / CORPORATION STREET, US 70 BUSINESS / NC 98 (HOLLOWAY STREET) TO RIGSBEE AVENUE; JUNIPER STREET, SPRUCE STREET TO GUTHRIE AVENUE; LINCOLN STREET / GRANT STREET, LAWSON STREET TO LAKELAND STREET; RIDGEWAY AVENUE / LAKELAND STREET, LAWSON STREET TO MATHISON STREET; LAVENDER AVENUE, ELGIN STREET TO STEPHENSON STREET; STEPHENSON STREET, LAVENDER AVENUE TO SR 1669 (CLUB BOULEVARD); UMSTEAD STREET / LODGE STREET, SR 1118 (FAYETTEVILLE STREET) TO FARGO STREET IN DURHAM. CONSTRUCT BICYCLE ACCOMODATIONS. | 8.23 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CONSTRUCTION | 121000 | FY 2025: 101000
BL-0032 | Bike & Ped | Locally Selected | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 0.58 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | CMAQ | ENGINEERING | 80000
BL-0032 | Bike & Ped | Locally Selected | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 0.58 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 20000
BL-0032 | Bike & Ped | Locally Selected | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 0.58 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | CMAQ | RIGHT-OF-WAY | 8000 | FY 2025: 8000
BL-0032 | Bike & Ped | Locally Selected | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 0.58 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 2000 | FY 2025: 2000
BL-0032 | Bike & Ped | Locally Selected | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 0.58 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | CMAQ | CONSTRUCTION | 272000 | FY 2025: 269000
BL-0032 | Bike & Ped | Locally Selected | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | 0.58 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 68000 | FY 2025: 1000; FY 2026: 67000
BL-0033 | Bike & Ped | Locally Selected | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 0.31 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | ENGINEERING | 150000
BL-0033 | Bike & Ped | Locally Selected | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 0.31 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L | ENGINEERING | 38000
BL-0033 | Bike & Ped | Locally Selected | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 0.31 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 40000
BL-0033 | Bike & Ped | Locally Selected | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 0.31 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L | RIGHT-OF-WAY | 10000
BL-0033 | Bike & Ped | Locally Selected | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 0.31 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1159000 | FY 2025: 828000; FY 2026: 331000
BL-0033 | Bike & Ped | Locally Selected | (TRYON COURTHOUSE ROAD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | 0.31 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L | CONSTRUCTION | 290000 | FY 2025: 200000; FY 2026: 90000
BL-0035 | Bike & Ped | Locally Selected | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 0.16 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CMAQ | ENGINEERING | 32000
BL-0035 | Bike & Ped | Locally Selected | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 0.16 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L | ENGINEERING | 8000
BL-0035 | Bike & Ped | Locally Selected | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 0.16 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 8000
BL-0035 | Bike & Ped | Locally Selected | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 0.16 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L | RIGHT-OF-WAY | 2000
BL-0035 | Bike & Ped | Locally Selected | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 0.16 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 128000
BL-0035 | Bike & Ped | Locally Selected | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | 0.16 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L | CONSTRUCTION | 32000
BL-0036 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 0.53 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 198000
BL-0036 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 0.53 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 50000
BL-0036 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 0.53 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1122000 | FY 2025: 111000
BL-0036 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | 0.53 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 280000 | FY 2025: 26000
BL-0037 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY CONNECTOR | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | 0.21 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 16000
BL-0037 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY CONNECTOR | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | 0.21 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 4000
BL-0037 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY CONNECTOR | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | 0.21 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 2261000 | FY 2025: 1915000; FY 2026: 346000
BL-0037 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY CONNECTOR | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | 0.21 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 565000 | FY 2025: 479000; FY 2026: 86000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 99000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 13000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | ENGINEERING | 3000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | ENGINEERING | 25000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 14000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | RIGHT-OF-WAY | 3000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | UTILITIES | 31000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | UTILITIES | 8000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 568000
BL-0038 | Bike & Ped | Locally Selected | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | 0.29 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | CONSTRUCTION | 142000
BL-0039 | Bike & Ped | Locally Selected | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 0.71 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 38000
BL-0039 | Bike & Ped | Locally Selected | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 0.71 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 12000
BL-0039 | Bike & Ped | Locally Selected | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 0.71 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 125000
BL-0039 | Bike & Ped | Locally Selected | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 0.71 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | RIGHT-OF-WAY | 42000
BL-0039 | Bike & Ped | Locally Selected | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 0.71 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 858000 | FY 2025: 9000; FY 2026: 849000
BL-0039 | Bike & Ped | Locally Selected | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | 0.71 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 286000 | FY 2025: 49000
BL-0040 | Bike & Ped | Locally Selected | VARIOUS | MIDDLE SOUND LOOP CONNECTOR CONSTRUCTION AND PORTERS NECK WALMART CONNECTOR. CONSTRUCT MULTI-USE PATH. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 554000 | FY 2025: 554000
BL-0040 | Bike & Ped | Locally Selected | VARIOUS | MIDDLE SOUND LOOP CONNECTOR CONSTRUCTION AND PORTERS NECK WALMART CONNECTOR. CONSTRUCT MULTI-USE PATH. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 138000 | FY 2025: 138000
BL-0041 | Bike & Ped | Locally Selected | LATHAM PARK GREENWAY LAKE DANIEL GREENWAY; | LAKE DANIEL GREENWAY, FRIENDLY AVENUE TO JOSEPHINE BOYD STREET, AND LATHAM PARK GREENWAY AT TENNIS COURTS NEAR WENDOVER AVENUE IN GREENSBORO. REPAIR SURFACES. | 1.33 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 400000 | FY 2025: 319000; FY 2026: 81000
BL-0041 | Bike & Ped | Locally Selected | LATHAM PARK GREENWAY LAKE DANIEL GREENWAY; | LAKE DANIEL GREENWAY, FRIENDLY AVENUE TO JOSEPHINE BOYD STREET, AND LATHAM PARK GREENWAY AT TENNIS COURTS NEAR WENDOVER AVENUE IN GREENSBORO. REPAIR SURFACES. | 1.33 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 100000 | FY 2025: 100000
BL-0042 | Bike & Ped | Locally Selected | VANCE ARLINGTON GREENWAY | NORTH OF FLORIDA STREET TO BRAGG STREET IN GREENSBORO. CONSTRUCT GREENWAY AND SIDEPATH. | 0.81 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 960000 | FY 2025: 614000; FY 2026: 346000
BL-0042 | Bike & Ped | Locally Selected | VANCE ARLINGTON GREENWAY | NORTH OF FLORIDA STREET TO BRAGG STREET IN GREENSBORO. CONSTRUCT GREENWAY AND SIDEPATH. | 0.81 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 240000 | FY 2025: 240000
BL-0043 | Bike & Ped | Locally Selected | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 0.17 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | ENGINEERING | 92000
BL-0043 | Bike & Ped | Locally Selected | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 0.17 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L | ENGINEERING | 23000
BL-0043 | Bike & Ped | Locally Selected | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 0.17 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 419000 | FY 2025: 415000
BL-0043 | Bike & Ped | Locally Selected | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER, AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | 0.17 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L | CONSTRUCTION | 105000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 1.55 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | HF | ENGINEERING | 175000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 1.55 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | BGDA | CONSTRUCTION | 978000 | FY 2025: 978000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 1.55 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | L(M) | CONSTRUCTION | 193000 | FY 2025: 193000
BL-0044 | Bike & Ped | Locally Selected | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | 1.55 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | “HF” FUNDING REFLECTS SPOT SAFETY ALLOCATION. | Division 7 |  | HF | CONSTRUCTION | 140000 | FY 2025: 140000
BL-0045 | Bike & Ped | Locally Selected | WILMINGTON | WILMINGTON RAIL TRAIL. CONSTRUCT MULTI-USE PATH FROM 3RD STREET IN DOWNTOWN WILMINGTON TO THE LOVE GROVE BRIDGE MULTI-USE PATH FACILITY. | 1.36 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDACV | ENGINEERING | 680000
BL-0046 | Bike & Ped | Locally Selected | SR 1116 (OCEAN BOULEVARD) | INSTALL BIKE LANES ALONG SR 1116 (OCEAN BOULEVARD) FROM JUST WEST OF SHELL DRIVE TO DUNESCAPE DRIVE IN HOLDEN BEACH. | 6.14 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | BGDA | CONSTRUCTION | 913000
BL-0046 | Bike & Ped | Locally Selected | SR 1116 (OCEAN BOULEVARD) | INSTALL BIKE LANES ALONG SR 1116 (OCEAN BOULEVARD) FROM JUST WEST OF SHELL DRIVE TO DUNESCAPE DRIVE IN HOLDEN BEACH. | 6.14 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | L | CONSTRUCTION | 700000
BL-0047 | Bike & Ped | Locally Selected | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 16000
BL-0047 | Bike & Ped | Locally Selected | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 4000
BL-0047 | Bike & Ped | Locally Selected | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 177000
BL-0047 | Bike & Ped | Locally Selected | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 44000
BL-0047 | Bike & Ped | Locally Selected | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 1219000 | FY 2025: 1219000
BL-0047 | Bike & Ped | Locally Selected | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 305000 | FY 2025: 305000
BL-0048 | Bike & Ped | Locally Selected | SR 1616 (OLD APEX ROAD) | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | 1.29 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 15000
BL-0048 | Bike & Ped | Locally Selected | SR 1616 (OLD APEX ROAD) | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | 1.29 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 10000
BL-0048 | Bike & Ped | Locally Selected | SR 1616 (OLD APEX ROAD) | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | 1.29 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1180000 | FY 2025: 1180000
BL-0048 | Bike & Ped | Locally Selected | SR 1616 (OLD APEX ROAD) | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | 1.29 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 795000 | FY 2025: 795000
BL-0049 | Bike & Ped | Locally Selected | SR 1632 (LOUIS STEPHENS DRIVE) | GRAY MARBLE ROAD TO ADDENBROCK DRIVE IN MORRISVILLE, AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | 0.63 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000 | FY 2025: 8000
BL-0049 | Bike & Ped | Locally Selected | SR 1632 (LOUIS STEPHENS DRIVE) | GRAY MARBLE ROAD TO ADDENBROCK DRIVE IN MORRISVILLE, AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | 0.63 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 2000 | FY 2025: 2000
BL-0049 | Bike & Ped | Locally Selected | SR 1632 (LOUIS STEPHENS DRIVE) | GRAY MARBLE ROAD TO ADDENBROCK DRIVE IN MORRISVILLE, AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | 0.63 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 385000 | FY 2026: 4000; FY 2027: 381000
BL-0049 | Bike & Ped | Locally Selected | SR 1632 (LOUIS STEPHENS DRIVE) | GRAY MARBLE ROAD TO ADDENBROCK DRIVE IN MORRISVILLE, AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | 0.63 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 165000 | FY 2026: 2000; FY 2027: 163000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 0.35 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 0.35 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L | ENGINEERING | 2000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 0.35 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | RIGHT-OF-WAY | 140000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 0.35 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L | RIGHT-OF-WAY | 60000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 0.35 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | CONSTRUCTION | 307000 | FY 2025: 307000
BL-0050 | Bike & Ped | Locally Selected | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | 0.35 | JOHNSTON | 4 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L | CONSTRUCTION | 133000 | FY 2025: 133000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 0.28 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | CMAQ | ENGINEERING | 39000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 0.28 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | HF(M) | ENGINEERING | 11000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 0.28 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | CMAQ | RIGHT-OF-WAY | 39000 | FY 2025: 39000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 0.28 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | HF(M) | RIGHT-OF-WAY | 11000 | FY 2025: 11000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 0.28 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | CMAQ | CONSTRUCTION | 273000 | FY 2025: 273000
BL-0051 | Bike & Ped | Locally Selected | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | 0.28 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT SAFETY HIGHWAY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 77000 | FY 2025: 77000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 0.24 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 60000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 0.24 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 15000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 0.24 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 200000 | FY 2025: 200000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 0.24 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | RIGHT-OF-WAY | 50000 | FY 2025: 50000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 0.24 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 400000 | FY 2025: 400000
BL-0052 | Bike & Ped | Locally Selected | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | 0.24 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 100000 | FY 2025: 100000
BL-0053 | Bike & Ped | Locally Selected | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 2.82 | FRANKLIN | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 480000
BL-0053 | Bike & Ped | Locally Selected | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 2.82 | FRANKLIN | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 120000
BL-0053 | Bike & Ped | Locally Selected | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 2.82 | FRANKLIN | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 96000 | FY 2025: 96000
BL-0053 | Bike & Ped | Locally Selected | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 2.82 | FRANKLIN | 5 | Capital Area MPO |  | Exempt |  | L | RIGHT-OF-WAY | 24000 | FY 2025: 24000
BL-0053 | Bike & Ped | Locally Selected | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 2.82 | FRANKLIN | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 2400000 | FY 2025: 2400000
BL-0053 | Bike & Ped | Locally Selected | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRANKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | 2.82 | FRANKLIN | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 600000 | FY 2025: 600000
BL-0054 | Bike & Ped | Locally Selected | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 0.07 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 48000
BL-0054 | Bike & Ped | Locally Selected | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 0.07 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 12000
BL-0054 | Bike & Ped | Locally Selected | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 0.07 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 582000
BL-0054 | Bike & Ped | Locally Selected | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | 0.07 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 146000
BL-0055 | Bike & Ped | Locally Selected | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. |  | IREDELL | 12 | Charlotte Regional TPO | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | TAANY | ENGINEERING | 272000 | FY 2025: 272000
BL-0055 | Bike & Ped | Locally Selected | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. |  | IREDELL | 12 | Charlotte Regional TPO | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L | ENGINEERING | 91000 | FY 2025: 91000
BL-0055 | Bike & Ped | Locally Selected | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. |  | IREDELL | 12 | Charlotte Regional TPO | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | TAANY | CONSTRUCTION | 1561000 | FY 2026: 1561000
BL-0055 | Bike & Ped | Locally Selected | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. |  | IREDELL | 12 | Charlotte Regional TPO | $1.833M IN STBG-DA FUNDS SWAPPED FOR $1.833M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L | CONSTRUCTION | 520000 | FY 2026: 520000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (WHITE OAK ROAD); MAPLE AVENUE; McNEELY AV | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 0.69 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | ENGINEERING | 422000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (WHITE OAK ROAD); MAPLE AVENUE; McNEELY AV | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 0.69 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | ENGINEERING | 141000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (WHITE OAK ROAD); MAPLE AVENUE; McNEELY AV | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 0.69 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 78000 | FY 2027: 78000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (WHITE OAK ROAD); MAPLE AVENUE; McNEELY AV | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 0.69 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | RIGHT-OF-WAY | 26000 | FY 2027: 26000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (WHITE OAK ROAD); MAPLE AVENUE; McNEELY AV | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 0.69 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | CONSTRUCTION | 1479000 | FY 2029: 1479000
BL-0056 | Bike & Ped | Locally Selected | SR 2162 (WHITE OAK ROAD); MAPLE AVENUE; McNEELY AV | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | 0.69 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | CONSTRUCTION | 493000 | FY 2029: 493000
BL-0057 | Bike & Ped | Locally Selected | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 1.3 | MECKLENBURG | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BGDA | ENGINEERING | 8000
BL-0057 | Bike & Ped | Locally Selected | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 1.3 | MECKLENBURG | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | ENGINEERING | 2000
BL-0057 | Bike & Ped | Locally Selected | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 1.3 | MECKLENBURG | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | CMAQ | CONSTRUCTION | 4484000 | FY 2030: 45000; FY 2031: 3254000; FY 2032: 1185000
BL-0057 | Bike & Ped | Locally Selected | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 1.3 | MECKLENBURG | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BGDA | CONSTRUCTION | 381000 | FY 2030: 381000
BL-0057 | Bike & Ped | Locally Selected | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | 1.3 | MECKLENBURG | 10 | Charlotte Regional TPO | $483K IN STBG-DA SWITCHED WITH $483K IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | CONSTRUCTION | 1216000 | FY 2030: 1216000
BL-0058 | Bike & Ped | Locally Selected | RAIL TRAIL PEDESTRIAN BRIDGE | SR 3815 (EAST MOREHEAD STREET) TO BROOKLYN VILLAGE LIGHT RAIL STATION. CONSTRUCT RAIL TRAIL PEDESTRIAN BRIDGE OVER I-277 (BELK FREEWAY). | 0.11 | MECKLENBURG | 10 | Charlotte Regional TPO | $1.903M IN STBG-DA FUNDS SWAPPED FOR $1.903M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TAANY | CONSTRUCTION | 1903000 | FY 2025: 1903000
BL-0058 | Bike & Ped | Locally Selected | RAIL TRAIL PEDESTRIAN BRIDGE | SR 3815 (EAST MOREHEAD STREET) TO BROOKLYN VILLAGE LIGHT RAIL STATION. CONSTRUCT RAIL TRAIL PEDESTRIAN BRIDGE OVER I-277 (BELK FREEWAY). | 0.11 | MECKLENBURG | 10 | Charlotte Regional TPO | $1.903M IN STBG-DA FUNDS SWAPPED FOR $1.903M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L | CONSTRUCTION | 4440000 | FY 2025: 4440000
BL-0059 | Bike & Ped | Locally Selected | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 0.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDACV | ENGINEERING | 57000
BL-0059 | Bike & Ped | Locally Selected | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 0.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | RIGHT-OF-WAY | 42000 | FY 2025: 42000
BL-0059 | Bike & Ped | Locally Selected | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 0.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | RIGHT-OF-WAY | 11000 | FY 2025: 11000
BL-0059 | Bike & Ped | Locally Selected | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 0.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | CONSTRUCTION | 250000 | FY 2025: 250000
BL-0059 | Bike & Ped | Locally Selected | FORT FISHER BOULEVARD, K AVENUE, AND NORTH 3RD STR | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | 0.2 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 52000 | FY 2025: 52000
BL-0060 | Bike & Ped | Locally Selected | CLARKE CREEK GREENWAY | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | 3.6 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | ENGINEERING | 10000
BL-0060 | Bike & Ped | Locally Selected | CLARKE CREEK GREENWAY | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | 3.6 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L | ENGINEERING | 3000
BL-0060 | Bike & Ped | Locally Selected | CLARKE CREEK GREENWAY | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | 3.6 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 3670000 | FY 2025: 3670000
BL-0060 | Bike & Ped | Locally Selected | CLARKE CREEK GREENWAY | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | 3.6 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L | CONSTRUCTION | 917000 | FY 2025: 917000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 0.44 | PERSON | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | ENGINEERING | 104000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 0.44 | PERSON | 5 | Kerr-Tar RPO |  | Exempt |  | L | ENGINEERING | 26000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 0.44 | PERSON | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 52000 | FY 2025: 52000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 0.44 | PERSON | 5 | Kerr-Tar RPO |  | Exempt |  | L | RIGHT-OF-WAY | 13000 | FY 2025: 13000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 0.44 | PERSON | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 360000 | FY 2025: 360000
BL-0061 | Bike & Ped | Locally Selected | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS /CROSSWALK IMPROVEMENTS, ACCESSIBLE PEDESTRIAN SIGNALS AND RECTANGULAR RAPID FLASHING BEACONS ACROSS NC 157. | 0.44 | PERSON | 5 | Kerr-Tar RPO |  | Exempt |  | L | CONSTRUCTION | 90000 | FY 2025: 90000
BL-0062 | Bike & Ped | Locally Selected | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 0.11 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CMAQ | ENGINEERING | 47000
BL-0062 | Bike & Ped | Locally Selected | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 0.11 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L | ENGINEERING | 12000
BL-0062 | Bike & Ped | Locally Selected | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 0.11 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 176000
BL-0062 | Bike & Ped | Locally Selected | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | 0.11 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L | CONSTRUCTION | 44000
BL-0063 | Bike & Ped | Locally Selected | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | ENGINEERING | 287000
BL-0063 | Bike & Ped | Locally Selected | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | ENGINEERING | 72000
BL-0063 | Bike & Ped | Locally Selected | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 457000 | FY 2025: 457000
BL-0063 | Bike & Ped | Locally Selected | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | RIGHT-OF-WAY | 114000 | FY 2025: 114000
BL-0063 | Bike & Ped | Locally Selected | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 220000 | FY 2025: 2000; FY 2026: 218000
BL-0063 | Bike & Ped | Locally Selected | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CONSTRUCTION | 55000 | FY 2025: 55000
BL-0064 | Bike & Ped | Locally Selected | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | ENGINEERING | 107000
BL-0064 | Bike & Ped | Locally Selected | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 27000
BL-0064 | Bike & Ped | Locally Selected | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 41000 | FY 2025: 41000
BL-0064 | Bike & Ped | Locally Selected | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2025: 10000
BL-0064 | Bike & Ped | Locally Selected | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 208000 | FY 2026: 208000
BL-0064 | Bike & Ped | Locally Selected | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 261000 | FY 2025: 261000
BL-0064 | Bike & Ped | Locally Selected | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 65000 | FY 2025: 65000
BL-0064 | Bike & Ped | Locally Selected | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10 FOOT MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | 0.69 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 52000 | FY 2026: 52000
BL-0065 | Bike & Ped | Locally Selected | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 0.84 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGDA | ENGINEERING | 245000
BL-0065 | Bike & Ped | Locally Selected | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 0.84 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | L | ENGINEERING | 61000
BL-0065 | Bike & Ped | Locally Selected | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 0.84 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGDA | RIGHT-OF-WAY | 225000 | FY 2025: 225000
BL-0065 | Bike & Ped | Locally Selected | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 0.84 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | L | RIGHT-OF-WAY | 56000 | FY 2025: 56000
BL-0065 | Bike & Ped | Locally Selected | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 0.84 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGDA | CONSTRUCTION | 1264000 | FY 2026: 1264000
BL-0065 | Bike & Ped | Locally Selected | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | 0.84 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | L | CONSTRUCTION | 317000 | FY 2026: 317000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | BGDA | ENGINEERING | 350000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | ENGINEERING | 87000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | TADA | RIGHT-OF-WAY | 250000 | FY 2025: 250000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | RIGHT-OF-WAY | 63000 | FY 2025: 63000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | BGDA | CONSTRUCTION | 15000 | FY 2026: 15000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | TAANY | CONSTRUCTION | 1600000 | FY 2026: 1600000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | TADA | CONSTRUCTION | 185000 | FY 2026: 185000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | CONSTRUCTION | 446000 | FY 2026: 446000
BL-0066 | Bike & Ped | Locally Selected | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | 1.26 | CATAWBA | 12 | Greater Hickory MPO | $1.6M IN TADA FUNDS SWITCHED WITH $1.6M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | CONSTRUCTION | 4000 | FY 2026: 4000
BL-0067 | Bike & Ped | Locally Selected | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 0.26 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | ENGINEERING | 120000
BL-0067 | Bike & Ped | Locally Selected | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 0.26 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | L | ENGINEERING | 30000
BL-0067 | Bike & Ped | Locally Selected | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 0.26 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 200000 | FY 2025: 200000
BL-0067 | Bike & Ped | Locally Selected | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 0.26 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | L | RIGHT-OF-WAY | 50000 | FY 2025: 50000
BL-0067 | Bike & Ped | Locally Selected | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 0.26 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | CONSTRUCTION | 1280000 | FY 2025: 1280000
BL-0067 | Bike & Ped | Locally Selected | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | 0.26 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | L | CONSTRUCTION | 320000 | FY 2025: 320000
BL-0068 | Bike & Ped | Locally Selected | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 0.56 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | ENGINEERING | 324000
BL-0068 | Bike & Ped | Locally Selected | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 0.56 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | L | ENGINEERING | 81000
BL-0068 | Bike & Ped | Locally Selected | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 0.56 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | RIGHT-OF-WAY | 400000 | FY 2025: 400000
BL-0068 | Bike & Ped | Locally Selected | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 0.56 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | L | RIGHT-OF-WAY | 100000 | FY 2025: 100000
BL-0068 | Bike & Ped | Locally Selected | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 0.56 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | BGDA | CONSTRUCTION | 680000 | FY 2027: 680000
BL-0068 | Bike & Ped | Locally Selected | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | 0.56 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | L | CONSTRUCTION | 170000 | FY 2027: 170000
BL-0069 | Bike & Ped | Other | WILSON | HOMINY CREEK GREENWAY AND TRAIL NETWORK PLAN. | 3.8 | WILSON | 4 | Upper Coastal Plain RPO | DP FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT. | Exempt |  | DP | ENGINEERING | 950000
BL-0070 | Bike & Ped | Locally Selected | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. |  | CHATHAM | 8 | Durham-Chapel Hill-Carrboro MPO | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | Division 8 |  | BGDACV | ENGINEERING | 5000
BL-0070 | Bike & Ped | Locally Selected | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. |  | CHATHAM | 8 | Durham-Chapel Hill-Carrboro MPO | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | Division 8 |  | BGDA | CONSTRUCTION | 140000
BL-0070 | Bike & Ped | Locally Selected | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. |  | CHATHAM | 8 | Durham-Chapel Hill-Carrboro MPO | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | Division 8 |  | L(M) | CONSTRUCTION | 17000
BL-0070 | Bike & Ped | Locally Selected | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. |  | CHATHAM | 8 | Durham-Chapel Hill-Carrboro MPO | "HF" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS. | Division 8 |  | HF | CONSTRUCTION | 18000
BL-0071 | Bike & Ped | Locally Selected | HIGH POINT | SUNSET DRIVE FROM HARVELL PARK AND GOLDSTON PARK. CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. | 4.3 | GUILFORD | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | Exempt |  | DP | ENGINEERING | 5000000
BL-0071 | Bike & Ped | Locally Selected | HIGH POINT | SUNSET DRIVE FROM HARVELL PARK AND GOLDSTON PARK. CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. | 4.3 | GUILFORD | 7 | High Point Urban Area MPO | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "HF" FUNDING REFLECTS SPOT SAFETY HIGHWAY FUNDS. "O" FUNDING REFLECTS HUD COMMUNITY PROJECT FUNDING. | Exempt |  | DP | RIGHT-OF-WAY | 2000000 | FY 2025: 2000000
BL-0071A | Bike & Ped | Locally Selected | SOUTHWEST HERITAGE GREENWAY | CONSTRUCT GREENWAY ON NEW LOCATION CONNECTING HARVELL PARK AND GOLDSTON PARK. | 0.72 | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | DP | CONSTRUCTION | 6626000 | FY 2025: 6626000
BL-0071A | Bike & Ped | Locally Selected | SOUTHWEST HERITAGE GREENWAY | CONSTRUCT GREENWAY ON NEW LOCATION CONNECTING HARVELL PARK AND GOLDSTON PARK. | 0.72 | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 1000000 | FY 2025: 1000000
BL-0071A | Bike & Ped | Locally Selected | SOUTHWEST HERITAGE GREENWAY | CONSTRUCT GREENWAY ON NEW LOCATION CONNECTING HARVELL PARK AND GOLDSTON PARK. | 0.72 | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | HF | CONSTRUCTION | 200000 | FY 2025: 2000; FY 2026: 159000; FY 2027: 39000
BL-0071B | Bike & Ped | Locally Selected | ELM STREET | CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS FROM SUNSET DRIVE TO COMMERCE AVENUE. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | DP | CONSTRUCTION | 6176000 | FY 2025: 6176000
BL-0071B | Bike & Ped | Locally Selected | ELM STREET | CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS FROM SUNSET DRIVE TO COMMERCE AVENUE. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | O | CONSTRUCTION | 1500000 | FY 2025: 1500000
BL-0071B | Bike & Ped | Locally Selected | ELM STREET | CONSTRUCT PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS FROM SUNSET DRIVE TO COMMERCE AVENUE. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 6188000 | FY 2025: 6188000
BL-0072 | Bike & Ped | Locally Selected | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 258000
BL-0072 | Bike & Ped | Locally Selected | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 64000
BL-0072 | Bike & Ped | Locally Selected | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 92000 | FY 2027: 92000
BL-0072 | Bike & Ped | Locally Selected | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 23000 | FY 2027: 23000
BL-0072 | Bike & Ped | Locally Selected | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 460000 | FY 2027: 460000
BL-0072 | Bike & Ped | Locally Selected | SALEM CREEK GREENWAY BRIDGE | WEST OF SALEM LAKE. CONSTRUCT GREENWAY TRAIL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 115000 | FY 2027: 115000
BL-0073 | Bike & Ped | Locally Selected | SR 1308 (GUM BRANCH ROAD) | CONSTRUCT PEDESTRIAN IMPROVEMENTS ALONG GUM BRANCH ROAD FROM ONSVILLE DRIVE TO ONSVILLE DRIVE. | 1.49 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Exempt |  | CRPDA | ENGINEERING | 256000
BL-0073 | Bike & Ped | Locally Selected | SR 1308 (GUM BRANCH ROAD) | CONSTRUCT PEDESTRIAN IMPROVEMENTS ALONG GUM BRANCH ROAD FROM ONSVILLE DRIVE TO ONSVILLE DRIVE. | 1.49 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 64000
BL-0074 | Bike & Ped | Locally Selected | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 0.1 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 209000
BL-0074 | Bike & Ped | Locally Selected | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 0.1 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | ENGINEERING | 53000
BL-0074 | Bike & Ped | Locally Selected | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 0.1 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | RIGHT-OF-WAY | 20000 | FY 2025: 20000
BL-0074 | Bike & Ped | Locally Selected | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 0.1 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | RIGHT-OF-WAY | 4000 | FY 2025: 4000
BL-0074 | Bike & Ped | Locally Selected | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 0.1 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 438000 | FY 2025: 438000
BL-0074 | Bike & Ped | Locally Selected | US 17 | INSTALLATION OF SIGNALIZED ZEBRA-TYPE PEDESTRIAN CROSSING AT PLOOF ROAD AND OLDE WATERFORD WAY IN LELAND. | 0.1 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 110000 | FY 2025: 110000
BL-0075 | Bike & Ped | Locally Selected | WRIGHTSVILLE BEACH | INSTALLATION OF ON-STREET BICYCLE LANES AND PEDESTRIAN CROSSWALKS ALONG US 76 (CAUSEWAY DRIVE) AND US 74 (WEST SALISBURY STREET) IN WRIGHTSVILLE BEACH. | 2.1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 8000
BL-0075 | Bike & Ped | Locally Selected | WRIGHTSVILLE BEACH | INSTALLATION OF ON-STREET BICYCLE LANES AND PEDESTRIAN CROSSWALKS ALONG US 76 (CAUSEWAY DRIVE) AND US 74 (WEST SALISBURY STREET) IN WRIGHTSVILLE BEACH. | 2.1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | ENGINEERING | 2000
BL-0075 | Bike & Ped | Locally Selected | WRIGHTSVILLE BEACH | INSTALLATION OF ON-STREET BICYCLE LANES AND PEDESTRIAN CROSSWALKS ALONG US 76 (CAUSEWAY DRIVE) AND US 74 (WEST SALISBURY STREET) IN WRIGHTSVILLE BEACH. | 2.1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 1833000
BL-0075 | Bike & Ped | Locally Selected | WRIGHTSVILLE BEACH | INSTALLATION OF ON-STREET BICYCLE LANES AND PEDESTRIAN CROSSWALKS ALONG US 76 (CAUSEWAY DRIVE) AND US 74 (WEST SALISBURY STREET) IN WRIGHTSVILLE BEACH. | 2.1 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 458000
BL-0076 | Bike & Ped | Locally Selected | RICEVILLE ROAD | US 70 TO NORTH OF THE VETERANS AFFAIRS HOSPITAL DRIVEWAY. CONSTRUCT SIDEWALK AND CROSSING IMPROVEMENTS. | 0.16 | BUNCOMBE | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | TADA | ENGINEERING | 187000
BL-0076 | Bike & Ped | Locally Selected | RICEVILLE ROAD | US 70 TO NORTH OF THE VETERANS AFFAIRS HOSPITAL DRIVEWAY. CONSTRUCT SIDEWALK AND CROSSING IMPROVEMENTS. | 0.16 | BUNCOMBE | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | HF(M) | ENGINEERING | 187000
BL-0076 | Bike & Ped | Locally Selected | RICEVILLE ROAD | US 70 TO NORTH OF THE VETERANS AFFAIRS HOSPITAL DRIVEWAY. CONSTRUCT SIDEWALK AND CROSSING IMPROVEMENTS. | 0.16 | BUNCOMBE | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | TADA | RIGHT-OF-WAY | 394000 | FY 2025: 394000
BL-0076 | Bike & Ped | Locally Selected | RICEVILLE ROAD | US 70 TO NORTH OF THE VETERANS AFFAIRS HOSPITAL DRIVEWAY. CONSTRUCT SIDEWALK AND CROSSING IMPROVEMENTS. | 0.16 | BUNCOMBE | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | HF(M) | RIGHT-OF-WAY | 394000 | FY 2025: 394000
BL-0076 | Bike & Ped | Locally Selected | RICEVILLE ROAD | US 70 TO NORTH OF THE VETERANS AFFAIRS HOSPITAL DRIVEWAY. CONSTRUCT SIDEWALK AND CROSSING IMPROVEMENTS. | 0.16 | BUNCOMBE | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | TADA | CONSTRUCTION | 917000 | FY 2026: 917000
BL-0076 | Bike & Ped | Locally Selected | RICEVILLE ROAD | US 70 TO NORTH OF THE VETERANS AFFAIRS HOSPITAL DRIVEWAY. CONSTRUCT SIDEWALK AND CROSSING IMPROVEMENTS. | 0.16 | BUNCOMBE | 13 | French Broad River MPO | HF(M) REPRESENTS OF $1.2M HIGH IMPACT LOW COST AND $415K HMIP | Division 13 |  | HF(M) | CONSTRUCTION | 1034000 | FY 2026: 1034000
BL-0077 | Bike & Ped | Locally Selected | SWANNANOA GREENWAY | BLEACHERY BOULEVARD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO | $2.381M OF STBG-DA FUNDS SWAPPED FOR $2.381M IN TAP-ANYAREA FUNDS ON 8-15-24. | Division 13 |  | BGDA | ENGINEERING | 8000 | FY 2027: 8000
BL-0077 | Bike & Ped | Locally Selected | SWANNANOA GREENWAY | BLEACHERY BOULEVARD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO | $2.381M OF STBG-DA FUNDS SWAPPED FOR $2.381M IN TAP-ANYAREA FUNDS ON 8-15-24. | Division 13 |  | L | ENGINEERING | 2000 | FY 2027: 2000
BL-0077 | Bike & Ped | Locally Selected | SWANNANOA GREENWAY | BLEACHERY BOULEVARD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO | $2.381M OF STBG-DA FUNDS SWAPPED FOR $2.381M IN TAP-ANYAREA FUNDS ON 8-15-24. | Division 13 |  | BGDA | CONSTRUCTION | 111000 | FY 2028: 111000
BL-0077 | Bike & Ped | Locally Selected | SWANNANOA GREENWAY | BLEACHERY BOULEVARD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO | $2.381M OF STBG-DA FUNDS SWAPPED FOR $2.381M IN TAP-ANYAREA FUNDS ON 8-15-24. | Division 13 |  | TAANY | CONSTRUCTION | 2381000 | FY 2028: 2381000
BL-0077 | Bike & Ped | Locally Selected | SWANNANOA GREENWAY | BLEACHERY BOULEVARD TO GLENDALE DRIVE. CONSTRUCT GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO | $2.381M OF STBG-DA FUNDS SWAPPED FOR $2.381M IN TAP-ANYAREA FUNDS ON 8-15-24. | Division 13 |  | L | CONSTRUCTION | 623000 | FY 2028: 623000
BL-0078 | Bike & Ped | Locally Selected | ECUSTA TRAIL | US 64 TO TRANSYLVANIA COUNTY LINE. CONSTRUCT GREENWAY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | BGDA | ENGINEERING | 1440000
BL-0078 | Bike & Ped | Locally Selected | ECUSTA TRAIL | US 64 TO TRANSYLVANIA COUNTY LINE. CONSTRUCT GREENWAY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | ENGINEERING | 360000
BL-0078 | Bike & Ped | Locally Selected | ECUSTA TRAIL | US 64 TO TRANSYLVANIA COUNTY LINE. CONSTRUCT GREENWAY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | BGDA | CONSTRUCTION | 9027000 | FY 2027: 9027000
BL-0078 | Bike & Ped | Locally Selected | ECUSTA TRAIL | US 64 TO TRANSYLVANIA COUNTY LINE. CONSTRUCT GREENWAY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | CONSTRUCTION | 2256000 | FY 2027: 2256000
BL-0079 | Bike & Ped | Locally Selected | TEXAS ROAD | REPLACE EXISTING HIGHWAY BRIDGE WITH PEDESTRIAN BRIDGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | ENGINEERING | 8000
BL-0079 | Bike & Ped | Locally Selected | TEXAS ROAD | REPLACE EXISTING HIGHWAY BRIDGE WITH PEDESTRIAN BRIDGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | ENGINEERING | 2000
BL-0079 | Bike & Ped | Locally Selected | TEXAS ROAD | REPLACE EXISTING HIGHWAY BRIDGE WITH PEDESTRIAN BRIDGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 145000
BL-0079 | Bike & Ped | Locally Selected | TEXAS ROAD | REPLACE EXISTING HIGHWAY BRIDGE WITH PEDESTRIAN BRIDGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 36000
BL-0080 | Bike & Ped | Locally Selected | HUNTERSVILLE | CONSTRUCT GREENWAY CULVERT UNDER US 21. | 0.21 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 8000
BL-0080 | Bike & Ped | Locally Selected | HUNTERSVILLE | CONSTRUCT GREENWAY CULVERT UNDER US 21. | 0.21 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 2000
BL-0080 | Bike & Ped | Locally Selected | HUNTERSVILLE | CONSTRUCT GREENWAY CULVERT UNDER US 21. | 0.21 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 2592000 | FY 2025: 2592000
BL-0080 | Bike & Ped | Locally Selected | HUNTERSVILLE | CONSTRUCT GREENWAY CULVERT UNDER US 21. | 0.21 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 648000 | FY 2025: 648000
BL-0081 | Bike & Ped | Locally Selected | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. CONSTRUCT SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. CONSTRUCT SIDEWALK. | 0.99 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 347000
BL-0081 | Bike & Ped | Locally Selected | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. CONSTRUCT SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. CONSTRUCT SIDEWALK. | 0.99 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 87000
BL-0081 | Bike & Ped | Locally Selected | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. CONSTRUCT SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. CONSTRUCT SIDEWALK. | 0.99 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 106000 | FY 2026: 106000
BL-0081 | Bike & Ped | Locally Selected | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. CONSTRUCT SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. CONSTRUCT SIDEWALK. | 0.99 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 27000 | FY 2026: 27000
BL-0081 | Bike & Ped | Locally Selected | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. CONSTRUCT SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. CONSTRUCT SIDEWALK. | 0.99 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 865000 | FY 2027: 865000
BL-0081 | Bike & Ped | Locally Selected | LEBANON ROAD AND MARGARET WALLACE ROAD | MARGARET WALLACE ROAD TO GRISTMILL LANE. CONSTRUCT SIDEWALK. IDLEWILD ROAD TO LEBANON ROAD. CONSTRUCT SIDEWALK. | 0.99 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 216000 | FY 2027: 216000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. CONSTRUCT SHARED USE PATH. | 0.55 | IREDELL | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | TAANY | ENGINEERING | 172000 | FY 2025: 172000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. CONSTRUCT SHARED USE PATH. | 0.55 | IREDELL | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | ENGINEERING | 172000 | FY 2025: 172000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. CONSTRUCT SHARED USE PATH. | 0.55 | IREDELL | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | TAANY | RIGHT-OF-WAY | 350000 | FY 2027: 350000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. CONSTRUCT SHARED USE PATH. | 0.55 | IREDELL | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | RIGHT-OF-WAY | 350000 | FY 2027: 350000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. CONSTRUCT SHARED USE PATH. | 0.55 | IREDELL | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | TADA | CONSTRUCTION | 358000 | FY 2029: 358000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. CONSTRUCT SHARED USE PATH. | 0.55 | IREDELL | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | TAANY | CONSTRUCTION | 1556000 | FY 2029: 1556000
BL-0082 | Bike & Ped | Locally Selected | NC 115 | FAIRVIEW ROAD TO WATERLYNN ROAD. CONSTRUCT SHARED USE PATH. | 0.55 | IREDELL | 12 | Charlotte Regional TPO | $2.078M IN TADA FUNDS SWITCHED WITH $2.078M IN TAANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | CONSTRUCTION | 1915000 | FY 2029: 1915000
BL-0083 | Bike & Ped | Locally Selected | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | TADA | ENGINEERING | 6000 | FY 2025: 6000
BL-0083 | Bike & Ped | Locally Selected | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | L | ENGINEERING | 4000 | FY 2025: 4000
BL-0083 | Bike & Ped | Locally Selected | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | TADA | RIGHT-OF-WAY | 377000 | FY 2025: 377000
BL-0083 | Bike & Ped | Locally Selected | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | L | RIGHT-OF-WAY | 309000 | FY 2025: 309000
BL-0083 | Bike & Ped | Locally Selected | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | DP | CONSTRUCTION | 12000000 | FY 2027: 12000000
BL-0083 | Bike & Ped | Locally Selected | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | TADA | CONSTRUCTION | 2040000 | FY 2027: 2040000
BL-0083 | Bike & Ped | Locally Selected | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | L | CONSTRUCTION | 4548000 | FY 2027: 4548000
BL-0083 | Bike & Ped | Locally Selected | SUGAR CREEK ROAD | RUMPLE ROAD TO NEVIN ROAD, ROMAN ROAD TO GRAHAM STREET. CONSTRUCT SIDEWALKS. MERLANE DRIVE TO NORTH TRYON STREET. CONSTRUCT MULTI-USE PATH. INSTALL PEDESTRIAN IMPROVEMENTS AT SOFLEY ROAD. IMPROVE SUGAR CREEK, MERLANE, AND MALLARD CREEK ROAD TRANSIT STOPS. | 1.07 | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FY 23 RAISE GRANT FUNDS. | Division 10 |  | L | CONSTRUCTION | 1674000 | FY 2027: 1674000
BL-0084 | Bike & Ped | Locally Selected | ALBEMARLE ROAD AND WILORA LAKE ROAD | REDMAN ROAD TO CENTRAL AVENUE. INSTALL SIDEWALK. ALBEMARLE ROAD TO 100 FEET NORTH OF BARR DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN IMPROVEMENTS AT VARIOUS INTERSECTIONS. | 0.93 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 6000 | FY 2025: 6000
BL-0084 | Bike & Ped | Locally Selected | ALBEMARLE ROAD AND WILORA LAKE ROAD | REDMAN ROAD TO CENTRAL AVENUE. INSTALL SIDEWALK. ALBEMARLE ROAD TO 100 FEET NORTH OF BARR DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN IMPROVEMENTS AT VARIOUS INTERSECTIONS. | 0.93 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 4000 | FY 2025: 4000
BL-0084 | Bike & Ped | Locally Selected | ALBEMARLE ROAD AND WILORA LAKE ROAD | REDMAN ROAD TO CENTRAL AVENUE. INSTALL SIDEWALK. ALBEMARLE ROAD TO 100 FEET NORTH OF BARR DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN IMPROVEMENTS AT VARIOUS INTERSECTIONS. | 0.93 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 1750000 | FY 2027: 1750000
BL-0084 | Bike & Ped | Locally Selected | ALBEMARLE ROAD AND WILORA LAKE ROAD | REDMAN ROAD TO CENTRAL AVENUE. INSTALL SIDEWALK. ALBEMARLE ROAD TO 100 FEET NORTH OF BARR DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN IMPROVEMENTS AT VARIOUS INTERSECTIONS. | 0.93 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 1432000 | FY 2027: 1432000
BL-0085 | Bike & Ped | Locally Selected | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED-USE PATH. | 0.91 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 198000 | FY 2025: 198000
BL-0085 | Bike & Ped | Locally Selected | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED-USE PATH. | 0.91 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 132000 | FY 2025: 132000
BL-0085 | Bike & Ped | Locally Selected | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED-USE PATH. | 0.91 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 361000 | FY 2027: 361000
BL-0085 | Bike & Ped | Locally Selected | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED-USE PATH. | 0.91 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 240000 | FY 2027: 240000
BL-0085 | Bike & Ped | Locally Selected | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED-USE PATH. | 0.91 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 1537000 | FY 2029: 1537000
BL-0085 | Bike & Ped | Locally Selected | BEATY STREET | NORTH MAIN STREET TO GRIFFITH STREET. INSTALL SHARED-USE PATH. | 0.91 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 1024000 | FY 2029: 1024000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | ENGINEERING | 230000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | ENGINEERING | 57000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 138000 | FY 2026: 138000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | RIGHT-OF-WAY | 34000 | FY 2026: 34000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | UTILITIES | 45000 | FY 2026: 45000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | UTILITIES | 11000 | FY 2026: 11000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | CONSTRUCTION | 1250000 | FY 2027: 1250000
BL-0086 | Bike & Ped | Locally Selected | SR 1138 (HICKORY RIDGE ROAD) | SR 1161 (STALLINGS ROAD) TO HICKORY RIDGE MIDDLE SCHOOL. SR 1161 (STALLINGS ROAD) FROM SR 1138 (HICKORY RIDGE ROAD) TO SR 1304 (HARRISBURG VETERANS ROAD). CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | CONSTRUCTION | 313000 | FY 2027: 313000
BL-0087 | Bike & Ped | Locally Selected | VARIOUS CONCORD | ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. GLENN STREET NORTHWEST FROM ELM AVENUE NORTHWEST TO ACADEMY AVENUE NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | ENGINEERING | 8000
BL-0087 | Bike & Ped | Locally Selected | VARIOUS CONCORD | ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. GLENN STREET NORTHWEST FROM ELM AVENUE NORTHWEST TO ACADEMY AVENUE NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | ENGINEERING | 2000
BL-0087 | Bike & Ped | Locally Selected | VARIOUS CONCORD | ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. GLENN STREET NORTHWEST FROM ELM AVENUE NORTHWEST TO ACADEMY AVENUE NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TADA | CONSTRUCTION | 1292000 | FY 2026: 1292000
BL-0087 | Bike & Ped | Locally Selected | VARIOUS CONCORD | ELM AVENUE NORTHWEST FROM GLENN STREET NORTHWEST TO ALEXANDER STREET NORTHWEST. GLENN STREET NORTHWEST FROM ELM AVENUE NORTHWEST TO ACADEMY AVENUE NORTHWEST. CROWELL DRIVE NORTHWEST FROM CLEARWATER ARTS CENTER DRIVEWAY TO CEDAR DRIVE NORTHWEST. CEDAR DRIVE NORTHWEST FROM GEORGIA STREET NORTHWEST TO BEECH STREET NORTHWEST. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L(M) | CONSTRUCTION | 323000 | FY 2026: 323000
BL-0088 | Bike & Ped | Locally Selected | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | TADA | ENGINEERING | 56000
BL-0088 | Bike & Ped | Locally Selected | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | L | ENGINEERING | 14000
BL-0088 | Bike & Ped | Locally Selected | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | TADA | RIGHT-OF-WAY | 72000 | FY 2025: 72000
BL-0088 | Bike & Ped | Locally Selected | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | L | RIGHT-OF-WAY | 18000 | FY 2025: 18000
BL-0088 | Bike & Ped | Locally Selected | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | TADA | UTILITIES | 8000 | FY 2025: 8000
BL-0088 | Bike & Ped | Locally Selected | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | L | UTILITIES | 2000 | FY 2025: 2000
BL-0088 | Bike & Ped | Locally Selected | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | TADA | CONSTRUCTION | 304000 | FY 2026: 304000
BL-0088 | Bike & Ped | Locally Selected | GRANITE QUARRY VARIOUS | KERNS STREET FROM NORTH MAIN STREET TO US 52. NORTH OAK STREET FROM CROOK STREET TO GRANITE CIVIC PARK. CROOK STREET FROM NORTH MAIN STREET TO NORTH OAK STREET. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | L | CONSTRUCTION | 76000 | FY 2026: 76000
BL-0089 | Bike & Ped | Locally Selected | US 401 (SOUTH SAUNDERS STREET) | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | 0.12 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0089 | Bike & Ped | Locally Selected | US 401 (SOUTH SAUNDERS STREET) | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | 0.12 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 2000
BL-0089 | Bike & Ped | Locally Selected | US 401 (SOUTH SAUNDERS STREET) | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | 0.12 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 657000 | FY 2025: 657000
BL-0089 | Bike & Ped | Locally Selected | US 401 (SOUTH SAUNDERS STREET) | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | 0.12 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 164000 | FY 2025: 164000
BL-0089 | Bike & Ped | Locally Selected | US 401 (SOUTH SAUNDERS STREET) | SR 1009 (LAKE WHEELER ROAD) TO NORTH OF DOROTHEA DRIVE IN RALEIGH. CONSTRUCT SHARED USE PATH. | 0.12 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 274000 | FY 2025: 274000
BL-0090 | Bike & Ped | Locally Selected | EAST MCIVER STREET, SOUTH WILMA STREET | EAST MCIVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 0.37 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 120000
BL-0090 | Bike & Ped | Locally Selected | EAST MCIVER STREET, SOUTH WILMA STREET | EAST MCIVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 0.37 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 30000
BL-0090 | Bike & Ped | Locally Selected | EAST MCIVER STREET, SOUTH WILMA STREET | EAST MCIVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 0.37 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BL-0090 | Bike & Ped | Locally Selected | EAST MCIVER STREET, SOUTH WILMA STREET | EAST MCIVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 0.37 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2025: 10000
BL-0090 | Bike & Ped | Locally Selected | EAST MCIVER STREET, SOUTH WILMA STREET | EAST MCIVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 0.37 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 718000 | FY 2025: 718000
BL-0090 | Bike & Ped | Locally Selected | EAST MCIVER STREET, SOUTH WILMA STREET | EAST MCIVER STREET TO SOUTH WILMA STREET IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS AND INSTALL A CROSSWALK. | 0.37 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 180000 | FY 2025: 180000
BL-0091 | Bike & Ped | Locally Selected | HIGGINS GREENWAY | SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | 0.27 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0091 | Bike & Ped | Locally Selected | HIGGINS GREENWAY | SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | 0.27 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 2000
BL-0091 | Bike & Ped | Locally Selected | HIGGINS GREENWAY | SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | 0.27 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1960000 | FY 2025: 1960000
BL-0091 | Bike & Ped | Locally Selected | HIGGINS GREENWAY | SHIRLEY DRIVE TO NORTH OF INTERSECTION OF WALNUT STREET AND SR 1300 (KILDAIRE FARM ROAD) IN CARY. COMPLETE A GAP OF GREENWAY TRAIL. | 0.27 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 490000 | FY 2025: 490000
BL-0092 | Bike & Ped | Locally Selected | ALSTON RIDGE GREENWAY | ALSTON RIDGE GREENWAY TO BASS LAKE GREENWAY IN FUQUAY-VARINA. COMPLETE A GAP OF GREENWAY TRAIL. | 0.41 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 10000
BL-0092 | Bike & Ped | Locally Selected | ALSTON RIDGE GREENWAY | ALSTON RIDGE GREENWAY TO BASS LAKE GREENWAY IN FUQUAY-VARINA. COMPLETE A GAP OF GREENWAY TRAIL. | 0.41 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 7000
BL-0092 | Bike & Ped | Locally Selected | ALSTON RIDGE GREENWAY | ALSTON RIDGE GREENWAY TO BASS LAKE GREENWAY IN FUQUAY-VARINA. COMPLETE A GAP OF GREENWAY TRAIL. | 0.41 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 919000 | FY 2025: 919000
BL-0092 | Bike & Ped | Locally Selected | ALSTON RIDGE GREENWAY | ALSTON RIDGE GREENWAY TO BASS LAKE GREENWAY IN FUQUAY-VARINA. COMPLETE A GAP OF GREENWAY TRAIL. | 0.41 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 612000 | FY 2025: 612000
BL-0093 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | 1.06 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 14000
BL-0093 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | 1.06 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | ENGINEERING | 6000
BL-0093 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | 1.06 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1925000 | FY 2025: 1925000
BL-0093 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | 1.06 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 481000 | FY 2025: 481000
BL-0093 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | NC 55 AND HOLLY GLEN SUBDIVISION SIDEWALK IN HOLLY SPRINGS. COMPLETE A GAP OF GREENWAY TRAIL. | 1.06 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 344000 | FY 2025: 344000
BL-0095 | Bike & Ped | Locally Selected | SAUNDERS STREET | SAUNDERS STREET AT WEST CHATHAM STREET TO HINTON STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS. | 0.4 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 16000
BL-0095 | Bike & Ped | Locally Selected | SAUNDERS STREET | SAUNDERS STREET AT WEST CHATHAM STREET TO HINTON STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS. | 0.4 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 4000
BL-0095 | Bike & Ped | Locally Selected | SAUNDERS STREET | SAUNDERS STREET AT WEST CHATHAM STREET TO HINTON STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS. | 0.4 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1075000 | FY 2025: 1075000
BL-0095 | Bike & Ped | Locally Selected | SAUNDERS STREET | SAUNDERS STREET AT WEST CHATHAM STREET TO HINTON STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS. | 0.4 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 269000 | FY 2025: 269000
BL-0096 | Bike & Ped | Locally Selected | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). CONSTRUCT SHARED USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 198000
BL-0096 | Bike & Ped | Locally Selected | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). CONSTRUCT SHARED USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 132000
BL-0096 | Bike & Ped | Locally Selected | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). CONSTRUCT SHARED USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 361000 | FY 2026: 361000
BL-0096 | Bike & Ped | Locally Selected | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). CONSTRUCT SHARED USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 240000 | FY 2026: 240000
BL-0096 | Bike & Ped | Locally Selected | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). CONSTRUCT SHARED USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 1537000 | FY 2028: 1537000
BL-0096 | Bike & Ped | Locally Selected | BEATY STREET | NC 115 (NORTH MAIN STREET) TO SR 2158 (GRIFFITH STREET). CONSTRUCT SHARED USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 1024000 | FY 2028: 1024000
BL-0101 | Bike & Ped | Locally Selected | CAMERON AVENUE | SOUTH MERRITT MILL ROAD TO NC 86 (SOUTH COLUMBIA STREET) IN CHAPEL HILL. CONSTRUCT BIKE LANES AND CYCLE PATH. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | ENGINEERING | 40000
BL-0101 | Bike & Ped | Locally Selected | CAMERON AVENUE | SOUTH MERRITT MILL ROAD TO NC 86 (SOUTH COLUMBIA STREET) IN CHAPEL HILL. CONSTRUCT BIKE LANES AND CYCLE PATH. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | ENGINEERING | 10000
BL-0101 | Bike & Ped | Locally Selected | CAMERON AVENUE | SOUTH MERRITT MILL ROAD TO NC 86 (SOUTH COLUMBIA STREET) IN CHAPEL HILL. CONSTRUCT BIKE LANES AND CYCLE PATH. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | RIGHT-OF-WAY | 140000 | FY 2026: 140000
BL-0101 | Bike & Ped | Locally Selected | CAMERON AVENUE | SOUTH MERRITT MILL ROAD TO NC 86 (SOUTH COLUMBIA STREET) IN CHAPEL HILL. CONSTRUCT BIKE LANES AND CYCLE PATH. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 35000 | FY 2026: 35000
BL-0101 | Bike & Ped | Locally Selected | CAMERON AVENUE | SOUTH MERRITT MILL ROAD TO NC 86 (SOUTH COLUMBIA STREET) IN CHAPEL HILL. CONSTRUCT BIKE LANES AND CYCLE PATH. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 580000 | FY 2027: 580000
BL-0101 | Bike & Ped | Locally Selected | CAMERON AVENUE | SOUTH MERRITT MILL ROAD TO NC 86 (SOUTH COLUMBIA STREET) IN CHAPEL HILL. CONSTRUCT BIKE LANES AND CYCLE PATH. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 145000 | FY 2027: 145000
BL-0105 | Bike & Ped | Locally Selected | DALLAS PARK GREENWAY (LEISURE LANE) | NC 275 TO TRAILHEAD FOR C-5606E NEAR SPORTSMAN DRIVE. CONSTRUCT GREEWAY. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | ENGINEERING | 124000
BL-0105 | Bike & Ped | Locally Selected | DALLAS PARK GREENWAY (LEISURE LANE) | NC 275 TO TRAILHEAD FOR C-5606E NEAR SPORTSMAN DRIVE. CONSTRUCT GREEWAY. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L | ENGINEERING | 31000
BL-0105 | Bike & Ped | Locally Selected | DALLAS PARK GREENWAY (LEISURE LANE) | NC 275 TO TRAILHEAD FOR C-5606E NEAR SPORTSMAN DRIVE. CONSTRUCT GREEWAY. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 339000 | FY 2026: 3000; FY 2027: 336000
BL-0105 | Bike & Ped | Locally Selected | DALLAS PARK GREENWAY (LEISURE LANE) | NC 275 TO TRAILHEAD FOR C-5606E NEAR SPORTSMAN DRIVE. CONSTRUCT GREEWAY. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L | CONSTRUCTION | 85000 | FY 2026: 85000
BL-0106 | Bike & Ped | Locally Selected | HIGGINS GREENWAY (PHASE IV) | KILDARE FARM ROAD TO HARRISON AVENUE IN CARY. CONSTRUCT MULTI-USE PATH. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0106 | Bike & Ped | Locally Selected | HIGGINS GREENWAY (PHASE IV) | KILDARE FARM ROAD TO HARRISON AVENUE IN CARY. CONSTRUCT MULTI-USE PATH. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 2000
BL-0106 | Bike & Ped | Locally Selected | HIGGINS GREENWAY (PHASE IV) | KILDARE FARM ROAD TO HARRISON AVENUE IN CARY. CONSTRUCT MULTI-USE PATH. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1936000 | FY 2025: 1551000; FY 2026: 366000
BL-0106 | Bike & Ped | Locally Selected | HIGGINS GREENWAY (PHASE IV) | KILDARE FARM ROAD TO HARRISON AVENUE IN CARY. CONSTRUCT MULTI-USE PATH. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 1015000
BL-0107 | Bike & Ped | Locally Selected | ALSTON RIDGE GREENWAY | ALSTON RIDGE TO BASS LAKE GREEWAY IN FUQUAY VARINA. CONSTRUCT 2000 FEET OF GREENWAY. | 0.41 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0107 | Bike & Ped | Locally Selected | ALSTON RIDGE GREENWAY | ALSTON RIDGE TO BASS LAKE GREEWAY IN FUQUAY VARINA. CONSTRUCT 2000 FEET OF GREENWAY. | 0.41 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 2000
BL-0107 | Bike & Ped | Locally Selected | ALSTON RIDGE GREENWAY | ALSTON RIDGE TO BASS LAKE GREEWAY IN FUQUAY VARINA. CONSTRUCT 2000 FEET OF GREENWAY. | 0.41 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 929000
BL-0107 | Bike & Ped | Locally Selected | ALSTON RIDGE GREENWAY | ALSTON RIDGE TO BASS LAKE GREEWAY IN FUQUAY VARINA. CONSTRUCT 2000 FEET OF GREENWAY. | 0.41 | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 619000
BL-0108 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | PARKWAY GREENWAY CONNECTION AND ALIGNMENT IN HOLLY SPRINGS. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0108 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | PARKWAY GREENWAY CONNECTION AND ALIGNMENT IN HOLLY SPRINGS. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 2000
BL-0108 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | PARKWAY GREENWAY CONNECTION AND ALIGNMENT IN HOLLY SPRINGS. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1919000 | FY 2025: 1585000; FY 2026: 315000
BL-0108 | Bike & Ped | Locally Selected | UTLEY CREEK GREENWAY WEST | PARKWAY GREENWAY CONNECTION AND ALIGNMENT IN HOLLY SPRINGS. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 830000
BL-0109 | Bike & Ped | Locally Selected | SOUTHWEST DOWNTOWN BIKE AND PEDESTRIAN GATEWAY | LAKE WHEELER ROAD FROM CENTENNIAL PARKWAY TO WEST SOUTH STREET IN RALEIGH. CONSTRUCT SHARED USE PATH. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BL-0109 | Bike & Ped | Locally Selected | SOUTHWEST DOWNTOWN BIKE AND PEDESTRIAN GATEWAY | LAKE WHEELER ROAD FROM CENTENNIAL PARKWAY TO WEST SOUTH STREET IN RALEIGH. CONSTRUCT SHARED USE PATH. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 2000
BL-0109 | Bike & Ped | Locally Selected | SOUTHWEST DOWNTOWN BIKE AND PEDESTRIAN GATEWAY | LAKE WHEELER ROAD FROM CENTENNIAL PARKWAY TO WEST SOUTH STREET IN RALEIGH. CONSTRUCT SHARED USE PATH. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 657000 | FY 2025: 650000
BL-0109 | Bike & Ped | Locally Selected | SOUTHWEST DOWNTOWN BIKE AND PEDESTRIAN GATEWAY | LAKE WHEELER ROAD FROM CENTENNIAL PARKWAY TO WEST SOUTH STREET IN RALEIGH. CONSTRUCT SHARED USE PATH. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 438000
BL-0114 | Bike & Ped | Locally Selected | SHALLOWFORD ROAD | LOWES FOODS DRIVE TO SHALLOWFORD RESERVE DRIVE IN LEWISVILLE. CONSTRUCT SIDEWALK. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | ENGINEERING | 167000 | FY 2026: 167000
BL-0114 | Bike & Ped | Locally Selected | SHALLOWFORD ROAD | LOWES FOODS DRIVE TO SHALLOWFORD RESERVE DRIVE IN LEWISVILLE. CONSTRUCT SIDEWALK. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | ENGINEERING | 42000 | FY 2026: 42000
BL-0114 | Bike & Ped | Locally Selected | SHALLOWFORD ROAD | LOWES FOODS DRIVE TO SHALLOWFORD RESERVE DRIVE IN LEWISVILLE. CONSTRUCT SIDEWALK. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 127000 | FY 2027: 127000
BL-0114 | Bike & Ped | Locally Selected | SHALLOWFORD ROAD | LOWES FOODS DRIVE TO SHALLOWFORD RESERVE DRIVE IN LEWISVILLE. CONSTRUCT SIDEWALK. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | RIGHT-OF-WAY | 32000 | FY 2027: 32000
BL-0114 | Bike & Ped | Locally Selected | SHALLOWFORD ROAD | LOWES FOODS DRIVE TO SHALLOWFORD RESERVE DRIVE IN LEWISVILLE. CONSTRUCT SIDEWALK. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 758000 | FY 2028: 758000
BL-0114 | Bike & Ped | Locally Selected | SHALLOWFORD ROAD | LOWES FOODS DRIVE TO SHALLOWFORD RESERVE DRIVE IN LEWISVILLE. CONSTRUCT SIDEWALK. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | CONSTRUCTION | 190000 | FY 2028: 190000
BL-0115 | Bike & Ped | Locally Selected | CLEMENT BOULEVARD; 21ST STREET NW | 21ST STREET NW TO 19TH STREET NW IN HICKORY. CLEMENT BOULEVARD TO 9TH AVENUE DRIVE NW IN HICKORY. CONSTRUCT MULTI-USE TRAIL. | 0.31 | CATAWBA | 12 | Greater Hickory MPO | $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | CRPDA | ENGINEERING | 240000
BL-0115 | Bike & Ped | Locally Selected | CLEMENT BOULEVARD; 21ST STREET NW | 21ST STREET NW TO 19TH STREET NW IN HICKORY. CLEMENT BOULEVARD TO 9TH AVENUE DRIVE NW IN HICKORY. CONSTRUCT MULTI-USE TRAIL. | 0.31 | CATAWBA | 12 | Greater Hickory MPO | $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | ENGINEERING | 60000
BL-0115 | Bike & Ped | Locally Selected | CLEMENT BOULEVARD; 21ST STREET NW | 21ST STREET NW TO 19TH STREET NW IN HICKORY. CLEMENT BOULEVARD TO 9TH AVENUE DRIVE NW IN HICKORY. CONSTRUCT MULTI-USE TRAIL. | 0.31 | CATAWBA | 12 | Greater Hickory MPO | $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | CRPDA | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BL-0115 | Bike & Ped | Locally Selected | CLEMENT BOULEVARD; 21ST STREET NW | 21ST STREET NW TO 19TH STREET NW IN HICKORY. CLEMENT BOULEVARD TO 9TH AVENUE DRIVE NW IN HICKORY. CONSTRUCT MULTI-USE TRAIL. | 0.31 | CATAWBA | 12 | Greater Hickory MPO | $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | RIGHT-OF-WAY | 10000 | FY 2025: 10000
BL-0115 | Bike & Ped | Locally Selected | CLEMENT BOULEVARD; 21ST STREET NW | 21ST STREET NW TO 19TH STREET NW IN HICKORY. CLEMENT BOULEVARD TO 9TH AVENUE DRIVE NW IN HICKORY. CONSTRUCT MULTI-USE TRAIL. | 0.31 | CATAWBA | 12 | Greater Hickory MPO | $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | BGANY | CONSTRUCTION | 1355000 | FY 2025: 1355000
BL-0115 | Bike & Ped | Locally Selected | CLEMENT BOULEVARD; 21ST STREET NW | 21ST STREET NW TO 19TH STREET NW IN HICKORY. CLEMENT BOULEVARD TO 9TH AVENUE DRIVE NW IN HICKORY. CONSTRUCT MULTI-USE TRAIL. | 0.31 | CATAWBA | 12 | Greater Hickory MPO | $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | BGDA | CONSTRUCTION | 765000 | FY 2025: 765000
BL-0115 | Bike & Ped | Locally Selected | CLEMENT BOULEVARD; 21ST STREET NW | 21ST STREET NW TO 19TH STREET NW IN HICKORY. CLEMENT BOULEVARD TO 9TH AVENUE DRIVE NW IN HICKORY. CONSTRUCT MULTI-USE TRAIL. | 0.31 | CATAWBA | 12 | Greater Hickory MPO | $1.355M IN BGDA FUNDS SWITCHED WITH $1.355M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 12 |  | L | CONSTRUCTION | 530000 | FY 2025: 530000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | TAANY | ENGINEERING | 280000 | FY 2025: 280000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | TAANY | ENGINEERING | 600000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | L(M) | ENGINEERING | 70000 | FY 2025: 70000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | L(M) | ENGINEERING | 150000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | HP | RIGHT-OF-WAY | 750000 | FY 2026: 750000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | L(M) | RIGHT-OF-WAY | 188000 | FY 2026: 188000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | HP | CONSTRUCTION | 2970000 | FY 2027: 2970000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | TAANY | CONSTRUCTION | 1680000 | FY 2027: 1680000
BL-0116 | Bike & Ped | Locally Selected | A & Y GREENWAY | HILL STREET TO ROLLINS ROAD. EXTEND GREENWAY. |  | GUILFORD | 7 | Greensboro Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC205. | Division 7 |  | L(M) | CONSTRUCTION | 1163000 | FY 2027: 1163000
BL-0117 | Bike & Ped | Locally Selected | A & Y GREENWAY | A & Y GREENWAY AT LAKE BRANDT. REPLACE BRIDGE, IMPROVE GREENWAY, AND IMPROVE CROSSING AT STRAWBERRY ROAD. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 88000
BL-0117 | Bike & Ped | Locally Selected | A & Y GREENWAY | A & Y GREENWAY AT LAKE BRANDT. REPLACE BRIDGE, IMPROVE GREENWAY, AND IMPROVE CROSSING AT STRAWBERRY ROAD. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 22000
BL-0117 | Bike & Ped | Locally Selected | A & Y GREENWAY | A & Y GREENWAY AT LAKE BRANDT. REPLACE BRIDGE, IMPROVE GREENWAY, AND IMPROVE CROSSING AT STRAWBERRY ROAD. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 1942000 | FY 2025: 1459000; FY 2026: 483000
BL-0117 | Bike & Ped | Locally Selected | A & Y GREENWAY | A & Y GREENWAY AT LAKE BRANDT. REPLACE BRIDGE, IMPROVE GREENWAY, AND IMPROVE CROSSING AT STRAWBERRY ROAD. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 486000 | FY 2025: 486000
BL-0118 | Bike & Ped | Locally Selected | US 117 (COLLEGE ROAD) | SR 2048 (GORDON ROAD) TO SR 2206 (NORTHCHASE PARKWAY). CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 2.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | RIGHT-OF-WAY | 410000 | FY 2025: 410000
BL-0118 | Bike & Ped | Locally Selected | US 117 (COLLEGE ROAD) | SR 2048 (GORDON ROAD) TO SR 2206 (NORTHCHASE PARKWAY). CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 2.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | RIGHT-OF-WAY | 103000 | FY 2025: 103000
BL-0118 | Bike & Ped | Locally Selected | US 117 (COLLEGE ROAD) | SR 2048 (GORDON ROAD) TO SR 2206 (NORTHCHASE PARKWAY). CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 2.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 1430000 | FY 2026: 1430000
BL-0118 | Bike & Ped | Locally Selected | US 117 (COLLEGE ROAD) | SR 2048 (GORDON ROAD) TO SR 2206 (NORTHCHASE PARKWAY). CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 2.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 357000 | FY 2026: 357000
BL-0119 | Bike & Ped | Locally Selected | MCDOWELL CREEK GREENWAY | NC 73 IN HUNTERSVILLE. CONSTRUCT PEDESTRIAN BRIDGE OVER NC 73 NEAR LINDHOLM DRIVE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 3095000 | FY 2027: 3095000
BL-0119 | Bike & Ped | Locally Selected | MCDOWELL CREEK GREENWAY | NC 73 IN HUNTERSVILLE. CONSTRUCT PEDESTRIAN BRIDGE OVER NC 73 NEAR LINDHOLM DRIVE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L(M) | CONSTRUCTION | 2064000 | FY 2027: 2064000
BL-0120 | Bike & Ped | Locally Selected | BAIN SCHOOL ROAD | GAIT DRIVE TO PHILADELPHIA CHURCH ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 305000 | FY 2026: 305000
BL-0120 | Bike & Ped | Locally Selected | BAIN SCHOOL ROAD | GAIT DRIVE TO PHILADELPHIA CHURCH ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 164000 | FY 2026: 164000
BL-0120 | Bike & Ped | Locally Selected | BAIN SCHOOL ROAD | GAIT DRIVE TO PHILADELPHIA CHURCH ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 143000 | FY 2028: 143000
BL-0120 | Bike & Ped | Locally Selected | BAIN SCHOOL ROAD | GAIT DRIVE TO PHILADELPHIA CHURCH ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 77000 | FY 2028: 77000
BL-0120 | Bike & Ped | Locally Selected | BAIN SCHOOL ROAD | GAIT DRIVE TO PHILADELPHIA CHURCH ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 715000 | FY 2030: 715000
BL-0120 | Bike & Ped | Locally Selected | BAIN SCHOOL ROAD | GAIT DRIVE TO PHILADELPHIA CHURCH ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 385000 | FY 2030: 385000
BL-0121 | Bike & Ped | Locally Selected | LAWYERS ROAD | PIAFFE AVENUE TO THOMPSON ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 255000 | FY 2026: 255000
BL-0121 | Bike & Ped | Locally Selected | LAWYERS ROAD | PIAFFE AVENUE TO THOMPSON ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 64000 | FY 2026: 64000
BL-0121 | Bike & Ped | Locally Selected | LAWYERS ROAD | PIAFFE AVENUE TO THOMPSON ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 189000 | FY 2028: 189000
BL-0121 | Bike & Ped | Locally Selected | LAWYERS ROAD | PIAFFE AVENUE TO THOMPSON ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 47000 | FY 2028: 47000
BL-0121 | Bike & Ped | Locally Selected | LAWYERS ROAD | PIAFFE AVENUE TO THOMPSON ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 619000 | FY 2030: 619000
BL-0121 | Bike & Ped | Locally Selected | LAWYERS ROAD | PIAFFE AVENUE TO THOMPSON ROAD IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 155000 | FY 2030: 155000
BL-0122 | Bike & Ped | Locally Selected | PATTERSON HEIGHTS | WEST MOORE AVENUE TO WEST IREDELL AVENUE IN MOORESVILLE. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | ENGINEERING | 8000 | FY 2025: 8000
BL-0122 | Bike & Ped | Locally Selected | PATTERSON HEIGHTS | WEST MOORE AVENUE TO WEST IREDELL AVENUE IN MOORESVILLE. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | ENGINEERING | 2000 | FY 2025: 2000
BL-0122 | Bike & Ped | Locally Selected | PATTERSON HEIGHTS | WEST MOORE AVENUE TO WEST IREDELL AVENUE IN MOORESVILLE. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDA | CONSTRUCTION | 2518000 | FY 2028: 2518000
BL-0122 | Bike & Ped | Locally Selected | PATTERSON HEIGHTS | WEST MOORE AVENUE TO WEST IREDELL AVENUE IN MOORESVILLE. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | CONSTRUCTION | 630000 | FY 2028: 630000
BL-0123 | Bike & Ped | Locally Selected | ROCKY RIVER ROAD | ROCKLAND DRIVE TO OLD CONCORD ROAD IN CHARLOTTE. CONSTRUCT SHARED-USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 5000 | FY 2025: 5000
BL-0123 | Bike & Ped | Locally Selected | ROCKY RIVER ROAD | ROCKLAND DRIVE TO OLD CONCORD ROAD IN CHARLOTTE. CONSTRUCT SHARED-USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 5000 | FY 2025: 5000
BL-0123 | Bike & Ped | Locally Selected | ROCKY RIVER ROAD | ROCKLAND DRIVE TO OLD CONCORD ROAD IN CHARLOTTE. CONSTRUCT SHARED-USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 1976000 | FY 2027: 1976000
BL-0123 | Bike & Ped | Locally Selected | ROCKY RIVER ROAD | ROCKLAND DRIVE TO OLD CONCORD ROAD IN CHARLOTTE. CONSTRUCT SHARED-USE PATH. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 1976000 | FY 2027: 1976000
BL-0124 | Bike & Ped | Locally Selected | TRUELIGHT CHURCH ROAD | WILGROVE-MINT ROAD TO HEATHER NICOLE LANE IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | ENGINEERING | 400000 | FY 2026: 400000
BL-0124 | Bike & Ped | Locally Selected | TRUELIGHT CHURCH ROAD | WILGROVE-MINT ROAD TO HEATHER NICOLE LANE IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 100000 | FY 2026: 100000
BL-0124 | Bike & Ped | Locally Selected | TRUELIGHT CHURCH ROAD | WILGROVE-MINT ROAD TO HEATHER NICOLE LANE IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | RIGHT-OF-WAY | 99000 | FY 2028: 99000
BL-0124 | Bike & Ped | Locally Selected | TRUELIGHT CHURCH ROAD | WILGROVE-MINT ROAD TO HEATHER NICOLE LANE IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 25000 | FY 2028: 25000
BL-0124 | Bike & Ped | Locally Selected | TRUELIGHT CHURCH ROAD | WILGROVE-MINT ROAD TO HEATHER NICOLE LANE IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 973000 | FY 2030: 973000
BL-0124 | Bike & Ped | Locally Selected | TRUELIGHT CHURCH ROAD | WILGROVE-MINT ROAD TO HEATHER NICOLE LANE IN MINT HILL. CONSTRUCT SIDEWALK. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 243000 | FY 2030: 243000
BL-0125 | Bike & Ped | Locally Selected | MAIN STREET | MOORE STREET TO SMITH STREET IN CLAYTON. CONSTRUCT SIDEWALK ON BOTH SIDES OF MAIN STREET FROM ROBERTSON STREET TO MOORE STREET. ADD CROSSWALKS, CURB EXTENSIONS, AND PEDESTRIAN SIGNALS FROM MOORE STREET TO SMITH STREET. | 1 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TADA | RIGHT-OF-WAY | 35000 | FY 2025: 35000
BL-0125 | Bike & Ped | Locally Selected | MAIN STREET | MOORE STREET TO SMITH STREET IN CLAYTON. CONSTRUCT SIDEWALK ON BOTH SIDES OF MAIN STREET FROM ROBERTSON STREET TO MOORE STREET. ADD CROSSWALKS, CURB EXTENSIONS, AND PEDESTRIAN SIGNALS FROM MOORE STREET TO SMITH STREET. | 1 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | RIGHT-OF-WAY | 6000 | FY 2025: 6000
BL-0125 | Bike & Ped | Locally Selected | MAIN STREET | MOORE STREET TO SMITH STREET IN CLAYTON. CONSTRUCT SIDEWALK ON BOTH SIDES OF MAIN STREET FROM ROBERTSON STREET TO MOORE STREET. ADD CROSSWALKS, CURB EXTENSIONS, AND PEDESTRIAN SIGNALS FROM MOORE STREET TO SMITH STREET. | 1 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 9000 | FY 2025: 9000
BL-0125 | Bike & Ped | Locally Selected | MAIN STREET | MOORE STREET TO SMITH STREET IN CLAYTON. CONSTRUCT SIDEWALK ON BOTH SIDES OF MAIN STREET FROM ROBERTSON STREET TO MOORE STREET. ADD CROSSWALKS, CURB EXTENSIONS, AND PEDESTRIAN SIGNALS FROM MOORE STREET TO SMITH STREET. | 1 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TADA | CONSTRUCTION | 1050000 | FY 2025: 1050000
BL-0125 | Bike & Ped | Locally Selected | MAIN STREET | MOORE STREET TO SMITH STREET IN CLAYTON. CONSTRUCT SIDEWALK ON BOTH SIDES OF MAIN STREET FROM ROBERTSON STREET TO MOORE STREET. ADD CROSSWALKS, CURB EXTENSIONS, AND PEDESTRIAN SIGNALS FROM MOORE STREET TO SMITH STREET. | 1 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 263000 | FY 2025: 263000
BL-0125 | Bike & Ped | Locally Selected | MAIN STREET | MOORE STREET TO SMITH STREET IN CLAYTON. CONSTRUCT SIDEWALK ON BOTH SIDES OF MAIN STREET FROM ROBERTSON STREET TO MOORE STREET. ADD CROSSWALKS, CURB EXTENSIONS, AND PEDESTRIAN SIGNALS FROM MOORE STREET TO SMITH STREET. | 1 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | CONSTRUCTION | 187000 | FY 2025: 187000
BL-0126 | Bike & Ped | NCDOT Selected (Other Selection Process) | OPTIMIST FARM GREENWAY | EXISTING SEGMENT OF THE GREENWAY BEHIND TRUELOVE DRIVE SOUTH AND WEST TO WEST LAKE ROAD IN CARY. CONSTRUCT 10' WIDE GREENWAY AND .2 MILES OF SIDEWALK. INCLUDES PEDESTRIAN IMPROVEMENTS AT ONE INTERSECTION, AND MID-BLOCK CROSSINGS ON OPTIMIST FARM ROAD (RRFB OR PHB) AND ON HENDERSON ROAD (HIGH VISIBILITY CROSSWALK AND PED CROSSING SIGNS). | 1.2 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | CMAQ | CONSTRUCTION | 3250000 | FY 2025: 3250000
BL-0126 | Bike & Ped | NCDOT Selected (Other Selection Process) | OPTIMIST FARM GREENWAY | EXISTING SEGMENT OF THE GREENWAY BEHIND TRUELOVE DRIVE SOUTH AND WEST TO WEST LAKE ROAD IN CARY. CONSTRUCT 10' WIDE GREENWAY AND .2 MILES OF SIDEWALK. INCLUDES PEDESTRIAN IMPROVEMENTS AT ONE INTERSECTION, AND MID-BLOCK CROSSINGS ON OPTIMIST FARM ROAD (RRFB OR PHB) AND ON HENDERSON ROAD (HIGH VISIBILITY CROSSWALK AND PED CROSSING SIGNS). | 1.2 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 937000 | FY 2025: 937000
BL-0126 | Bike & Ped | NCDOT Selected (Other Selection Process) | OPTIMIST FARM GREENWAY | EXISTING SEGMENT OF THE GREENWAY BEHIND TRUELOVE DRIVE SOUTH AND WEST TO WEST LAKE ROAD IN CARY. CONSTRUCT 10' WIDE GREENWAY AND .2 MILES OF SIDEWALK. INCLUDES PEDESTRIAN IMPROVEMENTS AT ONE INTERSECTION, AND MID-BLOCK CROSSINGS ON OPTIMIST FARM ROAD (RRFB OR PHB) AND ON HENDERSON ROAD (HIGH VISIBILITY CROSSWALK AND PED CROSSING SIGNS). | 1.2 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 813000 | FY 2025: 813000
BL-0127 | Bike & Ped | NCDOT Selected (Other Selection Process) | MAIN STREET | UPGRADE CROSSWALKS ALONG MAIN STREET, ADD A NEW MID-BLOCK CROSSING AT THE INTERSECTION OF WATER STREET AND MAIN STREET, AND AN IMPROVED CROSSING CONFIGURATION FOR THE FRANKLINTON TO NOVOZYMES RAIL TRAIL. | 0.5 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 68000 | FY 2025: 68000
BL-0127 | Bike & Ped | NCDOT Selected (Other Selection Process) | MAIN STREET | UPGRADE CROSSWALKS ALONG MAIN STREET, ADD A NEW MID-BLOCK CROSSING AT THE INTERSECTION OF WATER STREET AND MAIN STREET, AND AN IMPROVED CROSSING CONFIGURATION FOR THE FRANKLINTON TO NOVOZYMES RAIL TRAIL. | 0.5 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 17000 | FY 2025: 17000
BL-0127 | Bike & Ped | NCDOT Selected (Other Selection Process) | MAIN STREET | UPGRADE CROSSWALKS ALONG MAIN STREET, ADD A NEW MID-BLOCK CROSSING AT THE INTERSECTION OF WATER STREET AND MAIN STREET, AND AN IMPROVED CROSSING CONFIGURATION FOR THE FRANKLINTON TO NOVOZYMES RAIL TRAIL. | 0.5 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 600000 | FY 2025: 600000
BL-0127 | Bike & Ped | NCDOT Selected (Other Selection Process) | MAIN STREET | UPGRADE CROSSWALKS ALONG MAIN STREET, ADD A NEW MID-BLOCK CROSSING AT THE INTERSECTION OF WATER STREET AND MAIN STREET, AND AN IMPROVED CROSSING CONFIGURATION FOR THE FRANKLINTON TO NOVOZYMES RAIL TRAIL. | 0.5 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 150000 | FY 2025: 150000
BL-0128 | Bike & Ped | Locally Selected | VANDORA SPRINGS ROAD; WOODLAND ROAD | VANDORA SPRINGS ELEMENTARY SCHOOL TO WOODLAND ROAD; VANDORA SPRINGS ROAD TO PINEVIEW DRIVE IN GARNER. CONSTRUCT SIDEWALK. | 0.15 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 187000 | FY 2025: 187000
BL-0128 | Bike & Ped | Locally Selected | VANDORA SPRINGS ROAD; WOODLAND ROAD | VANDORA SPRINGS ELEMENTARY SCHOOL TO WOODLAND ROAD; VANDORA SPRINGS ROAD TO PINEVIEW DRIVE IN GARNER. CONSTRUCT SIDEWALK. | 0.15 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 47000 | FY 2025: 47000
BL-0128 | Bike & Ped | Locally Selected | VANDORA SPRINGS ROAD; WOODLAND ROAD | VANDORA SPRINGS ELEMENTARY SCHOOL TO WOODLAND ROAD; VANDORA SPRINGS ROAD TO PINEVIEW DRIVE IN GARNER. CONSTRUCT SIDEWALK. | 0.15 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 58000 | FY 2025: 58000
BL-0128 | Bike & Ped | Locally Selected | VANDORA SPRINGS ROAD; WOODLAND ROAD | VANDORA SPRINGS ELEMENTARY SCHOOL TO WOODLAND ROAD; VANDORA SPRINGS ROAD TO PINEVIEW DRIVE IN GARNER. CONSTRUCT SIDEWALK. | 0.15 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 15000 | FY 2025: 15000
BL-0129 | Bike & Ped | NCDOT Selected (Other Selection Process) | SOUTH GARNER GREENWAY | VANDORA SPRINGS ROAD AND BUFFALOE ROAD TO LAKE BENSON PARK IN GARNER. CONSTRUCT A MULTI-USE PATH ALONG THE WEST / SOUTH SIDE OF BUFFALOE ROAD. INCLUDES A PEDESTRIAN BRIDGE CROSSING AND BOARDWALK SEGMENTS. | 1.75 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | CMAQ | ENGINEERING | 8000 | FY 2025: 8000
BL-0129 | Bike & Ped | NCDOT Selected (Other Selection Process) | SOUTH GARNER GREENWAY | VANDORA SPRINGS ROAD AND BUFFALOE ROAD TO LAKE BENSON PARK IN GARNER. CONSTRUCT A MULTI-USE PATH ALONG THE WEST / SOUTH SIDE OF BUFFALOE ROAD. INCLUDES A PEDESTRIAN BRIDGE CROSSING AND BOARDWALK SEGMENTS. | 1.75 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 6000 | FY 2025: 6000
BL-0129 | Bike & Ped | NCDOT Selected (Other Selection Process) | SOUTH GARNER GREENWAY | VANDORA SPRINGS ROAD AND BUFFALOE ROAD TO LAKE BENSON PARK IN GARNER. CONSTRUCT A MULTI-USE PATH ALONG THE WEST / SOUTH SIDE OF BUFFALOE ROAD. INCLUDES A PEDESTRIAN BRIDGE CROSSING AND BOARDWALK SEGMENTS. | 1.75 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 2000 | FY 2025: 2000
BL-0129 | Bike & Ped | NCDOT Selected (Other Selection Process) | SOUTH GARNER GREENWAY | VANDORA SPRINGS ROAD AND BUFFALOE ROAD TO LAKE BENSON PARK IN GARNER. CONSTRUCT A MULTI-USE PATH ALONG THE WEST / SOUTH SIDE OF BUFFALOE ROAD. INCLUDES A PEDESTRIAN BRIDGE CROSSING AND BOARDWALK SEGMENTS. | 1.75 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | CMAQ | CONSTRUCTION | 2650000 | FY 2025: 2650000
BL-0129 | Bike & Ped | NCDOT Selected (Other Selection Process) | SOUTH GARNER GREENWAY | VANDORA SPRINGS ROAD AND BUFFALOE ROAD TO LAKE BENSON PARK IN GARNER. CONSTRUCT A MULTI-USE PATH ALONG THE WEST / SOUTH SIDE OF BUFFALOE ROAD. INCLUDES A PEDESTRIAN BRIDGE CROSSING AND BOARDWALK SEGMENTS. | 1.75 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 1987000 | FY 2025: 1987000
BL-0129 | Bike & Ped | NCDOT Selected (Other Selection Process) | SOUTH GARNER GREENWAY | VANDORA SPRINGS ROAD AND BUFFALOE ROAD TO LAKE BENSON PARK IN GARNER. CONSTRUCT A MULTI-USE PATH ALONG THE WEST / SOUTH SIDE OF BUFFALOE ROAD. INCLUDES A PEDESTRIAN BRIDGE CROSSING AND BOARDWALK SEGMENTS. | 1.75 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 663000 | FY 2025: 663000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (CAMERON ROAD) | FROM HOPE MILLS MIDDLE SCHOOL TO NC 59 (SOUTH MAIN STREET) IN HOPE MILLS. INSTALL NEW CONCRETE SIDEWALK. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 20000 | FY 2025: 20000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (CAMERON ROAD) | FROM HOPE MILLS MIDDLE SCHOOL TO NC 59 (SOUTH MAIN STREET) IN HOPE MILLS. INSTALL NEW CONCRETE SIDEWALK. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 5000 | FY 2025: 5000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (CAMERON ROAD) | FROM HOPE MILLS MIDDLE SCHOOL TO NC 59 (SOUTH MAIN STREET) IN HOPE MILLS. INSTALL NEW CONCRETE SIDEWALK. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | RIGHT-OF-WAY | 20000 | FY 2026: 20000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (CAMERON ROAD) | FROM HOPE MILLS MIDDLE SCHOOL TO NC 59 (SOUTH MAIN STREET) IN HOPE MILLS. INSTALL NEW CONCRETE SIDEWALK. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (CAMERON ROAD) | FROM HOPE MILLS MIDDLE SCHOOL TO NC 59 (SOUTH MAIN STREET) IN HOPE MILLS. INSTALL NEW CONCRETE SIDEWALK. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 419000 | FY 2027: 419000
BL-0130 | Bike & Ped | Locally Selected | SR 1131 (CAMERON ROAD) | FROM HOPE MILLS MIDDLE SCHOOL TO NC 59 (SOUTH MAIN STREET) IN HOPE MILLS. INSTALL NEW CONCRETE SIDEWALK. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 105000 | FY 2027: 105000
BL-0131 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | IN FAYETTEVILLE. CONSTRUCT 10 FOOT WIDE MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 176000 | FY 2025: 176000
BL-0131 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | IN FAYETTEVILLE. CONSTRUCT 10 FOOT WIDE MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 44000 | FY 2025: 44000
BL-0131 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | IN FAYETTEVILLE. CONSTRUCT 10 FOOT WIDE MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BL-0131 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | IN FAYETTEVILLE. CONSTRUCT 10 FOOT WIDE MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2025: 10000
BL-0131 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | IN FAYETTEVILLE. CONSTRUCT 10 FOOT WIDE MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 880000 | FY 2026: 880000
BL-0131 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | IN FAYETTEVILLE. CONSTRUCT 10 FOOT WIDE MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 220000 | FY 2026: 220000
BL-0132 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | FAYETTEVILLE TO COUNTY LINE (ARNETTE PARK). CONSTRUCT 10 FOOT MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 176000 | FY 2025: 176000
BL-0132 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | FAYETTEVILLE TO COUNTY LINE (ARNETTE PARK). CONSTRUCT 10 FOOT MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 44000 | FY 2025: 44000
BL-0132 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | FAYETTEVILLE TO COUNTY LINE (ARNETTE PARK). CONSTRUCT 10 FOOT MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BL-0132 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | FAYETTEVILLE TO COUNTY LINE (ARNETTE PARK). CONSTRUCT 10 FOOT MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2025: 10000
BL-0132 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | FAYETTEVILLE TO COUNTY LINE (ARNETTE PARK). CONSTRUCT 10 FOOT MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 880000 | FY 2026: 880000
BL-0132 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | FAYETTEVILLE TO COUNTY LINE (ARNETTE PARK). CONSTRUCT 10 FOOT MULTI-USE PATH. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 220000 | FY 2026: 220000
BL-0133 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | ALONG MILAN ROAD AND EUFAULA ROAD IN FAYETTEVILLE. CONSTRUCT EXTENSION TO CAPE FEAR RIVER TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 117000 | FY 2025: 117000
BL-0133 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | ALONG MILAN ROAD AND EUFAULA ROAD IN FAYETTEVILLE. CONSTRUCT EXTENSION TO CAPE FEAR RIVER TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 29000 | FY 2025: 29000
BL-0133 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | ALONG MILAN ROAD AND EUFAULA ROAD IN FAYETTEVILLE. CONSTRUCT EXTENSION TO CAPE FEAR RIVER TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 400000 | FY 2026: 400000
BL-0133 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | ALONG MILAN ROAD AND EUFAULA ROAD IN FAYETTEVILLE. CONSTRUCT EXTENSION TO CAPE FEAR RIVER TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 100000 | FY 2026: 100000
BL-0133 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | ALONG MILAN ROAD AND EUFAULA ROAD IN FAYETTEVILLE. CONSTRUCT EXTENSION TO CAPE FEAR RIVER TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1641000 | FY 2027: 1641000
BL-0133 | Bike & Ped | Locally Selected | CAPE FEAR RIVER TRAIL | ALONG MILAN ROAD AND EUFAULA ROAD IN FAYETTEVILLE. CONSTRUCT EXTENSION TO CAPE FEAR RIVER TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 410000 | FY 2027: 410000
BL-0134 | Bike & Ped | Locally Selected | EAST SHORE TRAIL | FROM ESSEX PLACE TO COLEY DRIVE AND MURCHISON ROAD INTERSECTION ALONG GLENVILLE LAKE IN FAYETTEVILLE. CONSTRUCT 10 FOOT MULTI-USE PATH INCLUDING SIDEWALK CONNECTIONS ALONG MATTHEWS STREET AND FROM COLEY DRIVE TO MURCHISON ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 270000 | FY 2025: 270000
BL-0134 | Bike & Ped | Locally Selected | EAST SHORE TRAIL | FROM ESSEX PLACE TO COLEY DRIVE AND MURCHISON ROAD INTERSECTION ALONG GLENVILLE LAKE IN FAYETTEVILLE. CONSTRUCT 10 FOOT MULTI-USE PATH INCLUDING SIDEWALK CONNECTIONS ALONG MATTHEWS STREET AND FROM COLEY DRIVE TO MURCHISON ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 67000 | FY 2025: 67000
BL-0134 | Bike & Ped | Locally Selected | EAST SHORE TRAIL | FROM ESSEX PLACE TO COLEY DRIVE AND MURCHISON ROAD INTERSECTION ALONG GLENVILLE LAKE IN FAYETTEVILLE. CONSTRUCT 10 FOOT MULTI-USE PATH INCLUDING SIDEWALK CONNECTIONS ALONG MATTHEWS STREET AND FROM COLEY DRIVE TO MURCHISON ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 62000 | FY 2025: 62000
BL-0134 | Bike & Ped | Locally Selected | EAST SHORE TRAIL | FROM ESSEX PLACE TO COLEY DRIVE AND MURCHISON ROAD INTERSECTION ALONG GLENVILLE LAKE IN FAYETTEVILLE. CONSTRUCT 10 FOOT MULTI-USE PATH INCLUDING SIDEWALK CONNECTIONS ALONG MATTHEWS STREET AND FROM COLEY DRIVE TO MURCHISON ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 15000 | FY 2025: 15000
BL-0134 | Bike & Ped | Locally Selected | EAST SHORE TRAIL | FROM ESSEX PLACE TO COLEY DRIVE AND MURCHISON ROAD INTERSECTION ALONG GLENVILLE LAKE IN FAYETTEVILLE. CONSTRUCT 10 FOOT MULTI-USE PATH INCLUDING SIDEWALK CONNECTIONS ALONG MATTHEWS STREET AND FROM COLEY DRIVE TO MURCHISON ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1349000 | FY 2026: 1349000
BL-0134 | Bike & Ped | Locally Selected | EAST SHORE TRAIL | FROM ESSEX PLACE TO COLEY DRIVE AND MURCHISON ROAD INTERSECTION ALONG GLENVILLE LAKE IN FAYETTEVILLE. CONSTRUCT 10 FOOT MULTI-USE PATH INCLUDING SIDEWALK CONNECTIONS ALONG MATTHEWS STREET AND FROM COLEY DRIVE TO MURCHISON ROAD. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 337000 | FY 2026: 337000
BL-0135 | Bike & Ped | Locally Selected | HOKE TRAIL | NEAR JAMES A. LEACH AQUATIC & RECREATION CENTER. CONSTRUCT COUNTY-OPERATED TRAIL SYSTEM IN HOKE COUNTY. |  | HOKE | 8 | Fayetteville Area MPO |  | Division 8 |  | CRPDA | CONSTRUCTION | 343000 | FY 2025: 343000
BL-0135 | Bike & Ped | Locally Selected | HOKE TRAIL | NEAR JAMES A. LEACH AQUATIC & RECREATION CENTER. CONSTRUCT COUNTY-OPERATED TRAIL SYSTEM IN HOKE COUNTY. |  | HOKE | 8 | Fayetteville Area MPO |  | Division 8 |  | L(M) | CONSTRUCTION | 86000 | FY 2025: 86000
BL-0136 | Bike & Ped | Locally Selected | US 401 | WALMART TO JAMES A. LEACH AQUATIC & RECREATION CENTER IN RAEFORD. CONSTRUCT SIDEWALK. |  | HOKE | 8 | Fayetteville Area MPO |  | Division 8 |  | BGDA | ENGINEERING | 162000 | FY 2025: 162000
BL-0136 | Bike & Ped | Locally Selected | US 401 | WALMART TO JAMES A. LEACH AQUATIC & RECREATION CENTER IN RAEFORD. CONSTRUCT SIDEWALK. |  | HOKE | 8 | Fayetteville Area MPO |  | Division 8 |  | L(M) | ENGINEERING | 40000 | FY 2025: 40000
BL-0136 | Bike & Ped | Locally Selected | US 401 | WALMART TO JAMES A. LEACH AQUATIC & RECREATION CENTER IN RAEFORD. CONSTRUCT SIDEWALK. |  | HOKE | 8 | Fayetteville Area MPO |  | Division 8 |  | BGDA | CONSTRUCTION | 274000 | FY 2025: 274000
BL-0136 | Bike & Ped | Locally Selected | US 401 | WALMART TO JAMES A. LEACH AQUATIC & RECREATION CENTER IN RAEFORD. CONSTRUCT SIDEWALK. |  | HOKE | 8 | Fayetteville Area MPO |  | Division 8 |  | L(M) | CONSTRUCTION | 69000 | FY 2025: 69000
BL-0137 | Bike & Ped | Locally Selected | VARIOUS | LOCATIONS IN FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, RETAINING WALL AND BUS PAD UPGRADES. | 5.35 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 240000 | FY 2025: 240000
BL-0137 | Bike & Ped | Locally Selected | VARIOUS | LOCATIONS IN FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, RETAINING WALL AND BUS PAD UPGRADES. | 5.35 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 60000 | FY 2025: 60000
BL-0137 | Bike & Ped | Locally Selected | VARIOUS | LOCATIONS IN FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, RETAINING WALL AND BUS PAD UPGRADES. | 5.35 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 280000 | FY 2025: 280000
BL-0137 | Bike & Ped | Locally Selected | VARIOUS | LOCATIONS IN FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, RETAINING WALL AND BUS PAD UPGRADES. | 5.35 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 70000 | FY 2025: 70000
BL-0137 | Bike & Ped | Locally Selected | VARIOUS | LOCATIONS IN FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, RETAINING WALL AND BUS PAD UPGRADES. | 5.35 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1640000 | FY 2026: 1640000
BL-0137 | Bike & Ped | Locally Selected | VARIOUS | LOCATIONS IN FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, RETAINING WALL AND BUS PAD UPGRADES. | 5.35 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 410000 | FY 2026: 410000
BL-0138 | Bike & Ped | Locally Selected | NC162 (BUNCE ROAD / BINGHAM DRIVE SR 1400 (CLIFFDA | RAEFORD ROAD TO REILLY ROAD ; LAKERIDGE DRIVE TO RAEFORD ROAD IN WEST FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, AND BUS PAD UPGRADES. | 4.9 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 160000 | FY 2025: 160000
BL-0138 | Bike & Ped | Locally Selected | NC162 (BUNCE ROAD / BINGHAM DRIVE SR 1400 (CLIFFDA | RAEFORD ROAD TO REILLY ROAD ; LAKERIDGE DRIVE TO RAEFORD ROAD IN WEST FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, AND BUS PAD UPGRADES. | 4.9 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | ENGINEERING | 40000 | FY 2025: 40000
BL-0138 | Bike & Ped | Locally Selected | NC162 (BUNCE ROAD / BINGHAM DRIVE SR 1400 (CLIFFDA | RAEFORD ROAD TO REILLY ROAD ; LAKERIDGE DRIVE TO RAEFORD ROAD IN WEST FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, AND BUS PAD UPGRADES. | 4.9 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 160000 | FY 2025: 160000
BL-0138 | Bike & Ped | Locally Selected | NC162 (BUNCE ROAD / BINGHAM DRIVE SR 1400 (CLIFFDA | RAEFORD ROAD TO REILLY ROAD ; LAKERIDGE DRIVE TO RAEFORD ROAD IN WEST FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, AND BUS PAD UPGRADES. | 4.9 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BL-0138 | Bike & Ped | Locally Selected | NC162 (BUNCE ROAD / BINGHAM DRIVE SR 1400 (CLIFFDA | RAEFORD ROAD TO REILLY ROAD ; LAKERIDGE DRIVE TO RAEFORD ROAD IN WEST FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, AND BUS PAD UPGRADES. | 4.9 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1640000 | FY 2026: 1640000
BL-0138 | Bike & Ped | Locally Selected | NC162 (BUNCE ROAD / BINGHAM DRIVE SR 1400 (CLIFFDA | RAEFORD ROAD TO REILLY ROAD ; LAKERIDGE DRIVE TO RAEFORD ROAD IN WEST FAYETTEVILLE. CONSTRUCT SIDEWALK, WHEELCHAIR RAMPS, AND BUS PAD UPGRADES. | 4.9 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L(M) | CONSTRUCTION | 410000 | FY 2026: 410000
BL-0139 | Bike & Ped | Locally Selected | ORANGE GROVE ROAD | CONSTRUCT TRANSIT ACCESS SIDEWALK | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TADA | ENGINEERING | 200000 | FY 2025: 200000
BL-0139 | Bike & Ped | Locally Selected | ORANGE GROVE ROAD | CONSTRUCT TRANSIT ACCESS SIDEWALK | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | ENGINEERING | 50000 | FY 2025: 50000
BL-0140 | Bike & Ped | Locally Selected | LOVELADY ROAD | LAUREL STREET TO LAKE RHODHISS DRIVE IN VALDESE. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13
BL-0140A | Bike & Ped | Locally Selected | LOVELADY ROAD | LAUREL STREET TO CRESCENT STREET IN VALDESE. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | ENGINEERING | 120000 | FY 2025: 120000
BL-0140A | Bike & Ped | Locally Selected | LOVELADY ROAD | LAUREL STREET TO CRESCENT STREET IN VALDESE. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | ENGINEERING | 30000 | FY 2025: 30000
BL-0140A | Bike & Ped | Locally Selected | LOVELADY ROAD | LAUREL STREET TO CRESCENT STREET IN VALDESE. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 1025000 | FY 2027: 1025000
BL-0140A | Bike & Ped | Locally Selected | LOVELADY ROAD | LAUREL STREET TO CRESCENT STREET IN VALDESE. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 256000 | FY 2027: 256000
BL-0140B | Bike & Ped | Locally Selected | LOVELADY ROAD | CRESCENT STREET TO LAKE RHODHISS DRIVE IN VALDESE. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13
BL-0141 | Bike & Ped | Locally Selected | NC 126 | BENFIELD'S LANDING BURKE ROAD TO EASTSIDE BURKE AVENUE IN NEBO. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | ENGINEERING | 80000 | FY 2025: 80000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | BENFIELD'S LANDING BURKE ROAD TO EASTSIDE BURKE AVENUE IN NEBO. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | ENGINEERING | 20000 | FY 2025: 20000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | BENFIELD'S LANDING BURKE ROAD TO EASTSIDE BURKE AVENUE IN NEBO. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | RIGHT-OF-WAY | 160000 | FY 2026: 160000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | BENFIELD'S LANDING BURKE ROAD TO EASTSIDE BURKE AVENUE IN NEBO. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2026: 40000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | BENFIELD'S LANDING BURKE ROAD TO EASTSIDE BURKE AVENUE IN NEBO. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 1000000 | FY 2027: 1000000
BL-0141 | Bike & Ped | Locally Selected | NC 126 | BENFIELD'S LANDING BURKE ROAD TO EASTSIDE BURKE AVENUE IN NEBO. CONSTRUCT SIDEWALK. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | L(M) | CONSTRUCTION | 250000 | FY 2027: 250000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (LEWISVILLE-CLEMMONS ROAD) | AUGUST DRIVE TO BRANDON FARM ROAD. CONSTRUCT SIDEWALK AND IMPROVE CROSSWALK AT WEST FORSYTH HIGH SCHOOL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | ENGINEERING | 10000 | FY 2025: 10000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (LEWISVILLE-CLEMMONS ROAD) | AUGUST DRIVE TO BRANDON FARM ROAD. CONSTRUCT SIDEWALK AND IMPROVE CROSSWALK AT WEST FORSYTH HIGH SCHOOL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 3000 | FY 2025: 3000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (LEWISVILLE-CLEMMONS ROAD) | AUGUST DRIVE TO BRANDON FARM ROAD. CONSTRUCT SIDEWALK AND IMPROVE CROSSWALK AT WEST FORSYTH HIGH SCHOOL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 35000 | FY 2025: 35000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (LEWISVILLE-CLEMMONS ROAD) | AUGUST DRIVE TO BRANDON FARM ROAD. CONSTRUCT SIDEWALK AND IMPROVE CROSSWALK AT WEST FORSYTH HIGH SCHOOL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 9000 | FY 2025: 9000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (LEWISVILLE-CLEMMONS ROAD) | AUGUST DRIVE TO BRANDON FARM ROAD. CONSTRUCT SIDEWALK AND IMPROVE CROSSWALK AT WEST FORSYTH HIGH SCHOOL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 210000 | FY 2026: 210000
BL-0142 | Bike & Ped | Locally Selected | SR 1103 (LEWISVILLE-CLEMMONS ROAD) | AUGUST DRIVE TO BRANDON FARM ROAD. CONSTRUCT SIDEWALK AND IMPROVE CROSSWALK AT WEST FORSYTH HIGH SCHOOL. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 53000 | FY 2026: 53000
BL-0143 | Bike & Ped | Locally Selected | FRIENDLY ROAD; RUXTON DRIVE | MAIN STREET TO YORK PLACE DRIVE NE. CONSTRUCT SIDEWALK ON RUXTON DRIVE AND IMPROVE WALKERTOWN ELEMENTARY SCHOOL CROSSWALK AT FRIENDLY ROAD. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | ENGINEERING | 10000 | FY 2025: 10000
BL-0143 | Bike & Ped | Locally Selected | FRIENDLY ROAD; RUXTON DRIVE | MAIN STREET TO YORK PLACE DRIVE NE. CONSTRUCT SIDEWALK ON RUXTON DRIVE AND IMPROVE WALKERTOWN ELEMENTARY SCHOOL CROSSWALK AT FRIENDLY ROAD. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 3000 | FY 2025: 3000
BL-0143 | Bike & Ped | Locally Selected | FRIENDLY ROAD; RUXTON DRIVE | MAIN STREET TO YORK PLACE DRIVE NE. CONSTRUCT SIDEWALK ON RUXTON DRIVE AND IMPROVE WALKERTOWN ELEMENTARY SCHOOL CROSSWALK AT FRIENDLY ROAD. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 10000 | FY 2026: 10000
BL-0143 | Bike & Ped | Locally Selected | FRIENDLY ROAD; RUXTON DRIVE | MAIN STREET TO YORK PLACE DRIVE NE. CONSTRUCT SIDEWALK ON RUXTON DRIVE AND IMPROVE WALKERTOWN ELEMENTARY SCHOOL CROSSWALK AT FRIENDLY ROAD. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 3000 | FY 2026: 3000
BL-0143 | Bike & Ped | Locally Selected | FRIENDLY ROAD; RUXTON DRIVE | MAIN STREET TO YORK PLACE DRIVE NE. CONSTRUCT SIDEWALK ON RUXTON DRIVE AND IMPROVE WALKERTOWN ELEMENTARY SCHOOL CROSSWALK AT FRIENDLY ROAD. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 464000 | FY 2027: 464000
BL-0143 | Bike & Ped | Locally Selected | FRIENDLY ROAD; RUXTON DRIVE | MAIN STREET TO YORK PLACE DRIVE NE. CONSTRUCT SIDEWALK ON RUXTON DRIVE AND IMPROVE WALKERTOWN ELEMENTARY SCHOOL CROSSWALK AT FRIENDLY ROAD. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 116000 | FY 2027: 116000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 TO YADKIN VALLEY ROAD AT ATRIUM WAKE FOREST BAPTIST HOSPITAL. CONSTRUCT SIDEWALK. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 198000 | FY 2025: 198000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 TO YADKIN VALLEY ROAD AT ATRIUM WAKE FOREST BAPTIST HOSPITAL. CONSTRUCT SIDEWALK. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 50000 | FY 2025: 50000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 TO YADKIN VALLEY ROAD AT ATRIUM WAKE FOREST BAPTIST HOSPITAL. CONSTRUCT SIDEWALK. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 132000 | FY 2026: 132000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 TO YADKIN VALLEY ROAD AT ATRIUM WAKE FOREST BAPTIST HOSPITAL. CONSTRUCT SIDEWALK. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 13000 | FY 2026: 13000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 TO YADKIN VALLEY ROAD AT ATRIUM WAKE FOREST BAPTIST HOSPITAL. CONSTRUCT SIDEWALK. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 528000 | FY 2026: 528000
BL-0144 | Bike & Ped | Locally Selected | NC 801 | US 158 TO YADKIN VALLEY ROAD AT ATRIUM WAKE FOREST BAPTIST HOSPITAL. CONSTRUCT SIDEWALK. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 132000 | FY 2026: 132000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (MARTY LANE) | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | CRPDA | ENGINEERING | 189000 | FY 2026: 189000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (MARTY LANE) | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 47000 | FY 2026: 47000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (MARTY LANE) | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | CRPDA | RIGHT-OF-WAY | 43000 | FY 2027: 43000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (MARTY LANE) | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 116000 | FY 2027: 116000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (MARTY LANE) | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 9000 | FY 2027: 9000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (MARTY LANE) | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 29000 | FY 2027: 29000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (MARTY LANE) | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1155000 | FY 2028: 1155000
BL-0145 | Bike & Ped | Locally Selected | SR 1261 (MARTY LANE) | SR 1103 (LEWISVILLE CLEMMONS ROAD) TO KING RICHARD DRIVE. CONSTRUCT SIDEWALK. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 289000 | FY 2028: 289000
BL-0146 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | CONSTRUCT BLUE HERON TRAIL PHASE III FROM ROYAL TROON DRIVE TO NC 801. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | ENGINEERING | 220000 | FY 2025: 220000
BL-0146 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | CONSTRUCT BLUE HERON TRAIL PHASE III FROM ROYAL TROON DRIVE TO NC 801. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 55000 | FY 2025: 55000
BL-0146 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | CONSTRUCT BLUE HERON TRAIL PHASE III FROM ROYAL TROON DRIVE TO NC 801. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | RIGHT-OF-WAY | 88000 | FY 2026: 88000
BL-0146 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | CONSTRUCT BLUE HERON TRAIL PHASE III FROM ROYAL TROON DRIVE TO NC 801. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 22000 | FY 2026: 22000
BL-0146 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | CONSTRUCT BLUE HERON TRAIL PHASE III FROM ROYAL TROON DRIVE TO NC 801. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | TADA | CONSTRUCTION | 528000 | FY 2026: 528000
BL-0146 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | CONSTRUCT BLUE HERON TRAIL PHASE III FROM ROYAL TROON DRIVE TO NC 801. |  | DAVIE | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 132000 | FY 2026: 132000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (MAIN STREET) | KIRBY ROAD TO KING CITY HALL. CONSTRUCT ADA-COMPLIANT SIDEWALK. |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | ENGINEERING | 8000 | FY 2025: 8000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (MAIN STREET) | KIRBY ROAD TO KING CITY HALL. CONSTRUCT ADA-COMPLIANT SIDEWALK. |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 2000 | FY 2025: 2000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (MAIN STREET) | KIRBY ROAD TO KING CITY HALL. CONSTRUCT ADA-COMPLIANT SIDEWALK. |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | RIGHT-OF-WAY | 78000 | FY 2026: 78000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (MAIN STREET) | KIRBY ROAD TO KING CITY HALL. CONSTRUCT ADA-COMPLIANT SIDEWALK. |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (MAIN STREET) | KIRBY ROAD TO KING CITY HALL. CONSTRUCT ADA-COMPLIANT SIDEWALK. |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 258000 | FY 2027: 258000
BL-0147 | Bike & Ped | Locally Selected | SR 1112 (MAIN STREET) | KIRBY ROAD TO KING CITY HALL. CONSTRUCT ADA-COMPLIANT SIDEWALK. |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 65000 | FY 2027: 65000
BL-0148 | Bike & Ped | Locally Selected | INGRAM DRIVE | CAMPBELL DRIVE TO EAST OF 5 FORKS STREET. CONSTRUCT ADA-COMPLIANT SIDEWALK CONNECTING TO EXISTING SIDEWALKS |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | ENGINEERING | 30000 | FY 2025: 30000
BL-0148 | Bike & Ped | Locally Selected | INGRAM DRIVE | CAMPBELL DRIVE TO EAST OF 5 FORKS STREET. CONSTRUCT ADA-COMPLIANT SIDEWALK CONNECTING TO EXISTING SIDEWALKS |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 8000 | FY 2025: 8000
BL-0148 | Bike & Ped | Locally Selected | INGRAM DRIVE | CAMPBELL DRIVE TO EAST OF 5 FORKS STREET. CONSTRUCT ADA-COMPLIANT SIDEWALK CONNECTING TO EXISTING SIDEWALKS |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 170000 | FY 2027: 170000
BL-0148 | Bike & Ped | Locally Selected | INGRAM DRIVE | CAMPBELL DRIVE TO EAST OF 5 FORKS STREET. CONSTRUCT ADA-COMPLIANT SIDEWALK CONNECTING TO EXISTING SIDEWALKS |  | STOKES | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 43000 | FY 2027: 43000
BL-0149 | Bike & Ped | Locally Selected | SHELTON STREET; EAST POPLAR AVENUE; MAPLE AVENUE; | CONSTRUCT CONTRAFLOW/CYCLE TRACK AND INSTALL PAVEMENT MARKINGS ON SHELTON STREET. CONSTRUCT PEDESTRIAN LANE ON EAST POPLAR AVENUE. CONSTRUCT CONTRAFLOW LANE ON MAPLE AVENUE. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 890000 | FY 2025: 890000
BL-0149 | Bike & Ped | Locally Selected | SHELTON STREET; EAST POPLAR AVENUE; MAPLE AVENUE; | CONSTRUCT CONTRAFLOW/CYCLE TRACK AND INSTALL PAVEMENT MARKINGS ON SHELTON STREET. CONSTRUCT PEDESTRIAN LANE ON EAST POPLAR AVENUE. CONSTRUCT CONTRAFLOW LANE ON MAPLE AVENUE. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 222000 | FY 2025: 222000
BL-0150 | Bike & Ped | Locally Selected | VARIOUS | ROUTES IN CHAPEL HILL. CONSTRUCT SIDEWALKS TO FILL IN GAPS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TADA | ENGINEERING | 287000 | FY 2026: 287000
BL-0150 | Bike & Ped | Locally Selected | VARIOUS | ROUTES IN CHAPEL HILL. CONSTRUCT SIDEWALKS TO FILL IN GAPS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | ENGINEERING | 72000 | FY 2026: 72000
BL-0150 | Bike & Ped | Locally Selected | VARIOUS | ROUTES IN CHAPEL HILL. CONSTRUCT SIDEWALKS TO FILL IN GAPS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TADA | RIGHT-OF-WAY | 141000 | FY 2027: 141000
BL-0150 | Bike & Ped | Locally Selected | VARIOUS | ROUTES IN CHAPEL HILL. CONSTRUCT SIDEWALKS TO FILL IN GAPS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 35000 | FY 2027: 35000
BL-0150 | Bike & Ped | Locally Selected | VARIOUS | ROUTES IN CHAPEL HILL. CONSTRUCT SIDEWALKS TO FILL IN GAPS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TADA | CONSTRUCTION | 2348000 | FY 2027: 2348000
BL-0150 | Bike & Ped | Locally Selected | VARIOUS | ROUTES IN CHAPEL HILL. CONSTRUCT SIDEWALKS TO FILL IN GAPS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 587000 | FY 2027: 587000
BL-0151 | Bike & Ped | Locally Selected | BOLIN CREEK GREENWAY PHASE TWO | LAKE HOGAN GREENWAY TO JONES CREEK/TWIN CREEKS GREENWAYS. CONSTRUCT GREENWAY. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TADA | ENGINEERING | 320000 | FY 2027: 320000
BL-0151 | Bike & Ped | Locally Selected | BOLIN CREEK GREENWAY PHASE TWO | LAKE HOGAN GREENWAY TO JONES CREEK/TWIN CREEKS GREENWAYS. CONSTRUCT GREENWAY. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | ENGINEERING | 80000 | FY 2027: 80000
BL-0152 | Bike & Ped | Locally Selected | SR 1999 (DAVIS DRIVE) | I-40 TO SR 1121 (CORNWALLIS ROAD). RECONSTRUCT MULTI-USE PATH. | 0.63 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TADA | ENGINEERING | 8000 | FY 2025: 8000
BL-0152 | Bike & Ped | Locally Selected | SR 1999 (DAVIS DRIVE) | I-40 TO SR 1121 (CORNWALLIS ROAD). RECONSTRUCT MULTI-USE PATH. | 0.63 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L(M) | ENGINEERING | 2000 | FY 2025: 2000
BL-0152 | Bike & Ped | Locally Selected | SR 1999 (DAVIS DRIVE) | I-40 TO SR 1121 (CORNWALLIS ROAD). RECONSTRUCT MULTI-USE PATH. | 0.63 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TADA | CONSTRUCTION | 969000 | FY 2026: 969000
BL-0152 | Bike & Ped | Locally Selected | SR 1999 (DAVIS DRIVE) | I-40 TO SR 1121 (CORNWALLIS ROAD). RECONSTRUCT MULTI-USE PATH. | 0.63 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 242000 | FY 2026: 242000
BL-0153 | Bike & Ped | Locally Selected | GULLAH GEECHEE HERITAGE TRAIL GAP | CONSTRUCT MULTI-USE PATH ADJACENT TO NC 133. | 0.22 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 130000 | FY 2025: 130000
BL-0153 | Bike & Ped | Locally Selected | GULLAH GEECHEE HERITAGE TRAIL GAP | CONSTRUCT MULTI-USE PATH ADJACENT TO NC 133. | 0.22 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 32000 | FY 2025: 32000
BL-0153 | Bike & Ped | Locally Selected | GULLAH GEECHEE HERITAGE TRAIL GAP | CONSTRUCT MULTI-USE PATH ADJACENT TO NC 133. | 0.22 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 590000 | FY 2027: 590000
BL-0153 | Bike & Ped | Locally Selected | GULLAH GEECHEE HERITAGE TRAIL GAP | CONSTRUCT MULTI-USE PATH ADJACENT TO NC 133. | 0.22 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | CONSTRUCTION | 148000 | FY 2027: 148000
BL-0154 | Bike & Ped | Locally Selected | COUNTRY CLUB MULTI-USE PATH | ADJACENT TO COUNTRY CLUB DRIVE AND JENKINS ROAD FROM SLOOP POINT LOOP ROAD TO NORTH ST. JOHNS CHURCH ROAD. CONSTRUCT MULTI-USE PATH. | 3.91 | PENDER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 886000 | FY 2025: 886000
BL-0154 | Bike & Ped | Locally Selected | COUNTRY CLUB MULTI-USE PATH | ADJACENT TO COUNTRY CLUB DRIVE AND JENKINS ROAD FROM SLOOP POINT LOOP ROAD TO NORTH ST. JOHNS CHURCH ROAD. CONSTRUCT MULTI-USE PATH. | 3.91 | PENDER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L(M) | ENGINEERING | 222000 | FY 2025: 222000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | (WEST MARKET STREET) US 70 BUSINESS | FROM SR 1913 (WILSON'S MILLS ROAD) TO NEUSE RIVER BRIDGE IN SMITHFIELD. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | CMAQ | ENGINEERING | 180000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | (WEST MARKET STREET) US 70 BUSINESS | FROM SR 1913 (WILSON'S MILLS ROAD) TO NEUSE RIVER BRIDGE IN SMITHFIELD. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | L | ENGINEERING | 45000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | (WEST MARKET STREET) US 70 BUSINESS | FROM SR 1913 (WILSON'S MILLS ROAD) TO NEUSE RIVER BRIDGE IN SMITHFIELD. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | CMAQ | RIGHT-OF-WAY | 80000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | (WEST MARKET STREET) US 70 BUSINESS | FROM SR 1913 (WILSON'S MILLS ROAD) TO NEUSE RIVER BRIDGE IN SMITHFIELD. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | L | RIGHT-OF-WAY | 20000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | (WEST MARKET STREET) US 70 BUSINESS | FROM SR 1913 (WILSON'S MILLS ROAD) TO NEUSE RIVER BRIDGE IN SMITHFIELD. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | CMAQ | CONSTRUCTION | 629000 | FY 2026: 241000; FY 2027: 388000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | (WEST MARKET STREET) US 70 BUSINESS | FROM SR 1913 (WILSON'S MILLS ROAD) TO NEUSE RIVER BRIDGE IN SMITHFIELD. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | CRP550 | CONSTRUCTION | 1246000 | FY 2026: 477000; FY 2027: 769000
BN-0001 | Bike & Ped | NCDOT Selected (Other Selection Process) | (WEST MARKET STREET) US 70 BUSINESS | FROM SR 1913 (WILSON'S MILLS ROAD) TO NEUSE RIVER BRIDGE IN SMITHFIELD. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO | WEST MARKET STREET MULTI-USE PATH | Exempt |  | L | CONSTRUCTION | 469000 | FY 2026: 469000
BN-0002 | Bike & Ped | NCDOT Selected (Other Selection Process) | EAST INDUSTRY DRIVE SIDEWALK | 250 FEET WEST OF THE INTERSECTION OF LEWIS STREET AND EAST INDUSTRY DRIVE TO SPEED EEZ CARWASH DRIVEWAY. CONSTRUCT SIDEWALK. |  | GRANVILLE | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
BN-0002 | Bike & Ped | NCDOT Selected (Other Selection Process) | EAST INDUSTRY DRIVE SIDEWALK | 250 FEET WEST OF THE INTERSECTION OF LEWIS STREET AND EAST INDUSTRY DRIVE TO SPEED EEZ CARWASH DRIVEWAY. CONSTRUCT SIDEWALK. |  | GRANVILLE | 5 | Kerr-Tar RPO |  | Exempt |  | L | ENGINEERING | 2000
BN-0002 | Bike & Ped | NCDOT Selected (Other Selection Process) | EAST INDUSTRY DRIVE SIDEWALK | 250 FEET WEST OF THE INTERSECTION OF LEWIS STREET AND EAST INDUSTRY DRIVE TO SPEED EEZ CARWASH DRIVEWAY. CONSTRUCT SIDEWALK. |  | GRANVILLE | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 527000
BN-0002 | Bike & Ped | NCDOT Selected (Other Selection Process) | EAST INDUSTRY DRIVE SIDEWALK | 250 FEET WEST OF THE INTERSECTION OF LEWIS STREET AND EAST INDUSTRY DRIVE TO SPEED EEZ CARWASH DRIVEWAY. CONSTRUCT SIDEWALK. |  | GRANVILLE | 5 | Kerr-Tar RPO |  | Exempt |  | L | CONSTRUCTION | 132000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | MONTEITH GREENWAY | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD AND GREENWAY. |  | JACKSON | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. | Exempt |  | CRP550 | ENGINEERING | 160000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | MONTEITH GREENWAY | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD AND GREENWAY. |  | JACKSON | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. | Exempt |  | O | ENGINEERING | 100000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | MONTEITH GREENWAY | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD AND GREENWAY. |  | JACKSON | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. | Exempt |  | L | ENGINEERING | 40000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | MONTEITH GREENWAY | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD AND GREENWAY. |  | JACKSON | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. | Exempt |  | CRP550 | CONSTRUCTION | 100000 | FY 2025: 100000
BN-0003 | Bike & Ped | NCDOT Selected (Other Selection Process) | MONTEITH GREENWAY | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD AND GREENWAY. |  | JACKSON | 14 | Southwestern RPO | "O' FUNDS REPRESENT FUNDS FROM JACKSON COUNTY. | Exempt |  | L | CONSTRUCTION | 25000 | FY 2025: 25000
BN-0003A | Bike & Ped | NCDOT Selected (Other Selection Process) | MONTEITH GREENWAY | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD. |  | JACKSON | 14 | Southwestern RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 300000 | FY 2025: 300000
BN-0003A | Bike & Ped | NCDOT Selected (Other Selection Process) | MONTEITH GREENWAY | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD. |  | JACKSON | 14 | Southwestern RPO |  | Exempt |  | O | CONSTRUCTION | 200000 | FY 2025: 200000
BN-0003A | Bike & Ped | NCDOT Selected (Other Selection Process) | MONTEITH GREENWAY | CONSTRUCT PEDESTRIAN BRIDGE OVER GREAT SMOKY MOUNTAIN RAILROAD. |  | JACKSON | 14 | Southwestern RPO |  | Exempt |  | L | CONSTRUCTION | 75000 | FY 2025: 75000
BN-0004 | Bike & Ped | NCDOT Selected (Other Selection Process) | DOBSON SCHOOL GREENWAY | CENTRAL MIDDLE SCHOOL TO THE ELEMENTARY SCHOOL OF DOBSON. CONSTRUCT GREENWAY CONNECTOR. |  | SURRY | 11 | Northwest Piedmont RPO |  | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BN-0004 | Bike & Ped | NCDOT Selected (Other Selection Process) | DOBSON SCHOOL GREENWAY | CENTRAL MIDDLE SCHOOL TO THE ELEMENTARY SCHOOL OF DOBSON. CONSTRUCT GREENWAY CONNECTOR. |  | SURRY | 11 | Northwest Piedmont RPO |  | Exempt |  | L | RIGHT-OF-WAY | 10000 | FY 2025: 10000
BN-0004 | Bike & Ped | NCDOT Selected (Other Selection Process) | DOBSON SCHOOL GREENWAY | CENTRAL MIDDLE SCHOOL TO THE ELEMENTARY SCHOOL OF DOBSON. CONSTRUCT GREENWAY CONNECTOR. |  | SURRY | 11 | Northwest Piedmont RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 1188000 | FY 2026: 1188000
BN-0004 | Bike & Ped | NCDOT Selected (Other Selection Process) | DOBSON SCHOOL GREENWAY | CENTRAL MIDDLE SCHOOL TO THE ELEMENTARY SCHOOL OF DOBSON. CONSTRUCT GREENWAY CONNECTOR. |  | SURRY | 11 | Northwest Piedmont RPO |  | Exempt |  | L | CONSTRUCTION | 297000 | FY 2026: 297000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 BUSINESS (MAIN STREET) | FROM NC 58 TO SR 1366 (EAST STREET) IN POLLOCKSVILLE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.83 | JONES | 2 | Down East RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 60000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 BUSINESS (MAIN STREET) | FROM NC 58 TO SR 1366 (EAST STREET) IN POLLOCKSVILLE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.83 | JONES | 2 | Down East RPO |  | Exempt |  | L | ENGINEERING | 15000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 BUSINESS (MAIN STREET) | FROM NC 58 TO SR 1366 (EAST STREET) IN POLLOCKSVILLE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.83 | JONES | 2 | Down East RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 340000 | FY 2025: 340000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 BUSINESS (MAIN STREET) | FROM NC 58 TO SR 1366 (EAST STREET) IN POLLOCKSVILLE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.83 | JONES | 2 | Down East RPO |  | Exempt |  | O | CONSTRUCTION | 50000 | FY 2025: 50000
BN-0005 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 17 BUSINESS (MAIN STREET) | FROM NC 58 TO SR 1366 (EAST STREET) IN POLLOCKSVILLE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.83 | JONES | 2 | Down East RPO |  | Exempt |  | L | CONSTRUCTION | 85000 | FY 2025: 85000
BN-0006 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 701 BUSINESS (E 5TH STREET) | FROM WEST OF LYNWOOD NORRIS ROAD TO US 701 BYPASS IN TABOR CITY. CONSTRUCT SIDEWALK AND SIGNALIZED PEDESTRIAN CROSSING. | 0.2 | COLUMBUS | 6 | Cape Fear RPO | HF(M) FUNDING REPRESENT LEGISLATIVE CONTINGENCY FUNDS. | Exempt |  | CRPLT5 | CONSTRUCTION | 200000 | FY 2025: 2000; FY 2026: 198000
BN-0006 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 701 BUSINESS (E 5TH STREET) | FROM WEST OF LYNWOOD NORRIS ROAD TO US 701 BYPASS IN TABOR CITY. CONSTRUCT SIDEWALK AND SIGNALIZED PEDESTRIAN CROSSING. | 0.2 | COLUMBUS | 6 | Cape Fear RPO | HF(M) FUNDING REPRESENT LEGISLATIVE CONTINGENCY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 50000 | FY 2025: 1000; FY 2026: 49000
BN-0007 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1510 (EAST WILMINGTON STREET) | FROM US 117 BUSINESS TO US 117 BYPASS CORRIDOR IN BURGAW. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 0.67 | PENDER | 3 | Cape Fear RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 40000
BN-0007 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1510 (EAST WILMINGTON STREET) | FROM US 117 BUSINESS TO US 117 BYPASS CORRIDOR IN BURGAW. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 0.67 | PENDER | 3 | Cape Fear RPO |  | Exempt |  | L | ENGINEERING | 10000
BN-0007 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1510 (EAST WILMINGTON STREET) | FROM US 117 BUSINESS TO US 117 BYPASS CORRIDOR IN BURGAW. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 0.67 | PENDER | 3 | Cape Fear RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 693000
BN-0007 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1510 (EAST WILMINGTON STREET) | FROM US 117 BUSINESS TO US 117 BYPASS CORRIDOR IN BURGAW. CONSTRUCT EIGHT FOOT MULTI-USE PATH. | 0.67 | PENDER | 3 | Cape Fear RPO |  | Exempt |  | L | CONSTRUCTION | 174000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | KINSTON RIVERWALK | CASWELL MEMORIAL PARK TO ATLANTIC AVENUE ALONG NEUSE RIVER IN KINSTON. CONSTRUCT 10 FOOT MULTI-USE PATH. | 1.58 | LENOIR | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | CRP550 | ENGINEERING | 244000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | KINSTON RIVERWALK | CASWELL MEMORIAL PARK TO ATLANTIC AVENUE ALONG NEUSE RIVER IN KINSTON. CONSTRUCT 10 FOOT MULTI-USE PATH. | 1.58 | LENOIR | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | L(M) | ENGINEERING | 61000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | KINSTON RIVERWALK | CASWELL MEMORIAL PARK TO ATLANTIC AVENUE ALONG NEUSE RIVER IN KINSTON. CONSTRUCT 10 FOOT MULTI-USE PATH. | 1.58 | LENOIR | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | CRP550 | RIGHT-OF-WAY | 4000 | FY 2025: 4000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | KINSTON RIVERWALK | CASWELL MEMORIAL PARK TO ATLANTIC AVENUE ALONG NEUSE RIVER IN KINSTON. CONSTRUCT 10 FOOT MULTI-USE PATH. | 1.58 | LENOIR | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | L(M) | RIGHT-OF-WAY | 1000 | FY 2025: 1000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | KINSTON RIVERWALK | CASWELL MEMORIAL PARK TO ATLANTIC AVENUE ALONG NEUSE RIVER IN KINSTON. CONSTRUCT 10 FOOT MULTI-USE PATH. | 1.58 | LENOIR | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | CRP550 | CONSTRUCTION | 2432000 | FY 2027: 2432000
BN-0008 | Bike & Ped | NCDOT Selected (Other Selection Process) | KINSTON RIVERWALK | CASWELL MEMORIAL PARK TO ATLANTIC AVENUE ALONG NEUSE RIVER IN KINSTON. CONSTRUCT 10 FOOT MULTI-USE PATH. | 1.58 | LENOIR | 2 | Eastern Carolina RPO | KINSTON RIVERWALK PHASE 2 | Exempt |  | L(M) | CONSTRUCTION | 608000 | FY 2027: 608000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421/ US 321 (WEST KING STREET) | SR 1180 (POPLAR GROVE CONNECTOR ROAD) TO WESTWOOD APARTMENTS IN BOONE. CONSTRUCT SIDEWALK AND OTHER CORRIDOR IMPROVEMENTS. | 0.42 | WATAUGA | 11 | High Country RPO |  | Exempt |  | CRP550 | ENGINEERING | 120000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421/ US 321 (WEST KING STREET) | SR 1180 (POPLAR GROVE CONNECTOR ROAD) TO WESTWOOD APARTMENTS IN BOONE. CONSTRUCT SIDEWALK AND OTHER CORRIDOR IMPROVEMENTS. | 0.42 | WATAUGA | 11 | High Country RPO |  | Exempt |  | L(M) | ENGINEERING | 30000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421/ US 321 (WEST KING STREET) | SR 1180 (POPLAR GROVE CONNECTOR ROAD) TO WESTWOOD APARTMENTS IN BOONE. CONSTRUCT SIDEWALK AND OTHER CORRIDOR IMPROVEMENTS. | 0.42 | WATAUGA | 11 | High Country RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421/ US 321 (WEST KING STREET) | SR 1180 (POPLAR GROVE CONNECTOR ROAD) TO WESTWOOD APARTMENTS IN BOONE. CONSTRUCT SIDEWALK AND OTHER CORRIDOR IMPROVEMENTS. | 0.42 | WATAUGA | 11 | High Country RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 10000 | FY 2025: 10000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421/ US 321 (WEST KING STREET) | SR 1180 (POPLAR GROVE CONNECTOR ROAD) TO WESTWOOD APARTMENTS IN BOONE. CONSTRUCT SIDEWALK AND OTHER CORRIDOR IMPROVEMENTS. | 0.42 | WATAUGA | 11 | High Country RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 525000 | FY 2025: 525000
BN-0010 | Bike & Ped | NCDOT Selected (Other Selection Process) | US 421/ US 321 (WEST KING STREET) | SR 1180 (POPLAR GROVE CONNECTOR ROAD) TO WESTWOOD APARTMENTS IN BOONE. CONSTRUCT SIDEWALK AND OTHER CORRIDOR IMPROVEMENTS. | 0.42 | WATAUGA | 11 | High Country RPO |  | Exempt |  | L(M) | CONSTRUCTION | 131000 | FY 2025: 131000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | ESTATOE TRAIL | CASHIERS VALLEY ROAD TO US HIGHWAY 64 IN BREVARD. CONSTRUCT MULTI-USE PATH. | 0.69 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | CRP550 | ENGINEERING | 80000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | ESTATOE TRAIL | CASHIERS VALLEY ROAD TO US HIGHWAY 64 IN BREVARD. CONSTRUCT MULTI-USE PATH. | 0.69 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | L(M) | ENGINEERING | 20000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | ESTATOE TRAIL | CASHIERS VALLEY ROAD TO US HIGHWAY 64 IN BREVARD. CONSTRUCT MULTI-USE PATH. | 0.69 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 448000 | FY 2025: 448000
BN-0011 | Bike & Ped | NCDOT Selected (Other Selection Process) | ESTATOE TRAIL | CASHIERS VALLEY ROAD TO US HIGHWAY 64 IN BREVARD. CONSTRUCT MULTI-USE PATH. | 0.69 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | L(M) | CONSTRUCTION | 112000 | FY 2025: 112000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | TOWN LAKE PARK | TOWN LAKE PARK INSTALL SIDEWALK. | 0.33 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | ENGINEERING | 117000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | TOWN LAKE PARK | TOWN LAKE PARK INSTALL SIDEWALK. | 0.33 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L | ENGINEERING | 29000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | TOWN LAKE PARK | TOWN LAKE PARK INSTALL SIDEWALK. | 0.33 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 25000 | FY 2025: 25000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | TOWN LAKE PARK | TOWN LAKE PARK INSTALL SIDEWALK. | 0.33 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L | RIGHT-OF-WAY | 6000 | FY 2025: 6000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | TOWN LAKE PARK | TOWN LAKE PARK INSTALL SIDEWALK. | 0.33 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 364000 | FY 2026: 364000
BN-0012 | Bike & Ped | NCDOT Selected (Other Selection Process) | TOWN LAKE PARK | TOWN LAKE PARK INSTALL SIDEWALK. | 0.33 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L | CONSTRUCTION | 91000 | FY 2026: 91000
BN-0013 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1605 (NORTH MAIN STREET) | CONSTRUCT SIDEWALK FROM US 501 (VIRGILINA ROAD) TO SCHOOL STREET. | 0.75 | PERSON | 5 | Kerr-Tar RPO |  | Exempt |  | CRP550 | ENGINEERING | 120000 | FY 2025: 120000
BN-0013 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1605 (NORTH MAIN STREET) | CONSTRUCT SIDEWALK FROM US 501 (VIRGILINA ROAD) TO SCHOOL STREET. | 0.75 | PERSON | 5 | Kerr-Tar RPO |  | Exempt |  | L(M) | ENGINEERING | 30000 | FY 2025: 30000
BN-0014 | Bike & Ped | NCDOT Selected (Other Selection Process) | DUKE STREET | CONSTRUCT SIDEWALK FROM SR 1147 (HARDISON STREET) TO SR 1853 (AVGOL DRIVE). | 0.15 | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 572000 | FY 2025: 572000
BN-0014 | Bike & Ped | NCDOT Selected (Other Selection Process) | DUKE STREET | CONSTRUCT SIDEWALK FROM SR 1147 (HARDISON STREET) TO SR 1853 (AVGOL DRIVE). | 0.15 | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | L(M) | CONSTRUCTION | 143000 | FY 2025: 143000
BN-0015 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 107 | SR 1330 (FOREST HILLS ROAD/NORTH COUNTRY CLUB ROAD) TO THE JACKSON COUNTY RECREATION COMPLEX NEAR THE INTERSECTION OF SR 1545 (WISDOM DRIVE) AND CULLOWHEE MOUNTAIN ROAD. CONSTRUCT MULTI-USE PATH ON WEST SIDE. | 0.3 | JACKSON | 14 | Southwestern RPO |  | Exempt |  | CRP550 | ENGINEERING | 352000 | FY 2025: 352000
BN-0015 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 107 | SR 1330 (FOREST HILLS ROAD/NORTH COUNTRY CLUB ROAD) TO THE JACKSON COUNTY RECREATION COMPLEX NEAR THE INTERSECTION OF SR 1545 (WISDOM DRIVE) AND CULLOWHEE MOUNTAIN ROAD. CONSTRUCT MULTI-USE PATH ON WEST SIDE. | 0.3 | JACKSON | 14 | Southwestern RPO |  | Exempt |  | L(M) | ENGINEERING | 88000 | FY 2025: 88000
BN-0015 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 107 | SR 1330 (FOREST HILLS ROAD/NORTH COUNTRY CLUB ROAD) TO THE JACKSON COUNTY RECREATION COMPLEX NEAR THE INTERSECTION OF SR 1545 (WISDOM DRIVE) AND CULLOWHEE MOUNTAIN ROAD. CONSTRUCT MULTI-USE PATH ON WEST SIDE. | 0.3 | JACKSON | 14 | Southwestern RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 1318000 | FY 2026: 1318000
BN-0015 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 107 | SR 1330 (FOREST HILLS ROAD/NORTH COUNTRY CLUB ROAD) TO THE JACKSON COUNTY RECREATION COMPLEX NEAR THE INTERSECTION OF SR 1545 (WISDOM DRIVE) AND CULLOWHEE MOUNTAIN ROAD. CONSTRUCT MULTI-USE PATH ON WEST SIDE. | 0.3 | JACKSON | 14 | Southwestern RPO |  | Exempt |  | L(M) | CONSTRUCTION | 329000 | FY 2026: 329000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (LEDGER SCHOOL ROAD) | NC 226 TO MITCHELL HIGH SCHOOL. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | ENGINEERING | 144000 | FY 2025: 144000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (LEDGER SCHOOL ROAD) | NC 226 TO MITCHELL HIGH SCHOOL. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | ENGINEERING | 36000 | FY 2025: 36000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (LEDGER SCHOOL ROAD) | NC 226 TO MITCHELL HIGH SCHOOL. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 8000 | FY 2025: 8000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (LEDGER SCHOOL ROAD) | NC 226 TO MITCHELL HIGH SCHOOL. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | RIGHT-OF-WAY | 2000 | FY 2025: 2000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (LEDGER SCHOOL ROAD) | NC 226 TO MITCHELL HIGH SCHOOL. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | CONSTRUCTION | 408000 | FY 2026: 408000
BN-0016 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1193 (LEDGER SCHOOL ROAD) | NC 226 TO MITCHELL HIGH SCHOOL. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 102000 | FY 2026: 102000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 | NORTH OF SR 1278 (BAKERS LANE) TO WILLIS COVE ROAD. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | ENGINEERING | 75000 | FY 2025: 75000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 | NORTH OF SR 1278 (BAKERS LANE) TO WILLIS COVE ROAD. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | ENGINEERING | 19000 | FY 2025: 19000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 | NORTH OF SR 1278 (BAKERS LANE) TO WILLIS COVE ROAD. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | CRPLT5 | CONSTRUCTION | 754000 | FY 2025: 754000
BN-0017 | Bike & Ped | NCDOT Selected (Other Selection Process) | SR 1260 | NORTH OF SR 1278 (BAKERS LANE) TO WILLIS COVE ROAD. CONSTRUCT SIDEWALK. |  | MITCHELL | 13 | High Country RPO | HIGHWAY FUNDS ARE CONTIGENCY FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 189000 | FY 2025: 189000
BN-0018 | Bike & Ped | Locally Selected | SR 1179 (UNION STREET) | NORTH OF SEWELL STREET TO HAWKS DRIVE IN MURFREESBORO. CONSTRUCT SIDEWALK ON WEST SIDE. |  | HERTFORD | 1 | Peanut Belt RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 8000 | FY 2025: 8000
BN-0018 | Bike & Ped | Locally Selected | SR 1179 (UNION STREET) | NORTH OF SEWELL STREET TO HAWKS DRIVE IN MURFREESBORO. CONSTRUCT SIDEWALK ON WEST SIDE. |  | HERTFORD | 1 | Peanut Belt RPO |  | Exempt |  | L(M) | ENGINEERING | 2000 | FY 2025: 2000
BN-0018 | Bike & Ped | Locally Selected | SR 1179 (UNION STREET) | NORTH OF SEWELL STREET TO HAWKS DRIVE IN MURFREESBORO. CONSTRUCT SIDEWALK ON WEST SIDE. |  | HERTFORD | 1 | Peanut Belt RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 261000 | FY 2025: 261000
BN-0018 | Bike & Ped | Locally Selected | SR 1179 (UNION STREET) | NORTH OF SEWELL STREET TO HAWKS DRIVE IN MURFREESBORO. CONSTRUCT SIDEWALK ON WEST SIDE. |  | HERTFORD | 1 | Peanut Belt RPO |  | Exempt |  | L(M) | CONSTRUCTION | 65000 | FY 2025: 65000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | LEE DRIVE TO CEDAR LANE IN ATLANTIC BEACH. CONSTRUCT SIDEWALK ON NORTH SIDE. | 2 | CARTERET | 2 | Down East RPO |  | Exempt |  | CRP550 | ENGINEERING | 88000 | FY 2025: 88000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | LEE DRIVE TO CEDAR LANE IN ATLANTIC BEACH. CONSTRUCT SIDEWALK ON NORTH SIDE. | 2 | CARTERET | 2 | Down East RPO |  | Exempt |  | L(M) | ENGINEERING | 22000 | FY 2025: 22000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | LEE DRIVE TO CEDAR LANE IN ATLANTIC BEACH. CONSTRUCT SIDEWALK ON NORTH SIDE. | 2 | CARTERET | 2 | Down East RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 171000 | FY 2025: 171000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | LEE DRIVE TO CEDAR LANE IN ATLANTIC BEACH. CONSTRUCT SIDEWALK ON NORTH SIDE. | 2 | CARTERET | 2 | Down East RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 43000 | FY 2025: 43000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | LEE DRIVE TO CEDAR LANE IN ATLANTIC BEACH. CONSTRUCT SIDEWALK ON NORTH SIDE. | 2 | CARTERET | 2 | Down East RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 320000 | FY 2026: 320000
BN-0019 | Bike & Ped | Locally Selected | NC 58 | LEE DRIVE TO CEDAR LANE IN ATLANTIC BEACH. CONSTRUCT SIDEWALK ON NORTH SIDE. | 2 | CARTERET | 2 | Down East RPO |  | Exempt |  | L(M) | CONSTRUCTION | 80000 | FY 2026: 80000
BN-0020 | Bike & Ped | Locally Selected | WEBB BOULEVARD | NORTH OF METHODIST DRIVE IN HAVELOCK. CONSTRUCT APPROXIMATELY 550 FEET OF SIDEWALK ON EAST SIDE. |  | CRAVEN | 2 | Down East RPO |  | Exempt |  | CRP550 | ENGINEERING | 64000 | FY 2025: 64000
BN-0020 | Bike & Ped | Locally Selected | WEBB BOULEVARD | NORTH OF METHODIST DRIVE IN HAVELOCK. CONSTRUCT APPROXIMATELY 550 FEET OF SIDEWALK ON EAST SIDE. |  | CRAVEN | 2 | Down East RPO |  | Exempt |  | L(M) | ENGINEERING | 16000 | FY 2025: 16000
BN-0020 | Bike & Ped | Locally Selected | WEBB BOULEVARD | NORTH OF METHODIST DRIVE IN HAVELOCK. CONSTRUCT APPROXIMATELY 550 FEET OF SIDEWALK ON EAST SIDE. |  | CRAVEN | 2 | Down East RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 317000 | FY 2026: 317000
BN-0020 | Bike & Ped | Locally Selected | WEBB BOULEVARD | NORTH OF METHODIST DRIVE IN HAVELOCK. CONSTRUCT APPROXIMATELY 550 FEET OF SIDEWALK ON EAST SIDE. |  | CRAVEN | 2 | Down East RPO |  | Exempt |  | L(M) | CONSTRUCTION | 79000 | FY 2026: 79000
BN-0021 | Bike & Ped | Locally Selected | SR 1763 (CHURCH ROAD) | SOUTH OF US 70 INTERSECTION IN HAVELOCK. CONSTRUCT APPROXIMATELY 580 FEET OF SIDEWALK ON THE WEST SIDE. | 0.11 | CRAVEN | 2 | Down East RPO |  | Exempt |  | CRP550 | ENGINEERING | 40000 | FY 2025: 40000
BN-0021 | Bike & Ped | Locally Selected | SR 1763 (CHURCH ROAD) | SOUTH OF US 70 INTERSECTION IN HAVELOCK. CONSTRUCT APPROXIMATELY 580 FEET OF SIDEWALK ON THE WEST SIDE. | 0.11 | CRAVEN | 2 | Down East RPO |  | Exempt |  | L(M) | ENGINEERING | 10000 | FY 2025: 10000
BN-0021 | Bike & Ped | Locally Selected | SR 1763 (CHURCH ROAD) | SOUTH OF US 70 INTERSECTION IN HAVELOCK. CONSTRUCT APPROXIMATELY 580 FEET OF SIDEWALK ON THE WEST SIDE. | 0.11 | CRAVEN | 2 | Down East RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 4000 | FY 2025: 4000
BN-0021 | Bike & Ped | Locally Selected | SR 1763 (CHURCH ROAD) | SOUTH OF US 70 INTERSECTION IN HAVELOCK. CONSTRUCT APPROXIMATELY 580 FEET OF SIDEWALK ON THE WEST SIDE. | 0.11 | CRAVEN | 2 | Down East RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 1000 | FY 2025: 1000
BN-0021 | Bike & Ped | Locally Selected | SR 1763 (CHURCH ROAD) | SOUTH OF US 70 INTERSECTION IN HAVELOCK. CONSTRUCT APPROXIMATELY 580 FEET OF SIDEWALK ON THE WEST SIDE. | 0.11 | CRAVEN | 2 | Down East RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 100000 | FY 2026: 100000
BN-0021 | Bike & Ped | Locally Selected | SR 1763 (CHURCH ROAD) | SOUTH OF US 70 INTERSECTION IN HAVELOCK. CONSTRUCT APPROXIMATELY 580 FEET OF SIDEWALK ON THE WEST SIDE. | 0.11 | CRAVEN | 2 | Down East RPO |  | Exempt |  | L(M) | CONSTRUCTION | 25000 | FY 2026: 25000
BN-0022 | Bike & Ped | Locally Selected | NC 24 | YAUPON DRIVE TO BAYSHORE DRIVE IN CAPE CARTERET. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE. | 1 | CARTERET | 2 | Down East RPO |  | Exempt |  | CRP550 | ENGINEERING | 124000 | FY 2025: 124000
BN-0022 | Bike & Ped | Locally Selected | NC 24 | YAUPON DRIVE TO BAYSHORE DRIVE IN CAPE CARTERET. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE. | 1 | CARTERET | 2 | Down East RPO |  | Exempt |  | L(M) | ENGINEERING | 31000 | FY 2025: 31000
BN-0022 | Bike & Ped | Locally Selected | NC 24 | YAUPON DRIVE TO BAYSHORE DRIVE IN CAPE CARTERET. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE. | 1 | CARTERET | 2 | Down East RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 800000 | FY 2026: 800000
BN-0022 | Bike & Ped | Locally Selected | NC 24 | YAUPON DRIVE TO BAYSHORE DRIVE IN CAPE CARTERET. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE. | 1 | CARTERET | 2 | Down East RPO |  | Exempt |  | L(M) | CONSTRUCTION | 200000 | FY 2026: 200000
BN-0023 | Bike & Ped | Locally Selected | VARIOUS | LOCATIONS IN ST. JAMES. REPLACE STREET LIGHTS WITH LED LIGHTS. |  | BRUNSWICK | 3 | Cape Fear RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 320000 | FY 2025: 320000
BN-0023 | Bike & Ped | Locally Selected | VARIOUS | LOCATIONS IN ST. JAMES. REPLACE STREET LIGHTS WITH LED LIGHTS. |  | BRUNSWICK | 3 | Cape Fear RPO |  | Exempt |  | L(M) | CONSTRUCTION | 80000 | FY 2025: 80000
BN-0024 | Bike & Ped | Locally Selected | NEUSE RIVER | FROM PROPOSED RESIDENTIAL DEVELOPMENT TO FUTURE SCHOOL COMPLEX NEAR SR 2589 (CLEARWATER DRIVE) IN WILSON'S MILLS. CONSTRUCT MULTI-USE PATH ALONG NEUSE RIVER. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | ENGINEERING | 160000 | FY 2025: 160000
BN-0024 | Bike & Ped | Locally Selected | NEUSE RIVER | FROM PROPOSED RESIDENTIAL DEVELOPMENT TO FUTURE SCHOOL COMPLEX NEAR SR 2589 (CLEARWATER DRIVE) IN WILSON'S MILLS. CONSTRUCT MULTI-USE PATH ALONG NEUSE RIVER. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 40000 | FY 2025: 40000
BN-0024 | Bike & Ped | Locally Selected | NEUSE RIVER | FROM PROPOSED RESIDENTIAL DEVELOPMENT TO FUTURE SCHOOL COMPLEX NEAR SR 2589 (CLEARWATER DRIVE) IN WILSON'S MILLS. CONSTRUCT MULTI-USE PATH ALONG NEUSE RIVER. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 3209000 | FY 2026: 3209000
BN-0024 | Bike & Ped | Locally Selected | NEUSE RIVER | FROM PROPOSED RESIDENTIAL DEVELOPMENT TO FUTURE SCHOOL COMPLEX NEAR SR 2589 (CLEARWATER DRIVE) IN WILSON'S MILLS. CONSTRUCT MULTI-USE PATH ALONG NEUSE RIVER. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 802000 | FY 2026: 802000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (WEST MAIN STREET) | SOUTH OF FAYETTEVILLE STREET TO DWIGHT DRIVE IN MICRO. CONSTRUCT SIDEWALK. | 0.3 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRP550 | ENGINEERING | 140000 | FY 2025: 140000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (WEST MAIN STREET) | SOUTH OF FAYETTEVILLE STREET TO DWIGHT DRIVE IN MICRO. CONSTRUCT SIDEWALK. | 0.3 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | ENGINEERING | 35000 | FY 2025: 35000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (WEST MAIN STREET) | SOUTH OF FAYETTEVILLE STREET TO DWIGHT DRIVE IN MICRO. CONSTRUCT SIDEWALK. | 0.3 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 140000 | FY 2025: 140000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (WEST MAIN STREET) | SOUTH OF FAYETTEVILLE STREET TO DWIGHT DRIVE IN MICRO. CONSTRUCT SIDEWALK. | 0.3 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 35000 | FY 2025: 35000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (WEST MAIN STREET) | SOUTH OF FAYETTEVILLE STREET TO DWIGHT DRIVE IN MICRO. CONSTRUCT SIDEWALK. | 0.3 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 696000 | FY 2026: 696000
BN-0025 | Bike & Ped | Locally Selected | SR 2130 (WEST MAIN STREET) | SOUTH OF FAYETTEVILLE STREET TO DWIGHT DRIVE IN MICRO. CONSTRUCT SIDEWALK. | 0.3 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Exempt |  | L(M) | CONSTRUCTION | 174000 | FY 2026: 174000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (EAST THIRD STREET) | SR 1006 (NORTH SECOND AVENUE) TO EAST FIFTH STREET IN SILER CITY. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.8 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | ENGINEERING | 220000 | FY 2025: 220000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (EAST THIRD STREET) | SR 1006 (NORTH SECOND AVENUE) TO EAST FIFTH STREET IN SILER CITY. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.8 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 55000 | FY 2025: 55000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (EAST THIRD STREET) | SR 1006 (NORTH SECOND AVENUE) TO EAST FIFTH STREET IN SILER CITY. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.8 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 147000 | FY 2025: 147000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (EAST THIRD STREET) | SR 1006 (NORTH SECOND AVENUE) TO EAST FIFTH STREET IN SILER CITY. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.8 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 37000 | FY 2025: 37000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (EAST THIRD STREET) | SR 1006 (NORTH SECOND AVENUE) TO EAST FIFTH STREET IN SILER CITY. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.8 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 1685000 | FY 2026: 1685000
BN-0026 | Bike & Ped | Locally Selected | SR 1107 (EAST THIRD STREET) | SR 1006 (NORTH SECOND AVENUE) TO EAST FIFTH STREET IN SILER CITY. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.8 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 421000 | FY 2026: 421000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (NORTH SECOND AVENUE) | EAST FOURTH STREET TO US 64 (WEST ELEVENTH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.6 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | ENGINEERING | 188000 | FY 2025: 188000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (NORTH SECOND AVENUE) | EAST FOURTH STREET TO US 64 (WEST ELEVENTH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.6 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 47000 | FY 2025: 47000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (NORTH SECOND AVENUE) | EAST FOURTH STREET TO US 64 (WEST ELEVENTH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.6 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | RIGHT-OF-WAY | 158000 | FY 2025: 158000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (NORTH SECOND AVENUE) | EAST FOURTH STREET TO US 64 (WEST ELEVENTH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.6 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (NORTH SECOND AVENUE) | EAST FOURTH STREET TO US 64 (WEST ELEVENTH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.6 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRP550 | CONSTRUCTION | 1214000 | FY 2026: 1214000
BN-0027 | Bike & Ped | Locally Selected | SR 1006 (NORTH SECOND AVENUE) | EAST FOURTH STREET TO US 64 (WEST ELEVENTH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.6 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 303000 | FY 2026: 303000
BN-0028 | Bike & Ped | Locally Selected | SALISBURY STREET | FAYETTEVILLE STREET TO JA FARRELL STREET IN PITTSBORO. CONSTRUCT SIDEWALK. | 0.5 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRPANY | ENGINEERING | 95000 | FY 2025: 95000
BN-0028 | Bike & Ped | Locally Selected | SALISBURY STREET | FAYETTEVILLE STREET TO JA FARRELL STREET IN PITTSBORO. CONSTRUCT SIDEWALK. | 0.5 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 24000 | FY 2025: 24000
BN-0028 | Bike & Ped | Locally Selected | SALISBURY STREET | FAYETTEVILLE STREET TO JA FARRELL STREET IN PITTSBORO. CONSTRUCT SIDEWALK. | 0.5 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRPANY | RIGHT-OF-WAY | 22000 | FY 2025: 22000
BN-0028 | Bike & Ped | Locally Selected | SALISBURY STREET | FAYETTEVILLE STREET TO JA FARRELL STREET IN PITTSBORO. CONSTRUCT SIDEWALK. | 0.5 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 6000 | FY 2025: 6000
BN-0028 | Bike & Ped | Locally Selected | SALISBURY STREET | FAYETTEVILLE STREET TO JA FARRELL STREET IN PITTSBORO. CONSTRUCT SIDEWALK. | 0.5 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 203000 | FY 2025: 203000
BN-0028 | Bike & Ped | Locally Selected | SALISBURY STREET | FAYETTEVILLE STREET TO JA FARRELL STREET IN PITTSBORO. CONSTRUCT SIDEWALK. | 0.5 | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 51000 | FY 2025: 51000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (RIVERSIDE DRIVE) | HICKORY GROVE ROAD TO FUTURE RIVERLINK TRAIL EXTENSION IN CRAMERTON. CONSTRUCT SIDEWALK. | 0.2 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | CMAQ | ENGINEERING | 38000 | FY 2025: 38000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (RIVERSIDE DRIVE) | HICKORY GROVE ROAD TO FUTURE RIVERLINK TRAIL EXTENSION IN CRAMERTON. CONSTRUCT SIDEWALK. | 0.2 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | L(M) | ENGINEERING | 9000 | FY 2025: 9000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (RIVERSIDE DRIVE) | HICKORY GROVE ROAD TO FUTURE RIVERLINK TRAIL EXTENSION IN CRAMERTON. CONSTRUCT SIDEWALK. | 0.2 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | CMAQ | RIGHT-OF-WAY | 32000 | FY 2026: 32000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (RIVERSIDE DRIVE) | HICKORY GROVE ROAD TO FUTURE RIVERLINK TRAIL EXTENSION IN CRAMERTON. CONSTRUCT SIDEWALK. | 0.2 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | L(M) | RIGHT-OF-WAY | 8000 | FY 2026: 8000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (RIVERSIDE DRIVE) | HICKORY GROVE ROAD TO FUTURE RIVERLINK TRAIL EXTENSION IN CRAMERTON. CONSTRUCT SIDEWALK. | 0.2 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | CMAQ | CONSTRUCTION | 1930000 | FY 2026: 1930000
BN-0029 | Bike & Ped | NCDOT Selected (Other Selection Process) | NC 7 (RIVERSIDE DRIVE) | HICKORY GROVE ROAD TO FUTURE RIVERLINK TRAIL EXTENSION IN CRAMERTON. CONSTRUCT SIDEWALK. | 0.2 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | MCADENVILLE RIVER LINK SIDEWALK CONNECTOR. | Exempt |  | L(M) | CONSTRUCTION | 483000 | FY 2026: 483000
BO-2401 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TALT5 | ENGINEERING | 100000
BO-2401 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2401 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2401 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2401 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TALT5 | UTILITIES | 50000
BO-2401 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2401 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TALT5 | CONSTRUCTION | 1000000
BO-2401 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2402 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TALT5 | ENGINEERING | 100000
BO-2402 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2402 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2402 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2402 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2402 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TALT5 | UTILITIES | 50000
BO-2402 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TALT5 | CONSTRUCTION | 1000000
BO-2402 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2403 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2403 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TALT5 | ENGINEERING | 100000
BO-2403 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2403 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2403 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2403 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TALT5 | UTILITIES | 50000
BO-2403 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2403 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3 |  | TALT5 | CONSTRUCTION | 1000000
BO-2404 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2404 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TALT5 | ENGINEERING | 100000
BO-2404 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2404 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2404 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TALT5 | UTILITIES | 50000
BO-2404 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2404 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2404 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4 |  | TALT5 | CONSTRUCTION | 1000000
BO-2405 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TALT5 | ENGINEERING | 100000
BO-2405 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2405 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2405 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2405 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TALT5 | UTILITIES | 50000
BO-2405 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2405 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2405 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5 |  | TALT5 | CONSTRUCTION | 1000000
BO-2406 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TALT5 | ENGINEERING | 100000
BO-2406 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2406 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2406 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2406 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2406 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TALT5 | UTILITIES | 50000
BO-2406 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TALT5 | CONSTRUCTION | 1000000
BO-2406 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2407 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TALT5 | ENGINEERING | 100000
BO-2407 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2407 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2407 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2407 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2407 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TALT5 | UTILITIES | 50000
BO-2407 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2407 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7 |  | TALT5 | CONSTRUCTION | 1000000
BO-2408 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2408 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TALT5 | ENGINEERING | 100000
BO-2408 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2408 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2408 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TALT5 | UTILITIES | 50000
BO-2408 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2408 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2408 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8 |  | TALT5 | CONSTRUCTION | 1000000
BO-2409 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TALT5 | ENGINEERING | 100000
BO-2409 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2409 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2409 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2409 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2409 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TALT5 | UTILITIES | 50000
BO-2409 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2409 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9 |  | TALT5 | CONSTRUCTION | 1000000
BO-2410 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TALT5 | ENGINEERING | 200000
BO-2410 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TA | ENGINEERING | 425000 | FY 2025: 125000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2410 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2410 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2410 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2410 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TALT5 | UTILITIES | 50000
BO-2410 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2410 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10 |  | TALT5 | CONSTRUCTION | 1000000
BO-2411 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2411 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TALT5 | ENGINEERING | 250000
BO-2411 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2411 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2411 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2411 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TALT5 | UTILITIES | 50000
BO-2411 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2411 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11 |  | TALT5 | CONSTRUCTION | 3500000
BO-2412 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TALT5 | ENGINEERING | 200000
BO-2412 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2412 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2412 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2412 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TALT5 | UTILITIES | 50000
BO-2412 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2412 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2412 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12 |  | TALT5 | CONSTRUCTION | 1000000
BO-2413 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TALT5 | ENGINEERING | 100000
BO-2413 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2413 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2413 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2413 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2413 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TALT5 | UTILITIES | 50000
BO-2413 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TALT5 | CONSTRUCTION | 1000000
BO-2413 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2414 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TA | ENGINEERING | 400000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
BO-2414 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TALT5 | ENGINEERING | 200000
BO-2414 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TALT5 | RIGHT-OF-WAY | 50000
BO-2414 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TA | RIGHT-OF-WAY | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2414 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TALT5 | UTILITIES | 50000
BO-2414 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TA | UTILITIES | 200000 | FY 2025: 50000; FY 2026: 50000; FY 2027: 50000; FY 2028: 50000
BO-2414 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TA | CONSTRUCTION | 4000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
BO-2414 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14 |  | TALT5 | CONSTRUCTION | 1000000
BO-2415 | Bike & Ped | Other | MORGAN CREEK GREENWAY | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TADA | RIGHT-OF-WAY | 623000
BO-2415 | Bike & Ped | Other | MORGAN CREEK GREENWAY | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 550000
BO-2415 | Bike & Ped | Other | MORGAN CREEK GREENWAY | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 647000
BO-2415 | Bike & Ped | Other | MORGAN CREEK GREENWAY | EXISITING MORGAN CREEK GREENWAY IN CHAPEL HILL TO SR 1919 SMITH LEVEL ROAD. CONSTRUCT GREENWAY AND CONNECTIONS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 550000
BO-2416 | Bike & Ped | Other | SR 1153 (TINGEN ROAD) | CONSTRUCT A PEDESTRIAN BRIDGE OVER CSX RAILROAD WITHIN THE EXISTING ALIGNMENT OF SR 1153 (TINGEN ROAD) IN APEX. | 0.25 | WAKE | 5 | Capital Area MPO | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME. | Exempt |  | HP | ENGINEERING | 520000
BO-2416 | Bike & Ped | Other | SR 1153 (TINGEN ROAD) | CONSTRUCT A PEDESTRIAN BRIDGE OVER CSX RAILROAD WITHIN THE EXISTING ALIGNMENT OF SR 1153 (TINGEN ROAD) IN APEX. | 0.25 | WAKE | 5 | Capital Area MPO | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME. | Exempt |  | L | ENGINEERING | 120000
BO-2416 | Bike & Ped | Other | SR 1153 (TINGEN ROAD) | CONSTRUCT A PEDESTRIAN BRIDGE OVER CSX RAILROAD WITHIN THE EXISTING ALIGNMENT OF SR 1153 (TINGEN ROAD) IN APEX. | 0.25 | WAKE | 5 | Capital Area MPO | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME. | Exempt |  | HP | RIGHT-OF-WAY | 40000 | FY 2025: 40000
BO-2416 | Bike & Ped | Other | SR 1153 (TINGEN ROAD) | CONSTRUCT A PEDESTRIAN BRIDGE OVER CSX RAILROAD WITHIN THE EXISTING ALIGNMENT OF SR 1153 (TINGEN ROAD) IN APEX. | 0.25 | WAKE | 5 | Capital Area MPO | HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. UTIL AND CON PHASES ARE UNFUNDED AT THIS TIME. | Exempt |  | L | RIGHT-OF-WAY | 8000 | FY 2025: 8000
BO-2417 | Bike & Ped | Other | THOMAS STREET | CONSTRUCT PEDESTRIAN BRIDGE OVER MAIN STREET IN ROCKY MOUNT. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | HP | ENGINEERING | 998000 | FY 2025: 998000
BO-2417 | Bike & Ped | Other | THOMAS STREET | CONSTRUCT PEDESTRIAN BRIDGE OVER MAIN STREET IN ROCKY MOUNT. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | L | ENGINEERING | 250000 | FY 2025: 250000
BO-2417 | Bike & Ped | Other | THOMAS STREET | CONSTRUCT PEDESTRIAN BRIDGE OVER MAIN STREET IN ROCKY MOUNT. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | HP | RIGHT-OF-WAY | 312000 | FY 2025: 312000
BO-2417 | Bike & Ped | Other | THOMAS STREET | CONSTRUCT PEDESTRIAN BRIDGE OVER MAIN STREET IN ROCKY MOUNT. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | L | RIGHT-OF-WAY | 78000 | FY 2025: 78000
BO-2417 | Bike & Ped | Other | THOMAS STREET | CONSTRUCT PEDESTRIAN BRIDGE OVER MAIN STREET IN ROCKY MOUNT. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | HP | CONSTRUCTION | 1690000 | FY 2026: 1690000
BO-2417 | Bike & Ped | Other | THOMAS STREET | CONSTRUCT PEDESTRIAN BRIDGE OVER MAIN STREET IN ROCKY MOUNT. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC198. | Exempt |  | L | CONSTRUCTION | 4113000 | FY 2026: 4113000
BO-2418 | Bike & Ped | Other | NORTH-SOUTH CONNECTOR | CONSTRUCT GREENWAY / SIDEPATH USING EXISTING ROAD AND SIDEWALK ALONG NORTH GREENE STREET FROM 1ST STREET TO MUMFORD ROAD IN GREENVILLE. | 1.1 | PITT | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | L | ENGINEERING | 590000 | FY 2025: 590000
BO-2418 | Bike & Ped | Other | NORTH-SOUTH CONNECTOR | CONSTRUCT GREENWAY / SIDEPATH USING EXISTING ROAD AND SIDEWALK ALONG NORTH GREENE STREET FROM 1ST STREET TO MUMFORD ROAD IN GREENVILLE. | 1.1 | PITT | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | HP | RIGHT-OF-WAY | 20000 | FY 2026: 20000
BO-2418 | Bike & Ped | Other | NORTH-SOUTH CONNECTOR | CONSTRUCT GREENWAY / SIDEPATH USING EXISTING ROAD AND SIDEWALK ALONG NORTH GREENE STREET FROM 1ST STREET TO MUMFORD ROAD IN GREENVILLE. | 1.1 | PITT | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2026: 5000
BO-2418 | Bike & Ped | Other | NORTH-SOUTH CONNECTOR | CONSTRUCT GREENWAY / SIDEPATH USING EXISTING ROAD AND SIDEWALK ALONG NORTH GREENE STREET FROM 1ST STREET TO MUMFORD ROAD IN GREENVILLE. | 1.1 | PITT | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | HP | UTILITIES | 80000 | FY 2026: 80000
BO-2418 | Bike & Ped | Other | NORTH-SOUTH CONNECTOR | CONSTRUCT GREENWAY / SIDEPATH USING EXISTING ROAD AND SIDEWALK ALONG NORTH GREENE STREET FROM 1ST STREET TO MUMFORD ROAD IN GREENVILLE. | 1.1 | PITT | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | L(M) | UTILITIES | 20000 | FY 2026: 20000
BO-2418 | Bike & Ped | Other | NORTH-SOUTH CONNECTOR | CONSTRUCT GREENWAY / SIDEPATH USING EXISTING ROAD AND SIDEWALK ALONG NORTH GREENE STREET FROM 1ST STREET TO MUMFORD ROAD IN GREENVILLE. | 1.1 | PITT | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | HP | CONSTRUCTION | 2400000 | FY 2026: 2400000
BO-2418 | Bike & Ped | Other | NORTH-SOUTH CONNECTOR | CONSTRUCT GREENWAY / SIDEPATH USING EXISTING ROAD AND SIDEWALK ALONG NORTH GREENE STREET FROM 1ST STREET TO MUMFORD ROAD IN GREENVILLE. | 1.1 | PITT | 2 | Greenville Urban Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC199. | Exempt |  | L(M) | CONSTRUCTION | 885000 | FY 2026: 885000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | DP | ENGINEERING | 1031000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HSIP | ENGINEERING | 344000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HF | ENGINEERING | 34000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | DP | RIGHT-OF-WAY | 89000 | FY 2025: 89000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2025: 30000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HF | RIGHT-OF-WAY | 3000 | FY 2025: 3000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | DP | UTILITIES | 89000 | FY 2025: 89000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HSIP | UTILITIES | 30000 | FY 2025: 30000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HF | UTILITIES | 3000 | FY 2025: 3000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | DP | CONSTRUCTION | 7791000 | FY 2025: 7791000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HSIP | CONSTRUCTION | 2596000 | FY 2025: 2596000
BO-2419 | Bike & Ped | Other | VARIOUS | CONSTRUCT PEDESTRIAN COUNTDOWN SIGNAL HEADS, CROSSWALKS, AND ACCESSIBLE ROUTES AT SIGNALIZED INTERSECTIONS IN 15 MUNICIPALITIES. |  | LENOIR, WILSON, ROWAN, DAVIDSON, RICHMOND, ROBESON, GRANVILLE, HALIFAX, JOHNSTON, VANCE, BEAUFORT, CHATHAM | 2, 4, 5, 6, 8, 9 | Lumber River RPO, Upper Coastal Plain RPO, Kerr-Tar RPO, Peanut Belt RPO, Cabarrus-Rowan MPO, Central Pines RPO, Eastern Carolina RPO, High Point Urban Area MPO, Mid-East RPO | WALK NC - CREATING SAFER CROSSINGS. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS. | Division 2, 4, 5, 6, 8, 9 |  | HF | CONSTRUCTION | 260000 | FY 2025: 260000
BO-2420 | Bike & Ped | Locally Selected | ELIZABETH CITY | WEEKSVILLE ROAD ACCESSIBILITY AND CONNECTIVITY PLAN. | 3.6 | PASQUOTANK | 1 | Albemarle RPO | 'DP' FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 2000000
BO-2421 | Bike & Ped | Other | EPHESUS CHURCH ROAD | US 15 / US 501 BYPASS (FORDHAM BOULEVARD) TO POPE ROAD. CONSTRUCT SIDEWALKS AND BIKE LANES TO FILL IN GAPS. | 1.6 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | HP | ENGINEERING | 80000 | FY 2025: 80000
BO-2421 | Bike & Ped | Other | EPHESUS CHURCH ROAD | US 15 / US 501 BYPASS (FORDHAM BOULEVARD) TO POPE ROAD. CONSTRUCT SIDEWALKS AND BIKE LANES TO FILL IN GAPS. | 1.6 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | HP | RIGHT-OF-WAY | 70000 | FY 2026: 70000
BO-2421 | Bike & Ped | Other | EPHESUS CHURCH ROAD | US 15 / US 501 BYPASS (FORDHAM BOULEVARD) TO POPE ROAD. CONSTRUCT SIDEWALKS AND BIKE LANES TO FILL IN GAPS. | 1.6 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | HP | UTILITIES | 150000 | FY 2026: 150000
BO-2421 | Bike & Ped | Other | EPHESUS CHURCH ROAD | US 15 / US 501 BYPASS (FORDHAM BOULEVARD) TO POPE ROAD. CONSTRUCT SIDEWALKS AND BIKE LANES TO FILL IN GAPS. | 1.6 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | HP | CONSTRUCTION | 200000 | FY 2026: 200000
BO-2421 | Bike & Ped | Other | EPHESUS CHURCH ROAD | US 15 / US 501 BYPASS (FORDHAM BOULEVARD) TO POPE ROAD. CONSTRUCT SIDEWALKS AND BIKE LANES TO FILL IN GAPS. | 1.6 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC204. | Exempt |  | L | CONSTRUCTION | 600000 | FY 2026: 600000
BO-2422 | Bike & Ped | Other | SR 1011 (SOUTH SALEM STREET) | PLEASANT PLAINS ROAD TO CHATHAM STREET. CONSTRUCT BICYCLE LANES AND INSTALL SHARED LANE MARKINGS. | 2.9 | WAKE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | L | ENGINEERING | 740000 | FY 2025: 740000
BO-2422 | Bike & Ped | Other | SR 1011 (SOUTH SALEM STREET) | PLEASANT PLAINS ROAD TO CHATHAM STREET. CONSTRUCT BICYCLE LANES AND INSTALL SHARED LANE MARKINGS. | 2.9 | WAKE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | HP | RIGHT-OF-WAY | 712000 | FY 2026: 712000
BO-2422 | Bike & Ped | Other | SR 1011 (SOUTH SALEM STREET) | PLEASANT PLAINS ROAD TO CHATHAM STREET. CONSTRUCT BICYCLE LANES AND INSTALL SHARED LANE MARKINGS. | 2.9 | WAKE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | L(M) | RIGHT-OF-WAY | 178000 | FY 2026: 178000
BO-2422 | Bike & Ped | Other | SR 1011 (SOUTH SALEM STREET) | PLEASANT PLAINS ROAD TO CHATHAM STREET. CONSTRUCT BICYCLE LANES AND INSTALL SHARED LANE MARKINGS. | 2.9 | WAKE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | HP | CONSTRUCTION | 138000 | FY 2027: 138000
BO-2422 | Bike & Ped | Other | SR 1011 (SOUTH SALEM STREET) | PLEASANT PLAINS ROAD TO CHATHAM STREET. CONSTRUCT BICYCLE LANES AND INSTALL SHARED LANE MARKINGS. | 2.9 | WAKE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | L | CONSTRUCTION | 2797000 | FY 2027: 2797000
BO-2422 | Bike & Ped | Other | SR 1011 (SOUTH SALEM STREET) | PLEASANT PLAINS ROAD TO CHATHAM STREET. CONSTRUCT BICYCLE LANES AND INSTALL SHARED LANE MARKINGS. | 2.9 | WAKE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC206. | Exempt |  | L(M) | CONSTRUCTION | 35000 | FY 2027: 35000
BO-2423 | Bike & Ped | Other | WALNUT CREEK GREENWAY | DOWNTOWN CARY PARK TO BUCK JONES ROAD AT I-40. CONSTRUCT GREENWAY. | 2.6 | WAKE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC207. | Exempt |  | HP | ENGINEERING | 500000 | FY 2025: 500000
BO-2423 | Bike & Ped | Other | WALNUT CREEK GREENWAY | DOWNTOWN CARY PARK TO BUCK JONES ROAD AT I-40. CONSTRUCT GREENWAY. | 2.6 | WAKE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDING - DEMO ID NC207. | Exempt |  | L(M) | ENGINEERING | 125000 | FY 2025: 125000
BO-2424 | Bike & Ped | Other | VARIOUS | INTEGRATED MOBILITY DIVISION BICYCLE AND PEDESTRIAN COORDINATION ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | CMAQ | ENGINEERING | 880000 | FY 2025: 294000; FY 2026: 293000; FY 2027: 293000
BO-2424 | Bike & Ped | Other | VARIOUS | INTEGRATED MOBILITY DIVISION BICYCLE AND PEDESTRIAN COORDINATION ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T(M) | ENGINEERING | 220000 | FY 2025: 74000; FY 2026: 73000; FY 2027: 73000
BO-2601 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1
BO-2602 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2
BO-2603 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3
BO-2604 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4
BO-2605 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5
BO-2606 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6
BO-2607 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Central Pines RPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7
BO-2608 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8
BO-2609 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9
BO-2610 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10
BO-2611 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11
BO-2612 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12
BO-2613 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13
BO-2614 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14
BP-0001 | Bike & Ped | STI (Prioritization) | BLOUNTS CREEK GREENWAY | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | CUMBERLAND | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | ENGINEERING | 202000 | FY 2029: 202000
BP-0001 | Bike & Ped | STI (Prioritization) | BLOUNTS CREEK GREENWAY | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | CUMBERLAND | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L(M) | ENGINEERING | 51000 | FY 2029: 51000
BP-0001 | Bike & Ped | STI (Prioritization) | BLOUNTS CREEK GREENWAY | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | CUMBERLAND | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | RIGHT-OF-WAY | 67000
BP-0001 | Bike & Ped | STI (Prioritization) | BLOUNTS CREEK GREENWAY | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | CUMBERLAND | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L(M) | RIGHT-OF-WAY | 19000
BP-0001 | Bike & Ped | STI (Prioritization) | BLOUNTS CREEK GREENWAY | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | CUMBERLAND | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | UTILITIES | 8000
BP-0001 | Bike & Ped | STI (Prioritization) | BLOUNTS CREEK GREENWAY | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | CUMBERLAND | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L(M) | UTILITIES | 2000
BP-0001 | Bike & Ped | STI (Prioritization) | BLOUNTS CREEK GREENWAY | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | CUMBERLAND | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | TAANY | CONSTRUCTION | 956000
BP-0001 | Bike & Ped | STI (Prioritization) | BLOUNTS CREEK GREENWAY | RUSELL STREET TO COOL SPRING STREET IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.62 | CUMBERLAND | 6 | Fayetteville Area MPO | BLOUNTS CREEK PHASE III | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L(M) | CONSTRUCTION | 239000
BP-5500DIV | Highway | Bridges | VARIOUS | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99
BP-5500REG | Highway | Bridges | VARIOUS | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW
BP-5500SW | Highway | Bridges | VARIOUS | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility
BR-0012 | Highway | Bridges | US 74 | REPLACE BRIDGES 220048 AND 220049 OVER SANDY RUN. | 0.25 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045 | Highway Fund |  | HFB | RIGHT-OF-WAY | 42000
BR-0012 | Highway | Bridges | US 74 | REPLACE BRIDGES 220048 AND 220049 OVER SANDY RUN. | 0.25 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH R-4045 | Highway Fund |  | HFB | CONSTRUCTION | 61591000 | FY 2025: 33875000; FY 2026: 20325000; FY 2027: 6775000
BR-0025 | Highway | Bridges | SR 1639 (MEACHAM RD) | REPLACE BRIDGE 480118 OVER I-40. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BFP | RIGHT-OF-WAY | 80000 | FY 2027: 80000
BR-0025 | Highway | Bridges | SR 1639 (MEACHAM RD) | REPLACE BRIDGE 480118 OVER I-40. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BFP | UTILITIES | 20000 | FY 2027: 20000
BR-0025 | Highway | Bridges | SR 1639 (MEACHAM RD) | REPLACE BRIDGE 480118 OVER I-40. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BFP | CONSTRUCTION | 4200000 | FY 2029: 2100000; FY 2030: 2100000
BR-0035 | Highway | Bridges | NC 22 | REPLACE BRIDGE 620062 OVER NICKS CREEK IN CARTHAGE. | 0.25 | MOORE | 8 | Sandhills MPO | PROJECT WILL BE COMPLETED UNDER THE STATE BRIDGE PROGRAM. PROJECT TO NO LONGER UTILIZE BUILD NC BONDS. UNDER CONSTRUCTION | Region E |  | NHPB | CONSTRUCTION | 4100000
BR-0036 | Highway | Bridges | NC 33 | REPLACE BRIDGE 630041 OVER I-95. | 0.25 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 4700000
BR-0039 | Highway | Bridges | SR 1510 | REPLACE BRIDGE 630224 OVER I-95. | 0.25 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 5200000
BR-0075 | Highway | Bridges | SR 1109 (KINNAMON ROAD) | REPLACE BRIDGE 330135 OVER I-40. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | RIGHT-OF-WAY | 700000 | FY 2027: 700000
BR-0075 | Highway | Bridges | SR 1109 (KINNAMON ROAD) | REPLACE BRIDGE 330135 OVER I-40. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | UTILITIES | 100000 | FY 2027: 100000
BR-0075 | Highway | Bridges | SR 1109 (KINNAMON ROAD) | REPLACE BRIDGE 330135 OVER I-40. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 12000000 | FY 2029: 4800000; FY 2030: 4800000; FY 2031: 2400000
BR-0079 | Highway | Bridges | TUSCALOOSA STREET | REPLACE BRIDGE 400302 OVER US 29/US 70/US 220. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 1800000 | FY 2025: 152000; FY 2026: 909000; FY 2027: 379000; FY 2028: 180000; FY 2029: 180000
BR-0079 | Highway | Bridges | TUSCALOOSA STREET | REPLACE BRIDGE 400302 OVER US 29/US 70/US 220. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | UTILITIES | 2000000 | FY 2025: 2000000
BR-0079 | Highway | Bridges | TUSCALOOSA STREET | REPLACE BRIDGE 400302 OVER US 29/US 70/US 220. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 6300000 | FY 2027: 2520000; FY 2028: 2520000; FY 2029: 1260000
BR-0080 | Highway | Bridges | SULLIVAN STREET | REPLACE BRIDGE 400331 OVER US 29/US 70/ US 220. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 805000 | FY 2025: 805000
BR-0080 | Highway | Bridges | SULLIVAN STREET | REPLACE BRIDGE 400331 OVER US 29/US 70/ US 220. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | UTILITIES | 100000 | FY 2025: 100000
BR-0080 | Highway | Bridges | SULLIVAN STREET | REPLACE BRIDGE 400331 OVER US 29/US 70/ US 220. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 7400000 | FY 2026: 2960000; FY 2027: 2960000; FY 2028: 1480000
BR-0081 | Highway | Bridges | PHILLIPS AVENUE | BRIDGES 400283 AND 400342 OVER US 29 / US 70 / US 220. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  |  |  | BFP | RIGHT-OF-WAY | 1150000 | FY 2025: 1150000
BR-0081 | Highway | Bridges | PHILLIPS AVENUE | BRIDGES 400283 AND 400342 OVER US 29 / US 70 / US 220. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  |  |  | BFP | CONSTRUCTION | 11500000 | FY 2027: 5750000; FY 2028: 5750000
BR-0096 | Highway | Bridges | SR 1700 (FISHER HILL ROAD) | REPLACE BRIDGE 780176 OVER NC 14/NC 87. |  | ROCKINGHAM | 7 | Piedmont Triad RPO | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM | Division 7 |  | BGOFF | CONSTRUCTION | 2700000 | FY 2026: 1755000; FY 2027: 945000
BR-0107 | Highway | Bridges | SR 1577 | REPLACE BRIDGE 480131 OVER UT TO SNOW CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT. | Highway Fund |  | HFB | CONSTRUCTION | 800000
BR-0108 | Highway | Bridges | SR 2418 | REPLACE BRIDGE 960004 OVER LITTLE HUNTING CREEK. | 0.25 | WILKES | 11 | High Country RPO | COMPLETE. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | Highway Fund |  | HFB | CONSTRUCTION | 1200000
BR-0109 | Highway | Bridges | SR 1512 | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | Highway Fund |  | HFB | RIGHT-OF-WAY | 3000
BR-0109 | Highway | Bridges | SR 1512 | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | Highway Fund |  | HFB | UTILITIES | 5000
BR-0109 | Highway | Bridges | SR 1512 | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. LEVERAGE PROJECT FOR GREATTER BUILD GRANT | Highway Fund |  | HFB | CONSTRUCTION | 788000
BR-0111 | Highway | Bridges | SR 1404 (SEVEN BRIDGES ROAD) | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | 0.5 | EDGECOMBE | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | RIGHT-OF-WAY | 420000
BR-0111 | Highway | Bridges | SR 1404 (SEVEN BRIDGES ROAD) | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | 0.5 | EDGECOMBE | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | UTILITIES | 56000
BR-0111 | Highway | Bridges | SR 1404 (SEVEN BRIDGES ROAD) | REPLACE BRIDGES 320003, 320004, 320005 OVER SWIFT CREEK. | 0.5 | EDGECOMBE | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | CONSTRUCTION | 5450000
BR-0112 | Highway | Bridges | SR 1616 (SHARP POINT ROAD) | REPLACE BRIDGE 320035 OVER OTTER CREEK. | 0.25 | EDGECOMBE | 4 | Upper Coastal Plain RPO | COMPLETE. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | CONSTRUCTION | 1112000
BR-0113 | Highway | Bridges | SR 1601 (SLEDGE ROAD) | REPLACE BRIDGE 410115 OVER ROCKY SWAMP. | 0.25 | HALIFAX | 4 | Peanut Belt RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | HFB | RIGHT-OF-WAY | 130000
BR-0113 | Highway | Bridges | SR 1601 (SLEDGE ROAD) | REPLACE BRIDGE 410115 OVER ROCKY SWAMP. | 0.25 | HALIFAX | 4 | Peanut Belt RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 4 |  | DP | CONSTRUCTION | 796000
BR-0114 | Highway | Bridges | SR 1601 (BRANTON ROAD) | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | HFB | RIGHT-OF-WAY | 150000
BR-0114 | Highway | Bridges | SR 1601 (BRANTON ROAD) | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | DP | CONSTRUCTION | 300000
BR-0114 | Highway | Bridges | SR 1601 (BRANTON ROAD) | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | HFB | CONSTRUCTION | 850000
BR-0115 | Highway | Bridges | SR 1595 (COOLBROOK ROAD) | REPLACE BRIDGE 480166 ON SR 1595 OVER ROCKY CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | HFB | RIGHT-OF-WAY | 170000
BR-0115 | Highway | Bridges | SR 1595 (COOLBROOK ROAD) | REPLACE BRIDGE 480166 ON SR 1595 OVER ROCKY CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Division 12 |  | DP | CONSTRUCTION | 1600000
BR-0116 | Highway | Bridges | SR 1403 (COOPER ROAD) | REPLACE BRIDGE 630080 OVER GIDEON SWAMP. | 0.25 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Highway Fund |  | HFB | CONSTRUCTION | 1000000
BR-0121 | Highway | Bridges | SR 1804 (HOUSES MILL ROAD) | REPLACE BRIDGE 810178 OVER SEVENMILE SWAMP. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 3 |  | DP | CONSTRUCTION | 1400000
BR-0122 | Highway | Bridges | SR 1703 (OLD GOLDSBORO ROAD) | REPLACE BRIDGE 810348 OVER BEAVERDAM CREEK. | 0.25 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. | Division 3 |  | DP | CONSTRUCTION | 727000
BR-0124 | Highway | Bridges | SR 1745 (SHUMATE MOUNTAIN ROAD) | REPLACE BRIDGE 960166 ON SR 1745 OVER WEST PRONG ROARING RIVER. | 0.25 | WILKES | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | RIGHT-OF-WAY | 40000
BR-0124 | Highway | Bridges | SR 1745 (SHUMATE MOUNTAIN ROAD) | REPLACE BRIDGE 960166 ON SR 1745 OVER WEST PRONG ROARING RIVER. | 0.25 | WILKES | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 2900000
BR-0125 | Highway | Bridges | SR 1002 (TRAPHILL ROAD) | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | 0.25 | WILKES | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | RIGHT-OF-WAY | 280000
BR-0125 | Highway | Bridges | SR 1002 (TRAPHILL ROAD) | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | 0.25 | WILKES | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 2350000
BR-0125 | Highway | Bridges | SR 1002 (TRAPHILL ROAD) | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | 0.25 | WILKES | 11 | High Country RPO | COMPLETE. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | CONSTRUCTION | 300000
BR-0126 | Highway | Bridges | SR 1749 (AUSTIN TRAPHILL ROAD) | REPLACE BRIDGE 960667 ON SR 1749 OVER SPARKS CREEK. | 0.25 | WILKES | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | RIGHT-OF-WAY | 80000
BR-0126 | Highway | Bridges | SR 1749 (AUSTIN TRAPHILL ROAD) | REPLACE BRIDGE 960667 ON SR 1749 OVER SPARKS CREEK. | 0.25 | WILKES | 11 | High Country RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 1550000
BR-0127 | Highway | Bridges | SR 1325 (MOUNTAIN VIEW CHURCH ROAD) | REPLACE BRIDGE 980189 ON SR 1325 OVER SOUTH DEEP CREEK. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | HFB | RIGHT-OF-WAY | 45000
BR-0127 | Highway | Bridges | SR 1325 (MOUNTAIN VIEW CHURCH ROAD) | REPLACE BRIDGE 980189 ON SR 1325 OVER SOUTH DEEP CREEK. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | COMPLETE. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 850000
BR-0130 | Highway | Bridges | I-40 | REPLACE BRIDGES 110114 AND 110120 OVER SILVER CREEK. | 0.25 | BURKE | 13 | Greater Hickory MPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 11800000 | FY 2030: 5900000; FY 2031: 5900000
BR-0141 | Highway | Bridges | SR 2150 (RIVER ROAD) | REPLACE BRIDGE 780123 OVER US 220/US 311. |  | ROCKINGHAM | 7 | Piedmont Triad RPO | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM | Division 7 |  | BGOFF | CONSTRUCTION | 4100000 | FY 2026: 2665000; FY 2027: 1435000
BR-0152 | Highway | Bridges | SR 1436 (PINEBROOK SCHOOL ROAD) | REPLACE BRIDGE 290076 OVER I-40. |  | DAVIE | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY ACQUISITION AND UTILITY RELOCATION FUNDED BY HIGHWAY FUND BRIDGE PROGRAM | Division 9 |  | BGOFF | CONSTRUCTION | 5800000 | FY 2025: 2320000; FY 2026: 2320000; FY 2027: 1160000
BR-0200 | Highway | Bridges | SR 1152 | REPLACE BRIDGE 980020 OVER SOUTH DEEP CREEK. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENT HFB PROJECT NUMBER 17BP.11.R.183. | Highway Fund |  | HFB | CONSTRUCTION | 850000
BR-0201 | Highway | Bridges | SR 1348 | REPLACE BRIDGE 10291 OVER DUCK CREEK. | 0.25 | ALEXANDER | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.88 | Highway Fund |  | HFB | CONSTRUCTION | 1050000
BR-0202 | Highway | Bridges | SR 1892 | REPLACE BRIDGE 480212 OVER PATTERSON CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.49 | Highway Fund |  | HFB | CONSTRUCTION | 1250000
BR-0203 | Highway | Bridges | SR 1896 | REPLACE BRIDGE 480214 OVER PATTERSON CREEK | 0.25 | IREDELL | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.50 | Highway Fund |  | HFB | CONSTRUCTION | 1000000
BR-0204 | Highway | Bridges | SR 1892 | REPLACE BRIDGE 480219 OVER OLIN CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.51 | Highway Fund |  | HFB | CONSTRUCTION | 900000
BR-0205 | Highway | Bridges | SR 1119 | REPLACE BRIDGE 980028 OVER NORTH LITTLE HUNTING CREEK. | 0.25 | YADKIN | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.130 | Highway Fund |  | HFB | CONSTRUCTION | 2000000
BR-0206 | Highway | Bridges | SR 1422 | REPLACE BRIDGE 20035 OVER GLADE CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.157 | Highway Fund |  | HFB | CONSTRUCTION | 750000
BR-0207 | Highway | Bridges | SR 1433 | REPLACE BRIDGE 20133 OVER LITTLE RIVER. | 0.25 | ALLEGHANY | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.159 | Highway Fund |  | HFB | CONSTRUCTION | 500000
BR-0208 | Highway | Bridges | SR 2516 | REPLACE BRIDGE 960733 OVER CUB CREEK. | 0.25 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.154 | Highway Fund |  | HFB | CONSTRUCTION | 600000
BR-0209 | Highway | Bridges | SR 1148 | REPLACE BRIDGE 960419 OVER NAKED CREEK. | 0.25 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION. THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.153 | Highway Fund |  | HFB | CONSTRUCTION | 650000
BR-0210 | Highway | Bridges | SR 2081 | REPLACE BRIDGE 850153 OVER HOGAN CREEK. | 0.25 | SURRY | 11 | Northwest Piedmont RPO | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING | Highway Fund |  | DP | CONSTRUCTION | 875000
BR-0241 | Highway | Bridges | SR 1243 (LEGGETT ROAD) | REPLACE BRIDGE 320054 OVER TAR RIVER. | 0.25 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO | COMPLETE. PROJECT REPRESENTS HFB 4.R.101 PROJECT. | Highway Fund |  | HFB | CONSTRUCTION | 3600000
BR-0243 | Highway | Bridges | SR 1162 (BAY ROAD) | REPLACE BRIDGE 300045 OVER ISLAND CREEK. | 0.25 | DUPLIN | 3 | Eastern Carolina RPO | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.83 PROJECT. | Highway Fund |  | HFB | CONSTRUCTION | 1700000
C-4902 | Highway | Other | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY SOLAR CENTER CLEAN TRANSPORTATION PROGRAM. DEVELOP AND ADMINISTER A SEVEN YEAR CLEAN FUEL-ADVANCED TECHNOLOGY REBATE PROGRAM IN ALL CMAQ ELIGIBLE COUNTIES TO REDUCE EMISSIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS BY NORTH CAROLINA STATE UNIVERSITY | Exempt
C-4902A | Highway | Other | NORTH CAROLINA STATE UNIVERSITY | PHASE 2 OF IMPLEMENTATION |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt
C-4908 | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT SIDEWALKS AT SELECTED LOCATIONS IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt
C-4908A | Highway | Other | HORAH STREET | BRENNER AVENUE TO PARTEE STREET |  | ROWAN | 9 | Cabarrus-Rowan MPO | PROJECT DELETED AT MPO REQUEST | Exempt
C-4908B | Bike & Ped | Pre-STI (Historic) | VARIOUS | SPORTS COMPLEX, RYAN STREET TO CELEBRATION DRIVE AND SOUTH BOUNDARY STREET, HILLBORO STREET TO HILLS STREET |  | ROWAN | 9 | Cabarrus-Rowan MPO | COMPLETE | Exempt
C-4908C | Bike & Ped | Pre-STI (Historic) | VARIOUS | SALISBURY HIGH SCHOOL, ON VARIOUS STREETS AROUND HIGH SCHOOL |  | ROWAN | 9 | Cabarrus-Rowan MPO | COMPLETE | Exempt
C-4908D | Bike & Ped | Locally Selected | ARLINGTON AVENUE | ARLINGTON AVENUE TO WALMART PARKING LOT |  | ROWAN | 9 | Cabarrus-Rowan MPO | COMPLETE | Exempt
C-4908E | Highway | Transition | SR 1002 (BRINGLE FERRY ROAD) | LONG STREET TO NEWSOME ROAD |  | ROWAN | 9 | Cabarrus-Rowan MPO | COMPLETE | Exempt
C-4908F | Bike & Ped | Locally Selected | NEWSOME ROAD | SR 1002 (BRINGLE FERRY ROAD) TO SR 1004 (STOKES FERRY ROAD) |  | ROWAN | 9 | Cabarrus-Rowan MPO | PROJECT DELETED AT MPO REQUEST | Exempt
C-4908G | Highway | Transition | US 70 (STATESVILLE BOULEVARD) | US 601 (JAKE ALEXANDER BOULEVARD) |  | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Exempt
C-4908H | Bike & Ped | Locally Selected | MAIN STREET | "D" AVENUE TO SUNSET DRIVE | 0.43 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Exempt
C-4924 | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRIANGLE J COUNCIL OF GOVERNMENTS (COG). TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN TRIANGLE OZONE NON-ATTAINMENT AREA. |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Exempt
C-4924A | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt
C-4924B | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 641000 | FY 2027: 641000
C-4924B | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 586000 | FY 2025: 586000
C-4924B | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 622000 | FY 2026: 622000
C-4924B | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 571000
C-4924B | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 155000 | FY 2026: 155000
C-4924B | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 147000 | FY 2025: 147000
C-4924B | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 160000 | FY 2027: 160000
C-4924B | Highway | Other | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 143000
C-4928 | Highway | Transition | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | CMAQ | ENGINEERING | 795000
C-4928 | Highway | Transition | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | L | ENGINEERING | 199000
C-4928 | Highway | Transition | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | CMAQ | RIGHT-OF-WAY | 1070000
C-4928 | Highway | Transition | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 268000
C-4928 | Highway | Transition | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | CMAQ | CONSTRUCTION | 466000 | FY 2025: 466000
C-4928 | Highway | Transition | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 6742000 | FY 2025: 6742000
C-4928 | Highway | Transition | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 4533000 | FY 2025: 4533000
C-4928 | Highway | Transition | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | 1.52 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 116000 | FY 2025: 116000
C-4934 | Highway | Pre-STI (Historic) | NC 279 (NEW HOPE ROAD) | NC 279 (NEW HOPE ROAD), BURTONWOOD DRIVE TO SR 2466 (GARRISON BOULEVARD) IN GASTONIA. ADD TURN LANE. | 0.53 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | Exempt
C-5166 | Bike & Ped | Locally Selected | NC 56 | GREENWAY IN CREEDMOOR. CONSTRUCT BIKE-PEDESTRIAN TRAIL SYSTEM. | 2.76 | GRANVILLE | 5 | Capital Area MPO | PROJECT COMPLETE BY TOWN OF CREEDMOOR; LET WITH EB-5513 | Exempt
C-5166A | Bike & Ped | Transition | NC 56 | GREENWAY IN CREEDMOOR - EASTERN SECTION | 1.61 | GRANVILLE | 5 | Capital Area MPO | PROJECT COMPLETE | Exempt
C-5166B | Bike & Ped | Locally Selected | NC 56 | GREENWAY IN CREEDMOOR - WESTERN SECTION | 1.15 | GRANVILLE | 5 | Capital Area MPO | PROJECT COMPLETE | Exempt
C-5168 | Bike & Ped | Locally Selected | CRABTREE CREEK GREENWAY | CONSTRUCT GREENWAY CONNECTING EXISTING GREENWAY IN CARY THROUGH MORRISVILLE, INCLUDING REPLACEMENT OF TRAIN TRESTLE. | 1.85 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE | Exempt
C-5179 | Bike & Ped | Locally Selected | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 0.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | CMAQ | CONSTRUCTION | 3072000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 0.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | BGDA | CONSTRUCTION | 1100000 | FY 2025: 1100000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 0.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | BGDA | CONSTRUCTION | 631000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 0.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | BGDACV | CONSTRUCTION | 429000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 0.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | L | CONSTRUCTION | 926000
C-5179 | Bike & Ped | Locally Selected | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTI-USE PATH. | 0.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL | Exempt |  | L(M) | CONSTRUCTION | 275000 | FY 2025: 275000
C-5181 | Bike & Ped | Transition | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 0.12 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 523000 | FY 2025: 523000
C-5181 | Bike & Ped | Transition | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 0.12 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | BGDA | CONSTRUCTION | 205000 | FY 2025: 205000
C-5181 | Bike & Ped | Transition | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 0.12 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CONSTRUCTION | 51000 | FY 2025: 51000
C-5181 | Bike & Ped | Transition | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 0.12 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CONSTRUCTION | 131000 | FY 2025: 131000
C-5181 | Bike & Ped | Transition | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 0.12 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 10000
C-5181 | Bike & Ped | Transition | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | 0.12 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | IMPLEMENTATION | 2000
C-5183 | Bike & Ped | Locally Selected | VARIOUS | CONSTRUCT SIDEWALKS IN DURHAM. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5
C-5183B | Bike & Ped | Locally Selected | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS STREET. | 0.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | CONSTRUCTION | 565000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS STREET. | 0.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 468000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS STREET. | 0.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Exempt |  | TADA | CONSTRUCTION | 403000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS STREET. | 0.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Exempt |  | L | CONSTRUCTION | 117000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS STREET. | 0.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Exempt |  | L | CONSTRUCTION | 101000
C-5183B | Bike & Ped | Locally Selected | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS STREET. | 0.44 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Exempt |  | L | CONSTRUCTION | 141000
C-5184 | Bike & Ped | Transition | RIVERWALK TRAIL | RIVERWALK TRAIL, PHASE III IN HILLSBOROUGH. CONSTRUCT A PAVED OFF-ROAD TAIL ALONG ENO RIVER CONNECTING RIVER PARK, GOLD PARK AND THE OCCONEECHEE MOUNTAIN STATE NATURAL AREA, AND CONSTRUCT SIDEWALK TO PROVIDE PEDESTRIAN AND BICYCLE CONNECTIONS TO THE GREE | 2.17 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY TOWN OF HILLSBOROUGH | Exempt
C-5195 | Highway | Transition | CLAREMONT | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN CLAREMONT. |  | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION | Exempt
C-5196 | Highway | Transition | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | ENGINEERING | 400000
C-5196 | Highway | Transition | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | L | ENGINEERING | 100000
C-5196 | Highway | Transition | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | CMAQ | RIGHT-OF-WAY | 2364000 | FY 2025: 2364000
C-5196 | Highway | Transition | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | L | RIGHT-OF-WAY | 492000 | FY 2025: 492000
C-5196 | Highway | Transition | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | CMAQ | CONSTRUCTION | 2000000 | FY 2026: 2000000
C-5196 | Highway | Transition | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | BGANY | CONSTRUCTION | 1990000 | FY 2026: 1990000
C-5196 | Highway | Transition | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | L | CONSTRUCTION | 498000 | FY 2026: 498000
C-5196 | Highway | Transition | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. |  | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $2.39M IN BGANY USED AS PART OF FUND SWAP. | Division 12 |  | L | CONSTRUCTION | 500000 | FY 2026: 500000
C-5200 | Highway | Locally Selected | MOORESVILLE | NC 115 AND NC 150 IN MOORESVILLE. CONSTRUCT SOUTHBOUND NC 115 RIGHT TURN LANE AT NC 150 AND WESTBOUND NC 150 SHARED THROUGH-RIGHT LANE AT NC 115. |  | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  | BGDA | CONSTRUCTION | 1211000
C-5200 | Highway | Locally Selected | MOORESVILLE | NC 115 AND NC 150 IN MOORESVILLE. CONSTRUCT SOUTHBOUND NC 115 RIGHT TURN LANE AT NC 150 AND WESTBOUND NC 150 SHARED THROUGH-RIGHT LANE AT NC 115. |  | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  | L | CONSTRUCTION | 303000
C-5225A | Bike & Ped | Pre-STI (Historic) | CHARLOTTE | TOBY CREEK GREENWAY, UNIVERSTIY CITY BOULEVARD TO ROCKLAND DRIVE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt
C-5225B | Bike & Ped | Locally Selected | CHARLOTTE | TOBY CREEK GREENWAY, ROCKLAND DRIVE TO BLUE ROCK DRIVE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE | Exempt
C-5505 | Highway | Transition | BELMONT | RAIL TRAIL, WOODLAWN AVENUE TO BELMONT ABBEY COLLEGE AND DOWNTOWN. CONVERT ABANDONED NCDOT RAILROAD LINE TO A PEDESTRIAN TRAIL. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | IN PROGRESS | Exempt
C-5529 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  | BGDA | ENGINEERING | 207000
C-5529 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  | L | ENGINEERING | 52000
C-5529 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 846000
C-5529 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Exempt |  | L | CONSTRUCTION | 282000
C-5531 | Bike & Ped | Locally Selected | MOORESVILLE | KISTLER FARM-BRIARCLIFF-BELLINGHAM-WHITE OAK SIDEWALK NETWORK IN MOORESVILLE. CONSTRUCT SIDEWALKS IN VARIOUS LOCATIONS. |  | IREDELL | 12 | Charlotte Regional TPO | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  | BGDA | CONSTRUCTION | 641000
C-5531 | Bike & Ped | Locally Selected | MOORESVILLE | KISTLER FARM-BRIARCLIFF-BELLINGHAM-WHITE OAK SIDEWALK NETWORK IN MOORESVILLE. CONSTRUCT SIDEWALKS IN VARIOUS LOCATIONS. |  | IREDELL | 12 | Charlotte Regional TPO | COMPLETE; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES. | Exempt |  | L | CONSTRUCTION | 160000
C-5534 | Highway | Transition | CHARLOTTE | SR 4979 (BALLANTYNE COMMONS PARKWAY-MCKEE ROAD) AND NC 16 (PROVIDENCE ROAD) IN CHARLOTTE. CONSTRUCT AN ADDITIONAL LEFT TURN LANE ON SR 4979 AND A SECOND LEFT TURN LANE ON SOUTHBOUND NC 16. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES. | Exempt |  | BGDA | CONSTRUCTION | 640000
C-5536 | Highway | Transition | CHARLOTTE | MECKLENBURG COUNTY AIR QUALITY -GRADE (GRANTS TO REPLACE AGING DIESEL ENGINES). REPLACE, REPOWER OR RETROFIT AGING DIESEL VEHICLES AND EQUIPMENT. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  | CMAQ | CONSTRUCTION | 139000
C-5538 | Highway | Locally Selected | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1053000
C-5538 | Highway | Locally Selected | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1797000
C-5538 | Highway | Locally Selected | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 563000
C-5538 | Highway | Locally Selected | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 263000
C-5546 | Highway | Transition | ROCKY MOUNT | BENVENUE ROAD (NC 43/NC 48) AT JEFFREYS ROAD. INTERSECTION IMPROVEMENTS. | 0.5 | NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 130000 | FY 2025: 130000
C-5549 | Bike & Ped | Locally Selected | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 2.27 | NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CRPDA | RIGHT-OF-WAY | 160000 | FY 2025: 160000
C-5549 | Bike & Ped | Locally Selected | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 2.27 | NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 40000 | FY 2025: 40000
C-5549 | Bike & Ped | Locally Selected | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 2.27 | NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 688000 | FY 2026: 688000
C-5549 | Bike & Ped | Locally Selected | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 2.27 | NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 410000 | FY 2026: 410000
C-5549 | Bike & Ped | Locally Selected | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 2.27 | NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 103000 | FY 2026: 103000
C-5549 | Bike & Ped | Locally Selected | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | 2.27 | NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 172000 | FY 2026: 172000
C-5555 | Bike & Ped | Pre-STI (Historic) | VARIOUS | SIDEWALK PROJECTS AT SELECTED LOCATIONS IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF GREENSBORO | Exempt
C-5555E | Bike & Ped | Locally Selected | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 200000
C-5555E | Bike & Ped | Locally Selected | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGDA | CONSTRUCTION | 722000
C-5555E | Bike & Ped | Locally Selected | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | CONSTRUCTION | 50000
C-5555E | Bike & Ped | Locally Selected | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | CONSTRUCTION | 181000
C-5558 | Highway | Other | VARIOUS | CITY OF HIGH POINT SIGNAL SYSTEM EXPANSION AND UPGRADE. |  | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | Exempt
C-5559 | Public Transportation (Transit) | Pre-STI (Historic) | VARIOUS | TRANSIT OPERATIONS SUPPORT FOR CITY OF LEXINGTON CIRCULATOR ROUTE AND THOMASVILLE / LEXINGTON CONNECTOR ROUTE. |  | DAVIDSON | 9 | High Point Urban Area MPO | IMPLEMENTATION BY DAVIDSON COUNTY - IN PROGRESS | Exempt
C-5600 | Highway | Other | VARIOUS | STATEWIDE CMAQ PROJECTS TO IMPROVE AIR QUALITY WITHIN NONATTAINMENT AND MAINTENANCE AREAS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt
C-5600E | Highway | Other | I-85 | GUILFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1050000 | FY 2025: 1050000
C-5600E | Highway | Other | I-85 | GUILFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 262000 | FY 2026: 262000
C-5600E | Highway | Other | I-85 | GUILFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | T(M) | CONSTRUCTION | 70000 | FY 2026: 70000
C-5600E | Highway | Other | I-85 | GUILFORD COUNTY EXTENSION OF TRAFFIC MANAGEMENT SYSTEMS |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | T(M) | CONSTRUCTION | 279000 | FY 2025: 279000
C-5600U | Highway | Other | I-85 | TRIAD TMC UPDGRADE. (TRIANGLE AND TRIAD PIEDMONT TRAFFIC MANAGEMENT). |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1318000 | FY 2025: 1318000
C-5600U | Highway | Other | I-85 | TRIAD TMC UPDGRADE. (TRIANGLE AND TRIAD PIEDMONT TRAFFIC MANAGEMENT). |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | T(M) | CONSTRUCTION | 330000 | FY 2025: 330000
C-5600VA | Rail | Other | QUEEN CITY EXPRESS | WILMINGTON TO CHARLOTTE. SUBSIDY FOR INTERMODAL RAIL SERVICE BETWEEN PORT OF WILMINGTON AND CHARLOTTE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | OTHER | 250000 | FY 2025: 250000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | ENGINEERING | 15000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | L | ENGINEERING | 3000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 15000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | L | RIGHT-OF-WAY | 3000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 78000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | L | CONSTRUCTION | 21000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 15000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | L | IMPLEMENTATION | 3000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | CMAQ | OPERATIONS | 15000
C-5602 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. |  | GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | L | OPERATIONS | 3000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 246000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 63000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 246000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 63000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 1479000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 369000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 246000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 63000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 246000
C-5603 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 63000
C-5603D | Highway | Other | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | ENGINEERING | 28000
C-5603D | Highway | Other | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | ENGINEERING | 7000
C-5603D | Highway | Other | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 19000
C-5603D | Highway | Other | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 12000
C-5603D | Highway | Other | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 5000
C-5603D | Highway | Other | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 3000
C-5603D | Highway | Other | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1560000 | FY 2025: 1560000
C-5603D | Highway | Other | OLD CONCORD ROAD | RYAN STREET TO JAKE ALEXANDER BOULEVARD. CONSTRUCT SIDEWALKS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 390000 | FY 2025: 390000
C-5603F | Highway | Other | SR 1643 (BETHPAGE ROAD) | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | ENGINEERING | 208000
C-5603F | Highway | Other | SR 1643 (BETHPAGE ROAD) | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | ENGINEERING | 52000
C-5603F | Highway | Other | SR 1643 (BETHPAGE ROAD) | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 94000 | FY 2025: 94000
C-5603F | Highway | Other | SR 1643 (BETHPAGE ROAD) | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 23000 | FY 2025: 23000
C-5603F | Highway | Other | SR 1643 (BETHPAGE ROAD) | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1892000 | FY 2025: 1892000
C-5603F | Highway | Other | SR 1643 (BETHPAGE ROAD) | SR 1008 (SOUTH MAIN STREET) TO LEONARD AVENUE AND FROM WESTGREEN DRIVE TO KLONDALE AVENUE IN KANNAPOLIS. CONSTRUCT SIDEWALKS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L(M) | CONSTRUCTION | 473000 | FY 2025: 473000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CMAQ | ENGINEERING | 44000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L(M) | ENGINEERING | 11000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CMAQ | RIGHT-OF-WAY | 50000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L(M) | RIGHT-OF-WAY | 12000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CMAQ | CONSTRUCTION | 514000 | FY 2025: 514000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CMAQ | CONSTRUCTION | 676000 | FY 2025: 676000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | CRPANY | CONSTRUCTION | 305000 | FY 2025: 305000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L(M) | CONSTRUCTION | 169000 | FY 2025: 169000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L(M) | CONSTRUCTION | 129000 | FY 2025: 129000
C-5603H | Highway | Other | BRENNER AVENUE | STATESVILLE BOULEVARD TO WEST HORAH STREET AND BRENNER AVENUE AT LINK AVENUE IN SALISBURY. |  | ROWAN | 9 | Cabarrus-Rowan MPO | $676,032 IN CMAQ TRANSFERRED FROM BL-0034 | Exempt |  | L | CONSTRUCTION | 76000 | FY 2025: 76000
C-5603I | Highway | Other | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | ENGINEERING | 400000
C-5603I | Highway | Other | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | ENGINEERING | 100000
C-5603I | Highway | Other | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | RIGHT-OF-WAY | 200000 | FY 2025: 200000
C-5603I | Highway | Other | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | RIGHT-OF-WAY | 50000 | FY 2025: 50000
C-5603I | Highway | Other | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | CMAQ | CONSTRUCTION | 3905000 | FY 2025: 3905000
C-5603I | Highway | Other | US 601 | FLOWES STORE ROAD TO ZION CHURCH ROAD AND AT THE US 601 AND FLOWES STORE ROAD INTERSECTION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Exempt |  | L(M) | CONSTRUCTION | 976000 | FY 2025: 976000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 951000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L | ENGINEERING | 237000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 951000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L | RIGHT-OF-WAY | 237000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 18897000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L | CONSTRUCTION | 4725000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 951000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L | IMPLEMENTATION | 237000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 951000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | BGDA | OPERATIONS | 414000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L | OPERATIONS | 103000
C-5604 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE | 4, 5 | Capital Area MPO | IN PROGRESS | Exempt |  | L | OPERATIONS | 237000
C-5604HA | Highway | Other | MINGO CREEK GREENWAY | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | RIGHT-OF-WAY | 538000
C-5604HA | Highway | Other | MINGO CREEK GREENWAY | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | RIGHT-OF-WAY | 134000
C-5604HA | Highway | Other | MINGO CREEK GREENWAY | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | CMAQ | CONSTRUCTION | 2745000
C-5604HA | Highway | Other | MINGO CREEK GREENWAY | EXISTING GREENWAY TO KNIGHTDALE STATION PARK IN KNIGHTDALE |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | CONSTRUCTION | 686000
C-5604ID | Highway | Other | HIGGINS GREENWAY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 1520000
C-5604ID | Highway | Other | HIGGINS GREENWAY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 380000
C-5604ID | Highway | Other | HIGGINS GREENWAY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 999000
C-5604ID | Highway | Other | HIGGINS GREENWAY | TOWN OF CARY HIGGINS GREENWAY PHASE 3 |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 250000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 357000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 90000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 357000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 90000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 4392000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 484000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 1098000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 121000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 925000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 232000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 357000
C-5605 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 90000
C-5605H | Highway | Other | VARIOUS | DESIGN AND INSTALL PEDESTRIAN AND VEHICLE WAYFINDING SIGNAGE TO FACILITATE NAVIGATION TO POINTS OF INTEREST AND PARKING IN DURHAM. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 484000
C-5605H | Highway | Other | VARIOUS | DESIGN AND INSTALL PEDESTRIAN AND VEHICLE WAYFINDING SIGNAGE TO FACILITATE NAVIGATION TO POINTS OF INTEREST AND PARKING IN DURHAM. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | CONSTRUCTION | 121000
C-5606 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GASTON-CLEVELAND-LINCOLN MPO. |  | GASTON, CLEVELAND, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | "HF" FUNDS ON SEGMENT I REPRESENT CONTIGENCY FUNDS | Exempt
C-5606B | Bike & Ped | Locally Selected | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 0.47 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | CMAQ | ENGINEERING | 101000
C-5606B | Bike & Ped | Locally Selected | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 0.47 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | L(M) | ENGINEERING | 25000
C-5606B | Bike & Ped | Locally Selected | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 0.47 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | CMAQ | RIGHT-OF-WAY | 4000 | FY 2025: 4000
C-5606B | Bike & Ped | Locally Selected | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 0.47 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | L(M) | RIGHT-OF-WAY | 1000 | FY 2025: 1000
C-5606B | Bike & Ped | Locally Selected | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 0.47 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | CMAQ | CONSTRUCTION | 423000 | FY 2025: 423000
C-5606B | Bike & Ped | Locally Selected | NC 161 | SOUTH 13TH STREET TO WEST BOSTON AVENUE. CONSTRUCT SIDEWALK WITH CROSSWALKS AT SOUTH 13TH STREET AND SOUTH 14TH STREET. | 0.47 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | INCORPORATES WORK FORMERLY UNDER C-5606L. CMAQ AWARD AMOUNT IS $527,847. | Exempt |  | L(M) | CONSTRUCTION | 106000 | FY 2025: 106000
C-5606D | Bike & Ped | Locally Selected | US 321 BUSINESS, NC 275/279 | CONSTRUCT SIDEWALKS ALONG PORTIONS OF US 321 BUSINESS AND NC 275/279 NEAR GASTON COLLEGE, INCLUDING A CROSSWALK ACROSS NC 275/279. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $383,779. | Exempt |  | CMAQ | CONSTRUCTION | 314000
C-5606D | Bike & Ped | Locally Selected | US 321 BUSINESS, NC 275/279 | CONSTRUCT SIDEWALKS ALONG PORTIONS OF US 321 BUSINESS AND NC 275/279 NEAR GASTON COLLEGE, INCLUDING A CROSSWALK ACROSS NC 275/279. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $383,779. | Exempt |  | L(M) | CONSTRUCTION | 79000
C-5606E | Bike & Ped | Locally Selected | NEW ROUTE | TECHNOLOGY PARK TO GASTON COLLEGE. CONSTRUCT GREENWAY. | 0.63 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $513,300. | Exempt |  | CMAQ | CONSTRUCTION | 470000
C-5606E | Bike & Ped | Locally Selected | NEW ROUTE | TECHNOLOGY PARK TO GASTON COLLEGE. CONSTRUCT GREENWAY. | 0.63 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $513,300. | Exempt |  | L(M) | CONSTRUCTION | 118000
C-5606I | Bike & Ped | Locally Selected | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 0.09 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000. | Exempt |  | CMAQ | CONSTRUCTION | 158000
C-5606I | Bike & Ped | Locally Selected | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 0.09 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000. | Exempt |  | CMAQ | CONSTRUCTION | 200000
C-5606I | Bike & Ped | Locally Selected | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 0.09 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000. | Exempt |  | L(M) | CONSTRUCTION | 42000
C-5606I | Bike & Ped | Locally Selected | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 0.09 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000. | Exempt |  | L(M) | CONSTRUCTION | 50000
C-5606I | Bike & Ped | Locally Selected | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | 0.09 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $158,000. | Exempt |  | HF | CONSTRUCTION | 250000
C-5606J | Bike & Ped | Locally Selected | NEW ROUTE | CONSTRUCT POSTON PARK SIDEWALK CONNECTOR. | 0.26 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $334,379. | Exempt |  | CMAQ | CONSTRUCTION | 149000
C-5606J | Bike & Ped | Locally Selected | NEW ROUTE | CONSTRUCT POSTON PARK SIDEWALK CONNECTOR. | 0.26 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $334,379. | Exempt |  | L(M) | CONSTRUCTION | 37000
C-5606K | Bike & Ped | Locally Selected | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 0.8 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | CMAQ | ENGINEERING | 103000
C-5606K | Bike & Ped | Locally Selected | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 0.8 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | L(M) | ENGINEERING | 26000
C-5606K | Bike & Ped | Locally Selected | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 0.8 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | CMAQ | RIGHT-OF-WAY | 12000
C-5606K | Bike & Ped | Locally Selected | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 0.8 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | L(M) | RIGHT-OF-WAY | 3000
C-5606K | Bike & Ped | Locally Selected | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 0.8 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | CMAQ | CONSTRUCTION | 1265000
C-5606K | Bike & Ped | Locally Selected | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | 0.8 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $757,478. | Exempt |  | L(M) | CONSTRUCTION | 316000
C-5606M | Bike & Ped | Locally Selected | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 1.82 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | CMAQ | ENGINEERING | 382000
C-5606M | Bike & Ped | Locally Selected | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 1.82 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | L(M) | ENGINEERING | 95000
C-5606M | Bike & Ped | Locally Selected | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 1.82 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | CMAQ | RIGHT-OF-WAY | 15000
C-5606M | Bike & Ped | Locally Selected | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 1.82 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | L(M) | RIGHT-OF-WAY | 4000
C-5606M | Bike & Ped | Locally Selected | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 1.82 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | CMAQ | CONSTRUCTION | 1091000 | FY 2025: 1091000
C-5606M | Bike & Ped | Locally Selected | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALK ON SOUTH SIDE OF NEAL HAWKINS ROAD FROM EXISTING SIDEWALK AT MARTHA RIVERS PARK TO EXISTING SIDEWALK AT VILLAGE OF PARKSIDE, CONSTRUCT MID-BLOCK CROSSING SOUTH OF FORBES ROAD, AND CONSTRUCT SIDEWALK ON NORTH SIDE OF NEAL HAWKINS ROAD FROM THE MID-BLOCK CROSSWALK TO TO HAWK RIDGE DRIVE. | 1.82 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,488,462. | Exempt |  | L(M) | CONSTRUCTION | 273000 | FY 2025: 273000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 288000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | L | ENGINEERING | 72000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 288000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | L | RIGHT-OF-WAY | 72000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1722000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 432000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 288000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | L | IMPLEMENTATION | 72000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CMAQ | OPERATIONS | 288000
C-5607 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | L | OPERATIONS | 72000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 41000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L | ENGINEERING | 10000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 41000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L | RIGHT-OF-WAY | 10000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 242000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L | CONSTRUCTION | 61000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 41000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L | IMPLEMENTATION | 10000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 41000
C-5608 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. |  | CATAWBA | 12 | Greater Hickory MPO | IN PROGRESS | Exempt |  | L | OPERATIONS | 10000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 195000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | ENGINEERING | 48000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 195000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 48000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 1164000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 291000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 195000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 48000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 195000
C-5609 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. |  | DAVIDSON, GUILFORD, FORSYTH | 7, 9 | High Point Urban Area MPO | IN PROGRESS | Exempt |  | L(M) | OPERATIONS | 48000
C-5609F | Highway | Other | VARIOUS | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 32000 | FY 2025: 32000
C-5609F | Highway | Other | VARIOUS | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 8000 | FY 2025: 8000
C-5609F | Highway | Other | VARIOUS | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 440000 | FY 2025: 440000
C-5609F | Highway | Other | VARIOUS | CHIMNEY COURT AND JAMESTOWN OAKS DRIVE IN JAMESTOWN. OAKDALE PEDESTRIAN IMPROVEMENTS CONSTRUCT SIDEWALKS. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 110000 | FY 2025: 110000
C-5609L | Highway | Other | VARIOUS | SIDEWALK IMPROVEMENTS. |  | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 76000
C-5609L | Highway | Other | VARIOUS | SIDEWALK IMPROVEMENTS. |  | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L(M) | RIGHT-OF-WAY | 19000
C-5609L | Highway | Other | VARIOUS | SIDEWALK IMPROVEMENTS. |  | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 1488000
C-5609L | Highway | Other | VARIOUS | SIDEWALK IMPROVEMENTS. |  | GUILFORD | 7 | High Point Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L(M) | CONSTRUCTION | 372000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 84000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L | ENGINEERING | 21000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 84000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L | RIGHT-OF-WAY | 21000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 495000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L | CONSTRUCTION | 123000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 84000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L | IMPLEMENTATION | 21000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 84000
C-5610 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. |  | GRANVILLE, FRANKLIN, PERSON | 5 | Kerr-Tar RPO | IN PROGRESS | Exempt |  | L | OPERATIONS | 21000
C-5610B | Bike & Ped | NCDOT Selected (Other Selection Process) | EAST INDUSTRY DRIVE SIDEWALK | 250 FEET WEST OF THE INTERSECTION OF LEWIS STREET AND EAST INDUSTRY DRIVE TO SPEED EEZ CARWASH DRIVEWAY. CONSTRUCT SIDEWALK. | 0.85 | GRANVILLE | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 769000 | FY 2025: 769000
C-5610B | Bike & Ped | NCDOT Selected (Other Selection Process) | EAST INDUSTRY DRIVE SIDEWALK | 250 FEET WEST OF THE INTERSECTION OF LEWIS STREET AND EAST INDUSTRY DRIVE TO SPEED EEZ CARWASH DRIVEWAY. CONSTRUCT SIDEWALK. | 0.85 | GRANVILLE | 5 | Kerr-Tar RPO |  | Exempt |  | L | CONSTRUCTION | 192000 | FY 2025: 192000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | SMOKE TREE WAY, NORTH MAIN STREET, HOSPITAL DRIVE | SMOKE TREE WAY, NORTH MAIN STREET, AND HOSPITAL DRIVE. CONSTRUCT 2245 FEET OF SIDEWALKS WITH CROSSWALK AT SMOKE TREE WAY. |  | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | ENGINEERING | 118000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | SMOKE TREE WAY, NORTH MAIN STREET, HOSPITAL DRIVE | SMOKE TREE WAY, NORTH MAIN STREET, AND HOSPITAL DRIVE. CONSTRUCT 2245 FEET OF SIDEWALKS WITH CROSSWALK AT SMOKE TREE WAY. |  | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | L | ENGINEERING | 30000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | SMOKE TREE WAY, NORTH MAIN STREET, HOSPITAL DRIVE | SMOKE TREE WAY, NORTH MAIN STREET, AND HOSPITAL DRIVE. CONSTRUCT 2245 FEET OF SIDEWALKS WITH CROSSWALK AT SMOKE TREE WAY. |  | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 126000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | SMOKE TREE WAY, NORTH MAIN STREET, HOSPITAL DRIVE | SMOKE TREE WAY, NORTH MAIN STREET, AND HOSPITAL DRIVE. CONSTRUCT 2245 FEET OF SIDEWALKS WITH CROSSWALK AT SMOKE TREE WAY. |  | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | L | RIGHT-OF-WAY | 31000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | SMOKE TREE WAY, NORTH MAIN STREET, HOSPITAL DRIVE | SMOKE TREE WAY, NORTH MAIN STREET, AND HOSPITAL DRIVE. CONSTRUCT 2245 FEET OF SIDEWALKS WITH CROSSWALK AT SMOKE TREE WAY. |  | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 440000 | FY 2025: 440000
C-5610E | Bike & Ped | NCDOT Selected (Other Selection Process) | SMOKE TREE WAY, NORTH MAIN STREET, HOSPITAL DRIVE | SMOKE TREE WAY, NORTH MAIN STREET, AND HOSPITAL DRIVE. CONSTRUCT 2245 FEET OF SIDEWALKS WITH CROSSWALK AT SMOKE TREE WAY. |  | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | L | CONSTRUCTION | 110000 | FY 2025: 110000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 3000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L | ENGINEERING | 1000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 3000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L | RIGHT-OF-WAY | 1000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 15000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L | CONSTRUCTION | 4000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 3000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L | IMPLEMENTATION | 1000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 3000
C-5612 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. |  | HAYWOOD, SWAIN | 14 | Land-of-Sky RPO, Southwestern RPO | IN PROGRESS | Exempt |  | L | OPERATIONS | 1000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | ENGINEERING | 414000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | ENGINEERING | 104000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | RIGHT-OF-WAY | 414000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | RIGHT-OF-WAY | 104000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | CONSTRUCTION | 2486000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | CONSTRUCTION | 622000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | IMPLEMENTATION | 414000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | IMPLEMENTATION | 104000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | CMAQ | OPERATIONS | 414000
C-5613 | Highway | Locally Selected | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. |  | MECKLENBURG, IREDELL, UNION | 10, 12 | Charlotte Regional TPO | IN PROGRESS. | Exempt |  | L(M) | OPERATIONS | 104000
C-5613BD | Highway | Locally Selected | SR 1138 (ARROWOOD ROAD) | NC 49 (SOUTH TRYON) TO SOUTH BOULEVARD. ITS UPGRADES. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | CMAQ | CONSTRUCTION | 485000
C-5613BD | Highway | Locally Selected | SR 1138 (ARROWOOD ROAD) | NC 49 (SOUTH TRYON) TO SOUTH BOULEVARD. ITS UPGRADES. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L(M) | CONSTRUCTION | 129000
C-5613BE | Highway | Locally Selected | SR 2467 (MALLARD CREEK ROAD) | NC 24 (HARRIS BOULEVARD) TO GOVERNOR HUNT ROAD. ITS AND TRAFFIC MANAGEMENT UPGRADES. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | CMAQ | CONSTRUCTION | 158000
C-5613BE | Highway | Locally Selected | SR 2467 (MALLARD CREEK ROAD) | NC 24 (HARRIS BOULEVARD) TO GOVERNOR HUNT ROAD. ITS AND TRAFFIC MANAGEMENT UPGRADES. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | L(M) | CONSTRUCTION | 42000
C-5613J | Highway | Locally Selected | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | CMAQ | RIGHT-OF-WAY | 50000
C-5613J | Highway | Locally Selected | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | L(M) | RIGHT-OF-WAY | 25000
C-5613J | Highway | Locally Selected | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | CMAQ | CONSTRUCTION | 822000 | FY 2025: 822000
C-5613J | Highway | Locally Selected | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | BGDA | CONSTRUCTION | 1121000 | FY 2025: 1121000
C-5613J | Highway | Locally Selected | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | L(M) | CONSTRUCTION | 405000 | FY 2025: 405000
C-5613J | Highway | Locally Selected | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. CMAQ AWARD AMOUNT IS $1,003,265 | Exempt |  | L(M) | CONSTRUCTION | 1121000 | FY 2025: 1121000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | ENGINEERING | 9000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | L | ENGINEERING | 3000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 9000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | L | RIGHT-OF-WAY | 3000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 45000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | L | CONSTRUCTION | 12000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 9000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | L | IMPLEMENTATION | 3000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | CMAQ | OPERATIONS | 9000
C-5614 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. |  | DAVIE | 9 | Northwest Piedmont RPO |  | Exempt |  | L | OPERATIONS | 3000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 92000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L | ENGINEERING | 24000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 92000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L | RIGHT-OF-WAY | 24000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 728000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 182000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 92000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L | IMPLEMENTATION | 24000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CMAQ | OPERATIONS | 92000
C-5616 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L | OPERATIONS | 24000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | CMAQ | ENGINEERING | 5000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | L | ENGINEERING | 1000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 5000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | L | RIGHT-OF-WAY | 1000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 30000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | L | CONSTRUCTION | 8000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 5000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | L | IMPLEMENTATION | 1000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | CMAQ | OPERATIONS | 5000
C-5617 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. |  | UNION | 10 | Rocky River RPO |  | Exempt |  | L | OPERATIONS | 1000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | ENGINEERING | 36000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | L | ENGINEERING | 9000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 36000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | L | RIGHT-OF-WAY | 9000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 204000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | L | CONSTRUCTION | 51000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 36000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | L | IMPLEMENTATION | 9000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | CMAQ | OPERATIONS | 36000
C-5618 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. |  | CHATHAM, ORANGE | 7, 8 | Central Pines RPO |  | Exempt |  | L | OPERATIONS | 9000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | ENGINEERING | 335000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | L | ENGINEERING | 85000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 335000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | L | RIGHT-OF-WAY | 85000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1995000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | L | CONSTRUCTION | 500000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 335000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | L | IMPLEMENTATION | 85000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | CMAQ | OPERATIONS | 335000
C-5619 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. |  | JOHNSTON, EDGECOMBE, NASH | 4 | Upper Coastal Plain RPO |  | Exempt |  | L | OPERATIONS | 85000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 291000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L | ENGINEERING | 75000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 291000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L | RIGHT-OF-WAY | 75000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 4266000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L | CONSTRUCTION | 1065000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 291000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L | IMPLEMENTATION | 75000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | CMAQ | OPERATIONS | 291000
C-5620 | Highway | Other | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. |  | FORSYTH, DAVIDSON, DAVIE | 9 | Winston-Salem Area TPO | IN PROGRESS | Exempt |  | L | OPERATIONS | 75000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | CMAQ | ENGINEERING | 1533000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | BA | ENGINEERING | 333000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | L | ENGINEERING | 50000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | CMAQ | RIGHT-OF-WAY | 4946000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | BA | RIGHT-OF-WAY | 785000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | L | RIGHT-OF-WAY | 452000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | CMAQ | CONSTRUCTION | 7474000 | FY 2025: 3054000; FY 2026: 667000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | BGDA | CONSTRUCTION | 4861000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | T(M) | CONSTRUCTION | 1870000 | FY 2025: 764000; FY 2026: 167000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | L | CONSTRUCTION | 4757000
C-5621 | Highway | Locally Selected | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP. | Region E |  | L | CONSTRUCTION | 4861000
C-5622 | Bike & Ped | Locally Selected | GASTON COUNTY | HIGHLAND BRANCH GREENWAY, PHASE I. CONSTRUCT GREENWAY | 0.62 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. CMAQ AWARD AMOUNT IS $1,068,204. | Exempt |  | L | CONSTRUCTION | 53000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | CMAQ | ENGINEERING | 167000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | L | ENGINEERING | 42000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | CMAQ | RIGHT-OF-WAY | 200000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | L | RIGHT-OF-WAY | 50000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | CMAQ | UTILITIES | 550000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | L | UTILITIES | 110000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | CMAQ | CONSTRUCTION | 633000 | FY 2025: 633000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | BGANY | CONSTRUCTION | 2123000 | FY 2025: 2123000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | L | CONSTRUCTION | 186000 | FY 2025: 186000
C-5624 | Bike & Ped | Locally Selected | CONOVER | 1ST STREET/US 70 IN CONOVER. CONSTRUCT BIKE AND PEDESTRIAN IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO | $2.123M IN BGANY USED AS PART OF FUND SWAP. CMAQ AWARD AMOUNT IS $1,894,000. | Division 12 |  | L | CONSTRUCTION | 531000 | FY 2025: 531000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGANY | ENGINEERING | 8000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | ENGINEERING | 2000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGANY | RIGHT-OF-WAY | 100000 | FY 2025: 100000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 25000 | FY 2025: 25000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | CMAQ | CONSTRUCTION | 1000000 | FY 2026: 1000000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGANY | CONSTRUCTION | 530000 | FY 2026: 530000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGANY | CONSTRUCTION | 206000 | FY 2026: 206000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 888000 | FY 2026: 888000
C-5650 | Bike & Ped | Locally Selected | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO EAST/WEST MAIN STREET IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 52000 | FY 2026: 52000
C-5700 | Bike & Ped | Locally Selected | OAKDALE ROAD | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | 0.53 | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 8000
C-5700 | Bike & Ped | Locally Selected | OAKDALE ROAD | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | 0.53 | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | L | ENGINEERING | 2000
C-5700 | Bike & Ped | Locally Selected | OAKDALE ROAD | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | 0.53 | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 136000 | FY 2025: 136000
C-5700 | Bike & Ped | Locally Selected | OAKDALE ROAD | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | 0.53 | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 34000 | FY 2025: 34000
C-5701 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | CMAQ | RIGHT-OF-WAY | 256000
C-5701 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | L | RIGHT-OF-WAY | 68000
C-5701 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | CMAQ | CONSTRUCTION | 1912000
C-5701 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | BGDA | CONSTRUCTION | 157000
C-5701 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | BA | CONSTRUCTION | 650000
C-5701 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | L | CONSTRUCTION | 478000
C-5701 | Highway | Locally Selected | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Region F |  | L | CONSTRUCTION | 39000
C-5702 | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM, INCLUDING EMISSIONS-REDUCING SUB-AWARDS, IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt
C-5702A | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Exempt
C-5702B | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Exempt
C-5702C | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt
C-5702D | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | IMPLEMENTATION | 1210000
C-5702D | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | IMPLEMENTATION | 1396000
C-5702D | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | IMPLEMENTATION | 4668000
C-5702D | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | L(M) | IMPLEMENTATION | 1167000
C-5702D | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | L(M) | IMPLEMENTATION | 303000
C-5702D | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | L(M) | IMPLEMENTATION | 349000
C-5702E | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | IMPLEMENTATION | 3245000
C-5702E | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | IMPLEMENTATION | 1222000
C-5702E | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | L(M) | IMPLEMENTATION | 306000
C-5702E | Highway | Other | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | L(M) | IMPLEMENTATION | 811000
C-5703 | Highway | Other | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | CMAQ | RIGHT-OF-WAY | 600000
C-5703 | Highway | Other | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | T(M) | RIGHT-OF-WAY | 139000
C-5703 | Highway | Other | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | L(M) | RIGHT-OF-WAY | 11000
C-5703 | Highway | Other | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | CMAQ | CONSTRUCTION | 9081000
C-5703 | Highway | Other | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | T(M) | CONSTRUCTION | 1963000
C-5703 | Highway | Other | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1). | Region F |  | L(M) | CONSTRUCTION | 319000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | CMAQ | ENGINEERING | 78000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | CMAQ | ENGINEERING | 175000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | L | ENGINEERING | 20000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | L | ENGINEERING | 44000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | CMAQ | RIGHT-OF-WAY | 41000 | FY 2025: 41000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | L | RIGHT-OF-WAY | 10000 | FY 2025: 10000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | CMAQ | CONSTRUCTION | 568000 | FY 2026: 568000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | CMAQ | CONSTRUCTION | 321000 | FY 2025: 321000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | L | CONSTRUCTION | 142000 | FY 2026: 142000
C-5704 | Bike & Ped | Locally Selected | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | 0.37 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | CMAQ AWARD AMOUNT IS $1,183,200 | Exempt |  | L | CONSTRUCTION | 332000 | FY 2025: 332000
C-5705 | Bike & Ped | Locally Selected | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 1.9 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | ENGINEERING | 124000
C-5705 | Bike & Ped | Locally Selected | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 1.9 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | ENGINEERING | 31000
C-5705 | Bike & Ped | Locally Selected | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 1.9 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 80000 | FY 2027: 80000
C-5705 | Bike & Ped | Locally Selected | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 1.9 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | RIGHT-OF-WAY | 20000 | FY 2027: 20000
C-5705 | Bike & Ped | Locally Selected | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 1.9 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1210000 | FY 2028: 12000; FY 2029: 1198000
C-5705 | Bike & Ped | Locally Selected | LEWISVILLE | LEWISVILLE-VIENNA ROAD. EXTEND SIDEWALK. | 1.9 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | CONSTRUCTION | 302000 | FY 2028: 302000
EB-3314 | Bike & Ped | Pre-STI (Historic) | VARIOUS | STATEWIDE PEDESTRIAN FACILITIES PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT | UNDER CONSTRUCTION | Pre-STI (Transition)
EB-4020 | Bike & Ped | Locally Selected | BRUSHY FORK GREENWAY | WATERWORKS ROAD TO REYNOLDS PARK ROAD IN WINSTON-SALEM. PAVED MULTI-USE TRAIL. | 2.2 | FORSYTH | 9 | Winston-Salem Area TPO |  | Pre-STI (Transition)
EB-4020A | Bike & Ped | Locally Selected | BRUSHY FORK GREENWAY | WATERWORKS ROAD TO OLD GREENSBORO ROAD |  | FORSYTH | 9 | Winston-Salem Area TPO | COMPLETE
EB-4020B | Bike & Ped | Locally Selected | BRUSHY FORK GREENWAY | OLD GREENSBORO ROAD TO LOWERY STREET |  | FORSYTH | 9 | Winston-Salem Area TPO | COMPLETE
EB-4020C | Bike & Ped | Transition | BRUSHY FORK GREENWAY | LOWERY STREET TO REYNOLDS PARK ROAD | 0.53 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 1726000 | FY 2025: 1726000
EB-4020C | Bike & Ped | Transition | BRUSHY FORK GREENWAY | LOWERY STREET TO REYNOLDS PARK ROAD | 0.53 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS, CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Pre-STI (Transition) |  | L | CONSTRUCTION | 432000 | FY 2025: 432000
EB-4539 | Bike & Ped | Pre-STI (Historic) | FAYETTEVILLE | CAPE FEAR RIVER GREENWAY, CLARK PARK SOUTH TO THE CAPE FEAR BOTANICAL GARDENS. CONSTRUCT SECOND PHASE OF AN OFF-ROAD MULTI-USE TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Pre-STI (Transition)
EB-4539A | Bike & Ped | Pre-STI (Historic) | FAYETTEVILLE | I-95 BUSINESS/US 301 TO THE SOUTH SIDE OF CSX RAIL LINE. | 1.23 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition)
EB-4539BB | Bike & Ped | Pre-STI (Historic) | FAYETTEVILLE | EXISTING TRAIL AT CLARK PARK TO NORTH SIDE OF CSX RAIL LINE. | 1.26 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition)
EB-4539BC | Bike & Ped | Pre-STI (Historic) | FAYETTEVILLE | NORTH OF CSX RAIL LINE TO SOUTH OF CSX RAIL LINE. | 0.27 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | TAANY | CONSTRUCTION | 761000
EB-4539BC | Bike & Ped | Pre-STI (Historic) | FAYETTEVILLE | NORTH OF CSX RAIL LINE TO SOUTH OF CSX RAIL LINE. | 0.27 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | L | CONSTRUCTION | 190000
EB-4707 | Bike & Ped | Pre-STI (Historic) | SR 2220 (OLD CHAPEL HILL ROAD) SR 1838 (OLD DURHAM | US 15 / US 501 IN ORANGE COUNTY TO SR 1116 (GARRETT ROAD) IN DURHAM COUNTY. BICYCLE, PEDESTRIAN, AND TRANSIT IMPROVEMENTS; AND CONSTRUCTION OF ROUNDABOUT. | 2.7 | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Pre-STI (Transition)
EB-4707A | Highway | Transition | SR 1838 / SR 2220 | US 15 / US 501 IN ORANGE COUNTY TO SR 1113 (POPE ROAD) IN DURHAM COUNTY | 1 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
EB-4707B | Highway | Transition | SR 2220 | SR 1113 (POPE ROAD) TO SR 1116 (GARRETT ROAD) | 2.63 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
EB-5517 | Bike & Ped | Transition | NEW PEDESTRIAN BRIDGE AND APPROACHES | EXISTING SIDEWALK TO PIEDMONT ENVIRONMENTAL CENTER ENTRANCE IN HIGH POINT AND JAMESTOWN. CONSTRUCT PEDESTRIAN BRIDGE OVER EAST FORK OF DEEP RIVER. | 0.5 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN | Pre-STI (Transition)
EB-5518 | Bike & Ped | Transition | LATHAM PARK GREENWAY | BATTLEGROUND AVENUE TO MENDENHALL STREET IN GREENSBORO. REMOVE THROUGH LANE ON HILL STREET AND CONSTRUCT MULTI-USE PATH. | 0.11 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION BY CITY OF GREENSBORO | Pre-STI (Transition)
EB-5519 | Bike & Ped | Transition | SR 4121 (EAST MAIN STREET) | EXISTING SIDEWALK NEAR JAMESTOWN MUNICIPAL BUILDING TO YORKLEIGH LANE NEAR GUILFORD TECHNICAL COMMUNITY COLLEGE JAMESTOWN CAMPUS/RAGSDALE HIGH SCHOOL COMPLEX IN JAMESTOWN. CONSTRUCT SIDEWALK. | 0.57 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN | Pre-STI (Transition)
EB-5521 | Bike & Ped | Transition | NC 134 (NORTH MAIN STREET); SR 1005 (SOUTH MAIN ST | SR 1323 (OKEEWEMEE ROAD) TO BARNHILL STREET IN TROY. CONSTRUCT SIDEWALKS. | 2.37 | MONTGOMERY | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION BY TOWN OF TROY | Pre-STI (Transition)
EB-5531 | Bike & Ped | Transition | BESSEMER CITY | PHASE I: 12TH STREET, CHADWICK COURT TO KAISER ROAD. PHASE II: YELLOW JACKET LANE/BESS TOWN ROAD, 12TH STREET TO 14TH STREET (NC 274). CONSTRUCT SIDEWALKS. | 0.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 300000
EB-5533 | Bike & Ped | Transition | GASTONIA | POSTON PARK TO SOUTH FORK RIVER GREENWAY. CONSTRUCT TRAIL. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
EB-5539 | Bike & Ped | Transition | GREENVILLE | SOUTH TAR RIVER GREENWAY. PHASE 3: PITT STREET TO NASH STREET. CONSTRUCT GREENWAY USING EXISTING SIDEWALKS, ROADS AND ON NEW LOCATION ALONG THE RIVER. | 0.89 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition)
EB-5540 | Bike & Ped | STI (Prioritization) | LITTLE CROSS CREEK GREENWAY EXTENSION | FILTER PLANT DRIVE TO ROWAN STREET BRIDGE IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.75 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | CONSTRUCTION | 600000 | FY 2027: 600000
EB-5540 | Bike & Ped | STI (Prioritization) | LITTLE CROSS CREEK GREENWAY EXTENSION | FILTER PLANT DRIVE TO ROWAN STREET BRIDGE IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | 0.75 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | CONSTRUCTION | 150000 | FY 2027: 150000
EB-5541 | Bike & Ped | Locally Selected | BIG CROSS CREEK GREENWAY | LITTLE CROSS CREEK TO 295 FOR A POSSIBLE FUTURE CONNECTION TO FORT LIBERTY TRAILS OUTSIDE OF FORT LIBERTY. CONSTRUCT MULTIUSE TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY USING STBGDA FUNDS. | Division 6 |  | TADA | ENGINEERING | 380000
EB-5541 | Bike & Ped | Locally Selected | BIG CROSS CREEK GREENWAY | LITTLE CROSS CREEK TO 295 FOR A POSSIBLE FUTURE CONNECTION TO FORT LIBERTY TRAILS OUTSIDE OF FORT LIBERTY. CONSTRUCT MULTIUSE TRAIL. |  | CUMBERLAND | 6 | Fayetteville Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY USING STBGDA FUNDS. | Division 6 |  | L(M) | ENGINEERING | 95000
EB-5547 | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM EXISTING FLAT CREEK GREENWAY TRAILHEAD NORTH OF US 70 TO THE OAKS TRAIL. |  | BUNCOMBE | 13 | French Broad River MPO | $3.234M IN BGANY USED AS PART OF MULTIPLE FUND SWAPS. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.991M. DUE TO COST CHANGES, THE TOTAL OF BGANY CHANGED TO $2.915M. | Division 13
EB-5547A | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | ENGINEERING | 232000
EB-5547A | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | ENGINEERING | 58000
EB-5547A | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 32000 | FY 2025: 32000
EB-5547A | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | RIGHT-OF-WAY | 8000 | FY 2025: 8000
EB-5547A | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 1247000 | FY 2026: 12000; FY 2027: 1235000
EB-5547A | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 312000 | FY 2026: 312000
EB-5547B | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | ENGINEERING | 147000
EB-5547B | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | ENGINEERING | 37000
EB-5547B | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 16000 | FY 2025: 16000
EB-5547B | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | RIGHT-OF-WAY | 4000 | FY 2025: 4000
EB-5547B | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 1241000 | FY 2026: 12000; FY 2027: 1229000
EB-5547B | Bike & Ped | Locally Selected | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 310000 | FY 2026: 310000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | BGANY | ENGINEERING | 120000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | L(M) | ENGINEERING | 30000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | BGANY | RIGHT-OF-WAY | 24000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | L(M) | RIGHT-OF-WAY | 6000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | BGANY | CONSTRUCTION | 590000 | FY 2025: 590000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | BGDA | CONSTRUCTION | 2400000 | FY 2026: 2400000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | L(M) | CONSTRUCTION | 148000 | FY 2025: 148000
EB-5600 | Bike & Ped | STI (Prioritization) | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | 1.76 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON. | Division 3 |  | L(M) | CONSTRUCTION | 600000 | FY 2026: 600000
EB-5619 | Bike & Ped | Other | GRANTS CREEK GREENWAY | KELSEY SCOTT PARK TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT MULTI-USE PATH. |  | ROWAN | 9 | Cabarrus-Rowan MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SALISBURY | Division 9
EB-5619A | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | VICINITY OF FORESTDALE DRIVE TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT LOW-WATER BRIDGE GREENWAY CONNECTION. |  | ROWAN | 9 | Cabarrus-Rowan MPO | COMPLETE | Division 9
EB-5619B | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO 1000 FEET SOUTH OF STATESVILLE BOULEVARD. CONSTRUCT MULTI-USE PATH. | 0.61 | ROWAN | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | RIGHT-OF-WAY | 660000
EB-5619B | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO 1000 FEET SOUTH OF STATESVILLE BOULEVARD. CONSTRUCT MULTI-USE PATH. | 0.61 | ROWAN | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 165000
EB-5619B | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO 1000 FEET SOUTH OF STATESVILLE BOULEVARD. CONSTRUCT MULTI-USE PATH. | 0.61 | ROWAN | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 1388000 | FY 2025: 1388000
EB-5619B | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO 1000 FEET SOUTH OF STATESVILLE BOULEVARD. CONSTRUCT MULTI-USE PATH. | 0.61 | ROWAN | 9 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 347000 | FY 2025: 347000
EB-5619C | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TADA | ENGINEERING | 540000
EB-5619C | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | ENGINEERING | 135000
EB-5619C | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 52000 | FY 2025: 52000
EB-5619C | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | RIGHT-OF-WAY | 13000 | FY 2025: 13000
EB-5619C | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | UTILITIES | 36000 | FY 2025: 36000
EB-5619C | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | UTILITIES | 9000 | FY 2025: 9000
EB-5619C | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1635000 | FY 2026: 1635000
EB-5619C | Bike & Ped | Locally Selected | GRANTS CREEK GREENWAY | 1000 FEET SOUTH OF STATESVILLE BOULEVARD TO KELSEY SCOTT PARK ALONG WILTSHIRE PLACE, EAST COLONIAL DRIVE AND SOUTH MCCOY ROAD. CONSTRUCT MULTI-USE PATH. | 0.31 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | CONSTRUCTION | 409000 | FY 2026: 409000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 0.52 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 176000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 0.52 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | RIGHT-OF-WAY | 44000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 0.52 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | UTILITIES | 60000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 0.52 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | UTILITIES | 15000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 0.52 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 1226000
EB-5701 | Bike & Ped | STI (Prioritization) | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | 0.52 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 307000
EB-5703 | Bike & Ped | STI (Prioritization) | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 0.69 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | RIGHT-OF-WAY | 120000
EB-5703 | Bike & Ped | STI (Prioritization) | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 0.69 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 30000
EB-5703 | Bike & Ped | STI (Prioritization) | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 0.69 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | CONSTRUCTION | 1040000 | FY 2025: 1040000
EB-5703 | Bike & Ped | STI (Prioritization) | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | 0.69 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 260000 | FY 2025: 260000
EB-5704 | Bike & Ped | STI (Prioritization) | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 0.35 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | RIGHT-OF-WAY | 135000
EB-5704 | Bike & Ped | STI (Prioritization) | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 0.35 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 34000
EB-5704 | Bike & Ped | STI (Prioritization) | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 0.35 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | CONSTRUCTION | 464000 | FY 2025: 464000
EB-5704 | Bike & Ped | STI (Prioritization) | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | 0.35 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 116000 | FY 2025: 116000
EB-5707 | Bike & Ped | STI (Prioritization) | STONEY CREEK GREENWAY | US 70 BYPASS TO SR 1560 (ROYALL AVENUE). CONSTRUCT 10 FOOT WIDE ASPHALT GREENWAY. | 0.39 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | L | CONSTRUCTION | 23000
EB-5707 | Bike & Ped | STI (Prioritization) | STONEY CREEK GREENWAY | US 70 BYPASS TO SR 1560 (ROYALL AVENUE). CONSTRUCT 10 FOOT WIDE ASPHALT GREENWAY. | 0.39 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | SRTS | CONSTRUCTION | 368000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 0.57 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | RIGHT-OF-WAY | 142000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 0.57 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 35000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 0.57 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | TAANY | CONSTRUCTION | 196000 | FY 2025: 196000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 0.57 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 19000 | FY 2025: 19000
EB-5708 | Bike & Ped | STI (Prioritization) | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | 0.57 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | SRTS | CONSTRUCTION | 215000 | FY 2025: 215000
EB-5711 | Bike & Ped | STI (Prioritization) | US 64 BUSINESS (SUNSET AVENUE) | SR 1836 (MAY DRIVE) TO US 301 BUSINESS, NORTH BOUND (CHURCH STREET). INSTALL PEDESTRIAN SIGNALS. | 1.7 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 464000
EB-5711 | Bike & Ped | STI (Prioritization) | US 64 BUSINESS (SUNSET AVENUE) | SR 1836 (MAY DRIVE) TO US 301 BUSINESS, NORTH BOUND (CHURCH STREET). INSTALL PEDESTRIAN SIGNALS. | 1.7 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 116000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 2.42 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  | TAANY | RIGHT-OF-WAY | 237000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 2.42 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  | L | RIGHT-OF-WAY | 59000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 2.42 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  | TAANY | CONSTRUCTION | 2144000 | FY 2025: 2144000
EB-5715 | Bike & Ped | STI (Prioritization) | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | 2.42 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM | Division 5 |  | L | CONSTRUCTION | 536000 | FY 2025: 536000
EB-5716 | Bike & Ped | STI (Prioritization) | HOLDEN ROAD; EAST LINDSAY STREET | HOLDEN ROAD, SOUTH OF MEADOWVIEW ROAD TO SPRING GARDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK ON WEST SIDE. EAST LINDSAY STREET, MURROW BOULEVARD TO BESSEMER AVENUE IN GREENSBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.89 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 0.06 | WAKE | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | TAANY | RIGHT-OF-WAY | 4880000 | FY 2028: 4880000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 0.06 | WAKE | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | L(M) | RIGHT-OF-WAY | 1220000 | FY 2028: 1220000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 0.06 | WAKE | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | TAANY | UTILITIES | 248000 | FY 2028: 248000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 0.06 | WAKE | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | L(M) | UTILITIES | 62000 | FY 2028: 62000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 0.06 | WAKE | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | TAANY | CONSTRUCTION | 4480000 | FY 2029: 2851000; FY 2030: 1629000
EB-5718 | Bike & Ped | STI (Prioritization) | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | 0.06 | WAKE | 5 | Capital Area MPO | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166 | Division 5 |  | L(M) | CONSTRUCTION | 1120000 | FY 2029: 713000; FY 2030: 407000
EB-5720 | Bike & Ped | STI (Prioritization) | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 1.11 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | Division 5 |  | TAANY | RIGHT-OF-WAY | 1440000 | FY 2025: 1440000
EB-5720 | Bike & Ped | STI (Prioritization) | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 1.11 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | Division 5 |  | L(M) | RIGHT-OF-WAY | 360000 | FY 2025: 360000
EB-5720 | Bike & Ped | STI (Prioritization) | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 1.11 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | Division 5 |  | HP | CONSTRUCTION | 2320000 | FY 2026: 2320000
EB-5720 | Bike & Ped | STI (Prioritization) | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 1.11 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | Division 5 |  | TAANY | CONSTRUCTION | 1360000 | FY 2026: 1360000
EB-5720 | Bike & Ped | STI (Prioritization) | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 1.11 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | Division 5 |  | L(M) | CONSTRUCTION | 580000 | FY 2026: 580000
EB-5720 | Bike & Ped | STI (Prioritization) | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | 1.11 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720. HP REPRESENTS FUNDS FROM 2023 FEDERAL APPROPRIATIONS ACT. | Division 5 |  | L(M) | CONSTRUCTION | 340000 | FY 2026: 340000
EB-5721 | Bike & Ped | STI (Prioritization) | ORANGE COUNTY BICYCLE ROUTE 1 | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | 0.67 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 747000 | FY 2025: 747000
EB-5721 | Bike & Ped | STI (Prioritization) | ORANGE COUNTY BICYCLE ROUTE 1 | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | 0.67 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TADA | CONSTRUCTION | 1413000 | FY 2025: 1413000
EB-5721 | Bike & Ped | STI (Prioritization) | ORANGE COUNTY BICYCLE ROUTE 1 | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | 0.67 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 187000 | FY 2025: 187000
EB-5721 | Bike & Ped | STI (Prioritization) | ORANGE COUNTY BICYCLE ROUTE 1 | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | 0.67 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 353000 | FY 2025: 353000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | TADA | ENGINEERING | 32000 | FY 2025: 32000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | ENGINEERING | 8000 | FY 2025: 8000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 728000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | TADA | RIGHT-OF-WAY | 344000 | FY 2025: 344000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 86000 | FY 2025: 86000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 182000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 3424000 | FY 2025: 3424000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 1252000 | FY 2025: 1252000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | TAANY | CONSTRUCTION | 1978000 | FY 2025: 1978000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 856000 | FY 2025: 856000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 314000 | FY 2025: 314000
EB-5722 | Bike & Ped | STI (Prioritization) | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | 2.28 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 494000 | FY 2025: 494000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 0.6 | UNION | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | TAANY | RIGHT-OF-WAY | 100000 | FY 2025: 100000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 0.6 | UNION | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | RIGHT-OF-WAY | 25000 | FY 2025: 25000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 0.6 | UNION | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 2042000 | FY 2026: 2042000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 0.6 | UNION | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | TAANY | CONSTRUCTION | 868000 | FY 2026: 868000
EB-5723 | Bike & Ped | STI (Prioritization) | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | 0.6 | UNION | 10 | Charlotte Regional TPO | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L(M) | CONSTRUCTION | 1020000 | FY 2026: 1020000
EB-5732 | Bike & Ped | STI (Prioritization) | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 1.71 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TAANY | RIGHT-OF-WAY | 2200000 | FY 2029: 2200000
EB-5732 | Bike & Ped | STI (Prioritization) | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 1.71 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L | RIGHT-OF-WAY | 547000 | FY 2029: 547000
EB-5732 | Bike & Ped | STI (Prioritization) | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 1.71 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | TAANY | CONSTRUCTION | 8400000 | FY 2031: 1512000; FY 2032: 4788000; FY 2033: 2100000
EB-5732 | Bike & Ped | STI (Prioritization) | BRUTON SMITH BOULEVARD/ CONCORD MILLS BOULEVARD/ P | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | 1.71 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L | CONSTRUCTION | 2100000 | FY 2031: 378000; FY 2032: 1197000; FY 2033: 525000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (EAST RALEIGH STREET) | 6TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 1.1 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 164000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (EAST RALEIGH STREET) | 6TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 1.1 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 41000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (EAST RALEIGH STREET) | 6TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 1.1 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | UTILITIES | 114000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (EAST RALEIGH STREET) | 6TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 1.1 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | L | UTILITIES | 29000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (EAST RALEIGH STREET) | 6TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 1.1 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1200000 | FY 2025: 1200000
EB-5734 | Bike & Ped | STI (Prioritization) | SR 2103 (EAST RALEIGH STREET) | 6TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 1.1 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | L | CONSTRUCTION | 300000 | FY 2025: 300000
EB-5741 | Bike & Ped | STI (Prioritization) | US 1 / US 15 / US 501 (SANDHILLS BOULEVARD) | MAPLE AVENUE IN ABERDEEN. CONSTRUCT MID-BLOCK CROSSWALK, MEDIAN REFUGE ISLAND, AND INSTALL PEDESTRIAN SIGNAL. | 0.26 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | CONSTRUCTION | 250000
EB-5741 | Bike & Ped | STI (Prioritization) | US 1 / US 15 / US 501 (SANDHILLS BOULEVARD) | MAPLE AVENUE IN ABERDEEN. CONSTRUCT MID-BLOCK CROSSWALK, MEDIAN REFUGE ISLAND, AND INSTALL PEDESTRIAN SIGNAL. | 0.26 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | L | CONSTRUCTION | 62000
EB-5742 | Bike & Ped | STI (Prioritization) | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 0.42 | LEE | 8 | Central Pines RPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | Division 8 |  | TA5T50 | ENGINEERING | 62000
EB-5742 | Bike & Ped | STI (Prioritization) | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 0.42 | LEE | 8 | Central Pines RPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | Division 8 |  | L | ENGINEERING | 15000
EB-5742 | Bike & Ped | STI (Prioritization) | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 0.42 | LEE | 8 | Central Pines RPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | Division 8 |  | TA5T50 | CONSTRUCTION | 809000 | FY 2026: 809000
EB-5742 | Bike & Ped | STI (Prioritization) | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTI-USE PATH. | 0.42 | LEE | 8 | Central Pines RPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS | Division 8 |  | L | CONSTRUCTION | 202000 | FY 2026: 202000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 1.12 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 257000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 1.12 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 64000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 1.12 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 1028000 | FY 2025: 1028000
EB-5743 | Bike & Ped | STI (Prioritization) | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | 1.12 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 257000 | FY 2025: 257000
EB-5744 | Bike & Ped | STI (Prioritization) | SR 1950 (WEST ACADEMY STREET) | SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN. CONSTRUCT SIDEWALK ON NORTH SIDE. | 1.04 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 640000 | FY 2026: 640000
EB-5744 | Bike & Ped | STI (Prioritization) | SR 1950 (WEST ACADEMY STREET) | SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN. CONSTRUCT SIDEWALK ON NORTH SIDE. | 1.04 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | L | CONSTRUCTION | 160000 | FY 2026: 160000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 1.11 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 246000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 1.11 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 62000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 1.11 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 720000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 1.11 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | RIGHT-OF-WAY | 180000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 1.11 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 2000000 | FY 2025: 1485000; FY 2026: 515000
EB-5745 | Bike & Ped | STI (Prioritization) | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | 1.11 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 500000 | FY 2025: 465000; FY 2026: 35000
EB-5748 | Bike & Ped | STI (Prioritization) | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.36 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 81000
EB-5748 | Bike & Ped | STI (Prioritization) | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.36 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 20000
EB-5748 | Bike & Ped | STI (Prioritization) | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.36 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 640000 | FY 2027: 640000
EB-5748 | Bike & Ped | STI (Prioritization) | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | 0.36 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 160000 | FY 2027: 160000
EB-5750 | Bike & Ped | STI (Prioritization) | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 1.2 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | TAANY | CONSTRUCTION | 7680000
EB-5750 | Bike & Ped | STI (Prioritization) | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 1.2 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | TAANY | CONSTRUCTION | 3600000
EB-5750 | Bike & Ped | STI (Prioritization) | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 1.2 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | L | CONSTRUCTION | 1920000
EB-5750 | Bike & Ped | STI (Prioritization) | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | 1.2 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | L | CONSTRUCTION | 900000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (EAST COURT STREET). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 0.56 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | TAANY | ENGINEERING | 152000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (EAST COURT STREET). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 0.56 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | L | ENGINEERING | 38000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (EAST COURT STREET). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 0.56 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | RIGHT-OF-WAY | 80000 | FY 2026: 80000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (EAST COURT STREET). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 0.56 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | L | RIGHT-OF-WAY | 20000 | FY 2026: 20000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (EAST COURT STREET). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 0.56 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | TA5T50 | CONSTRUCTION | 118000 | FY 2027: 118000
EB-5753 | Bike & Ped | STI (Prioritization) | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (EAST COURT STREET). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | 0.56 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | L | CONSTRUCTION | 29000 | FY 2027: 29000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 0.63 | MACON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | TAANY | ENGINEERING | 14000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 0.63 | MACON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | L | ENGINEERING | 4000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 0.63 | MACON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | TAANY | CONSTRUCTION | 235000
EB-5756 | Bike & Ped | STI (Prioritization) | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | 0.63 | MACON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | L | CONSTRUCTION | 59000
EB-5761 | Bike & Ped | STI (Prioritization) | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 1.69 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA5200 | ENGINEERING | 160000
EB-5761 | Bike & Ped | STI (Prioritization) | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 1.69 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L | ENGINEERING | 40000
EB-5761 | Bike & Ped | STI (Prioritization) | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 1.69 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L | RIGHT-OF-WAY | 1600000 | FY 2025: 1600000
EB-5761 | Bike & Ped | STI (Prioritization) | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 1.69 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 4800000 | FY 2026: 4800000
EB-5761 | Bike & Ped | STI (Prioritization) | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | 1.69 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L | CONSTRUCTION | 1200000 | FY 2026: 1200000
EB-5763 | Bike & Ped | STI (Prioritization) | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 2.43 | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | ENGINEERING | 160000
EB-5763 | Bike & Ped | STI (Prioritization) | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 2.43 | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | ENGINEERING | 40000
EB-5763 | Bike & Ped | STI (Prioritization) | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 2.43 | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | RIGHT-OF-WAY | 240000 | FY 2025: 240000
EB-5763 | Bike & Ped | STI (Prioritization) | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 2.43 | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | RIGHT-OF-WAY | 60000 | FY 2025: 60000
EB-5763 | Bike & Ped | STI (Prioritization) | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 2.43 | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 1200000 | FY 2026: 1200000
EB-5763 | Bike & Ped | STI (Prioritization) | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | 2.43 | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 300000 | FY 2026: 300000
EB-5768 | Bike & Ped | STI (Prioritization) | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 280000
EB-5768 | Bike & Ped | STI (Prioritization) | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 70000
EB-5768 | Bike & Ped | STI (Prioritization) | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 960000 | FY 2026: 960000
EB-5768 | Bike & Ped | STI (Prioritization) | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | RIGHT-OF-WAY | 240000 | FY 2026: 240000
EB-5768 | Bike & Ped | STI (Prioritization) | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | UTILITIES | 640000 | FY 2026: 640000
EB-5768 | Bike & Ped | STI (Prioritization) | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | UTILITIES | 160000 | FY 2026: 160000
EB-5768 | Bike & Ped | STI (Prioritization) | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 800000 | FY 2026: 800000
EB-5768 | Bike & Ped | STI (Prioritization) | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 200000 | FY 2026: 200000
EB-5774 | Bike & Ped | Locally Selected | NC 251 (RIVERSIDE DRIVE) MULTI-USE PATH | US 19/23/70 (EXIT 25) TO US 25. CONSTRUCT MULTI-USE PATH VIA BEAVERDAM CREEK. |  | BUNCOMBE | 13 | French Broad River MPO | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION | Division 13 |  | BGDA | ENGINEERING | 1600000
EB-5774 | Bike & Ped | Locally Selected | NC 251 (RIVERSIDE DRIVE) MULTI-USE PATH | US 19/23/70 (EXIT 25) TO US 25. CONSTRUCT MULTI-USE PATH VIA BEAVERDAM CREEK. |  | BUNCOMBE | 13 | French Broad River MPO | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION | Division 13 |  | L | ENGINEERING | 400000
EB-5774A | Bike & Ped | Locally Selected | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | TADA | RIGHT-OF-WAY | 3406000 | FY 2025: 3406000
EB-5774A | Bike & Ped | Locally Selected | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | RIGHT-OF-WAY | 853000 | FY 2025: 853000
EB-5774A | Bike & Ped | Locally Selected | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 4808000 | FY 2026: 4808000
EB-5774A | Bike & Ped | Locally Selected | NC 251 (RIVERSIDE DRIVE) WOODFIN GREENWAY | US 19/23/70 (EXIT 25) TO THE MILLS AT RIVERSIDE. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 1202000 | FY 2026: 1202000
EB-5774B | Bike & Ped | Locally Selected | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | RIGHT-OF-WAY | 176000 | FY 2025: 176000
EB-5774B | Bike & Ped | Locally Selected | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | TADA | RIGHT-OF-WAY | 310000 | FY 2025: 310000
EB-5774B | Bike & Ped | Locally Selected | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | RIGHT-OF-WAY | 44000 | FY 2025: 44000
EB-5774B | Bike & Ped | Locally Selected | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | RIGHT-OF-WAY | 78000 | FY 2025: 78000
EB-5774B | Bike & Ped | Locally Selected | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGANY | CONSTRUCTION | 2000000 | FY 2026: 20000; FY 2027: 1518000; FY 2028: 462000
EB-5774B | Bike & Ped | Locally Selected | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 760000 | FY 2026: 760000
EB-5774B | Bike & Ped | Locally Selected | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 500000 | FY 2026: 500000
EB-5774B | Bike & Ped | Locally Selected | BEAVERDAM CREEK GREENWAY | THE MILLS AT RIVERSIDE TO US 25. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 190000 | FY 2026: 190000
EB-5777 | Bike & Ped | Locally Selected | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY, SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY CONSTRUCT GREENWAY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | RIGHT-OF-WAY | 768000
EB-5777 | Bike & Ped | Locally Selected | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY, SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY CONSTRUCT GREENWAY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 192000
EB-5777 | Bike & Ped | Locally Selected | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY, SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY CONSTRUCT GREENWAY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 1632000 | FY 2026: 1632000
EB-5777 | Bike & Ped | Locally Selected | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY, SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY CONSTRUCT GREENWAY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 408000 | FY 2026: 408000
EB-5781 | Bike & Ped | STI (Prioritization) | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | CMAQ | CONSTRUCTION | 2116000
EB-5781 | Bike & Ped | STI (Prioritization) | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | BGDA | CONSTRUCTION | 411000
EB-5781 | Bike & Ped | STI (Prioritization) | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 529000
EB-5781 | Bike & Ped | STI (Prioritization) | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 103000
EB-5782 | Bike & Ped | STI (Prioritization) | GREENWAY MCALPINE CREEK | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | 1.65 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 3926000
EB-5782 | Bike & Ped | STI (Prioritization) | GREENWAY MCALPINE CREEK | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | 1.65 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | CONSTRUCTION | 1848000
EB-5782 | Bike & Ped | STI (Prioritization) | GREENWAY MCALPINE CREEK | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | 1.65 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 1444000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGDA | ENGINEERING | 120000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGDA | ENGINEERING | 185000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L | ENGINEERING | 46000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L | ENGINEERING | 30000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGANY | RIGHT-OF-WAY | 30000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGDA | RIGHT-OF-WAY | 238000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L | RIGHT-OF-WAY | 67000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | BGDA | CONSTRUCTION | 1221000 | FY 2025: 1221000
EB-5783 | Bike & Ped | Locally Selected | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 305000 | FY 2025: 305000
EB-5785 | Bike & Ped | Locally Selected | HUNTERSVILLE | UPPER MCDOWELL CREEK GREENWAY, CHILGROVE LANE TO NC 73. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | CMAQ | CONSTRUCTION | 4271000 | FY 2025: 4271000
EB-5785 | Bike & Ped | Locally Selected | HUNTERSVILLE | UPPER MCDOWELL CREEK GREENWAY, CHILGROVE LANE TO NC 73. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $4.271 M IN STBG-DA SWITCHED WITH $4.271M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | CONSTRUCTION | 1068000 | FY 2025: 1068000
EB-5787 | Bike & Ped | Locally Selected | MOORESVILLE | BELLINGHAM PARK GREENWAY EXTENSION TO JOHNSON DAIRY ROAD. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | TADA | CONSTRUCTION | 3555000
EB-5787 | Bike & Ped | Locally Selected | MOORESVILLE | BELLINGHAM PARK GREENWAY EXTENSION TO JOHNSON DAIRY ROAD. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | L | CONSTRUCTION | 889000
EB-5788 | Bike & Ped | Locally Selected | STATESVILLE | SHELTON AVENUE MULTI-USE PATH, GARNER BAGNAL BOULEVARD TO AMITY HILL ROAD. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 12 |  | BGDA | RIGHT-OF-WAY | 201000
EB-5788 | Bike & Ped | Locally Selected | STATESVILLE | SHELTON AVENUE MULTI-USE PATH, GARNER BAGNAL BOULEVARD TO AMITY HILL ROAD. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Division 12 |  | L | RIGHT-OF-WAY | 50000
EB-5790 | Bike & Ped | Locally Selected | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. |  | BUNCOMBE | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | BGDA | CONSTRUCTION | 182000
EB-5790 | Bike & Ped | Locally Selected | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. |  | BUNCOMBE | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | CONSTRUCTION | 772000
EB-5790 | Bike & Ped | Locally Selected | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. |  | BUNCOMBE | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | CONSTRUCTION | 357000
EB-5790 | Bike & Ped | Locally Selected | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. |  | BUNCOMBE | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L | CONSTRUCTION | 193000
EB-5790 | Bike & Ped | Locally Selected | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. |  | BUNCOMBE | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L | CONSTRUCTION | 46000
EB-5790 | Bike & Ped | Locally Selected | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. |  | BUNCOMBE | 13 | French Broad River MPO | PROJECT INCLUDES WORK AND TAANY FUNDING THAT WAS PREVIOUSLY INCLUDED UNDER EB-5919. $772K OF STBG-DA FUNDS SWAPPED FOR $772K IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L | CONSTRUCTION | 89000
EB-5798 | Bike & Ped | Locally Selected | US 221 | MAIN STREET IN BLOWING ROCK TO MOSES H CONE MEMORIAL PARK AND BASS LAKE. CONSTRUCT SIDEWALK. | 0.6 | WATAUGA | 11 | High Country RPO | UNDER CONSTRUCTION. PROJECT TO BE ADMINISTERED BY THE TOWN OF BLOWING ROCK | Exempt
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | TADA | RIGHT-OF-WAY | 96000
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | L | RIGHT-OF-WAY | 24000
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | BGANY | CONSTRUCTION | 414000
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | BGDA | CONSTRUCTION | 1640000
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | BGDA | CONSTRUCTION | 261000
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | TADA | CONSTRUCTION | 125000
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | L | CONSTRUCTION | 410000
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | L | CONSTRUCTION | 169000
EB-5806 | Bike & Ped | Locally Selected | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. |  | CALDWELL | 11 | Greater Hickory MPO | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22. UNDER CONSTRUCTION. | Division 11 |  | L | CONSTRUCTION | 31000
EB-5807 | Bike & Ped | Locally Selected | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. |  | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 13 |  | BGANY | CONSTRUCTION | 1000000
EB-5807 | Bike & Ped | Locally Selected | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. |  | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 13 |  | BGDA | CONSTRUCTION | 295000
EB-5807 | Bike & Ped | Locally Selected | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. |  | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 13 |  | L | CONSTRUCTION | 250000
EB-5807 | Bike & Ped | Locally Selected | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. |  | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Division 13 |  | L | CONSTRUCTION | 74000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | ENGINEERING | 8000 | FY 2025: 8000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | ENGINEERING | 2000 | FY 2025: 2000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | RIGHT-OF-WAY | 4000 | FY 2025: 4000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 1000 | FY 2025: 1000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 5000 | FY 2025: 5000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 356000 | FY 2025: 356000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | TAANY | CONSTRUCTION | 176000 | FY 2025: 176000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 44000 | FY 2025: 44000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 89000 | FY 2025: 89000
EB-5810 | Bike & Ped | STI (Prioritization) | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.96 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 1000 | FY 2025: 1000
EB-5812 | Bike & Ped | STI (Prioritization) | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.04 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | ENGINEERING | 120000
EB-5812 | Bike & Ped | STI (Prioritization) | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.04 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 30000
EB-5812 | Bike & Ped | STI (Prioritization) | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.04 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | CONSTRUCTION | 8320000 | FY 2026: 8320000
EB-5812 | Bike & Ped | STI (Prioritization) | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | 1.04 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 2080000 | FY 2026: 2080000
EB-5817 | Bike & Ped | Locally Selected | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. | Division 10 |  | BGDA | CONSTRUCTION | 1026000
EB-5817 | Bike & Ped | Locally Selected | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. | Division 10 |  | TADA | CONSTRUCTION | 1400000
EB-5817 | Bike & Ped | Locally Selected | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. | Division 10 |  | L | CONSTRUCTION | 256000
EB-5817 | Bike & Ped | Locally Selected | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. | Division 10 |  | L | CONSTRUCTION | 1200000
EB-5818 | Bike & Ped | Locally Selected | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). |  | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | BGDA | CONSTRUCTION | 1001000 | FY 2025: 1001000
EB-5818 | Bike & Ped | Locally Selected | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). |  | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | TAANY | CONSTRUCTION | 1200000
EB-5818 | Bike & Ped | Locally Selected | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). |  | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L | CONSTRUCTION | 470000
EB-5818 | Bike & Ped | Locally Selected | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). |  | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. $1.2M IN STBG-DA FUNDS SWAPPED FOR $1.2M IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 12 |  | L | CONSTRUCTION | 389000 | FY 2025: 389000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | ENGINEERING | 26000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TADA | ENGINEERING | 180000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | ENGINEERING | 52000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 383000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 106000 | FY 2025: 106000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 392000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TADA | CONSTRUCTION | 26000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 26000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 106000 | FY 2025: 106000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 392000
EB-5819 | Bike & Ped | Locally Selected | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 383000
EB-5820 | Bike & Ped | Locally Selected | CHARLOTTE | CHARLOTTE BICYCLE EXPANSION. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Division 10
EB-5821 | Bike & Ped | Locally Selected | REEMS CREEK GREENWAY | CONSTRUCT MULTI-USE PATH ALONG REEMS CREEK CORRIDOR FROM WESTERN EDGE OF TOWN OF WEAVERVILLE TO KARPEN SOCCER FIELDS |  | BUNCOMBE | 13 | French Broad River MPO | IN PROGRESS | Division 13 |  | BGDA | ENGINEERING | 480000 | FY 2029: 480000
EB-5821 | Bike & Ped | Locally Selected | REEMS CREEK GREENWAY | CONSTRUCT MULTI-USE PATH ALONG REEMS CREEK CORRIDOR FROM WESTERN EDGE OF TOWN OF WEAVERVILLE TO KARPEN SOCCER FIELDS |  | BUNCOMBE | 13 | French Broad River MPO | IN PROGRESS | Division 13 |  | L | ENGINEERING | 120000 | FY 2029: 120000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | ENGINEERING | 240000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | ENGINEERING | 240000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L | ENGINEERING | 60000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L | ENGINEERING | 60000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | RIGHT-OF-WAY | 103000 | FY 2026: 103000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L | RIGHT-OF-WAY | 26000 | FY 2026: 26000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | CONSTRUCTION | 2200000 | FY 2027: 22000; FY 2028: 1497000; FY 2029: 681000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | TAANY | CONSTRUCTION | 1000000 | FY 2027: 10000; FY 2028: 681000; FY 2029: 309000
EB-5822 | Bike & Ped | STI (Prioritization) | GREENWAY WILMA DYKEMAN | NORTHERN TERMINUS NEAR RIVERSIDE DRIVE AND HILL STREET TO PEARSON BRIDGE ROAD. CONSTRUCT MULTI-USE PATH ALONG THE FRENCH BROAD RIVER. | 1.48 | BUNCOMBE | 13 | French Broad River MPO | $1M OF STBG-DA FUNDS SWAPPED FOR $1M IN TAP-ANYAREA FUNDS ON 6-9-23. | Division 13 |  | L | CONSTRUCTION | 800000 | FY 2027: 800000
EB-5823 | Bike & Ped | Locally Selected | BENT CREEK GREENWAY | HOMINY CREEK RIVER PARK TO WESTERN NC FARMERS MARKET. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | ENGINEERING | 320000 | FY 2029: 320000
EB-5823 | Bike & Ped | Locally Selected | BENT CREEK GREENWAY | HOMINY CREEK RIVER PARK TO WESTERN NC FARMERS MARKET. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | ENGINEERING | 80000 | FY 2029: 80000
EB-5824 | Bike & Ped | Locally Selected | ENKA HERITAGE TRAIL | WARREN HAYNES DRIVE AND SAND HILL ROAD INTERSECTION TO EAST OF US 19 / US 23 AND SAND HILL ROAD INTERSECTION. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | BGANY | ENGINEERING | 528000
EB-5824 | Bike & Ped | Locally Selected | ENKA HERITAGE TRAIL | WARREN HAYNES DRIVE AND SAND HILL ROAD INTERSECTION TO EAST OF US 19 / US 23 AND SAND HILL ROAD INTERSECTION. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | BGDA | ENGINEERING | 520000
EB-5824 | Bike & Ped | Locally Selected | ENKA HERITAGE TRAIL | WARREN HAYNES DRIVE AND SAND HILL ROAD INTERSECTION TO EAST OF US 19 / US 23 AND SAND HILL ROAD INTERSECTION. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | L(M) | ENGINEERING | 132000
EB-5824 | Bike & Ped | Locally Selected | ENKA HERITAGE TRAIL | WARREN HAYNES DRIVE AND SAND HILL ROAD INTERSECTION TO EAST OF US 19 / US 23 AND SAND HILL ROAD INTERSECTION. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | L(M) | ENGINEERING | 130000
EB-5824 | Bike & Ped | Locally Selected | ENKA HERITAGE TRAIL | WARREN HAYNES DRIVE AND SAND HILL ROAD INTERSECTION TO EAST OF US 19 / US 23 AND SAND HILL ROAD INTERSECTION. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | BGANY | CONSTRUCTION | 2789000 | FY 2026: 1210000; FY 2027: 1579000
EB-5824 | Bike & Ped | Locally Selected | ENKA HERITAGE TRAIL | WARREN HAYNES DRIVE AND SAND HILL ROAD INTERSECTION TO EAST OF US 19 / US 23 AND SAND HILL ROAD INTERSECTION. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | BGDA | CONSTRUCTION | 37000 | FY 2026: 37000
EB-5824 | Bike & Ped | Locally Selected | ENKA HERITAGE TRAIL | WARREN HAYNES DRIVE AND SAND HILL ROAD INTERSECTION TO EAST OF US 19 / US 23 AND SAND HILL ROAD INTERSECTION. CONSTRUCT MULTI-USE PATH. |  | BUNCOMBE | 13 | French Broad River MPO | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE; $163K BGDA USED AS SWAP FOR $163K BGANY PER EXCESS BGANY FROM EB-5547 BOARD APPROVED CHANGES. | Division 13 |  | L(M) | CONSTRUCTION | 1018000 | FY 2026: 1018000
EB-5827 | Bike & Ped | Locally Selected | FONTA FLORA TRAIL | FONTA FLORA STATE TRAIL, INTERSECTION OF LAUREL RIDGE COURT AND NORTH POWERHOUSE ROAD TO THE PROPOSED HARRIS WHISNANT TRAILHEAD AT THE INTERSECTION OF HARRY WHISNANT ROAD AND COBB ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN FACILITY. |  | BURKE | 13 | Greater Hickory MPO | $410K IN STBG-DA FUNDS SWITCHED WITH $410K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 13 |  | BGANY | RIGHT-OF-WAY | 410000
EB-5827 | Bike & Ped | Locally Selected | FONTA FLORA TRAIL | FONTA FLORA STATE TRAIL, INTERSECTION OF LAUREL RIDGE COURT AND NORTH POWERHOUSE ROAD TO THE PROPOSED HARRIS WHISNANT TRAILHEAD AT THE INTERSECTION OF HARRY WHISNANT ROAD AND COBB ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN FACILITY. |  | BURKE | 13 | Greater Hickory MPO | $410K IN STBG-DA FUNDS SWITCHED WITH $410K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 13 |  | L | RIGHT-OF-WAY | 216000
EB-5828 | Bike & Ped | Locally Selected | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. |  | CATAWBA | 12 | Greater Hickory MPO | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGDA | RIGHT-OF-WAY | 25000
EB-5828 | Bike & Ped | Locally Selected | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. |  | CATAWBA | 12 | Greater Hickory MPO | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L | RIGHT-OF-WAY | 6000
EB-5828 | Bike & Ped | Locally Selected | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. |  | CATAWBA | 12 | Greater Hickory MPO | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | CONSTRUCTION | 433000 | FY 2025: 433000
EB-5828 | Bike & Ped | Locally Selected | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. |  | CATAWBA | 12 | Greater Hickory MPO | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L | CONSTRUCTION | 108000 | FY 2025: 108000
EB-5829 | Bike & Ped | Locally Selected | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TADA | CONSTRUCTION | 2174000
EB-5829 | Bike & Ped | Locally Selected | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 725000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | BGDA | ENGINEERING | 420000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | TADA | ENGINEERING | 300000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | L(M) | ENGINEERING | 75000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | L(M) | ENGINEERING | 105000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | BGDA | RIGHT-OF-WAY | 240000 | FY 2025: 240000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | L(M) | RIGHT-OF-WAY | 60000 | FY 2025: 60000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | BGANY | CONSTRUCTION | 7555000 | FY 2026: 76000; FY 2027: 4165000; FY 2028: 2898000; FY 2029: 416000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | BGDA | CONSTRUCTION | 1247000 | FY 2027: 1247000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | L(M) | CONSTRUCTION | 313000 | FY 2027: 313000
EB-5831 | Bike & Ped | Locally Selected | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. |  | BUNCOMBE | 13 | French Broad River MPO | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP. | Division 13 |  | L(M) | CONSTRUCTION | 1888000 | FY 2026: 1888000
EB-5832 | Bike & Ped | STI (Prioritization) | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 0.62 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDA | CONSTRUCTION | 800000
EB-5832 | Bike & Ped | STI (Prioritization) | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 0.62 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | TAANY | CONSTRUCTION | 542000
EB-5832 | Bike & Ped | STI (Prioritization) | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 0.62 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 136000
EB-5832 | Bike & Ped | STI (Prioritization) | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | 0.62 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | L | CONSTRUCTION | 200000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 1.14 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TAANY | RIGHT-OF-WAY | 163000 | FY 2025: 163000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 1.14 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 41000 | FY 2025: 41000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 1.14 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TAANY | CONSTRUCTION | 1128000 | FY 2026: 1128000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 1.14 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CONSTRUCTION | 694000 | FY 2026: 694000
EB-5834 | Bike & Ped | STI (Prioritization) | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | 1.14 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 282000 | FY 2026: 282000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (APEX HIGHWAY) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 1.07 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TAANY | ENGINEERING | 84000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (APEX HIGHWAY) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 1.07 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | ENGINEERING | 21000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (APEX HIGHWAY) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 1.07 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TAANY | RIGHT-OF-WAY | 40000 | FY 2030: 40000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (APEX HIGHWAY) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 1.07 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 10000 | FY 2030: 10000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (APEX HIGHWAY) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 1.07 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TAANY | CONSTRUCTION | 957000 | FY 2031: 957000
EB-5835 | Bike & Ped | STI (Prioritization) | NC 55 (APEX HIGHWAY) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | 1.07 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CONSTRUCTION | 239000 | FY 2031: 239000
EB-5837 | Bike & Ped | STI (Prioritization) | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TAANY | RIGHT-OF-WAY | 770000
EB-5837 | Bike & Ped | STI (Prioritization) | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 193000
EB-5837 | Bike & Ped | STI (Prioritization) | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | TAANY | CONSTRUCTION | 4640000 | FY 2026: 4640000
EB-5837 | Bike & Ped | STI (Prioritization) | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | 1.6 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CONSTRUCTION | 1160000 | FY 2026: 1160000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 2.97 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TAANY | ENGINEERING | 240000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 2.97 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 60000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 2.97 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TAANY | RIGHT-OF-WAY | 200000 | FY 2025: 200000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 2.97 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 50000 | FY 2025: 50000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 2.97 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TAANY | CONSTRUCTION | 1160000 | FY 2025: 1160000
EB-5838 | Bike & Ped | STI (Prioritization) | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | 2.97 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 290000 | FY 2025: 290000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.52 | FORSYTH | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | BGDA | CONSTRUCTION | 477000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.52 | FORSYTH | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | TAANY | CONSTRUCTION | 1600000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.52 | FORSYTH | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | TADA | CONSTRUCTION | 907000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.52 | FORSYTH | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | L | CONSTRUCTION | 346000
EB-5840 | Bike & Ped | STI (Prioritization) | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.52 | FORSYTH | 9 | Winston-Salem Area TPO | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT. UNDER CONSTRUCTION | Division 9 |  | L | CONSTRUCTION | 400000
EB-5841 | Bike & Ped | STI (Prioritization) | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | ENGINEERING | 920000
EB-5841 | Bike & Ped | STI (Prioritization) | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | ENGINEERING | 230000
EB-5841 | Bike & Ped | STI (Prioritization) | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | RIGHT-OF-WAY | 160000 | FY 2029: 160000
EB-5841 | Bike & Ped | STI (Prioritization) | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | RIGHT-OF-WAY | 40000 | FY 2029: 40000
EB-5841 | Bike & Ped | STI (Prioritization) | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | UTILITIES | 352000 | FY 2029: 352000
EB-5841 | Bike & Ped | STI (Prioritization) | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | UTILITIES | 88000 | FY 2029: 88000
EB-5841 | Bike & Ped | STI (Prioritization) | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | CONSTRUCTION | 3680000 | FY 2031: 3680000
EB-5841 | Bike & Ped | STI (Prioritization) | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | 1.64 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | CONSTRUCTION | 920000 | FY 2031: 920000
EB-5844 | Bike & Ped | STI (Prioritization) | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2.02 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | TAANY | RIGHT-OF-WAY | 320000
EB-5844 | Bike & Ped | STI (Prioritization) | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2.02 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L | RIGHT-OF-WAY | 80000
EB-5844 | Bike & Ped | STI (Prioritization) | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2.02 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | CMAQ | CONSTRUCTION | 131000 | FY 2025: 131000
EB-5844 | Bike & Ped | STI (Prioritization) | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2.02 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | TAANY | CONSTRUCTION | 4389000 | FY 2025: 4389000
EB-5844 | Bike & Ped | STI (Prioritization) | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2.02 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L | CONSTRUCTION | 33000 | FY 2025: 33000
EB-5844 | Bike & Ped | STI (Prioritization) | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | 2.02 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Division 10 |  | L | CONSTRUCTION | 947000 | FY 2025: 947000
EB-5845 | Bike & Ped | STI (Prioritization) | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 0.69 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | TA5T50 | ENGINEERING | 154000
EB-5845 | Bike & Ped | STI (Prioritization) | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 0.69 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | L | ENGINEERING | 38000
EB-5845 | Bike & Ped | STI (Prioritization) | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 0.69 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | TA5T50 | RIGHT-OF-WAY | 129000 | FY 2026: 129000
EB-5845 | Bike & Ped | STI (Prioritization) | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 0.69 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | L | RIGHT-OF-WAY | 32000 | FY 2026: 32000
EB-5845 | Bike & Ped | STI (Prioritization) | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 0.69 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | TA5T50 | CONSTRUCTION | 344000 | FY 2027: 344000
EB-5845 | Bike & Ped | STI (Prioritization) | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | 0.69 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | L | CONSTRUCTION | 86000 | FY 2027: 86000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | 3.87 | DARE | 1 | Albemarle RPO |  | Division 1 |  | TA5T50 | ENGINEERING | 80000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | 3.87 | DARE | 1 | Albemarle RPO |  | Division 1 |  | L(M) | ENGINEERING | 20000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | 3.87 | DARE | 1 | Albemarle RPO |  | Division 1 |  | TA5T50 | CONSTRUCTION | 5760000 | FY 2026: 1920000; FY 2027: 3840000
EB-5848 | Bike & Ped | STI (Prioritization) | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | 3.87 | DARE | 1 | Albemarle RPO |  | Division 1 |  | L(M) | CONSTRUCTION | 1440000 | FY 2026: 480000; FY 2027: 960000
EB-5850 | Bike & Ped | STI (Prioritization) | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 0.33 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | TA50200 | ENGINEERING | 15000 | FY 2025: 15000
EB-5850 | Bike & Ped | STI (Prioritization) | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 0.33 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | L | ENGINEERING | 4000 | FY 2025: 4000
EB-5850 | Bike & Ped | STI (Prioritization) | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 0.33 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | TA50200 | UTILITIES | 160000 | FY 2026: 160000
EB-5850 | Bike & Ped | STI (Prioritization) | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 0.33 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | L | UTILITIES | 40000 | FY 2026: 40000
EB-5850 | Bike & Ped | STI (Prioritization) | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 0.33 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 960000 | FY 2026: 960000
EB-5850 | Bike & Ped | STI (Prioritization) | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | 0.33 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | L | CONSTRUCTION | 240000 | FY 2026: 240000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | TALT5 | ENGINEERING | 20000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | TALT5 | ENGINEERING | 76000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | L(M) | ENGINEERING | 19000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | HF(M) | ENGINEERING | 5000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | TALT5 | RIGHT-OF-WAY | 168000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | TALT5 | RIGHT-OF-WAY | 64000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | L(M) | RIGHT-OF-WAY | 16000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | HF(M) | RIGHT-OF-WAY | 42000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | TALT5 | CONSTRUCTION | 212000 | FY 2026: 2000; FY 2027: 210000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | TALT5 | CONSTRUCTION | 476000 | FY 2026: 5000; FY 2027: 471000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | L(M) | CONSTRUCTION | 119000 | FY 2026: 119000
EB-5857 | Bike & Ped | STI (Prioritization) | STANFIELD | NC 200, NORTH LOVE CHAPEL ROAD TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | 0.84 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | HF(M) | CONSTRUCTION | 53000 | FY 2026: 1000; FY 2027: 52000
EB-5858 | Bike & Ped | STI (Prioritization) | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | TA5200 | ENGINEERING | 656000
EB-5858 | Bike & Ped | STI (Prioritization) | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | L | ENGINEERING | 164000
EB-5858 | Bike & Ped | STI (Prioritization) | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | TA5200 | RIGHT-OF-WAY | 16000
EB-5858 | Bike & Ped | STI (Prioritization) | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | L | RIGHT-OF-WAY | 4000
EB-5858 | Bike & Ped | STI (Prioritization) | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | TA5200 | UTILITIES | 112000
EB-5858 | Bike & Ped | STI (Prioritization) | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | L | UTILITIES | 28000
EB-5858 | Bike & Ped | STI (Prioritization) | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | TA5200 | CONSTRUCTION | 960000
EB-5858 | Bike & Ped | STI (Prioritization) | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | 0.04 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | L | CONSTRUCTION | 240000
EB-5859 | Bike & Ped | Locally Selected | HAZELWOOD AVENUE (PLOTT CREEK ROAD) | HAZELWOOD AVENUE (PLOTT CREEK ROAD), RICHLAND CREEK BRIDGE TO WILL HYATT ROAD. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | 0.56 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION | Division 14
EB-5860 | Bike & Ped | STI (Prioritization) | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TAANY | ENGINEERING | 214000
EB-5860 | Bike & Ped | STI (Prioritization) | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | ENGINEERING | 53000
EB-5860 | Bike & Ped | STI (Prioritization) | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TAANY | RIGHT-OF-WAY | 36000 | FY 2026: 36000
EB-5860 | Bike & Ped | STI (Prioritization) | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | RIGHT-OF-WAY | 9000 | FY 2026: 9000
EB-5860 | Bike & Ped | STI (Prioritization) | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TAANY | UTILITIES | 28000 | FY 2026: 28000
EB-5860 | Bike & Ped | STI (Prioritization) | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | UTILITIES | 7000 | FY 2026: 7000
EB-5860 | Bike & Ped | STI (Prioritization) | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TAANY | CONSTRUCTION | 922000 | FY 2030: 922000
EB-5860 | Bike & Ped | STI (Prioritization) | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | 0.78 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | CONSTRUCTION | 231000 | FY 2030: 231000
EB-5861 | Bike & Ped | STI (Prioritization) | THIRD STREET GREENWAY | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 5.77 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TAANY | ENGINEERING | 148000
EB-5861 | Bike & Ped | STI (Prioritization) | THIRD STREET GREENWAY | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 5.77 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | ENGINEERING | 37000
EB-5861 | Bike & Ped | STI (Prioritization) | THIRD STREET GREENWAY | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 5.77 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | TAANY | CONSTRUCTION | 3430000 | FY 2026: 3430000
EB-5861 | Bike & Ped | STI (Prioritization) | THIRD STREET GREENWAY | WEST OF OLD MOCKSVILLE ROAD NEAR GRANTS CREEK AT EXISTING SALISBURY GREENWAY TO FIELDCREST CANNON LANE IN SPENCER. CONSTRUCT GREENWAY AND SIDEWALK. | 5.77 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L(M) | CONSTRUCTION | 857000 | FY 2026: 857000
EB-5862 | Bike & Ped | STI (Prioritization) | INDUSTRIAL PARK AVENUE | RANDOLPH COMMUNITY COLLEGE ENTRANCE TO CONTINUING EDUCATION AND INDUSTRIAL CENTER IN ASHEBORO. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 0.26 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 118000
EB-5862 | Bike & Ped | STI (Prioritization) | INDUSTRIAL PARK AVENUE | RANDOLPH COMMUNITY COLLEGE ENTRANCE TO CONTINUING EDUCATION AND INDUSTRIAL CENTER IN ASHEBORO. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 0.26 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | L | CONSTRUCTION | 29000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 236000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | ENGINEERING | 59000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 120000 | FY 2026: 120000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 30000 | FY 2026: 30000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1175000 | FY 2027: 1175000
EB-5863 | Bike & Ped | STI (Prioritization) | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | 0.85 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | CONSTRUCTION | 294000 | FY 2027: 294000
EB-5864 | Bike & Ped | STI (Prioritization) | KNOLL ROAD | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 1.44 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | ENGINEERING | 152000
EB-5864 | Bike & Ped | STI (Prioritization) | KNOLL ROAD | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 1.44 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | L | ENGINEERING | 38000
EB-5864 | Bike & Ped | STI (Prioritization) | KNOLL ROAD | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 1.44 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | CONSTRUCTION | 2880000 | FY 2025: 2880000
EB-5864 | Bike & Ped | STI (Prioritization) | KNOLL ROAD | NC 2 (MIDLAND ROAD) TO SR 1843 (AIRPORT ROAD). CONSTRUCT MULTI-USE PATH ALONG KNOLL ROAD TO CONNECT WITH EXISTING SOUTHERN PINES GREENWAY ON MIDLAND ROAD. | 1.44 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | L | CONSTRUCTION | 720000 | FY 2025: 720000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 61000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L | ENGINEERING | 15000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 80000 | FY 2025: 80000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 20000 | FY 2025: 20000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | UTILITIES | 72000 | FY 2025: 72000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L | UTILITIES | 18000 | FY 2025: 18000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 744000 | FY 2027: 420000; FY 2028: 324000
EB-5865 | Bike & Ped | STI (Prioritization) | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | 0.96 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L | CONSTRUCTION | 186000 | FY 2027: 186000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 119000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | ENGINEERING | 30000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 85000 | FY 2025: 85000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 17000 | FY 2025: 17000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | UTILITIES | 72000 | FY 2025: 72000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | UTILITIES | 18000 | FY 2025: 18000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 812000 | FY 2026: 812000
EB-5867 | Bike & Ped | STI (Prioritization) | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | 0.99 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | CONSTRUCTION | 203000 | FY 2026: 203000
EB-5868 | Bike & Ped | STI (Prioritization) | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 93000
EB-5868 | Bike & Ped | STI (Prioritization) | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | ENGINEERING | 23000
EB-5868 | Bike & Ped | STI (Prioritization) | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 89000 | FY 2025: 89000
EB-5868 | Bike & Ped | STI (Prioritization) | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 22000 | FY 2025: 22000
EB-5868 | Bike & Ped | STI (Prioritization) | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | UTILITIES | 80000 | FY 2025: 80000
EB-5868 | Bike & Ped | STI (Prioritization) | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | UTILITIES | 20000 | FY 2025: 20000
EB-5868 | Bike & Ped | STI (Prioritization) | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 884000 | FY 2025: 884000
EB-5868 | Bike & Ped | STI (Prioritization) | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | 1.25 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | CONSTRUCTION | 221000 | FY 2025: 221000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 0.39 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | RIGHT-OF-WAY | 24000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 0.39 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | L | RIGHT-OF-WAY | 6000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 0.39 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | TA50200 | CONSTRUCTION | 240000 | FY 2026: 240000
EB-5869 | Bike & Ped | STI (Prioritization) | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | 0.39 | MOORE | 8 | Sandhills MPO |  | Division 8 |  | L | CONSTRUCTION | 60000 | FY 2026: 60000
EB-5872 | Bike & Ped | STI (Prioritization) | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE, AND PROVIDE PEDESTRIAN ACCOMMODATIONS AT US 15 / US 401 / US 501 INTERSECTION AND ACROSS US 74. | 1.2 | SCOTLAND | 8 | Lumber River RPO | PROJECT LENGTH REFLECTS PARTS A ONLY- PART B IS NON-STI PROJECT; EB 5872C PROJECT BREAK DELETED WORK TO BE ACCOMPLISHED UNDER EB-5872A. | Division 8
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE. | 1.27 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 70000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE. | 1.27 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L | ENGINEERING | 17000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE. | 1.27 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 133000 | FY 2026: 133000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE. | 1.27 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 33000 | FY 2026: 33000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE. | 1.27 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 348000 | FY 2028: 185000; FY 2029: 163000
EB-5872A | Bike & Ped | STI (Prioritization) | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE. | 1.27 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L | CONSTRUCTION | 88000 | FY 2028: 88000
EB-5872B | Bike & Ped | Locally Selected | SR 1108 (WEST BOULEVARD) | GLASGOW DRIVE TO EAST OF US 15 / US 401 / US 501 (MCCOLL ROAD) IN LAURINBURG. PROVIDE PEDESTRIAN ACCOMMODATIONS AT US 15 / US 401 / US 501 INTERSECTION AND ACROSS US 74. |  | SCOTLAND | 8 | Lumber River RPO |  | Exempt
EB-5873 | Bike & Ped | STI (Prioritization) | SR 1278 (UNIVERSITY PARKWAY) | SR 1300 (EAST GREEN DRIVE) TO SR 1113 (EAST MARTIN LUTHER KING JUNIOR DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.6 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 288000
EB-5873 | Bike & Ped | STI (Prioritization) | SR 1278 (UNIVERSITY PARKWAY) | SR 1300 (EAST GREEN DRIVE) TO SR 1113 (EAST MARTIN LUTHER KING JUNIOR DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.6 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 72000
EB-5874 | Bike & Ped | STI (Prioritization) | NC 68 (EASTCHESTER DRIVE) | JOHNSON STREET TO SR 1278 (UNIVERSITY PARKWAY) IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.65 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 504000
EB-5874 | Bike & Ped | STI (Prioritization) | NC 68 (EASTCHESTER DRIVE) | JOHNSON STREET TO SR 1278 (UNIVERSITY PARKWAY) IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.65 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 126000
EB-5876 | Bike & Ped | STI (Prioritization) | HOLDEN ROAD | SR 4121 (WEST GATE CITY BOULEVARD) TO NORTH OF SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.56 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION BY CITY OF GREENSBORO | Division 7
EB-5877 | Bike & Ped | STI (Prioritization) | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.97 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | RIGHT-OF-WAY | 20000
EB-5877 | Bike & Ped | STI (Prioritization) | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.97 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 5000
EB-5877 | Bike & Ped | STI (Prioritization) | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.97 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | CONSTRUCTION | 960000 | FY 2025: 960000
EB-5877 | Bike & Ped | STI (Prioritization) | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.97 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 240000 | FY 2025: 240000
EB-5878 | Bike & Ped | STI (Prioritization) | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.47 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | RIGHT-OF-WAY | 40000
EB-5878 | Bike & Ped | STI (Prioritization) | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.47 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | RIGHT-OF-WAY | 10000
EB-5878 | Bike & Ped | STI (Prioritization) | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.47 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | TAANY | CONSTRUCTION | 760000 | FY 2025: 760000
EB-5878 | Bike & Ped | STI (Prioritization) | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | 0.47 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L | CONSTRUCTION | 190000 | FY 2025: 190000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | ENGINEERING | 13000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | ENGINEERING | 3000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 2640000 | FY 2025: 2640000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 660000 | FY 2025: 660000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | UTILITIES | 760000 | FY 2025: 760000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | UTILITIES | 190000 | FY 2025: 190000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 744000 | FY 2025: 744000
EB-5879 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.41 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 186000 | FY 2025: 186000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TAANY | ENGINEERING | 71000 | FY 2025: 71000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | ENGINEERING | 18000 | FY 2025: 18000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 64000 | FY 2026: 64000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 16000 | FY 2026: 16000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TAANY | UTILITIES | 144000 | FY 2026: 144000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | UTILITIES | 36000 | FY 2026: 36000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 552000 | FY 2027: 552000
EB-5880 | Bike & Ped | STI (Prioritization) | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | 0.51 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 138000 | FY 2027: 138000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 2.21 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 237000 | FY 2025: 237000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 2.21 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 59000 | FY 2025: 59000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 2.21 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 2249000 | FY 2025: 2249000
EB-5883 | Bike & Ped | STI (Prioritization) | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | 2.21 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 562000 | FY 2025: 562000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.47 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 24000 | FY 2025: 24000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.47 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 6000 | FY 2025: 6000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.47 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | UTILITIES | 600000 | FY 2025: 600000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.47 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L | UTILITIES | 150000 | FY 2025: 150000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.47 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 552000 | FY 2025: 552000
EB-5885 | Bike & Ped | STI (Prioritization) | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | 0.47 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L | CONSTRUCTION | 138000 | FY 2025: 138000
EB-5886 | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) IN CARRBORO TO NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.7 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | ENGINEERING | 136000 | FY 2025: 136000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | ENGINEERING | 34000 | FY 2025: 34000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | RIGHT-OF-WAY | 6080000 | FY 2026: 6080000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | RIGHT-OF-WAY | 1520000 | FY 2026: 1520000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | UTILITIES | 384000 | FY 2026: 384000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | UTILITIES | 96000 | FY 2026: 96000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | CONSTRUCTION | 678000 | FY 2028: 678000
EB-5886A | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.43 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | CONSTRUCTION | 170000 | FY 2028: 170000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | ENGINEERING | 427000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | ENGINEERING | 107000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | RIGHT-OF-WAY | 691000 | FY 2026: 691000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | RIGHT-OF-WAY | 173000 | FY 2026: 173000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | TAANY | CONSTRUCTION | 2483000 | FY 2027: 1983000; FY 2028: 500000
EB-5886B | Bike & Ped | STI (Prioritization) | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 1.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7. | Division 7 |  | L(M) | CONSTRUCTION | 621000 | FY 2027: 496000; FY 2028: 125000
EB-5888 | Bike & Ped | STI (Prioritization) | SR 1747 (EAST STADIUM DRIVE) | SR 1962 (NORTH PIERCE STREET) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | 0.57 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | TA5T50 | CONSTRUCTION | 1278000 | FY 2025: 14000; FY 2026: 1264000
EB-5888 | Bike & Ped | STI (Prioritization) | SR 1747 (EAST STADIUM DRIVE) | SR 1962 (NORTH PIERCE STREET) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | 0.57 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | L | CONSTRUCTION | 322000 | FY 2025: 184000; FY 2026: 138000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 0.7 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 2000000 | FY 2025: 2000000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 0.7 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 500000 | FY 2025: 500000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 0.7 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | UTILITIES | 1520000 | FY 2025: 1520000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 0.7 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | UTILITIES | 380000 | FY 2025: 380000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 0.7 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 3280000 | FY 2025: 3280000
EB-5889 | Bike & Ped | STI (Prioritization) | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | 0.7 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 820000 | FY 2025: 820000
EB-5890 | Bike & Ped | STI (Prioritization) | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TAANY | ENGINEERING | 37000 | FY 2025: 37000
EB-5890 | Bike & Ped | STI (Prioritization) | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | ENGINEERING | 9000 | FY 2025: 9000
EB-5890 | Bike & Ped | STI (Prioritization) | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 40000 | FY 2026: 40000
EB-5890 | Bike & Ped | STI (Prioritization) | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 10000 | FY 2026: 10000
EB-5890 | Bike & Ped | STI (Prioritization) | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TAANY | UTILITIES | 272000 | FY 2026: 272000
EB-5890 | Bike & Ped | STI (Prioritization) | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | UTILITIES | 68000 | FY 2026: 68000
EB-5890 | Bike & Ped | STI (Prioritization) | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 280000 | FY 2027: 280000
EB-5890 | Bike & Ped | STI (Prioritization) | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | 0.25 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 70000 | FY 2027: 70000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 BUSINESS | EAST JACKSON STREET IN MAYODAN TO MAYO RIVER STATE PARK. CONSTRUCT MULTI-USE PATH. | 1.37 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | TALT5 | CONSTRUCTION | 522000 | FY 2026: 522000
EB-5891 | Bike & Ped | STI (Prioritization) | US 220 BUSINESS | EAST JACKSON STREET IN MAYODAN TO MAYO RIVER STATE PARK. CONSTRUCT MULTI-USE PATH. | 1.37 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | L | CONSTRUCTION | 130000 | FY 2026: 130000
EB-5894 | Bike & Ped | STI (Prioritization) | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 2.74 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | CMAQ | CONSTRUCTION | 985000
EB-5894 | Bike & Ped | STI (Prioritization) | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 2.74 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | TAANY | CONSTRUCTION | 7112000 | FY 2025: 7112000
EB-5894 | Bike & Ped | STI (Prioritization) | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 2.74 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | TAANY | CONSTRUCTION | 4000000
EB-5894 | Bike & Ped | STI (Prioritization) | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 2.74 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 246000
EB-5894 | Bike & Ped | STI (Prioritization) | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 2.74 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 1778000 | FY 2025: 1778000
EB-5894 | Bike & Ped | STI (Prioritization) | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | 2.74 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 1000000
EB-5895 | Bike & Ped | STI (Prioritization) | NC 55 (EAST WILLIAMS STREET) | SR 1301 (SUNSET LAKE ROAD) TO NC 55 IN HOLLY SPRINGS. CONSTRUCT SIDEWALK. | 0.9 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | TAANY | CONSTRUCTION | 400000
EB-5895 | Bike & Ped | STI (Prioritization) | NC 55 (EAST WILLIAMS STREET) | SR 1301 (SUNSET LAKE ROAD) TO NC 55 IN HOLLY SPRINGS. CONSTRUCT SIDEWALK. | 0.9 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 100000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 20000 | FY 2025: 20000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 5000 | FY 2025: 5000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 206000 | FY 2026: 206000
EB-5898 | Bike & Ped | STI (Prioritization) | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | L | CONSTRUCTION | 52000 | FY 2026: 52000
EB-5899 | Bike & Ped | STI (Prioritization) | NC 731 (EAST ALLENTON STREET) | EXISTING SIDEWALK ON NC 731 TO STANBECK PARK IN MT. GILEAD. CONSTRUCT SIDEWALK. | 0.19 | MONTGOMERY | 8 | Piedmont Triad RPO |  | Division 8 |  | TALT5 | CONSTRUCTION | 222000
EB-5899 | Bike & Ped | STI (Prioritization) | NC 731 (EAST ALLENTON STREET) | EXISTING SIDEWALK ON NC 731 TO STANBECK PARK IN MT. GILEAD. CONSTRUCT SIDEWALK. | 0.19 | MONTGOMERY | 8 | Piedmont Triad RPO |  | Division 8 |  | L | CONSTRUCTION | 55000
EB-5900 | Bike & Ped | STI (Prioritization) | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 2.58 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 312000 | FY 2025: 312000
EB-5900 | Bike & Ped | STI (Prioritization) | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 2.58 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 78000 | FY 2025: 78000
EB-5900 | Bike & Ped | STI (Prioritization) | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 2.58 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 3120000 | FY 2025: 3120000
EB-5900 | Bike & Ped | STI (Prioritization) | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTI-USE PATH. | 2.58 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 780000 | FY 2025: 780000
EB-5903 | Bike & Ped | Locally Selected | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. | Division 10 |  | CMAQ | CONSTRUCTION | 373000
EB-5903 | Bike & Ped | Locally Selected | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. | Division 10 |  | TADA | CONSTRUCTION | 320000
EB-5903 | Bike & Ped | Locally Selected | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. | Division 10 |  | L | CONSTRUCTION | 80000
EB-5903 | Bike & Ped | Locally Selected | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. | Division 10 |  | L | CONSTRUCTION | 93000
EB-5904 | Bike & Ped | STI (Prioritization) | DURHAM RAIL TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 1.75 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | DP | CONSTRUCTION | 9000000 | FY 2025: 9000000
EB-5904 | Bike & Ped | STI (Prioritization) | DURHAM RAIL TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 1.75 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | BGDA | CONSTRUCTION | 1863000 | FY 2025: 1863000
EB-5904 | Bike & Ped | STI (Prioritization) | DURHAM RAIL TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 1.75 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | TAANY | CONSTRUCTION | 120000 | FY 2025: 120000
EB-5904 | Bike & Ped | STI (Prioritization) | DURHAM RAIL TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 1.75 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | TADA | CONSTRUCTION | 410000 | FY 2025: 410000
EB-5904 | Bike & Ped | STI (Prioritization) | DURHAM RAIL TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | 1.75 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT | Division 5 |  | L | CONSTRUCTION | 6016000 | FY 2025: 6016000
EB-5905 | Bike & Ped | STI (Prioritization) | US 64 BUSINESS (THOMAS STREET) | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. |  | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | BG50200 | CONSTRUCTION | 1120000 | FY 2027: 1120000
EB-5905 | Bike & Ped | STI (Prioritization) | US 64 BUSINESS (THOMAS STREET) | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. |  | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L(M) | CONSTRUCTION | 280000 | FY 2027: 280000
EB-5907 | Bike & Ped | STI (Prioritization) | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | ENGINEERING | 67000
EB-5907 | Bike & Ped | STI (Prioritization) | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | ENGINEERING | 17000
EB-5907 | Bike & Ped | STI (Prioritization) | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | RIGHT-OF-WAY | 504000 | FY 2026: 504000
EB-5907 | Bike & Ped | STI (Prioritization) | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | RIGHT-OF-WAY | 126000 | FY 2026: 126000
EB-5907 | Bike & Ped | STI (Prioritization) | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TAANY | CONSTRUCTION | 640000 | FY 2028: 640000
EB-5907 | Bike & Ped | STI (Prioritization) | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | 0.94 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | CONSTRUCTION | 160000 | FY 2028: 160000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TAANY | ENGINEERING | 114000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TADA | ENGINEERING | 1082000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | L | ENGINEERING | 299000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | CRPDA | RIGHT-OF-WAY | 960000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TAANY | RIGHT-OF-WAY | 504000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | L | RIGHT-OF-WAY | 240000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | L | RIGHT-OF-WAY | 126000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TADA | CONSTRUCTION | 1132000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TAANY | CONSTRUCTION | 7000000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | TAANY | CONSTRUCTION | 4688000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | L | CONSTRUCTION | 1455000
EB-5911 | Bike & Ped | STI (Prioritization) | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | 1.76 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP. | Division 12 |  | L | CONSTRUCTION | 1750000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TAANY | ENGINEERING | 349000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 87000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | RIGHT-OF-WAY | 2000000 | FY 2025: 2000000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | RIGHT-OF-WAY | 500000 | FY 2025: 500000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | UTILITIES | 344000 | FY 2025: 344000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | UTILITIES | 86000 | FY 2025: 86000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 3600000 | FY 2027: 3600000
EB-5912 | Bike & Ped | STI (Prioritization) | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | 0.48 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 900000 | FY 2027: 900000
EB-5913 | Bike & Ped | STI (Prioritization) | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 0.14 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 131000
EB-5913 | Bike & Ped | STI (Prioritization) | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 0.14 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 33000
EB-5913 | Bike & Ped | STI (Prioritization) | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 0.14 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 283000 | FY 2025: 283000
EB-5913 | Bike & Ped | STI (Prioritization) | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | 0.14 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 71000 | FY 2025: 71000
EB-5915 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | 6.18 | RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. | Division 13 |  | TAANY | CONSTRUCTION | 364000
EB-5915 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | 6.18 | RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. | Division 13 |  | TAANY | CONSTRUCTION | 57000
EB-5915 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | 6.18 | RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. | Division 13 |  | L(M) | CONSTRUCTION | 91000
EB-5915 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | 6.18 | RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. | Division 13 |  | HF(M) | CONSTRUCTION | 14000
EB-5916 | Bike & Ped | STI (Prioritization) | FONTA FLORA TRAIL | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | TA5200 | ENGINEERING | 160000
EB-5916 | Bike & Ped | STI (Prioritization) | FONTA FLORA TRAIL | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | TA5200 | ENGINEERING | 288000
EB-5916 | Bike & Ped | STI (Prioritization) | FONTA FLORA TRAIL | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | L | ENGINEERING | 72000
EB-5916 | Bike & Ped | STI (Prioritization) | FONTA FLORA TRAIL | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | L | ENGINEERING | 40000
EB-5916 | Bike & Ped | STI (Prioritization) | FONTA FLORA TRAIL | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | TAANY | RIGHT-OF-WAY | 60000 | FY 2025: 60000
EB-5916 | Bike & Ped | STI (Prioritization) | FONTA FLORA TRAIL | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | L | RIGHT-OF-WAY | 15000 | FY 2025: 15000
EB-5916 | Bike & Ped | STI (Prioritization) | FONTA FLORA TRAIL | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | TAANY | CONSTRUCTION | 2450000 | FY 2025: 2450000
EB-5916 | Bike & Ped | STI (Prioritization) | FONTA FLORA TRAIL | SR 1221 (RESISTOFLEX ROAD) TO SR 1197 (ROBY CONLEY ROAD) ALONG THE CATAWBA RIVER. CONSTRUCT GREENWAY. | 1.57 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | L | CONSTRUCTION | 613000 | FY 2025: 613000
EB-5918 | Bike & Ped | STI (Prioritization) | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL, AND PEDESTRIAN REFUGE. | 0.14 | MADISON | 13 | Land-of-Sky RPO |  | Division 13 |  | TALT5 | ENGINEERING | 36000
EB-5918 | Bike & Ped | STI (Prioritization) | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL, AND PEDESTRIAN REFUGE. | 0.14 | MADISON | 13 | Land-of-Sky RPO |  | Division 13 |  | L(M) | ENGINEERING | 9000
EB-5918 | Bike & Ped | STI (Prioritization) | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL, AND PEDESTRIAN REFUGE. | 0.14 | MADISON | 13 | Land-of-Sky RPO |  | Division 13 |  | TALT5 | CONSTRUCTION | 120000 | FY 2026: 120000
EB-5918 | Bike & Ped | STI (Prioritization) | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL, AND PEDESTRIAN REFUGE. | 0.14 | MADISON | 13 | Land-of-Sky RPO |  | Division 13 |  | L(M) | CONSTRUCTION | 30000 | FY 2026: 30000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | ENGINEERING | 160000 | FY 2025: 160000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 40000 | FY 2025: 40000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | RIGHT-OF-WAY | 160000 | FY 2025: 160000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 40000 | FY 2025: 40000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | UTILITIES | 640000 | FY 2025: 640000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | UTILITIES | 160000 | FY 2025: 160000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | CONSTRUCTION | 720000 | FY 2026: 720000
EB-5920 | Bike & Ped | STI (Prioritization) | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | 0.64 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 180000 | FY 2026: 180000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 0.92 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | TAANY | ENGINEERING | 360000 | FY 2026: 360000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 0.92 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | L | ENGINEERING | 90000 | FY 2026: 90000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 0.92 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | TAANY | RIGHT-OF-WAY | 1280000 | FY 2030: 1280000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 0.92 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | L | RIGHT-OF-WAY | 320000 | FY 2030: 320000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 0.92 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | TAANY | CONSTRUCTION | 2080000 | FY 2033: 2080000
EB-5921 | Bike & Ped | STI (Prioritization) | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | 0.92 | ROWAN | 9 | Cabarrus-Rowan MPO | COORDINATE WITH U-6062 | Division 9 |  | L | CONSTRUCTION | 520000 | FY 2033: 520000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.41 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 104000 | FY 2025: 104000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.41 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 26000 | FY 2025: 26000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.41 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | UTILITIES | 368000 | FY 2025: 368000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.41 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | UTILITIES | 92000 | FY 2025: 92000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.41 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 432000 | FY 2025: 432000
EB-5922 | Bike & Ped | STI (Prioritization) | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | 0.41 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 108000 | FY 2025: 108000
EB-5923 | Bike & Ped | STI (Prioritization) | SR 1432 (SKYLAND DRIVE) | SR 1429 (CHIPPER CURVE ROAD) TO US 23 BUSINESS. CONSTRUCT SIDEWALK. | 0.72 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | TALT5 | CONSTRUCTION | 768000
EB-5923 | Bike & Ped | STI (Prioritization) | SR 1432 (SKYLAND DRIVE) | SR 1429 (CHIPPER CURVE ROAD) TO US 23 BUSINESS. CONSTRUCT SIDEWALK. | 0.72 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | L | CONSTRUCTION | 192000
EB-5924 | Bike & Ped | Locally Selected | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). |  | WATAUGA | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF HF(M) IS CONTINGENCY FUNDS ON WBS 44607 | Exempt |  | FLAP | RIGHT-OF-WAY | 73000
EB-5924 | Bike & Ped | Locally Selected | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). |  | WATAUGA | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF HF(M) IS CONTINGENCY FUNDS ON WBS 44607 | Exempt |  | L | RIGHT-OF-WAY | 17000
EB-5924 | Bike & Ped | Locally Selected | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). |  | WATAUGA | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF HF(M) IS CONTINGENCY FUNDS ON WBS 44607 | Exempt |  | FLAP | CONSTRUCTION | 1624000
EB-5924 | Bike & Ped | Locally Selected | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). |  | WATAUGA | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF HF(M) IS CONTINGENCY FUNDS ON WBS 44607 | Exempt |  | L | CONSTRUCTION | 245000
EB-5924 | Bike & Ped | Locally Selected | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). |  | WATAUGA | 11 | High Country RPO | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF HF(M) IS CONTINGENCY FUNDS ON WBS 44607 | Exempt |  | HF(M) | CONSTRUCTION | 145000
EB-5926 | Bike & Ped | Locally Selected | US 19 (SOCO ROAD) | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. |  | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP | Division 14 |  | BGANY | CONSTRUCTION | 80000
EB-5926 | Bike & Ped | Locally Selected | US 19 (SOCO ROAD) | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. |  | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP | Division 14 |  | BGDA | CONSTRUCTION | 1440000
EB-5926 | Bike & Ped | Locally Selected | US 19 (SOCO ROAD) | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. |  | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. $80K IN BGANY USED AS PART OF FUND SWAP | Division 14 |  | L | CONSTRUCTION | 380000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | TADA | ENGINEERING | 129000 | FY 2025: 129000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | TADA | ENGINEERING | 57000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | L | ENGINEERING | 56000 | FY 2025: 56000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | L | ENGINEERING | 23000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | TADA | RIGHT-OF-WAY | 362000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | L | RIGHT-OF-WAY | 155000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | BGANY | CONSTRUCTION | 1159000 | FY 2026: 1159000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | BGDA | CONSTRUCTION | 9000 | FY 2026: 9000
EB-5929 | Bike & Ped | Locally Selected | SOUTH MCDOWELL STREET | BAXTER STREET TO EAST STONEWALL STREET. CONSTRUCT BIKE LANES AND UPGRADE PEDESTRIAN ACCOMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $1.159M IN STBG-DA SWITCHED FOR BGANY AS PART OF I-77 PPSL FUND SWAP. RIGHT-OF-WAY IN PROGRESS. BELK GREENWAY CONNECTOR PHASE ONE. | Division 10 |  | L | CONSTRUCTION | 501000 | FY 2026: 501000
EB-5930 | Bike & Ped | Locally Selected | TROUTMAN | RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. DOWNTOWN TROUTMAN SIDEWALK IMPROVEMENTS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | ENGINEERING | 203000
EB-5930 | Bike & Ped | Locally Selected | TROUTMAN | RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. DOWNTOWN TROUTMAN SIDEWALK IMPROVEMENTS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | ENGINEERING | 109000
EB-5930 | Bike & Ped | Locally Selected | TROUTMAN | RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. DOWNTOWN TROUTMAN SIDEWALK IMPROVEMENTS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | RIGHT-OF-WAY | 129000
EB-5930 | Bike & Ped | Locally Selected | TROUTMAN | RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. DOWNTOWN TROUTMAN SIDEWALK IMPROVEMENTS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | RIGHT-OF-WAY | 70000
EB-5930 | Bike & Ped | Locally Selected | TROUTMAN | RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. DOWNTOWN TROUTMAN SIDEWALK IMPROVEMENTS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | CONSTRUCTION | 1055000
EB-5930 | Bike & Ped | Locally Selected | TROUTMAN | RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. DOWNTOWN TROUTMAN SIDEWALK IMPROVEMENTS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | CONSTRUCTION | 568000
EB-5931 | Bike & Ped | Locally Selected | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). |  | UNION | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BGDA | ENGINEERING | 20000
EB-5931 | Bike & Ped | Locally Selected | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). |  | UNION | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | ENGINEERING | 5000
EB-5931 | Bike & Ped | Locally Selected | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). |  | UNION | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | TADA | RIGHT-OF-WAY | 1207000
EB-5931 | Bike & Ped | Locally Selected | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). |  | UNION | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | RIGHT-OF-WAY | 302000
EB-5931 | Bike & Ped | Locally Selected | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). |  | UNION | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | CMAQ | CONSTRUCTION | 4013000 | FY 2025: 4013000
EB-5931 | Bike & Ped | Locally Selected | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). |  | UNION | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | CONSTRUCTION | 723000 | FY 2025: 723000
EB-5931 | Bike & Ped | Locally Selected | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD) (FORMERLY U-6250). |  | UNION | 10 | Charlotte Regional TPO | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP. $4.719 M IN STBG-DANY SWITCHED WITH $4.719M IN CMAQ FUNDS FOR CON AS PART OF FUND SWAP 8-9-22. | Division 10 |  | L | CONSTRUCTION | 1003000 | FY 2025: 1003000
EB-5932 | Bike & Ped | Locally Selected | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | ENGINEERING | 97000
EB-5932 | Bike & Ped | Locally Selected | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | ENGINEERING | 25000
EB-5932 | Bike & Ped | Locally Selected | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | RIGHT-OF-WAY | 174000
EB-5932 | Bike & Ped | Locally Selected | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | RIGHT-OF-WAY | 43000
EB-5932 | Bike & Ped | Locally Selected | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | TADA | CONSTRUCTION | 1000000 | FY 2025: 1000000
EB-5932 | Bike & Ped | Locally Selected | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. CONSTRUCT GREENWAY. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | L | CONSTRUCTION | 250000 | FY 2025: 250000
EB-5933 | Bike & Ped | Locally Selected | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TAANY | ENGINEERING | 175000
EB-5933 | Bike & Ped | Locally Selected | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L | ENGINEERING | 44000
EB-5933 | Bike & Ped | Locally Selected | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | TAANY | CONSTRUCTION | 702000 | FY 2025: 702000
EB-5933 | Bike & Ped | Locally Selected | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $702K IN STBG-DA FUNDS SWAPPED FOR $702K IN TAP-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L | CONSTRUCTION | 176000 | FY 2025: 176000
EB-5935 | Bike & Ped | Locally Selected | CENTENNIAL BOULEVARD | NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II) IN CLAREMONT. CONSTRUCT SIDEWALK. | 1.16 | CATAWBA | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | ENGINEERING | 8000
EB-5935 | Bike & Ped | Locally Selected | CENTENNIAL BOULEVARD | NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II) IN CLAREMONT. CONSTRUCT SIDEWALK. | 1.16 | CATAWBA | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L | ENGINEERING | 2000
EB-5935 | Bike & Ped | Locally Selected | CENTENNIAL BOULEVARD | NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II) IN CLAREMONT. CONSTRUCT SIDEWALK. | 1.16 | CATAWBA | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | CONSTRUCTION | 472000
EB-5935 | Bike & Ped | Locally Selected | CENTENNIAL BOULEVARD | NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II) IN CLAREMONT. CONSTRUCT SIDEWALK. | 1.16 | CATAWBA | 12 | Greater Hickory MPO | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L | CONSTRUCTION | 118000
EB-5937 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | TADA | RIGHT-OF-WAY | 180000
EB-5937 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | L(M) | RIGHT-OF-WAY | 45000
EB-5937 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | BGANY | CONSTRUCTION | 1420000
EB-5937 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | BGANY | CONSTRUCTION | 1290000 | FY 2025: 1290000
EB-5937 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | L(M) | CONSTRUCTION | 323000 | FY 2025: 323000
EB-5937 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | $1,420,000 STBG-ANYAREA FUNDS ARE FROM A FUND SWAP IN MAY 2018. UNDER CONSTRUCTION. | Division 12 |  | L(M) | CONSTRUCTION | 355000
EB-5938 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | TADA | ENGINEERING | 640000
EB-5938 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L | ENGINEERING | 160000
EB-5938 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | TADA | RIGHT-OF-WAY | 84000
EB-5938 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L | RIGHT-OF-WAY | 21000
EB-5938 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | BGANY | CONSTRUCTION | 2476000
EB-5938 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | TAANY | CONSTRUCTION | 1600000
EB-5938 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L | CONSTRUCTION | 400000
EB-5938 | Bike & Ped | Locally Selected | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | 0.61 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L | CONSTRUCTION | 619000
EB-5939 | Bike & Ped | Locally Selected | HICKORY | RIVERWALK. CONSTRUCT MULTI-USE PATH FROM OLD LENOIR ROAD AT CITY OWNED PROPERTY TO END OF PROPOSED ROSALES BRIDGE. | 0.59 | BURKE | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 13 |  | BGDA | CONSTRUCTION | 5200000
EB-5939 | Bike & Ped | Locally Selected | HICKORY | RIVERWALK. CONSTRUCT MULTI-USE PATH FROM OLD LENOIR ROAD AT CITY OWNED PROPERTY TO END OF PROPOSED ROSALES BRIDGE. | 0.59 | BURKE | 13 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 13 |  | L | CONSTRUCTION | 1300000
EB-5944 | Bike & Ped | Locally Selected | JOHNSTON BOULEVARD ASHEVILLE | PATTON AVENUE TO IONA CIRCLE IN ASHEVILLE. CONSTRUCT SIDEWALKS. | 0.95 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | BGDA | CONSTRUCTION | 1880000 | FY 2025: 1880000
EB-5944 | Bike & Ped | Locally Selected | JOHNSTON BOULEVARD ASHEVILLE | PATTON AVENUE TO IONA CIRCLE IN ASHEVILLE. CONSTRUCT SIDEWALKS. | 0.95 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 470000 | FY 2025: 470000
EB-5945 | Bike & Ped | Locally Selected | TOWN OF CANTON | CHAMPION DRIVE, NORTH CANTON ROAD TO THICKETY ROAD. CONSTRUCT MULTI-USE PATH. | 0.68 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | BGDA | RIGHT-OF-WAY | 307000
EB-5945 | Bike & Ped | Locally Selected | TOWN OF CANTON | CHAMPION DRIVE, NORTH CANTON ROAD TO THICKETY ROAD. CONSTRUCT MULTI-USE PATH. | 0.68 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | L | RIGHT-OF-WAY | 77000
EB-5946 | Bike & Ped | Locally Selected | TOWN OF MILLS RIVER | NC 280, FRENCH BROAD RIVER TO HAYWOOD ROAD (NC 191). CONSTRUCT MULTI-USE PATH. | 3.09 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TADA | ENGINEERING | 300000 | FY 2026: 300000
EB-5946 | Bike & Ped | Locally Selected | TOWN OF MILLS RIVER | NC 280, FRENCH BROAD RIVER TO HAYWOOD ROAD (NC 191). CONSTRUCT MULTI-USE PATH. | 3.09 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | ENGINEERING | 75000 | FY 2026: 75000
EB-5947 | Bike & Ped | Locally Selected | NEW HAW CREEK ROAD ASHEVILLE | BEVERLY ROAD TO BELL ROAD IN ASHEVILLE. CONSTRUCT SIDEWALKS. | 0.79 | BUNCOMBE | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | Division 13 |  | BGANY | ENGINEERING | 8000
EB-5947 | Bike & Ped | Locally Selected | NEW HAW CREEK ROAD ASHEVILLE | BEVERLY ROAD TO BELL ROAD IN ASHEVILLE. CONSTRUCT SIDEWALKS. | 0.79 | BUNCOMBE | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | Division 13 |  | L | ENGINEERING | 2000
EB-5947 | Bike & Ped | Locally Selected | NEW HAW CREEK ROAD ASHEVILLE | BEVERLY ROAD TO BELL ROAD IN ASHEVILLE. CONSTRUCT SIDEWALKS. | 0.79 | BUNCOMBE | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | Division 13 |  | BGANY | CONSTRUCTION | 1892000
EB-5947 | Bike & Ped | Locally Selected | NEW HAW CREEK ROAD ASHEVILLE | BEVERLY ROAD TO BELL ROAD IN ASHEVILLE. CONSTRUCT SIDEWALKS. | 0.79 | BUNCOMBE | 13 | French Broad River MPO | $1.9M IN BGANY USED AS PART OF FUND SWAP | Division 13 |  | L | CONSTRUCTION | 473000
EB-5948 | Bike & Ped | Locally Selected | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | 0.39 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | BGDA | CONSTRUCTION | 572000
EB-5948 | Bike & Ped | Locally Selected | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | 0.39 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | TADA | CONSTRUCTION | 340000
EB-5948 | Bike & Ped | Locally Selected | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | 0.39 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Division 13 |  | L | CONSTRUCTION | 228000
EB-5949 | Bike & Ped | Locally Selected | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 0.06 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | Division 10 |  | BGDA | CONSTRUCTION | 1175000
EB-5949 | Bike & Ped | Locally Selected | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 0.06 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | Division 10 |  | O | CONSTRUCTION | 1141000
EB-5949 | Bike & Ped | Locally Selected | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 0.06 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | Division 10 |  | O | CONSTRUCTION | 1435000
EB-5949 | Bike & Ped | Locally Selected | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 0.06 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | Division 10 |  | L | CONSTRUCTION | 294000
EB-5949 | Bike & Ped | Locally Selected | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | 0.06 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH | Division 10 |  | L | CONSTRUCTION | 359000
EB-5950 | Highway | Locally Selected | WAXHAW KENSINGTON DRIVE | NC 16 TO SUNSET HILL ROAD. IMPROVE CORRIDOR. | 0.24 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGDA | RIGHT-OF-WAY | 421000
EB-5950 | Highway | Locally Selected | WAXHAW KENSINGTON DRIVE | NC 16 TO SUNSET HILL ROAD. IMPROVE CORRIDOR. | 0.24 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L | RIGHT-OF-WAY | 170000
EB-5950 | Highway | Locally Selected | WAXHAW KENSINGTON DRIVE | NC 16 TO SUNSET HILL ROAD. IMPROVE CORRIDOR. | 0.24 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | BGANY | CONSTRUCTION | 2749000 | FY 2025: 2749000
EB-5950 | Highway | Locally Selected | WAXHAW KENSINGTON DRIVE | NC 16 TO SUNSET HILL ROAD. IMPROVE CORRIDOR. | 0.24 | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $2.749M IN STBG-DA FUNDS SWAPPED FOR $2.749M IN STBG-ANYAREA FUNDS ON 5-17-23 | Division 10 |  | L | CONSTRUCTION | 1069000 | FY 2025: 1069000
EB-5952 | Bike & Ped | Locally Selected | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.39 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 198000
EB-5952 | Bike & Ped | Locally Selected | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.39 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 50000
EB-5952 | Bike & Ped | Locally Selected | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.39 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 593000 | FY 2025: 593000
EB-5952 | Bike & Ped | Locally Selected | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.39 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 148000 | FY 2025: 148000
EB-5953 | Bike & Ped | Locally Selected | SR 4000 (UNIVERSITY PARKWAY) | SR-1686 (SHATTALON DRIVE) TO ROBIN WOOD LANE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.3 | FORSYTH | 9 | Winston-Salem Area TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM | Division 9 |  | BGDA | CONSTRUCTION | 508000 | FY 2025: 508000
EB-5953 | Bike & Ped | Locally Selected | SR 4000 (UNIVERSITY PARKWAY) | SR-1686 (SHATTALON DRIVE) TO ROBIN WOOD LANE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.3 | FORSYTH | 9 | Winston-Salem Area TPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM | Division 9 |  | L | CONSTRUCTION | 127000 | FY 2025: 127000
EB-5954 | Bike & Ped | Locally Selected | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 1.07 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | ENGINEERING | 32000 | FY 2025: 32000
EB-5954 | Bike & Ped | Locally Selected | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 1.07 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | ENGINEERING | 8000 | FY 2025: 8000
EB-5954 | Bike & Ped | Locally Selected | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 1.07 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 234000 | FY 2025: 234000
EB-5954 | Bike & Ped | Locally Selected | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 1.07 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 59000 | FY 2025: 59000
EB-5954 | Bike & Ped | Locally Selected | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 1.07 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 2944000 | FY 2026: 2944000
EB-5954 | Bike & Ped | Locally Selected | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 1.07 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 736000 | FY 2026: 736000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | ENGINEERING | 42000 | FY 2025: 42000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | ENGINEERING | 11000 | FY 2025: 11000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 53000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | RIGHT-OF-WAY | 13000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 376000 | FY 2025: 376000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 286000 | FY 2025: 286000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 94000 | FY 2025: 94000
EB-5955 | Bike & Ped | Locally Selected | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | 0.34 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L(M) | CONSTRUCTION | 72000 | FY 2025: 72000
EB-5956 | Bike & Ped | Locally Selected | SR 1992 (SULLIVANTOWN ROAD) | US 311 AT HARLEY DRIVE TO WALKERTOWN HIGH/MIDDLE SCHOOL IN WALKERTOWN. INSTALL BICYCLE AND PEDESTRIAN FACILITIES AND CONSTRUCT SIDEWALK. | 0.44 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 694000 | FY 2025: 694000
EB-5956 | Bike & Ped | Locally Selected | SR 1992 (SULLIVANTOWN ROAD) | US 311 AT HARLEY DRIVE TO WALKERTOWN HIGH/MIDDLE SCHOOL IN WALKERTOWN. INSTALL BICYCLE AND PEDESTRIAN FACILITIES AND CONSTRUCT SIDEWALK. | 0.44 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 174000 | FY 2025: 174000
EB-5957 | Bike & Ped | Locally Selected | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 0.09 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 29000
EB-5957 | Bike & Ped | Locally Selected | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 0.09 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 7000
EB-5957 | Bike & Ped | Locally Selected | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 0.09 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | BGDA | CONSTRUCTION | 186000
EB-5957 | Bike & Ped | Locally Selected | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | 0.09 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 46000 | FY 2025: 46000
EB-5958 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 1 | DAVIE | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  | BGANY | CONSTRUCTION | 1452000
EB-5958 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 1 | DAVIE | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  | BGDA | CONSTRUCTION | 1502000
EB-5958 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 1 | DAVIE | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  | L | CONSTRUCTION | 364000
EB-5958 | Bike & Ped | Locally Selected | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTI-USE PATH. | 1 | DAVIE | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Division 9 |  | L | CONSTRUCTION | 375000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | ENGINEERING | 154000 | FY 2025: 154000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | ENGINEERING | 38000 | FY 2025: 38000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 196000 | FY 2025: 196000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 49000 | FY 2025: 49000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | UTILITIES | 336000 | FY 2025: 336000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | UTILITIES | 84000 | FY 2025: 84000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 120000 | FY 2027: 120000
EB-5959 | Bike & Ped | Locally Selected | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | 0.92 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 30000 | FY 2027: 30000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | ENGINEERING | 100000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | ENGINEERING | 25000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | RIGHT-OF-WAY | 206000 | FY 2025: 206000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | RIGHT-OF-WAY | 51000 | FY 2025: 51000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | UTILITIES | 160000 | FY 2025: 160000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | UTILITIES | 40000 | FY 2025: 40000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | BGANY | CONSTRUCTION | 2137000 | FY 2026: 2137000
EB-5960 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | 1.01 | FORSYTH | 9 | Winston-Salem Area TPO | IN PROGRESS | Division 9 |  | L | CONSTRUCTION | 534000 | FY 2026: 534000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 0.23 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | TALT5 | ENGINEERING | 50000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 0.23 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | L | ENGINEERING | 13000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 0.23 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | TALT5 | RIGHT-OF-WAY | 42000 | FY 2026: 42000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 0.23 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | L | RIGHT-OF-WAY | 11000 | FY 2026: 11000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 0.23 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | TALT5 | CONSTRUCTION | 140000 | FY 2027: 140000
EB-5961 | Bike & Ped | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | 0.23 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | L | CONSTRUCTION | 35000 | FY 2027: 35000
EB-5963 | Bike & Ped | STI (Prioritization) | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TAANY | ENGINEERING | 126000
EB-5963 | Bike & Ped | STI (Prioritization) | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | ENGINEERING | 31000
EB-5963 | Bike & Ped | STI (Prioritization) | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TAANY | RIGHT-OF-WAY | 640000 | FY 2025: 640000
EB-5963 | Bike & Ped | STI (Prioritization) | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | RIGHT-OF-WAY | 160000 | FY 2025: 160000
EB-5963 | Bike & Ped | STI (Prioritization) | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TAANY | UTILITIES | 76000 | FY 2025: 76000
EB-5963 | Bike & Ped | STI (Prioritization) | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | UTILITIES | 19000 | FY 2025: 19000
EB-5963 | Bike & Ped | STI (Prioritization) | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | TAANY | CONSTRUCTION | 720000 | FY 2027: 720000
EB-5963 | Bike & Ped | STI (Prioritization) | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | 0.72 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | L | CONSTRUCTION | 180000 | FY 2027: 180000
EB-5964 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET/ US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 0.83 | MACON | 14 | Southwestern RPO |  | Division 14 |  | TA5T50 | ENGINEERING | 16000
EB-5964 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET/ US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 0.83 | MACON | 14 | Southwestern RPO |  | Division 14 |  | L | ENGINEERING | 4000
EB-5964 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET/ US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 0.83 | MACON | 14 | Southwestern RPO |  | Division 14 |  | TA5T50 | RIGHT-OF-WAY | 16000 | FY 2025: 16000
EB-5964 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET/ US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 0.83 | MACON | 14 | Southwestern RPO |  | Division 14 |  | L | RIGHT-OF-WAY | 4000 | FY 2025: 4000
EB-5964 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET/ US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 0.83 | MACON | 14 | Southwestern RPO |  | Division 14 |  | TA5T50 | CONSTRUCTION | 520000 | FY 2025: 520000
EB-5964 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET/ US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | 0.83 | MACON | 14 | Southwestern RPO |  | Division 14 |  | L | CONSTRUCTION | 130000 | FY 2025: 130000
EB-5965 | Bike & Ped | STI (Prioritization) | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | TAANY | ENGINEERING | 568000 | FY 2028: 568000
EB-5965 | Bike & Ped | STI (Prioritization) | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | ENGINEERING | 142000 | FY 2028: 142000
EB-5965 | Bike & Ped | STI (Prioritization) | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | TAANY | RIGHT-OF-WAY | 200000 | FY 2029: 200000
EB-5965 | Bike & Ped | STI (Prioritization) | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | RIGHT-OF-WAY | 50000 | FY 2029: 50000
EB-5965 | Bike & Ped | STI (Prioritization) | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | TAANY | UTILITIES | 880000 | FY 2029: 880000
EB-5965 | Bike & Ped | STI (Prioritization) | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | UTILITIES | 220000 | FY 2029: 220000
EB-5965 | Bike & Ped | STI (Prioritization) | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | TAANY | CONSTRUCTION | 5560000 | FY 2031: 5560000
EB-5965 | Bike & Ped | STI (Prioritization) | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | 0.75 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | L | CONSTRUCTION | 1390000 | FY 2031: 1390000
EB-5966 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 2.78 | RUTHERFORD | 13 | Foothills RPO |  | Division 13 |  | TAANY | ENGINEERING | 120000
EB-5966 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 2.78 | RUTHERFORD | 13 | Foothills RPO |  | Division 13 |  | L | ENGINEERING | 30000
EB-5966 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 2.78 | RUTHERFORD | 13 | Foothills RPO |  | Division 13 |  | TAANY | RIGHT-OF-WAY | 416000 | FY 2025: 416000
EB-5966 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 2.78 | RUTHERFORD | 13 | Foothills RPO |  | Division 13 |  | L | RIGHT-OF-WAY | 104000 | FY 2025: 104000
EB-5966 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 2.78 | RUTHERFORD | 13 | Foothills RPO |  | Division 13 |  | TAANY | CONSTRUCTION | 1680000 | FY 2026: 1680000
EB-5966 | Bike & Ped | STI (Prioritization) | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | 2.78 | RUTHERFORD | 13 | Foothills RPO |  | Division 13 |  | L | CONSTRUCTION | 420000 | FY 2026: 420000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 371000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 93000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 692000 | FY 2029: 692000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | RIGHT-OF-WAY | 76000 | FY 2029: 76000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 173000 | FY 2029: 173000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 19000 | FY 2029: 19000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | CONSTRUCTION | 103000 | FY 2031: 103000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 937000 | FY 2031: 937000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 234000 | FY 2031: 234000
EB-5969 | Bike & Ped | STI (Prioritization) | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | 0.53 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 26000 | FY 2031: 26000
EB-5970 | Bike & Ped | STI (Prioritization) | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | 0.55 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | CONSTRUCTION | 325000 | FY 2028: 325000
EB-5970 | Bike & Ped | STI (Prioritization) | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | 0.55 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | CONSTRUCTION | 2921000 | FY 2029: 2921000
EB-5970 | Bike & Ped | STI (Prioritization) | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | 0.55 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 139000 | FY 2028: 139000
EB-5970 | Bike & Ped | STI (Prioritization) | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | 0.55 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 1252000 | FY 2029: 1252000
EB-5971 | Bike & Ped | STI (Prioritization) | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | 0.66 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | ENGINEERING | 8000 | FY 2025: 8000
EB-5971 | Bike & Ped | STI (Prioritization) | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | 0.66 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 2000 | FY 2025: 2000
EB-5971 | Bike & Ped | STI (Prioritization) | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | 0.66 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TAANY | CONSTRUCTION | 720000 | FY 2026: 720000
EB-5971 | Bike & Ped | STI (Prioritization) | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | 0.66 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 180000 | FY 2026: 180000
EB-5972 | Bike & Ped | STI (Prioritization) | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | ENGINEERING | 240000
EB-5972 | Bike & Ped | STI (Prioritization) | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | ENGINEERING | 60000
EB-5972 | Bike & Ped | STI (Prioritization) | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | RIGHT-OF-WAY | 274000 | FY 2026: 274000
EB-5972 | Bike & Ped | STI (Prioritization) | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | RIGHT-OF-WAY | 68000 | FY 2026: 68000
EB-5972 | Bike & Ped | STI (Prioritization) | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | UTILITIES | 65000 | FY 2026: 65000
EB-5972 | Bike & Ped | STI (Prioritization) | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | UTILITIES | 16000 | FY 2026: 16000
EB-5972 | Bike & Ped | STI (Prioritization) | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | CONSTRUCTION | 960000 | FY 2027: 960000
EB-5972 | Bike & Ped | STI (Prioritization) | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | 0.51 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | CONSTRUCTION | 240000 | FY 2027: 240000
EB-5973 | Bike & Ped | STI (Prioritization) | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | ENGINEERING | 670000
EB-5973 | Bike & Ped | STI (Prioritization) | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | ENGINEERING | 168000
EB-5973 | Bike & Ped | STI (Prioritization) | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | RIGHT-OF-WAY | 302000 | FY 2025: 302000
EB-5973 | Bike & Ped | STI (Prioritization) | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | RIGHT-OF-WAY | 76000 | FY 2025: 76000
EB-5973 | Bike & Ped | STI (Prioritization) | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | UTILITIES | 48000 | FY 2025: 48000
EB-5973 | Bike & Ped | STI (Prioritization) | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | UTILITIES | 12000 | FY 2025: 12000
EB-5973 | Bike & Ped | STI (Prioritization) | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | TA5T50 | CONSTRUCTION | 2680000 | FY 2025: 2680000
EB-5973 | Bike & Ped | STI (Prioritization) | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | 0.43 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | L | CONSTRUCTION | 670000 | FY 2025: 670000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 1.03 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 413000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 1.03 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 103000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 1.03 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 1652000 | FY 2025: 1652000
EB-5975 | Bike & Ped | STI (Prioritization) | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | 1.03 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 413000 | FY 2025: 413000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 0.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | ENGINEERING | 280000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 0.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 70000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 0.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TA50200 | CONSTRUCTION | 1120000 | FY 2025: 1120000
EB-5976 | Bike & Ped | STI (Prioritization) | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | 0.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 280000 | FY 2025: 280000
EB-5977 | Bike & Ped | Locally Selected | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 0.27 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | BGDA | RIGHT-OF-WAY | 86000
EB-5977 | Bike & Ped | Locally Selected | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 0.27 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L | RIGHT-OF-WAY | 22000
EB-5977 | Bike & Ped | Locally Selected | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 0.27 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | CRPDA | CONSTRUCTION | 1168000
EB-5977 | Bike & Ped | Locally Selected | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | 0.27 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | L | CONSTRUCTION | 292000
EB-5978 | Bike & Ped | STI (Prioritization) | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 1.33 | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | TAANY | RIGHT-OF-WAY | 80000 | FY 2026: 80000
EB-5978 | Bike & Ped | STI (Prioritization) | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 1.33 | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | L | RIGHT-OF-WAY | 20000 | FY 2026: 20000
EB-5978 | Bike & Ped | STI (Prioritization) | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 1.33 | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | TAANY | CONSTRUCTION | 2320000 | FY 2026: 2320000
EB-5978 | Bike & Ped | STI (Prioritization) | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | 1.33 | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | L | CONSTRUCTION | 580000 | FY 2026: 580000
EB-5979 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 0.33 | MARTIN | 1 | Mid-East RPO |  | Division 1 |  | TAANY | ENGINEERING | 8000 | FY 2025: 8000
EB-5979 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 0.33 | MARTIN | 1 | Mid-East RPO |  | Division 1 |  | L | ENGINEERING | 2000 | FY 2025: 2000
EB-5979 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 0.33 | MARTIN | 1 | Mid-East RPO |  | Division 1 |  | TAANY | CONSTRUCTION | 224000 | FY 2027: 224000
EB-5979 | Bike & Ped | STI (Prioritization) | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | 0.33 | MARTIN | 1 | Mid-East RPO |  | Division 1 |  | L | CONSTRUCTION | 56000 | FY 2027: 56000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 0.26 | BRUNSWICK | 3 | Cape Fear RPO |  | Division 3 |  | TA5T50 | ENGINEERING | 24000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 0.26 | BRUNSWICK | 3 | Cape Fear RPO |  | Division 3 |  | L | ENGINEERING | 6000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 0.26 | BRUNSWICK | 3 | Cape Fear RPO |  | Division 3 |  | TA5T50 | RIGHT-OF-WAY | 40000 | FY 2025: 40000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 0.26 | BRUNSWICK | 3 | Cape Fear RPO |  | Division 3 |  | L | RIGHT-OF-WAY | 10000 | FY 2025: 10000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 0.26 | BRUNSWICK | 3 | Cape Fear RPO |  | Division 3 |  | TA5T50 | CONSTRUCTION | 140000 | FY 2025: 140000
EB-5982 | Bike & Ped | STI (Prioritization) | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | 0.26 | BRUNSWICK | 3 | Cape Fear RPO |  | Division 3 |  | L | CONSTRUCTION | 35000 | FY 2025: 35000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 1.14 | WATAUGA | 11 | High Country RPO |  | Division 11 |  | TAANY | ENGINEERING | 240000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 1.14 | WATAUGA | 11 | High Country RPO |  | Division 11 |  | L | ENGINEERING | 60000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 1.14 | WATAUGA | 11 | High Country RPO |  | Division 11 |  | TAANY | RIGHT-OF-WAY | 16000 | FY 2026: 16000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 1.14 | WATAUGA | 11 | High Country RPO |  | Division 11 |  | L | RIGHT-OF-WAY | 4000 | FY 2026: 4000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 1.14 | WATAUGA | 11 | High Country RPO |  | Division 11 |  | TAANY | CONSTRUCTION | 1492000 | FY 2027: 1492000
EB-5983 | Bike & Ped | STI (Prioritization) | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | 1.14 | WATAUGA | 11 | High Country RPO |  | Division 11 |  | L | CONSTRUCTION | 373000 | FY 2027: 373000
EB-5984 | Bike & Ped | STI (Prioritization) | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 2.28 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | ENGINEERING | 240000 | FY 2027: 240000
EB-5984 | Bike & Ped | STI (Prioritization) | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 2.28 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L | ENGINEERING | 60000 | FY 2027: 60000
EB-5984 | Bike & Ped | STI (Prioritization) | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 2.28 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | RIGHT-OF-WAY | 560000 | FY 2029: 560000
EB-5984 | Bike & Ped | STI (Prioritization) | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 2.28 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L | RIGHT-OF-WAY | 140000 | FY 2029: 140000
EB-5984 | Bike & Ped | STI (Prioritization) | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 2.28 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | TA50200 | CONSTRUCTION | 2960000 | FY 2031: 2960000
EB-5984 | Bike & Ped | STI (Prioritization) | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | 2.28 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | L | CONSTRUCTION | 740000 | FY 2031: 740000
EB-5985 | Bike & Ped | STI (Prioritization) | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 120000
EB-5985 | Bike & Ped | STI (Prioritization) | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 30000
EB-5985 | Bike & Ped | STI (Prioritization) | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 62000 | FY 2025: 62000
EB-5985 | Bike & Ped | STI (Prioritization) | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 16000 | FY 2025: 16000
EB-5985 | Bike & Ped | STI (Prioritization) | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 377000 | FY 2025: 377000
EB-5985 | Bike & Ped | STI (Prioritization) | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 94000 | FY 2025: 94000
EB-5986 | Bike & Ped | STI (Prioritization) | BENJAMIN PARKWAY | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 32000
EB-5986 | Bike & Ped | STI (Prioritization) | BENJAMIN PARKWAY | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 8000
EB-5986 | Bike & Ped | STI (Prioritization) | BENJAMIN PARKWAY | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 1360000 | FY 2025: 1360000
EB-5986 | Bike & Ped | STI (Prioritization) | BENJAMIN PARKWAY | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 340000 | FY 2025: 340000
EB-5986 | Bike & Ped | STI (Prioritization) | BENJAMIN PARKWAY | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 576000 | FY 2025: 576000
EB-5986 | Bike & Ped | STI (Prioritization) | BENJAMIN PARKWAY | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | UTILITIES | 144000 | FY 2025: 144000
EB-5986 | Bike & Ped | STI (Prioritization) | BENJAMIN PARKWAY | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 4160000 | FY 2026: 4160000
EB-5986 | Bike & Ped | STI (Prioritization) | BENJAMIN PARKWAY | ELAM AVENUE TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT BENJAMIN PARKWAY SIDEPATH INCLUDING ROADWAY IMPROVEMENTS, SIGNAL MODIFICATIONS, AND CROSSING IMPROVEMENTS. | 1.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 1040000 | FY 2026: 1040000
EB-5987 | Bike & Ped | STI (Prioritization) | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 79000
EB-5987 | Bike & Ped | STI (Prioritization) | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 20000
EB-5987 | Bike & Ped | STI (Prioritization) | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 696000 | FY 2025: 696000
EB-5987 | Bike & Ped | STI (Prioritization) | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | RIGHT-OF-WAY | 174000 | FY 2025: 174000
EB-5987 | Bike & Ped | STI (Prioritization) | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 880000 | FY 2025: 880000
EB-5987 | Bike & Ped | STI (Prioritization) | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 220000 | FY 2025: 220000
EB-5987 | Bike & Ped | STI (Prioritization) | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 3440000 | FY 2026: 3440000
EB-5987 | Bike & Ped | STI (Prioritization) | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 0.6 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 860000 | FY 2026: 860000
EB-5988 | Bike & Ped | STI (Prioritization) | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | ENGINEERING | 24000
EB-5988 | Bike & Ped | STI (Prioritization) | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L | ENGINEERING | 6000
EB-5988 | Bike & Ped | STI (Prioritization) | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 32000 | FY 2026: 32000
EB-5988 | Bike & Ped | STI (Prioritization) | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 8000 | FY 2026: 8000
EB-5988 | Bike & Ped | STI (Prioritization) | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | UTILITIES | 224000 | FY 2026: 224000
EB-5988 | Bike & Ped | STI (Prioritization) | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L | UTILITIES | 56000 | FY 2026: 56000
EB-5988 | Bike & Ped | STI (Prioritization) | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 248000 | FY 2027: 248000
EB-5988 | Bike & Ped | STI (Prioritization) | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | 0.15 | ALAMANCE | 7 | Burlington-Graham MPO |  | Division 7 |  | L | CONSTRUCTION | 62000 | FY 2027: 62000
EB-5989 | Bike & Ped | STI (Prioritization) | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | ENGINEERING | 96000 | FY 2025: 96000
EB-5989 | Bike & Ped | STI (Prioritization) | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 24000 | FY 2025: 24000
EB-5989 | Bike & Ped | STI (Prioritization) | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | RIGHT-OF-WAY | 128000 | FY 2029: 128000
EB-5989 | Bike & Ped | STI (Prioritization) | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 32000 | FY 2029: 32000
EB-5989 | Bike & Ped | STI (Prioritization) | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | UTILITIES | 144000 | FY 2029: 144000
EB-5989 | Bike & Ped | STI (Prioritization) | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | UTILITIES | 36000 | FY 2029: 36000
EB-5989 | Bike & Ped | STI (Prioritization) | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | TA50200 | CONSTRUCTION | 3000000 | FY 2031: 3000000
EB-5989 | Bike & Ped | STI (Prioritization) | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTI-USE FACILITY ACROSS I-74. | 0.08 | GUILFORD | 7 | High Point Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 750000 | FY 2031: 750000
EB-5995 | Bike & Ped | STI (Prioritization) | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 48000
EB-5995 | Bike & Ped | STI (Prioritization) | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 12000
EB-5995 | Bike & Ped | STI (Prioritization) | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 288000 | FY 2025: 288000
EB-5995 | Bike & Ped | STI (Prioritization) | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 72000 | FY 2025: 72000
EB-5995 | Bike & Ped | STI (Prioritization) | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 736000 | FY 2025: 736000
EB-5995 | Bike & Ped | STI (Prioritization) | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | UTILITIES | 184000 | FY 2025: 184000
EB-5995 | Bike & Ped | STI (Prioritization) | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 1360000 | FY 2026: 1360000
EB-5995 | Bike & Ped | STI (Prioritization) | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 2.54 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 340000 | FY 2026: 340000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 1.2 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 80000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 1.2 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 20000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 1.2 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 664000 | FY 2025: 664000
EB-5996 | Bike & Ped | STI (Prioritization) | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | 1.2 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 166000 | FY 2025: 166000
EB-5997 | Bike & Ped | STI (Prioritization) | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | ENGINEERING | 56000
EB-5997 | Bike & Ped | STI (Prioritization) | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 14000
EB-5997 | Bike & Ped | STI (Prioritization) | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | RIGHT-OF-WAY | 36000 | FY 2025: 36000
EB-5997 | Bike & Ped | STI (Prioritization) | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 9000 | FY 2025: 9000
EB-5997 | Bike & Ped | STI (Prioritization) | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | UTILITIES | 448000 | FY 2025: 448000
EB-5997 | Bike & Ped | STI (Prioritization) | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | UTILITIES | 112000 | FY 2025: 112000
EB-5997 | Bike & Ped | STI (Prioritization) | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 1440000 | FY 2025: 1440000
EB-5997 | Bike & Ped | STI (Prioritization) | GREEN VALLEY ROAD | MARKET STREET TO BATTLEGROUND AVENUE IN GREENSBORO. CONSTRUCT SIDEWALKS. | 1.29 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 360000 | FY 2025: 360000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | Division 7 |  | TAANY | ENGINEERING | 163000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | Division 7 |  | L | ENGINEERING | 41000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | Division 7 |  | TAANY | RIGHT-OF-WAY | 384000 | FY 2025: 384000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | Division 7 |  | L | RIGHT-OF-WAY | 96000 | FY 2025: 96000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | Division 7 |  | TAANY | UTILITIES | 880000 | FY 2025: 880000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | Division 7 |  | L | UTILITIES | 220000 | FY 2025: 220000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | Division 7 |  | TAANY | CONSTRUCTION | 5760000 | FY 2026: 5760000
EB-5998 | Bike & Ped | STI (Prioritization) | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTI-USE PATHS. | 1.24 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5304 | Division 7 |  | L | CONSTRUCTION | 1440000 | FY 2026: 1440000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 0.36 | MOORE | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | TA50200 | ENGINEERING | 21000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 0.36 | MOORE | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | L | ENGINEERING | 5000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 0.36 | MOORE | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | TA50200 | RIGHT-OF-WAY | 27000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 0.36 | MOORE | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | L | RIGHT-OF-WAY | 7000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 0.36 | MOORE | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | TA50200 | CONSTRUCTION | 272000 | FY 2025: 272000
EB-6001 | Bike & Ped | STI (Prioritization) | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | 0.36 | MOORE | 8 | Sandhills MPO | COORDINATE WITH U-5815 | Division 8 |  | L | CONSTRUCTION | 68000 | FY 2025: 68000
EB-6002 | Bike & Ped | STI (Prioritization) | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 0.95 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 153000
EB-6002 | Bike & Ped | STI (Prioritization) | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 0.95 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | ENGINEERING | 38000
EB-6002 | Bike & Ped | STI (Prioritization) | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 0.95 | LEE | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1120000 | FY 2025: 1120000
EB-6002 | Bike & Ped | STI (Prioritization) | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | 0.95 | LEE | 8 | Central Pines RPO |  | Division 8 |  | L | CONSTRUCTION | 280000 | FY 2025: 280000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | 0.15 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 272000 | FY 2027: 272000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | 0.15 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 68000 | FY 2027: 68000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | 0.15 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | UTILITIES | 90000 | FY 2027: 90000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | 0.15 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1680000 | FY 2027: 1680000
EB-6004 | Bike & Ped | STI (Prioritization) | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | 0.15 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | L | CONSTRUCTION | 420000 | FY 2027: 420000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 266000 | FY 2025: 266000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | L | ENGINEERING | 67000 | FY 2025: 67000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 176000 | FY 2025: 176000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 44000 | FY 2025: 44000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | UTILITIES | 128000 | FY 2025: 128000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | L | UTILITIES | 32000 | FY 2025: 32000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1600000 | FY 2026: 1600000
EB-6006 | Bike & Ped | STI (Prioritization) | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | 0.45 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | L | CONSTRUCTION | 400000 | FY 2026: 400000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | ENGINEERING | 271000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 68000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | CMAQ | RIGHT-OF-WAY | 238000 | FY 2025: 238000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | RIGHT-OF-WAY | 88000 | FY 2025: 88000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 82000 | FY 2025: 82000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | CMAQ | CONSTRUCTION | 2265000 | FY 2026: 2265000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | CRPDA | CONSTRUCTION | 286000 | FY 2026: 286000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | TAANY | CONSTRUCTION | 1804000 | FY 2026: 1804000
EB-6008 | Bike & Ped | STI (Prioritization) | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | 0.35 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 1089000 | FY 2026: 1089000
EB-6012 | Bike & Ped | STI (Prioritization) | DOWNTOWN GREENWAY | CHANEY AVENUE TO WARDOLA DRIVE IN JACKSONVILLE. CONSTRUCT MULTI-USE PATH. | 0.58 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | TA50200 | CONSTRUCTION | 1094000
EB-6012 | Bike & Ped | STI (Prioritization) | DOWNTOWN GREENWAY | CHANEY AVENUE TO WARDOLA DRIVE IN JACKSONVILLE. CONSTRUCT MULTI-USE PATH. | 0.58 | ONSLOW | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L | CONSTRUCTION | 273000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 1.52 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | TAANY | ENGINEERING | 136000 | FY 2027: 136000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 1.52 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | L | ENGINEERING | 34000 | FY 2027: 34000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 1.52 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | TAANY | RIGHT-OF-WAY | 134000 | FY 2028: 134000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 1.52 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | L | RIGHT-OF-WAY | 34000 | FY 2028: 34000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 1.52 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | TAANY | CONSTRUCTION | 2000000 | FY 2029: 2000000
EB-6013 | Bike & Ped | STI (Prioritization) | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | 1.52 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | L | CONSTRUCTION | 500000 | FY 2029: 500000
EB-6014 | Bike & Ped | STI (Prioritization) | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 0.81 | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | TAANY | RIGHT-OF-WAY | 28000
EB-6014 | Bike & Ped | STI (Prioritization) | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 0.81 | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | L | RIGHT-OF-WAY | 7000
EB-6014 | Bike & Ped | STI (Prioritization) | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 0.81 | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | TAANY | CONSTRUCTION | 504000
EB-6014 | Bike & Ped | STI (Prioritization) | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | 0.81 | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | L | CONSTRUCTION | 126000
EB-6015 | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS. | 1 | SCOTLAND | 8 | Lumber River RPO
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.52 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 53000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.52 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L(M) | ENGINEERING | 13000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.52 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 61000 | FY 2025: 61000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.52 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 15000 | FY 2025: 15000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.52 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 528000 | FY 2027: 208000; FY 2028: 320000
EB-6015A | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.52 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 132000 | FY 2027: 132000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.45 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 56000 | FY 2025: 56000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.45 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L(M) | ENGINEERING | 14000 | FY 2025: 14000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.45 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 24000 | FY 2025: 24000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.45 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L(M) | RIGHT-OF-WAY | 6000 | FY 2025: 6000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.45 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1040000 | FY 2027: 1040000
EB-6015B | Bike & Ped | STI (Prioritization) | US 401 BUSINESS (SOUTH MAIN STREET) | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | 0.45 | SCOTLAND | 8 | Lumber River RPO |  | Division 8 |  | L(M) | CONSTRUCTION | 260000 | FY 2027: 260000
EB-6016 | Bike & Ped | STI (Prioritization) | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TAANY | ENGINEERING | 206000 | FY 2027: 206000
EB-6016 | Bike & Ped | STI (Prioritization) | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | ENGINEERING | 52000 | FY 2027: 52000
EB-6016 | Bike & Ped | STI (Prioritization) | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TAANY | RIGHT-OF-WAY | 624000 | FY 2029: 624000
EB-6016 | Bike & Ped | STI (Prioritization) | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | RIGHT-OF-WAY | 156000 | FY 2029: 156000
EB-6016 | Bike & Ped | STI (Prioritization) | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TAANY | UTILITIES | 2320000 | FY 2029: 2320000
EB-6016 | Bike & Ped | STI (Prioritization) | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | UTILITIES | 580000 | FY 2029: 580000
EB-6016 | Bike & Ped | STI (Prioritization) | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TAANY | CONSTRUCTION | 4240000 | FY 2031: 4240000
EB-6016 | Bike & Ped | STI (Prioritization) | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | 1.06 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | CONSTRUCTION | 1060000 | FY 2031: 1060000
EB-6017 | Bike & Ped | STI (Prioritization) | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TAANY | ENGINEERING | 66000 | FY 2028: 66000
EB-6017 | Bike & Ped | STI (Prioritization) | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | ENGINEERING | 17000 | FY 2028: 17000
EB-6017 | Bike & Ped | STI (Prioritization) | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TAANY | RIGHT-OF-WAY | 8000 | FY 2030: 8000
EB-6017 | Bike & Ped | STI (Prioritization) | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | RIGHT-OF-WAY | 2000 | FY 2030: 2000
EB-6017 | Bike & Ped | STI (Prioritization) | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TAANY | UTILITIES | 8000 | FY 2030: 8000
EB-6017 | Bike & Ped | STI (Prioritization) | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | UTILITIES | 2000 | FY 2030: 2000
EB-6017 | Bike & Ped | STI (Prioritization) | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TAANY | CONSTRUCTION | 1840000 | FY 2032: 1840000
EB-6017 | Bike & Ped | STI (Prioritization) | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | 0.54 | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | CONSTRUCTION | 460000 | FY 2032: 460000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | ENGINEERING | 22000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | L | ENGINEERING | 6000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | RIGHT-OF-WAY | 256000 | FY 2026: 256000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | L | RIGHT-OF-WAY | 64000 | FY 2026: 64000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | UTILITIES | 44000 | FY 2026: 44000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | L | UTILITIES | 11000 | FY 2026: 11000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | TA5T50 | CONSTRUCTION | 1920000 | FY 2028: 1920000
EB-6018 | Bike & Ped | STI (Prioritization) | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | 0.58 | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | L | CONSTRUCTION | 480000 | FY 2028: 480000
EB-6019 | Bike & Ped | Locally Selected | SR 1306 (LAURA DUNCAN ROAD) | APEX COMMUNITY PARK AND NORTH SALEM STREET IN APEX. IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION. | Division 5 |  | BGDA | CONSTRUCTION | 381000
EB-6019 | Bike & Ped | Locally Selected | SR 1306 (LAURA DUNCAN ROAD) | APEX COMMUNITY PARK AND NORTH SALEM STREET IN APEX. IMPROVE SAFETY OF PEDESTRIAN CROSSING. |  | WAKE | 5 | Capital Area MPO | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION. | Division 5 |  | L | CONSTRUCTION | 163000
EB-6020 | Bike & Ped | Locally Selected | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 0.73 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 140000
EB-6020 | Bike & Ped | Locally Selected | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 0.73 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | L | ENGINEERING | 35000
EB-6020 | Bike & Ped | Locally Selected | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 0.73 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 120000
EB-6020 | Bike & Ped | Locally Selected | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 0.73 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | L | RIGHT-OF-WAY | 30000
EB-6020 | Bike & Ped | Locally Selected | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 0.73 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 1166000 | FY 2025: 1166000
EB-6020 | Bike & Ped | Locally Selected | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | 0.73 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | L | CONSTRUCTION | 291000 | FY 2025: 291000
EB-6021 | Bike & Ped | Locally Selected | BEAVER CREEK GREENWAY EXTENSION | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | 1.21 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 1053000
EB-6021 | Bike & Ped | Locally Selected | BEAVER CREEK GREENWAY EXTENSION | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | 1.21 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 3443000
EB-6021 | Bike & Ped | Locally Selected | BEAVER CREEK GREENWAY EXTENSION | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | 1.21 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 860000
EB-6021 | Bike & Ped | Locally Selected | BEAVER CREEK GREENWAY EXTENSION | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | 1.21 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 263000
EB-6021 | Bike & Ped | Locally Selected | BEAVER CREEK GREENWAY EXTENSION | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | 1.21 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 2582000
EB-6025 | Bike & Ped | Locally Selected | RICE HOPE MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 0.17 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | BGDA | ENGINEERING | 14000
EB-6025 | Bike & Ped | Locally Selected | RICE HOPE MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 0.17 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L | ENGINEERING | 4000
EB-6025 | Bike & Ped | Locally Selected | RICE HOPE MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 0.17 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | BGDA | CONSTRUCTION | 146000
EB-6025 | Bike & Ped | Locally Selected | RICE HOPE MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | 0.17 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L | CONSTRUCTION | 36000
EB-6026 | Bike & Ped | Locally Selected | BELVILLE ELEMENTARY MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 0.37 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | TADA | ENGINEERING | 42000
EB-6026 | Bike & Ped | Locally Selected | BELVILLE ELEMENTARY MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 0.37 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L | ENGINEERING | 10000
EB-6026 | Bike & Ped | Locally Selected | BELVILLE ELEMENTARY MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 0.37 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | TADA | CONSTRUCTION | 354000
EB-6026 | Bike & Ped | Locally Selected | BELVILLE ELEMENTARY MULTI-USE PATH | MULTI-USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | 0.37 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | L | CONSTRUCTION | 88000
EB-6027 | Bike & Ped | Locally Selected | SR 1403 (MIDDLE SOUND LOOP) | CONSTRUCT MULTI-USE PATH SOUTH OF MARKET STREET FROM RED CEDAR ROAD TO EXISTING TRAIL AT CORNER OF MARKET STREET AND MIDDLE SOUND LOOP ROAD. | 6.73 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT OF WAY IN PROGRESS. | Division 3 |  | L | RIGHT-OF-WAY | 500000
EB-6027 | Bike & Ped | Locally Selected | SR 1403 (MIDDLE SOUND LOOP) | CONSTRUCT MULTI-USE PATH SOUTH OF MARKET STREET FROM RED CEDAR ROAD TO EXISTING TRAIL AT CORNER OF MARKET STREET AND MIDDLE SOUND LOOP ROAD. | 6.73 | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT OF WAY IN PROGRESS. | Division 3 |  | L | CONSTRUCTION | 1000000 | FY 2025: 1000000
EB-6028 | Bike & Ped | Locally Selected | WILMINGTON | CONSTRUCT SIGNALIZED PEDESTRIAN CROSSING AT US 17 BUSINESS (MARKET STREET) AND 21ST STREET. | 0 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION | Division 3 |  | TADA | CONSTRUCTION | 131000
EB-6028 | Bike & Ped | Locally Selected | WILMINGTON | CONSTRUCT SIGNALIZED PEDESTRIAN CROSSING AT US 17 BUSINESS (MARKET STREET) AND 21ST STREET. | 0 | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION | Division 3 |  | L | CONSTRUCTION | 33000
EB-6030 | Bike & Ped | Locally Selected | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 2.73 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 60000
EB-6030 | Bike & Ped | Locally Selected | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 2.73 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | ENGINEERING | 15000
EB-6030 | Bike & Ped | Locally Selected | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 2.73 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | RIGHT-OF-WAY | 80000
EB-6030 | Bike & Ped | Locally Selected | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 2.73 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | RIGHT-OF-WAY | 20000
EB-6030 | Bike & Ped | Locally Selected | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 2.73 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 1200000 | FY 2025: 1200000
EB-6030 | Bike & Ped | Locally Selected | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | 2.73 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | CONSTRUCTION | 300000 | FY 2025: 300000
EB-6031 | Bike & Ped | Locally Selected | US 401 (RAMSEY STREET) | CONSTRUCT SIDEWALK FROM SUMMERCHASE DRIVE TO SR 1611 (ANDREWS ROAD). | 0.17 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Division 6 |  | TADA | CONSTRUCTION | 68000
EB-6031 | Bike & Ped | Locally Selected | US 401 (RAMSEY STREET) | CONSTRUCT SIDEWALK FROM SUMMERCHASE DRIVE TO SR 1611 (ANDREWS ROAD). | 0.17 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Division 6 |  | L | CONSTRUCTION | 17000
EB-6032 | Bike & Ped | Locally Selected | NC 59 (HOPE MILLS ROAD) | CONSTRUCT SIDEWALK FROM FAYETTEVILLE CITY LIMITS TO SUMAC CIRCLE. | 1.32 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Division 6 |  | TADA | CONSTRUCTION | 300000
EB-6032 | Bike & Ped | Locally Selected | NC 59 (HOPE MILLS ROAD) | CONSTRUCT SIDEWALK FROM FAYETTEVILLE CITY LIMITS TO SUMAC CIRCLE. | 1.32 | CUMBERLAND | 6 | Fayetteville Area MPO | COMPLETED. | Division 6 |  | L | CONSTRUCTION | 75000
EB-6033 | Bike & Ped | Other | VARIOUS | SAFE ROUTES TO SCHOOL EDUCATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99
EB-6034 | Bike & Ped | Locally Selected | SR 1144 (FIRST STREET) | CONSTRUCTION OF BIKE LANES ON BOTH SIDES OF FIRST STREET FROM EAST OF WEST FIRST STREET EXTENSION TO EAST OF GREENSBORO STREET IN OCEAN ISLE BEACH. | 2.88 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | BGDA | CONSTRUCTION | 622000
EB-6034 | Bike & Ped | Locally Selected | SR 1144 (FIRST STREET) | CONSTRUCTION OF BIKE LANES ON BOTH SIDES OF FIRST STREET FROM EAST OF WEST FIRST STREET EXTENSION TO EAST OF GREENSBORO STREET IN OCEAN ISLE BEACH. | 2.88 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Division 3 |  | L | CONSTRUCTION | 414000
EB-6036 | Bike & Ped | Locally Selected | SUNSET ROAD | OAKDALE ROAD / MIRANDA ROAD TO KIEV DRIVE. CONSTRUCT SIDEWALKS ON NORTH SIDE. | 2.83 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  |  | ENGINEERING | 5000
EB-6036 | Bike & Ped | Locally Selected | SUNSET ROAD | OAKDALE ROAD / MIRANDA ROAD TO KIEV DRIVE. CONSTRUCT SIDEWALKS ON NORTH SIDE. | 2.83 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 1496000 | FY 2025: 1496000
EB-6036 | Bike & Ped | Locally Selected | SUNSET ROAD | OAKDALE ROAD / MIRANDA ROAD TO KIEV DRIVE. CONSTRUCT SIDEWALKS ON NORTH SIDE. | 2.83 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | BGDA | CONSTRUCTION | 1030000 | FY 2026: 1030000
EB-6036 | Bike & Ped | Locally Selected | SUNSET ROAD | OAKDALE ROAD / MIRANDA ROAD TO KIEV DRIVE. CONSTRUCT SIDEWALKS ON NORTH SIDE. | 2.83 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 374000 | FY 2025: 374000
EB-6036 | Bike & Ped | Locally Selected | SUNSET ROAD | OAKDALE ROAD / MIRANDA ROAD TO KIEV DRIVE. CONSTRUCT SIDEWALKS ON NORTH SIDE. | 2.83 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 258000 | FY 2026: 258000
EB-6037 | Bike & Ped | Other | VARIOUS | RAILS TO TRAILS PROGRAM |  | STATEWIDE | 99 | STATEWIDE PROJECT | LOCAL FUNDS REPRESENT LOCAL MATCH FOR RIGHT-OF-WAY AND CONSTRUCTION OF TRAILS BY LOCAL GOVERNMENTS. | Division 99
EB-6037A | Bike & Ped | Locally Selected | SHELBY RAIL TRAIL | SOUTH DEKALB STREET TO GARDNER STREET IN SHELBY. GRAHAM STREET TO WEST MARION STREET IN SHELBY. CONSTRUCT MULTI-USE PATH. | 10.41 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TAANY | ENGINEERING | 8000
EB-6037A | Bike & Ped | Locally Selected | SHELBY RAIL TRAIL | SOUTH DEKALB STREET TO GARDNER STREET IN SHELBY. GRAHAM STREET TO WEST MARION STREET IN SHELBY. CONSTRUCT MULTI-USE PATH. | 10.41 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | ENGINEERING | 2000
EB-6037A | Bike & Ped | Locally Selected | SHELBY RAIL TRAIL | SOUTH DEKALB STREET TO GARDNER STREET IN SHELBY. GRAHAM STREET TO WEST MARION STREET IN SHELBY. CONSTRUCT MULTI-USE PATH. | 10.41 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | TAANY | CONSTRUCTION | 4160000 | FY 2025: 1706000; FY 2026: 2038000; FY 2027: 416000
EB-6037A | Bike & Ped | Locally Selected | SHELBY RAIL TRAIL | SOUTH DEKALB STREET TO GARDNER STREET IN SHELBY. GRAHAM STREET TO WEST MARION STREET IN SHELBY. CONSTRUCT MULTI-USE PATH. | 10.41 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CONSTRUCTION | 1038000 | FY 2025: 1038000
EB-6037B | Bike & Ped | Locally Selected | ECUSTA TRAIL | BREVARD BIKE PATH IN BREVARD TO KANUGA ROAD IN HENDERSONVILLE. CONSTRUCT MULTI-USE PATH. | 19.57 | HENDERSON, TRANSYLVANIA | 14 | French Broad River MPO, Land-of-Sky RPO | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE. | Division 14 |  | TAANY | RIGHT-OF-WAY | 6400000
EB-6037B | Bike & Ped | Locally Selected | ECUSTA TRAIL | BREVARD BIKE PATH IN BREVARD TO KANUGA ROAD IN HENDERSONVILLE. CONSTRUCT MULTI-USE PATH. | 19.57 | HENDERSON, TRANSYLVANIA | 14 | French Broad River MPO, Land-of-Sky RPO | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY. RIGHT-OF-WAY COMPLETE. | Division 14 |  | L | RIGHT-OF-WAY | 1600000
EB-6037C | Bike & Ped | Locally Selected | A&Y GREENWAY | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | CONSTRUCTION | 2749000
EB-6037C | Bike & Ped | Locally Selected | A&Y GREENWAY | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | TAANY | CONSTRUCTION | 4400000
EB-6037C | Bike & Ped | Locally Selected | A&Y GREENWAY | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTI-USE PATH. | 3.08 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 1787000
EB-6038 | Bike & Ped | Locally Selected | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 2.58 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | DP | ENGINEERING | 1764000
EB-6038 | Bike & Ped | Locally Selected | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 2.58 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | L | ENGINEERING | 288000
EB-6038 | Bike & Ped | Locally Selected | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 2.58 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | DP | RIGHT-OF-WAY | 403000
EB-6038 | Bike & Ped | Locally Selected | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 2.58 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | L | RIGHT-OF-WAY | 259000
EB-6038 | Bike & Ped | Locally Selected | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 2.58 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | DP | CONSTRUCTION | 15092000
EB-6038 | Bike & Ped | Locally Selected | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STREET NW ALONG MAIN AVENUE NW TO 11TH STREET NW AND ALONG 11TH STREET NW TO OLD LENOIR ROAD. | 2.58 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT. | Exempt |  | L | CONSTRUCTION | 4124000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 59000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | ENGINEERING | 539000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | ENGINEERING | 15000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | ENGINEERING | 134000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | RIGHT-OF-WAY | 48000 | FY 2025: 48000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | RIGHT-OF-WAY | 12000 | FY 2025: 12000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 398000 | FY 2025: 398000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | TADA | CONSTRUCTION | 586000 | FY 2026: 586000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 147000 | FY 2026: 147000
EB-6039 | Bike & Ped | Locally Selected | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | 1.3 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 100000 | FY 2025: 100000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 53000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | ENGINEERING | 13000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 90000 | FY 2025: 90000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | RIGHT-OF-WAY | 22000 | FY 2025: 22000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | UTILITIES | 16000 | FY 2025: 16000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | UTILITIES | 4000 | FY 2025: 4000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1164000 | FY 2026: 1164000
EB-6040 | Bike & Ped | Locally Selected | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | 0.62 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CONSTRUCTION | 291000 | FY 2026: 291000
EB-6041 | Bike & Ped | Locally Selected | SPRING LAKE | CONSTRUCT 5-MILES OF UNPAVED GREENWAY TRAIL BETWEEN CHAPEL HILL ROAD AND THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | BGDA | ENGINEERING | 190000 | FY 2025: 190000
EB-6041 | Bike & Ped | Locally Selected | SPRING LAKE | CONSTRUCT 5-MILES OF UNPAVED GREENWAY TRAIL BETWEEN CHAPEL HILL ROAD AND THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | L | ENGINEERING | 48000 | FY 2025: 48000
EB-6041 | Bike & Ped | Locally Selected | SPRING LAKE | CONSTRUCT 5-MILES OF UNPAVED GREENWAY TRAIL BETWEEN CHAPEL HILL ROAD AND THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | BGDA | RIGHT-OF-WAY | 102000 | FY 2025: 102000
EB-6041 | Bike & Ped | Locally Selected | SPRING LAKE | CONSTRUCT 5-MILES OF UNPAVED GREENWAY TRAIL BETWEEN CHAPEL HILL ROAD AND THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | L | RIGHT-OF-WAY | 26000 | FY 2025: 26000
EB-6041 | Bike & Ped | Locally Selected | SPRING LAKE | CONSTRUCT 5-MILES OF UNPAVED GREENWAY TRAIL BETWEEN CHAPEL HILL ROAD AND THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | BGDA | CONSTRUCTION | 1228000 | FY 2026: 1228000
EB-6041 | Bike & Ped | Locally Selected | SPRING LAKE | CONSTRUCT 5-MILES OF UNPAVED GREENWAY TRAIL BETWEEN CHAPEL HILL ROAD AND THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | TADA | CONSTRUCTION | 106000
EB-6041 | Bike & Ped | Locally Selected | SPRING LAKE | CONSTRUCT 5-MILES OF UNPAVED GREENWAY TRAIL BETWEEN CHAPEL HILL ROAD AND THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | 5 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | L | CONSTRUCTION | 746000 | FY 2026: 307000
EB-6042 | Bike & Ped | Locally Selected | GREENVILLE | CONSTRUCT MULTI-USE PATH AT VARIOUS LOCATIONS INCLUDING ALONG THE TAR RIVER, MOYE BOULEVARD, THE NORFOLK SOUTHERN RAIL CORRIDOR, AND TOWN CREEK IN GREENVILLE. | 2.27 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 3600000
EB-6042 | Bike & Ped | Locally Selected | GREENVILLE | CONSTRUCT MULTI-USE PATH AT VARIOUS LOCATIONS INCLUDING ALONG THE TAR RIVER, MOYE BOULEVARD, THE NORFOLK SOUTHERN RAIL CORRIDOR, AND TOWN CREEK IN GREENVILLE. | 2.27 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT BUILD GRANT FUNDS. | Exempt |  | L | CONSTRUCTION | 4691000
EB-6046 | Bike & Ped | Locally Selected | (SR 1307) WEST CHATHAM STREET | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 0.31 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 8000
EB-6046 | Bike & Ped | Locally Selected | (SR 1307) WEST CHATHAM STREET | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 0.31 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 2000
EB-6046 | Bike & Ped | Locally Selected | (SR 1307) WEST CHATHAM STREET | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 0.31 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 381000
EB-6046 | Bike & Ped | Locally Selected | (SR 1307) WEST CHATHAM STREET | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | 0.31 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 572000
EB-6048 | Bike & Ped | Locally Selected | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 1.47 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | RIGHT-OF-WAY | 60000
EB-6048 | Bike & Ped | Locally Selected | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 1.47 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | RIGHT-OF-WAY | 15000
EB-6048 | Bike & Ped | Locally Selected | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 1.47 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | BGDA | CONSTRUCTION | 1260000
EB-6048 | Bike & Ped | Locally Selected | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | 1.47 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | L | CONSTRUCTION | 315000
EB-6049 | Bike & Ped | Locally Selected | AVENT FERRY ROAD | GB ALFORD HIGHWAY TO NORTH OF OAK STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO GRIGSBY AVENUE VIA OAK STREET IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | 0.65 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 8000
EB-6049 | Bike & Ped | Locally Selected | AVENT FERRY ROAD | GB ALFORD HIGHWAY TO NORTH OF OAK STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO GRIGSBY AVENUE VIA OAK STREET IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | 0.65 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 2000
EB-6049 | Bike & Ped | Locally Selected | AVENT FERRY ROAD | GB ALFORD HIGHWAY TO NORTH OF OAK STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO GRIGSBY AVENUE VIA OAK STREET IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | 0.65 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1000000
EB-6049 | Bike & Ped | Locally Selected | AVENT FERRY ROAD | GB ALFORD HIGHWAY TO NORTH OF OAK STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO GRIGSBY AVENUE VIA OAK STREET IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | 0.65 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 250000
EB-6051 | Bike & Ped | Locally Selected | LAWYERS ROAD; WILGROVE-MINT HILL ROAD; WILSON GROV | EXTEND EXISTING SIDEWALKS. | 2.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 188000
EB-6051 | Bike & Ped | Locally Selected | LAWYERS ROAD; WILGROVE-MINT HILL ROAD; WILSON GROV | EXTEND EXISTING SIDEWALKS. | 2.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 188000
EB-6051 | Bike & Ped | Locally Selected | LAWYERS ROAD; WILGROVE-MINT HILL ROAD; WILSON GROV | EXTEND EXISTING SIDEWALKS. | 2.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 30000 | FY 2025: 30000
EB-6051 | Bike & Ped | Locally Selected | LAWYERS ROAD; WILGROVE-MINT HILL ROAD; WILSON GROV | EXTEND EXISTING SIDEWALKS. | 2.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 30000 | FY 2025: 30000
EB-6051 | Bike & Ped | Locally Selected | LAWYERS ROAD; WILGROVE-MINT HILL ROAD; WILSON GROV | EXTEND EXISTING SIDEWALKS. | 2.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 1287000 | FY 2028: 1287000
EB-6051 | Bike & Ped | Locally Selected | LAWYERS ROAD; WILGROVE-MINT HILL ROAD; WILSON GROV | EXTEND EXISTING SIDEWALKS. | 2.26 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 1287000 | FY 2028: 1287000
EB-6052 | Bike & Ped | Locally Selected | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | ENGINEERING | 6000
EB-6052 | Bike & Ped | Locally Selected | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | ENGINEERING | 4000
EB-6052 | Bike & Ped | Locally Selected | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | RIGHT-OF-WAY | 240000 | FY 2025: 240000
EB-6052 | Bike & Ped | Locally Selected | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | RIGHT-OF-WAY | 160000 | FY 2025: 160000
EB-6052 | Bike & Ped | Locally Selected | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | TADA | CONSTRUCTION | 751000 | FY 2026: 751000
EB-6052 | Bike & Ped | Locally Selected | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | L | CONSTRUCTION | 501000 | FY 2026: 501000
EL-4828 | Bike & Ped | Transition | MORGAN CREEK GREENWAY | WESTERN SECTION, SR 1919 (SMITH LEVEL ROAD) TO UNIVERSITY LAKE IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 1.7 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY TOWN OF CARRBORO | Pre-STI (Transition)
EL-4828A | Bike & Ped | Pre-STI (Historic) | MORGAN CREEK GREENWAY (CARRBORO) | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 0.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Pre-STI (Transition) |  | BGDA | CONSTRUCTION | 863000 | FY 2025: 863000
EL-4828A | Bike & Ped | Pre-STI (Historic) | MORGAN CREEK GREENWAY (CARRBORO) | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 0.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Pre-STI (Transition) |  | TADA | CONSTRUCTION | 730000 | FY 2025: 730000
EL-4828A | Bike & Ped | Pre-STI (Historic) | MORGAN CREEK GREENWAY (CARRBORO) | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 0.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Pre-STI (Transition) |  | L | CONSTRUCTION | 183000 | FY 2025: 183000
EL-4828A | Bike & Ped | Pre-STI (Historic) | MORGAN CREEK GREENWAY (CARRBORO) | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | 0.29 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Pre-STI (Transition) |  | L | CONSTRUCTION | 216000 | FY 2025: 216000
EL-5100 | Bike & Ped | Other | VARIOUS | PEDESTRIAN, BICYCLE, AND TRANSIT PROJECTS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO). |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Division 4, 5, 6
EL-5101 | Bike & Ped | Other | VARIOUS | PEDESTRIAN AND BICYCLE PROJECTS IN THE GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO). |  | GUILFORD | 7 | Greensboro Urban Area MPO | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS - IN PROGRESS | Division 7
EL-5101DR | Bike & Ped | Locally Selected | MURROW BLVD | MURROW BOULEVARD BRIDGE OVER CHURCH STREET. REPAIR BRIDGE DECK AND COMPLETE GREENWAY ACROSS STRUCTURE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | BGDA | CONSTRUCTION | 1440000
EL-5101DR | Bike & Ped | Locally Selected | MURROW BLVD | MURROW BOULEVARD BRIDGE OVER CHURCH STREET. REPAIR BRIDGE DECK AND COMPLETE GREENWAY ACROSS STRUCTURE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | L | CONSTRUCTION | 360000
ER-2971 | Bike & Ped | Pre-STI (Historic) | VARIOUS | SIDEWALK PROGRAM IN ALL FOURTEEN HIGHWAY DIVISIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS - $182,000 IN STPDA FUNDS ALLOCATED TO ER-2971E | Pre-STI (Transition)
ER-5600 | Highway | Other | VARIOUS | VEGETATION MANAGEMENT - CLEAR ZONE IMPROVEMENT AND LANDSCAPING STATEWIDE. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  | STPE | ENGINEERING | 700000 | FY 2025: 100000; FY 2026: 100000; FY 2027: 100000; FY 2028: 100000
ER-5600 | Highway | Other | VARIOUS | VEGETATION MANAGEMENT - CLEAR ZONE IMPROVEMENT AND LANDSCAPING STATEWIDE. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  | STPE | CONSTRUCTION | 9000000 | FY 2025: 1000000; FY 2026: 1000000; FY 2027: 1000000; FY 2028: 1000000
F-5700 | Ferry | STI (Prioritization) | NC 12 | CONSTRUCT RIVER CLASS FERRY. |  | DARE, HYDE | 1 | Albemarle RPO | COMPLETE | Division 1
F-5702 | Ferry | Other | NC 12 | HATTERAS FERRY DOCK IN DARE COUNTY TO OCRACOKE FERRY DOCKS IN HYDE COUNTY. CONSTRUCT TWO PASSENGER FERRIES TO BE USED ALONG NEW ROUTE. IMPLEMENT TRANSIT SYSTEM TO AID PASSENGERS ON OCRACOKE ISLAND. |  | DARE, HYDE | 1 | Albemarle RPO | OTHER FUNDS ARE FROM STATE APPROPRIATION 7355. | Division 1
F-5702A | Ferry | Other | NC 12 | HATTERAS PARKING LOT IMPROVEMENTS AND CONNECTIVITY MEASURES, HATTERAS LOADING FACILITY |  | DARE | 1 | Albemarle RPO | COMPLETED. WORK ACCOMPLISHED UNDER F-5702B. | Division 1
F-5702B | Ferry | Other | NC 12 | OCRACOKE PEDESTRIAN WAITING AND ACCESS ACCOMMODATIONS |  | HYDE | 1 | Albemarle RPO | COMPLETED. | Division 1
F-5702C | Ferry | Other | NC 12 | CONSTRUCT TWO PASSENGER FERRIES |  | DARE, HYDE | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1
F-5702E | Ferry | Other | NC 12 | HATTERAS AND OCRACOKE DOCK IMPROVEMENTS |  | DARE, HALIFAX | 1, 4 | Albemarle RPO | COMPLETED. WORK ACCOMPLISHED UNDER F-5702B. | Division 1, 4
F-5703 | Ferry | STI (Prioritization) | VARIOUS | REPLACEMENT VESSEL (SUPPORT FLEET) FOR TUGS AND BARGES |  | BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | 1, 2, 3 | Jacksonville Urban Area MPO, Albemarle RPO, Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RPO |  | Division 1, 2, 3
F-5703A | Ferry | STI (Prioritization) | VARIOUS | Z-DRIVE TOWING AND PUSHING TUG |  | BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | 1, 2, 3 | Albemarle RPO, Cape Fear RPO, Down East RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RP | COMPLETED. | Division 1, 2, 3 |  | T | CONSTRUCTION | 3250000
F-5703B | Ferry | STI (Prioritization) | VARIOUS | TWO SUPPORT/ANCHOR TUGS, ONE SUPPORT TUG, THREE BARGES |  | BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | 1, 2, 3 | Albemarle RPO, Cape Fear RPO, Down East RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Grand Strand Area Transportation Study, Greenville Urban Area MPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Mid-East RPO, New Bern Area MPO, Peanut Belt RP | COMPLETED. | Division 1, 2, 3 |  | T | CONSTRUCTION | 2100000
F-5704 | Ferry | STI (Prioritization) | NC 12 | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY |  | CARTERET, HYDE | 1, 2 | Albemarle RPO, Down East RPO |  | Division 1, 2 |  | FBP | ENGINEERING | 1437000
F-5704 | Ferry | STI (Prioritization) | NC 12 | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY |  | CARTERET, HYDE | 1, 2 | Albemarle RPO, Down East RPO |  | Division 1, 2 |  | T | CONSTRUCTION | 23600000 | FY 2025: 11800000; FY 2026: 11800000
F-5704 | Ferry | STI (Prioritization) | NC 12 | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY |  | CARTERET, HYDE | 1, 2 | Albemarle RPO, Down East RPO |  | Division 1, 2 |  | FBP | CONSTRUCTION | 2000000 | FY 2025: 1000000; FY 2026: 1000000
F-5707 | Ferry | STI (Prioritization) | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. |  | BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | Region B |  | T | ENGINEERING | 406000
F-5707 | Ferry | STI (Prioritization) | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. |  | BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | Region B |  | FBP | ENGINEERING | 1625000
F-5707 | Ferry | STI (Prioritization) | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. |  | BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | Region B |  | T | CONSTRUCTION | 500000 | FY 2025: 500000
F-5707 | Ferry | STI (Prioritization) | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. |  | BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | Region B |  | T | CONSTRUCTION | 500000 | FY 2026: 500000
F-5707 | Ferry | STI (Prioritization) | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. |  | BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | Region B |  | FBP | CONSTRUCTION | 2000000 | FY 2026: 2000000
F-5707 | Ferry | STI (Prioritization) | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. |  | BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO |  | Region B |  | FBP | CONSTRUCTION | 2000000 | FY 2025: 2000000
FF-0001 | Ferry | Federal Lands Access Program | NC 12 | HATTERAS AND OCRACOKE ISLAND FERRY RAMP AND DOCK IMPROVEMENTS. |  | DARE, HYDE | 1 | Albemarle RPO | FLAP PROJECT NC 62. AWARDED $3.5M. | Exempt |  | FLAP | ENGINEERING | 1070000
FF-0001 | Ferry | Federal Lands Access Program | NC 12 | HATTERAS AND OCRACOKE ISLAND FERRY RAMP AND DOCK IMPROVEMENTS. |  | DARE, HYDE | 1 | Albemarle RPO | FLAP PROJECT NC 62. AWARDED $3.5M. | Exempt |  | FLAP | CONSTRUCTION | 2430000 | FY 2026: 2430000
FO-0001 | Ferry | Other | INTEGRATED MOBILITY DIVISION | CHERRY BRANCH FERRY TERMINAL - RURAL FERRY PROGRAM |  | CRAVEN | 2 | Down East RPO |  | Public Transit |  | T | PLANNING | 100000
FO-0001 | Ferry | Other | INTEGRATED MOBILITY DIVISION | CHERRY BRANCH FERRY TERMINAL - RURAL FERRY PROGRAM |  | CRAVEN | 2 | Down East RPO |  | Public Transit |  | FSRC | PLANNING | 400000
HA-0001 | Highway | Appalachian Development Highway System | NEW ROUTE | CONSTRUCT ACCESS ROAD INTO BURKE COUNTY INDUSTRIAL PARK. | 0.36 | BURKE | 13 | Greater Hickory MPO | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000 | Exempt |  | ADHSL | ENGINEERING | 200000
HA-0001 | Highway | Appalachian Development Highway System | NEW ROUTE | CONSTRUCT ACCESS ROAD INTO BURKE COUNTY INDUSTRIAL PARK. | 0.36 | BURKE | 13 | Greater Hickory MPO | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000 | Exempt |  | ADHSL | CONSTRUCTION | 1700000
HA-0002 | Highway | Appalachian Development Highway System | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | 0.41 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | Exempt |  | ADHSL | ENGINEERING | 200000
HA-0002 | Highway | Appalachian Development Highway System | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | 0.41 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | Exempt |  | ADHSL | RIGHT-OF-WAY | 10000
HA-0002 | Highway | Appalachian Development Highway System | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | 0.41 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610 | Exempt |  | ADHSL | CONSTRUCTION | 739000
HA-0003 | Highway | Appalachian Development Highway System | SR 1970 (COMMERCIAL BLVD) | CONSTRUCT ROADWAY EXTENSION TO INDUSTRIAL PARK. | 0.38 | HENDERSON | 14 | French Broad River MPO | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000 | Exempt |  | ADHSL | RIGHT-OF-WAY | 70000
HA-0003 | Highway | Appalachian Development Highway System | SR 1970 (COMMERCIAL BLVD) | CONSTRUCT ROADWAY EXTENSION TO INDUSTRIAL PARK. | 0.38 | HENDERSON | 14 | French Broad River MPO | UNDER CONSTRUCTION. ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000 | Exempt |  | ADHSL | CONSTRUCTION | 1830000
HA-0004 | Highway | Appalachian Development Highway System | US 441 | SR 1515 (HYATT ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND RIGHT-IN/RIGHT-OUT AT INGLES DEVELOPMENT SITE. | 0.5 | MACON | 14 | Southwestern RPO | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,900,000. UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 1046000
HA-0004 | Highway | Appalachian Development Highway System | US 441 | SR 1515 (HYATT ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND RIGHT-IN/RIGHT-OUT AT INGLES DEVELOPMENT SITE. | 0.5 | MACON | 14 | Southwestern RPO | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,900,000. UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 400000
HA-0004 | Highway | Appalachian Development Highway System | US 441 | SR 1515 (HYATT ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND RIGHT-IN/RIGHT-OUT AT INGLES DEVELOPMENT SITE. | 0.5 | MACON | 14 | Southwestern RPO | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,900,000. UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 454000
HA-0005 | Highway | Appalachian Development Highway System | NEW ROUTE | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | 0.14 | RUTHERFORD | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | Exempt |  | ADHSL | ENGINEERING | 15000
HA-0005 | Highway | Appalachian Development Highway System | NEW ROUTE | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | 0.14 | RUTHERFORD | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | Exempt |  | ADHSL | RIGHT-OF-WAY | 15000 | FY 2025: 15000
HA-0005 | Highway | Appalachian Development Highway System | NEW ROUTE | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | 0.14 | RUTHERFORD | 13 | Foothills RPO | ARC PROJECT NO. 20187, AWARD AMOUNT = $930,045 | Exempt |  | ADHSL | CONSTRUCTION | 900000 | FY 2026: 10000; FY 2027: 890000
HA-0006 | Highway | Appalachian Development Highway System | NORTHWEST DRIVE, AEV LANE | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AMERICAN EMERGENCY VEHICLES LANE FROM NORTHWEST DRIVE TO AMERICAN EMERGENCY VEHICLES FACILITY. WIDEN ROAD TO 12' LANES. | 0.49 | ASHE | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | Exempt |  | ADHSL | ENGINEERING | 47000
HA-0006 | Highway | Appalachian Development Highway System | NORTHWEST DRIVE, AEV LANE | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AMERICAN EMERGENCY VEHICLES LANE FROM NORTHWEST DRIVE TO AMERICAN EMERGENCY VEHICLES FACILITY. WIDEN ROAD TO 12' LANES. | 0.49 | ASHE | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | Exempt |  | ADHSL | RIGHT-OF-WAY | 60000 | FY 2025: 60000
HA-0006 | Highway | Appalachian Development Highway System | NORTHWEST DRIVE, AEV LANE | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AMERICAN EMERGENCY VEHICLES LANE FROM NORTHWEST DRIVE TO AMERICAN EMERGENCY VEHICLES FACILITY. WIDEN ROAD TO 12' LANES. | 0.49 | ASHE | 11 | High Country RPO | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000 | Exempt |  | ADHSL | CONSTRUCTION | 643000 | FY 2025: 643000
HA-0007 | Highway | Appalachian Development Highway System | NEW ROUTE | FAIRGROVE CHURCH ROAD SE. CONSTRUCT 0.27 MILE ACCESS ROAD TO CUL-DE-SAC. | 0.27 | CATAWBA | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | ADHS | ENGINEERING | 182000
HA-0007 | Highway | Appalachian Development Highway System | NEW ROUTE | FAIRGROVE CHURCH ROAD SE. CONSTRUCT 0.27 MILE ACCESS ROAD TO CUL-DE-SAC. | 0.27 | CATAWBA | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | L | ENGINEERING | 182000
HA-0007 | Highway | Appalachian Development Highway System | NEW ROUTE | FAIRGROVE CHURCH ROAD SE. CONSTRUCT 0.27 MILE ACCESS ROAD TO CUL-DE-SAC. | 0.27 | CATAWBA | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | ADHS | CONSTRUCTION | 818000
HA-0007 | Highway | Appalachian Development Highway System | NEW ROUTE | FAIRGROVE CHURCH ROAD SE. CONSTRUCT 0.27 MILE ACCESS ROAD TO CUL-DE-SAC. | 0.27 | CATAWBA | 12 | Greater Hickory MPO | "ADHS" FUNDS ARE ARC AREA DEVELOPMENT FUNDS. "L" FUNDS ARE PROVIDED BY THE CITY OF HICKORY. ARC PROJECT # 21035. | Exempt |  | L | CONSTRUCTION | 818000
HB-0001 | Highway | Bridges | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | TYRRELL | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | HFB | RIGHT-OF-WAY | 590000
HB-0001 | Highway | Bridges | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | TYRRELL | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | HFB | UTILITIES | 500000
HB-0001 | Highway | Bridges | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | TYRRELL | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | DP | CONSTRUCTION | 94100000 | FY 2025: 59478000; FY 2026: 34622000
HB-0001 | Highway | Bridges | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | TYRRELL | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | BFP | CONSTRUCTION | 242313000 | FY 2025: 0; FY 2026: 4400000; FY 2027: 99131000; FY 2028: 79304000; FY 2029: 59478000
HB-0001 | Highway | Bridges | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | TYRRELL | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 18783000 | FY 2025: 2817000; FY 2026: 4696000; FY 2027: 4696000; FY 2028: 3757000; FY 2029: 2817000
HB-0001 | Highway | Bridges | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | TYRRELL | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | PROTCT | CONSTRUCTION | 60109000 | FY 2025: 0; FY 2026: 60109000
HB-0001 | Highway | Bridges | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | TYRRELL | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | HFB | CONSTRUCTION | 45856000 | FY 2025: 15965000; FY 2026: 25509000; FY 2027: 1826000; FY 2028: 1461000; FY 2029: 1095000
HB-0001 | Highway | Bridges | US 64 | REPLACE BRIDGE 880007 OVER ALLIGATOR RIVER. | 4 | TYRRELL | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. DP FUNDS REPRESENT FEDERAL MEGA GRANT FUNDS. HF(M) FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. | Statewide Mobility |  | HF(M) | CONSTRUCTION | 60579000 | FY 2025: 0; FY 2026: 1100000; FY 2027: 24783000; FY 2028: 19826000; FY 2029: 14870000
HB-0001A | Highway | Other | US 64 | BROADBAND AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | 145.54 | MARTIN, EDGECOMBE, WASHINGTON, DARE, TYRRELL, NASH | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | DP | CONSTRUCTION | 15900000 | FY 2027: 265000; FY 2028: 11130000; FY 2029: 4505000
HB-0001A | Highway | Other | US 64 | BROADBAND AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | 145.54 | MARTIN, EDGECOMBE, WASHINGTON, DARE, TYRRELL, NASH | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 9540000 | FY 2027: 95000; FY 2028: 4013000; FY 2029: 3198000; FY 2030: 2234000
HB-0001A | Highway | Other | US 64 | BROADBAND AND ITS INSTALLATION FROM I-95 INTERCHANGE TO NC 12. | 145.54 | MARTIN, EDGECOMBE, WASHINGTON, DARE, TYRRELL, NASH | 1, 4 | Albemarle RPO, Mid-East RPO, Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 1060000 | FY 2027: 11000; FY 2028: 446000; FY 2029: 355000; FY 2030: 248000
HB-0002 | Highway | Bridges | I-40 | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | 0.25 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 2000000 | FY 2025: 200000
HB-0002 | Highway | Bridges | I-40 | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | 0.25 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | UTILITIES | 390000
HB-0002 | Highway | Bridges | I-40 | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | 0.25 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HIB | CONSTRUCTION | 23276000
HB-0002 | Highway | Bridges | I-40 | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | 0.25 | HAYWOOD | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | BFP | CONSTRUCTION | 15000000
HB-0003 | Highway | Bridges | I-40 | REPLACE BRIDGE 430239 OVER SR 1550 (INCINERATOR ROAD). | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 1000000 | FY 2025: 100000; FY 2026: 100000
HB-0003 | Highway | Bridges | I-40 | REPLACE BRIDGE 430239 OVER SR 1550 (INCINERATOR ROAD). | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | HFB | UTILITIES | 30000
HB-0003 | Highway | Bridges | I-40 | REPLACE BRIDGE 430239 OVER SR 1550 (INCINERATOR ROAD). | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | HFB | CONSTRUCTION | 27600000 | FY 2025: 13800000
HB-0004 | Highway | Bridges | I-40 | REPLACE BRIDGE 430243 OVER NC 215 (CHAMPION DRIVE). | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 1100000 | FY 2025: 100000; FY 2026: 100000
HB-0004 | Highway | Bridges | I-40 | REPLACE BRIDGE 430243 OVER NC 215 (CHAMPION DRIVE). | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | HFB | UTILITIES | 360000
HB-0004 | Highway | Bridges | I-40 | REPLACE BRIDGE 430243 OVER NC 215 (CHAMPION DRIVE). | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | HFB | CONSTRUCTION | 26100000 | FY 2025: 10440000; FY 2026: 10440000
HB-0005 | Highway | Bridges | I-40 | REPLACE BRIDGES 430205 AND 430208 OVER SR 1364 (COLEMAN MOUNTAIN ROAD). | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 2000000 | FY 2025: 52000; FY 2026: 315000; FY 2027: 315000; FY 2028: 315000; FY 2029: 1003000
HB-0005 | Highway | Bridges | I-40 | REPLACE BRIDGES 430205 AND 430208 OVER SR 1364 (COLEMAN MOUNTAIN ROAD). | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | BFP | UTILITIES | 170000 | FY 2025: 170000
HB-0005 | Highway | Bridges | I-40 | REPLACE BRIDGES 430205 AND 430208 OVER SR 1364 (COLEMAN MOUNTAIN ROAD). | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 17850000 | FY 2030: 8500000; FY 2031: 8500000; FY 2032: 850000
HB-0006 | Highway | Bridges | US 74 | REPLACE BRIDGE 430126 OVER I-40. | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 1000000 | 16000 | 99000 | 99000 | 99000 | 487000 |  |  |  |  | 100000 | 100000
HB-0006 | Highway | Bridges | US 74 | REPLACE BRIDGE 430126 OVER I-40. | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 9000000 | FY 2033: 4500000; FY 2034: 4500000
HB-0007 | Highway | Bridges | CHURCH ROAD) SR 1529 (MOUNT OLIVE | REPLACE BRIDGE 770299 AND 770300 OVER SADDLE TREE SWAMP. | 0.5 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | BGOFF | RIGHT-OF-WAY | 77000
HB-0007 | Highway | Bridges | CHURCH ROAD) SR 1529 (MOUNT OLIVE | REPLACE BRIDGE 770299 AND 770300 OVER SADDLE TREE SWAMP. | 0.5 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | BGOFF | UTILITIES | 185000
HB-0007 | Highway | Bridges | CHURCH ROAD) SR 1529 (MOUNT OLIVE | REPLACE BRIDGE 770299 AND 770300 OVER SADDLE TREE SWAMP. | 0.5 | ROBESON | 6 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS. | Division 6 |  | BGOFF | CONSTRUCTION | 1339000
HB-0008 | Highway | Bridges | CHURCH ROAD) SR 1214 (MOUNT PISGAH | REPLACE BRIDGE 420034 OVER UPPER LITTLE RIVER. | 0.25 | HARNETT | 6 | Mid-Carolina RPO |  | Division 6 |  | BGOFF | RIGHT-OF-WAY | 330000 | FY 2026: 330000
HB-0008 | Highway | Bridges | CHURCH ROAD) SR 1214 (MOUNT PISGAH | REPLACE BRIDGE 420034 OVER UPPER LITTLE RIVER. | 0.25 | HARNETT | 6 | Mid-Carolina RPO |  | Division 6 |  | BGOFF | CONSTRUCTION | 1900000 | FY 2028: 1246000; FY 2029: 654000
HB-0009 | Highway | Bridges | ROAD) SR 1800 (BLACKSMITH | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | 0.25 | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 |  | BGOFF | RIGHT-OF-WAY | 140000 | FY 2029: 140000
HB-0009 | Highway | Bridges | ROAD) SR 1800 (BLACKSMITH | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | 0.25 | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 |  | BGOFF | UTILITIES | 110000 | FY 2029: 110000
HB-0009 | Highway | Bridges | ROAD) SR 1800 (BLACKSMITH | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | 0.25 | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 |  | BGOFF | CONSTRUCTION | 1400000 | FY 2030: 1400000
HB-0010 | Highway | Bridges | SR 1716 (JACKIE LEE ROAD) | REPLACE BRIDGE 250091 OVER WADE CANAL. | 0.25 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGOFF | RIGHT-OF-WAY | 120000 | FY 2028: 120000
HB-0010 | Highway | Bridges | SR 1716 (JACKIE LEE ROAD) | REPLACE BRIDGE 250091 OVER WADE CANAL. | 0.25 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGOFF | CONSTRUCTION | 850000 | FY 2030: 850000
HB-0015 | Highway | Bridges | US 19/23/74 | REPLACE BRIDGE 430133 OVER JONES COVE ROAD (SR 1527). | 0.25 | HAYWOOD | 14 | French Broad River MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY | Highway Fund
HB-0016 | Highway | Bridges | NC 32 | PRESERVATION OF BRIDGE 930015 ON NC 32 OVER ALBEMARLE SOUND. | 3.5 | WASHINGTON | 1 | Albemarle RPO |  | Region A |  | BFP | CONSTRUCTION | 50001000 | FY 2027: 6051000; FY 2028: 17008000; FY 2029: 13538000; FY 2030: 12192000; FY 2031: 1212000
HB-0017 | Highway | Bridges | US 64 | PRESERVATION OF BRIDGE 270009 ON US 64 IN MANNS HARBOR. | 2.85 | DARE | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | BFP | CONSTRUCTION | 38823000 | FY 2025: 11250000
HB-0018 | Highway | Bridges | I-40 | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 700000 | FY 2026: 700000
HB-0018 | Highway | Bridges | I-40 | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | UTILITIES | 700000 | FY 2026: 700000
HB-0018 | Highway | Bridges | I-40 | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 59900000 | FY 2028: 599000; FY 2029: 20965000; FY 2030: 19767000; FY 2031: 13777000; FY 2032: 4792000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 222000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 890000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000 | FY 2025: 13000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 502000 | FY 2025: 502000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 235000 | FY 2025: 235000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 94000 | FY 2025: 94000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 196000 | FY 2025: 196000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 1293000 | FY 2027: 1293000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 7328000 | FY 2027: 7328000
HB-0020 | Highway | Bridges | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER YADKIN RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 5179000 | FY 2027: 5179000
HB-0021 | Highway | Municipal Bridge | OXFORD ROAD | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | 0.25 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | BFPOFF | RIGHT-OF-WAY | 50000
HB-0021 | Highway | Municipal Bridge | OXFORD ROAD | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | 0.25 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | BFPOFF | UTILITIES | 143000
HB-0021 | Highway | Municipal Bridge | OXFORD ROAD | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | 0.25 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 2 |  | BFPOFF | CONSTRUCTION | 1900000
HB-0022 | Highway | Municipal Bridge | ROCK SPRINGS ROAD | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | 0.25 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | BFPOFF | RIGHT-OF-WAY | 100000 | FY 2029: 100000
HB-0022 | Highway | Municipal Bridge | ROCK SPRINGS ROAD | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | 0.25 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | BFPOFF | UTILITIES | 126000 | FY 2029: 126000
HB-0022 | Highway | Municipal Bridge | ROCK SPRINGS ROAD | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | 0.25 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | BFPOFF | CONSTRUCTION | 2277000 | FY 2030: 1934000; FY 2031: 343000
HB-0023 | Highway | Bridges | SR 1876 (SONOMA ROAD/ MAX THOMPSON ROAD) | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. REPLACE BRIDGE 430170 OVER EAST FORK PIGEON RIVER. | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 320000
HB-0023 | Highway | Bridges | SR 1876 (SONOMA ROAD/ MAX THOMPSON ROAD) | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. REPLACE BRIDGE 430170 OVER EAST FORK PIGEON RIVER. | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | BGOFF | UTILITIES | 300000 | FY 2025: 300000
HB-0023 | Highway | Bridges | SR 1876 (SONOMA ROAD/ MAX THOMPSON ROAD) | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. REPLACE BRIDGE 430170 OVER EAST FORK PIGEON RIVER. | 0.25 | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 5000000 | FY 2025: 5000000
HB-0024 | Highway | Bridges | US-401 | REPLACE BRIDGE 340056 OVER SANDY CREEK. | 0.25 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | BGLT5 | RIGHT-OF-WAY | 60000 | FY 2027: 60000
HB-0024 | Highway | Bridges | US-401 | REPLACE BRIDGE 340056 OVER SANDY CREEK. | 0.25 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | BGLT5 | UTILITIES | 180000 | FY 2027: 180000
HB-0024 | Highway | Bridges | US-401 | REPLACE BRIDGE 340056 OVER SANDY CREEK. | 0.25 | FRANKLIN | 5 | Capital Area MPO |  | Division 5 |  | BGLT5 | CONSTRUCTION | 3700000 | FY 2029: 3700000
HB-0025 | Highway | Bridges | SR 1004 (POORS FORD ROAD) | REPLACE BRIDGE 740087 OVER BROAD RIVER. | 0.25 | POLK | 14 | Foothills RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 260000 | FY 2025: 260000
HB-0025 | Highway | Bridges | SR 1004 (POORS FORD ROAD) | REPLACE BRIDGE 740087 OVER BROAD RIVER. | 0.25 | POLK | 14 | Foothills RPO |  | Division 14 |  | BGOFF | UTILITIES | 260000 | FY 2025: 260000
HB-0025 | Highway | Bridges | SR 1004 (POORS FORD ROAD) | REPLACE BRIDGE 740087 OVER BROAD RIVER. | 0.25 | POLK | 14 | Foothills RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 5200000 | FY 2028: 5200000
HB-0026 | Highway | Bridges | SR 1533 (EVERETT ROAD) | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | 0.25 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 200000 | FY 2025: 200000
HB-0026 | Highway | Bridges | SR 1533 (EVERETT ROAD) | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | 0.25 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | UTILITIES | 200000 | FY 2025: 200000
HB-0026 | Highway | Bridges | SR 1533 (EVERETT ROAD) | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | 0.25 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 4000000 | FY 2028: 4000000
HB-0027 | Highway | Bridges | SR 1355 (PANTHER CREEK ROAD) | REPLACE BRIDGE 430206 OVER FINES CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 50000 | FY 2025: 50000
HB-0027 | Highway | Bridges | SR 1355 (PANTHER CREEK ROAD) | REPLACE BRIDGE 430206 OVER FINES CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | UTILITIES | 50000 | FY 2025: 50000
HB-0027 | Highway | Bridges | SR 1355 (PANTHER CREEK ROAD) | REPLACE BRIDGE 430206 OVER FINES CREEK. | 0.25 | HAYWOOD | 14 | Land-of-Sky RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1000000 | FY 2028: 1000000
HB-0029 | Highway | Bridges | SR 1179 (BRIDGE STREET) | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | RIGHT-OF-WAY | 100000 | FY 2027: 100000
HB-0029 | Highway | Bridges | SR 1179 (BRIDGE STREET) | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | UTILITIES | 100000 | FY 2027: 100000
HB-0029 | Highway | Bridges | SR 1179 (BRIDGE STREET) | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGOFF | CONSTRUCTION | 2000000 | FY 2029: 2000000
HB-0030 | Highway | Bridges | SR 1679 (PEEKS CREEK ROAD) | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | 0.25 | MACON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 480000 | FY 2025: 480000
HB-0030 | Highway | Bridges | SR 1679 (PEEKS CREEK ROAD) | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | 0.25 | MACON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | UTILITIES | 360000 | FY 2025: 360000
HB-0030 | Highway | Bridges | SR 1679 (PEEKS CREEK ROAD) | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | 0.25 | MACON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 2700000 | FY 2026: 2700000
HB-0031 | Highway | Bridges | THIRD STREET; FOURTH STREET; FIFTH STREET; | REPLACE BRIDGES 330185, 330191, AND 330203 OVER US 52 / US 311 IN DOWNTOWN WINSTON-SALEM. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | RIGHT-OF-WAY | 950000 | FY 2026: 950000
HB-0031 | Highway | Bridges | THIRD STREET; FOURTH STREET; FIFTH STREET; | REPLACE BRIDGES 330185, 330191, AND 330203 OVER US 52 / US 311 IN DOWNTOWN WINSTON-SALEM. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | UTILITIES | 50000 | FY 2026: 50000
HB-0031 | Highway | Bridges | THIRD STREET; FOURTH STREET; FIFTH STREET; | REPLACE BRIDGES 330185, 330191, AND 330203 OVER US 52 / US 311 IN DOWNTOWN WINSTON-SALEM. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 9500000 | FY 2027: 95000; FY 2028: 5477000; FY 2029: 3928000
HB-0032 | Highway | Bridges | SR 1004 (HUDSON CHAPEL ROAD) | REPLACE BRIDGE 480081 CATAWBA RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | RIGHT-OF-WAY | 100000 | FY 2025: 100000
HB-0032 | Highway | Bridges | SR 1004 (HUDSON CHAPEL ROAD) | REPLACE BRIDGE 480081 CATAWBA RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | UTILITIES | 250000 | FY 2025: 250000
HB-0032 | Highway | Bridges | SR 1004 (HUDSON CHAPEL ROAD) | REPLACE BRIDGE 480081 CATAWBA RIVER. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGOFF | CONSTRUCTION | 20400000 | FY 2028: 10200000; FY 2029: 10200000
HB-0033 | Highway | Bridges | POLO ROAD | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFP | RIGHT-OF-WAY | 300000 | FY 2027: 300000
HB-0033 | Highway | Bridges | POLO ROAD | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFP | UTILITIES | 300000 | FY 2027: 300000
HB-0033 | Highway | Bridges | POLO ROAD | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFP | CONSTRUCTION | 6000000 | FY 2029: 778000; FY 2030: 4259000; FY 2031: 963000
HB-0034 | Highway | Bridges | SR 1007 (PLANK ROAD) | REPLACE BRIDGE 180169 OVER DEEP RIVER. | 0.25 | CHATHAM, LEE | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | RIGHT-OF-WAY | 325000 | FY 2030: 325000
HB-0034 | Highway | Bridges | SR 1007 (PLANK ROAD) | REPLACE BRIDGE 180169 OVER DEEP RIVER. | 0.25 | CHATHAM, LEE | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | UTILITIES | 325000 | FY 2030: 325000
HB-0034 | Highway | Bridges | SR 1007 (PLANK ROAD) | REPLACE BRIDGE 180169 OVER DEEP RIVER. | 0.25 | CHATHAM, LEE | 8 | Central Pines RPO |  | Division 8 |  | BGOFF | CONSTRUCTION | 6500000 | FY 2032: 6500000
HB-0035 | Highway | Bridges | SR 1535 (PRICE ROAD) | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | RIGHT-OF-WAY | 410000 | FY 2025: 410000
HB-0035 | Highway | Bridges | SR 1535 (PRICE ROAD) | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | UTILITIES | 300000 | FY 2025: 300000
HB-0035 | Highway | Bridges | SR 1535 (PRICE ROAD) | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | 0.25 | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | BGOFF | CONSTRUCTION | 4500000 | FY 2026: 4500000
HB-0036 | Highway | Bridges | SIXTEENTH STREET | REPLACE BRIDGE 330390 OVER RAIL CORRIDOR AND BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | RIGHT-OF-WAY | 210000 | FY 2026: 210000
HB-0036 | Highway | Bridges | SIXTEENTH STREET | REPLACE BRIDGE 330390 OVER RAIL CORRIDOR AND BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | UTILITIES | 210000 | FY 2026: 210000
HB-0036 | Highway | Bridges | SIXTEENTH STREET | REPLACE BRIDGE 330390 OVER RAIL CORRIDOR AND BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGOFF | CONSTRUCTION | 4200000 | FY 2027: 42000; FY 2028: 3316000; FY 2029: 842000
HB-0037 | Highway | Bridges | SR 1679 (GOLD MINE ROAD) | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | 0.25 | MACON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | RIGHT-OF-WAY | 50000 | FY 2026: 50000
HB-0037 | Highway | Bridges | SR 1679 (GOLD MINE ROAD) | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | 0.25 | MACON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | UTILITIES | 50000 | FY 2026: 50000
HB-0037 | Highway | Bridges | SR 1679 (GOLD MINE ROAD) | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | 0.25 | MACON | 14 | Southwestern RPO |  | Division 14 |  | BGOFF | CONSTRUCTION | 1000000 | FY 2027: 1000000
HB-0038 | Highway | Bridges | SR 1745 (BEND OF THE RIVER ROAD) | REPLACE BRIDGE 630110 OVER TAR RIVER RESERVOIR. | 0.25 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | BGOFF | RIGHT-OF-WAY | 80000 | FY 2026: 80000
HB-0038 | Highway | Bridges | SR 1745 (BEND OF THE RIVER ROAD) | REPLACE BRIDGE 630110 OVER TAR RIVER RESERVOIR. | 0.25 | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | BGOFF | CONSTRUCTION | 6500000 | FY 2027: 3705000; FY 2028: 2795000
HB-0039 | Highway | STI (Prioritization) | US 17/76/421 | REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. TOLL PROJECT. | 0.8 | NEW HANOVER | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 48515000 | FY 2029: 24258000; FY 2030: 24257000
HB-0039 | Highway | STI (Prioritization) | US 17/76/421 | REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. TOLL PROJECT. | 0.8 | NEW HANOVER | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | BOND R | UTILITIES | 3688000 | FY 2029: 3688000
HB-0039 | Highway | STI (Prioritization) | US 17/76/421 | REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. TOLL PROJECT. | 0.8 | NEW HANOVER | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | NHP | GARVEE CON | 109395000 | FY 2033: 7293000; FY 2034: 7293000; FY 2035: 7293000 | 87516000
HB-0039 | Highway | STI (Prioritization) | US 17/76/421 | REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. TOLL PROJECT. | 0.8 | NEW HANOVER | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | DP | CONSTRUCTION | 242000000 | FY 2029: 101240000; FY 2030: 101240000; FY 2031: 39520000
HB-0039 | Highway | STI (Prioritization) | US 17/76/421 | REPLACE BRIDGE 640013 (CAPE FEAR MEMORIAL BRIDGE) OVER CAPE FEAR RIVER. TOLL PROJECT. | 0.8 | NEW HANOVER | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT BRIDGE INVESTMENT PROGRAM - LARGE BRIDGE GRANT FUNDING. GARVEE BOND FUNDING: $85M FOR CONSTRUCTION, PAYBACK FY 2033-2047. | Statewide Mobility |  | BOND R | CONSTRUCTION | 179200000 | FY 2031: 61720000; FY 2032: 101240000; FY 2033: 16240000
HB-0040 | Highway | Bridges | US 76 AND US 74 | REPLACE BRIDGES 640021, 640022, AND 640024 IN NEW HANOVER COUNTY. | 0.9 | NEW HANOVER | 3 | Wilmington Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
HB-0041 | Highway | Bridges | I-77 | REPLACE BRIDGES 480133 AND 480128 OVER THIRD CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | RIGHT-OF-WAY | 500000 | FY 2026: 500000
HB-0041 | Highway | Bridges | I-77 | REPLACE BRIDGES 480133 AND 480128 OVER THIRD CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | UTILITIES | 500000 | FY 2026: 500000
HB-0041 | Highway | Bridges | I-77 | REPLACE BRIDGES 480133 AND 480128 OVER THIRD CREEK. | 0.25 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 10000000 | FY 2028: 100000; FY 2029: 6218000; FY 2030: 3682000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 25000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 100000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 20000 | FY 2025: 20000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 101000 | FY 2025: 101000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 79000 | FY 2025: 79000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 11000 | FY 2025: 11000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 59000 | FY 2025: 59000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 146000 | FY 2026: 146000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 771000 | FY 2026: 771000
HB-0043 | Highway | Bridges | SR 1523 | REPLACE BRIDGE 040047 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 583000 | FY 2026: 583000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 42000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 167000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 21000 | FY 2025: 21000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 146000 | FY 2025: 146000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 124000 | FY 2025: 124000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000 | FY 2025: 10000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 243000 | FY 2026: 243000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 986000 | FY 2026: 986000
HB-0044 | Highway | Bridges | (MCNEIL ROAD) SR 1644 | REPLACE BRIDGE 040093 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 971000 | FY 2026: 971000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 12000 | FY 2025: 12000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 192000 | FY 2025: 192000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 67000 | FY 2025: 67000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000 | FY 2025: 12000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 28000 | FY 2025: 28000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 791000 | FY 2026: 791000
HB-0045 | Highway | Bridges | SR 1609 | REPLACE BRIDGE 040183 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 647000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 36000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 145000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 19000 | FY 2025: 19000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 87000 | FY 2025: 87000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 114000 | FY 2025: 114000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000 | FY 2025: 10000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 210000 | FY 2026: 210000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1248000 | FY 2026: 1248000
HB-0046 | Highway | Bridges | SR 1105 | REPLACE BRIDGE 040226 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 841000 | FY 2026: 841000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 22000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 89000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000 | FY 2025: 13000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 116000 | FY 2025: 116000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 80000 | FY 2025: 80000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 9000 | FY 2025: 9000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 11000 | FY 2025: 11000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 129000 | FY 2026: 129000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 953000 | FY 2026: 953000
HB-0047 | Highway | Bridges | SR 1528 | REPLACE BRIDGE 040304 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 517000 | FY 2026: 517000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000 | FY 2025: 13000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 294000 | FY 2025: 294000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 92000 | FY 2025: 92000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000 | FY 2025: 12000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 8000 | FY 2025: 8000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 791000 | FY 2026: 791000
HB-0048 | Highway | Bridges | SR 1606 | REPLACE BRIDGE 040343 OVER CRANBERRY CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 647000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 56000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 222000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 11000 | FY 2025: 11000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 19000 | FY 2025: 19000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 110000 | FY 2025: 110000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 24000 | FY 2025: 24000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 26000 | FY 2025: 26000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 324000 | FY 2026: 324000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 682000 | FY 2026: 682000
HB-0049 | Highway | Bridges | SR 1602 | REPLACE BRIDGE 040351 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 1295000 | FY 2026: 1295000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 56000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 222000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 172000 | FY 2025: 172000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 800000 | FY 2025: 800000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 728000 | FY 2025: 728000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000 | FY 2025: 10000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 323000 | FY 2026: 323000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 2082000 | FY 2026: 2082000
HB-0050 | Highway | Bridges | SR 1563 | REPLACE BRIDGE 040463 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 1295000 | FY 2026: 1295000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 42000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 167000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 20000 | FY 2025: 20000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 65000 | FY 2025: 65000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 124000 | FY 2025: 124000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000 | FY 2025: 10000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 243000 | FY 2026: 243000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 971000 | FY 2026: 971000
HB-0051 | Highway | Bridges | (BOGGS ROAD) SR 1159 | REPLACE BRIDGE 040466 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 971000 | FY 2026: 971000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 36000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 145000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 17000 | FY 2025: 17000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 84000 | FY 2025: 84000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 108000 | FY 2025: 108000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 15000 | FY 2025: 15000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 210000 | FY 2026: 210000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1348000 | FY 2026: 1348000
HB-0052 | Highway | Bridges | SR 1104 | REPLACE BRIDGE 040477 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 841000 | FY 2026: 841000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 25000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 100000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 20000 | FY 2025: 20000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 168000 | FY 2025: 168000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 92000 | FY 2025: 92000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 11000 | FY 2025: 11000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 29000 | FY 2025: 29000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 146000 | FY 2026: 146000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 583000 | FY 2026: 583000
HB-0053 | Highway | Bridges | (ED LITTLE ROAD) SR 1126 | REPLACE BRIDGE 040480 OVER NORTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 972000 | FY 2026: 972000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 56000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 222000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000 | FY 2025: 13000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 84000 | FY 2025: 84000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 53000 | FY 2025: 53000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 24000 | FY 2025: 24000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 6000 | FY 2025: 6000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 324000 | FY 2026: 324000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 2082000 | FY 2026: 2082000
HB-0054 | Highway | Bridges | SR 1222 | REPLACE BRIDGE 040509 OVER SOUTH FORK NEW RIVER. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 1295000 | FY 2026: 1295000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 15000 | FY 2025: 15000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 155000 | FY 2025: 155000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 100000 | FY 2025: 100000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000 | FY 2025: 10000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 991000 | FY 2026: 991000
HB-0055 | Highway | Bridges | SR 1326 | REPLACE BRIDGE 050091 OVER ELK RIVER. | 0.25 | AVERY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 647000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 12000 | FY 2025: 12000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 15000 | FY 2025: 15000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 243000 | FY 2025: 243000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000 | FY 2025: 12000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 68000 | FY 2025: 68000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 991000 | FY 2026: 991000
HB-0056 | Highway | Bridges | SR 1514 | REPLACE BRIDGE 130130 OVER YADKIN RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 647000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 19000 | FY 2025: 19000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 155000 | FY 2025: 155000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 116000 | FY 2025: 116000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000 | FY 2025: 10000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1791000 | FY 2027: 1791000
HB-0057 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130185 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 647000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000 | FY 2025: 13000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 94000 | FY 2025: 94000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 53000 | FY 2025: 53000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000 | FY 2025: 12000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 48000 | FY 2025: 48000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0058 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130186 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 2137000 | FY 2026: 2137000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | ENGINEERING | 28000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | ENGINEERING | 111000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | RIGHT-OF-WAY | 26000 | FY 2025: 26000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | RIGHT-OF-WAY | 94000 | FY 2025: 94000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | UTILITIES | 12000 | FY 2025: 12000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | UTILITIES | 28000 | FY 2025: 28000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | CONSTRUCTION | 161000 | FY 2026: 161000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | BGOFF | CONSTRUCTION | 1391000 | FY 2026: 1391000
HB-0059 | Highway | Bridges | (OLD JOHNS RIVER ROAD) SR 1356 | REPLACE BRIDGE 130275 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | CONSTRUCTION | 648000 | FY 2026: 648000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 36000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 145000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 17000 | FY 2025: 17000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 167000 | FY 2025: 167000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 85000 | FY 2025: 85000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 15000 | FY 2025: 15000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 45000 | FY 2025: 45000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 210000 | FY 2026: 210000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1348000 | FY 2027: 1348000
HB-0060 | Highway | Bridges | SR 1356 | REPLACE BRIDGE 130317 OVER JOHNS RIVER. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 841000 | FY 2026: 841000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | ENGINEERING | 22000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | ENGINEERING | 89000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | RIGHT-OF-WAY | 26000 | FY 2025: 26000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | RIGHT-OF-WAY | 114000 | FY 2025: 114000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | UTILITIES | 9000 | FY 2025: 9000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | UTILITIES | 31000 | FY 2025: 31000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | DP | CONSTRUCTION | 130000 | FY 2026: 130000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | BGOFF | CONSTRUCTION | 852000 | FY 2026: 852000
HB-0061 | Highway | Bridges | SR 1574 | REPLACE BRIDGE 130349 OVER JONES CREEK. | 0.25 | CALDWELL | 11 | Greater Hickory MPO | DP REPRESENTS RAISE GRANT FUNDS | Exempt |  | HFB | CONSTRUCTION | 518000 | FY 2026: 518000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 17000 | FY 2025: 17000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 414000 | FY 2025: 414000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 69000 | FY 2025: 69000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000 | FY 2025: 12000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 48000 | FY 2025: 48000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1191000 | FY 2026: 1191000
HB-0062 | Highway | Bridges | (ALDRIDGE ROAD) SR 1594 | REPLACE BRIDGE 940319 OVER WATAUGA RIVER. | 0.25 | WATAUGA | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 647000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000 | FY 2025: 13000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 57000 | FY 2025: 57000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000 | FY 2025: 12000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 8000 | FY 2025: 8000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 791000 | FY 2026: 791000
HB-0063 | Highway | Bridges | SR 1559 | REPLACE BRIDGE 960341 OVER MID FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 647000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 22000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 89000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 26000 | FY 2025: 26000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 74000 | FY 2025: 74000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 29000 | FY 2025: 29000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 9000 | FY 2025: 9000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 31000 | FY 2025: 31000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 129000 | FY 2026: 129000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 753000 | FY 2026: 753000
HB-0064 | Highway | Bridges | (SHEETS GAP ROAD) SR 1567 | REPLACE BRIDGE 960655 OVER WINGLER CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 519000 | FY 2026: 519000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 25000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 100000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 13000 | FY 2025: 13000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 181000 | FY 2025: 181000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 86000 | FY 2025: 86000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 11000 | FY 2025: 11000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 9000 | FY 2025: 9000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 145000 | FY 2026: 145000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1172000 | FY 2026: 1172000
HB-0065 | Highway | Bridges | SR 1170 | REPLACE BRIDGE 960691 OVER STONY FORK CREEK. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 583000 | FY 2026: 583000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 11000 | FY 2025: 11000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 77000 | FY 2025: 77000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 42000 | FY 2025: 42000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 12000 | FY 2025: 12000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 48000 | FY 2025: 48000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 1291000 | FY 2026: 1291000
HB-0066 | Highway | Bridges | SR 1355 | REPLACE BRIDGE 960340 OVER SOUTH FORK REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 666000 | FY 2026: 666000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 12000 | FY 2025: 12000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 98000 | FY 2025: 98000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 89000 | FY 2025: 89000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000 | FY 2025: 10000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 891000 | FY 2026: 891000
HB-0067 | Highway | Bridges | (SCENIC VALLEY ROAD) SR 1433 | REPLACE BRIDGE 020082 OVER BRUSH CREEK. | 0.25 | ALLEGHANY | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 647000 | FY 2026: 647000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 28000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 111000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 15000 | FY 2025: 15000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | RIGHT-OF-WAY | 25000 | FY 2025: 25000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 100000 | FY 2025: 100000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 10000 | FY 2025: 10000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 162000 | FY 2026: 162000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BGOFF | CONSTRUCTION | 591000 | FY 2026: 591000
HB-0068 | Highway | Bridges | (HELTON ROAD) SR 1527 | REPLACE BRIDGE 040048 OVER HELTON CREEK. | 0.25 | ASHE | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 648000 | FY 2026: 648000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | ENGINEERING | 333000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | ENGINEERING | 1334000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 106000 | FY 2025: 106000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BFP | RIGHT-OF-WAY | 3472000 | FY 2025: 3472000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | RIGHT-OF-WAY | 422000 | FY 2025: 422000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | UTILITIES | 142000 | FY 2025: 142000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BFP | UTILITIES | 692000 | FY 2025: 692000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | UTILITIES | 566000 | FY 2025: 566000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | DP | CONSTRUCTION | 1942000 | FY 2027: 1942000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | BFP | CONSTRUCTION | 10990000 | FY 2027: 10990000
HB-0069 | Highway | Bridges | US 421 BUSINESS | REPLACE BRIDGE 960012 OVER REDDIES RIVER. | 0.25 | WILKES | 11 | High Country RPO | DP REPRESENTS RAISE GRANT FUNDS. | Exempt |  | HFB | CONSTRUCTION | 7768000 | FY 2027: 7768000
HB-0070 | Highway | Bridges | US 13 / US 17 | OVER ROANOKE RIVER OVERFLOW IN BERTIE COUNTY. REPAIR BRIDGES 070155, 070156, 070158, AND 070159. | 1 | BERTIE | 1 | Peanut Belt RPO |  | Statewide Mobility |  | BFP | CONSTRUCTION | 5000000 | FY 2025: 50000; FY 2026: 3708000; FY 2027: 1242000
HB-0071 | Highway | Bridges | SR 2207 (FAITH ROCK ROAD) | REPLACE BRIDGE 750176 OVER CREEK OFF DEEP RIVER. |  | RANDOLPH | 8 | Piedmont Triad RPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. | Division 8 |  | BGOFF | RIGHT-OF-WAY | 20000 | FY 2025: 20000
HB-0071 | Highway | Bridges | SR 2207 (FAITH ROCK ROAD) | REPLACE BRIDGE 750176 OVER CREEK OFF DEEP RIVER. |  | RANDOLPH | 8 | Piedmont Triad RPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. | Division 8 |  | HP | CONSTRUCTION | 409000 | FY 2026: 409000
HB-0071 | Highway | Bridges | SR 2207 (FAITH ROCK ROAD) | REPLACE BRIDGE 750176 OVER CREEK OFF DEEP RIVER. |  | RANDOLPH | 8 | Piedmont Triad RPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. | Division 8 |  | BGOFF | CONSTRUCTION | 289000 | FY 2026: 289000
HB-0071 | Highway | Bridges | SR 2207 (FAITH ROCK ROAD) | REPLACE BRIDGE 750176 OVER CREEK OFF DEEP RIVER. |  | RANDOLPH | 8 | Piedmont Triad RPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC114. | Division 8 |  | T(M) | CONSTRUCTION | 102000 | FY 2026: 102000
HB-0072 | Highway | Bridges | SR 1629 (FLAT ROCK ROAD) | REPLACE BRIDGE 380199 OVER FORK CREEK. |  | GRANVILLE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC077. | Division 5 |  | HP | CONSTRUCTION | 770000 | FY 2026: 770000
HB-0072 | Highway | Bridges | SR 1629 (FLAT ROCK ROAD) | REPLACE BRIDGE 380199 OVER FORK CREEK. |  | GRANVILLE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC077. | Division 5 |  | BGOFF | CONSTRUCTION | 1238000 | FY 2026: 1238000
HB-0072 | Highway | Bridges | SR 1629 (FLAT ROCK ROAD) | REPLACE BRIDGE 380199 OVER FORK CREEK. |  | GRANVILLE | 5 | Capital Area MPO | HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC077. | Division 5 |  | T(M) | CONSTRUCTION | 193000 | FY 2026: 193000
HB-0088 | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | CONSTRUCTION | 218897000 | 5456000 | 0 | 5957000 | 0 | 584000 | 18470000 | 25740000 | 31377000 | 43187000 | 44063000 | 44063000
HB-0088DIV | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BFP | CONSTRUCTION | 91692000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7894000 | 24986000 | 28732000 | 30080000
HB-0088REG | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | BFP | CONSTRUCTION | 91692000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7894000 | 24986000 | 28732000 | 30080000
HB-0088SW | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | BFP | CONSTRUCTION | 122255000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10524000 | 33314000 | 38309000 | 40108000
HB-0099A | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HB-0099ADIV | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 85800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000
HB-0099AREG | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 85800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000
HB-0099ASW | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 114400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000
HB-0099B | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HB-0099BDIV | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 6600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
HB-0099C | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HB-0099CDIV | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 8580000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000
HB-0099CREG | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 8580000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000 | 780000
HB-0099CSW | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 11440000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000
HB-8888 | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | CONSTRUCTION | 6844000
HB-8888DIV | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BFP | CONSTRUCTION | 0
HB-8888REG | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | BFP | CONSTRUCTION | 0
HB-8888SW | Highway | Bridges | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | BFP | CONSTRUCTION | 0
HB-9999A | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HB-9999ADIV | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 31200000
HB-9999AREG | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 31200000
HB-9999ASW | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 41600000
HB-9999B | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HB-9999BDIV | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 2400000
HB-9999C | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HB-9999CDIV | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 3120000
HB-9999CREG | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 3120000
HB-9999CSW | Highway | Bridges | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 4160000
HE-0001 | Highway | Economic Development | I-26 | CONSTRUCT NEW INTERCHANGE NEAR AN ACCESS ROAD NEAR MILEMARKER 35, CONNECTING TO FREDERICK LAW OLMSTEAD WAY EAST. | 1 | BUNCOMBE | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. HIGHWAY FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY. | Exempt |  | HF | ENGINEERING | 4274000
HE-0001 | Highway | Economic Development | I-26 | CONSTRUCT NEW INTERCHANGE NEAR AN ACCESS ROAD NEAR MILEMARKER 35, CONNECTING TO FREDERICK LAW OLMSTEAD WAY EAST. | 1 | BUNCOMBE | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. HIGHWAY FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY. | Exempt |  | HF | RIGHT-OF-WAY | 200000
HE-0001 | Highway | Economic Development | I-26 | CONSTRUCT NEW INTERCHANGE NEAR AN ACCESS ROAD NEAR MILEMARKER 35, CONNECTING TO FREDERICK LAW OLMSTEAD WAY EAST. | 1 | BUNCOMBE | 13 | French Broad River MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR PRATT AND WHITNEY. HIGHWAY FUNDS ARE AN APPROPRIATION BY THE GENERAL ASSEMBLY. | Exempt |  | HF | MITIGATION | 84000
HE-0001A | Highway | Economic Development | I-26 | MILEMARKER 35. CONSTRUCT INTERCHANGE. |  | BUNCOMBE | 13 | French Broad River MPO |  | Exempt |  | HF | CONSTRUCTION | 24360000
HE-0001B | Highway | Economic Development | NEW ROUTE | FREDERICK LAW OLMSTEAD WAY EAST TO I-26. CONSTRUCT TWO LANE ROAD WITH SIDEWALK. |  | BUNCOMBE | 13 | French Broad River MPO |  | Exempt |  | ADHSL | CONSTRUCTION | 2500000 | FY 2025: 2500000
HE-0001B | Highway | Economic Development | NEW ROUTE | FREDERICK LAW OLMSTEAD WAY EAST TO I-26. CONSTRUCT TWO LANE ROAD WITH SIDEWALK. |  | BUNCOMBE | 13 | French Broad River MPO |  | Exempt |  | HF | CONSTRUCTION | 8082000 | FY 2025: 8082000
HE-0002 | Highway | Economic Development | NEW ROUTE; SR 1152 (HOLLY SPRINGS - NEW HILL ROAD) | NEW ROUTE INTERSECTING GREEN OAKS PARKWAY BETWEEN THOMAS MILL ROAD AND NC 55, SR 1153 INTERSECTION WITH BENNET KNOLL PARKWAY, AND SR 1152 INTERSECTION WITH SR 1153 IN HOLLY SPRINGS. CONSTRUCT ACCESS ROAD AND INTERSECTION IMPROVEMENTS. | 1.55 | WAKE | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR FUJIFILM DIOSYNTH BIOTECHNOLOGIES. | Division 5 |  | T | CONSTRUCTION | 9691000 | FY 2025: 2234000; FY 2026: 5219000; FY 2027: 2238000
HE-0003 | Highway | Economic Development | SR 1710 (GRACE DRIVE/ WATKINS DRIVE) AND SR 1737 | FROM US-158 TO NORTH OF SR 1734 (KENNAMETAL DRIVE). WIDEN TO FOUR LANES. REALIGN SR 1737 (POWER PLACE) AND US-158 INTERSECTION. | 0.72 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR ROSEBURG FOREST PRODUCTS. | Division 4 |  | T | CONSTRUCTION | 2050000
HE-0004 | Highway | Economic Development | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 3.18 | RANDOLPH | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | HF | RIGHT-OF-WAY | 5000000
HE-0004 | Highway | Economic Development | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 3.18 | RANDOLPH | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | HF | UTILITIES | 2000000
HE-0004 | Highway | Economic Development | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 3.18 | RANDOLPH | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | HF | MITIGATION | 1000000
HE-0004 | Highway | Economic Development | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 3.18 | RANDOLPH | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | T | CONSTRUCTION | 10000000 | FY 2025: 10000000
HE-0004 | Highway | Economic Development | VARIOUS | CONSTRUCT ROAD ENHANCEMENTS AND WETLANDS MITIGATION AT THE RANDOLPH COUNTY MEGASITE NEAR LIBERTY. | 3.18 | RANDOLPH | 8 | Piedmont Triad RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR TOYOTA BATTERY. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Division 8 |  | HF | CONSTRUCTION | 27000000
HE-0005 | Highway | Economic Development | VARIOUS | CONSTUCT ROAD IMPROVEMENTS AND WETLANDS MITIGATION AT THE PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | Exempt |  | HF | RIGHT-OF-WAY | 1000000
HE-0005 | Highway | Economic Development | VARIOUS | CONSTUCT ROAD IMPROVEMENTS AND WETLANDS MITIGATION AT THE PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | Exempt |  | HF | UTILITIES | 500000
HE-0005 | Highway | Economic Development | VARIOUS | CONSTUCT ROAD IMPROVEMENTS AND WETLANDS MITIGATION AT THE PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. |  | GUILFORD | 7 | Greensboro Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOOM SUPERSONIC. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. UNDER CONSTRUCTION | Exempt |  | HF | CONSTRUCTION | 30000000 | FY 2025: 6199000; FY 2026: 1766000
HE-0006 | Highway | Economic Development | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS NEAR THE TRIANGLE INNOVATION POINT MEGASITE. |  | CHATHAM | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund
HE-0006A | Highway | Economic Development | VARIOUS | CONSTRUCTION OF SITE DESIGN 1A. RESURFACING AND STRENGTHENING OF SURROUNDING ROADWAYS NEAR TRIANGLE INNOVATION POINT MEGASITE. |  | CHATHAM | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | CONSTRUCTION | 7000000
HE-0006B | Highway | Economic Development | VARIOUS | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. |  | CHATHAM | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | ENGINEERING | 3000000
HE-0006B | Highway | Economic Development | VARIOUS | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. |  | CHATHAM | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | RIGHT-OF-WAY | 10000000
HE-0006B | Highway | Economic Development | VARIOUS | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. |  | CHATHAM | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | UTILITIES | 5000000
HE-0006B | Highway | Economic Development | VARIOUS | CONTRUCTION OF SITE DESIGN 1B AND 1C. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. |  | CHATHAM | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | CONSTRUCTION | 175000000 | FY 2025: 75000000
HE-0006C | Highway | Economic Development | VARIOUS | CONSTRUCTION OF SITE DESIGN 2A AND 2B. ROADWAY IMPROVEMENTS INCLUDING CONSTRUCTION OF MULTIPLE INDUSTRIAL ACCESS ROADS AND NEW INTERCHANGES ALONG US 1. |  | CHATHAM | 8 | Central Pines RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR VINFAST. "HF" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION. | Highway Fund |  | HF | CONSTRUCTION | 50000000 | FY 2025: 25000000; FY 2026: 25000000
HE-0007 | Highway | Economic Development | VARIOUS | CONSTRUCT ACCESS ROAD AND INTERSECTION IMPROVEMENTS AT SR 1004 (OLD OXFORD ROAD), SR 1794 (TEKNIKA PARKWAY), AND SR 2635 (INTERNATIONAL DRIVE). |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5
HE-0007A | Highway | Economic Development | SR 1004 (OLD OXFORD ROAD) | FIRST AVE (MERCK DRIVEWAY). CONSTRUCT RIGHT TURN LANE. | 0.1 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | ENGINEERING | 25000
HE-0007A | Highway | Economic Development | SR 1004 (OLD OXFORD ROAD) | FIRST AVE (MERCK DRIVEWAY). CONSTRUCT RIGHT TURN LANE. | 0.1 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | CONSTRUCTION | 165000
HE-0007B | Highway | Economic Development | SR 1794 (TEKNIKA PARKWAY) | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | T | ENGINEERING | 90000
HE-0007B | Highway | Economic Development | SR 1794 (TEKNIKA PARKWAY) | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | T | RIGHT-OF-WAY | 95000
HE-0007B | Highway | Economic Development | SR 1794 (TEKNIKA PARKWAY) | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. RIGHT-OF-WAY IN PROGRESS. | Division 5 |  | T | CONSTRUCTION | 815000 | FY 2025: 424000; FY 2026: 391000
HE-0007C | Highway | Economic Development | SR 2635 (INTERNATIONAL DRIVE) | SR 1004 (OLD OXFORD RD) TO NEW LOCATION. CONSTRUCT NEW LANES. | 0.49 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. | Division 5 |  | T | ENGINEERING | 600000
HE-0007D | Highway | Economic Development | SR 1631 (SNOW HILL ROAD) | SR 1004 (OLD OXFORD ROAD) INTERSECTION. CONSTRUCT A LEFT TURN LANE AND SIGNALIZE INTERSECTION | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | ENGINEERING | 200000 | FY 2025: 200000
HE-0007D | Highway | Economic Development | SR 1631 (SNOW HILL ROAD) | SR 1004 (OLD OXFORD ROAD) INTERSECTION. CONSTRUCT A LEFT TURN LANE AND SIGNALIZE INTERSECTION | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | RIGHT-OF-WAY | 50000 | FY 2026: 50000
HE-0007D | Highway | Economic Development | SR 1631 (SNOW HILL ROAD) | SR 1004 (OLD OXFORD ROAD) INTERSECTION. CONSTRUCT A LEFT TURN LANE AND SIGNALIZE INTERSECTION | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | UTILITIES | 75000 | FY 2026: 75000
HE-0007D | Highway | Economic Development | SR 1631 (SNOW HILL ROAD) | SR 1004 (OLD OXFORD ROAD) INTERSECTION. CONSTRUCT A LEFT TURN LANE AND SIGNALIZE INTERSECTION | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MERCK. | Division 5 |  | T | CONSTRUCTION | 700000 | FY 2027: 700000
HE-0008 | Highway | Economic Development | US 64 | EXTEND LEFT TURN LANE AND CONSTRUCT RIGHT TURN LANE AT PROPOSED NEW ACCESS ROAD ACROSS FROM SR 2112 (DECKER ROAD) AND WIDEN RAIL CROSSING 836515Y. | 0.09 | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR. | Division 9 |  | T | ENGINEERING | 300000
HE-0008 | Highway | Economic Development | US 64 | EXTEND LEFT TURN LANE AND CONSTRUCT RIGHT TURN LANE AT PROPOSED NEW ACCESS ROAD ACROSS FROM SR 2112 (DECKER ROAD) AND WIDEN RAIL CROSSING 836515Y. | 0.09 | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NUCOR. | Division 9 |  | T | CONSTRUCTION | 1500000
HE-0009 | Highway | Economic Development | NC 152 | WIDEN PAVEMENT AND CONSTRUCT ROUNDABOUT AT THE INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. |  | ROWAN | 9 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | Division 9 |  | T | ENGINEERING | 600000
HE-0009 | Highway | Economic Development | NC 152 | WIDEN PAVEMENT AND CONSTRUCT ROUNDABOUT AT THE INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. |  | ROWAN | 9 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | Division 9 |  | T | MITIGATION | 889000
HE-0009 | Highway | Economic Development | NC 152 | WIDEN PAVEMENT AND CONSTRUCT ROUNDABOUT AT THE INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. |  | ROWAN | 9 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | Division 9 |  | T | CONSTRUCTION | 5411000 | FY 2025: 2532000; FY 2026: 2879000
HE-0009A | Highway | Economic Development | NC 152 | NC 152, INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. INTERMEDIATE INTERSECTION IMPROVEMENTS. WIDEN PAVEMENT AND CONSTRUCT TURN LANES FOR PHASE I OF ROADWAY IMPROVEMENTS. | 0.4 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. CONSTRUCTION BY STATE FORCES. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR MACYS. | Division 9 |  | T | CONSTRUCTION | 1000000
HE-0010 | Highway | Economic Development | VARIOUS | INTERCHANGE IMPROVEMENTS AT US 1 / SR 1127 (NEW HILL-HOLLEMANN ROAD), INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) / SR 1149 (FRIENDSHIP ROAD) AND SR 1149 (FRIENDSHIP ROAD) / SR 1152 (OLD HOLLY SPRINGS-NEW HILL ROAD). |  | WAKE | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | Division 5 |  | T | ENGINEERING | 500000
HE-0010 | Highway | Economic Development | VARIOUS | INTERCHANGE IMPROVEMENTS AT US 1 / SR 1127 (NEW HILL-HOLLEMANN ROAD), INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) / SR 1149 (FRIENDSHIP ROAD) AND SR 1149 (FRIENDSHIP ROAD) / SR 1152 (OLD HOLLY SPRINGS-NEW HILL ROAD). |  | WAKE | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | Division 5 |  | T | RIGHT-OF-WAY | 200000 | FY 2026: 200000
HE-0010 | Highway | Economic Development | VARIOUS | INTERCHANGE IMPROVEMENTS AT US 1 / SR 1127 (NEW HILL-HOLLEMANN ROAD), INTERSECTION IMPROVEMENTS AT BOTH SR 1127 (NEW HILL-HOLLEMANN ROAD) / SR 1149 (FRIENDSHIP ROAD) AND SR 1149 (FRIENDSHIP ROAD) / SR 1152 (OLD HOLLY SPRINGS-NEW HILL ROAD). |  | WAKE | 5 | Capital Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMGEN. | Division 5 |  | T | CONSTRUCTION | 9301000 | FY 2027: 2144000; FY 2028: 5009000; FY 2029: 2148000
HE-0011 | Highway | Economic Development | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. |  | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | Division 8 |  | T | ENGINEERING | 1000000
HE-0011 | Highway | Economic Development | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. |  | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | Division 8 |  | T | RIGHT-OF-WAY | 250000
HE-0011 | Highway | Economic Development | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. |  | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | Division 8 |  | T | UTILITIES | 250000
HE-0011 | Highway | Economic Development | VARIOUS | CONSTRUCT ROADWAY IMPROVEMENTS ALONG US 64 JUST WEST OF SILER CITY AND CONSTRUCTION OF AN INDUSTRIAL ACCESS ROAD. |  | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR WOLFSPEED. | Division 8 |  | T | CONSTRUCTION | 8500000 | FY 2025: 4991000
HE-0012 | Highway | Economic Development | FAYETTEVILLE | CONSTRUCT NEW ACCESS ROAD WITH IMPROVEMENTS AT INTERSECTION WITH SR 1838 (DUNN ROAD) IN FAYETTEVILLE. | 0.2 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | Division 6 |  | T | RIGHT-OF-WAY | 20000
HE-0012 | Highway | Economic Development | FAYETTEVILLE | CONSTRUCT NEW ACCESS ROAD WITH IMPROVEMENTS AT INTERSECTION WITH SR 1838 (DUNN ROAD) IN FAYETTEVILLE. | 0.2 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | Division 6 |  | T | UTILITIES | 50000
HE-0012 | Highway | Economic Development | FAYETTEVILLE | CONSTRUCT NEW ACCESS ROAD WITH IMPROVEMENTS AT INTERSECTION WITH SR 1838 (DUNN ROAD) IN FAYETTEVILLE. | 0.2 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR NVR, INC. | Division 6 |  | T | CONSTRUCTION | 1100000
HE-0013 | Highway | Economic Development | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE. |  | SCOTLAND | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT PUBLIC ACCESS AND ECONOMIC DEVELOPMENT FUNDS. | Division 8 |  | T | ENGINEERING | 265000
HE-0013 | Highway | Economic Development | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE. |  | SCOTLAND | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT PUBLIC ACCESS AND ECONOMIC DEVELOPMENT FUNDS. | Division 8 |  | HF | ENGINEERING | 485000
HE-0013 | Highway | Economic Development | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE. |  | SCOTLAND | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT PUBLIC ACCESS AND ECONOMIC DEVELOPMENT FUNDS. | Division 8 |  | T | RIGHT-OF-WAY | 130000
HE-0013 | Highway | Economic Development | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE. |  | SCOTLAND | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT PUBLIC ACCESS AND ECONOMIC DEVELOPMENT FUNDS. | Division 8 |  | HF | RIGHT-OF-WAY | 20000
HE-0013 | Highway | Economic Development | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE. |  | SCOTLAND | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT PUBLIC ACCESS AND ECONOMIC DEVELOPMENT FUNDS. | Division 8 |  | T | UTILITIES | 470000
HE-0013 | Highway | Economic Development | US 15/501 (ABERDEEN ROAD) | CONSTRUCT AN INDUSTRIAL ACCESS ROAD AND ROADWAY IMPROVEMENTS ALONG US 15/501 (ABERDEEN ROAD) AT THE LAURINBURG/SCOTLAND INDUSTRIAL SITE. |  | SCOTLAND | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. RIGHT-OF-WAY IN PROGRESS. "HF" FUNDS REPRESENT PUBLIC ACCESS AND ECONOMIC DEVELOPMENT FUNDS. | Division 8 |  | T | CONSTRUCTION | 7300000 | FY 2025: 73000; FY 2026: 4996000; FY 2027: 2231000
HE-0013A | Highway | Economic Development | SCOTLAND COUNTY INDUSTRIAL PARK ACCESS ROAD | IMPROVE THE EXISTING ACCESS ROAD INTO THE SCOTLAND COUNTY INDUSTRIAL PARK. |  | SCOTLAND | 8 | Lumber River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SO-PACK-CO. | Division 8 |  | T | CONSTRUCTION | 333000
HE-0014 | Highway | Economic Development | SR 1104 OLD LINWOOD ROAD | CONSTRUCT NEW ACCESS ROAD NORTH OF SR 1254 (BROWN STREET) AND IMPROVEMENTS TO SR 1104 (OLD LINWOOD ROAD). |  | DAVIDSON | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | Division 9 |  | T | ENGINEERING | 400000
HE-0014 | Highway | Economic Development | SR 1104 OLD LINWOOD ROAD | CONSTRUCT NEW ACCESS ROAD NORTH OF SR 1254 (BROWN STREET) AND IMPROVEMENTS TO SR 1104 (OLD LINWOOD ROAD). |  | DAVIDSON | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | Division 9 |  | T | UTILITIES | 10000
HE-0014 | Highway | Economic Development | SR 1104 OLD LINWOOD ROAD | CONSTRUCT NEW ACCESS ROAD NORTH OF SR 1254 (BROWN STREET) AND IMPROVEMENTS TO SR 1104 (OLD LINWOOD ROAD). |  | DAVIDSON | 9 | High Point Urban Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SIEMENS MOBILITY. | Division 9 |  | T | CONSTRUCTION | 8590000 | FY 2025: 5179000; FY 2026: 3325000
HE-0015 | Highway | Economic Development | NC 49 | PRINCE CIRCLE TO WEST OF GENERAL SERVICES DRIVE SW. CONVERT EXISTING FULL ACCESS CROSSOVER TO REDUCED CONFLICT INTERSECTION WITH LEFTOVERS AND SIGNALIZED U-TURN LEFTOVERS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841. | Division 10 |  | T | CONSTRUCTION | 2000000
HE-0015 | Highway | Economic Development | NC 49 | PRINCE CIRCLE TO WEST OF GENERAL SERVICES DRIVE SW. CONVERT EXISTING FULL ACCESS CROSSOVER TO REDUCED CONFLICT INTERSECTION WITH LEFTOVERS AND SIGNALIZED U-TURN LEFTOVERS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR KROGER. "O" FUNDS REPRESENT DEVELOPER CONTRIBUTION OF $2,090,841. | Division 10 |  | O | CONSTRUCTION | 2091000
HE-0016 | Highway | Economic Development | NEW ROUTE | ALONG NORTH SIDE OF US 74 FROM 0.5 MILES EAST OF BRUNSWICK COUNTY LINE TO 1.5 MILES EAST OF BRUNSWICK COUNTY LINE. CONSTRUCT ROAD ON NEW LOCATION AND CONSTRUCT INTERSECTIONS WITH US 74 ON EAST AND WEST TERMINI. | 1 | BRUNSWICK | 3 | Cape Fear RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS. | Division 3 |  | T | ENGINEERING | 600000
HE-0016 | Highway | Economic Development | NEW ROUTE | ALONG NORTH SIDE OF US 74 FROM 0.5 MILES EAST OF BRUNSWICK COUNTY LINE TO 1.5 MILES EAST OF BRUNSWICK COUNTY LINE. CONSTRUCT ROAD ON NEW LOCATION AND CONSTRUCT INTERSECTIONS WITH US 74 ON EAST AND WEST TERMINI. | 1 | BRUNSWICK | 3 | Cape Fear RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS. | Division 3 |  | T | UTILITIES | 40000 | FY 2025: 40000
HE-0016 | Highway | Economic Development | NEW ROUTE | ALONG NORTH SIDE OF US 74 FROM 0.5 MILES EAST OF BRUNSWICK COUNTY LINE TO 1.5 MILES EAST OF BRUNSWICK COUNTY LINE. CONSTRUCT ROAD ON NEW LOCATION AND CONSTRUCT INTERSECTIONS WITH US 74 ON EAST AND WEST TERMINI. | 1 | BRUNSWICK | 3 | Cape Fear RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR EPSILON ADVANCED MATERIALS. | Division 3 |  | T | CONSTRUCTION | 9360000 | FY 2025: 2620000; FY 2026: 5242000; FY 2027: 1498000
HE-0017 | Highway | Economic Development | SR 1711 (BETHUNE DRIVE) | EAST OF US 401 INTERSECTION IN FAYETTEVILLE. PART OF ROUTE ON NEW LOCATION. INSTALL SIGNAL AT US 401 (RAMSEY STREET) INTERSECTION AND EXTEND SR 1711 (BETHUNE DRIVE). |  | CUMBERLAND | 6 | Fayetteville Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL. | Division 6 |  | T | ENGINEERING | 800000 | FY 2025: 800000
HE-0017 | Highway | Economic Development | SR 1711 (BETHUNE DRIVE) | EAST OF US 401 INTERSECTION IN FAYETTEVILLE. PART OF ROUTE ON NEW LOCATION. INSTALL SIGNAL AT US 401 (RAMSEY STREET) INTERSECTION AND EXTEND SR 1711 (BETHUNE DRIVE). |  | CUMBERLAND | 6 | Fayetteville Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL. | Division 6 |  | T | RIGHT-OF-WAY | 300000 | FY 2026: 300000
HE-0017 | Highway | Economic Development | SR 1711 (BETHUNE DRIVE) | EAST OF US 401 INTERSECTION IN FAYETTEVILLE. PART OF ROUTE ON NEW LOCATION. INSTALL SIGNAL AT US 401 (RAMSEY STREET) INTERSECTION AND EXTEND SR 1711 (BETHUNE DRIVE). |  | CUMBERLAND | 6 | Fayetteville Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL. | Division 6 |  | T | UTILITIES | 700000 | FY 2026: 700000
HE-0017 | Highway | Economic Development | SR 1711 (BETHUNE DRIVE) | EAST OF US 401 INTERSECTION IN FAYETTEVILLE. PART OF ROUTE ON NEW LOCATION. INSTALL SIGNAL AT US 401 (RAMSEY STREET) INTERSECTION AND EXTEND SR 1711 (BETHUNE DRIVE). |  | CUMBERLAND | 6 | Fayetteville Area MPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR AMERICAN TITANIUM METAL. | Division 6 |  | T | CONSTRUCTION | 6900000 | FY 2027: 3450000; FY 2028: 3450000
HF-0001 | Highway | Federal Lands Access Program | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 2.19 | CALDWELL | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | FLAP | ENGINEERING | 4000
HF-0001 | Highway | Federal Lands Access Program | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 2.19 | CALDWELL | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | HF(M) | ENGINEERING | 1000
HF-0001 | Highway | Federal Lands Access Program | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 2.19 | CALDWELL | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | FLAP | CONSTRUCTION | 188000
HF-0001 | Highway | Federal Lands Access Program | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 2.19 | CALDWELL | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. UNDER CONSTRUCTION. | Exempt |  | HF(M) | CONSTRUCTION | 47000
HF-0002 | Highway | Federal Lands Access Program | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 1.65 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | ENGINEERING | 8000
HF-0002 | Highway | Federal Lands Access Program | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 1.65 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 2000
HF-0002 | Highway | Federal Lands Access Program | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 1.65 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | CONSTRUCTION | 184000
HF-0002 | Highway | Federal Lands Access Program | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | 1.65 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 46000
HF-0003 | Highway | Federal Lands Access Program | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 2.19 | CALDWELL | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | ENGINEERING | 140000
HF-0003 | Highway | Federal Lands Access Program | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 2.19 | CALDWELL | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 35000
HF-0003 | Highway | Federal Lands Access Program | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 2.19 | CALDWELL | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | CONSTRUCTION | 1260000 | FY 2025: 1260000
HF-0003 | Highway | Federal Lands Access Program | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN PAVEMENT TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | 2.19 | CALDWELL | 11 | Greater Hickory MPO | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 315000 | FY 2025: 315000
HF-0004 | Highway | Federal Lands Access Program | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | ENGINEERING | 24000
HF-0004 | Highway | Federal Lands Access Program | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 6000
HF-0004 | Highway | Federal Lands Access Program | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | FLAP | CONSTRUCTION | 396000 | FY 2026: 396000
HF-0004 | Highway | Federal Lands Access Program | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. HF(M) ARE HIGHWAY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 99000 | FY 2026: 1000; FY 2027: 98000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | ENGINEERING | 96000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | ENGINEERING | 240000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | ENGINEERING | 180000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | ENGINEERING | 45000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | ENGINEERING | 24000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF | ENGINEERING | 100000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | ENGINEERING | 60000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | RIGHT-OF-WAY | 248000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | RIGHT-OF-WAY | 62000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | UTILITIES | 229000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | UTILITIES | 57000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | FLAP | CONSTRUCTION | 207000 | FY 2025: 207000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF(M) | CONSTRUCTION | 52000 | FY 2025: 52000
HF-0005 | Highway | Bridges | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE 210063 OVER BLAIR CREEK AND BRIDGE 210088 OVER HYATT MILL CREEK. | 0.5 | CLAY | 14 | Southwestern RPO | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. HF(M) ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS. | Exempt |  | HF | CONSTRUCTION | 3421000 | FY 2025: 3421000
HF-0006 | Highway | Federal Lands Access Program | US 64 | DRY FALLS RECREATION AREA. IMPROVE PARKING AREA, CONSTRUCT PEDESTRIAN BRIDGE, AND CONSTRUCT OBSERVATION PLATFORM. | 0.2 | MACON | 14 | Southwestern RPO | FLAP PROJECT NC 64. AWARDED $1.0M. | Exempt |  | FLAP | ENGINEERING | 1000000
HF-0007 | Highway | Federal Lands Access Program | SR 1286/ SR 1383 (TSALI ROAD) | NC 28 TO END OF MAINTENANCE. RESURFACE AND REPAIR CORRIDOR. | 1.85 | GRAHAM, SWAIN | 14 | Southwestern RPO | FLAP PROJECT NC 65. AWARDED $1.2M. | Exempt |  | FLAP | ENGINEERING | 150000
HF-0007 | Highway | Federal Lands Access Program | SR 1286/ SR 1383 (TSALI ROAD) | NC 28 TO END OF MAINTENANCE. RESURFACE AND REPAIR CORRIDOR. | 1.85 | GRAHAM, SWAIN | 14 | Southwestern RPO | FLAP PROJECT NC 65. AWARDED $1.2M. | Exempt |  | FLAP | CONSTRUCTION | 1050000 | FY 2025: 1050000
HF-0008 | Highway | Federal Lands Access Program | NC 615 (MARSH CAUSEWAY) | HQ/ VC ENTRANCE ROAD TO WEST OF KNOTTS ISLAND ROAD. IMPROVE CORRIDOR AT VARIOUS LOCATIONS. | 3.89 | CURRITUCK | 1 | Albemarle RPO | FLAP PROJECT NC 71. AWARDED $700K. | Exempt |  | FLAP | ENGINEERING | 50000
HF-0008 | Highway | Federal Lands Access Program | NC 615 (MARSH CAUSEWAY) | HQ/ VC ENTRANCE ROAD TO WEST OF KNOTTS ISLAND ROAD. IMPROVE CORRIDOR AT VARIOUS LOCATIONS. | 3.89 | CURRITUCK | 1 | Albemarle RPO | FLAP PROJECT NC 71. AWARDED $700K. | Exempt |  | FLAP | CONSTRUCTION | 650000 | FY 2025: 650000
HI-0001 | Highway | Interstate Maintenance | I-85 / US 15 | NORTH OF SR 1637 (REDWOOD ROAD) IN DURHAM COUNTY TO SOUTH OF US 15 / SR 1100 (GATE ONE ROAD) IN GRANVILLE COUNTY. PAVEMENT REHABILITATION. | 2.03 | GRANVILLE, DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO, Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5665000
HI-0002 | Highway | Interstate Maintenance | I-85 | NC 109 IN THOMASVILLE TO SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. PAVEMENT REHABILITATION. | 7.61 | RANDOLPH, DAVIDSON | 8, 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 15672000
HI-0003 | Highway | Interstate Maintenance | I-73 / US 220 | SR 1009 (OLD US HIGHWAY 311) TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | 7.69 | RANDOLPH | 8 | Piedmont Triad RPO, High Point Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 8121000 | FY 2029: 2778000; FY 2030: 4202000; FY 2031: 1141000
HI-0004 | Highway | Interstate Maintenance | I-74 | SR 1928 (CEDAR SQUARE ROAD) TO I-73 / US 220. PAVEMENT REHABILITATION. | 7.58 | RANDOLPH | 8 | High Point Urban Area MPO, Piedmont Triad RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 8140000 | FY 2031: 3206000; FY 2032: 3918000; FY 2033: 1016000
HI-0005 | Highway | Interstate Maintenance | I-285 / US 52 / NC 8 | I-40 IN FORSYTH COUNTY TO SR 3010 (OLD US 52) IN DAVIDSON COUNTY. PAVEMENT REHABILITATION. | 18.55 | FORSYTH, DAVIDSON | 9 | Winston-Salem Area TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 28800000 | FY 2025: 270000; FY 2026: 10869000; FY 2027: 10477000; FY 2028: 7184000
HI-0006 | Highway | Interstate Maintenance | US 264 | US 264 FROM I-795 TO TOISNOT SWAMP. PAVEMENT REHABILITATION. | 7.05 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13706000
HI-0007 | Highway | Interstate Maintenance | US 264 | US 264 FROM TOISNOT SWAMP TO THE GREENE COUNTY LINE. PAVEMENT REHABILITATION. | 8.23 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 11015000
HI-0008 | Highway | Interstate Maintenance | I-95 | I-95 FROM MILE MARKER 97 TO MILE MARKER 101. PAVEMENT REHABILITATION. | 4.01 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 7229000
HI-0009 | Highway | Interstate Maintenance | I-40 | SR 1001 (SUGAR HILL ROAD)/MILE MARKER 81 TO NC 226/MILE MARKER 86. PAVEMENT REHABILITATION. | 4.97 | McDOWELL | 13 | Foothills RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 14900000 | FY 2028: 149000; FY 2029: 9919000; FY 2030: 4832000
HI-0010 | Highway | Interstate Maintenance | I-40 | MILE MARKER 67 TO MILE MARKER 73 (OLD FORT MOUNTAIN). CONSTRUCT SAFETY AND DRAINAGE IMPROVEMENTS, REHABILITATE PAVEMENT, AND RECONSTRUCT MEDIAN BARRIER. | 5.95 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | PROTCT | CONSTRUCTION | 17600000
HI-0011 | Highway | Interstate Maintenance | I-40 | I-40 FROM THE JOHNSTON COUNTY LINE (MILE MARKER 340) TO THE DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | 20.18 | SAMPSON | 3 | Mid-Carolina RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1638000 | FY 2028: 522000; FY 2029: 687000; FY 2030: 429000
HI-0011 | Highway | Interstate Maintenance | I-40 | I-40 FROM THE JOHNSTON COUNTY LINE (MILE MARKER 340) TO THE DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | 20.18 | SAMPSON | 3 | Mid-Carolina RPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 20761000 | FY 2028: 6612000; FY 2029: 8713000; FY 2030: 5436000
HI-0012 | Highway | Interstate Maintenance | I-40 | I-40 FROM THE SAMPSON COUNTY LINE (MILE MARKER 360) TO THE PENDER COUNTY LINE (MILE MARKER 388). PAVEMENT REHABILITATION. | 28 | DUPLIN | 3 | Eastern Carolina RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 31100000 | FY 2030: 7640000; FY 2031: 12343000; FY 2032: 8344000; FY 2033: 2773000
HI-0013 | Highway | Interstate Maintenance | US 264 | US 264 FROM THE US 64 / US 264 SPLIT TO THE WILSON COUNTY LINE. PAVEMENT REHABILITATION. | 14.27 | NASH, WAKE, JOHNSTON | 4, 5 | Upper Coastal Plain RPO, Capital Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 16500000 | FY 2027: 4915000; FY 2028: 7516000; FY 2029: 4069000
HI-0014 | Highway | Interstate Maintenance | US 264 | US 264 FROM THE WILSON COUNTY LINE TO I-95. PAVEMENT REHABILITATION. | 4.55 | WILSON | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6000000 | FY 2026: 2357000; FY 2027: 3005000; FY 2028: 638000
HI-0015 | Highway | Interstate Maintenance | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM EAST OF NC 214 TO WEST OF SR 1824 (WATER TANK ROAD). PAVEMENT REHABILITATION. | 7 | COLUMBUS | 6 | Cape Fear RPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 10300000 | FY 2025: 5515000; FY 2026: 1248000
HI-0016 | Highway | Interstate Maintenance | US 74 (FUTURE I-74) | 1 MILE EAST OF NC 41 TO 0.26 MILES EAST OF COLUMBUS COUNTY LINE. PAVEMENT REHABILITATION. | 10.93 | ROBESON | 6 | Lumber River RPO | TO BE LET WITH HI-0017. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 10000000 | FY 2025: 4969000; FY 2026: 781000
HI-0017 | Highway | Interstate Maintenance | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM THE SCOTLAND COUNTY LINE TO I-74/US 74 BUSINESS. PAVEMENT REHABILITATION. | 3.44 | ROBESON | 6 | Lumber River RPO | TO BE LET WITH HI-0016 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6800000 | FY 2025: 3227000
HI-0018 | Highway | Interstate Maintenance | US 74 (FUTURE I-74) | WEST OF US 701 BUSINESS TO WEST OF NC 214. PAVEMENT REHABILITATION. | 17.59 | COLUMBUS | 6 | Cape Fear RPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 16875000 | FY 2025: 4237000; FY 2026: 6394000; FY 2027: 4682000; FY 2028: 1562000
HI-0018 | Highway | Interstate Maintenance | US 74 (FUTURE I-74) | WEST OF US 701 BUSINESS TO WEST OF NC 214. PAVEMENT REHABILITATION. | 17.59 | COLUMBUS | 6 | Cape Fear RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 16025000 | FY 2025: 4023000; FY 2026: 6072000; FY 2027: 4447000; FY 2028: 1483000
HI-0019 | Highway | Interstate Maintenance | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM WEST OF SR 1585 (UNION VALLEY ROAD) TO WEST OF US 701 BUSINESS. PAVEMENT REHABILITATION. | 6.54 | COLUMBUS | 6 | Cape Fear RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5400000 | FY 2031: 2379000; FY 2032: 3021000
HI-0020 | Highway | Interstate Maintenance | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM THE ROBESON COUNTY LINE TO WEST OF SR 1585 (UNION VALLEY ROAD). PAVEMENT REHABILITATION. | 13.86 | COLUMBUS | 6 | Cape Fear RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 15000000 | FY 2031: 4944000; FY 2032: 6964000; FY 2033: 3092000
HI-0021 | Highway | Interstate Maintenance | I-95 | I-95 FROM THE ROBESON COUNTY LINE TO NC 53/210. PAVEMENT REHABILITATION. | 10.28 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 7999000 | FY 2029: 3229000; FY 2030: 3979000; FY 2031: 791000
HI-0022 | Highway | Interstate Maintenance | I-95 | I-95 FROM NC 53 TO I-95 BUSINESS / US 301. PAVEMENT REHABILITATION. | 8.92 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5800000 | FY 2029: 2426000; FY 2030: 3374000
HI-0023 | Highway | Interstate Maintenance | I-885 | I-40 TO 0.4 MILES NORTH OF TW ALEXANDER DRIVE. PAVEMENT REHABILITATION. | 2.28 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4363000 | FY 2025: 1222000
HI-0024 | Highway | Interstate Maintenance | US 13 / US 17 | SR 1154 (BUDS LANE) TO US 13 BUSINESS OVERPASS. REHABILITATE PAVEMENT | 2.18 | BERTIE | 1 | Peanut Belt RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2200000 | FY 2029: 22000; FY 2030: 2178000
HI-0025 | Highway | Interstate Maintenance | US 17 | US 13 BUSINESS OVERPASS TO PAVEMENT JOINT NEAR US 17. REHABILITATE OPEN GRADE FRICTION COURSE PAVEMENT. | 6.48 | BERTIE | 1 | Peanut Belt RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2000000 | FY 2029: 20000; FY 2030: 1980000
HI-0026 | Highway | Interstate Maintenance | US 17 | BRIDGES 710014 AND 710080 OVER PERQUIMANS RIVER TO SR 1304 (CARTWRIGHT SWAMP ROAD). REHABILITATE PAVEMENT. | 4.38 | PERQUIMANS | 1 | Albemarle RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4400000 | FY 2029: 44000; FY 2030: 3395000; FY 2031: 961000
HI-0027 | Highway | Interstate Maintenance | US 17 | SR 1304 (CARTWRIGHT SWAMP ROAD) TO PASQUOTANK COUNTY LINE. REHABILITATE PAVEMENT. | 4.17 | PERQUIMANS | 1 | Albemarle RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4200000 | FY 2030: 42000; FY 2031: 3334000; FY 2032: 824000
HI-0028 | Highway | Interstate Maintenance | US 17 | US 17 BUSINESS TO BRIDGES 710014 AND 710080 OVER PERQUIMANS RIVER. REHABILITATE PAVEMENT. | 1.74 | PERQUIMANS | 1 | Albemarle RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2000000 | FY 2030: 20000; FY 2031: 1980000
HI-9999 | Highway | Interstate Maintenance | VARIOUS | INTERSTATE MAINTENANCE PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 626273000 |  | 0 | 0 | 0 | 18049000 | 61482000 | 59408000 | 76956000 | 112358000 | 148020000 | 150000000
HL-0001 | Highway | Locally Selected | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | BGANY | ENGINEERING | 1368000
HL-0001 | Highway | Locally Selected | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | L | ENGINEERING | 342000
HL-0001 | Highway | Locally Selected | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | BGANY | RIGHT-OF-WAY | 3632000 | FY 2025: 3632000
HL-0001 | Highway | Locally Selected | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | BGDA | RIGHT-OF-WAY | 784000 | FY 2025: 784000
HL-0001 | Highway | Locally Selected | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | L | RIGHT-OF-WAY | 196000 | FY 2025: 196000
HL-0001 | Highway | Locally Selected | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | L | RIGHT-OF-WAY | 908000 | FY 2025: 908000
HL-0001 | Highway | Locally Selected | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | BGDA | CONSTRUCTION | 6280000 | FY 2026: 6280000
HL-0001 | Highway | Locally Selected | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENT. SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. WIDEN TO FOUR LANES. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022. | Division 10 |  | L | CONSTRUCTION | 1570000 | FY 2026: 1570000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | BGDA | RIGHT-OF-WAY | 80000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | L(M) | RIGHT-OF-WAY | 20000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | BGANY | CONSTRUCTION | 320000 | FY 2025: 320000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | BGDA | CONSTRUCTION | 400000 | FY 2026: 400000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | L(M) | CONSTRUCTION | 80000 | FY 2025: 80000
HL-0002 | Highway | Locally Selected | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CATAWBA | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Exempt |  | L(M) | CONSTRUCTION | 100000 | FY 2026: 100000
HL-0003 | Highway | Locally Selected | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 1.88 | BUNCOMBE | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | BGDA | ENGINEERING | 96000
HL-0003 | Highway | Locally Selected | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 1.88 | BUNCOMBE | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | BGDA | ENGINEERING | 144000
HL-0003 | Highway | Locally Selected | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 1.88 | BUNCOMBE | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | HF(M) | ENGINEERING | 32000
HL-0003 | Highway | Locally Selected | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 1.88 | BUNCOMBE | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | HF(M) | ENGINEERING | 48000
HL-0003 | Highway | Locally Selected | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 1.88 | BUNCOMBE | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | BGANY | CONSTRUCTION | 2899000 | FY 2025: 29000; FY 2026: 1831000; FY 2027: 1039000
HL-0003 | Highway | Locally Selected | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 1.88 | BUNCOMBE | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | BGDA | CONSTRUCTION | 1968000 | FY 2025: 1968000
HL-0003 | Highway | Locally Selected | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | 1.88 | BUNCOMBE | 13 | French Broad River MPO | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "HF(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. | Region G |  | HF(M) | CONSTRUCTION | 2656000 | FY 2025: 27000; FY 2026: 1677000; FY 2027: 952000
HL-0004 | Highway | Locally Selected | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGDA | ENGINEERING | 384000
HL-0004 | Highway | Locally Selected | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L | ENGINEERING | 96000
HL-0004 | Highway | Locally Selected | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | RIGHT-OF-WAY | 80000
HL-0004 | Highway | Locally Selected | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGDA | RIGHT-OF-WAY | 496000
HL-0004 | Highway | Locally Selected | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L | RIGHT-OF-WAY | 20000
HL-0004 | Highway | Locally Selected | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L | RIGHT-OF-WAY | 124000
HL-0004 | Highway | Locally Selected | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | BGANY | CONSTRUCTION | 3840000
HL-0004 | Highway | Locally Selected | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | 0.2 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22. | Division 12 |  | L | CONSTRUCTION | 960000
HL-0005 | Highway | Locally Selected | VARIOUS | CITY OF SALISBURY SIGNAL SYSTEM UPGRADE. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 343000
HL-0005 | Highway | Locally Selected | VARIOUS | CITY OF SALISBURY SIGNAL SYSTEM UPGRADE. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | CONSTRUCTION | 86000
HL-0006 | Highway | Locally Selected | US 401 | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | NHPBA | RIGHT-OF-WAY | 2601000 | FY 2025: 397000; FY 2026: 149000; FY 2027: 149000
HL-0006 | Highway | Locally Selected | US 401 | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | NHPBA | UTILITIES | 509000
HL-0006 | Highway | Locally Selected | US 401 | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | NHPBA | CONSTRUCTION | 30500000 | FY 2026: 3690000; FY 2027: 11416000; FY 2028: 8693000; FY 2029: 6701000
HL-0007 | Highway | Locally Selected | NC 55 | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | 1 | WAKE | 5 | Capital Area MPO |  | Exempt |  | BA | ENGINEERING | 2615000
HL-0007 | Highway | Locally Selected | NC 55 | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | 1 | WAKE | 5 | Capital Area MPO |  | Exempt |  | NHPBA | RIGHT-OF-WAY | 9100000 | FY 2025: 4853000; FY 2026: 910000; FY 2027: 910000
HL-0007 | Highway | Locally Selected | NC 55 | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | 1 | WAKE | 5 | Capital Area MPO |  | Exempt |  | NHPBA | UTILITIES | 2900000 | FY 2025: 1450000
HL-0007 | Highway | Locally Selected | NC 55 | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE OR ALTERNATIVE INTERSECTION. | 1 | WAKE | 5 | Capital Area MPO |  | Exempt |  | NHPBA | CONSTRUCTION | 27099000 | FY 2025: 6051000; FY 2026: 11208000; FY 2027: 7643000; FY 2028: 2197000
HL-0008 | Highway | Locally Selected | VARIOUS | INTERSECTION IMPROVEMENTS AT MULTIPLE LOCATIONS WITHIN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) BOUNDARY. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY | Exempt
HL-0008C | Highway | Locally Selected | NC 50 (BENSON ROAD) | SR 2812 (TIMBER DRIVE) INTERSECTION IN GARNER. INTERSECTION IMPROVEMENTS | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 100000
HL-0008C | Highway | Locally Selected | NC 50 (BENSON ROAD) | SR 2812 (TIMBER DRIVE) INTERSECTION IN GARNER. INTERSECTION IMPROVEMENTS | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 525000 | FY 2025: 5000; FY 2026: 520000
HL-0008D | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 1330000 | FY 2025: 700000
HL-0008D | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 170000 | FY 2025: 170000
HL-0008D | Highway | Locally Selected | SR 1152 (HOLLY SPRINGS ROAD) | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 3400000 | FY 2025: 34000; FY 2026: 2961000; FY 2027: 405000
HL-0008F | Highway | Locally Selected | SR 1010 (TEN TEN ROAD) | SR 1006 (OLD STAGE ROAD) AND SR 1010 (TEN TEN ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | BGBA | RIGHT-OF-WAY | 510000 | FY 2025: 510000
HL-0008F | Highway | Locally Selected | SR 1010 (TEN TEN ROAD) | SR 1006 (OLD STAGE ROAD) AND SR 1010 (TEN TEN ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | BGBA | UTILITIES | 50000 | FY 2025: 50000
HL-0008F | Highway | Locally Selected | SR 1010 (TEN TEN ROAD) | SR 1006 (OLD STAGE ROAD) AND SR 1010 (TEN TEN ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | BGBA | CONSTRUCTION | 2000000 | FY 2026: 1349000; FY 2027: 651000
HL-0008G | Highway | Locally Selected | SR 1375 (LAKE WHEELER ROAD) | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGBA | RIGHT-OF-WAY | 790000
HL-0008G | Highway | Locally Selected | SR 1375 (LAKE WHEELER ROAD) | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 240000
HL-0008G | Highway | Locally Selected | SR 1375 (LAKE WHEELER ROAD) | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGBA | CONSTRUCTION | 2000000 | FY 2025: 1596000; FY 2026: 404000
HL-0008H | Highway | Locally Selected | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 251000
HL-0008H | Highway | Locally Selected | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 300000
HL-0008H | Highway | Locally Selected | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 1750000 | FY 2025: 18000; FY 2026: 1732000
HL-0008I | Highway | Locally Selected | SR 1006 (OLD STAGE ROAD) | SR 1006 (OLD STAGE ROAD) AND SR 2736 (ROCK SERVICE STATION ROAD) INTERSECTION IMPROVEMENTS | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 3100000 | FY 2025: 1526000; FY 2026: 310000; FY 2027: 310000
HL-0008I | Highway | Locally Selected | SR 1006 (OLD STAGE ROAD) | SR 1006 (OLD STAGE ROAD) AND SR 2736 (ROCK SERVICE STATION ROAD) INTERSECTION IMPROVEMENTS | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 350000 | FY 2025: 350000
HL-0008I | Highway | Locally Selected | SR 1006 (OLD STAGE ROAD) | SR 1006 (OLD STAGE ROAD) AND SR 2736 (ROCK SERVICE STATION ROAD) INTERSECTION IMPROVEMENTS | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 9300000 | FY 2025: 93000; FY 2026: 5385000; FY 2027: 3822000
HL-0008J | Highway | Locally Selected | NC 50 | NC 50 (BENSON ROAD) AT SR 2728 (RAND ROAD) AND SR 2711 (BUFFALOE ROAD). INTERSECTION IMPROVEMENTS, INCLUDING WIDENING OF BENSON ROAD BETWEEN RAND ROAD AND BUFFALOE ROAD. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | BGBA | ENGINEERING | 10000
HL-0008J | Highway | Locally Selected | NC 50 | NC 50 (BENSON ROAD) AT SR 2728 (RAND ROAD) AND SR 2711 (BUFFALOE ROAD). INTERSECTION IMPROVEMENTS, INCLUDING WIDENING OF BENSON ROAD BETWEEN RAND ROAD AND BUFFALOE ROAD. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | BGBA | RIGHT-OF-WAY | 1000000 | FY 2025: 1000000
HL-0008J | Highway | Locally Selected | NC 50 | NC 50 (BENSON ROAD) AT SR 2728 (RAND ROAD) AND SR 2711 (BUFFALOE ROAD). INTERSECTION IMPROVEMENTS, INCLUDING WIDENING OF BENSON ROAD BETWEEN RAND ROAD AND BUFFALOE ROAD. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | BGBA | UTILITIES | 600000 | FY 2026: 600000
HL-0008J | Highway | Locally Selected | NC 50 | NC 50 (BENSON ROAD) AT SR 2728 (RAND ROAD) AND SR 2711 (BUFFALOE ROAD). INTERSECTION IMPROVEMENTS, INCLUDING WIDENING OF BENSON ROAD BETWEEN RAND ROAD AND BUFFALOE ROAD. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | BGBA | CONSTRUCTION | 14301000 | FY 2026: 3838000; FY 2027: 6521000; FY 2028: 3942000
HL-0008L | Highway | Locally Selected | SR 1010 (TEN-TEN ROAD) | SR 1386 (BELLS LAKE ROAD) AND SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 300000
HL-0008L | Highway | Locally Selected | SR 1010 (TEN-TEN ROAD) | SR 1386 (BELLS LAKE ROAD) AND SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 225000 | FY 2025: 225000
HL-0008L | Highway | Locally Selected | SR 1010 (TEN-TEN ROAD) | SR 1386 (BELLS LAKE ROAD) AND SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 3000000 | FY 2025: 1314000; FY 2026: 1686000
HL-0008O | Highway | Locally Selected | NC 42 | SR 2735 (JOHNSON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 175000
HL-0008O | Highway | Locally Selected | NC 42 | SR 2735 (JOHNSON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 125000 | FY 2025: 125000
HL-0008O | Highway | Locally Selected | NC 42 | SR 2735 (JOHNSON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 1300000 | FY 2025: 1026000; FY 2026: 274000
HL-0008P | Highway | Locally Selected | SR 1010 (TEN-TEN ROAD) | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 370000
HL-0008P | Highway | Locally Selected | SR 1010 (TEN-TEN ROAD) | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 240000 | FY 2025: 240000
HL-0008P | Highway | Locally Selected | SR 1010 (TEN-TEN ROAD) | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | HSIP | CONSTRUCTION | 400000 | FY 2025: 122000; FY 2026: 278000
HL-0008P | Highway | Locally Selected | SR 1010 (TEN-TEN ROAD) | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 2300000 | FY 2025: 699000; FY 2026: 1601000
HL-0008Q | Highway | Locally Selected | SR 1390 (OPTIMIST FARM ROAD) | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | ENGINEERING | 10000
HL-0008Q | Highway | Locally Selected | SR 1390 (OPTIMIST FARM ROAD) | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | RIGHT-OF-WAY | 360000
HL-0008Q | Highway | Locally Selected | SR 1390 (OPTIMIST FARM ROAD) | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | UTILITIES | 60000 | FY 2025: 60000
HL-0008Q | Highway | Locally Selected | SR 1390 (OPTIMIST FARM ROAD) | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BA | CONSTRUCTION | 3034000 | FY 2025: 1315000; FY 2026: 1719000
HL-0008S | Highway | Locally Selected | SR 1379 (PENNY ROAD) | SR 1382 (OLDE SOUTH ROAD) INTERSECTION IN RALIEGH. INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO | DELETED | Exempt
HL-0009 | Highway | Locally Selected | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 0.17 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | DP | ENGINEERING | 350000
HL-0009 | Highway | Locally Selected | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 0.17 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | DP | RIGHT-OF-WAY | 100000
HL-0009 | Highway | Locally Selected | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 0.17 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | DP | UTILITIES | 930000
HL-0009 | Highway | Locally Selected | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 0.17 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | DP | CONSTRUCTION | 3882000
HL-0009 | Highway | Locally Selected | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 0.17 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | L | CONSTRUCTION | 1178000
HL-0009 | Highway | Locally Selected | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | 0.17 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. HF FUNDS REPRESENT STATE HIGHWAY FUNDS AND CONTINGENCY FUNDS. | Exempt |  | HF | CONSTRUCTION | 3750000
HL-0012 | Highway | Locally Selected | I-240 | US 70 (CHARLOTTE STREET) INTERSECTIONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS AND A RIGHT TURN LANE ON THE I-240 EASTBOUND OFF-RAMP. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. "HF(M)" FUNDS REPRESENT SPOT MOBILITY AND HIGH IMPACT/LOW COST FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. PE AND ROW FUNDED UNDER SM-5713E (HIGHWAY FUNDS). | Exempt |  | BGDA | CONSTRUCTION | 668000
HL-0012 | Highway | Locally Selected | I-240 | US 70 (CHARLOTTE STREET) INTERSECTIONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS AND A RIGHT TURN LANE ON THE I-240 EASTBOUND OFF-RAMP. | 0.5 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. "HF(M)" FUNDS REPRESENT SPOT MOBILITY AND HIGH IMPACT/LOW COST FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. PE AND ROW FUNDED UNDER SM-5713E (HIGHWAY FUNDS). | Exempt |  | HF(M) | CONSTRUCTION | 1012000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | ENGINEERING | 160000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | ENGINEERING | 76000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGDA | ENGINEERING | 16000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | ENGINEERING | 19000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | ENGINEERING | 4000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | ENGINEERING | 40000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | RIGHT-OF-WAY | 96000 | FY 2025: 96000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | RIGHT-OF-WAY | 24000 | FY 2025: 24000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | CONSTRUCTION | 288000 | FY 2026: 288000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGDA | CONSTRUCTION | 256000 | FY 2026: 256000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | CONSTRUCTION | 64000 | FY 2026: 64000
HL-0013 | Highway | Locally Selected | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. |  | BUNCOMBE | 13 | French Broad River MPO | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | CONSTRUCTION | 72000 | FY 2026: 72000
HL-0014 | Highway | Locally Selected | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | ENGINEERING | 28000
HL-0014 | Highway | Locally Selected | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGDA | ENGINEERING | 32000
HL-0014 | Highway | Locally Selected | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | ENGINEERING | 8000
HL-0014 | Highway | Locally Selected | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | ENGINEERING | 7000
HL-0014 | Highway | Locally Selected | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HL-0014 | Highway | Locally Selected | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HL-0014 | Highway | Locally Selected | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | BGANY | CONSTRUCTION | 272000 | FY 2027: 272000
HL-0014 | Highway | Locally Selected | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP | Division 13 |  | L | CONSTRUCTION | 68000 | FY 2027: 68000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGDA | ENGINEERING | 657000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | L(M) | ENGINEERING | 164000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGDA | RIGHT-OF-WAY | 226000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | L(M) | RIGHT-OF-WAY | 56000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGANY | CONSTRUCTION | 2545000 | FY 2025: 2545000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | BGDA | CONSTRUCTION | 186000 | FY 2025: 186000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | L(M) | CONSTRUCTION | 46000 | FY 2025: 46000
HL-0015 | Highway | Locally Selected | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | 0.77 | FORSYTH | 9 | Winston-Salem Area TPO | CON FUND SWAP FROM BGDA TO BGANY ON 10-3-2022 | Exempt |  | L(M) | CONSTRUCTION | 636000 | FY 2025: 636000
HL-0016 | Highway | Locally Selected | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | ENGINEERING | 8000
HL-0016 | Highway | Locally Selected | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | ENGINEERING | 2000
HL-0016 | Highway | Locally Selected | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | RIGHT-OF-WAY | 72000
HL-0016 | Highway | Locally Selected | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | RIGHT-OF-WAY | 18000
HL-0016 | Highway | Locally Selected | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | BGDA | CONSTRUCTION | 412000
HL-0016 | Highway | Locally Selected | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | CONSTRUCTION | 103000
HL-0023 | Highway | Locally Selected | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 0.73 | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | T(DA) | ENGINEERING | 14000 | FY 2025: 14000
HL-0023 | Highway | Locally Selected | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 0.73 | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | BA | ENGINEERING | 10000
HL-0023 | Highway | Locally Selected | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 0.73 | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | BA | RIGHT-OF-WAY | 779000
HL-0023 | Highway | Locally Selected | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 0.73 | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | O | RIGHT-OF-WAY | 41000
HL-0023 | Highway | Locally Selected | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 0.73 | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | T(DA) | CONSTRUCTION | 5871000 | FY 2025: 5871000
HL-0023 | Highway | Locally Selected | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN TO SIX LANES. | 0.73 | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE. RIGHT-OF-WAY IN PROGRESS. $5.885M IN BA FUNDS SWITCHED WITH $5.885M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | O | CONSTRUCTION | 311000 | FY 2025: 311000
HL-0024 | Highway | Locally Selected | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BA | ENGINEERING | 1211000
HL-0024 | Highway | Locally Selected | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BA | RIGHT-OF-WAY | 1500000 | FY 2025: 533000; FY 2026: 489000; FY 2027: 150000; FY 2028: 150000
HL-0024 | Highway | Locally Selected | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 800000
HL-0024 | Highway | Locally Selected | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | T(DA) | UTILITIES | 400000
HL-0024 | Highway | Locally Selected | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | BA | UTILITIES | 800000
HL-0024 | Highway | Locally Selected | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN BA FUNDS SWITCHED WITH $5.923M IN HTF AS PART OF FUND SWAP 8-9-22. | Division 10 |  | T(DA) | CONSTRUCTION | 4723000 | FY 2027: 1937000; FY 2028: 2120000; FY 2029: 666000
HL-0025 | Highway | Locally Selected | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | BA | ENGINEERING | 1016000
HL-0025 | Highway | Locally Selected | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | BA | RIGHT-OF-WAY | 701000
HL-0025 | Highway | Locally Selected | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | T(DA) | UTILITIES | 500000 | FY 2025: 250000
HL-0025 | Highway | Locally Selected | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | T(DA) | MITIGATION | 24000
HL-0025 | Highway | Locally Selected | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | BGDA | CONSTRUCTION | 1563000 | FY 2025: 1563000
HL-0025 | Highway | Locally Selected | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | T(DA) | CONSTRUCTION | 5368000 | FY 2025: 54000; FY 2026: 3918000; FY 2027: 1396000
HL-0025 | Highway | Locally Selected | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.25 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.892M IN BA FUNDS SWITCHED WITH $5.892M IN T(DA) FUNDS AS PART OF FUND SWAP 8-29-23. | Division 10 |  | L(M) | CONSTRUCTION | 391000 | FY 2025: 391000
HL-0026 | Highway | Locally Selected | VARIOUS | FAYETTEVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO |  | Division 6, 8 |  | BGANY | CONSTRUCTION | 8477000 | FY 2025: 8477000
HL-0026 | Highway | Locally Selected | VARIOUS | FAYETTEVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO |  | Division 6, 8 |  | BGDA | CONSTRUCTION | 84849000 | 3710000 | 2381000 | 0 | 0 | 734000 | 5746000 | 5746000 | 5746000 | 5746000 | 5746000 | 5746000 | 40222000
HL-0027 | Highway | Locally Selected | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | ENGINEERING | 50000
HL-0027 | Highway | Locally Selected | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | ENGINEERING | 12000
HL-0027 | Highway | Locally Selected | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 308000
HL-0027 | Highway | Locally Selected | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 77000
HL-0027 | Highway | Locally Selected | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | UTILITIES | 460000
HL-0027 | Highway | Locally Selected | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | UTILITIES | 115000
HL-0027 | Highway | Locally Selected | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 462000 | FY 2025: 462000
HL-0027 | Highway | Locally Selected | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO FOUR LANE FACILITY. | 0.55 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 116000 | FY 2025: 116000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | ENGINEERING | 107000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | ENGINEERING | 27000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | BGDA | CONSTRUCTION | 2022000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L | CONSTRUCTION | 675000
HL-0028 | Highway | Locally Selected | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | L(M) | CONSTRUCTION | 505000
HL-0029 | Highway | Locally Selected | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 0.39 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGDA | RIGHT-OF-WAY | 51000
HL-0029 | Highway | Locally Selected | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 0.39 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | RIGHT-OF-WAY | 51000
HL-0029 | Highway | Locally Selected | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 0.39 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | BGDA | CONSTRUCTION | 457000
HL-0029 | Highway | Locally Selected | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | 0.39 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | CONSTRUCTION | 457000
HL-0030 | Highway | Locally Selected | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 0.12 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 293000
HL-0030 | Highway | Locally Selected | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 0.12 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 158000
HL-0030 | Highway | Locally Selected | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 0.12 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 487000
HL-0030 | Highway | Locally Selected | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | 0.12 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 262000
HL-0031 | Highway | Locally Selected | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 272000
HL-0031 | Highway | Locally Selected | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF(M) | RIGHT-OF-WAY | 68000
HL-0031 | Highway | Locally Selected | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | UTILITIES | 120000
HL-0031 | Highway | Locally Selected | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF(M) | UTILITIES | 30000
HL-0031 | Highway | Locally Selected | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 1361000 | FY 2025: 1361000
HL-0031 | Highway | Locally Selected | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | "HF(M)" FUNDING REFLECTS SPOT MOBILITY FUNDS. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF(M) | CONSTRUCTION | 339000 | FY 2025: 339000
HL-0032 | Highway | Locally Selected | LAKE BOONE TRAIL | I-440 TO RIDGE ROAD IN RALEIGH. UPGRADE ROADWAY TO COMPLETE STREET. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1011000
HL-0032 | Highway | Locally Selected | LAKE BOONE TRAIL | I-440 TO RIDGE ROAD IN RALEIGH. UPGRADE ROADWAY TO COMPLETE STREET. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 253000
HL-0033 | Highway | Locally Selected | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 360000
HL-0033 | Highway | Locally Selected | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | RIGHT-OF-WAY | 240000
HL-0033 | Highway | Locally Selected | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 3884000 | FY 2025: 3884000
HL-0033 | Highway | Locally Selected | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | 0.44 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 5 |  | L | CONSTRUCTION | 2590000 | FY 2025: 2590000
HL-0034 | Highway | Locally Selected | SR 1356 (RALEIGH ROAD PARKWAY) | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | 0.47 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Exempt |  | BA | ENGINEERING | 45000
HL-0034 | Highway | Locally Selected | SR 1356 (RALEIGH ROAD PARKWAY) | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | 0.47 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Exempt |  | BA | UTILITIES | 75000
HL-0034 | Highway | Locally Selected | SR 1356 (RALEIGH ROAD PARKWAY) | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | 0.47 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Exempt |  | BA | CONSTRUCTION | 2357000
HL-0036 | Highway | Locally Selected | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW MULTI-USE PATH ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 1.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | ENGINEERING | 40000
HL-0036 | Highway | Locally Selected | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW MULTI-USE PATH ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 1.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | ENGINEERING | 10000
HL-0036 | Highway | Locally Selected | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW MULTI-USE PATH ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 1.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 614000
HL-0036 | Highway | Locally Selected | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW MULTI-USE PATH ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | 1.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | CONSTRUCTION | 154000
HL-0037 | Highway | Locally Selected | VARIOUS | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING AND PAVEMENT RESTRIPING. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | BGDACV | CONSTRUCTION | 975000
HL-0038 | Highway | Locally Selected | VARIOUS | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, PAVEMENT RESTRIPING AND MARKERS, AND SIGN REPLACEMENT. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  |  |  | BGDACV | ENGINEERING | 5000
HL-0038A | Highway | Locally Selected | US 29/74 (WILKINSON BLVD) AND US 29 (N TRYON ST) | US 29/74 (WILKINSON BLVD) FROM GASTON COUNTY LINE TO FIELD RIDGE ROAD AND US 29 (NORTH TRYON STREET) FROM WEST SUGAR CREEK ROAD TO OLD CONCORD ROAD. RESURFACE ROADWAYS. | 3.46 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  | BGDACV | CONSTRUCTION | 2596000
HL-0038B | Highway | Locally Selected | VARIOUS | REPLACE PAVEMENT MARKINGS AND SNOW PLOWABLE MARKERS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDACV | CONSTRUCTION | 2318000
HL-0038C | Highway | Locally Selected | VARIOUS | REPLACE TRAFFIC SIGNAL LOOPS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  | BGDACV | CONSTRUCTION | 90000
HL-0038D | Highway | Locally Selected | I-485 | REPLACE OVERHEAD SIGNS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDACV | CONSTRUCTION | 705000
HL-0039 | Highway | Locally Selected | VARIOUS | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, AND PAVEMENT RESTRIPING. |  | UNION | 10 | Charlotte Regional TPO
HL-0039A | Highway | Locally Selected | NORTH CHARLOTTE AVENUE AND NEW TOWN ROAD | NORTH CHARLOTTE AVENUE FROM WALNUT STREET TO NC 200 AND NEW TOWN ROAD FROM CUTHBERTSON ROAD TO ENNIS ROAD. RESURFACE ROADWAYS. | 3.23 | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | BGDACV | CONSTRUCTION | 938000
HL-0039B | Highway | Locally Selected | VARIOUS | REPLACE PAVEMENT MARKINGS. |  | UNION | 10 | Charlotte Regional TPO | COMPLETE. | Exempt |  | BGDACV | CONSTRUCTION | 126000
HL-0039C | Highway | Locally Selected | VARIOUS | REPLACE TRAFFIC SIGNAL LOOPS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Exempt |  | BGDACV | CONSTRUCTION | 189000
HL-0040 | Highway | Locally Selected | WILMINGTON | CONSTRUCT A NEW NORTH GATE ON NORTH CAROLINA PORTS AUTHORITY PROPERTY. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY. | Division 3 |  | BGDA | ENGINEERING | 250000
HL-0040 | Highway | Locally Selected | WILMINGTON | CONSTRUCT A NEW NORTH GATE ON NORTH CAROLINA PORTS AUTHORITY PROPERTY. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY. | Division 3 |  | L | ENGINEERING | 63000
HL-0041 | Highway | Locally Selected | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 69000
HL-0041 | Highway | Locally Selected | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | HF(M) | ENGINEERING | 17000
HL-0041 | Highway | Locally Selected | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 50000
HL-0041 | Highway | Locally Selected | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | HF(M) | RIGHT-OF-WAY | 13000
HL-0041 | Highway | Locally Selected | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 1550000
HL-0041 | Highway | Locally Selected | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | HF(M) | CONSTRUCTION | 388000
HL-0041 | Highway | Locally Selected | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) AND HF REPRESENT SPOT MOBILITY FUNDS OF $640K. RIGHT-OF-WAY IN PROGRESS | Exempt |  | HF(M) | CONSTRUCTION | 223000
HL-0042 | Highway | Locally Selected | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | ENGINEERING | 202000
HL-0042 | Highway | Locally Selected | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | ENGINEERING | 51000
HL-0042 | Highway | Locally Selected | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | RIGHT-OF-WAY | 112000
HL-0042 | Highway | Locally Selected | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | RIGHT-OF-WAY | 28000
HL-0042 | Highway | Locally Selected | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | UTILITIES | 208000
HL-0042 | Highway | Locally Selected | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | UTILITIES | 52000
HL-0042 | Highway | Locally Selected | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | CMAQ | CONSTRUCTION | 975000 | FY 2025: 965000
HL-0042 | Highway | Locally Selected | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | 0.5 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Exempt |  | L | CONSTRUCTION | 299000 | FY 2025: 296000
HL-0043 | Highway | Locally Selected | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | CMAQ | ENGINEERING | 152000
HL-0043 | Highway | Locally Selected | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | HF | ENGINEERING | 38000
HL-0043 | Highway | Locally Selected | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | CMAQ | RIGHT-OF-WAY | 220000
HL-0043 | Highway | Locally Selected | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | HF | RIGHT-OF-WAY | 55000
HL-0043 | Highway | Locally Selected | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | CMAQ | CONSTRUCTION | 832000 | FY 2026: 8000; FY 2027: 824000
HL-0043 | Highway | Locally Selected | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO | "HF" FUNDING REFLECTS SPOT MOBILITY FUNDS | Exempt |  | HF | CONSTRUCTION | 208000 | FY 2026: 2000; FY 2027: 206000
HL-0044 | Highway | Locally Selected | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.35 | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | ENGINEERING | 85000
HL-0044 | Highway | Locally Selected | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.35 | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | L | ENGINEERING | 21000
HL-0044 | Highway | Locally Selected | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.35 | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 30000 | FY 2025: 30000
HL-0044 | Highway | Locally Selected | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.35 | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | L | RIGHT-OF-WAY | 8000 | FY 2025: 8000
HL-0044 | Highway | Locally Selected | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.35 | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | CMAQ | CONSTRUCTION | 370000 | FY 2025: 4000; FY 2026: 366000
HL-0044 | Highway | Locally Selected | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | 0.35 | FRANKLIN | 5 | Kerr-Tar RPO |  | Exempt |  | L | CONSTRUCTION | 92000 | FY 2025: 92000
HL-0045 | Highway | Locally Selected | EXCHANGE PARK LANE | SOUTH CHURTON STREET TO FARIBAULT LANE IN HILLSBOROUGH. REPAIR BRIDGE 670241 OVER ENO RIVER. | 0.13 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 126000 | FY 2025: 126000
HL-0045 | Highway | Locally Selected | EXCHANGE PARK LANE | SOUTH CHURTON STREET TO FARIBAULT LANE IN HILLSBOROUGH. REPAIR BRIDGE 670241 OVER ENO RIVER. | 0.13 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 32000 | FY 2025: 32000
HL-0046 | Highway | Locally Selected | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 0.91 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | RIGHT-OF-WAY | 120000
HL-0046 | Highway | Locally Selected | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 0.91 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2025: 80000
HL-0046 | Highway | Locally Selected | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 0.91 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L(M) | RIGHT-OF-WAY | 20000 | FY 2025: 20000
HL-0046 | Highway | Locally Selected | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 0.91 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | L(M) | RIGHT-OF-WAY | 30000
HL-0046 | Highway | Locally Selected | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | 0.91 | GUILFORD | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | Division 7 |  | T(DA) | CONSTRUCTION | 3560000 | FY 2025: 3560000
HL-0047 | Highway | Locally Selected | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | ENGINEERING | 8000
HL-0047 | Highway | Locally Selected | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | ENGINEERING | 2000
HL-0047 | Highway | Locally Selected | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | RIGHT-OF-WAY | 56000 | FY 2025: 56000
HL-0047 | Highway | Locally Selected | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 14000 | FY 2025: 14000
HL-0047 | Highway | Locally Selected | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 440000 | FY 2025: 440000
HL-0047 | Highway | Locally Selected | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEGROUND ROAD, US 220 (BATTLEGROUND AVENUE) TO BRITISH LAKE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK. | 0.86 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 110000 | FY 2025: 110000
HL-0048 | Highway | Locally Selected | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDACV | ENGINEERING | 255000
HL-0048 | Highway | Locally Selected | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | RIGHT-OF-WAY | 8000 | FY 2025: 8000
HL-0048 | Highway | Locally Selected | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | RIGHT-OF-WAY | 2000 | FY 2025: 2000
HL-0048 | Highway | Locally Selected | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 800000 | FY 2025: 800000
HL-0048 | Highway | Locally Selected | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L | CONSTRUCTION | 200000 | FY 2025: 200000
HL-0049 | Highway | Locally Selected | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 0.21 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | ENGINEERING | 176000
HL-0049 | Highway | Locally Selected | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 0.21 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | ENGINEERING | 44000
HL-0049 | Highway | Locally Selected | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 0.21 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 11000 | FY 2025: 11000
HL-0049 | Highway | Locally Selected | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 0.21 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | RIGHT-OF-WAY | 3000 | FY 2025: 3000
HL-0049 | Highway | Locally Selected | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 0.21 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 633000 | FY 2025: 633000
HL-0049 | Highway | Locally Selected | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | 0.21 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | CONSTRUCTION | 158000 | FY 2025: 158000
HL-0050 | Highway | Locally Selected | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | WAKE | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 79000
HL-0050 | Highway | Locally Selected | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | WAKE | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 221000 | FY 2025: 221000
HL-0050 | Highway | Locally Selected | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | WAKE | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | RIGHT-OF-WAY | 110000
HL-0050 | Highway | Locally Selected | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | WAKE | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF | RIGHT-OF-WAY | 64000
HL-0050 | Highway | Locally Selected | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | WAKE | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF | RIGHT-OF-WAY | 130000 | FY 2025: 130000
HL-0050 | Highway | Locally Selected | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | WAKE | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF | RIGHT-OF-WAY | 46000
HL-0050 | Highway | Locally Selected | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | WAKE | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | BGDA | CONSTRUCTION | 393000 | FY 2025: 393000
HL-0050 | Highway | Locally Selected | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | 0.15 | WAKE | 5 | Capital Area MPO | "HF" funds represent SPOT Mobility funds. RIGHT-OF-WAY IN PROGRESS | Division 5 |  | HF | CONSTRUCTION | 230000 | FY 2025: 230000
HL-0051 | Highway | Locally Selected | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. |  | WAKE | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | BGDA | ENGINEERING | 88000
HL-0051 | Highway | Locally Selected | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. |  | WAKE | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | HF(M) | ENGINEERING | 22000
HL-0051 | Highway | Locally Selected | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. |  | WAKE | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | BGDA | RIGHT-OF-WAY | 64000 | FY 2025: 64000
HL-0051 | Highway | Locally Selected | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. |  | WAKE | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | HF(M) | RIGHT-OF-WAY | 16000 | FY 2025: 16000
HL-0051 | Highway | Locally Selected | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. |  | WAKE | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | BGDA | CONSTRUCTION | 320000 | FY 2027: 320000
HL-0051 | Highway | Locally Selected | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. |  | WAKE | 5 | Capital Area MPO | "HF(M)" REPRESENTS SPOT MOBILITY FUNDS FOR PE AND ROW PHASES. "HF(M)" REPRESENTS HIGH-IMPACT LOW-COST FUNDS FOR CON PHASE. | Division 5 |  | HF(M) | CONSTRUCTION | 80000 | FY 2027: 80000
HL-0052 | Highway | Locally Selected | BLUE RIDGE ROAD | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | 0.32 | WAKE | 5 | Capital Area MPO | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 5 |  | BGDA | ENGINEERING | 8000
HL-0052 | Highway | Locally Selected | BLUE RIDGE ROAD | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | 0.32 | WAKE | 5 | Capital Area MPO | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 5 |  | L(M) | ENGINEERING | 2000
HL-0052 | Highway | Locally Selected | BLUE RIDGE ROAD | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | 0.32 | WAKE | 5 | Capital Area MPO | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 5 |  | BGANY | CONSTRUCTION | 6398000 | FY 2025: 6398000
HL-0052 | Highway | Locally Selected | BLUE RIDGE ROAD | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | 0.32 | WAKE | 5 | Capital Area MPO | $6,398,000 IN STBG-ANY AREA FUNDS ARE FROM A FUND SWAP. | Division 5 |  | L(M) | CONSTRUCTION | 1599000 | FY 2025: 1599000
HL-0053 | Highway | Locally Selected | SR 2822 (ROBINSON CHURCH ROAD) | NC 24 TO PLOTT ROAD. WIDEN TO THREE LANES. | 0.58 | MECKLENBURG | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Division 10 |  | T(DA) | ENGINEERING | 5000 | FY 2026: 5000
HL-0053 | Highway | Locally Selected | SR 2822 (ROBINSON CHURCH ROAD) | NC 24 TO PLOTT ROAD. WIDEN TO THREE LANES. | 0.58 | MECKLENBURG | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Division 10 |  | L | ENGINEERING | 5000 | FY 2026: 5000
HL-0053 | Highway | Locally Selected | SR 2822 (ROBINSON CHURCH ROAD) | NC 24 TO PLOTT ROAD. WIDEN TO THREE LANES. | 0.58 | MECKLENBURG | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Division 10 |  | T(DA) | CONSTRUCTION | 6222000 | FY 2027: 1773000; FY 2028: 3093000; FY 2029: 1356000
HL-0053 | Highway | Locally Selected | SR 2822 (ROBINSON CHURCH ROAD) | NC 24 TO PLOTT ROAD. WIDEN TO THREE LANES. | 0.58 | MECKLENBURG | 10 | Charlotte Regional TPO | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Division 10 |  | L | CONSTRUCTION | 6222000 | FY 2027: 6222000
HL-0055 | Highway | Locally Selected | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | T(DA) | ENGINEERING | 380000
HL-0055 | Highway | Locally Selected | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | L | ENGINEERING | 95000
HL-0055 | Highway | Locally Selected | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | BGANY | RIGHT-OF-WAY | 466000
HL-0055 | Highway | Locally Selected | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | O | RIGHT-OF-WAY | 60000
HL-0055 | Highway | Locally Selected | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | L(M) | RIGHT-OF-WAY | 117000
HL-0055 | Highway | Locally Selected | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | BGANY | CONSTRUCTION | 1098000 | FY 2026: 672000; FY 2027: 426000
HL-0055 | Highway | Locally Selected | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | L(M) | CONSTRUCTION | 275000 | FY 2026: 275000
HL-0055 | Highway | Locally Selected | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | 0.5 | UNION | 10 | Charlotte Regional TPO | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP. "HF" REPRESENTS SPOT SAFETY FUNDS. | Division 10 |  | HF | CONSTRUCTION | 400000 | FY 2026: 245000; FY 2027: 155000
HL-0056 | Highway | Locally Selected | NC 115 | HARVEST POINT DRIVE TO SAM FURR ROAD. IMPROVE CORRIDOR. | 0.43 | MECKLENBURG | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | T(DA) | ENGINEERING | 526000
HL-0056 | Highway | Locally Selected | NC 115 | HARVEST POINT DRIVE TO SAM FURR ROAD. IMPROVE CORRIDOR. | 0.43 | MECKLENBURG | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | L | ENGINEERING | 225000
HL-0056 | Highway | Locally Selected | NC 115 | HARVEST POINT DRIVE TO SAM FURR ROAD. IMPROVE CORRIDOR. | 0.43 | MECKLENBURG | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | T(DA) | RIGHT-OF-WAY | 1996000 | FY 2025: 499000; FY 2026: 998000; FY 2027: 499000
HL-0056 | Highway | Locally Selected | NC 115 | HARVEST POINT DRIVE TO SAM FURR ROAD. IMPROVE CORRIDOR. | 0.43 | MECKLENBURG | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | L | RIGHT-OF-WAY | 856000 | FY 2025: 214000; FY 2026: 428000; FY 2027: 214000
HL-0056 | Highway | Locally Selected | NC 115 | HARVEST POINT DRIVE TO SAM FURR ROAD. IMPROVE CORRIDOR. | 0.43 | MECKLENBURG | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | T(DA) | CONSTRUCTION | 3457000 | FY 2027: 3457000
HL-0056 | Highway | Locally Selected | NC 115 | HARVEST POINT DRIVE TO SAM FURR ROAD. IMPROVE CORRIDOR. | 0.43 | MECKLENBURG | 10 | Charlotte Regional TPO | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP. | Exempt |  | L | CONSTRUCTION | 1481000 | FY 2027: 1481000
HL-0057 | Highway | Locally Selected | NC 24 (WT HARRIS BOULEVARD) | SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO I-85 NORTH RAMP. INSTALL OVERHEAD STREET LIGHTS. | 7.92 | MECKLENBURG | 10 | Charlotte Regional TPO | $981,000 IN I-5507 BONUS ALLOCATION (BA) FUNDS SWITCHED TO T(DA) FUNDS FROM U-5907 TO ENSURE BA FUNDS ARE AUTHORIZED BY JUNE 30, 2024. | Exempt |  | BA | ENGINEERING | 10000
HL-0057 | Highway | Locally Selected | NC 24 (WT HARRIS BOULEVARD) | SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO I-85 NORTH RAMP. INSTALL OVERHEAD STREET LIGHTS. | 7.92 | MECKLENBURG | 10 | Charlotte Regional TPO | $981,000 IN I-5507 BONUS ALLOCATION (BA) FUNDS SWITCHED TO T(DA) FUNDS FROM U-5907 TO ENSURE BA FUNDS ARE AUTHORIZED BY JUNE 30, 2024. | Exempt |  | T(DA) | CONSTRUCTION | 981000 | FY 2025: 981000
HL-0057 | Highway | Locally Selected | NC 24 (WT HARRIS BOULEVARD) | SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO I-85 NORTH RAMP. INSTALL OVERHEAD STREET LIGHTS. | 7.92 | MECKLENBURG | 10 | Charlotte Regional TPO | $981,000 IN I-5507 BONUS ALLOCATION (BA) FUNDS SWITCHED TO T(DA) FUNDS FROM U-5907 TO ENSURE BA FUNDS ARE AUTHORIZED BY JUNE 30, 2024. | Exempt |  | L | CONSTRUCTION | 534000 | FY 2025: 534000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | BGDA | ENGINEERING | 61000 | FY 2025: 61000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | BGDA | ENGINEERING | 25000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | L(M) | ENGINEERING | 15000 | FY 2025: 15000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | HF | ENGINEERING | 50000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | BGDA | RIGHT-OF-WAY | 487000 | FY 2025: 487000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | BGDA | RIGHT-OF-WAY | 250000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | L(M) | RIGHT-OF-WAY | 122000 | FY 2025: 122000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | HF | RIGHT-OF-WAY | 200000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | BGDA | UTILITIES | 370000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | HF | UTILITIES | 200000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | CMAQ | CONSTRUCTION | 180000 | FY 2026: 180000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | BGDA | CONSTRUCTION | 1720000 | FY 2026: 1720000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | BGDA | CONSTRUCTION | 669000 | FY 2026: 669000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | L(M) | CONSTRUCTION | 167000 | FY 2026: 167000
HL-0059 | Highway | Locally Selected | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO | "HF" FUNDS REFLECT SPOT MOBILITY FUNDS | Region D |  | HF | CONSTRUCTION | 300000 | FY 2026: 300000
HL-0060 | Highway | Locally Selected | HIGH POINT | HIGH POINT SIGNAL SYSTEM RETIMING STUDY |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 1218000
HL-0060 | Highway | Locally Selected | HIGH POINT | HIGH POINT SIGNAL SYSTEM RETIMING STUDY |  | GUILFORD | 7 | High Point Urban Area MPO |  | Exempt |  | L(M) | ENGINEERING | 305000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | BGDA | ENGINEERING | 320000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 80000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 986000 | FY 2025: 986000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | BGDA | RIGHT-OF-WAY | 599000 | FY 2025: 599000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 397000 | FY 2025: 397000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | BGDA | UTILITIES | 414000 | FY 2026: 414000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | L(M) | UTILITIES | 104000 | FY 2026: 104000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | BGDA | CONSTRUCTION | 1294000 | FY 2027: 1294000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 311000 | FY 2027: 311000
HL-0061 | Highway | Locally Selected | NC 109 | RAY LANNING ROAD TO WALLBURG ROAD. CONSTRUCT TURN LANE AND TRAFFIC SIGNAL. | 0.21 | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 402000 | FY 2027: 280000; FY 2028: 122000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGDA | ENGINEERING | 1117000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | ENGINEERING | 279000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGANY | RIGHT-OF-WAY | 579000 | FY 2025: 579000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGDA | RIGHT-OF-WAY | 185000 | FY 2025: 185000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | RIGHT-OF-WAY | 191000 | FY 2025: 191000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGANY | UTILITIES | 306000 | FY 2025: 306000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | UTILITIES | 76000 | FY 2025: 76000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGANY | CONSTRUCTION | 5156000 | FY 2026: 5156000
HL-0062 | Highway | Locally Selected | NC 49 | SR 1300 (MOREHEAD ROAD) TO CEDAR DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 0.54 | CABARRUS | 10 | Cabarrus-Rowan MPO | STBG-DA FUNDS ARE EXEMPT AS THE PROJECT IS ELIGIBLE FOR REGIONAL IMPACT FUNDS. $3.863M IN BGDA FUNDS SWITCHED WITH $3.8631M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | CONSTRUCTION | 1289000 | FY 2026: 1289000
HL-0063 | Highway | Locally Selected | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | T(DA) | ENGINEERING | 666000
HL-0063 | Highway | Locally Selected | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | L | ENGINEERING | 167000
HL-0063 | Highway | Locally Selected | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | T(DA) | RIGHT-OF-WAY | 886000 | FY 2025: 886000
HL-0063 | Highway | Locally Selected | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | L | RIGHT-OF-WAY | 222000 | FY 2025: 222000
HL-0063 | Highway | Locally Selected | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | T(DA) | UTILITIES | 8000 | FY 2025: 8000
HL-0063 | Highway | Locally Selected | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | L | UTILITIES | 2000 | FY 2025: 2000
HL-0063 | Highway | Locally Selected | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | T(DA) | CONSTRUCTION | 3325000 | FY 2026: 3325000
HL-0063 | Highway | Locally Selected | SR 1173 (CALDWELL ROAD) | NC 49 TO US 29. EXTEND ROADWAY APPROXIMATELY 3000 FEET AND IMPROVE INTERSECTION OF SR 1173 (CALDWELL ROAD) AND NC 49. | 0.6 | CABARRUS | 10 | Cabarrus-Rowan MPO | $4.885M IN BGDA FUNDS SWITCHED WITH $4.885M IN T(DA) FUNDS AS PART OF FUND SWAP 10-8-24. | Division 10 |  | L | CONSTRUCTION | 831000 | FY 2026: 831000
HL-0064 | Highway | Locally Selected | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 0.52 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | ENGINEERING | 8000
HL-0064 | Highway | Locally Selected | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 0.52 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | ENGINEERING | 2000
HL-0064 | Highway | Locally Selected | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 0.52 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | UTILITIES | 2609000
HL-0064 | Highway | Locally Selected | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 0.52 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | UTILITIES | 652000
HL-0064 | Highway | Locally Selected | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 0.52 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BGDA | CONSTRUCTION | 4809000 | FY 2025: 4809000
HL-0064 | Highway | Locally Selected | US 29 MAIN STREET | KERR STREET TO HORAH STREET IN SALISBURY. SAFETY IMPROVEMENTS. | 0.52 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | L | CONSTRUCTION | 1202000 | FY 2025: 1202000
HL-0065 | Highway | Locally Selected | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | RUTHERFORD | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | DP | ENGINEERING | 1140000
HL-0065 | Highway | Locally Selected | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | RUTHERFORD | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | DP | RIGHT-OF-WAY | 1050000
HL-0065 | Highway | Locally Selected | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | RUTHERFORD | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | DP | UTILITIES | 2110000
HL-0065 | Highway | Locally Selected | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | RUTHERFORD | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | DP | CONSTRUCTION | 15740000 | FY 2025: 15740000
HL-0065 | Highway | Locally Selected | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | RUTHERFORD | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | HSIP | CONSTRUCTION | 900000 | FY 2026: 9000; FY 2027: 375000; FY 2028: 336000; FY 2029: 180000
HL-0065 | Highway | Locally Selected | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | RUTHERFORD | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | L | CONSTRUCTION | 1010000 | FY 2025: 1010000
HL-0065 | Highway | Locally Selected | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | RUTHERFORD | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | HF(M) | CONSTRUCTION | 2360000 | FY 2026: 24000; FY 2027: 982000; FY 2028: 882000; FY 2029: 472000
HL-0065 | Highway | Locally Selected | US-221A (CHARLOTTE ROAD / MAIN STREET) | CONSTRUCT COMPLETE STREET TO INCLUDE INTERSECTION IMPROVEMENTS, MULTI-USE PATH, SIDEWALKS, AND IMPROVED TRANSIT FACILITIES. | 6.08 | RUTHERFORD | 13 | Foothills RPO | "DP" = RAISE GRANT; HF(M) CONSISTS OF $100K NCDOT SAFETY, $1M HIGH IMPACT LOW COST, $750K HMIP, $500K NCDOT TRANSIT, & $10K NCDOT COMBINED CAPITAL GRANT | Division 13 |  | 5311 | CONSTRUCTION | 100000 | FY 2026: 1000; FY 2027: 42000; FY 2028: 37000; FY 2029: 20000
HL-0090 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. |  | BUNCOMBE, HENDERSON, HAYWOOD, MADISON | 13, 14 | French Broad River MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 599000 | FY 2025: 0; FY 2026: 599000
HL-0090 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. |  | BUNCOMBE, HENDERSON, HAYWOOD, MADISON | 13, 14 | French Broad River MPO |  | Exempt |  | L | CONSTRUCTION | 150000 | FY 2025: 0; FY 2026: 150000
HL-0091 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE BURLINGON PLANNING ORGANIZATION. |  | ALAMANCE, GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1365000 | FY 2025: 274000; FY 2026: 274000
HL-0091 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE BURLINGON PLANNING ORGANIZATION. |  | ALAMANCE, GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Exempt |  | L | CONSTRUCTION | 343000 | FY 2025: 69000; FY 2026: 69000
HL-0092 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION. |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1131000 | FY 2025: 0; FY 2026: 1131000
HL-0092 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION. |  | MECKLENBURG, UNION, IREDELL | 10, 12 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 283000 | FY 2025: 0; FY 2026: 283000
HL-0093 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CABARRUS-ROWAN PLANNING ORGANIZATION. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 0 | FY 2025: 0; FY 2026: 0
HL-0093 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CABARRUS-ROWAN PLANNING ORGANIZATION. |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO |  | Exempt |  | L | CONSTRUCTION | 0 | FY 2025: 0; FY 2026: 0
HL-0094 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE DURHAM PLANNING ORGANIZATION. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1918000 | FY 2025: 1271000; FY 2026: 647000
HL-0094 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE DURHAM PLANNING ORGANIZATION. |  | DURHAM, ORANGE, CHATHAM | 5, 7, 8 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CONSTRUCTION | 377000 | FY 2025: 162000; FY 2026: 215000
HL-0095 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FAYETTEVILLE PLANNING ORGANIZATION. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 5726000 | FY 2025: 2907000; FY 2026: 706000
HL-0095 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE FAYETTEVILLE PLANNING ORGANIZATION. |  | CUMBERLAND, HARNETT, HOKE, ROBESON | 6, 8 | Fayetteville Area MPO |  | Exempt |  | L | CONSTRUCTION | 1432000 | FY 2025: 727000; FY 2026: 177000
HL-0096 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GASTON CLEVELAND LINCOLN PLANNING ORGANIZATION. |  | GASTON, CLEVELAND, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1232000 | FY 2025: 848000; FY 2026: 384000
HL-0096 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GASTON CLEVELAND LINCOLN PLANNING ORGANIZATION. |  | GASTON, CLEVELAND, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Exempt |  | L | CONSTRUCTION | 308000 | FY 2025: 212000; FY 2026: 96000
HL-0097 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GOLDSBORO PLANNING ORGANIZATION. |  | WAYNE | 4 | Goldsboro Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1532000 | FY 2025: 628000; FY 2026: 118000
HL-0097 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GOLDSBORO PLANNING ORGANIZATION. |  | WAYNE | 4 | Goldsboro Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 360000 | FY 2025: 157000; FY 2026: 30000
HL-0098 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENSBORO PLANNING ORGANIZATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1472000 | FY 2025: 736000; FY 2026: 736000
HL-0098 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENSBORO PLANNING ORGANIZATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 368000 | FY 2025: 184000; FY 2026: 184000
HL-0099 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENVILLE PLANNING ORGANIZATION. |  | PITT | 2 | Greenville Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 2894000 | FY 2025: 1311000; FY 2026: 261000
HL-0099 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREENVILLE PLANNING ORGANIZATION. |  | PITT | 2 | Greenville Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 727000 | FY 2025: 328000; FY 2026: 65000
HL-0100 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREATER HICKORY PLANNING ORGANIZATION. |  | CATAWBA, ALEXANDER, BURKE, CALDWELL | 11, 12, 13 | Greater Hickory MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 0 | FY 2025: 0; FY 2026: 0
HL-0100 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GREATER HICKORY PLANNING ORGANIZATION. |  | CATAWBA, ALEXANDER, BURKE, CALDWELL | 11, 12, 13 | Greater Hickory MPO |  | Exempt |  | L | CONSTRUCTION | 0 | FY 2025: 0; FY 2026: 0
HL-0101 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE HIGH POINT PLANNING ORGANIZATION. |  | DAVIDSON, GUILFORD, RANDOLPH, FORSYTH | 7, 8, 9 | High Point Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1893000 | FY 2025: 380000; FY 2026: 380000
HL-0101 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE HIGH POINT PLANNING ORGANIZATION. |  | DAVIDSON, GUILFORD, RANDOLPH, FORSYTH | 7, 8, 9 | High Point Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 473000 | FY 2025: 95000; FY 2026: 95000
HL-0102 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE JACKSONVILLE PLANNING ORGANIZATION. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 2372000 | FY 2025: 940000; FY 2026: 241000
HL-0102 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE JACKSONVILLE PLANNING ORGANIZATION. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 530000 | FY 2025: 235000; FY 2026: 60000
HL-0103 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GRAND STRAND AREA TRANSPORTATION STUDY PLANNING ORGANIZATION. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Exempt |  | CRPDA | CONSTRUCTION | 143000 | FY 2025: 0; FY 2026: 51000
HL-0103 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE GRAND STRAND AREA TRANSPORTATION STUDY PLANNING ORGANIZATION. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Exempt |  | L | CONSTRUCTION | 71000 | FY 2025: 0; FY 2026: 13000
HL-0104 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE NEW BERN PLANNING ORGANIZATION. |  | CRAVEN | 2 | New Bern Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 684000 | FY 2025: 228000; FY 2026: 0
HL-0104 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE NEW BERN PLANNING ORGANIZATION. |  | CRAVEN | 2 | New Bern Area MPO |  | Exempt |  | L | CONSTRUCTION | 215000 | FY 2025: 57000; FY 2026: 0
HL-0105 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 4806000 | FY 2025: 2403000; FY 2026: 2403000
HL-0105 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION. |  | WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | 4, 5, 6 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 1202000 | FY 2025: 601000; FY 2026: 601000
HL-0106 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE ROCKY MOUNT PLANNING ORGANIZATION. |  | NASH, EDGECOMBE, WILSON | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | BGANY | CONSTRUCTION | 696000 | FY 2025: 696000
HL-0106 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE ROCKY MOUNT PLANNING ORGANIZATION. |  | NASH, EDGECOMBE, WILSON | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 465000 | FY 2025: 0; FY 2026: 0
HL-0106 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE ROCKY MOUNT PLANNING ORGANIZATION. |  | NASH, EDGECOMBE, WILSON | 4 | Rocky Mount Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 145000 | FY 2025: 29000; FY 2026: 0
HL-0107 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WILMINGTON PLANNING ORGANIZATION. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 3490000 | FY 2025: 1769000; FY 2026: 0
HL-0107 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WILMINGTON PLANNING ORGANIZATION. |  | NEW HANOVER, BRUNSWICK, PENDER | 3 | Wilmington Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 873000 | FY 2025: 442000; FY 2026: 0
HL-0108 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WINSTON-SALEM PLANNING ORGANIZATION. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 0 | FY 2025: 0; FY 2026: 0
HL-0108 | Highway | Locally Selected | VARIOUS | UNALLOCATED CARBON REDUCTION PROGRAM FUNDS IN THE WINSTON-SALEM PLANNING ORGANIZATION. |  | FORSYTH, DAVIDSON, STOKES, DAVIE | 9 | Winston-Salem Area TPO |  | Exempt |  | L | CONSTRUCTION | 0 | FY 2025: 0; FY 2026: 0
HL-0109 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | ENGINEERING | 380000
HL-0109 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | ENGINEERING | 109000
HL-0109 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | RIGHT-OF-WAY | 49000 | FY 2025: 49000
HL-0109 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | RIGHT-OF-WAY | 12000 | FY 2025: 12000
HL-0109 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 532000 | FY 2025: 532000
HL-0109 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNALS WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ANN STREET IN WILMINGTON. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 132000 | FY 2025: 132000
HL-0110 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | BGDA | ENGINEERING | 8000 | FY 2025: 8000
HL-0110 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | BGDA | ENGINEERING | 47000
HL-0110 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | HF | ENGINEERING | 12000
HL-0110 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | HF | ENGINEERING | 2000 | FY 2025: 2000
HL-0110 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | BGDA | RIGHT-OF-WAY | 237000 | FY 2025: 237000
HL-0110 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | HF | RIGHT-OF-WAY | 59000 | FY 2025: 59000
HL-0110 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | BGDA | CONSTRUCTION | 219000 | FY 2025: 219000
HL-0110 | Highway | Locally Selected | SOUTH 3RD STREET | INSTALLATION OF TRAFFIC SIGNAL WITH PEDESTRIAN SIGNAL HEADS AT INTERSECTION OF SOUTH 3RD STREET AND ORANGE STREET. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO | MATCHING FUNDS ARE PROVIDED BY NCDOT DIVISION 3 HIGHWAY FUNDS - SPOT SAFETY. | Division 3 |  | HF | CONSTRUCTION | 55000 | FY 2025: 1000; FY 2026: 54000
HL-0111 | Highway | Locally Selected | BEATY STREET | MAIN STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | ENGINEERING | 215000 | FY 2025: 215000
HL-0111 | Highway | Locally Selected | BEATY STREET | MAIN STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | ENGINEERING | 143000 | FY 2025: 143000
HL-0111 | Highway | Locally Selected | BEATY STREET | MAIN STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 203000 | FY 2027: 203000
HL-0111 | Highway | Locally Selected | BEATY STREET | MAIN STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 136000 | FY 2027: 136000
HL-0111 | Highway | Locally Selected | BEATY STREET | MAIN STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1645000 | FY 2029: 1645000
HL-0111 | Highway | Locally Selected | BEATY STREET | MAIN STREET INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 1097000 | FY 2029: 1097000
HL-0112 | Highway | Locally Selected | DEARMON ROAD | BENFIELD ROAD TO BROWNE ROAD. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 0.78 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 | Division 10 |  | T(DA) | ENGINEERING | 4000
HL-0112 | Highway | Locally Selected | DEARMON ROAD | BENFIELD ROAD TO BROWNE ROAD. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 0.78 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 | Division 10 |  | L | ENGINEERING | 6000
HL-0112 | Highway | Locally Selected | DEARMON ROAD | BENFIELD ROAD TO BROWNE ROAD. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 0.78 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 | Division 10 |  | T(DA) | CONSTRUCTION | 5482000 | FY 2026: 2587000; FY 2027: 2194000; FY 2028: 701000
HL-0112 | Highway | Locally Selected | DEARMON ROAD | BENFIELD ROAD TO BROWNE ROAD. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 0.78 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 $5.486M IN STBG-DA FUNDS SWAPPED FOR $5.486M IN STATE FUNDS ON 5-17-23 | Division 10 |  | L | CONSTRUCTION | 10183000 | FY 2026: 10183000
HL-0113 | Highway | Locally Selected | LANCASTER HIGHWAY | PROVIDENCE ROAD W. INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | ENGINEERING | 7000 | FY 2025: 7000
HL-0113 | Highway | Locally Selected | LANCASTER HIGHWAY | PROVIDENCE ROAD W. INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | ENGINEERING | 3000 | FY 2025: 3000
HL-0113 | Highway | Locally Selected | LANCASTER HIGHWAY | PROVIDENCE ROAD W. INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1178000 | FY 2027: 960000; FY 2028: 218000
HL-0113 | Highway | Locally Selected | LANCASTER HIGHWAY | PROVIDENCE ROAD W. INTERSECTION. IMPROVE INTERSECTION. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 505000 | FY 2026: 505000
HL-0114 | Highway | Locally Selected | LANGTREE ROAD | PIN OAK LANE TO MOUNT MOURNE LOOP. WIDEN ROADWAY. | 1.21 | IREDELL | 12 | Charlotte Regional TPO | $873K IN STBG-DA FUNDS SWAPPED FOR $873K IN STATE FUNDS ON 5-17-23 | Division 12 |  | T(DA) | ENGINEERING | 873000
HL-0114 | Highway | Locally Selected | LANGTREE ROAD | PIN OAK LANE TO MOUNT MOURNE LOOP. WIDEN ROADWAY. | 1.21 | IREDELL | 12 | Charlotte Regional TPO | $873K IN STBG-DA FUNDS SWAPPED FOR $873K IN STATE FUNDS ON 5-17-23 | Division 12 |  | L | ENGINEERING | 218000
HL-0115 | Highway | Locally Selected | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMPROVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 0.38 | UNION | 10 | Charlotte Regional TPO | $1.605M IN BGDA FUNDS SWITCHED WITH $1.605M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region E |  | BGANY | ENGINEERING | 369000 | FY 2025: 369000
HL-0115 | Highway | Locally Selected | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMPROVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 0.38 | UNION | 10 | Charlotte Regional TPO | $1.605M IN BGDA FUNDS SWITCHED WITH $1.605M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region E |  | L | ENGINEERING | 92000 | FY 2025: 92000
HL-0115 | Highway | Locally Selected | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMPROVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 0.38 | UNION | 10 | Charlotte Regional TPO | $1.605M IN BGDA FUNDS SWITCHED WITH $1.605M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region E |  | BGANY | RIGHT-OF-WAY | 414000 | FY 2027: 414000
HL-0115 | Highway | Locally Selected | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMPROVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 0.38 | UNION | 10 | Charlotte Regional TPO | $1.605M IN BGDA FUNDS SWITCHED WITH $1.605M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region E |  | L | RIGHT-OF-WAY | 103000 | FY 2027: 103000
HL-0115 | Highway | Locally Selected | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMPROVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 0.38 | UNION | 10 | Charlotte Regional TPO | $1.605M IN BGDA FUNDS SWITCHED WITH $1.605M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region E |  | BGANY | CONSTRUCTION | 822000 | FY 2028: 822000
HL-0115 | Highway | Locally Selected | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMPROVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 0.38 | UNION | 10 | Charlotte Regional TPO | $1.605M IN BGDA FUNDS SWITCHED WITH $1.605M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region E |  | BGDA | CONSTRUCTION | 1657000 | FY 2028: 1657000
HL-0115 | Highway | Locally Selected | STREET) NC 16 (NORTH BROOME | NORTH CHURCH STREET TO NC 75. WIDEN TO THREE LANES, IMPROVE INTERSECTIONS, ADD SIDEWALKS, AND UPGRADE EXISTING PEDESTRIAN FACILITIES. | 0.38 | UNION | 10 | Charlotte Regional TPO | $1.605M IN BGDA FUNDS SWITCHED WITH $1.605M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region E |  | L | CONSTRUCTION | 620000 | FY 2028: 620000
HL-0116 | Highway | Locally Selected | BONDS GROVE CHURCH ROAD | WAXAHAW MARVIN ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | ENGINEERING | 350000
HL-0116 | Highway | Locally Selected | BONDS GROVE CHURCH ROAD | WAXAHAW MARVIN ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | ENGINEERING | 88000
HL-0116 | Highway | Locally Selected | BONDS GROVE CHURCH ROAD | WAXAHAW MARVIN ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 476000 | FY 2026: 476000
HL-0116 | Highway | Locally Selected | BONDS GROVE CHURCH ROAD | WAXAHAW MARVIN ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | RIGHT-OF-WAY | 119000 | FY 2026: 119000
HL-0116 | Highway | Locally Selected | BONDS GROVE CHURCH ROAD | WAXAHAW MARVIN ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 3541000 | FY 2028: 35000; FY 2029: 2759000; FY 2030: 747000
HL-0116 | Highway | Locally Selected | BONDS GROVE CHURCH ROAD | WAXAHAW MARVIN ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | L(M) | CONSTRUCTION | 885000 | FY 2028: 885000
HL-0117 | Highway | Locally Selected | NC 218 | LOVE MILL ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | CMAQ | ENGINEERING | 140000
HL-0117 | Highway | Locally Selected | NC 218 | LOVE MILL ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | HF(M) | ENGINEERING | 60000
HL-0117 | Highway | Locally Selected | NC 218 | LOVE MILL ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | CMAQ | RIGHT-OF-WAY | 216000 | FY 2025: 216000
HL-0117 | Highway | Locally Selected | NC 218 | LOVE MILL ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | HF(M) | RIGHT-OF-WAY | 92000 | FY 2025: 92000
HL-0117 | Highway | Locally Selected | NC 218 | LOVE MILL ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | CMAQ | CONSTRUCTION | 1644000 | FY 2026: 941000; FY 2027: 703000
HL-0117 | Highway | Locally Selected | NC 218 | LOVE MILL ROAD INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) IS SPOT SAFETY FUND AND HIGH IMPACT-LOW COST FUNDS (CONSTRUCTION ONLY) | Exempt |  | HF(M) | CONSTRUCTION | 705000 | FY 2026: 404000; FY 2027: 301000
HL-0118 | Highway | Locally Selected | STUMPTOWN ROAD | ABERFELD ROAD TO NC 115. WIDEN ROADWAY. | 0.154 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23 | Region E |  | T(DA) | ENGINEERING | 148000 | FY 2025: 148000
HL-0118 | Highway | Locally Selected | STUMPTOWN ROAD | ABERFELD ROAD TO NC 115. WIDEN ROADWAY. | 0.154 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23 | Region E |  | L | ENGINEERING | 37000 | FY 2025: 37000
HL-0118 | Highway | Locally Selected | STUMPTOWN ROAD | ABERFELD ROAD TO NC 115. WIDEN ROADWAY. | 0.154 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23 | Region E |  | T(DA) | RIGHT-OF-WAY | 1584000 | FY 2025: 1584000
HL-0118 | Highway | Locally Selected | STUMPTOWN ROAD | ABERFELD ROAD TO NC 115. WIDEN ROADWAY. | 0.154 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23 | Region E |  | L | RIGHT-OF-WAY | 396000 | FY 2025: 396000
HL-0118 | Highway | Locally Selected | STUMPTOWN ROAD | ABERFELD ROAD TO NC 115. WIDEN ROADWAY. | 0.154 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23 | Region E |  | T(DA) | CONSTRUCTION | 3424000 | FY 2027: 3424000
HL-0118 | Highway | Locally Selected | STUMPTOWN ROAD | ABERFELD ROAD TO NC 115. WIDEN ROADWAY. | 0.154 | MECKLENBURG | 10 | Charlotte Regional TPO | $5.156M IN STBG-DA FUNDS SWAPPED FOR $5.156M IN STATE FUNDS ON 5-17-23 | Region E |  | L | CONSTRUCTION | 856000 | FY 2027: 856000
HL-0119 | Highway | Locally Selected | SR 1005 (SIX FORKS ROAD) | ROWAN STREET TO SR 2018 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPARATED BIKEWAYS, PROTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 1.69 | WAKE | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | BGDA | ENGINEERING | 23000 | FY 2025: 23000
HL-0119 | Highway | Locally Selected | SR 1005 (SIX FORKS ROAD) | ROWAN STREET TO SR 2018 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPARATED BIKEWAYS, PROTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 1.69 | WAKE | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | L(M) | ENGINEERING | 22000 | FY 2025: 22000
HL-0119 | Highway | Locally Selected | SR 1005 (SIX FORKS ROAD) | ROWAN STREET TO SR 2018 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPARATED BIKEWAYS, PROTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 1.69 | WAKE | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | L | ENGINEERING | 6000 | FY 2025: 6000
HL-0119 | Highway | Locally Selected | SR 1005 (SIX FORKS ROAD) | ROWAN STREET TO SR 2018 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPARATED BIKEWAYS, PROTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 1.69 | WAKE | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | BGANY | CONSTRUCTION | 13999000 | FY 2025: 140000; FY 2026: 5737000; FY 2027: 4902000; FY 2028: 3220000
HL-0119 | Highway | Locally Selected | SR 1005 (SIX FORKS ROAD) | ROWAN STREET TO SR 2018 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPARATED BIKEWAYS, PROTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 1.69 | WAKE | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | L(M) | CONSTRUCTION | 13499000 | FY 2025: 135000; FY 2026: 5532000; FY 2027: 4727000; FY 2028: 3105000
HL-0119 | Highway | Locally Selected | SR 1005 (SIX FORKS ROAD) | ROWAN STREET TO SR 2018 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT SIX-LANE MEDIAN DIVIDED AVENUE WITH SIDEWALKS. SEPARATED BIKEWAYS, PROTECTED INTERSECTIONS, UPGRADED TRAFFIC SIGNALS AND UPGRADED TRANSIT STOPS. | 1.69 | WAKE | 5 | Capital Area MPO | $14 MILLION OF STBG-ANY APPLIED TO PROJECT AS RESULT OF FUND SWAP | Division 5 |  | L | CONSTRUCTION | 3500000 | FY 2025: 3500000
HL-0121 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Division 5 |  | BGDA | ENGINEERING | 213000
HL-0121 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Division 5 |  | HF(M) | ENGINEERING | 53000
HL-0121 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Division 5 |  | BGDA | RIGHT-OF-WAY | 82000 | FY 2025: 82000
HL-0121 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Division 5 |  | HF(M) | RIGHT-OF-WAY | 21000 | FY 2025: 21000
HL-0121 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Division 5 |  | BGDA | CONSTRUCTION | 622000 | FY 2025: 622000
HL-0121 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND SR 1901 (OLD WEAVER TRAIL) IN CREEDMOOR. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Division 5 |  | HF(M) | CONSTRUCTION | 156000 | FY 2025: 156000
HL-0122 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | BGDA | ENGINEERING | 80000 | FY 2025: 80000
HL-0122 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | BGDA | ENGINEERING | 186000
HL-0122 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | HF(M) | ENGINEERING | 46000
HL-0122 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | HF(M) | ENGINEERING | 20000 | FY 2025: 20000
HL-0122 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | BGDA | RIGHT-OF-WAY | 150000 | FY 2025: 150000
HL-0122 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | HF(M) | RIGHT-OF-WAY | 37000 | FY 2025: 37000
HL-0122 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | BGDA | CONSTRUCTION | 750000 | FY 2026: 750000
HL-0122 | Highway | Locally Selected | NC 50 | INTERSECTION OF NC 50 AND MOUNT VERNON CHURCH ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) REPRESENT SPOT MOBILITY FUNDING | Division 5 |  | HF(M) | CONSTRUCTION | 190000 | FY 2026: 190000
HL-0123 | Highway | Locally Selected | CONCORD | UPGRADE SOFTWARE FOR CONCORD CITYWIDE SIGNAL SYSTEM. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CRPDA | ENGINEERING | 800000
HL-0123 | Highway | Locally Selected | CONCORD | UPGRADE SOFTWARE FOR CONCORD CITYWIDE SIGNAL SYSTEM. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L | ENGINEERING | 200000
HL-0123 | Highway | Locally Selected | CONCORD | UPGRADE SOFTWARE FOR CONCORD CITYWIDE SIGNAL SYSTEM. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 400000 | FY 2025: 400000
HL-0123 | Highway | Locally Selected | CONCORD | UPGRADE SOFTWARE FOR CONCORD CITYWIDE SIGNAL SYSTEM. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Exempt |  | L | CONSTRUCTION | 100000 | FY 2025: 100000
HL-0125 | Highway | Locally Selected | (LEWISVILLE-CLEMMONS ROAD) SR 1103 | LEWISVILLE-CLEMMONS ROAD INTERSECTION AT HOLDER ROAD IN CLEMMONS. INSTALL TRAFFIC SIGNAL. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | ENGINEERING | 12000
HL-0125 | Highway | Locally Selected | (LEWISVILLE-CLEMMONS ROAD) SR 1103 | LEWISVILLE-CLEMMONS ROAD INTERSECTION AT HOLDER ROAD IN CLEMMONS. INSTALL TRAFFIC SIGNAL. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | ENGINEERING | 3000
HL-0125 | Highway | Locally Selected | (LEWISVILLE-CLEMMONS ROAD) SR 1103 | LEWISVILLE-CLEMMONS ROAD INTERSECTION AT HOLDER ROAD IN CLEMMONS. INSTALL TRAFFIC SIGNAL. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | RIGHT-OF-WAY | 189000
HL-0125 | Highway | Locally Selected | (LEWISVILLE-CLEMMONS ROAD) SR 1103 | LEWISVILLE-CLEMMONS ROAD INTERSECTION AT HOLDER ROAD IN CLEMMONS. INSTALL TRAFFIC SIGNAL. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L | RIGHT-OF-WAY | 47000
HL-0126 | Highway | Locally Selected | LINDLEY ROAD | LINDLEY ROAD MODERNIZATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | ENGINEERING | 8000
HL-0126 | Highway | Locally Selected | LINDLEY ROAD | LINDLEY ROAD MODERNIZATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | ENGINEERING | 2000
HL-0126 | Highway | Locally Selected | LINDLEY ROAD | LINDLEY ROAD MODERNIZATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | UTILITIES | 8000
HL-0126 | Highway | Locally Selected | LINDLEY ROAD | LINDLEY ROAD MODERNIZATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | UTILITIES | 2000
HL-0126 | Highway | Locally Selected | LINDLEY ROAD | LINDLEY ROAD MODERNIZATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | BGANY | CONSTRUCTION | 1843000 | FY 2025: 1843000
HL-0126 | Highway | Locally Selected | LINDLEY ROAD | LINDLEY ROAD MODERNIZATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 461000 | FY 2025: 461000
HL-0127 | Highway | Locally Selected | US 70 BUSINESS | INTERSECTION OF US 70 BUSINESS AND SR 1553 (SHOTWELL ROAD). IMPROVE INTERSECTION. | 0.5 | JOHNSTON | 4 | Capital Area MPO | HF(M) REPRESENTS HIGH-IMPACT LOW-COST FUNDS | Exempt |  | CRPDA | CONSTRUCTION | 4600000
HL-0127 | Highway | Locally Selected | US 70 BUSINESS | INTERSECTION OF US 70 BUSINESS AND SR 1553 (SHOTWELL ROAD). IMPROVE INTERSECTION. | 0.5 | JOHNSTON | 4 | Capital Area MPO | HF(M) REPRESENTS HIGH-IMPACT LOW-COST FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 1151000 | FY 2025: 923000; FY 2026: 216000
HL-0128 | Highway | Locally Selected | ROLESVILLE ROAD | INTERSECTION OF ROLESVILLE ROAD AND RILEY HILL ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 158000
HL-0128 | Highway | Locally Selected | ROLESVILLE ROAD | INTERSECTION OF ROLESVILLE ROAD AND RILEY HILL ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HF(M) | ENGINEERING | 39000
HL-0128 | Highway | Locally Selected | ROLESVILLE ROAD | INTERSECTION OF ROLESVILLE ROAD AND RILEY HILL ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 72000 | FY 2025: 72000
HL-0128 | Highway | Locally Selected | ROLESVILLE ROAD | INTERSECTION OF ROLESVILLE ROAD AND RILEY HILL ROAD. IMPROVE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HF(M) | RIGHT-OF-WAY | 18000 | FY 2025: 18000
HL-0129 | Highway | Locally Selected | SOUTH ROBERTSON STREET MAIN STREET | SOUTH ROBERTSON STREET AND AMELIA CHURCH ROAD FROM MAIN STREET TO KENMORE DRIVE. MAIN STREET FROM SOUTH ROBERTSON STREET TO SOUTH MOORE STREET IN CLAYTON. INSTALL CURB AND GUTTER, CONSTRUCT SIDEWALKS, AND IMPROVE INTERSECTION. |  | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TADA | ENGINEERING | 490000
HL-0129 | Highway | Locally Selected | SOUTH ROBERTSON STREET MAIN STREET | SOUTH ROBERTSON STREET AND AMELIA CHURCH ROAD FROM MAIN STREET TO KENMORE DRIVE. MAIN STREET FROM SOUTH ROBERTSON STREET TO SOUTH MOORE STREET IN CLAYTON. INSTALL CURB AND GUTTER, CONSTRUCT SIDEWALKS, AND IMPROVE INTERSECTION. |  | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | ENGINEERING | 210000
HL-0129 | Highway | Locally Selected | SOUTH ROBERTSON STREET MAIN STREET | SOUTH ROBERTSON STREET AND AMELIA CHURCH ROAD FROM MAIN STREET TO KENMORE DRIVE. MAIN STREET FROM SOUTH ROBERTSON STREET TO SOUTH MOORE STREET IN CLAYTON. INSTALL CURB AND GUTTER, CONSTRUCT SIDEWALKS, AND IMPROVE INTERSECTION. |  | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | TADA | RIGHT-OF-WAY | 385000 | FY 2025: 385000
HL-0129 | Highway | Locally Selected | SOUTH ROBERTSON STREET MAIN STREET | SOUTH ROBERTSON STREET AND AMELIA CHURCH ROAD FROM MAIN STREET TO KENMORE DRIVE. MAIN STREET FROM SOUTH ROBERTSON STREET TO SOUTH MOORE STREET IN CLAYTON. INSTALL CURB AND GUTTER, CONSTRUCT SIDEWALKS, AND IMPROVE INTERSECTION. |  | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | L | RIGHT-OF-WAY | 165000 | FY 2025: 165000
HL-0130 | Highway | Locally Selected | BURLINGTON | PURCHASE, CONSTRUCTION, AND INSTALLATION OF ELECTRIC CHARGING STATION AT JOE DAVIDSON PARK IN BURLINGTON. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 132000
HL-0130 | Highway | Locally Selected | BURLINGTON | PURCHASE, CONSTRUCTION, AND INSTALLATION OF ELECTRIC CHARGING STATION AT JOE DAVIDSON PARK IN BURLINGTON. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Exempt |  | L | CONSTRUCTION | 33000
HL-0131 | Highway | Locally Selected | NC 133 | BELVILLE RIVERWALK PARK ENTRANCE. CONSTRUCT TRAFFIC SIGNAL AND RELATED PEDESTRIAN INFRASTRUCTURE. |  | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Exempt |  | CRPDA | ENGINEERING | 65000 | FY 2025: 65000
HL-0131 | Highway | Locally Selected | NC 133 | BELVILLE RIVERWALK PARK ENTRANCE. CONSTRUCT TRAFFIC SIGNAL AND RELATED PEDESTRIAN INFRASTRUCTURE. |  | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Exempt |  | L | ENGINEERING | 16000 | FY 2025: 16000
HL-0131 | Highway | Locally Selected | NC 133 | BELVILLE RIVERWALK PARK ENTRANCE. CONSTRUCT TRAFFIC SIGNAL AND RELATED PEDESTRIAN INFRASTRUCTURE. |  | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1166000 | FY 2026: 1166000
HL-0131 | Highway | Locally Selected | NC 133 | BELVILLE RIVERWALK PARK ENTRANCE. CONSTRUCT TRAFFIC SIGNAL AND RELATED PEDESTRIAN INFRASTRUCTURE. |  | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Exempt |  | L | CONSTRUCTION | 292000 | FY 2026: 292000
HL-0132 | Highway | Locally Selected | SHALLOTTE | INSTALL ADAPTIVE SIGNAL SYSTEM IN SHALLOTTE. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study | HF(M) FUNDS REPRESENT DIVISION 3 HIGH IMPACT LOW COST FUNDS. | Division 3 |  | BGDA | CONSTRUCTION | 167000
HL-0132 | Highway | Locally Selected | SHALLOTTE | INSTALL ADAPTIVE SIGNAL SYSTEM IN SHALLOTTE. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study | HF(M) FUNDS REPRESENT DIVISION 3 HIGH IMPACT LOW COST FUNDS. | Division 3 |  | CRPDA | CONSTRUCTION | 151000
HL-0132 | Highway | Locally Selected | SHALLOTTE | INSTALL ADAPTIVE SIGNAL SYSTEM IN SHALLOTTE. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study | HF(M) FUNDS REPRESENT DIVISION 3 HIGH IMPACT LOW COST FUNDS. | Division 3 |  | HF(M) | CONSTRUCTION | 80000
HL-0133 | Highway | Locally Selected | VARIOUS | CONGESTION AND SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | BA | ENGINEERING | 2500000 | FY 2025: 2500000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (MAIN STREET) | MURDOCK ROAD / OLD MOUNTAIN ROAD INTERSECTION IN TROUTMAN; CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region F |  | BGANY | ENGINEERING | 377000 | FY 2025: 377000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (MAIN STREET) | MURDOCK ROAD / OLD MOUNTAIN ROAD INTERSECTION IN TROUTMAN; CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region F |  | L | ENGINEERING | 203000 | FY 2025: 203000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (MAIN STREET) | MURDOCK ROAD / OLD MOUNTAIN ROAD INTERSECTION IN TROUTMAN; CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region F |  | BGANY | RIGHT-OF-WAY | 1028000 | FY 2027: 1028000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (MAIN STREET) | MURDOCK ROAD / OLD MOUNTAIN ROAD INTERSECTION IN TROUTMAN; CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region F |  | L | RIGHT-OF-WAY | 554000 | FY 2027: 554000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (MAIN STREET) | MURDOCK ROAD / OLD MOUNTAIN ROAD INTERSECTION IN TROUTMAN; CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region F |  | BGANY | CONSTRUCTION | 2142000 | FY 2029: 2142000
HL-0134 | Highway | Locally Selected | US 21 / NC 115 (MAIN STREET) | MURDOCK ROAD / OLD MOUNTAIN ROAD INTERSECTION IN TROUTMAN; CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | $3.547M IN BGDA FUNDS SWITCHED WITH $3.547M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Region F |  | L | CONSTRUCTION | 1153000 | FY 2029: 1153000
HL-0135 | Highway | Locally Selected | NEW TOWN ROAD | CUTHBERTSON ROAD INTERSECTION IN WESLEY CHAPEL. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | BGANY | ENGINEERING | 285000
HL-0135 | Highway | Locally Selected | NEW TOWN ROAD | CUTHBERTSON ROAD INTERSECTION IN WESLEY CHAPEL. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | HF(M) | ENGINEERING | 122000
HL-0135 | Highway | Locally Selected | NEW TOWN ROAD | CUTHBERTSON ROAD INTERSECTION IN WESLEY CHAPEL. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | BGANY | RIGHT-OF-WAY | 313000 | FY 2025: 313000
HL-0135 | Highway | Locally Selected | NEW TOWN ROAD | CUTHBERTSON ROAD INTERSECTION IN WESLEY CHAPEL. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | HF(M) | RIGHT-OF-WAY | 134000 | FY 2025: 134000
HL-0135 | Highway | Locally Selected | NEW TOWN ROAD | CUTHBERTSON ROAD INTERSECTION IN WESLEY CHAPEL. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | BGANY | CONSTRUCTION | 2552000 | FY 2027: 2552000
HL-0135 | Highway | Locally Selected | NEW TOWN ROAD | CUTHBERTSON ROAD INTERSECTION IN WESLEY CHAPEL. CONSTRUCT ROUNDABOUT. | 0.5 | UNION | 10 | Charlotte Regional TPO | HF(M) REPRESENTS SPOT SAFETY MOBILITY FUNDS. $3.15M IN BGDA FUNDS SWITCHED WITH $3.15M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | L | CONSTRUCTION | 1094000 | FY 2027: 1094000
HL-0137 | Highway | Locally Selected | WT HARRIS BOULEVARD | SUGAR CREEK INTERSECTION IN CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGANY | ENGINEERING | 7000 | FY 2025: 7000
HL-0137 | Highway | Locally Selected | WT HARRIS BOULEVARD | SUGAR CREEK INTERSECTION IN CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | ENGINEERING | 3000 | FY 2025: 3000
HL-0137 | Highway | Locally Selected | WT HARRIS BOULEVARD | SUGAR CREEK INTERSECTION IN CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | BGANY | CONSTRUCTION | 1331000 | FY 2028: 1331000
HL-0137 | Highway | Locally Selected | WT HARRIS BOULEVARD | SUGAR CREEK INTERSECTION IN CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | STBG-DA FUNDS ARE EXEMPT. $1.338M IN BGDA FUNDS SWITCHED WITH $1.338M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Exempt |  | L | CONSTRUCTION | 570000 | FY 2028: 570000
HL-0138 | Highway | Locally Selected | BROWN-GRIER ROAD; SANDY PORTER ROAD | NC 160 TO I-485; WILLIAM GLEN TO BROWN-GRIER ROAD. IMPROVE CORRIDORS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | BGANY | ENGINEERING | 4000 | FY 2025: 4000
HL-0138 | Highway | Locally Selected | BROWN-GRIER ROAD; SANDY PORTER ROAD | NC 160 TO I-485; WILLIAM GLEN TO BROWN-GRIER ROAD. IMPROVE CORRIDORS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | L | ENGINEERING | 6000 | FY 2025: 6000
HL-0138 | Highway | Locally Selected | BROWN-GRIER ROAD; SANDY PORTER ROAD | NC 160 TO I-485; WILLIAM GLEN TO BROWN-GRIER ROAD. IMPROVE CORRIDORS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | BGANY | CONSTRUCTION | 11113000 | FY 2026: 11113000
HL-0138 | Highway | Locally Selected | BROWN-GRIER ROAD; SANDY PORTER ROAD | NC 160 TO I-485; WILLIAM GLEN TO BROWN-GRIER ROAD. IMPROVE CORRIDORS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $11.117M IN BGDA FUNDS SWITCHED WITH $11.117M IN BGANY FUNDS AS PART OF FUND SWAP 8-16-24. | Division 10 |  | L | CONSTRUCTION | 20638000 | FY 2026: 20638000
HL-0139 | Highway | Locally Selected | INDIAN TRAIL | INSTALL LEVEL 2 ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSING PATHS PARK. |  | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | ENGINEERING | 4000 | FY 2025: 4000
HL-0139 | Highway | Locally Selected | INDIAN TRAIL | INSTALL LEVEL 2 ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSING PATHS PARK. |  | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | L | ENGINEERING | 1000 | FY 2025: 1000
HL-0139 | Highway | Locally Selected | INDIAN TRAIL | INSTALL LEVEL 2 ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSING PATHS PARK. |  | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 627000 | FY 2025: 627000
HL-0139 | Highway | Locally Selected | INDIAN TRAIL | INSTALL LEVEL 2 ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSING PATHS PARK. |  | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 157000 | FY 2025: 157000
HL-0140 | Highway | Locally Selected | SR 5220 JONES SAUSAGE ROAD | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 8000 | FY 2025: 8000
HL-0140 | Highway | Locally Selected | SR 5220 JONES SAUSAGE ROAD | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 2000 | FY 2025: 2000
HL-0140 | Highway | Locally Selected | SR 5220 JONES SAUSAGE ROAD | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 1600000 | FY 2025: 1600000
HL-0140 | Highway | Locally Selected | SR 5220 JONES SAUSAGE ROAD | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 400000 | FY 2025: 400000
HL-0140 | Highway | Locally Selected | SR 5220 JONES SAUSAGE ROAD | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | UTILITIES | 400000 | FY 2025: 400000
HL-0140 | Highway | Locally Selected | SR 5220 JONES SAUSAGE ROAD | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | UTILITIES | 100000 | FY 2025: 100000
HL-0140 | Highway | Locally Selected | SR 5220 JONES SAUSAGE ROAD | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 5672000 | FY 2026: 5672000
HL-0140 | Highway | Locally Selected | SR 5220 JONES SAUSAGE ROAD | SR 1004 (EAST GARNER ROAD) TO SOUTHERN BOUNDARY OF AMAZON FULFILLMENT CENTER. WIDEN ROADWAY TO 4-LANE DIVIDED FACILITY. | 0.6 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 1418000 | FY 2026: 1418000
HL-0141 | Highway | Locally Selected | SR 2765 (OLD HONEYCUTT ROAD) | INTERSECTION OF OLD HONEYCUTT ROAD AND KENNEBEC ROAD (SR 2754). PROVIDE SIGNALIZATION AT THE INTERSECTION. ADD CURB, GUTTER, SIDEWALK AND ADA RAMPS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 12000 | FY 2025: 12000
HL-0141 | Highway | Locally Selected | SR 2765 (OLD HONEYCUTT ROAD) | INTERSECTION OF OLD HONEYCUTT ROAD AND KENNEBEC ROAD (SR 2754). PROVIDE SIGNALIZATION AT THE INTERSECTION. ADD CURB, GUTTER, SIDEWALK AND ADA RAMPS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 3000 | FY 2025: 3000
HL-0141 | Highway | Locally Selected | SR 2765 (OLD HONEYCUTT ROAD) | INTERSECTION OF OLD HONEYCUTT ROAD AND KENNEBEC ROAD (SR 2754). PROVIDE SIGNALIZATION AT THE INTERSECTION. ADD CURB, GUTTER, SIDEWALK AND ADA RAMPS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 970000 | FY 2025: 970000
HL-0141 | Highway | Locally Selected | SR 2765 (OLD HONEYCUTT ROAD) | INTERSECTION OF OLD HONEYCUTT ROAD AND KENNEBEC ROAD (SR 2754). PROVIDE SIGNALIZATION AT THE INTERSECTION. ADD CURB, GUTTER, SIDEWALK AND ADA RAMPS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 242000 | FY 2025: 242000
HL-0142 | Highway | Locally Selected | US 401; NC 211 | VARIOUS LOCATIONS ALONG ROUTES IN RAEFORD. INSTALL AND MAINTAIN 5 ELECTRIC VEHICLE DC FAST CHARGERS. |  | HOKE | 8 | Fayetteville Area MPO |  | Region E |  | CRPDA | ENGINEERING | 40000 | FY 2025: 40000
HL-0142 | Highway | Locally Selected | US 401; NC 211 | VARIOUS LOCATIONS ALONG ROUTES IN RAEFORD. INSTALL AND MAINTAIN 5 ELECTRIC VEHICLE DC FAST CHARGERS. |  | HOKE | 8 | Fayetteville Area MPO |  | Region E |  | L(M) | ENGINEERING | 10000 | FY 2025: 10000
HL-0142 | Highway | Locally Selected | US 401; NC 211 | VARIOUS LOCATIONS ALONG ROUTES IN RAEFORD. INSTALL AND MAINTAIN 5 ELECTRIC VEHICLE DC FAST CHARGERS. |  | HOKE | 8 | Fayetteville Area MPO |  | Region E |  | CRPDA | CONSTRUCTION | 464000 | FY 2026: 464000
HL-0142 | Highway | Locally Selected | US 401; NC 211 | VARIOUS LOCATIONS ALONG ROUTES IN RAEFORD. INSTALL AND MAINTAIN 5 ELECTRIC VEHICLE DC FAST CHARGERS. |  | HOKE | 8 | Fayetteville Area MPO |  | Region E |  | L(M) | CONSTRUCTION | 116000 | FY 2026: 116000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | ENGINEERING | 60000 | FY 2025: 60000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | ENGINEERING | 15000 | FY 2025: 15000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | RIGHT-OF-WAY | 160000 | FY 2026: 160000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | RIGHT-OF-WAY | 40000 | FY 2026: 40000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | UTILITIES | 80000 | FY 2026: 80000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | UTILITIES | 20000 | FY 2026: 20000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | CONSTRUCTION | 280000 | FY 2028: 280000
HL-0143 | Highway | Locally Selected | NC 24 | NC 210 INTERSECTION IN FAYETTEVILLE. UPGRADE EXISTING TRAFFIC SIGNALS WITH PEDESTRIAN IMPROVEMENTS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | CONSTRUCTION | 70000 | FY 2028: 70000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | ROBESON | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | ENGINEERING | 160000 | FY 2025: 160000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | ROBESON | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | ENGINEERING | 40000 | FY 2025: 40000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | ROBESON | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | RIGHT-OF-WAY | 120000 | FY 2026: 120000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | ROBESON | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | RIGHT-OF-WAY | 30000 | FY 2026: 30000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | ROBESON | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | UTILITIES | 80000 | FY 2026: 80000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | ROBESON | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | UTILITIES | 20000 | FY 2026: 20000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | ROBESON | 6 | Fayetteville Area MPO |  | Region C |  | BGDA | CONSTRUCTION | 720000 | FY 2028: 720000
HL-0144 | Highway | Locally Selected | NC 71 | SR 1723 (DAVID PARNELL STREET) AND SR 1717 (LEEPER ROAD / PARKTON STREET) INTERSECTIONS IN PARKTON. IMPROVE INTERSECTIONS. |  | ROBESON | 6 | Fayetteville Area MPO |  | Region C |  | HF(M) | CONSTRUCTION | 180000 | FY 2028: 180000
HL-0145 | Highway | Locally Selected | SR 1112 (ROCKFISH ROAD) | NEAR ROCKFISH ELEMENTRAY SCHOOL. CONSTRUCT ADDITIONAL RIGHT TURN LANE ON SR 1112 (ROCKFISH ROAD). |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 200000 | FY 2025: 200000
HL-0145 | Highway | Locally Selected | SR 1112 (ROCKFISH ROAD) | NEAR ROCKFISH ELEMENTRAY SCHOOL. CONSTRUCT ADDITIONAL RIGHT TURN LANE ON SR 1112 (ROCKFISH ROAD). |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | ENGINEERING | 50000 | FY 2025: 50000
HL-0145 | Highway | Locally Selected | SR 1112 (ROCKFISH ROAD) | NEAR ROCKFISH ELEMENTRAY SCHOOL. CONSTRUCT ADDITIONAL RIGHT TURN LANE ON SR 1112 (ROCKFISH ROAD). |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2026: 80000
HL-0145 | Highway | Locally Selected | SR 1112 (ROCKFISH ROAD) | NEAR ROCKFISH ELEMENTRAY SCHOOL. CONSTRUCT ADDITIONAL RIGHT TURN LANE ON SR 1112 (ROCKFISH ROAD). |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HL-0145 | Highway | Locally Selected | SR 1112 (ROCKFISH ROAD) | NEAR ROCKFISH ELEMENTRAY SCHOOL. CONSTRUCT ADDITIONAL RIGHT TURN LANE ON SR 1112 (ROCKFISH ROAD). |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 2202000 | FY 2028: 2202000
HL-0145 | Highway | Locally Selected | SR 1112 (ROCKFISH ROAD) | NEAR ROCKFISH ELEMENTRAY SCHOOL. CONSTRUCT ADDITIONAL RIGHT TURN LANE ON SR 1112 (ROCKFISH ROAD). |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | CONSTRUCTION | 550000 | FY 2028: 550000
HL-0146 | Highway | Locally Selected | SR 1115 (BUFFALO LAKE ROAD) | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | ENGINEERING | 400000 | FY 2025: 400000
HL-0146 | Highway | Locally Selected | SR 1115 (BUFFALO LAKE ROAD) | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | ENGINEERING | 100000 | FY 2025: 100000
HL-0146 | Highway | Locally Selected | SR 1115 (BUFFALO LAKE ROAD) | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | RIGHT-OF-WAY | 240000 | FY 2026: 240000
HL-0146 | Highway | Locally Selected | SR 1115 (BUFFALO LAKE ROAD) | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | RIGHT-OF-WAY | 60000 | FY 2026: 60000
HL-0146 | Highway | Locally Selected | SR 1115 (BUFFALO LAKE ROAD) | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | UTILITIES | 128000 | FY 2026: 128000
HL-0146 | Highway | Locally Selected | SR 1115 (BUFFALO LAKE ROAD) | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | UTILITIES | 32000 | FY 2026: 32000
HL-0146 | Highway | Locally Selected | SR 1115 (BUFFALO LAKE ROAD) | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | BGDA | CONSTRUCTION | 2000000 | FY 2028: 2000000
HL-0146 | Highway | Locally Selected | SR 1115 (BUFFALO LAKE ROAD) | SR 1141 (ALPINE DRIVE) INTERSECTION NORTH OF SPOUT SPRINGS. CONSTRUCT ROUNDABOUT. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | HF(M) | CONSTRUCTION | 500000 | FY 2028: 500000
HL-0152 | Highway | Locally Selected | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $3.606M IN CRPDA FUNDS SWITCHED WITH $3.606M IN CRPANY FUNDS AS PART OF FUND SWAP 8-12-24. | Exempt |  | CRPDA | ENGINEERING | 686000 | FY 2025: 686000
HL-0152 | Highway | Locally Selected | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $3.606M IN CRPDA FUNDS SWITCHED WITH $3.606M IN CRPANY FUNDS AS PART OF FUND SWAP 8-12-24. | Exempt |  | L | ENGINEERING | 171000 | FY 2025: 171000
HL-0152 | Highway | Locally Selected | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $3.606M IN CRPDA FUNDS SWITCHED WITH $3.606M IN CRPANY FUNDS AS PART OF FUND SWAP 8-12-24. | Exempt |  | CRPANY | CONSTRUCTION | 834000 | FY 2027: 834000
HL-0152 | Highway | Locally Selected | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $3.606M IN CRPDA FUNDS SWITCHED WITH $3.606M IN CRPANY FUNDS AS PART OF FUND SWAP 8-12-24. | Exempt |  | CRPDA | CONSTRUCTION | 2398000 | FY 2027: 2398000
HL-0152 | Highway | Locally Selected | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO | $3.606M IN CRPDA FUNDS SWITCHED WITH $3.606M IN CRPANY FUNDS AS PART OF FUND SWAP 8-12-24. | Exempt |  | L | CONSTRUCTION | 808000 | FY 2027: 808000
HL-0153 | Highway | Locally Selected | US 311 (HARLEY DRIVE) | US 311 (MAIN STREET) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | ENGINEERING | 10000 | FY 2025: 10000
HL-0153 | Highway | Locally Selected | US 311 (HARLEY DRIVE) | US 311 (MAIN STREET) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | ENGINEERING | 3000 | FY 2025: 3000
HL-0153 | Highway | Locally Selected | US 311 (HARLEY DRIVE) | US 311 (MAIN STREET) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HL-0153 | Highway | Locally Selected | US 311 (HARLEY DRIVE) | US 311 (MAIN STREET) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | RIGHT-OF-WAY | 3000 | FY 2026: 3000
HL-0153 | Highway | Locally Selected | US 311 (HARLEY DRIVE) | US 311 (MAIN STREET) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CONSTRUCTION | 1190000 | FY 2027: 1190000
HL-0153 | Highway | Locally Selected | US 311 (HARLEY DRIVE) | US 311 (MAIN STREET) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CONSTRUCTION | 297000 | FY 2027: 297000
HL-0154 | Highway | Locally Selected | US 421 (SALEM PARKWAY) | SILAS CREEK PARKWAY TO MARTIN LUTHER KING JR DRIVE. REPLACE EXISTING LIGHTING ON SALEM PARKWAY WITH LED LIGHTING. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | ENGINEERING | 32000 | FY 2025: 32000
HL-0154 | Highway | Locally Selected | US 421 (SALEM PARKWAY) | SILAS CREEK PARKWAY TO MARTIN LUTHER KING JR DRIVE. REPLACE EXISTING LIGHTING ON SALEM PARKWAY WITH LED LIGHTING. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | ENGINEERING | 8000 | FY 2025: 8000
HL-0154 | Highway | Locally Selected | US 421 (SALEM PARKWAY) | SILAS CREEK PARKWAY TO MARTIN LUTHER KING JR DRIVE. REPLACE EXISTING LIGHTING ON SALEM PARKWAY WITH LED LIGHTING. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 768000 | FY 2026: 768000
HL-0154 | Highway | Locally Selected | US 421 (SALEM PARKWAY) | SILAS CREEK PARKWAY TO MARTIN LUTHER KING JR DRIVE. REPLACE EXISTING LIGHTING ON SALEM PARKWAY WITH LED LIGHTING. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CONSTRUCTION | 192000 | FY 2026: 192000
HL-0155 | Highway | Locally Selected | (NEW ROUTE) HIGHLAND SCHOOL ROAD | CONNECTING SR 1115 (BUFFALO LAKE ROAD) TO SR 1139 (TINGEN ROAD) SOUTH OF HIGHLAND ELEMENTARY AND MIDDLE SCHOOL CAMPUSES. CONSTRUCT TWO-LANE MINOR THOROUGHFARE PARTIALLY ON NEW GROUND. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | T(DA) | ENGINEERING | 125000 | FY 2025: 125000
HL-0155 | Highway | Locally Selected | (NEW ROUTE) HIGHLAND SCHOOL ROAD | CONNECTING SR 1115 (BUFFALO LAKE ROAD) TO SR 1139 (TINGEN ROAD) SOUTH OF HIGHLAND ELEMENTARY AND MIDDLE SCHOOL CAMPUSES. CONSTRUCT TWO-LANE MINOR THOROUGHFARE PARTIALLY ON NEW GROUND. |  | HARNETT | 6 | Fayetteville Area MPO |  | Division 6 |  | T(DA) | CONSTRUCTION | 2658000 | FY 2026: 2658000
HL-0156 | Highway | Locally Selected | VARIOUS | LOCATIONS IN CHATHAM COUNTY. PURCHASE AND INSTALL TWO ELECTRIC VEHICLE CHARGING STATIONS. |  | CHATHAM | 8 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 213000 | FY 2026: 213000
HL-0156 | Highway | Locally Selected | VARIOUS | LOCATIONS IN CHATHAM COUNTY. PURCHASE AND INSTALL TWO ELECTRIC VEHICLE CHARGING STATIONS. |  | CHATHAM | 8 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | CONSTRUCTION | 53000 | FY 2026: 53000
HL-0157 | Highway | Locally Selected | I-85 | GEORGES LILES PARKWAY INTERCHANGE. INSTALL LIGHTING AT INTERCHANGE. | 0.1 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | BGDA | CONSTRUCTION | 800000 | FY 2025: 800000
HL-0157 | Highway | Locally Selected | I-85 | GEORGES LILES PARKWAY INTERCHANGE. INSTALL LIGHTING AT INTERCHANGE. | 0.1 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | L(M) | CONSTRUCTION | 133000 | FY 2025: 133000
HL-0157 | Highway | Locally Selected | I-85 | GEORGES LILES PARKWAY INTERCHANGE. INSTALL LIGHTING AT INTERCHANGE. | 0.1 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HF(M) | CONSTRUCTION | 67000 | FY 2025: 67000
HM-0001 | Highway | Municipal Bridge | EAST FISHER STREET | REPLACE 790138 OVER NORFOLK SOUTHERN RAILROAD BETWEEN SOUTH LONG STREET AND SOUTH LEE STREET IN SALISBURY. | 0.25 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | BFPOFF | CONSTRUCTION | 2000000
HM-0002 | Highway | Municipal Bridge | SHELLEY ROAD | REPLACE BRIDGE 910378 OVER MINE CREEK FROM SHADOWBROOK DRIVE TO FOREST LAWN COURT. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | RIGHT-OF-WAY | 300000 | FY 2025: 300000
HM-0002 | Highway | Municipal Bridge | SHELLEY ROAD | REPLACE BRIDGE 910378 OVER MINE CREEK FROM SHADOWBROOK DRIVE TO FOREST LAWN COURT. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | UTILITIES | 250000 | FY 2025: 250000
HM-0002 | Highway | Municipal Bridge | SHELLEY ROAD | REPLACE BRIDGE 910378 OVER MINE CREEK FROM SHADOWBROOK DRIVE TO FOREST LAWN COURT. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | CONSTRUCTION | 2125000 | FY 2026: 2125000
HM-0002 | Highway | Municipal Bridge | SHELLEY ROAD | REPLACE BRIDGE 910378 OVER MINE CREEK FROM SHADOWBROOK DRIVE TO FOREST LAWN COURT. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | CONSTRUCTION | 375000 | FY 2027: 375000
HM-0003 | Highway | Municipal Bridge | CHESWICK DRIVE | REPLACE BRIDGE 910627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | ENGINEERING | 500000
HM-0003 | Highway | Municipal Bridge | CHESWICK DRIVE | REPLACE BRIDGE 910627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | RIGHT-OF-WAY | 250000 | FY 2025: 250000
HM-0003 | Highway | Municipal Bridge | CHESWICK DRIVE | REPLACE BRIDGE 910627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | UTILITIES | 250000 | FY 2025: 250000
HM-0003 | Highway | Municipal Bridge | CHESWICK DRIVE | REPLACE BRIDGE 910627 OVER BIG BRANCH CONNECTING OAKLAND DRIVE TO CHESWICK DRIVE. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BFPOFF | CONSTRUCTION | 1250000 | FY 2025: 922000; FY 2026: 328000
HM-0004 | Highway | Municipal Bridge | OLD GREENSBORO ROAD | REPLACE BRIDGE 330330 OVER BRUSHY FORK CREEK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | ENGINEERING | 1240000 | FY 2026: 1240000
HM-0004 | Highway | Municipal Bridge | OLD GREENSBORO ROAD | REPLACE BRIDGE 330330 OVER BRUSHY FORK CREEK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | RIGHT-OF-WAY | 300000 | FY 2027: 300000
HM-0004 | Highway | Municipal Bridge | OLD GREENSBORO ROAD | REPLACE BRIDGE 330330 OVER BRUSHY FORK CREEK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | UTILITIES | 475000 | FY 2027: 475000
HM-0004 | Highway | Municipal Bridge | OLD GREENSBORO ROAD | REPLACE BRIDGE 330330 OVER BRUSHY FORK CREEK. | 0.25 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BFPOFF | CONSTRUCTION | 2800000 | FY 2028: 2800000
HM-9999 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | IMPLEMENTATION | 13000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 2000000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | RALEIGH | NEW HOPE ROAD AND EVA MAE DRIVE. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 129000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | RALEIGH | NEW HOPE ROAD AND EVA MAE DRIVE. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | T | ENGINEERING | 32000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | RALEIGH | NEW HOPE ROAD AND EVA MAE DRIVE. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 50000 | FY 2025: 50000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | RALEIGH | NEW HOPE ROAD AND EVA MAE DRIVE. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | T | RIGHT-OF-WAY | 13000 | FY 2025: 13000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | RALEIGH | NEW HOPE ROAD AND EVA MAE DRIVE. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 541000 | FY 2026: 348000; FY 2027: 193000
HN-0012 | Highway | NCDOT Selected (Other Selection Process) | RALEIGH | NEW HOPE ROAD AND EVA MAE DRIVE. CONSTRUCT TURN LANES. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | T | CONSTRUCTION | 135000 | FY 2026: 87000; FY 2027: 48000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | ERWIN ROAD | ERWIN ROAD AT CORNWALLIS ROAD. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | ENGINEERING | 206000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | ERWIN ROAD | ERWIN ROAD AT CORNWALLIS ROAD. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | T(M) | ENGINEERING | 52000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | ERWIN ROAD | ERWIN ROAD AT CORNWALLIS ROAD. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 80000 | FY 2026: 80000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | ERWIN ROAD | ERWIN ROAD AT CORNWALLIS ROAD. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 20000 | FY 2026: 20000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | ERWIN ROAD | ERWIN ROAD AT CORNWALLIS ROAD. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 597000 | FY 2027: 597000
HN-0013 | Highway | NCDOT Selected (Other Selection Process) | ERWIN ROAD | ERWIN ROAD AT CORNWALLIS ROAD. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | T(M) | CONSTRUCTION | 149000 | FY 2027: 149000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | CORNWALLIS ROAD | CORNWALLIS ROAD AND ALSTON AVENUE. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | ENGINEERING | 198000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | CORNWALLIS ROAD | CORNWALLIS ROAD AND ALSTON AVENUE. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | T(M) | ENGINEERING | 50000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | CORNWALLIS ROAD | CORNWALLIS ROAD AND ALSTON AVENUE. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 35000 | FY 2026: 35000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | CORNWALLIS ROAD | CORNWALLIS ROAD AND ALSTON AVENUE. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 9000 | FY 2026: 9000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | CORNWALLIS ROAD | CORNWALLIS ROAD AND ALSTON AVENUE. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 437000 | FY 2027: 437000
HN-0014 | Highway | NCDOT Selected (Other Selection Process) | CORNWALLIS ROAD | CORNWALLIS ROAD AND ALSTON AVENUE. CONSTRUCT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | T(M) | CONSTRUCTION | 109000 | FY 2027: 109000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | US 158 AND DORSEY ROAD. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | CRPLT5 | ENGINEERING | 560000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | US 158 AND DORSEY ROAD. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | ENGINEERING | 140000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | US 158 AND DORSEY ROAD. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | CMAQ | RIGHT-OF-WAY | 125000 | FY 2025: 125000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | US 158 AND DORSEY ROAD. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 31000 | FY 2025: 31000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | US 158 AND DORSEY ROAD. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | CMAQ | CONSTRUCTION | 1556000 | FY 2026: 611000; FY 2027: 945000
HN-0015 | Highway | NCDOT Selected (Other Selection Process) | US 158 | US 158 AND DORSEY ROAD. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | T(M) | CONSTRUCTION | 389000 | FY 2026: 153000; FY 2027: 236000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | GLENWOOD AVENUE | SR 1728 (WADE AVENUE) EASTBOUND RAMPS / COLE STREET INTERSECTION. CONSTRUCT LEFT TURN LANE FROM WESTBOUND GLENWOOD AVENUE TO EASTBOUND WADE AVENUE LOOP. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | CMAQ | ENGINEERING | 99000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | GLENWOOD AVENUE | SR 1728 (WADE AVENUE) EASTBOUND RAMPS / COLE STREET INTERSECTION. CONSTRUCT LEFT TURN LANE FROM WESTBOUND GLENWOOD AVENUE TO EASTBOUND WADE AVENUE LOOP. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | HF(M) | ENGINEERING | 25000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | GLENWOOD AVENUE | SR 1728 (WADE AVENUE) EASTBOUND RAMPS / COLE STREET INTERSECTION. CONSTRUCT LEFT TURN LANE FROM WESTBOUND GLENWOOD AVENUE TO EASTBOUND WADE AVENUE LOOP. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | CMAQ | RIGHT-OF-WAY | 20000 | FY 2025: 20000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | GLENWOOD AVENUE | SR 1728 (WADE AVENUE) EASTBOUND RAMPS / COLE STREET INTERSECTION. CONSTRUCT LEFT TURN LANE FROM WESTBOUND GLENWOOD AVENUE TO EASTBOUND WADE AVENUE LOOP. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | HF(M) | RIGHT-OF-WAY | 5000 | FY 2025: 5000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | GLENWOOD AVENUE | SR 1728 (WADE AVENUE) EASTBOUND RAMPS / COLE STREET INTERSECTION. CONSTRUCT LEFT TURN LANE FROM WESTBOUND GLENWOOD AVENUE TO EASTBOUND WADE AVENUE LOOP. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | CMAQ | CONSTRUCTION | 188000 | FY 2026: 188000
HN-0016 | Highway | NCDOT Selected (Other Selection Process) | GLENWOOD AVENUE | SR 1728 (WADE AVENUE) EASTBOUND RAMPS / COLE STREET INTERSECTION. CONSTRUCT LEFT TURN LANE FROM WESTBOUND GLENWOOD AVENUE TO EASTBOUND WADE AVENUE LOOP. | 0.5 | WAKE | 5 | Capital Area MPO | HF(M) ARE SPOT SAFETY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 47000 | FY 2026: 47000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | HESTER ROAD AND US 15. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | CMAQ | ENGINEERING | 354000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | HESTER ROAD AND US 15. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | HF(M) | ENGINEERING | 88000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | HESTER ROAD AND US 15. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | CMAQ | RIGHT-OF-WAY | 112000 | FY 2025: 112000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | HESTER ROAD AND US 15. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | HF(M) | RIGHT-OF-WAY | 28000 | FY 2025: 28000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | HESTER ROAD AND US 15. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | CMAQ | CONSTRUCTION | 1309000 | FY 2026: 1309000
HN-0017 | Highway | NCDOT Selected (Other Selection Process) | US 15 | HESTER ROAD AND US 15. CONSTRUCT ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Capital Area MPO | HF(M) REPRESENTS SPOT MOBILITY FUNDS FOR THE MATCHING FUNDS | Exempt |  | HF(M) | CONSTRUCTION | 327000 | FY 2026: 327000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | ZEBULON | PEARCES ROAD AND PROCTOR STREET. CONSTRUCT ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 94000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | ZEBULON | PEARCES ROAD AND PROCTOR STREET. CONSTRUCT ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | T | ENGINEERING | 24000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | ZEBULON | PEARCES ROAD AND PROCTOR STREET. CONSTRUCT ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 32000 | FY 2025: 32000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | ZEBULON | PEARCES ROAD AND PROCTOR STREET. CONSTRUCT ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | T | RIGHT-OF-WAY | 8000 | FY 2025: 8000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | ZEBULON | PEARCES ROAD AND PROCTOR STREET. CONSTRUCT ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 1120000 | FY 2026: 560000; FY 2027: 560000
HN-0018 | Highway | NCDOT Selected (Other Selection Process) | ZEBULON | PEARCES ROAD AND PROCTOR STREET. CONSTRUCT ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Exempt |  | T | CONSTRUCTION | 280000 | FY 2026: 140000; FY 2027: 140000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64/ US 74A | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | RUTHERFORD | 13 | Foothills RPO |  | Region G |  | CRP550 | ENGINEERING | 520000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64/ US 74A | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | RUTHERFORD | 13 | Foothills RPO |  | Region G |  | T(M) | ENGINEERING | 130000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64/ US 74A | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | RUTHERFORD | 13 | Foothills RPO |  | Region G |  | CRP550 | RIGHT-OF-WAY | 2640000 | FY 2025: 2640000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64/ US 74A | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | RUTHERFORD | 13 | Foothills RPO |  | Region G |  | T(M) | RIGHT-OF-WAY | 660000 | FY 2025: 660000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64/ US 74A | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | RUTHERFORD | 13 | Foothills RPO |  | Region G |  | CRP550 | UTILITIES | 200000 | FY 2025: 200000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64/ US 74A | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | RUTHERFORD | 13 | Foothills RPO |  | Region G |  | T(M) | UTILITIES | 50000 | FY 2025: 50000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64/ US 74A | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | RUTHERFORD | 13 | Foothills RPO |  | Region G |  | CRP550 | CONSTRUCTION | 2320000 | FY 2026: 2320000
HN-0019 | Highway | NCDOT Selected (Other Selection Process) | US 64/ US 74A | NORTH WASHINGTON STREET INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | RUTHERFORD | 13 | Foothills RPO |  | Region G |  | T(M) | CONSTRUCTION | 580000 | FY 2026: 580000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1312 (OXENDINE SCHOOL ROAD/RED HILL ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | ENGINEERING | 326000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1312 (OXENDINE SCHOOL ROAD/RED HILL ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | ENGINEERING | 82000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1312 (OXENDINE SCHOOL ROAD/RED HILL ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | RIGHT-OF-WAY | 120000 | FY 2025: 120000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1312 (OXENDINE SCHOOL ROAD/RED HILL ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 30000 | FY 2025: 30000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1312 (OXENDINE SCHOOL ROAD/RED HILL ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | CONSTRUCTION | 2274000 | FY 2026: 1444000; FY 2027: 830000
HN-0020 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1312 (OXENDINE SCHOOL ROAD/RED HILL ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | CONSTRUCTION | 568000 | FY 2026: 361000; FY 2027: 207000
HN-0021 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1001 (SHANNON ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | ENGINEERING | 326000
HN-0021 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1001 (SHANNON ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | ENGINEERING | 82000
HN-0021 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1001 (SHANNON ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | RIGHT-OF-WAY | 120000 | FY 2025: 120000
HN-0021 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1001 (SHANNON ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 30000 | FY 2025: 30000
HN-0021 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1001 (SHANNON ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | CONSTRUCTION | 2274000 | FY 2026: 1444000; FY 2027: 830000
HN-0021 | Highway | NCDOT Selected (Other Selection Process) | NC 71 | AT SR 1001 (SHANNON ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | CONSTRUCTION | 568000 | FY 2026: 361000; FY 2027: 207000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | AT NC 904. CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | ENGINEERING | 486000 | FY 2025: 160000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | AT NC 904. CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | ENGINEERING | 122000 | FY 2025: 40000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | AT NC 904. CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | RIGHT-OF-WAY | 120000 | FY 2025: 120000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | AT NC 904. CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 30000 | FY 2025: 30000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | AT NC 904. CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | CRPLT5 | CONSTRUCTION | 2274000 | FY 2026: 1444000; FY 2027: 830000
HN-0022 | Highway | NCDOT Selected (Other Selection Process) | NC 130 | AT NC 904. CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | T(M) | CONSTRUCTION | 568000 | FY 2026: 361000; FY 2027: 207000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 BUSINESS (MADISON STREET) | AT SR 1916 (LEE STREET), AND SR 1953 (FRANKLIN STREET). CONSTRUCT ROUNDABOUT TO REPLACE EXISTING TRAFFIC SIGNAL. | 0.5 | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | CRPLT5 | ENGINEERING | 320000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 BUSINESS (MADISON STREET) | AT SR 1916 (LEE STREET), AND SR 1953 (FRANKLIN STREET). CONSTRUCT ROUNDABOUT TO REPLACE EXISTING TRAFFIC SIGNAL. | 0.5 | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | T(M) | ENGINEERING | 80000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 BUSINESS (MADISON STREET) | AT SR 1916 (LEE STREET), AND SR 1953 (FRANKLIN STREET). CONSTRUCT ROUNDABOUT TO REPLACE EXISTING TRAFFIC SIGNAL. | 0.5 | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | CRPLT5 | RIGHT-OF-WAY | 80000 | FY 2025: 80000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 BUSINESS (MADISON STREET) | AT SR 1916 (LEE STREET), AND SR 1953 (FRANKLIN STREET). CONSTRUCT ROUNDABOUT TO REPLACE EXISTING TRAFFIC SIGNAL. | 0.5 | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | T(M) | RIGHT-OF-WAY | 20000 | FY 2025: 20000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 BUSINESS (MADISON STREET) | AT SR 1916 (LEE STREET), AND SR 1953 (FRANKLIN STREET). CONSTRUCT ROUNDABOUT TO REPLACE EXISTING TRAFFIC SIGNAL. | 0.5 | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | CRPLT5 | CONSTRUCTION | 2400000 | FY 2026: 1524000; FY 2027: 876000
HN-0023 | Highway | NCDOT Selected (Other Selection Process) | US 701 BUSINESS (MADISON STREET) | AT SR 1916 (LEE STREET), AND SR 1953 (FRANKLIN STREET). CONSTRUCT ROUNDABOUT TO REPLACE EXISTING TRAFFIC SIGNAL. | 0.5 | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | T(M) | CONSTRUCTION | 600000 | FY 2026: 381000; FY 2027: 219000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | VEAZEY ROAD | INTERSECTION OF VEAZEY ROAD, CENTRAL AVENUE, AND WESTBROOK. INSTALL ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Division 5 |  | CRPLT5 | ENGINEERING | 428000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | VEAZEY ROAD | INTERSECTION OF VEAZEY ROAD, CENTRAL AVENUE, AND WESTBROOK. INSTALL ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Division 5 |  | CRPLT5 | ENGINEERING | 132000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | VEAZEY ROAD | INTERSECTION OF VEAZEY ROAD, CENTRAL AVENUE, AND WESTBROOK. INSTALL ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Division 5 |  | T(M) | ENGINEERING | 33000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | VEAZEY ROAD | INTERSECTION OF VEAZEY ROAD, CENTRAL AVENUE, AND WESTBROOK. INSTALL ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Division 5 |  | L(M) | ENGINEERING | 107000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | VEAZEY ROAD | INTERSECTION OF VEAZEY ROAD, CENTRAL AVENUE, AND WESTBROOK. INSTALL ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Division 5 |  | CRPLT5 | CONSTRUCTION | 1607000 | FY 2025: 1407000; FY 2026: 184000
HN-0024 | Highway | NCDOT Selected (Other Selection Process) | VEAZEY ROAD | INTERSECTION OF VEAZEY ROAD, CENTRAL AVENUE, AND WESTBROOK. INSTALL ROUNDABOUT. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO | HF REPRESENTS HIGH-IMPACT LOW-COST HIGHWAY FUNDS | Division 5 |  | HF(M) | CONSTRUCTION | 402000 | FY 2025: 352000; FY 2026: 46000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | BLADEN | 6 | Mid-Carolina RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 220000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | BLADEN | 6 | Mid-Carolina RPO |  | Exempt |  | T(M) | ENGINEERING | 55000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | BLADEN | 6 | Mid-Carolina RPO |  | Exempt |  | CRPLT5 | UTILITIES | 16000 | FY 2025: 16000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | BLADEN | 6 | Mid-Carolina RPO |  | Exempt |  | T(M) | UTILITIES | 4000 | FY 2025: 4000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | BLADEN | 6 | Mid-Carolina RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 19000 | FY 2025: 19000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | BLADEN | 6 | Mid-Carolina RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 1881000 | FY 2026: 1881000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | BLADEN | 6 | Mid-Carolina RPO |  | Exempt |  | T(M) | CONSTRUCTION | 470000 | FY 2026: 470000
HN-0025 | Highway | NCDOT Selected (Other Selection Process) | NC 410 / NC 131 | AT NC 211 BYPASS IN BLADENBORO. REPLACE EXISTING TRAFFIC SIGNAL WITH ROUNDABOUT. | 0.5 | BLADEN | 6 | Mid-Carolina RPO |  | Exempt |  | T(M) | CONSTRUCTION | 5000 | FY 2025: 5000
HN-0026 | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS. |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Exempt
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 639000 | FY 2026: 639000
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 601000
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 658000 | FY 2027: 658000
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 619000 | FY 2025: 619000
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 164000 | FY 2027: 164000
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 150000
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 155000 | FY 2025: 155000
HN-0026A | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 160000 | FY 2026: 160000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 641000 | FY 2027: 641000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 586000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 604000 | FY 2025: 604000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 622000 | FY 2026: 622000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 155000 | FY 2026: 155000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 146000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 151000 | FY 2025: 151000
HN-0026B | Highway | NCDOT Selected (Other Selection Process) | CENTRAL PINES REGIONAL COUNCIL | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC). |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | IMPLEMENTATION | 160000 | FY 2027: 160000
HN-0027 | Highway | NCDOT Selected (Other Selection Process) | NC 275 / NC 279 | US 321 TO US 321 BUSINESS. EXTEND RIGHT TURN LANE. ADD RIGHT TURN LANE ON SOUTHBOUND OFF RAMP FROM US 321. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS | Region F |  | CRPANY | ENGINEERING | 164000
HN-0027 | Highway | NCDOT Selected (Other Selection Process) | NC 275 / NC 279 | US 321 TO US 321 BUSINESS. EXTEND RIGHT TURN LANE. ADD RIGHT TURN LANE ON SOUTHBOUND OFF RAMP FROM US 321. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS | Region F |  | HF(M) | ENGINEERING | 41000
HN-0027 | Highway | NCDOT Selected (Other Selection Process) | NC 275 / NC 279 | US 321 TO US 321 BUSINESS. EXTEND RIGHT TURN LANE. ADD RIGHT TURN LANE ON SOUTHBOUND OFF RAMP FROM US 321. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS | Region F |  | CRPANY | CONSTRUCTION | 832000 | FY 2025: 832000
HN-0027 | Highway | NCDOT Selected (Other Selection Process) | NC 275 / NC 279 | US 321 TO US 321 BUSINESS. EXTEND RIGHT TURN LANE. ADD RIGHT TURN LANE ON SOUTHBOUND OFF RAMP FROM US 321. | 0.5 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | HF(M) REPRESENTS SPOT MOBILITY HIGHWAY FUNDS | Region F |  | HF(M) | CONSTRUCTION | 208000 | FY 2025: 208000
HN-0028 | Highway | NCDOT Selected (Other Selection Process) | US 421 | SR 1710 (SPEER BRIDGE ROAD) INTERCHANGE. CONSTRUCT ROUNDABOUTS AT RAMP TERMINALS. |  | YADKIN | 11 | Northwest Piedmont RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 3600000 | FY 2025: 3600000
HN-0028 | Highway | NCDOT Selected (Other Selection Process) | US 421 | SR 1710 (SPEER BRIDGE ROAD) INTERCHANGE. CONSTRUCT ROUNDABOUTS AT RAMP TERMINALS. |  | YADKIN | 11 | Northwest Piedmont RPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 400000 | FY 2025: 400000
HN-0029 | Highway | NCDOT Selected (Other Selection Process) | NC 141 | SR 1533 (HENDRIX ROAD) INTERSECTION. CONSTRUCT LEFT TURN LANE. |  | CHEROKEE | 14 | Southwestern RPO |  | Region G |  | CRPLT5 | CONSTRUCTION | 480000
HN-0029 | Highway | NCDOT Selected (Other Selection Process) | NC 141 | SR 1533 (HENDRIX ROAD) INTERSECTION. CONSTRUCT LEFT TURN LANE. |  | CHEROKEE | 14 | Southwestern RPO |  | Region G |  | T(M) | CONSTRUCTION | 120000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (CASCADE LAKE ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 595000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (CASCADE LAKE ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | T(M) | ENGINEERING | 149000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (CASCADE LAKE ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 1056000 | FY 2025: 1056000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (CASCADE LAKE ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 264000 | FY 2025: 264000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (CASCADE LAKE ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 3360000 | FY 2026: 3360000
HN-0031 | Highway | NCDOT Selected (Other Selection Process) | US 276 | SR 1536 (CASCADE LAKE ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Exempt |  | T(M) | CONSTRUCTION | 840000 | FY 2026: 840000
HN-0032 | Highway | NCDOT Selected (Other Selection Process) | US 52 | SR 1654 (MERNER TERRACE) INTERSECTION IN MISENHEIMER. CONSTRUCT ROUNDABOUT. | 0.5 | STANLY | 10 | Rocky River RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 440000
HN-0032 | Highway | NCDOT Selected (Other Selection Process) | US 52 | SR 1654 (MERNER TERRACE) INTERSECTION IN MISENHEIMER. CONSTRUCT ROUNDABOUT. | 0.5 | STANLY | 10 | Rocky River RPO |  | Exempt |  | T(M) | ENGINEERING | 110000
HN-0032 | Highway | NCDOT Selected (Other Selection Process) | US 52 | SR 1654 (MERNER TERRACE) INTERSECTION IN MISENHEIMER. CONSTRUCT ROUNDABOUT. | 0.5 | STANLY | 10 | Rocky River RPO |  | Exempt |  | CRPLT5 | RIGHT-OF-WAY | 155000 | FY 2025: 155000
HN-0032 | Highway | NCDOT Selected (Other Selection Process) | US 52 | SR 1654 (MERNER TERRACE) INTERSECTION IN MISENHEIMER. CONSTRUCT ROUNDABOUT. | 0.5 | STANLY | 10 | Rocky River RPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 39000 | FY 2025: 39000
HN-0032 | Highway | NCDOT Selected (Other Selection Process) | US 52 | SR 1654 (MERNER TERRACE) INTERSECTION IN MISENHEIMER. CONSTRUCT ROUNDABOUT. | 0.5 | STANLY | 10 | Rocky River RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 2102000 | FY 2026: 2102000
HN-0032 | Highway | NCDOT Selected (Other Selection Process) | US 52 | SR 1654 (MERNER TERRACE) INTERSECTION IN MISENHEIMER. CONSTRUCT ROUNDABOUT. | 0.5 | STANLY | 10 | Rocky River RPO |  | Exempt |  | T(M) | CONSTRUCTION | 525000 | FY 2026: 525000
HN-0033 | Highway | Locally Selected | NC 55 | SR 1744 (OLD SEVEN SPRINGS ROAD / INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. |  | WAYNE | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | ENGINEERING | 880000
HN-0033 | Highway | Locally Selected | NC 55 | SR 1744 (OLD SEVEN SPRINGS ROAD / INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. |  | WAYNE | 4 | Upper Coastal Plain RPO |  | Exempt |  | T(M) | ENGINEERING | 220000
HN-0033 | Highway | Locally Selected | NC 55 | SR 1744 (OLD SEVEN SPRINGS ROAD / INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. |  | WAYNE | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | RIGHT-OF-WAY | 530000 | FY 2026: 530000
HN-0033 | Highway | Locally Selected | NC 55 | SR 1744 (OLD SEVEN SPRINGS ROAD / INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. |  | WAYNE | 4 | Upper Coastal Plain RPO |  | Exempt |  | T(M) | RIGHT-OF-WAY | 132000 | FY 2026: 132000
HN-0033 | Highway | Locally Selected | NC 55 | SR 1744 (OLD SEVEN SPRINGS ROAD / INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. |  | WAYNE | 4 | Upper Coastal Plain RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 5054000 | FY 2026: 5054000
HN-0033 | Highway | Locally Selected | NC 55 | SR 1744 (OLD SEVEN SPRINGS ROAD / INDIAN SPRINGS ROAD) INTERSECTION IN MOUNT OLIVE. CONSTRUCT ROUNDABOUT. |  | WAYNE | 4 | Upper Coastal Plain RPO |  | Exempt |  | T(M) | CONSTRUCTION | 1264000 | FY 2026: 1264000
HN-0034 | Highway | Locally Selected | VARIOUS | LOCATIONS IN COLUMBUS COUNTY. PURCHASE AND INSTALL 24 ELECTRIC VEHICLE CHARGING STATIONS. |  | COLUMBUS | 6 | Cape Fear RPO |  | Exempt |  | CRPANY | ENGINEERING | 10000 | FY 2025: 10000
HN-0034 | Highway | Locally Selected | VARIOUS | LOCATIONS IN COLUMBUS COUNTY. PURCHASE AND INSTALL 24 ELECTRIC VEHICLE CHARGING STATIONS. |  | COLUMBUS | 6 | Cape Fear RPO |  | Exempt |  | L(M) | ENGINEERING | 2000 | FY 2025: 2000
HN-0034 | Highway | Locally Selected | VARIOUS | LOCATIONS IN COLUMBUS COUNTY. PURCHASE AND INSTALL 24 ELECTRIC VEHICLE CHARGING STATIONS. |  | COLUMBUS | 6 | Cape Fear RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 115000 | FY 2026: 115000
HN-0034 | Highway | Locally Selected | VARIOUS | LOCATIONS IN COLUMBUS COUNTY. PURCHASE AND INSTALL 24 ELECTRIC VEHICLE CHARGING STATIONS. |  | COLUMBUS | 6 | Cape Fear RPO |  | Exempt |  | L(M) | CONSTRUCTION | 29000 | FY 2026: 29000
HN-0035 | Highway | NCDOT Selected (Other Selection Process) | VARIOUS | LOCATIONS IN CHATHAM COUNTY. PURCHASE AND INSTALL FOUR ELECTRIC VEHICLE CHARGING STATIONS. |  | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRPANY | ENGINEERING | 59000 | FY 2025: 59000
HN-0035 | Highway | NCDOT Selected (Other Selection Process) | VARIOUS | LOCATIONS IN CHATHAM COUNTY. PURCHASE AND INSTALL FOUR ELECTRIC VEHICLE CHARGING STATIONS. |  | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | ENGINEERING | 15000 | FY 2025: 15000
HN-0035 | Highway | NCDOT Selected (Other Selection Process) | VARIOUS | LOCATIONS IN CHATHAM COUNTY. PURCHASE AND INSTALL FOUR ELECTRIC VEHICLE CHARGING STATIONS. |  | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CRPANY | CONSTRUCTION | 37000 | FY 2026: 37000
HN-0035 | Highway | NCDOT Selected (Other Selection Process) | VARIOUS | LOCATIONS IN CHATHAM COUNTY. PURCHASE AND INSTALL FOUR ELECTRIC VEHICLE CHARGING STATIONS. |  | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | CONSTRUCTION | 9000 | FY 2026: 9000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | ROBERTA ROAD | MAIN STREET INTERSECTION. CONSTRUCT ROUNDABOUT. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | CMAQ | ENGINEERING | 572000 | FY 2025: 572000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | ROBERTA ROAD | MAIN STREET INTERSECTION. CONSTRUCT ROUNDABOUT. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L | ENGINEERING | 143000 | FY 2025: 143000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | ROBERTA ROAD | MAIN STREET INTERSECTION. CONSTRUCT ROUNDABOUT. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | CMAQ | RIGHT-OF-WAY | 200000 | FY 2027: 200000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | ROBERTA ROAD | MAIN STREET INTERSECTION. CONSTRUCT ROUNDABOUT. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L | RIGHT-OF-WAY | 50000 | FY 2027: 50000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | ROBERTA ROAD | MAIN STREET INTERSECTION. CONSTRUCT ROUNDABOUT. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | CMAQ | CONSTRUCTION | 1393000 | FY 2028: 1393000
HN-0036 | Highway | NCDOT Selected (Other Selection Process) | ROBERTA ROAD | MAIN STREET INTERSECTION. CONSTRUCT ROUNDABOUT. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L | CONSTRUCTION | 348000 | FY 2028: 348000
HO-0001 | Highway | Other | VARIOUS | NCDOT MULTI-MODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. |  | WAKE | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT. "HF(M)" FUNDS REFLECT SPOT MOBILITY MATCHING FUNDS. | Exempt |  | DP | ENGINEERING | 64000
HO-0001 | Highway | Other | VARIOUS | NCDOT MULTI-MODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. |  | WAKE | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT. "HF(M)" FUNDS REFLECT SPOT MOBILITY MATCHING FUNDS. | Exempt |  | HF(M) | ENGINEERING | 247000
HO-0001 | Highway | Other | VARIOUS | NCDOT MULTI-MODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. |  | WAKE | 5 | Capital Area MPO | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT. "HF(M)" FUNDS REFLECT SPOT MOBILITY MATCHING FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 227000
HO-0001AA | Highway | Other | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | DP | ENGINEERING | 186000
HO-0001AA | Highway | Other | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | HF(M) | ENGINEERING | 183000
HO-0001AA | Highway | Other | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | DP | CONSTRUCTION | 1491000 | FY 2025: 282000; FY 2026: 35000
HO-0001AA | Highway | Other | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Exempt |  | HF(M) | CONSTRUCTION | 1490000 | FY 2025: 282000; FY 2026: 35000
HO-0001AB | Highway | Other | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | DP | ENGINEERING | 75000
HO-0001AB | Highway | Other | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | HF(M) | ENGINEERING | 75000
HO-0001AB | Highway | Other | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | DP | CONSTRUCTION | 84000
HO-0001AB | Highway | Other | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | HF(M) | CONSTRUCTION | 84000 | FY 2025: 29000
HO-0001AC | Highway | Other | NCSU CAMPUS | ECO DRIVING APPLICATION |  | WAKE | 5 | Capital Area MPO | PROJECT DELETED | Exempt |  | DP | ENGINEERING | 37000
HO-0001AC | Highway | Other | NCSU CAMPUS | ECO DRIVING APPLICATION |  | WAKE | 5 | Capital Area MPO | PROJECT DELETED | Exempt |  | HF(M) | ENGINEERING | 37000
HO-0001AC | Highway | Other | NCSU CAMPUS | ECO DRIVING APPLICATION |  | WAKE | 5 | Capital Area MPO | PROJECT DELETED | Exempt |  | DP | CONSTRUCTION | 352000
HO-0001AC | Highway | Other | NCSU CAMPUS | ECO DRIVING APPLICATION |  | WAKE | 5 | Capital Area MPO | PROJECT DELETED | Exempt |  | HF(M) | CONSTRUCTION | 352000
HO-0001B | Highway | Other | NCSU CAMPUS | SYSTEMS ENGINEERING, GRANT ADMINISTRATION |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | DP | ENGINEERING | 50000
HO-0001B | Highway | Other | NCSU CAMPUS | SYSTEMS ENGINEERING, GRANT ADMINISTRATION |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | HF(M) | ENGINEERING | 150000
HO-0001C | Highway | Other | NCSU CAMPUS | BEFORE & AFTER STUDY, EXPANSION FEASIBILITY STUDY |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | DP | ENGINEERING | 156000
HO-0001C | Highway | Other | NCSU CAMPUS | BEFORE & AFTER STUDY, EXPANSION FEASIBILITY STUDY |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | HF(M) | ENGINEERING | 154000
HO-0002 | Highway | Other | US 74 | I-40 IN ASHEVILLE TO I-140 IN WILMINGTON. IMPLEMENT BROADBAND, ITS, AND RESILIENCY IMPROVEMENTS. | 279.24 | COLUMBUS, ROBESON, CLEVELAND, ANSON, GASTON, POLK, SCOTLAND, HENDERSON, RICHMOND, RUTHERFORD, MECKLENBURG, BRUNSWICK, BUNCOMBE, UNION | 3, 6, 8, 10, 12, 13, 14 | Lumber River RPO, Cape Fear RPO, Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS.
HO-0002A | Highway | Other | US 74 | I-40 IN ASHEVILLE TO I-77 AT I-485 (SOUTH) IN CHARLOTTE. INSTALL BROADBAND. | 123.09 | CLEVELAND, POLK, GASTON, HENDERSON, RUTHERFORD, MECKLENBURG, BUNCOMBE | 10, 12, 13, 14 | Gaston-Cleveland-Lincoln MPO, Foothills RPO, French Broad River MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002B, AND HO-0002C. | Statewide Mobility |  | HSIP | CONSTRUCTION | 18435000
HO-0002B | Highway | Other | US 74 | EASTERN END OF MONROE BYPASS TO I-95 IN LUMBERTON. INSTALL BROADBAND AND ITS COMPONENTS INCLUDING CONNECTIONS TO SIGNAL SYSTEMS, DMS, AND CCTV. | 86.48 | ANSON, ROBESON, RICHMOND, SCOTLAND, UNION | 6, 8, 10 | Lumber River RPO, Rocky River RPO, Charlotte Regional TPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002C. UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 14216000
HO-0002C | Highway | Other | US 74 | I-95 IN LUMBERTON TO I-140 IN WILMINGTON. INSTALL BROADBAND. | 69.67 | COLUMBUS, ROBESON, BRUNSWICK | 3, 6 | Cape Fear RPO, Lumber River RPO, Wilmington Urban Area MPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002B. UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 10456000
HO-0002D | Highway | Other | US 74 | EASTERN END OF MONROE BYPASS TO I-140 IN WILMINGTON. VULNERABILITY ASSESSMENTS, INSTALLATION OF FLOOD GAUGES, AND FLOOD MONITORING. | 156.15 | COLUMBUS, ROBESON, ANSON, SCOTLAND, RICHMOND, BRUNSWICK, UNION | 3, 6, 8, 10 | Lumber River RPO, Cape Fear RPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO |  | Statewide Mobility |  | DP | ENGINEERING | 1760000
HO-0002D | Highway | Other | US 74 | EASTERN END OF MONROE BYPASS TO I-140 IN WILMINGTON. VULNERABILITY ASSESSMENTS, INSTALLATION OF FLOOD GAUGES, AND FLOOD MONITORING. | 156.15 | COLUMBUS, ROBESON, ANSON, SCOTLAND, RICHMOND, BRUNSWICK, UNION | 3, 6, 8, 10 | Lumber River RPO, Cape Fear RPO, Rocky River RPO, Charlotte Regional TPO, Wilmington Urban Area MPO |  | Statewide Mobility |  | T | ENGINEERING | 440000
HO-0003 | Highway | Other | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. |  | HAYWOOD | 14 | Land-of-Sky RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 100000
HO-0003 | Highway | Other | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. |  | HAYWOOD | 14 | Land-of-Sky RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 100000
HO-0003 | Highway | Other | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. |  | HAYWOOD | 14 | Land-of-Sky RPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 25000
HO-0003 | Highway | Other | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. |  | HAYWOOD | 14 | Land-of-Sky RPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 25000
HO-0004 | Highway | Other | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. |  | SWAIN | 14 | Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 200000
HO-0004 | Highway | Other | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. |  | SWAIN | 14 | Southwestern RPO | IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 100000
HO-0004 | Highway | Other | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. |  | SWAIN | 14 | Southwestern RPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 50000
HO-0004 | Highway | Other | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. |  | SWAIN | 14 | Southwestern RPO | IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 25000
HO-0005 | Highway | Other | VARIOUS | NCDOT TRAFFIC SYSTEMS OPERATIONS. INSTALL STATEWIDE ITS DEVICE OPERATIONS. |  | MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, NASH, DAVIE, EDGECOMBE, GRANVILLE, HAYWOOD | 4, 5, 7, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Winston-Salem Area TPO, Greensboro Urban Area MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Rocky Mount Urban Area MPO, Ker | UNDER CONSTRUCTION. | Exempt |  | CMAQ | CONSTRUCTION | 17284000
HO-0005 | Highway | Other | VARIOUS | NCDOT TRAFFIC SYSTEMS OPERATIONS. INSTALL STATEWIDE ITS DEVICE OPERATIONS. |  | MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, NASH, DAVIE, EDGECOMBE, GRANVILLE, HAYWOOD | 4, 5, 7, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Winston-Salem Area TPO, Greensboro Urban Area MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Rocky Mount Urban Area MPO, Ker | UNDER CONSTRUCTION. | Exempt |  | T(M) | CONSTRUCTION | 4321000
HO-0009 | Highway | Other | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. |  | MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, LINCOLN, NASH, CHATHAM, DAVIE, EDGECOMBE, FRANKLIN, GRANVILLE, HAYWOOD, PERSON, SWAIN | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 595000
HO-0009 | Highway | Other | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. |  | MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, LINCOLN, NASH, CHATHAM, DAVIE, EDGECOMBE, FRANKLIN, GRANVILLE, HAYWOOD, PERSON, SWAIN | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS | Exempt |  | CMAQ | IMPLEMENTATION | 578000
HO-0009 | Highway | Other | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. |  | MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, LINCOLN, NASH, CHATHAM, DAVIE, EDGECOMBE, FRANKLIN, GRANVILLE, HAYWOOD, PERSON, SWAIN | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS | Exempt |  | O | IMPLEMENTATION | 282000
HO-0009 | Highway | Other | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. |  | MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, LINCOLN, NASH, CHATHAM, DAVIE, EDGECOMBE, FRANKLIN, GRANVILLE, HAYWOOD, PERSON, SWAIN | 4, 5, 7, 8, 9, 10, 12, 14 | Charlotte Regional TPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Cabarrus-Rowan MPO, Winston-Salem Area TPO, Gaston-Cleveland-Lincoln MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Greater Hickory MPO, Kerr-Tar RPO, Rocky Mount Urban | "O" FUNDING REFLECTS PARTICIPATION BY DAQ - IN PROGRESS | Exempt |  | L(M) | IMPLEMENTATION | 149000
HO-0010 | Highway | Other | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HO-0010A | Highway | Other | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT IN THE TRIANGLE AND METROLINA AREAS. |  | WAKE, IREDELL, MECKLENBURG, ROWAN, CLEVELAND, UNION, CABARRUS, GASTON, JOHNSTON, DURHAM, LINCOLN, FRANKLIN, ORANGE, CHATHAM, GRANVILLE, HARNETT | 4, 5, 6, 7, 8, 9, 10, 12 | Capital Area MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO, Cabarrus-Rowan MPO, Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | CRPANY | IMPLEMENTATION | 3200000
HO-0010A | Highway | Other | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT IN THE TRIANGLE AND METROLINA AREAS. |  | WAKE, IREDELL, MECKLENBURG, ROWAN, CLEVELAND, UNION, CABARRUS, GASTON, JOHNSTON, DURHAM, LINCOLN, FRANKLIN, ORANGE, CHATHAM, GRANVILLE, HARNETT | 4, 5, 6, 7, 8, 9, 10, 12 | Capital Area MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO, Cabarrus-Rowan MPO, Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | HF(M) | IMPLEMENTATION | 800000
HO-0010B | Highway | Other | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT ACROSS THE ENTIRE STATE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | IMPLEMENTATION | 31979000 | FY 2025: 31979000
HO-0010B | Highway | Other | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT ACROSS THE ENTIRE STATE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | IMPLEMENTATION | 33456000 | FY 2026: 33456000
HO-0010B | Highway | Other | STATEWIDE TRAFFIC OPERATIONS | IMPLEMENT STATEWIDE TRAFFIC OPERATIONS ACTIVITIES SUCH AS TRAFFIC MANAGEMENT CENTERS, TRAVELER INFORMATION, INTELLIGENT TRANSPORTATION SYSTEMS (ITS), AND TRAFFIC INCIDENT AND EVENT MANAGEMENT ACROSS THE ENTIRE STATE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | CMAQ | IMPLEMENTATION | 27785000
HO-0011 | Highway | Other | I-40 AND I-95 | I-40 FROM TENNESSEE STATE LINE TO MM 20 AND I-95 FROM EXIT 13 TO SOUTH OF PROPOSED I-295. IMPLEMENT SYSTEM TO PROVIDE REAL TIME ALERTS IN VEHICLES WHEN DRIVERS ENCOUNTER A ROAD ANOMALY REQUIRING THEM TO TAKE DRIVING ACTION. | 40 | HAYWOOD, ROBESON | 6, 14 | Land-of-Sky RPO, Lumber River RPO | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH. | Statewide Mobility |  | DP | IMPLEMENTATION | 1534000
HO-0011 | Highway | Other | I-40 AND I-95 | I-40 FROM TENNESSEE STATE LINE TO MM 20 AND I-95 FROM EXIT 13 TO SOUTH OF PROPOSED I-295. IMPLEMENT SYSTEM TO PROVIDE REAL TIME ALERTS IN VEHICLES WHEN DRIVERS ENCOUNTER A ROAD ANOMALY REQUIRING THEM TO TAKE DRIVING ACTION. | 40 | HAYWOOD, ROBESON | 6, 14 | Land-of-Sky RPO, Lumber River RPO | DP FUNDS REPRESENT FEDERAL SMART GRANT FUNDS. O FUNDS REPRESENT IN KIND MATCH. | Statewide Mobility |  | O | IMPLEMENTATION | 438000
HO-0012 | Highway | Other | BLUE RIDGE PARKWAY ASSOCIATION | UPDATE THE BLUE RIDGE PARKWAY ASSOCIATION TRAVEL PLANNER AND MAP BROCHURE. REDESIGN BLUE RIDGE PARKWAY WEBSITE AND MOBILE APPLICATION. IMPLEMENT MARKETING PLAN FOR BLUE RIDGE PARKWAY ASSOCIATION. |  | BUNCOMBE, ALLEGHANY, JACKSON, WATAUGA, ASHE, SWAIN, HAYWOOD, AVERY, McDOWELL, TRANSYLVANIA, YANCEY, MITCHELL, HENDERSON, WILKES, BURKE, CALDWELL | 11, 13, 14 | High Country RPO, French Broad River MPO, Southwestern RPO, Land-of-Sky RPO, Foothills RPO, Greater Hickory MPO | NATIONAL SCENIC BYWAYS GRANT AWARD: $460,000. DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING. LOCAL MATCH PROVIDED BY BLUE RIDGE PARKWAYS ASSOCIATION. | Exempt |  | DP | IMPLEMENTATION | 460000
HO-0012 | Highway | Other | BLUE RIDGE PARKWAY ASSOCIATION | UPDATE THE BLUE RIDGE PARKWAY ASSOCIATION TRAVEL PLANNER AND MAP BROCHURE. REDESIGN BLUE RIDGE PARKWAY WEBSITE AND MOBILE APPLICATION. IMPLEMENT MARKETING PLAN FOR BLUE RIDGE PARKWAY ASSOCIATION. |  | BUNCOMBE, ALLEGHANY, JACKSON, WATAUGA, ASHE, SWAIN, HAYWOOD, AVERY, McDOWELL, TRANSYLVANIA, YANCEY, MITCHELL, HENDERSON, WILKES, BURKE, CALDWELL | 11, 13, 14 | High Country RPO, French Broad River MPO, Southwestern RPO, Land-of-Sky RPO, Foothills RPO, Greater Hickory MPO | NATIONAL SCENIC BYWAYS GRANT AWARD: $460,000. DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING. LOCAL MATCH PROVIDED BY BLUE RIDGE PARKWAYS ASSOCIATION. | Exempt |  | L | IMPLEMENTATION | 115000
HO-0013 | Highway | Other | CHAPEL HILL | FRANKLIN STREET AND ROSEMARY STREET, AND THE STREETS IN BETWEEN FROM MERRITT MILL ROAD TO HENDERSON STREET IN DOWNTOWN CHAPEL HILL. INSTALL NEW MAST ARM AND CURB AND SIDEWALK IMPROVEMENTS. | 2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. | Exempt |  | DP | ENGINEERING | 400000
HO-0013 | Highway | Other | CHAPEL HILL | FRANKLIN STREET AND ROSEMARY STREET, AND THE STREETS IN BETWEEN FROM MERRITT MILL ROAD TO HENDERSON STREET IN DOWNTOWN CHAPEL HILL. INSTALL NEW MAST ARM AND CURB AND SIDEWALK IMPROVEMENTS. | 2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. | Exempt |  | DP | RIGHT-OF-WAY | 250000 | FY 2025: 250000
HO-0013 | Highway | Other | CHAPEL HILL | FRANKLIN STREET AND ROSEMARY STREET, AND THE STREETS IN BETWEEN FROM MERRITT MILL ROAD TO HENDERSON STREET IN DOWNTOWN CHAPEL HILL. INSTALL NEW MAST ARM AND CURB AND SIDEWALK IMPROVEMENTS. | 2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. | Exempt |  | DP | UTILITIES | 550000 | FY 2026: 550000
HO-0013 | Highway | Other | CHAPEL HILL | FRANKLIN STREET AND ROSEMARY STREET, AND THE STREETS IN BETWEEN FROM MERRITT MILL ROAD TO HENDERSON STREET IN DOWNTOWN CHAPEL HILL. INSTALL NEW MAST ARM AND CURB AND SIDEWALK IMPROVEMENTS. | 2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. | Exempt |  | DP | CONSTRUCTION | 800000 | FY 2026: 800000
HO-0013 | Highway | Other | CHAPEL HILL | FRANKLIN STREET AND ROSEMARY STREET, AND THE STREETS IN BETWEEN FROM MERRITT MILL ROAD TO HENDERSON STREET IN DOWNTOWN CHAPEL HILL. INSTALL NEW MAST ARM AND CURB AND SIDEWALK IMPROVEMENTS. | 2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | DP FUNDS REPRESENTS 2023 FEDERAL APPROPRIATIONS EARMARK FUNDS OF $2M. | Exempt |  | L | CONSTRUCTION | 500000 | FY 2026: 500000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HSIP | ENGINEERING | 1282000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HF | ENGINEERING | 148000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HSIP | RIGHT-OF-WAY | 105000 | FY 2025: 105000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HF | RIGHT-OF-WAY | 15000 | FY 2025: 15000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HSIP | UTILITIES | 97000 | FY 2025: 97000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HF | UTILITIES | 13000 | FY 2025: 13000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | DP | CONSTRUCTION | 8600000 | FY 2026: 8600000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HSIP | CONSTRUCTION | 667000 | FY 2026: 7000; FY 2027: 443000; FY 2028: 217000
HO-0014 | Highway | Other | NC 72 | FROM NC 41 TO NC 211 IN LUMBERTON. CONSTRUCT COMPLETE STREET IMPROVEMENTS. | 2.06 | ROBESON | 6 | Lumber River RPO | SAFE LUMBERTON PROJECT. DP FUNDS REPRESENT FEDERAL RAISE GRANT FUNDS. "HF" FUNDS REPRESENT SPOT SAFETY PROGRAM FUNDS FOR NON-FEDERAL MATCH. | Region C |  | HF | CONSTRUCTION | 74000 | FY 2026: 1000; FY 2027: 49000; FY 2028: 24000
HO-0015 | Highway | Other | BLUE RIDGE PARKWAY | MARKETING AND BRANDING FOR BLUE RIDGE PARKWAY ASSOCIATION. |  | AVERY, BUNCOMBE, BURKE, HAYWOOD, HENDERSON, JACKSON, McDOWELL, MITCHELL, SWAIN, TRANSYLVANIA, ALLEGHANY, ASHE, CALDWELL, WATAUGA, WILKES | 11, 13, 14 | French Broad River MPO, Greater Hickory MPO, High Country RPO, Land-of-Sky RPO, Southwestern RPO, Foothills RPO | DP FUNDS REPRESENT NATIONAL SCENIC BYWAYS GRANT FUNDING. | Exempt |  | DP | IMPLEMENTATION | 460000
HO-0016 | Highway | Other | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | ENGINEERING | 686000 | FY 2025: 686000
HO-0016 | Highway | Other | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L | ENGINEERING | 171000 | FY 2025: 171000
HO-0016 | Highway | Other | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 3232000 | FY 2026: 3232000
HO-0016 | Highway | Other | VARIOUS | SARDIS ROAD / RAMA ROAD; IDLEWILD ROAD; MOUNT HOLLY ROAD; WILKINSON BOULEVARD. INSTALL ITS INFRASTRUCTURE, IMPROVE TRAFFIC FLOW, AND UPGRADE SIGNALS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 808000 | FY 2026: 808000
HO-0017 | Highway | Other | DURHAM | CONSTRUCT EV CHARGING STATIONS ALONG I-85, US 70, AND POSSIBLY I-40. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | DP | CONSTRUCTION | 4864000 | FY 2025: 4864000
HO-0017 | Highway | Other | DURHAM | CONSTRUCT EV CHARGING STATIONS ALONG I-85, US 70, AND POSSIBLY I-40. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | L(M) | CONSTRUCTION | 1216000 | FY 2025: 1216000
HO-0018 | Highway | Other | KINGS MOUNTAIN | INSTALL 20 EV CHARGERS ACROSS FIVE LOCATIONS IN KINGS MOUNTAIN. |  | CLEVELAND, GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. | Exempt |  | DP | CONSTRUCTION | 823000 | FY 2025: 823000
HO-0018 | Highway | Other | KINGS MOUNTAIN | INSTALL 20 EV CHARGERS ACROSS FIVE LOCATIONS IN KINGS MOUNTAIN. |  | CLEVELAND, GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. | Exempt |  | L | CONSTRUCTION | 206000 | FY 2025: 206000
HO-0019 | Highway | Other | VARIOUS | INSTALL EV CHARGERS AT MULTIPLE COMMUNITY COLLEGES: BLUE RIDGE COMMUNITY COLLEGE CENTRAL CAROLINA COMMUNITY COLLEGE EDGECOMBE COMMUNITY COLLEGE FAYETTEVILLE COMMUNITY COLLEGE GASTON COLLEGE MARTIN COMMUNITY COLLEGE NASH COMMUNITY COLLEGE RANDOLPH COMMUNITY COLLEGE ROANOKE-CHOWAN COMMUNITY COLLEGE WAKE TECHNICAL COMMUNITY COLLEGE |  | CHATHAM, CUMBERLAND, EDGECOMBE, GASTON, HARNETT, HENDERSON, LEE, LINCOLN, MARTIN, TRANSYLVANIA, BERTIE, HERTFORD, NASH, RANDOLPH, WAKE | 1, 4, 5, 6, 8, 12, 14 | Capital Area MPO, Central Pines RPO, Fayetteville Area MPO, French Broad River MPO, Gaston-Cleveland-Lincoln MPO, Land-of-Sky RPO, Mid-Carolina RPO, Peanut Belt RPO, Piedmont Triad RPO, Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. HF REPRESENT CONTINGENCY FUNDS. | Exempt |  | DP | CONSTRUCTION | 1007000 | FY 2025: 1007000
HO-0019 | Highway | Other | VARIOUS | INSTALL EV CHARGERS AT MULTIPLE COMMUNITY COLLEGES: BLUE RIDGE COMMUNITY COLLEGE CENTRAL CAROLINA COMMUNITY COLLEGE EDGECOMBE COMMUNITY COLLEGE FAYETTEVILLE COMMUNITY COLLEGE GASTON COLLEGE MARTIN COMMUNITY COLLEGE NASH COMMUNITY COLLEGE RANDOLPH COMMUNITY COLLEGE ROANOKE-CHOWAN COMMUNITY COLLEGE WAKE TECHNICAL COMMUNITY COLLEGE |  | CHATHAM, CUMBERLAND, EDGECOMBE, GASTON, HARNETT, HENDERSON, LEE, LINCOLN, MARTIN, TRANSYLVANIA, BERTIE, HERTFORD, NASH, RANDOLPH, WAKE | 1, 4, 5, 6, 8, 12, 14 | Capital Area MPO, Central Pines RPO, Fayetteville Area MPO, French Broad River MPO, Gaston-Cleveland-Lincoln MPO, Land-of-Sky RPO, Mid-Carolina RPO, Peanut Belt RPO, Piedmont Triad RPO, Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | DP REPRESENTS FEDERAL 2024 CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT. HF REPRESENT CONTINGENCY FUNDS. | Exempt |  | HF(M) | CONSTRUCTION | 252000 | FY 2025: 252000
HO-0020 | Highway | Other | NC 12 | RODANTHE TO OREGON INLET. CONDUCT PLANNING STUDY FOR THE LONG-TERM OPERATION OF THE ROADWAY DURING MAJOR STORM EVENTS. |  | DARE | 1 | Albemarle RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT AWARD. | Exempt |  | DP | PLANNING | 1865000 | FY 2025: 1865000
HO-0021 | Highway | Other | US 74 (FUTURE I-74) | BRIDGES 770466 AND 770118 OVER THE LUMBER RIVER. REINFORCE SHOULDER EMBANKMENTS. |  | ROBESON | 6 | Lumber River RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. | Exempt |  | DP | ENGINEERING | 244000 | FY 2025: 244000
HO-0021 | Highway | Other | US 74 (FUTURE I-74) | BRIDGES 770466 AND 770118 OVER THE LUMBER RIVER. REINFORCE SHOULDER EMBANKMENTS. |  | ROBESON | 6 | Lumber River RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. | Exempt |  | HF(M) | ENGINEERING | 61000 | FY 2025: 61000
HO-0021 | Highway | Other | US 74 (FUTURE I-74) | BRIDGES 770466 AND 770118 OVER THE LUMBER RIVER. REINFORCE SHOULDER EMBANKMENTS. |  | ROBESON | 6 | Lumber River RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. | Exempt |  | DP | CONSTRUCTION | 1560000 | FY 2025: 1560000
HO-0021 | Highway | Other | US 74 (FUTURE I-74) | BRIDGES 770466 AND 770118 OVER THE LUMBER RIVER. REINFORCE SHOULDER EMBANKMENTS. |  | ROBESON | 6 | Lumber River RPO | DP FUNDS REPRESENT 2023 FEDERAL PROTECT GRANT. | Exempt |  | HF(M) | CONSTRUCTION | 390000 | FY 2025: 390000
HO-0022 | Highway | Other | DURHAM | INSTALL EV CHARGING EQUIPMENT TO SUPPORT EQUITABLE ELECTRIFICATION IN THE CITY OF DURHAM. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | DP | CONSTRUCTION | 4000000 | FY 2025: 4000000
HO-0022 | Highway | Other | DURHAM | INSTALL EV CHARGING EQUIPMENT TO SUPPORT EQUITABLE ELECTRIFICATION IN THE CITY OF DURHAM. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | DP REPRESENTS 2024 FEDERAL CHARGING AND FUELING INFRASTRUCTURE (CFI) GRANT | Exempt |  | L | CONSTRUCTION | 1000000 | FY 2025: 1000000
HO-0023 | Highway | Other | SR 1202 (HICKORY FORK ROAD) | OVER PEMBROKE CREEK IN CHOWAN COUNTY. REPLACE CULVERT BP-021-2074. |  | CHOWAN | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | DP | ENGINEERING | 79000 | FY 2025: 79000
HO-0023 | Highway | Other | SR 1202 (HICKORY FORK ROAD) | OVER PEMBROKE CREEK IN CHOWAN COUNTY. REPLACE CULVERT BP-021-2074. |  | CHOWAN | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | HF(M) | ENGINEERING | 21000 | FY 2025: 21000
HO-0023 | Highway | Other | SR 1202 (HICKORY FORK ROAD) | OVER PEMBROKE CREEK IN CHOWAN COUNTY. REPLACE CULVERT BP-021-2074. |  | CHOWAN | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | DP | RIGHT-OF-WAY | 118000 | FY 2026: 118000
HO-0023 | Highway | Other | SR 1202 (HICKORY FORK ROAD) | OVER PEMBROKE CREEK IN CHOWAN COUNTY. REPLACE CULVERT BP-021-2074. |  | CHOWAN | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | HF(M) | RIGHT-OF-WAY | 32000 | FY 2026: 32000
HO-0023 | Highway | Other | SR 1202 (HICKORY FORK ROAD) | OVER PEMBROKE CREEK IN CHOWAN COUNTY. REPLACE CULVERT BP-021-2074. |  | CHOWAN | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | DP | CONSTRUCTION | 275000 | FY 2026: 275000
HO-0023 | Highway | Other | SR 1202 (HICKORY FORK ROAD) | OVER PEMBROKE CREEK IN CHOWAN COUNTY. REPLACE CULVERT BP-021-2074. |  | CHOWAN | 1 | Albemarle RPO | DP FUNDS REPRESENT FEDERAL CULVERT AQUATIC ORGANISM PASSAGE GRANT FUNDS - FFY22 | Exempt |  | HF(M) | CONSTRUCTION | 75000 | FY 2026: 75000
HP-0001 | Highway | STI (Prioritization) | US 74 | INDIAN TRAIL-FAIRVIEW ROAD TO NORTH ROCKY RIVER ROAD IN MONROE. WIDEN ROADWAY TO SIX LANES. |  | UNION | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4650000
HP-0001 | Highway | STI (Prioritization) | US 74 | INDIAN TRAIL-FAIRVIEW ROAD TO NORTH ROCKY RIVER ROAD IN MONROE. WIDEN ROADWAY TO SIX LANES. |  | UNION | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2250000
HP-0001 | Highway | STI (Prioritization) | US 74 | INDIAN TRAIL-FAIRVIEW ROAD TO NORTH ROCKY RIVER ROAD IN MONROE. WIDEN ROADWAY TO SIX LANES. |  | UNION | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 84700000
HP-0002 | Highway | STI (Prioritization) | I-485 | I-77 TO I-85 IN SOUTHWEST CHARLOTTE. CONSTRUCT ONE EXPRESS LANE IN EACH DIRECTION. TOLL PROJECT. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BOND R | RIGHT-OF-WAY | 1600000
HP-0002 | Highway | STI (Prioritization) | I-485 | I-77 TO I-85 IN SOUTHWEST CHARLOTTE. CONSTRUCT ONE EXPRESS LANE IN EACH DIRECTION. TOLL PROJECT. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BOND R | UTILITIES | 23700000
HP-0002 | Highway | STI (Prioritization) | I-485 | I-77 TO I-85 IN SOUTHWEST CHARLOTTE. CONSTRUCT ONE EXPRESS LANE IN EACH DIRECTION. TOLL PROJECT. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 91500000
HP-0002 | Highway | STI (Prioritization) | I-485 | I-77 TO I-85 IN SOUTHWEST CHARLOTTE. CONSTRUCT ONE EXPRESS LANE IN EACH DIRECTION. TOLL PROJECT. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BOND R | CONSTRUCTION | 154700000
HP-0003 | Highway | STI (Prioritization) | I-40 | CARY TOWNE BOULEVARD TO WADE AVENUE. CONSTRUCT OPERATIONAL IMPROVEMENTS INCLUDING AUXILIARY LANES BETWEEN WADE AVENUE AND CARY TOWNE BOULEVARD AND INTERCHANGE IMPROVEMENTS AT CARY TOWNE BOULEVARD. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 6000000
HP-0003 | Highway | STI (Prioritization) | I-40 | CARY TOWNE BOULEVARD TO WADE AVENUE. CONSTRUCT OPERATIONAL IMPROVEMENTS INCLUDING AUXILIARY LANES BETWEEN WADE AVENUE AND CARY TOWNE BOULEVARD AND INTERCHANGE IMPROVEMENTS AT CARY TOWNE BOULEVARD. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 500000
HP-0003 | Highway | STI (Prioritization) | I-40 | CARY TOWNE BOULEVARD TO WADE AVENUE. CONSTRUCT OPERATIONAL IMPROVEMENTS INCLUDING AUXILIARY LANES BETWEEN WADE AVENUE AND CARY TOWNE BOULEVARD AND INTERCHANGE IMPROVEMENTS AT CARY TOWNE BOULEVARD. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 27500000
HP-0004 | Highway | STI (Prioritization) | I-85 | SR 1291 (BILLY GRAHAM PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 6567000
HP-0004 | Highway | STI (Prioritization) | I-85 | SR 1291 (BILLY GRAHAM PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 500000
HP-0004 | Highway | STI (Prioritization) | I-85 | SR 1291 (BILLY GRAHAM PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 30532000
HP-0005 | Highway | STI (Prioritization) | VARIOUS | LOCATIONS IN DIVISION 5. PROVIDE COMMUNICATION AND CAMERAS TO IMPROVE SIGNAL TIMING. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1200000
HP-0005 | Highway | STI (Prioritization) | VARIOUS | LOCATIONS IN DIVISION 5. PROVIDE COMMUNICATION AND CAMERAS TO IMPROVE SIGNAL TIMING. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 15596000
HP-0006 | Highway | STI (Prioritization) | CHAPEL HILL CARRBORO | IMPLEMENT AN IMPROVED SIGNAL SYSTEM FOR THE TOWN OF CHAPEL HILL AND TOWN OF CARRBORO. | 14.79 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Region C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1700000
HP-0006 | Highway | STI (Prioritization) | CHAPEL HILL CARRBORO | IMPLEMENT AN IMPROVED SIGNAL SYSTEM FOR THE TOWN OF CHAPEL HILL AND TOWN OF CARRBORO. | 14.79 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Region C, D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 13910000
HP-0007 | Highway | STI (Prioritization) | US 70 BUSINESS | RAYNOR ROAD AND GUY ROAD INTERSECTION IN RALEIGH. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 1.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 2500000
HP-0007 | Highway | STI (Prioritization) | US 70 BUSINESS | RAYNOR ROAD AND GUY ROAD INTERSECTION IN RALEIGH. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 1.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0007 | Highway | STI (Prioritization) | US 70 BUSINESS | RAYNOR ROAD AND GUY ROAD INTERSECTION IN RALEIGH. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 1.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 8000000
HP-0008 | Highway | STI (Prioritization) | HOLLY SPRINGS | HOLLY SPRINGS CITYWIDE SIGNAL SYSTEM. INSTALL FIBER TO CONNECT EXISTING TOWN FIBER TO INTERSECTIONS, UPGRADE EXISTING INFRASTRUCTURE INCLUDING CABINETS, CONTROLLERS, AND SOFTWARE. | 4.58 | WAKE | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 3085000 | FY 2028: 2005000; FY 2029: 1080000
HP-0009 | Highway | STI (Prioritization) | US 401 / US 70 BUSINESS | TRYON ROAD INTERSECTION IN RALEIGH. IMPROVE INTERSECTION SIGNALS AND MERGING BETWEEN TRYON ROAD AND MECHANICAL BOULEVARD. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1500000
HP-0009 | Highway | STI (Prioritization) | US 401 / US 70 BUSINESS | TRYON ROAD INTERSECTION IN RALEIGH. IMPROVE INTERSECTION SIGNALS AND MERGING BETWEEN TRYON ROAD AND MECHANICAL BOULEVARD. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0009 | Highway | STI (Prioritization) | US 401 / US 70 BUSINESS | TRYON ROAD INTERSECTION IN RALEIGH. IMPROVE INTERSECTION SIGNALS AND MERGING BETWEEN TRYON ROAD AND MECHANICAL BOULEVARD. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 5500000
HP-0010 | Highway | STI (Prioritization) | TOWN OF CARY | TOWN OF CARY SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE, INSTALL NEW FIBER, CONTROLLERS, SIGNALS, CONNECTED VEHICLE TECHNOLOGY AND OTHER EQUIPMENT AS NECESSARY. | 7.94 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 6000000
HP-0010 | Highway | STI (Prioritization) | TOWN OF CARY | TOWN OF CARY SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE, INSTALL NEW FIBER, CONTROLLERS, SIGNALS, CONNECTED VEHICLE TECHNOLOGY AND OTHER EQUIPMENT AS NECESSARY. | 7.94 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | L | CONSTRUCTION | 4000000
HP-0011 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (NURSERY ROAD) INTERSECTION IN FAYETTEVILLE. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | HARNETT | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 400000
HP-0011 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (NURSERY ROAD) INTERSECTION IN FAYETTEVILLE. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | HARNETT | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 400000
HP-0011 | Highway | STI (Prioritization) | NC 24 / NC 87 | SR 1117 (NURSERY ROAD) INTERSECTION IN FAYETTEVILLE. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 2 | HARNETT | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 33400000
HP-0012 | Highway | STI (Prioritization) | US 401 | TRYON ROAD INTERSECTION IN RALEIGH. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 2500000
HP-0012 | Highway | STI (Prioritization) | US 401 | TRYON ROAD INTERSECTION IN RALEIGH. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0012 | Highway | STI (Prioritization) | US 401 | TRYON ROAD INTERSECTION IN RALEIGH. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 8000000
HP-0013 | Highway | STI (Prioritization) | US 1 (RALEIGH ROAD) | BELMONT DRIVE (OLD COUNTY HOME ROAD) AND WELCOME AVENUE INTERSECTION IN HENDERSON. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 600000
HP-0013 | Highway | STI (Prioritization) | US 1 (RALEIGH ROAD) | BELMONT DRIVE (OLD COUNTY HOME ROAD) AND WELCOME AVENUE INTERSECTION IN HENDERSON. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 200000
HP-0013 | Highway | STI (Prioritization) | US 1 (RALEIGH ROAD) | BELMONT DRIVE (OLD COUNTY HOME ROAD) AND WELCOME AVENUE INTERSECTION IN HENDERSON. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 2000000
HP-0014 | Highway | STI (Prioritization) | NC 55 | SOUTH MAIN STREET TO HOLLY SPRINGS ROAD. UPGRADE CORRIDOR TO SIX LANE EXPRESSWAY. | 1.6 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 60000000
HP-0014 | Highway | STI (Prioritization) | NC 55 | SOUTH MAIN STREET TO HOLLY SPRINGS ROAD. UPGRADE CORRIDOR TO SIX LANE EXPRESSWAY. | 1.6 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 9000000
HP-0014 | Highway | STI (Prioritization) | NC 55 | SOUTH MAIN STREET TO HOLLY SPRINGS ROAD. UPGRADE CORRIDOR TO SIX LANE EXPRESSWAY. | 1.6 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 64000000
HP-0015 | Highway | STI (Prioritization) | US 401 BYPASS (PAMALEE DRIVE) | NC 24 / 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). CONSTRUCT RAISED CENTER MEDIAN WITH ACCESS MANAGEMENT IMPROVEMENTS. | 2.32 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 18900000
HP-0015 | Highway | STI (Prioritization) | US 401 BYPASS (PAMALEE DRIVE) | NC 24 / 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). CONSTRUCT RAISED CENTER MEDIAN WITH ACCESS MANAGEMENT IMPROVEMENTS. | 2.32 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 23200000
HP-0015 | Highway | STI (Prioritization) | US 401 BYPASS (PAMALEE DRIVE) | NC 24 / 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). CONSTRUCT RAISED CENTER MEDIAN WITH ACCESS MANAGEMENT IMPROVEMENTS. | 2.32 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 28400000
HP-0016 | Highway | STI (Prioritization) | US 70 (GLENWOOD AVENUE) | AT NC 50 (CREEDMOOR ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 2500000
HP-0016 | Highway | STI (Prioritization) | US 70 (GLENWOOD AVENUE) | AT NC 50 (CREEDMOOR ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 500000
HP-0016 | Highway | STI (Prioritization) | US 70 (GLENWOOD AVENUE) | AT NC 50 (CREEDMOOR ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 8000000
HP-0017 | Highway | STI (Prioritization) | NC 55 BYPASS | AT SR 1144 (MAIN STREET). UPGRADE EXISTING INTERSECTION TO INTERCHANGE. | 2 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 18200000
HP-0017 | Highway | STI (Prioritization) | NC 55 BYPASS | AT SR 1144 (MAIN STREET). UPGRADE EXISTING INTERSECTION TO INTERCHANGE. | 2 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 12300000
HP-0017 | Highway | STI (Prioritization) | NC 55 BYPASS | AT SR 1144 (MAIN STREET). UPGRADE EXISTING INTERSECTION TO INTERCHANGE. | 2 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 24700000
HP-0018 | Highway | STI (Prioritization) | NC 55 (APEX HIGHWAY) | AT CORNWALLIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1000000
HP-0018 | Highway | STI (Prioritization) | NC 55 (APEX HIGHWAY) | AT CORNWALLIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0018 | Highway | STI (Prioritization) | NC 55 (APEX HIGHWAY) | AT CORNWALLIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 1500000
HP-0019 | Highway | STI (Prioritization) | NC 211 (NORTH ROBERTS AVENUE) | AT SR 1531 (SADDLETREE ROAD / CLYBOURN CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 400000
HP-0019 | Highway | STI (Prioritization) | NC 211 (NORTH ROBERTS AVENUE) | AT SR 1531 (SADDLETREE ROAD / CLYBOURN CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0019 | Highway | STI (Prioritization) | NC 211 (NORTH ROBERTS AVENUE) | AT SR 1531 (SADDLETREE ROAD / CLYBOURN CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 3100000
HP-0020 | Highway | STI (Prioritization) | NC 24 / NC 87 | FROM SR 1117 (NURSERY ROAD) TO SR 1451 (MANCHESTER ROAD). WIDEN ROADWAY. | 3.23 | CUMBERLAND, HARNETT | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 28300000
HP-0020 | Highway | STI (Prioritization) | NC 24 / NC 87 | FROM SR 1117 (NURSERY ROAD) TO SR 1451 (MANCHESTER ROAD). WIDEN ROADWAY. | 3.23 | CUMBERLAND, HARNETT | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 2400000
HP-0020 | Highway | STI (Prioritization) | NC 24 / NC 87 | FROM SR 1117 (NURSERY ROAD) TO SR 1451 (MANCHESTER ROAD). WIDEN ROADWAY. | 3.23 | CUMBERLAND, HARNETT | 6 | Fayetteville Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 33300000
HP-0021 | Highway | STI (Prioritization) | HENDERSON CITYWIDE SIGNAL SYSTEM | INSTALL CITYWIDE SIGNAL SYSTEM. | 9.71 | VANCE | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 300000
HP-0021 | Highway | STI (Prioritization) | HENDERSON CITYWIDE SIGNAL SYSTEM | INSTALL CITYWIDE SIGNAL SYSTEM. | 9.71 | VANCE | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 4736000
HP-0022 | Highway | STI (Prioritization) | NC 49 (MAPLE AVENUE) | I-85 / I-40 TO NC 54 AND PLAZA DRIVE INTERSECTION IN BURLINGTON. RELOCATION OF MAPLE AVENUE ON NEW ALIGNMENT FROM I-85 / I-40 TO NC 54, AND RELOCATION OF PLAZA DRIVE INTERSECTION WITH A NEW SIGNALIZED FOUR-LEGGED INTERSECTION AT RELOCATED PLANTATION DRIVE. INCLUDED LANDSCAPED MEDIANS AND MULTI-USE PATHS. | 1 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | RIGHT-OF-WAY | 1400000
HP-0022 | Highway | STI (Prioritization) | NC 49 (MAPLE AVENUE) | I-85 / I-40 TO NC 54 AND PLAZA DRIVE INTERSECTION IN BURLINGTON. RELOCATION OF MAPLE AVENUE ON NEW ALIGNMENT FROM I-85 / I-40 TO NC 54, AND RELOCATION OF PLAZA DRIVE INTERSECTION WITH A NEW SIGNALIZED FOUR-LEGGED INTERSECTION AT RELOCATED PLANTATION DRIVE. INCLUDED LANDSCAPED MEDIANS AND MULTI-USE PATHS. | 1 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | UTILITIES | 1000000
HP-0022 | Highway | STI (Prioritization) | NC 49 (MAPLE AVENUE) | I-85 / I-40 TO NC 54 AND PLAZA DRIVE INTERSECTION IN BURLINGTON. RELOCATION OF MAPLE AVENUE ON NEW ALIGNMENT FROM I-85 / I-40 TO NC 54, AND RELOCATION OF PLAZA DRIVE INTERSECTION WITH A NEW SIGNALIZED FOUR-LEGGED INTERSECTION AT RELOCATED PLANTATION DRIVE. INCLUDED LANDSCAPED MEDIANS AND MULTI-USE PATHS. | 1 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | CONSTRUCTION | 4200000
HP-0023 | Highway | STI (Prioritization) | US 158 | NC 801 INTERSECTION IN WINSTON-SALEM. UPGRADE INTERSECTION WITH LEFT TURN LANE ON EB US 158, AND RIGHT THRU LANE AND RIGHT TURN LANE ON NC 801. | 0.5 | DAVIE | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 3600000
HP-0023 | Highway | STI (Prioritization) | US 158 | NC 801 INTERSECTION IN WINSTON-SALEM. UPGRADE INTERSECTION WITH LEFT TURN LANE ON EB US 158, AND RIGHT THRU LANE AND RIGHT TURN LANE ON NC 801. | 0.5 | DAVIE | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 600000
HP-0023 | Highway | STI (Prioritization) | US 158 | NC 801 INTERSECTION IN WINSTON-SALEM. UPGRADE INTERSECTION WITH LEFT TURN LANE ON EB US 158, AND RIGHT THRU LANE AND RIGHT TURN LANE ON NC 801. | 0.5 | DAVIE | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 3100000
HP-0024 | Highway | STI (Prioritization) | US 401 | SR 5056 / SR 2768 (JUDD PARKWAY) TO FIVE POINTS INTERCHANGE OF US 401, NC 55, AND NC 42. CONSTRUCT MEDIAN THROUGHOUT CORRIDOR WITH OTHER ACCESS MANAGEMENT IMPROVEMENTS. | 1.18 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 3500000
HP-0024 | Highway | STI (Prioritization) | US 401 | SR 5056 / SR 2768 (JUDD PARKWAY) TO FIVE POINTS INTERCHANGE OF US 401, NC 55, AND NC 42. CONSTRUCT MEDIAN THROUGHOUT CORRIDOR WITH OTHER ACCESS MANAGEMENT IMPROVEMENTS. | 1.18 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 470000
HP-0024 | Highway | STI (Prioritization) | US 401 | SR 5056 / SR 2768 (JUDD PARKWAY) TO FIVE POINTS INTERCHANGE OF US 401, NC 55, AND NC 42. CONSTRUCT MEDIAN THROUGHOUT CORRIDOR WITH OTHER ACCESS MANAGEMENT IMPROVEMENTS. | 1.18 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 5800000
HP-0025 | Highway | STI (Prioritization) | NC 98 | SIX FORKS ROAD INTERSECTION IN RALEIGH. UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 2500000
HP-0025 | Highway | STI (Prioritization) | NC 98 | SIX FORKS ROAD INTERSECTION IN RALEIGH. UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0025 | Highway | STI (Prioritization) | NC 98 | SIX FORKS ROAD INTERSECTION IN RALEIGH. UPGRADE INTERSECTION. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 8000000
HP-0026 | Highway | STI (Prioritization) | I-40 | US 158 (STRATFORD ROAD) |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0026 | Highway | STI (Prioritization) | I-40 | US 158 (STRATFORD ROAD) |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 3300000
HP-0027 | Highway | STI (Prioritization) | US 52 (FUTURE I-285) | US 421 (SALEM PARKWAY) - EXIT 109 TO SR 2264 (AKRON DRIVE) - EXIT 112. UPGRADE US 52 TO INTERSTATE STANDARDS (I-285) BY WIDENING EXISTING FACILIITIES TO SIX LANES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 56400000
HP-0027 | Highway | STI (Prioritization) | US 52 (FUTURE I-285) | US 421 (SALEM PARKWAY) - EXIT 109 TO SR 2264 (AKRON DRIVE) - EXIT 112. UPGRADE US 52 TO INTERSTATE STANDARDS (I-285) BY WIDENING EXISTING FACILIITIES TO SIX LANES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 4200000
HP-0027 | Highway | STI (Prioritization) | US 52 (FUTURE I-285) | US 421 (SALEM PARKWAY) - EXIT 109 TO SR 2264 (AKRON DRIVE) - EXIT 112. UPGRADE US 52 TO INTERSTATE STANDARDS (I-285) BY WIDENING EXISTING FACILIITIES TO SIX LANES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 317100000
HP-0028 | Highway | STI (Prioritization) | NC 152 | SR 1509 (MILLER ROAD) INTERSECTION IN CHINA GROVE. CONSTRUCT ROUNDABOUT. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1400000
HP-0028 | Highway | STI (Prioritization) | NC 152 | SR 1509 (MILLER ROAD) INTERSECTION IN CHINA GROVE. CONSTRUCT ROUNDABOUT. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0028 | Highway | STI (Prioritization) | NC 152 | SR 1509 (MILLER ROAD) INTERSECTION IN CHINA GROVE. CONSTRUCT ROUNDABOUT. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 4200000
HP-0029 | Highway | STI (Prioritization) | NC 150 | SR 1526 (ROWAN MILL ROAD) AND SR 1526 (SHERRILLS FORD ROAD) INTERSECTIONS IN SHERRILLS FORD AND SALISBURY. ADD STORAGE AND TURN LANES PER THE ROAD PLANS FOR U-5900 TIP PROJECT |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 1300000
HP-0029 | Highway | STI (Prioritization) | NC 150 | SR 1526 (ROWAN MILL ROAD) AND SR 1526 (SHERRILLS FORD ROAD) INTERSECTIONS IN SHERRILLS FORD AND SALISBURY. ADD STORAGE AND TURN LANES PER THE ROAD PLANS FOR U-5900 TIP PROJECT |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0029 | Highway | STI (Prioritization) | NC 150 | SR 1526 (ROWAN MILL ROAD) AND SR 1526 (SHERRILLS FORD ROAD) INTERSECTIONS IN SHERRILLS FORD AND SALISBURY. ADD STORAGE AND TURN LANES PER THE ROAD PLANS FOR U-5900 TIP PROJECT |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 2300000
HP-0030 | Highway | STI (Prioritization) | US 70 (CHURCH STREET) | NC 62 INTERSESCTION IN BURLINGTON. IMPROVE INTERSECTION. PROJECT INCLUDES IMPROVEMENTS TO NC 62. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 700000
HP-0030 | Highway | STI (Prioritization) | US 70 (CHURCH STREET) | NC 62 INTERSESCTION IN BURLINGTON. IMPROVE INTERSECTION. PROJECT INCLUDES IMPROVEMENTS TO NC 62. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 500000
HP-0030 | Highway | STI (Prioritization) | US 70 (CHURCH STREET) | NC 62 INTERSESCTION IN BURLINGTON. IMPROVE INTERSECTION. PROJECT INCLUDES IMPROVEMENTS TO NC 62. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 1200000
HP-0031 | Highway | STI (Prioritization) | US 421 | SR 1122 (JONESTOWN ROAD) INTERSECTION IN WINSTON-SALEM. UPGRADE INTERSECTION REMOVE TWO-WAY TRAFFIC FROM US 421 NB ON RAMP, AND EXTEND ACCELERATION LANE DISTANCE ONTO MAINLINE. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 4300000
HP-0031 | Highway | STI (Prioritization) | US 421 | SR 1122 (JONESTOWN ROAD) INTERSECTION IN WINSTON-SALEM. UPGRADE INTERSECTION REMOVE TWO-WAY TRAFFIC FROM US 421 NB ON RAMP, AND EXTEND ACCELERATION LANE DISTANCE ONTO MAINLINE. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 1500000
HP-0031 | Highway | STI (Prioritization) | US 421 | SR 1122 (JONESTOWN ROAD) INTERSECTION IN WINSTON-SALEM. UPGRADE INTERSECTION REMOVE TWO-WAY TRAFFIC FROM US 421 NB ON RAMP, AND EXTEND ACCELERATION LANE DISTANCE ONTO MAINLINE. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 14900000
HP-0032 | Highway | STI (Prioritization) | US 1 | SR 1010 (TEN TEN ROAD) INTERCHANGE. RECONSTRUCT INTERCHANGE. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | T | RIGHT-OF-WAY | 21300000 | FY 2027: 2130000; FY 2028: 7455000; FY 2029: 7455000; FY 2030: 2130000; FY 2031: 2130000
HP-0032 | Highway | STI (Prioritization) | US 1 | SR 1010 (TEN TEN ROAD) INTERCHANGE. RECONSTRUCT INTERCHANGE. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | T | UTILITIES | 3300000 | FY 2027: 1100000; FY 2028: 1100000; FY 2029: 1100000
HP-0032 | Highway | STI (Prioritization) | US 1 | SR 1010 (TEN TEN ROAD) INTERCHANGE. RECONSTRUCT INTERCHANGE. |  | WAKE | 5 | Capital Area MPO |  | Region C |  | T | CONSTRUCTION | 20600000 | FY 2030: 5150000; FY 2031: 7210000; FY 2032: 5150000; FY 2033: 3090000
HP-0033 | Highway | STI (Prioritization) | NC 55 | NC 210 INTERSECTION IN ANGIER. CONSTRUCT TURN LANES. | 0.1 | HARNETT | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 800000
HP-0033 | Highway | STI (Prioritization) | NC 55 | NC 210 INTERSECTION IN ANGIER. CONSTRUCT TURN LANES. | 0.1 | HARNETT | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 800000
HP-0033 | Highway | STI (Prioritization) | NC 55 | NC 210 INTERSECTION IN ANGIER. CONSTRUCT TURN LANES. | 0.1 | HARNETT | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 2200000
HP-0034 | Highway | STI (Prioritization) | NC 55 | AT NORTH BROAD STREET IN ANGIER. CONSTRUCT ROUNDABOUT. | 0.5 | HARNETT | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 2700000
HP-0034 | Highway | STI (Prioritization) | NC 55 | AT NORTH BROAD STREET IN ANGIER. CONSTRUCT ROUNDABOUT. | 0.5 | HARNETT | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 600000
HP-0034 | Highway | STI (Prioritization) | NC 55 | AT NORTH BROAD STREET IN ANGIER. CONSTRUCT ROUNDABOUT. | 0.5 | HARNETT | 6 | Capital Area MPO |  | Division 6 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 4400000
HS-2001 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2001A | Highway | Safety | US 158 | CONSTRUCT ROUNDABOUT AT US 158 AND SR 1147 (INDIANTOWN ROAD). | 0.5 | CURRITUCK | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 45000
HS-2001B | Highway | Safety | US 13, US 17, NC 171 | UPGRADE CURVE WARNING SIGNS AT VARIOUS LOCATIONS. |  | MARTIN, BERTIE | 1 | Mid-East RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 35000
HS-2001C | Highway | Safety | SR 1354 (MILLPOND ROAD) | SR 1354 (MILLPOND ROAD) BETWEEN US 158 AND SR 1001 (TURNPIKE ROAD). UPGRADE PAVEMENT MARKINGS. | 4.42 | PASQUOTANK | 1 | Albemarle RPO |  | Division 1 |  | HSIP | CONSTRUCTION | 40000
HS-2001D | Highway | Safety | VARIOUS | UPGRADE WARNING SIGNS AT CURVES AT VARIOUS LOCATIONS. |  | PASQUOTANK, CAMDEN, PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | HSIP | CONSTRUCTION | 41000
HS-2001E | Highway | Safety | VARIOUS | UPGRADE WARNING SIGNS AT CURVES AT VARIOUS LOCATIONS. |  | BERTIE, CURRITUCK | 1 | Peanut Belt RPO, Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | HSIP | CONSTRUCTION | 12000
HS-2001F | Highway | Safety | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 0.36 | CURRITUCK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | HSIP | RIGHT-OF-WAY | 766000 | FY 2026: 766000
HS-2001F | Highway | Safety | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 0.36 | CURRITUCK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | T | RIGHT-OF-WAY | 1534000 | FY 2026: 1534000
HS-2001F | Highway | Safety | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 0.36 | CURRITUCK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | HSIP | UTILITIES | 266000 | FY 2026: 266000
HS-2001F | Highway | Safety | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 0.36 | CURRITUCK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | T | UTILITIES | 534000 | FY 2026: 534000
HS-2001F | Highway | Safety | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 0.36 | CURRITUCK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | HSIP | CONSTRUCTION | 800000 | FY 2026: 8000; FY 2027: 792000
HS-2001F | Highway | Safety | US 158 | CONSTRUCT U-TURN BULB OUTS AND MODIFY MEDIAN AT INTERSECTION OF US 158 AND EDGEWATER ROAD. | 0.36 | CURRITUCK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Region A |  | T | CONSTRUCTION | 1600000 | FY 2026: 16000; FY 2027: 1584000
HS-2001G | Highway | Safety | US 13; NC 11 / SR 1212 (SHORTCUT ROAD) | SR 1302 (LEAN LUMBER COMPANY ROAD) IN BERTIE COUNTY TO 0.25 MILES NORTH OF SR 1418 (ARROW ROAD) IN HERTFORD COUNTY, AND SR 1212 (SHORTCUT ROAD) IN HERTFORD COUNTY TO US 158 IN GATES COUNTY; 450 FEET SOUTH OF SR 1130 (MODLIN ROAD) TO US 13. | 22.2 | BERTIE, HERTFORD, GATES | 1 | Peanut Belt RPO, Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 895000
HS-2001H | Highway | Safety | US 64 | FROM 0.85 MILES EAST OF SR 1326 (KEISER DRIVE) TO EASTERN INTERSECTION WITH SR 1229 (OLD HIGHWAY 64). INSTALL RUMBLE STRIPES. | 5.19 | TYRRELL | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 250000
HS-2001I | Highway | Safety | NC 344 | FROM SOUTH OF AIRPORT ENTRANCE TO SR 1100 (SAWMILL ROAD). INSTALL RUMBLE STRIPES AND PAVEMENT MARKERS. | 3.72 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 160000
HS-2002 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2002A | Highway | Safety | SR 1703 (14TH STREET) | INSTALL CROSSWALK, WHEELCHAIR RAMPS, SIDEWALK, AND FENCING ALONG SR 1703 (14TH STREET) FROM HASKETT WAY AND BERKLEY ROAD. REMOVE TWO EXISTING OBSOLETE CROSSWALKS. | 0.09 | PITT | 2 | Greenville Urban Area MPO | COMPLETED. | Division 2 |  | HSIP | CONSTRUCTION | 50000
HS-2002AA | Highway | Safety | NC 58 | APPROXIMATELY 1280 FEET EAST OF LEE DRIVE IN ATLANTIC BEACH. INSTALL RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | CARTERET | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 32000
HS-2002AB | Highway | Safety | US 70 | AT SR 1174 (TURNER STREET) IN BEAUFORT. ADD PEDESTRIAN SIGNAL HEADS AT EXISTING CROSSWALKS. | 0.5 | CARTERET | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 55000
HS-2002AC | Highway | Safety | US 70 | AT SR 1300 (MERRIMON ROAD). UPGRADE TRAFFIC SIGNAL. | 0.5 | CARTERET | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 25000 | FY 2025: 25000
HS-2002AD | Highway | Safety | NC 55 | FROM .86 MILES WEST OF NC 903 TO NC 11. INSTALL RUMBLE STRIPS. | 11.76 | LENOIR, WAYNE | 2, 4 | Eastern Carolina RPO |  | Region A, B |  | HSIP | CONSTRUCTION | 380000 | FY 2025: 380000
HS-2002AE | Highway | Safety | US 70 / US 258 (WEST VERNON AVENUE) | 630 FEET EAST OF US 258 IN KINSTON. REMOVE EASTBOUND LEFT-OVER. | 0.5 | LENOIR | 2 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 205000
HS-2002AF | Highway | Safety | US 70 | FROM GLADYS TEASLEY LANE TO SR 1753 (ARTHUR FARM ROAD) IN MOREHEAD CITY. CONSTRUCT REDUCED CONFLICT INTERSECTION INCLUDING MODIFICATION OF FIVE FULL-MOVEMENT MEDIAN OPENINGS. | 0.65 | CARTERET | 2 | Down East RPO |  | Region B |  | HSIP | UTILITIES | 150000 | FY 2025: 150000
HS-2002AF | Highway | Safety | US 70 | FROM GLADYS TEASLEY LANE TO SR 1753 (ARTHUR FARM ROAD) IN MOREHEAD CITY. CONSTRUCT REDUCED CONFLICT INTERSECTION INCLUDING MODIFICATION OF FIVE FULL-MOVEMENT MEDIAN OPENINGS. | 0.65 | CARTERET | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 940000 | FY 2025: 648000; FY 2026: 292000
HS-2002AG | Highway | Safety | US 70 | AT SR 1002 (WYSE FORK ROAD) / SR 1309 (CASWELL STATION ROAD). CONSTRUCT A REDUCED CONFLICT INTERSECTION. | 0.5 | JONES | 2 | Down East RPO |  | Region B |  | HSIP | UTILITIES | 30000
HS-2002AG | Highway | Safety | US 70 | AT SR 1002 (WYSE FORK ROAD) / SR 1309 (CASWELL STATION ROAD). CONSTRUCT A REDUCED CONFLICT INTERSECTION. | 0.5 | JONES | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 965000
HS-2002AH | Highway | Safety | US 264 ALTERNATE (GREENVILLE BOULEVARD) | FROM 200 FEET SOUTH OF LUCI DRIVE AND NC 33 (10TH STREET) IN GREENVILLE. CONSTRUCT PEDESTRIAN IMPORVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, AND SIDEWALK. | 0.5 | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | UTILITIES | 125000
HS-2002AH | Highway | Safety | US 264 ALTERNATE (GREENVILLE BOULEVARD) | FROM 200 FEET SOUTH OF LUCI DRIVE AND NC 33 (10TH STREET) IN GREENVILLE. CONSTRUCT PEDESTRIAN IMPORVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, AND SIDEWALK. | 0.5 | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 320000 | FY 2025: 317000
HS-2002AI | Highway | Safety | US 70 | AT NC 101 IN BEAUFORT. UPGRADE TRAFFIC SIGNAL AND INSTALL ADVANCE SIGNAL AHEAD FLASHERS. | 0.5 | CARTERET | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 55000
HS-2002B | Highway | Safety | NC 24 | NC 24 BETWEEN SR 1259 (TAYLOR NOTION ROAD) AND US 70. INSTALL PAVEMENT MARKINGS AND RUMBLE STRIPES ON TWO-WAY LEFT TURN LANE. | 15.07 | CARTERET | 2 | Down East RPO | COMPLETED. | Statewide Mobility |  | HSIP | CONSTRUCTION | 640000
HS-2002C | Highway | Safety | US 70 | INSTALL RESTRICTED CROSSING INTERSECTIONS AT US 70 AND SR 1324 (KENNEDY HOME ROAD) / SR 1519 (EASON ROAD) AND AT ADJACENT CROSSOVER TO THE WEST. | 0.5 | LENOIR | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | UTILITIES | 20000
HS-2002C | Highway | Safety | US 70 | INSTALL RESTRICTED CROSSING INTERSECTIONS AT US 70 AND SR 1324 (KENNEDY HOME ROAD) / SR 1519 (EASON ROAD) AND AT ADJACENT CROSSOVER TO THE WEST. | 0.5 | LENOIR | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 250000
HS-2002D | Highway | Safety | US 264 | CONSTRUCT REDUCED CONFLICT INTERSECTION AT US 264 AND SR 1410 (VOA ROAD). | 0.5 | BEAUFORT | 2 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 15000
HS-2002D | Highway | Safety | US 264 | CONSTRUCT REDUCED CONFLICT INTERSECTION AT US 264 AND SR 1410 (VOA ROAD). | 0.5 | BEAUFORT | 2 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 939000
HS-2002E | Highway | Safety | US 264 ALTERNATE | US 264 ALTERNATE (GREENVILLE BOULEVARD) AT SR 1534 (OLD PACTOLUS ROAD). CONSTRUCT RESTRICTED-CROSSING INTERSECTION. | 0.48 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 882000
HS-2002F | Highway | Safety | SR 1001 / SR 1256 (MAIN STREET) | AT SR 1005 (SUNSET BOULEVARD). INSTALL ALL WAY STOP, REVISE OVERHEAD FLASHER, AND INSTALL CHANNELIZATION. | 1 | CRAVEN | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | HSIP | RIGHT-OF-WAY | 15000
HS-2002F | Highway | Safety | SR 1001 / SR 1256 (MAIN STREET) | AT SR 1005 (SUNSET BOULEVARD). INSTALL ALL WAY STOP, REVISE OVERHEAD FLASHER, AND INSTALL CHANNELIZATION. | 1 | CRAVEN | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | HSIP | CONSTRUCTION | 58000 | FY 2025: 58000
HS-2002G | Highway | Safety | NC 58 (SALTER PATH ROAD) | NC 58 (SALTER PATH ROAD) AT THE OCEAN CLUB ENTRANCE JUST WEST OF TRADEWINDS DRIVE. INSTALL CROSSWALK WITH RAPID FLASHING BEACONS. | 0.5 | CARTERET | 2 | Down East RPO | COMPLETED. | Region B |  | HSIP | CONSTRUCTION | 25000
HS-2002H | Highway | Safety | NC 58 (WEST FORT MACON ROAD) | NC 58 (WEST FORT MACON ROAD) AT ATLANTIC STATION SHOPPING CENTER / ATLANTIC BEACH TOWN PARK. INSTALL PEDESTRIAN HEADS FOR EXISTING SIGNAL AND WHEEL CHAIR RAMP REVISIONS. | 0.5 | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 12000
HS-2002I | Highway | Safety | NC 58 | NC 58 JUST WEST OF CEDAR LANE. INSTALL CROSSWALKS, CONCRETE MONOLITHIC PEDESTRIAN REFUGE ISLAND, SIDEWALKS, AND RECTANGULAR RAPID-FLASHING BEACONS. | 0.5 | CARTERET | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 95000
HS-2002J | Highway | Safety | NC 33 | NC 33 FROM US 13/NC 11 (MEMORIAL DRIVE) TO DAUGHTRIDGE DRIVE IN GREENVILLE. INSTALL MEDIAN ISLAND AND REVISE PAVEMENT MARKINGS. | 0.07 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 120000
HS-2002K | Highway | Safety | NC 11 | NC 11 AT SR 1716 (HARVEY ROUSE ROAD), NC 11 AT NC 118/SR 1091 (GRIFTON-HUGO ROAD), AND NC 11 AT SR 1714 (CREEK ROAD). CONVERT MEDIAN OPENINGS TO REDUCED CONFLICT INTERSECTIONS. | 0.68 | LENOIR | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | UTILITIES | 80000
HS-2002K | Highway | Safety | NC 11 | NC 11 AT SR 1716 (HARVEY ROUSE ROAD), NC 11 AT NC 118/SR 1091 (GRIFTON-HUGO ROAD), AND NC 11 AT SR 1714 (CREEK ROAD). CONVERT MEDIAN OPENINGS TO REDUCED CONFLICT INTERSECTIONS. | 0.68 | LENOIR | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 1235000 | FY 2025: 135000
HS-2002L | Highway | Safety | US 264 ALTERNATE | US 264 ALTERNATE/NC 43 (GREENVILLE BOULEVARD) AT NC 11/NC 43/NC 903 (MEMORIAL DRIVE) AND NC 11/NC 903 (MEMORIAL DRIVE) AT MALL DRIVE IN GREENVILLE. REVISE AND CONSTRUCT TURN LANES. | 0.5 | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 896000
HS-2002M | Highway | Safety | SR 1598 (10TH STREET) | AT COLLEGE HILL DRIVE AND AT ELM STREET IN GREENVILLE. UPGRADE TRAFFIC SIGNALS. | 0.5 | PITT | 2 | Greenville Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Division 2 |  | HSIP | CONSTRUCTION | 55000
HS-2002N | Highway | Safety | US 258 | US 258 AT SR 1342 (WILL BAKER ROAD / CENTRAL AVENUE). INSTALL FLASHER AND UPGRADE TRAFFIC SIGNAL. | 0.5 | LENOIR | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 87000 | FY 2025: 25000
HS-2002O | Highway | Safety | US 17 BUSINESS (MARTIN LUTHER KING JR. BOULEVARD) | US 17 BUSINESS (MARTIN LUTHER KING JR. BOULEVARD) AT TRENT CREEK ROAD. INSTALL FLASHER. | 0.5 | CRAVEN | 2 | New Bern Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 42000
HS-2002P | Highway | Safety | US 258 | US 258 AT SR 1120 (NOBLES MILL ROAD) AND US 258 AT SR 1908 (BILL STROUD ROAD). CONSTRUCT TURN LANES. | 0.5 | LENOIR | 2 | Eastern Carolina RPO | UTILITY RELOCATION IN PROGRESS. | Region B |  | HSIP | UTILITIES | 150000
HS-2002P | Highway | Safety | US 258 | US 258 AT SR 1120 (NOBLES MILL ROAD) AND US 258 AT SR 1908 (BILL STROUD ROAD). CONSTRUCT TURN LANES. | 0.5 | LENOIR | 2 | Eastern Carolina RPO | UTILITY RELOCATION IN PROGRESS. | Region B |  | HSIP | CONSTRUCTION | 661000
HS-2002Q | Highway | Safety | US 258 | US 258 BETWEEN NC 24 IN RICHLANDS AND US 70 IN KINSTON. INSTALL RUMBLES STRIPES. | 25.07 | LENOIR, ONSLOW, JONES | 2, 3 | Eastern Carolina RPO, Jacksonville Urban Area MPO, Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 585000 | FY 2025: 332000; FY 2026: 253000
HS-2002R | Highway | Safety | SR 1702 (EVANS STREET) | SR 1702 (EVANS STREET) AT HOWELL STREET IN GREENVILLE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | UTILITIES | 65000
HS-2002R | Highway | Safety | SR 1702 (EVANS STREET) | SR 1702 (EVANS STREET) AT HOWELL STREET IN GREENVILLE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | CONSTRUCTION | 400000
HS-2002S | Highway | Safety | NC 43 | NC 43 BETWEEN NC 118 IN CRAVEN COUNTY AND SR 1730 (HERMAN GARRIS ROAD) IN PITT COUNTY, NC 43 BETWEEN SR 1205 (ROCK SPRING ROAD) AND THE SOUTHERN LIMITS OF FALKLAND, AND NC 43 BETWEEN THE NORTHERN LIMITS OF FALKLAND IN PITT COUNTY AND NC 42 IN EDGECOMBE COUNTY. INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | 33.01 | PITT, CRAVEN, EDGECOMBE | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Down East RPO, Upper Coastal Plain RPO |  | Region A, B |  | HSIP | CONSTRUCTION | 815000
HS-2002T | Highway | Safety | US 264 | US 264 BETWEEN THE WILSON COUNTY LINE AND SR 1128 (DAVENPORT FARM ROAD) / SR 1206 (BELL ARTHUR ROAD) IN PITT COUNTY. INSTALL RUMBLE STRIPES. | 11.76 | PITT, GREENE | 2 | Mid-East RPO, Eastern Carolina RPO, Greenville Urban Area MPO | UNDER CONSTRUCTION. | Region B |  | HSIP | CONSTRUCTION | 378000
HS-2002U | Highway | Safety | SR 1310 (LENNOXVILLE ROAD) | AT CARTERET AVENUE IN BEAUFORT. INSTALL CROSSWALK SIGNALIZATION. |  | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | CONSTRUCTION | 25000
HS-2002V | Highway | Safety | NC 55 (NEUSE BOULEVARD) | AT SR 1215 (SIMMONS STREET) IN NEW BERN. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 0.5 | CRAVEN | 2 | New Bern Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 18000
HS-2002W | Highway | Safety | NC 55 (NEUSE BOULEVARD) | AT SR 1309 / SR 1402 (GLENBURNIE ROAD) IN NEW BERN. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 0.5 | CRAVEN | 2 | New Bern Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 18000
HS-2002X | Highway | Safety | SR 1725 (COUNTY HOME ROAD) | AT EXISTING CROSSWALK JUST SOUTH OF DISTRICT PARK DRIVE IN GREENVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Division 2 |  | HSIP | CONSTRUCTION | 35000
HS-2002Y | Highway | Safety | NC 55 (NEUSE BOULEVARD) | AT FORT TOTTEN DRIVE AND FIRST STREET INTERSECTIONS IN NEW BERN. INSTALL PEDESTRIAN HEADS AT FORT TOTTEN DRIVE. UPGRADE BOTH TRAFFIC SIGNALS. | 0.5 | CRAVEN | 2 | New Bern Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 76000
HS-2002Z | Highway | Safety | SR 1131 (REEDY BRANCH ROAD) | SR 1131 (REEDY BRANCH ROAD) AT BULLDOG RUN AND EDDIE SMITH STREET IN WINTERVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | HSIP | CONSTRUCTION | 55000
HS-2003 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2003A | Highway | Safety | SR 1217 (17TH STREET) | INSTALL NEAR SIDE SIGNAL HEADS ON PEDESTAL ON BOTH SIDES OF SR 1217 (17TH STREET) AT DOCK STREET IN WILMINGTON. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 34000 | FY 2025: 19000; FY 2026: 15000
HS-2003AA | Highway | Safety | SR 1308 (BELL FORK ROAD) | AT BRYNN MARR ROAD. UPGRADE TRAFFIC SIGNAL, SIGNING, AND PAVEMENT MARKINGS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | RIGHT-OF-WAY | 126000
HS-2003AA | Highway | Safety | SR 1308 (BELL FORK ROAD) | AT BRYNN MARR ROAD. UPGRADE TRAFFIC SIGNAL, SIGNING, AND PAVEMENT MARKINGS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 246000 | FY 2025: 246000
HS-2003AB | Highway | Safety | SR 1428 (RIGGS ROAD) | FROM NAUTICAL WAVE ROAD TO SR 1744 (HUBERT BOULEVARD). INSTALL PAVEMENT MARKINGS. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 53000
HS-2003AC | Highway | Safety | US 117 | AT SR 1411 (ASHTON ROAD / OLD RIVER ROAD). INSTALL TRAFFIC SIGNAL. | 0.5 | PENDER | 3 | Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 325000 | FY 2025: 325000
HS-2003AD | Highway | Safety | US 117/NC 132 (COLLEGE ROAD) | AT CREWS DRIVE. UPGRADE TRAFFIC SIGNAL. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 123000
HS-2003AE | Highway | Safety | US 117 / NC 132 (COLLEGE ROAD) | AT SR 1411 (WRIGHTSVILLE AVENUE) IN WILMINGTON. INSTALL CROSSWALKS AND PEDESTRIAN COUNTDOWN HEADS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 110000
HS-2003AF | Highway | Safety | US 17 BUSINESS (MARINE BOULEVARD) | AT SR 1308 (GUM BRANCH ROAD / BELL FORK ROAD) IN JACKSONVILLE. UPDATE / INSTALL TRAFFIC SIGNAL, PAVEMENT MARKINGS, CURB RAMPS, AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 82000 | FY 2025: 82000
HS-2003AG | Highway | Safety | US 17 BUSINESS (MARINE BOULEVARD) | AT SR 1336 (ONSLOW DRIVE) IN JACKSONVILLE. UPDATE / INSTALL TRAFFIC SIGNAL, PAVEMENT MARKINGS, AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 144000 | FY 2025: 144000
HS-2003AH | Highway | Safety | US 117 | FROM I-40 IN SAMPSON COUTY TO THE WAYNE COUNTY LINE. INSTALL GUARDRAIL. | 6.95 | DUPLIN, SAMPSON | 3 | Eastern Carolina RPO, Mid-Carolina RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 507000 | FY 2025: 507000
HS-2003AI | Highway | Safety | US 117/NC 132 (COLLEGE ROAD) | AT SR 2160 (LONG RIDGE ROAD). INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 575000 | FY 2025: 575000
HS-2003AJ | Highway | Safety | US 17 (MARINE BOULEVARD) | AT US 17 BUSINESS (MARINE BOULEVARD) AND HENDERSON DRIVE IN JACKSONVILLE. UPGRADE TRAFFIC SIGNAL AND PAVEMENT MARKINGS, AND INSTALL PEDESTRIAN IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 51000 | FY 2025: 51000
HS-2003AJ | Highway | Safety | US 17 (MARINE BOULEVARD) | AT US 17 BUSINESS (MARINE BOULEVARD) AND HENDERSON DRIVE IN JACKSONVILLE. UPGRADE TRAFFIC SIGNAL AND PAVEMENT MARKINGS, AND INSTALL PEDESTRIAN IMPROVEMENTS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 159000 | FY 2025: 2000; FY 2026: 157000
HS-2003AK | Highway | Safety | SR 1301 (PRINCESS PLACE DRIVE) | AT NORTH 30TH STREET IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND PAVEMENT MARKINGS, AND INSTALL PEDESTRIAN SIGNALS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | RIGHT-OF-WAY | 15000
HS-2003AK | Highway | Safety | SR 1301 (PRINCESS PLACE DRIVE) | AT NORTH 30TH STREET IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND PAVEMENT MARKINGS, AND INSTALL PEDESTRIAN SIGNALS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 151000 | FY 2025: 151000
HS-2003AL | Highway | Safety | US 117 | AT NC 53 IN BURGAW. UPGRADE TRAFFIC SIGNAL. | 0.5 | PENDER | 3 | Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 12000
HS-2003AM | Highway | Safety | NC 53 (WESTERN BOULEVARD) | AT FORUM ROAD/MARTY GOLDMAN WAY IN JACKSONVILLE. INSTALL CROSSWALKS AND PEDESTRIAN SIGNALS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 178000 | FY 2025: 178000
HS-2003AN | Highway | Safety | US 17/76 (DAWSON STREET AND WOOSTER STREET) | AT SR 1216 (16TH STREET) AND SR 1217 (17TH STREET) IN WILMINGTON. UPGRADE TRAFFIC SIGNALS, AND INSTALL CROSSWALKS AND PEDESTRIAN SIGNALS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 147000 | FY 2025: 147000
HS-2003AO | Highway | Safety | SR 1175 (KERR AVENUE) | AT SR 2048 (GORDON ROAD)/SR 1327 (FARLEY DRIVE). UPGRADE TRAFFIC SIGNAL. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 33000
HS-2003AP | Highway | Safety | SR 1302 (23RD STREET) | AT SR 1301 (PRINCESS PLACE DRIVE) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 195000 | FY 2025: 195000
HS-2003AQ | Highway | Safety | SR 2817 (17TH STREET) | AT CASTLE STREET IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND SIGNS, AND INSTALL PEDESTRIAN SIGNALS AND CURB BUMP OUTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 141000 | FY 2025: 141000
HS-2003AR | Highway | Safety | US 17 BUSINESS | AT NC 906 (MIDWAY ROAD). INSTALL TRAFFIC SIGNAL. | 0.5 | BRUNSWICK | 3 | Cape Fear RPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 48000 | FY 2025: 48000
HS-2003AR | Highway | Safety | US 17 BUSINESS | AT NC 906 (MIDWAY ROAD). INSTALL TRAFFIC SIGNAL. | 0.5 | BRUNSWICK | 3 | Cape Fear RPO |  | Region B |  | HSIP | CONSTRUCTION | 257000 | FY 2025: 3000; FY 2026: 254000
HS-2003AS | Highway | Safety | US 74/76 (ANDREW JACKSON HIGHWAY) | EASTBOUND RAMP AT SR 1426 (LANVALE ROAD). INSTALLTRAFFIC SIGNAL. | 0.5 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 237000 | FY 2025: 237000
HS-2003AT | Highway | Safety | NC 24 | AT SR 1445 (NORRIS ROAD) IN SWANSBORO. INSTALL CROSSWALKS, RAMPS, PEDESTRIAN SIGNALS, AND 100 FEET OF SIDEWALK. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 125000 | FY 2025: 125000
HS-2003AT | Highway | Safety | NC 24 | AT SR 1445 (NORRIS ROAD) IN SWANSBORO. INSTALL CROSSWALKS, RAMPS, PEDESTRIAN SIGNALS, AND 100 FEET OF SIDEWALK. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 325000 | FY 2025: 325000
HS-2003B | Highway | Safety | VARIOUS | INSTALL PAVEMENT MARKINGS ALONG VARIOUS ROUTES. |  | DUPLIN, SAMPSON | 3 | Eastern Carolina RPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 3 |  | HSIP | CONSTRUCTION | 3432000
HS-2003C | Highway | Safety | SR 1535 (LIDDELL ROAD) | SR 1535 (LIDDELL ROAD) AND SR 1534 (DRUMMERSVILLE ROAD). INSTALL ALL WAY STOP. | 0.5 | DUPLIN | 3 | Eastern Carolina RPO |  | Division 3 |  | HSIP | CONSTRUCTION | 51000 | FY 2025: 51000
HS-2003D | Highway | Safety | US 17 | US 17 AND SR 1130 (MOUNT PISGAH ROAD) / SR 1344 (SELLERS ROAD). INSTALL SIGNALIZED LEFTOVER. |  | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 269000 | FY 2025: 269000
HS-2003E | Highway | Safety | US 117 (SYCAMORE STREET) | US 117 (SYCAMORE STREET) AND SR 1102 (CHARITY ROAD) IN ROSE HILL. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 0.5 | DUPLIN | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 102000 | FY 2025: 102000
HS-2003F | Highway | Safety | US 17 | NC 210 INTERSECTION IN SURF CITY. REVISE TRAFFIC SIGNAL AND INSTALL BE PREPARED TO STOP SIGNS. | 0.5 | PENDER | 3 | Cape Fear RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 271000
HS-2003G | Highway | Safety | NC 130 | NC 130 AND SR 1120 (SABBATH HOME ROAD) / SR 1239 (OCEAN VIEW AVENUE) IN HOLDEN BEACH. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 0.5 | BRUNSWICK | 3 | Grand Strand Area Transportation Study |  | Region B |  | HSIP | CONSTRUCTION | 101000
HS-2003H | Highway | Safety | US 117 / NC 132 (COLLEGE ROAD) | US 117 / NC 132 (COLLEGE ROAD) AT LAKE AVENUE-HUGH MCRAE PARK IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 66000 | FY 2025: 66000
HS-2003I | Highway | Safety | NC 403 | NC 403 AT SR 1306 (BEAUTANCUS ROAD). INSTALL ALL WAY STOP, STOP AHEAD WARNING SIGNS, BRIGHTSIDES, STOP BARS, CONCRETE ISLAND, AND REFRESH PAVEMENT MARKINGS. REMOVE ACTUATED CURVE WARNING FLASHER. | 0.5 | DUPLIN | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 224000 | FY 2025: 224000
HS-2003J | Highway | Safety | US 17 (OLEANDER DRIVE) | US 17 (OLEANDER DRIVE) AT 42ND STREET IN WILMINGTON. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 59000 | FY 2025: 59000
HS-2003K | Highway | Safety | US 74 WESTBOUND ON-RAMP | US 74 WESTBOUND ON-RAMP AND SR 1627 (3RD STREET / MARTIN LUTHER KING JUNIOR BOULEVARD) IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 16000 | FY 2025: 16000
HS-2003L | Highway | Safety | US 17-76 (OLEANDER DRIVE) | US 17-76 (OLEANDER DRIVE) AND SR 1421 (GREENVILLE LOOP ROAD) / GREENVILLE AVENUE IN WILMINGTON. REVISE TRAFFIC SIGNAL. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 84000 | FY 2025: 84000
HS-2003M | Highway | Safety | US 117 (NORWOOD STREET) | US 117 (NORWOOD STREET) AND SR 1173 (SOUTHERLAND STREET) IN WALLACE. REVISE TRAFFIC SIGNAL. | 0.5 | DUPLIN | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 44000 | FY 2025: 44000
HS-2003N | Highway | Safety | NC 24 BUSINESS (ROUTELEDGE ROAD) | NC 24 BUSINESS (ROUTELEDGE ROAD) AND NC 24 / NC 903 (SOUTH KENANSVILLE BYPASS). REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | 0.5 | DUPLIN | 3 | Eastern Carolina RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 252000
HS-2003O | Highway | Safety | US 74/76 | US 74/76 AT SR 1714 (ENTERPRISE DRIVE) AND US 74/76 AT SR 1494 (WOOD TREATMENT ROAD). INSTALL TRAFFIC SIGNALS. | 0.5 | BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 533000 | FY 2026: 533000
HS-2003P | Highway | Safety | US 117 (SHIPYARD BOULEVARD) | US 117 (SHIPYARD BOULEVARD) AT CONVERSE ROAD / LONGSTREET DRIVE IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND ADD PEDESTRIAN ACCOMMODATIONS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2025: 30000
HS-2003P | Highway | Safety | US 117 (SHIPYARD BOULEVARD) | US 117 (SHIPYARD BOULEVARD) AT CONVERSE ROAD / LONGSTREET DRIVE IN WILMINGTON. UPGRADE TRAFFIC SIGNAL AND ADD PEDESTRIAN ACCOMMODATIONS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 271000 | FY 2026: 271000
HS-2003Q | Highway | Safety | US 17 (DAWSON STREET) | US 17 (DAWSON STREET) AT US 421 (3RD STREET) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL, UPGRADE PAVEMENT MARKINGS, AND ADD PEDESTRIAN ACCOMMODATIONS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 184000 | FY 2026: 184000
HS-2003R | Highway | Safety | US 421 | US 421 AT SR 1573 (DOW ROAD) IN CAROLINA BEACH. UPGRADE TRAFFIC SIGNAL. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 23000 | FY 2026: 23000
HS-2003S | Highway | Safety | US 17 BUSINESS (MARKET STREET) | US 17 BUSINESS (MARKET STREET) AND SR 1272 (NEW CENTRE DRIVE). INSTALL CROSSWALKS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 58000 | FY 2025: 58000
HS-2003S | Highway | Safety | US 17 BUSINESS (MARKET STREET) | US 17 BUSINESS (MARKET STREET) AND SR 1272 (NEW CENTRE DRIVE). INSTALL CROSSWALKS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 114000 | FY 2026: 114000
HS-2003T | Highway | Safety | US 17 BUSINESS (MARKET STREET) | US 17 BUSINESS (MARKET STREET) AT SR 2219 (GREEN MEADOWS DRIVE) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 32000 | FY 2026: 32000
HS-2003U | Highway | Safety | SR 2048 (GORDON ROAD) | SR 2048 (GORDON ROAD) JUST WEST OF I-40. INSTALL SIX INCH PAVEMENT MARKINGS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Division 3 |  | HSIP | CONSTRUCTION | 37000
HS-2003V | Highway | Safety | US 17/76 (OLEANDER DRIVE) | US 17/76 (OLEANDER DRIVE) AT SR 1209 (INDEPENDENCE BOULEVARD) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2025: 30000
HS-2003V | Highway | Safety | US 17/76 (OLEANDER DRIVE) | US 17/76 (OLEANDER DRIVE) AT SR 1209 (INDEPENDENCE BOULEVARD) IN WILMINGTON. UPGRADE TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 23000 | FY 2026: 23000
HS-2003W | Highway | Safety | US 17 | US 17 AT SR 1136 (RED BUG ROAD) AND US 17 AT SR 1345 (ROYAL OAK ROAD). INSTALL A REDUCED CONFLICT INTERSECTION. | 0.5 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 1900000
HS-2003X | Highway | Safety | NC 24 | AT SR 1514 (PHILLIPS LOOP ROAD) IN SWANSBORO. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNALS AND ADVANCE FLASHERS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 184000 | FY 2025: 184000
HS-2003X | Highway | Safety | NC 24 | AT SR 1514 (PHILLIPS LOOP ROAD) IN SWANSBORO. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNALS AND ADVANCE FLASHERS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 202000 | FY 2025: 202000
HS-2003Y | Highway | Safety | US 117 / NC 132 (COLLEGE ROAD) | AT SR 2313 (WILSHIRE BOULEVARD) IN WILMINGTON. INSTALL PEDESTRIAN COUNTDOWN HEADS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 63000 | FY 2026: 63000
HS-2003Z | Highway | Safety | US 17/76 (WOOSTER STREET) | AT SR 1217 (17TH STREET) IN WILMINGTON. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN COUNTDOWN HEADS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 114000 | FY 2026: 114000
HS-2004 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2004AA | Highway | Safety | US 64 | US 64 BUSINESS (SUNSET AVENUE) AT RIVER DRIVE/LAKE DRIVE IN ROCKY MOUNT. CONSTRUCT PEDESTRIAN CROSSING INCLUDING REFUGE ISLAND, SIDEWALK, RECTANGULAR RAPID-FLASHING BEACONS, AND CONVERSION OF FULL MOVEMENT MEDIAN OPENING TO LEFT-OVER INTO LAKE DRIVE AND REVERSING ONE-WAY TRAFFIC FLOW ON RIVER DRIVE. | 0.5 | NASH | 4 | Rocky Mount Urban Area MPO |  | Region A |  | HSIP | CONSTRUCTION | 215000 | FY 2025: 215000
HS-2004AB | Highway | Safety | US 64 BUSINESS (RALEIGH BOULEVARD) | AT NC 43 (FAIRVIEW ROAD) IN ROCKY MOUNT. INSTALL PEDESTRIAN SIGNAL HEADS. | 0.5 | EDGECOMBE | 4 | Rocky Mount Urban Area MPO |  | Region A |  | HSIP | CONSTRUCTION | 28000
HS-2004AC | Highway | Safety | SR 1556 (WAYNE MEMORIAL DRIVE) | FROM US 70 BYPASS TO THE GREENE COUNTY LINE. INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS. | 7.3 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | HSIP | CONSTRUCTION | 210000
HS-2004AD | Highway | Safety | NC 39 | FROM US 301 NORTH OF SELMA TO THE WAKE COUNT LINE. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 18.5 | JOHNSTON | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 490000
HS-2004B | Highway | Safety | NC 97 | INSTALL LEFT TURN LANE AT NC 97 AND SR 1603 (OLD CARRIAGE ROAD). | 0.5 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | RIGHT-OF-WAY | 86000
HS-2004B | Highway | Safety | NC 97 | INSTALL LEFT TURN LANE AT NC 97 AND SR 1603 (OLD CARRIAGE ROAD). | 0.5 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 205000
HS-2004C | Highway | Safety | SR 1537 (AIRPORT ROAD) | INSTALL ALL WAY STOP AT SR 1537 (AIRPORT ROAD) AND SR 1545 (MT. CARMEL CHURCH ROAD). | 0.5 | WAYNE | 4 | Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 66000
HS-2004D | Highway | Safety | SR 1002 (PIKEVILLE-PRINCETON ROAD) | INSTALL ALL WAY STOP WITH ISLAND AT SR 1002 (PIKEVILLE-PRINCETON ROAD) AND SR 1320 (HINNANT ROAD). | 0.5 | WAYNE | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 65000
HS-2004E | Highway | Safety | NC 111 | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT NC 111 AND SR 1754 (ZION CHURCH ROAD). | 0.5 | WAYNE | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 152000
HS-2004F | Highway | Safety | SR 1103 (WIGGINS MILL ROAD) | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT SR 1103 (WIGGINS MILL ROAD) AND SR 1169 (RADFORD ROAD). | 0.5 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004G AND HS-2004H. | Division 4 |  | HSIP | CONSTRUCTION | 30000
HS-2004G | Highway | Safety | NC 48 | INSTALL ALL WAY STOP AND REVISE EXISTING OVERHEAD AND SHOULDER-MOUNTED FLASHERS AT NC 48 AND NC 903. | 0.5 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004H. | Region A |  | HSIP | CONSTRUCTION | 50000
HS-2004H | Highway | Safety | SR 1001 (OLD BAILEY HIGHWAY) | INSTALL ALL WAY STOP AT SR 1001 (OLD BAILEY HIGHWAY) AND SR 1717 (MACEDONIA ROAD / SANDY CROSS ROAD). | 0.5 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING COMBINED WITH HS-2004F AND HS-2004G. | Division 4 |  | HSIP | CONSTRUCTION | 25000
HS-2004I | Highway | Safety | SR 1744 (INDIAN SPRINGS ROAD) | INSTALL ALL WAY STOP AT SR 1744 (INDIAN SPRINGS ROAD) AND SR 1941 (NORTHEAST CHURCH ROAD). | 0.5 | WAYNE | 4 | Eastern Carolina RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 65000
HS-2004J | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS. |  | HALIFAX, JOHNSTON | 4 | Peanut Belt RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 5246000
HS-2004L | Highway | Safety | NC 242 | CURVE IMPROVEMENTS BETWEEN 0.08 MILES AND 0.31 MILES NORTH OF SR 1116 (GODWIN LAKE ROAD). | 0.23 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | RIGHT-OF-WAY | 272000
HS-2004L | Highway | Safety | NC 242 | CURVE IMPROVEMENTS BETWEEN 0.08 MILES AND 0.31 MILES NORTH OF SR 1116 (GODWIN LAKE ROAD). | 0.23 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 685000
HS-2004M | Highway | Safety | NC 48 | INSTALL MINI ROUNDABOUTS ALONG NC 48 (GOLDROCK ROAD) AT WATERLOO DRIVE / ROUNDTREE DRIVE AND AT GREYSON ROAD / CUNNINGHAM DRIVE. | 0.5 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 441000
HS-2004N | Highway | Safety | SR 1700 (OAK LEVEL ROAD) | SR 1700 (OAK LEVEL ROAD) AT SR 1603 (OLD CARRIAGE ROAD). REVISE TRAFFIC SIGNAL. | 0.5 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 351000
HS-2004O | Highway | Safety | SR 1320 (AIRPORT BOULEVARD) | SR 1320 (AIRPORT BOULEVARD) AT CHELSEA DRIVE AND SR 1320 (AIRPORT BOULEVARD) AT JETSTREAM DRIVE IN WILSON. INSTALL TRAFFIC SIGNALS. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | UTILITIES | 140000
HS-2004O | Highway | Safety | SR 1320 (AIRPORT BOULEVARD) | SR 1320 (AIRPORT BOULEVARD) AT CHELSEA DRIVE AND SR 1320 (AIRPORT BOULEVARD) AT JETSTREAM DRIVE IN WILSON. INSTALL TRAFFIC SIGNALS. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 520000 | FY 2025: 58000
HS-2004P | Highway | Safety | US 301 (BRIGHTLEAF BOULEVARD) | US 301 (BRIGHTLEAF BOULEVARD) AT NORTH STREET IN SMITHFIELD. INSTALL / UPGRADE HIGH VISIBILITY CROSSWALKS, AUDIBLE COUNTDOWN PEDESTRIAN SIGNAL HEADS, PEDESTRIAN IMPROVEMENTS, TRAFFIC SIGNAL, AND TRAFFIC SIGNAL SYSTEM. | 0.5 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 350000
HS-2004Q | Highway | Safety | US 64 | US 64 AT BRIDGES 630019 AND 630020 OVER TAR RIVER. PAVEMENT IMPROVEMENTS. | 0.5 | NASH | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 900000
HS-2004R | Highway | Safety | US 258 | US 258 BETWEEN THE PITT COUNTY LINE AND US 64 IN EDGECOMBE COUNTY AND BETWEEN PRINCEVILLE AND SR 1102 (MULLIN ROAD) IN HALIFAX COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS, SNOWPLOWABLE PAVEMENT MARKERS, AND RUMBLE STRIPES. | 31.69 | EDGECOMBE, HALIFAX | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 780000
HS-2004S | Highway | Safety | SR 1902 (GLEN LAUREL ROAD) | SR 1902 (GLEN LAUREL ROAD) AT SR 1903 (VINSON ROAD). TRAFFIC SIGNAL INSTALLATION. | 0.5 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. | Division 4 |  | HSIP | CONSTRUCTION | 350000
HS-2004T | Highway | Safety | US 158 | US 158 FROM EASTERN LITTLETON TOWN LIMITS AND 0.15 MILES WEST OF SR 1432 (EVERETTS SCHOOL ROAD). INSTALL RUMBLE STRIPES WITH SIX-INCH PAVEMENT MARKINGS. | 9.41 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 2474000
HS-2004U | Highway | Safety | NC 58 | NC 58 FROM NORTHERN STATONSBURG TOWN LIMITS TO 0.3 MILES NORTH OF SR 1622 (EVANSDALE ROAD) IN WILSON COUNTY. NC 58 FROM SOUTH OF SR 1314 (THOMPSON CHAPEL CHURCH ROAD) IN WILSON COUNTY TO SOUTHERN NASHVILLE TOWN LIMIT IN NASH COUNTY. NC 58 FROM SOUTH OF SR 1004 (TAYLORS STORE ROAD) TO SOUTHERN CASTALIA TOWN LIMIT IN NASH COUNTY. INSTALL RUMBLE STRIPS WITH SIX-INCH PAVEMENT MARKINGS. |  | NASH, WILSON | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 2474000
HS-2004V | Highway | Safety | NC 111 | NC 111 FROM WAYNE/DUPLIN COUNTY LINE TO SR 1727 (DOLLARD TOWN ROAD). NC 111 FROM US 70 BYPASS OVERPASS TO NC 222. NC 111/NC 222 FROM FREMONT LIMITS TO SR 1513 (RED HILL ROAD). NC 111/NC 222 FROM STANTONSBURG LIMITS TO SARATOGA LIMITS. NC 111 FROM NC 222 IN WILSON COUNTY TO SR 1344 (SARA LEE ROAD) IN EDGECOMBE COUNTY. NC 111 FROM PRINCEVILLE TO EDGECOMBE/MARTIN COUNTY LINE. INSTALL RUMBLE STRIPS WITH SIX-INCH PAVEMENT MARKINGS. |  | WAYNE, EDGECOMBE, WILSON | 4 | Upper Coastal Plain RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 2474000 | FY 2025: 693000
HS-2004W | Highway | Safety | US 70 | US 70 AT US 70A/SR 2532 (WEST EDWARDS STREET) AND US 70 AT SR 2314 (PONDFIELD ROAD). INSTALL REDUCED CONFLICT INTERSECTION WITH WESTBOUND U-TURN AT SR 2314 (PONDFIELD ROAD). | 0.38 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 754000
HS-2004X | Highway | Safety | NC 43 | NC 43 FROM 0.5 MILES NORTH OF SR 1425 (CASTALIA ROAD) IN NASH COUNTY TO NC 561 IN HALIFAX COUNTY. INSTALL RUMBLE STRIPS. | 13.51 | NASH, HALIFAX | 4 | Upper Coastal Plain RPO, Peanut Belt RPO | UNDER CONSTRUCTION. | Region A |  | HSIP | CONSTRUCTION | 2474000
HS-2004Y | Highway | Safety | VARIOUS | 194 FREEWAY RAMPS. INSTALL WRONG WAY PAVEMENT MARKINGS AND SIGNS | 0.5 | JOHNSTON, NASH, WAYNE, WILSON, EDGECOMBE, HALIFAX | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 650000 | FY 2025: 155000
HS-2005 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2005A | Highway | Safety | SR 1602 (MAIN STREET) | SR 1207 (SPRING STREET) INTERSECTION IN OXFORD. CONSTRUCT MINI-ROUNDABOUT. |  | GRANVILLE | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 100000
HS-2005B | Highway | Safety | NC 903 | NC 903 CAUSEWAY ON EATONS FERRY BRIDGE OVER LAKE GASTON. UPGRADE GUARDRAIL. | 0.85 | WARREN | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 130000
HS-2005C | Highway | Safety | NC 54 | NC 55 IN DURHAM. INSTALL CONCRETE PEDESTRIAN REFUGE ISLANDS IN ALL QUADRANTS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 75000 | FY 2025: 74000
HS-2005D | Highway | Safety | SR 1303 (PICKETT ROAD) | SR 1116 (GARRETT ROAD)/(LUNA LANE) INTERSECTION IN DURHAM. INSTALL ALL WAY STOP. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000
HS-2005D | Highway | Safety | SR 1303 (PICKETT ROAD) | SR 1116 (GARRETT ROAD)/(LUNA LANE) INTERSECTION IN DURHAM. INSTALL ALL WAY STOP. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 40000
HS-2005E | Highway | Safety | US 15 / US 501 BUSINESS | NC 751 (ACADEMY ROAD) INTERCHANGE IN DURHAM. INSTALL GUARDRAIL. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 175000
HS-2005F | Highway | Safety | VARIOUS | DOWNTOWN RALEIGH BUSINESS DISTRICT. TRAFFIC SIGNAL REVISIONS AT VARIOUS LOCATIONS. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Division 5 |  | HSIP | CONSTRUCTION | 200000
HS-2005G | Highway | Safety | SR 2215 (BUFFALOE ROAD) | SR 2214 (SOUTHHALL ROAD)/BRINTONS COTTAGE STREET AND VALLEY STREAM DRIVE INTERSECTIONS IN RALEIGH. TRAFFIC SIGNALS REVISIONS, CURB RAMPS, AND PAVEMENT MARKINGS. | 0.33 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 147000 | FY 2025: 48000
HS-2005H | Highway | Safety | SR 1973 (PAGE ROAD) | CHURCHILL HALL/ARBY'S/MCDONALD DRIVEWAY. INSTALL DIRECTIONAL CROSSOVER. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 20000 | FY 2025: 20000
HS-2005I | Highway | Safety | SR 1645 (LUMLEY ROAD) | I-540 WESTBOUND RAMP/ARCO CORPORATE DRIVE IN RALEIGH. WIDENING, TURN LANE CONSTRUCTION, TRAFFIC SIGNAL UPGRADE. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 240000 | FY 2025: 240000
HS-2005J | Highway | Safety | SR 2516 (HODGE ROAD) | THE MINGO CREEK TRAIL CROSSING. RELOCATE CROSSWALK. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 190000
HS-2005K | Highway | Safety | US 401 | SR 2108/SR 2036 (NEW HOPE ROAD) AND US 401 AT CALVARY DRIVE. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | 0.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C |  | HSIP | CONSTRUCTION | 170000 | FY 2025: 55000
HS-2005L | Highway | Safety | SR 1327 (GREGSON STREET) | SR 1327 (GREGSON STREET) AT KNOX STREET. INSTALL TRAFFIC SIGNAL. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 110000 | FY 2025: 74000; FY 2026: 36000
HS-2005M | Highway | Safety | NC 55 (ALSTON AVENUE) | SR 1670 (GEER STREET) IN DURHAM. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNAL HEADS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 62000 | FY 2025: 61000
HS-2005N | Highway | Safety | NC 98 | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 500000 | FY 2025: 500000
HS-2005N | Highway | Safety | NC 98 | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 285000 | FY 2026: 217000; FY 2027: 68000
HS-2005N | Highway | Safety | NC 98 | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | T | CONSTRUCTION | 1000000 | FY 2026: 760000; FY 2027: 240000
HS-2005N | Highway | Safety | NC 98 | NC 98 AT SR 1919 (LYNN ROAD). WIDEN FOR LEFT TURN LANES. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | L | CONSTRUCTION | 500000 | FY 2026: 345000; FY 2027: 155000
HS-2005O | Highway | Safety | US 1 / US 158 | US 1 / US 158 AT SR 1237 (MASON DREWRY ROAD). INTERSECTION REALIGNMENT. | 0.5 | WARREN | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 31000 | FY 2025: 31000
HS-2005O | Highway | Safety | US 1 / US 158 | US 1 / US 158 AT SR 1237 (MASON DREWRY ROAD). INTERSECTION REALIGNMENT. | 0.5 | WARREN | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | UTILITIES | 80000 | FY 2025: 80000
HS-2005O | Highway | Safety | US 1 / US 158 | US 1 / US 158 AT SR 1237 (MASON DREWRY ROAD). INTERSECTION REALIGNMENT. | 0.5 | WARREN | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 335000 | FY 2025: 335000
HS-2005P | Highway | Safety | US 501 | US 501 AT NC 57 (HILLSBOROUGH ROAD). INSTALL TRAFFIC SIGNAL. | 0.5 | PERSON | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 260000 | FY 2025: 3000; FY 2026: 257000
HS-2005Q | Highway | Safety | SR 1142 (HUMIE OLIVE ROAD) | SR 1142 (HUMIE OLIVE ROAD) AT BLAZING TRAIL DRIVE/DRIVEWAY ACCESS TO APEX FRIENDSHIP HIGH AND ELEMENTARY SCHOOLS. INSTALL TRAFFIC AND PEDESTRIAN SIGNALS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 130000 | FY 2025: 42000
HS-2005S | Highway | Safety | NC 98 NC 98 | NC 98 NC 98 AT SR 1815 (MINERAL SPRINGS ROAD). CONSTRUCT RIGHT TURN LANES AND SIDEWALK. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 700000 | FY 2025: 7000; FY 2026: 693000
HS-2006 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2006A | Highway | Safety | SR 1415 (YADKIN ROAD) | SR 1415 (YADKIN ROAD) AT US 401 (SKIBO ROAD), AT SR 1437 (SANTE FE DRIVE), AND AT SOUTHWICK DRIVE. ADD SIGNALIZED PEDESTRIAN CROSSINGS TO ALL THREE INTERSECTIONS AND UPGRADE SIGNAL AT SOUTHWICK DRIVE. | 1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 1350000
HS-2006A | Highway | Safety | SR 1415 (YADKIN ROAD) | SR 1415 (YADKIN ROAD) AT US 401 (SKIBO ROAD), AT SR 1437 (SANTE FE DRIVE), AND AT SOUTHWICK DRIVE. ADD SIGNALIZED PEDESTRIAN CROSSINGS TO ALL THREE INTERSECTIONS AND UPGRADE SIGNAL AT SOUTHWICK DRIVE. | 1 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | TADA | CONSTRUCTION | 100000
HS-2006AA | Highway | Safety | SR 1340 (ODOM STREET / PROSPECT ROAD) | AT NC 711 (THIRD STREET) IN PEMBROKE. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNAL HEADS AND PEDESTRIAN REFUGE ISLAND, AND UPGRADE TRAFFIC SIGNAL. FROM NC 711 (THIRD STREET) TO SR 1566 (CORINTH ROAD). INSTALL RECTANGUAR RAPID FLASHING BEACONS. | 0.89 | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 835000 | FY 2025: 835000
HS-2006AB | Highway | Safety | VARIOUS | I-95, US 74, US 301, NC 87, AND SR 1007. INSTALL PAVEMENT MARKING ARROWS AND RAISED PAVEMENT MARKERS ON FREEWAY/EXPRESSWAY RAMPS. |  | CUMBERLAND, ROBESON, COLUMBUS, HARNETT | 6 | Lumber River RPO, Fayetteville Area MPO, Mid-Carolina RPO, Cape Fear RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 200000
HS-2006AC | Highway | Safety | NC 210 | FROM THE BLADEN COUNTY LINE TO NC 53 IN CUMBERLAND COUNTY AND FROM THE CUMBERLAND COUNTY LINE TO LILLINGTON CITY LIMITS IN HARNETT COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | CUMBERLAND, HARNETT | 6 | Mid-Carolina RPO, Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 1170000 | FY 2025: 662000
HS-2006AD | Highway | Safety | NC 71 | FROM LUMBER BRIDGE CITY LIMITS TO PARKTON CITY LIMITS AND FROM PARKTON CITY LIMITS TO US 301. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 320000 | FY 2025: 115000
HS-2006AE | Highway | Safety | SR 1561 (UNIVERSITY ROAD) | FROM NC 711 TO HAWK DRIVE IN PEMBROKE. INSTALL PEDESTRIAN SIGNALS AND CROSS WALKS AT FIVE LOCATIONS. | 0.51 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | HSIP | CONSTRUCTION | 300000 | FY 2025: 300000
HS-2006B | Highway | Safety | SR 1006 (PERSON STREET) | SR 1006 (PERSON STREET) FROM US 301 / I-95 BUSINESS (EASTERN BOULEVARD) TO JUST EAST OF WATER STREET. CONVERT SECTION FROM FOUR LANES TO THREE LANES WITH INTERSECTION IMPROVEMENTS AT BROAD STREET AND EASTERN BOULEVARD IN FAYETTEVILLE. | 0.34 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 651000
HS-2006C | Highway | Safety | NC 53 (CEDAR CREEK ROAD) | NC 53 (CEDAR CREEK ROAD) FROM JUST NORTH OF PLYMOUTH STREET TO JUST SOUTH OF TROY DRIVE. INSTALL MEDIAN WITH SOUTHBOUND U-TURN AND BULB-OUT, SIDEWALK, AND RECTANGULAR RAPID FLASHING BEACON PEDESTRIAN CROSSING WITH REFUGE IN FAYETTEVILLE. | 0.21 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HSIP | RIGHT-OF-WAY | 210000
HS-2006C | Highway | Safety | NC 53 (CEDAR CREEK ROAD) | NC 53 (CEDAR CREEK ROAD) FROM JUST NORTH OF PLYMOUTH STREET TO JUST SOUTH OF TROY DRIVE. INSTALL MEDIAN WITH SOUTHBOUND U-TURN AND BULB-OUT, SIDEWALK, AND RECTANGULAR RAPID FLASHING BEACON PEDESTRIAN CROSSING WITH REFUGE IN FAYETTEVILLE. | 0.21 | CUMBERLAND | 6 | Fayetteville Area MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | HSIP | CONSTRUCTION | 1631000
HS-2006D | Highway | Safety | SR 1935 (HOWELL ROAD) | CONVERT INTERSECTION OF SR 1924 (BARKER TEN MILE ROAD) AND SR 1935 (HOWELL ROAD) TO AN ALL WAY STOP. REALIGN NORTH LEG OF SR 1005 (TOLARSVILLE ROAD) AT SR 1935 (HOWELL ROAD) AND REMOVE SOUTH LEG. | 0.5 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | RIGHT-OF-WAY | 25000
HS-2006D | Highway | Safety | SR 1935 (HOWELL ROAD) | CONVERT INTERSECTION OF SR 1924 (BARKER TEN MILE ROAD) AND SR 1935 (HOWELL ROAD) TO AN ALL WAY STOP. REALIGN NORTH LEG OF SR 1005 (TOLARSVILLE ROAD) AT SR 1935 (HOWELL ROAD) AND REMOVE SOUTH LEG. | 0.5 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 566000
HS-2006E | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS AT VARIOUS LOCATIONS. |  | HARNETT, BLADEN, CUMBERLAND, COLUMBUS | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 4715000
HS-2006F | Highway | Safety | NC 211 | NC 211 FROM THE BRUNSWICK COUNTY LINE TO NC 214. INSTALL RUMBLE STRIPES. | 9.48 | COLUMBUS | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 1051000
HS-2006G | Highway | Safety | SR 1835 (ROCK HILL ROAD) | SR 1835 (ROCK HILL ROAD) AT SR 1838 (DUNN ROAD) IN EASTOVER. REALIGN SR 1838 (DUNN ROAD) TO FORM A T-INTERSECTION WITH SR 1835 (ROCK HILL ROAD) AND REMOVE SLIP LANES. | 0.15 | CUMBERLAND | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 282000
HS-2006H | Highway | Safety | NC 27 | NC 24/27 FROM THE MOORE COUNTY LINE AND THE NC 24/27 SPLIT, NC 27 FROM NC 24 TO LILLINGTON, NC 27 FROM US 421 TO COATS, AND NC 27 FROM COATS TO THE JOHNSTON COUNTY LINE. INSTALL RUMBLE STRIPES, RUMBLE STRIPS, AND LONG-LIFE PAVEMENT MARKINGS. |  | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 1065000
HS-2006I | Highway | Safety | NC 710 | NC 710 AT SR 1340 (PROSPECT ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 170000
HS-2006I | Highway | Safety | NC 710 | NC 710 AT SR 1340 (PROSPECT ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 80000
HS-2006I | Highway | Safety | NC 710 | NC 710 AT SR 1340 (PROSPECT ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 2262000 | FY 2025: 1622000; FY 2026: 640000
HS-2006J | Highway | Safety | US 501/NC 130 | US 501/NC 130 NEAR SR 1134 (KITCHEN ROAD). CURVE IMPROVEMENTS. | 0.14 | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 25000
HS-2006J | Highway | Safety | US 501/NC 130 | US 501/NC 130 NEAR SR 1134 (KITCHEN ROAD). CURVE IMPROVEMENTS. | 0.14 | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | UTILITIES | 1000
HS-2006J | Highway | Safety | US 501/NC 130 | US 501/NC 130 NEAR SR 1134 (KITCHEN ROAD). CURVE IMPROVEMENTS. | 0.14 | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 410000 | FY 2025: 410000
HS-2006K | Highway | Safety | SR 1441 (CHALYBEATE SPRINGS ROAD) | FROM NC 55 TO US 401. CURVE AND PAVEMENT MARKING IMPROVEMENTS. | 4.23 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | HSIP | RIGHT-OF-WAY | 45000
HS-2006K | Highway | Safety | SR 1441 (CHALYBEATE SPRINGS ROAD) | FROM NC 55 TO US 401. CURVE AND PAVEMENT MARKING IMPROVEMENTS. | 4.23 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | HSIP | UTILITIES | 25000 | FY 2025: 25000
HS-2006K | Highway | Safety | SR 1441 (CHALYBEATE SPRINGS ROAD) | FROM NC 55 TO US 401. CURVE AND PAVEMENT MARKING IMPROVEMENTS. | 4.23 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 1150000 | FY 2025: 1150000
HS-2006L | Highway | Safety | NC 87 | NC 87 AT SR 1004 (TAR HEEL ROAD) AND SR 1316 (TAR HEEL FERRY ROAD). REVISE TRAFFIC SIGNAL. | 0.5 | BLADEN | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 121000
HS-2006M | Highway | Safety | SR 1325 (GUM SPRINGS ROAD) | SR 1325 (GUM SPRINGS ROAD) NEAR SR 1327. CURVE IMPROVEMENTS. | 0.25 | BLADEN | 6 | Mid-Carolina RPO |  | Division 6 |  | HSIP | CONSTRUCTION | 174000
HS-2006N | Highway | Safety | SR 1596 (GLENSFORD DRIVE) | FROM US 401 (RAEFORD ROAD) AND SR 1400 (CLIFFDALE ROAD) IN FAYETTEVILLE. PAVEMENT MARKING AND SIGNING IMPROVEMENTS. | 1.16 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 81000 | FY 2025: 81000
HS-2006O | Highway | Safety | SR 1596 (GLENSFORD DRIVE) | SR 1596 (GLENSFORD DRIVE) AT BEREAN BAPTIST ACADEMY AND AT CHAMBERSURG ROAD IN FAYETTEVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACONS WITH REFUGE ISLANDS. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 334000 | FY 2025: 334000
HS-2006P | Highway | Safety | SR 3950 (RAMSEY STREET) | SR 3950 (RAMSEY STREET) AT RAILROAD BRIDGE 250216 IN FAYETTEVILLE. INSTALL GUARDRAIL. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 250000 | FY 2025: 250000
HS-2006Q | Highway | Safety | SR 1532 (LANGDON ROAD) | SR 1532 (LANGDON ROAD) AT BRIDGE 420015. UPGRADE GUARDRAIL. | 0.5 | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | RIGHT-OF-WAY | 40000
HS-2006Q | Highway | Safety | SR 1532 (LANGDON ROAD) | SR 1532 (LANGDON ROAD) AT BRIDGE 420015. UPGRADE GUARDRAIL. | 0.5 | HARNETT | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 1767000
HS-2006R | Highway | Safety | I-95 | I-95 FROM MILEMARKER 2.0 TO MILEMARKER 12.45. INSTALL CABLE MEDIAN BARRIER. | 10.45 | ROBESON | 6 | Lumber River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 815000
HS-2006S | Highway | Safety | US 501 | FROM NC 130 TO THE SCOTLAND COUNTY LINE. INSTALL RUMBLE STRIPES. | 5.41 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 1051000
HS-2006T | Highway | Safety | NC 72 | FROM US 74 TO NC 41 / NC 211. INSTALL RUMBLE STRIPES AND RAISED PAVEMENT MARKERS. | 11.84 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 1051000
HS-2006U | Highway | Safety | NC 72 | FROM NC 711 TO NC 710. INSTALL RUMBLE STRIPES AND RAISED PAVEMENT MARKERS. | 14.42 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 1051000
HS-2006V | Highway | Safety | SR 1600 (MCARTHUR ROAD) | SR 1600 (MCARTHUR ROAD) AT SR 1615 (ROSEHILL ROAD/STACY WEAVER ROAD) IN FAYETTEVILLE. CONSTRUCT SIGNALIZED PEDESTRIAN ACCOMMODATIONS. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 1450000
HS-2006W | Highway | Safety | US 401 | BETWEEN FAYETTEVILLE AND HARNETT COUNTY (MILEPOST 20 - 27.7), BETWEEN CUMBERLAND COUNTY AND LILLINGTON (MILEPOST 0 - 9.5), AND BETWEEN LILLINGTON AND WAKE COUNTY (MILEPOST 12.5 - 22.1). INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS. |  | HARNETT, CUMBERLAND | 6 | Mid-Carolina RPO, Capital Area MPO, Fayetteville Area MPO | UNDER CONSTRUCTION. | Region C |  | HSIP | CONSTRUCTION | 975000
HS-2006X | Highway | Safety | US 401 (SKIBO ROAD) | AT SR 1007 (ALL AMERICAN FREEWAY) NORTHBOUND AND SOUTHBOUND RAMPS IN FAYETTEVILLE. INSTALL SIGNALIZED PEDESTRIAN ACCOMMODATIONS. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1450000
HS-2006Y | Highway | Safety | SR 1115 (BUFFALO LAKE ROAD) | FROM NC 27 TO NC 87. INSTALL RUMBLE STRIPES WITH PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS. | 4.57 | HARNETT | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | Division 6 |  | HSIP | CONSTRUCTION | 235000
HS-2006Z | Highway | Safety | SR 1414 (BROADFOOT ROAD) | SR 1414 (RAEFORD ROAD/BROADFOOT AVENUE) AT ARSENAL AVENUE IN FAYETTEVILLE. INSTALL CROSSWALKS WITH PEDESTRIAN SIGNAL HEAD. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | HSIP | CONSTRUCTION | 390000 | FY 2025: 141000
HS-2007 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2007A | Highway | Safety | I-85 BUSINESS/US29/70 | I-85 BUSINESS/US 29/70 SOUTHBOUND AND NORTHBOUND FROM RANDOLPH COUNTY LINE TO NORTH OF SR 1145 (RIVERDALE DRIVE) IN HIGH POINT. INSTALL GUARDRAIL. | 6.52 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 540000
HS-2007B | Highway | Safety | I-85 BUSINESS/US29/70 | I-85 BUSINESS/US 29/70 NORTHBOUND FROM NORTH OF SR 1145 (RIVERDALE DRIVE) TO I-85 IN HIGH POINT. INSTALL GUARDRAIL. | 3.13 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 270000
HS-2007C | Highway | Safety | VARIOUS | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Burlington-Graham MPO, Central Pines RPO, Greensboro Urban Area MPO, Piedmont Triad RPO | UNDER CONSTRUCTION | Division 7 |  | HSIP | CONSTRUCTION | 1717000
HS-2007D | Highway | Safety | I-74 AND US 29/70 | I-74 AND US 29/70 (I-85 BUSINESS INTERCHANGE). UPGRADE SIGNALS, PAVEMENT MARKINGS, AND SIGNING. | 1 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | HSIP | CONSTRUCTION | 400000 | FY 2025: 396000
HS-2007E | Highway | Safety | NC 62 | NC 62 FROM WEST OF SR 1138 (TOM BALL ROAD) TO WEST OF THE ALAMANCE COUNTY LINE. INSTALL PAVEMENT MARKINGS. | 20.69 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Division 7 |  | HSIP | CONSTRUCTION | 401000
HS-2007F | Highway | Safety | NC 87 | NC 87 AT I-40 EASTBOUND ON-RAMP. INSTALL PEDESTRIAN ACCOMMODATIONS. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Region D |  | HSIP | CONSTRUCTION | 87000
HS-2007G | Highway | Safety | US 29 | US 29 AT LAKEVIEW MEMORIAL PARK CEMETERY ENTRANCE. CONSTRUCT DIRECTIONAL CROSSOVER. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 410000
HS-2007H | Highway | Safety | SR 1009 (OLD NC 86) | SR 1727 (EUBANKS ROAD) NEAR CHAPEL HILL. MODIFY RIGHT TURN LANE. | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2025: 10000
HS-2007H | Highway | Safety | SR 1009 (OLD NC 86) | SR 1727 (EUBANKS ROAD) NEAR CHAPEL HILL. MODIFY RIGHT TURN LANE. | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | HSIP | UTILITIES | 5000 | FY 2025: 5000
HS-2007H | Highway | Safety | SR 1009 (OLD NC 86) | SR 1727 (EUBANKS ROAD) NEAR CHAPEL HILL. MODIFY RIGHT TURN LANE. | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 137000 | FY 2025: 137000
HS-2007I | Highway | Safety | SR 4240 (EAST GATE CITY BOULEVARD / LEE STREET) | SR 4240 (EAST GATE CITY BOULEVARD / LEE STREET) AT I-40 WESTBOUND RAMPS. INTERSECTION AND TURN LANE IMPROVEMENTS, AND TRAFFIC SIGNAL INSTALLATION. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 5000 | FY 2025: 5000
HS-2007I | Highway | Safety | SR 4240 (EAST GATE CITY BOULEVARD / LEE STREET) | SR 4240 (EAST GATE CITY BOULEVARD / LEE STREET) AT I-40 WESTBOUND RAMPS. INTERSECTION AND TURN LANE IMPROVEMENTS, AND TRAFFIC SIGNAL INSTALLATION. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 752000 | FY 2026: 752000
HS-2007J | Highway | Safety | NC 86 | NC 86 (MARTIN LUTHER KING BOULEVARD) AT CRITZ DRIVE. INSTALL PEDISTRIAN IMPROVEMENTS. | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | HSIP | CONSTRUCTION | 530000 | FY 2025: 530000
HS-2007K | Highway | Safety | I-40 | I-40 WEST MEDIAN FROM BUFFALO CREEK BRIDGE EAST FOR 1550 FEET AND I-40 EAST EXIT 219 TO US 29 SOUTH. INSTALL GUARDRAIL. | 0.4 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 265000
HS-2008 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2008A | Highway | Safety | US 74 | RICHMOND COUNTY LINE TO SR 1363. UPGRADE GUARDRAIL. | 4.33 | SCOTLAND | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | HSIP | CONSTRUCTION | 360000
HS-2008B | Highway | Safety | VARIOUS | VARIOUS NHS AND PRIMARY ROUTES IN DIVISION 8, DISTRICT 2. UPGRADE GUARDRAIL. |  | MOORE, HOKE, LEE | 8 | Central Pines RPO, Lumber River RPO, Sandhills MPO | UNDER CONSTRUCTION | Region E |  | HSIP | CONSTRUCTION | 250000
HS-2008C | Highway | Safety | VARIOUS | VARIOUS SECONDARY ROUTES IN CHATHAM, LEE, HOKE, RANDOLPH AND SCOTLAND COUNTIES. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | CHATHAM, HOKE, LEE, RANDOLPH, SCOTLAND | 8 | Central Pines RPO, Lumber River RPO, Piedmont Triad RPO, High Point Urban Area MPO, Fayetteville Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Region E |  | HSIP | CONSTRUCTION | 1580000
HS-2008D | Highway | Safety | US 421 | CHATHAM COUNTY LINE TO THE GUILFORD COUNTY LINE. INSTALL 1 MILE AND .5 MILE MARKERS AND REVISE EXIT NUMBER SIGNS. | 9.98 | RANDOLPH | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 50000
HS-2008E | Highway | Safety | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 0.5 | SCOTLAND | 8 | Lumber River RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 33000
HS-2008E | Highway | Safety | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 0.5 | SCOTLAND | 8 | Lumber River RPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 67000
HS-2008E | Highway | Safety | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 0.5 | SCOTLAND | 8 | Lumber River RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 17000
HS-2008E | Highway | Safety | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 0.5 | SCOTLAND | 8 | Lumber River RPO |  | Statewide Mobility |  | T | UTILITIES | 33000
HS-2008E | Highway | Safety | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 0.5 | SCOTLAND | 8 | Lumber River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 867000 | FY 2025: 382000; FY 2026: 485000
HS-2008E | Highway | Safety | US 74 | AT NC 144 (MORGAN STREET) / SR 1148 (SAINT JOHNS CHURCH ROAD). CONVERT TO A SIGNALIZED RCI. | 0.5 | SCOTLAND | 8 | Lumber River RPO |  | Statewide Mobility |  | T | CONSTRUCTION | 1733000 | FY 2025: 763000; FY 2026: 970000
HS-2008F | Highway | Safety | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | MOORE | 8 | Sandhills MPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 167000 | FY 2026: 167000
HS-2008F | Highway | Safety | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | MOORE | 8 | Sandhills MPO |  | Region E |  | T | RIGHT-OF-WAY | 333000 | FY 2026: 333000
HS-2008F | Highway | Safety | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | MOORE | 8 | Sandhills MPO |  | Region E |  | HSIP | UTILITIES | 83000 | FY 2027: 83000
HS-2008F | Highway | Safety | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | MOORE | 8 | Sandhills MPO |  | Region E |  | T | UTILITIES | 167000 | FY 2027: 167000
HS-2008F | Highway | Safety | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | MOORE | 8 | Sandhills MPO |  | Region E |  | HSIP | CONSTRUCTION | 826000 | FY 2028: 826000
HS-2008F | Highway | Safety | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | MOORE | 8 | Sandhills MPO |  | Region E |  | HSIP | CONSTRUCTION | 357000 | FY 2029: 357000
HS-2008F | Highway | Safety | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | MOORE | 8 | Sandhills MPO |  | Region E |  | T | CONSTRUCTION | 714000 | FY 2029: 714000
HS-2008F | Highway | Safety | NC 5 | AT SR 1205 (MORGANTON ROAD). REALIGN INTERSECTION AND ADD TURN LANES. | 0.5 | MOORE | 8 | Sandhills MPO |  | Region E |  | T | CONSTRUCTION | 1653000 | FY 2028: 1653000
HS-2009 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2009A | Highway | Safety | VARIOUS | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Area TPO |  | Division 9 |  | HSIP | CONSTRUCTION | 1900000
HS-2009B | Highway | Safety | US 64 | US 64 FROM SR 2782 (BOWERS ROAD TO EAST OF SR 2012 / SR 2227 (HEATH CHURCH ROAD / NEW BOWERS ROAD). CONSTRUCT 4 REDUCED CONFLICT INTERSECTIONS AND LEFT-OVER WITH U-TURN BULB EAST OF SR 2012 / SR 2227. | 0.61 | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | UTILITIES | 20000
HS-2009B | Highway | Safety | US 64 | US 64 FROM SR 2782 (BOWERS ROAD TO EAST OF SR 2012 / SR 2227 (HEATH CHURCH ROAD / NEW BOWERS ROAD). CONSTRUCT 4 REDUCED CONFLICT INTERSECTIONS AND LEFT-OVER WITH U-TURN BULB EAST OF SR 2012 / SR 2227. | 0.61 | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 150000
HS-2009B | Highway | Safety | US 64 | US 64 FROM SR 2782 (BOWERS ROAD TO EAST OF SR 2012 / SR 2227 (HEATH CHURCH ROAD / NEW BOWERS ROAD). CONSTRUCT 4 REDUCED CONFLICT INTERSECTIONS AND LEFT-OVER WITH U-TURN BULB EAST OF SR 2012 / SR 2227. | 0.61 | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 2536000
HS-2009C | Highway | Safety | US 29 / US 70 | US 29 / US 70, VICINITY OF FLEET DARR ROAD WEST OF SR 2123 (LEXINGTON AVENUE) CONNECTOR. INSTALL DIRECTIONAL LEFTOVERS. | 0.5 | DAVIDSON | 9 | High Point Urban Area MPO |  | Region D |  | HSIP | CONSTRUCTION | 500000 | FY 2026: 500000
HS-2009D | Highway | Safety | SR 1007 (JAKE ALEXANDER BOULEVARD) | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | HSIP | RIGHT-OF-WAY | 50000
HS-2009D | Highway | Safety | SR 1007 (JAKE ALEXANDER BOULEVARD) | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | HSIP | UTILITIES | 20000
HS-2009D | Highway | Safety | SR 1007 (JAKE ALEXANDER BOULEVARD) | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION | Division 9 |  | HSIP | CONSTRUCTION | 520000
HS-2009E | Highway | Safety | SR 1002 (OLD CONCORD ROAD) | SR 1002 (OLD CONCORD ROAD) FROM JAKE ALEXANDER BOULEVARD IN SALISBURY TO THE CABARRUS COUNTY LINE. INSTALL PAVEMENT MARKINGS. | 10.94 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | CONSTRUCTION | 396000
HS-2009F | Highway | Safety | NC 109 | NC 109. FORSYTH COUNTY FROM MILE POST 0.256 TO DAVIDSON COUNTY MILE POST 38.367. INSTALL CENTERLINE AND EDGELINE SINUSOIDAL RUMBLESTRIPES. | 0.48 | DAVIDSON, FORSYTH | 9 | High Point Urban Area MPO, Winston-Salem Area TPO | UNDER CONSTRUCTION | Region D |  | HSIP | CONSTRUCTION | 238000
HS-2009H | Highway | Safety | SR 1528 (NORTH POINT BOULEVARD) | SR 1528 (NORTH POINT BOULEVARD) AT UNIVERSITY PLAZA SHOPPING CENTER MAIN DRIVEWAY AND BP FILLING STATION DRIVEWAY, AND SR 1528 (NORTH POINT BOULEVARD) AT NORTHPOINT DRIVE NORTHCLIFFE DRIVE. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 1 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | HSIP | UTILITIES | 25000
HS-2009H | Highway | Safety | SR 1528 (NORTH POINT BOULEVARD) | SR 1528 (NORTH POINT BOULEVARD) AT UNIVERSITY PLAZA SHOPPING CENTER MAIN DRIVEWAY AND BP FILLING STATION DRIVEWAY, AND SR 1528 (NORTH POINT BOULEVARD) AT NORTHPOINT DRIVE NORTHCLIFFE DRIVE. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 1 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | HSIP | CONSTRUCTION | 995000 | FY 2025: 995000
HS-2009I | Highway | Safety | NC 152 | NC 152 AT NC 153 NEAR CHINA GROVE. INTERSECTION IMPROVEMENTS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | HSIP | RIGHT-OF-WAY | 20000
HS-2009I | Highway | Safety | NC 152 | NC 152 AT NC 153 NEAR CHINA GROVE. INTERSECTION IMPROVEMENTS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | HSIP | CONSTRUCTION | 350000
HS-2009J | Highway | Safety | VARIOUS | MULTIPLE FREEWAY AND EXPRESSWAY RAMPS. INSTALL LONG LIFE WRONG WAY PAVEMENT MARKINGS. |  | FORSYTH, DAVIDSON, DAVIE | 9 | High Point Urban Area MPO, Northwest Piedmont RPO, Winston-Salem Area TPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 525000
HS-2009K | Highway | Safety | NC 109 | NC 109 AT SR 2335 CANAAN CHURCH ROAD AND SNYDER STATION ROAD NEAR DENTON. INSTALL TURN LANES. | 0.5 | DAVIDSON | 9 | High Point Urban Area MPO |  | Region D |  | CRPLT5 | CONSTRUCTION | 496000 | FY 2025: 491000
HS-2009K | Highway | Safety | NC 109 | NC 109 AT SR 2335 CANAAN CHURCH ROAD AND SNYDER STATION ROAD NEAR DENTON. INSTALL TURN LANES. | 0.5 | DAVIDSON | 9 | High Point Urban Area MPO |  | Region D |  | T(M) | CONSTRUCTION | 124000 | FY 2025: 123000
HS-2009L | Highway | Safety | NC 62 | NC 62 (CLONINGER) DRIVE AT SR 2055 (LIBERTY DRIVE) IN THOMASVILLE. IMPROVE VERTICAL ALIGNMENT. | 0.5 | DAVIDSON | 9 | High Point Urban Area MPO |  | Region D |  | HSIP | CONSTRUCTION | 530000 | FY 2025: 530000
HS-2010 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2010A | Highway | Safety | NC 24, NC 27 | SR 3110 (ARLINGTON CHURCH ROAD) NEAR CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | HSIP | RIGHT-OF-WAY | 4000
HS-2010A | Highway | Safety | NC 24, NC 27 | SR 3110 (ARLINGTON CHURCH ROAD) NEAR CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | HSIP | CONSTRUCTION | 1900000
HS-2010B | Highway | Safety | I-277 | INSTALL SMART CUSHIONS AT VARIOUS EXITS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 144000
HS-2010C | Highway | Safety | NC 218 | US 74 IN ANSON COUNTY TO US 601 IN UNION COUNTY, AND FROM MILL GROVE ROAD IN UNION COUNTY TO I-485 IN MECKLENBURG COUNTY. INSTALL MILLED RUMBLE STRIPS. | 27.51 | UNION, ANSON, MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | HSIP | CONSTRUCTION | 616000
HS-2010D | Highway | Safety | NC 24/27 | SR 1120 (BETHEL SCHOOL ROAD) INTERSECTION. INSTALL A REDUCED CONFLICT INTERSECTION (RCI) WITH SIGNALIZED BULBOUTS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | HSIP | RIGHT-OF-WAY | 301000
HS-2010D | Highway | Safety | NC 24/27 | SR 1120 (BETHEL SCHOOL ROAD) INTERSECTION. INSTALL A REDUCED CONFLICT INTERSECTION (RCI) WITH SIGNALIZED BULBOUTS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | HSIP | CONSTRUCTION | 769000
HS-2010E | Highway | Safety | NC 49 (SOUTH TRYON STREET) | NC 49 (SOUTH TRYON STREET) AT GENERAL DRIVE; AND, NC 49 (SOUTH TRYON STREET) AT SR 1347 (NEVADA BOULEVARD). INSTALL TRAFFIC SIGNAL AT NC 49 AND GENERAL DRIVE, AND CONVERT NC 49 AT SR 1347 (NEVADA BOULEVARD) TO A DIRECTIONAL CROSSOVER. | 0.42 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | UTILITIES | 25000 | FY 2025: 25000
HS-2010E | Highway | Safety | NC 49 (SOUTH TRYON STREET) | NC 49 (SOUTH TRYON STREET) AT GENERAL DRIVE; AND, NC 49 (SOUTH TRYON STREET) AT SR 1347 (NEVADA BOULEVARD). INSTALL TRAFFIC SIGNAL AT NC 49 AND GENERAL DRIVE, AND CONVERT NC 49 AT SR 1347 (NEVADA BOULEVARD) TO A DIRECTIONAL CROSSOVER. | 0.42 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 720000 | FY 2025: 720000
HS-2010F | Highway | Safety | NC 24/27 | NC 24/27 AND SR 1100 (PINE BLUFF ROAD/ REED MINE ROAD) NEAR LOCUST. INSTALL A REDUCED CONFLICT INTERSECTION. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 5000
HS-2010F | Highway | Safety | NC 24/27 | NC 24/27 AND SR 1100 (PINE BLUFF ROAD/ REED MINE ROAD) NEAR LOCUST. INSTALL A REDUCED CONFLICT INTERSECTION. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Region E |  | HSIP | CONSTRUCTION | 1160000
HS-2010G | Highway | Safety | NC 51 | NC 51 AND POLK STREET. INSTALL PEDESTRIAN SIGNALS AND ACCOMMODATIONS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 70000 | FY 2025: 70000
HS-2010G | Highway | Safety | NC 51 | NC 51 AND POLK STREET. INSTALL PEDESTRIAN SIGNALS AND ACCOMMODATIONS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 360000 | FY 2025: 360000
HS-2010H | Highway | Safety | NC 49 | SR 1155 (ZION CHURCH ROAD) INTERSECTION NEAR CONCORD. INSTALL REDUCED CONFLICT INTERSECTION WITH SIGNALIZED BULBOUTS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 210000
HS-2010H | Highway | Safety | NC 49 | SR 1155 (ZION CHURCH ROAD) INTERSECTION NEAR CONCORD. INSTALL REDUCED CONFLICT INTERSECTION WITH SIGNALIZED BULBOUTS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 70000
HS-2010H | Highway | Safety | NC 49 | SR 1155 (ZION CHURCH ROAD) INTERSECTION NEAR CONCORD. INSTALL REDUCED CONFLICT INTERSECTION WITH SIGNALIZED BULBOUTS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1949000 | FY 2026: 1475000; FY 2027: 474000
HS-2010I | Highway | Safety | NC 16 (PROVIDENCE ROAD) | SR 1307 (BONDS GROVE CHURCH ROAD) INTERSECTION NEAR MARVIN. WIDEN ROAD, ADD TURN LANE, AND INSTALL TRAFFIC SIGNAL. | 0.5 | UNION | 10 | Charlotte Regional TPO |  | Region E
HS-2010J | Highway | Safety | NC 73 (SAM FURR ROAD) | SR 5544 (CATAWBA AVENUE) AND GLENFURNESS DRIVE INTERSECTIONS IN HUNTERSVILLE. INSTALL PEDESTRIAN ACCOMMODATIONS. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | HSIP | CONSTRUCTION | 865000
HS-2010K | Highway | Safety | NC 24/NC 27 | LEONARD AVENUE. INSTALL AUDIBLE PEDESTRIAN SIGNALS. | 0.5 | STANLY | 10 | Rocky River RPO |  | Region E |  | HSIP | CONSTRUCTION | 15000 | FY 2025: 3000
HS-2010L | Highway | Safety | SR 5901 (BILLY GRAHAM PARKWAY) | NC 49 (TRYON ROAD) TO I-85. INSTALL GUARDRAIL. | 5.1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 960000
HS-2010M | Highway | Safety | VARIOUS | I-85, I-77, I-277, I-485, AND US 74. INSTALL WRONG WAY PAVEMENT MARKINGS AND SIGNS. |  | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 783000
HS-2010N | Highway | Safety | NC 740; US 52 | MILE MARKER 0 TO MILE MARKER 12.8 IN STANLY COUNTY; MILE MARKER 4.9 TO MILE MARKER 10.5 IN ANSON COUNTY. INSTALL RUMBLE STRIPS AND LONG LIFE PAVEMENT MARKINGS. |  | STANLY, ANSON | 10 | Rocky River RPO |  | Region E |  | HSIP | CONSTRUCTION | 636000 | FY 2025: 140000
HS-2010O | Highway | Safety | NC 73 | MILE MARKER 0 TO MILE MARKER 4.3, MILE MARKER 13.1 TO MILE MARKER 18.9, MILE MARKER 20.9 TO MILE MARKER 24.0 IN CABARRUS COUNTY; MILE MARKER 0 TO MILE MARKER 8.1 IN STANLY COUNTY. INSTALL RUMBLE STRIPS AND LONG LIFE PAVEMENT MARKINGS. |  | CABARRUS, STANLY | 10 | Cabarrus-Rowan MPO, Rocky River RPO |  | Region E |  | HSIP | CONSTRUCTION | 1400000 | FY 2025: 382000
HS-2010P | Highway | Safety | NC 49; US 601; NC 3 | MILE MARKER 13.8 TO MILE MARKER 15.8; MILE MARKER 5.4 TO MILE MARKER 12.3; MILE MARKER 13.8 TO MILE MARKER 20.3. INSTALL RUMBLE STRIPS AND LONG LIFE PAVEMENT MARKINGS. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Region E |  | HSIP | CONSTRUCTION | 885000 | FY 2025: 202000
HS-2010Q | Highway | Safety | NC 49 | SR 2635 (OLD AIRPORT ROAD). INSTALL DIRECTIONAL CROSSOVER WITH U-TURN BULBOUT. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2025: 10000
HS-2010Q | Highway | Safety | NC 49 | SR 2635 (OLD AIRPORT ROAD). INSTALL DIRECTIONAL CROSSOVER WITH U-TURN BULBOUT. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 10000 | FY 2026: 10000
HS-2010Q | Highway | Safety | NC 49 | SR 2635 (OLD AIRPORT ROAD). INSTALL DIRECTIONAL CROSSOVER WITH U-TURN BULBOUT. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 750000 | FY 2027: 597000; FY 2028: 153000
HS-2010R | Highway | Safety | SR 1168 (ROBINSON CHURCH ROAD) | SR 1169 (PEACH ORCHARD ROAD) NEAR HARRISBURG. WIDEN SHOULDERS AND IMPROVE SUPERELEVATION. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 50000 | FY 2025: 50000
HS-2010R | Highway | Safety | SR 1168 (ROBINSON CHURCH ROAD) | SR 1169 (PEACH ORCHARD ROAD) NEAR HARRISBURG. WIDEN SHOULDERS AND IMPROVE SUPERELEVATION. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | UTILITIES | 25000 | FY 2027: 25000
HS-2010R | Highway | Safety | SR 1168 (ROBINSON CHURCH ROAD) | SR 1169 (PEACH ORCHARD ROAD) NEAR HARRISBURG. WIDEN SHOULDERS AND IMPROVE SUPERELEVATION. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | CONSTRUCTION | 715000 | FY 2027: 426000; FY 2028: 289000
HS-2011 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2011A | Highway | Safety | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | HSIP | CONSTRUCTION | 1816000
HS-2011B | Highway | Safety | US 221 / US 321 | DEERFIELD ROAD TO BOONE MALL. INSTALL PEDESTRIAN COUNTDOWN HEADS AND FLASHING YELLOW ARROWS AT VARIOUS INTERSECTIONS. | 0.99 | WATAUGA | 11 | High Country RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 116000
HS-2011C | Highway | Safety | SR 1511 (ROSEBORO ROAD) | INSTALL SHOULDER GUARDRAIL. | 0.05 | AVERY | 11 | High Country RPO | UNDER CONSTRUCTION. | Division 11 |  | HSIP | CONSTRUCTION | 20000
HS-2011C | Highway | Safety | SR 1511 (ROSEBORO ROAD) | INSTALL SHOULDER GUARDRAIL. | 0.05 | AVERY | 11 | High Country RPO | UNDER CONSTRUCTION. | Division 11 |  | HSIP | CONSTRUCTION | 0
HS-2011D | Highway | Safety | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | HSIP | CONSTRUCTION | 846000
HS-2011D | Highway | Safety | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. | Division 11 |  | HSIP | CONSTRUCTION | 9000
HS-2011E | Highway | Safety | NC 16 | US 221 TO THE VIRGINIA STATE LINE. INSTALL NEW AND UPGRADE EXISTING GUARDRAIL. |  | ASHE | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | HSIP | CONSTRUCTION | 1575000
HS-2011F | Highway | Safety | VARIOUS | INSTALL RUMBLE STRIPES AND LONG LIFE PAVEMENT MARKINGS. INSTALL SHOULDER GUARDRAIL NEAR SR 2329. |  | WILKES | 11 | High Country RPO |  | Division 11 |  | HSIP | CONSTRUCTION | 395000
HS-2011G | Highway | Safety | NC 89 (PINE STREET) | SR 1345 (BEULAH ROAD/ BEULAH CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HF | ENGINEERING | 100000
HS-2011G | Highway | Safety | NC 89 (PINE STREET) | SR 1345 (BEULAH ROAD/ BEULAH CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HSIP | RIGHT-OF-WAY | 300000 | FY 2025: 300000
HS-2011G | Highway | Safety | NC 89 (PINE STREET) | SR 1345 (BEULAH ROAD/ BEULAH CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HF | RIGHT-OF-WAY | 125000 | FY 2025: 125000
HS-2011G | Highway | Safety | NC 89 (PINE STREET) | SR 1345 (BEULAH ROAD/ BEULAH CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HF | UTILITIES | 25000 | FY 2025: 25000
HS-2011G | Highway | Safety | NC 89 (PINE STREET) | SR 1345 (BEULAH ROAD/ BEULAH CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HSIP | CONSTRUCTION | 500000 | FY 2026: 382000; FY 2027: 118000
HS-2011G | Highway | Safety | NC 89 (PINE STREET) | SR 1345 (BEULAH ROAD/ BEULAH CHURCH ROAD). CONSTRUCT ROUNDABOUT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | "HF" FUNDS ARE HI-IMPACT/ LOW COST FUNDS. | Region F |  | HF | CONSTRUCTION | 750000 | FY 2026: 573000; FY 2027: 177000
HS-2012 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2012A | Highway | Safety | SR 1849 (MOUNT PLEASANT ROAD) | INSTALL GUARDRAIL ON BRIDGE 163 ON SR 1849 OVER MOUNTAIN CREEK PORTION OF LAKE NORMAN | 0.05 | CATAWBA | 12 | Greater Hickory MPO | COMPLETE | Division 12 |  | HSIP | CONSTRUCTION | 85000
HS-2012B | Highway | Safety | SR 1844 (SLANTING BRIDGE ROAD) | UPGRADE GUARDRAIL AND END UNITS AT BRIDGE 23 | 0.09 | CATAWBA | 12 | Greater Hickory MPO | COMPLETE | Division 12 |  | HSIP | CONSTRUCTION | 372000
HS-2012C | Highway | Safety | SR 1125 (SHEARERS ROAD) | SR 1147 (ROCKY RIVER ROAD) INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | ENGINEERING | 20000
HS-2012C | Highway | Safety | SR 1125 (SHEARERS ROAD) | SR 1147 (ROCKY RIVER ROAD) INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | CONSTRUCTION | 205000
HS-2012D | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ON APPROXIMATELY 65 SECONDARY ROADS. |  | ALEXANDER, CATAWBA, IREDELL | 12 | Cabarrus-Rowan MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | CONSTRUCTION | 3615000
HS-2012E | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ON APPROXIMATELY 59 SECONDARY ROADS. |  | LINCOLN, CLEVELAND, GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | CONSTRUCTION | 2675000
HS-2012F | Highway | Safety | SR 1360 (BETH HAVEN CHURCH ROAD) | SR 1373 (WINGATE HILL ROAD/ FORNEY HILL ROAD). INSTALL ALL WAY STOP, UPGRADE SIGNS AND PAVEMENT MARKINGS, AND IMPROVE SHOULDERS. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. | Division 12 |  | HSIP | CONSTRUCTION | 25000
HS-2012G | Highway | Safety | NC 18 | MILE MARKER 0.0 TO MILE MARKER 6.0. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 451000
HS-2012H | Highway | Safety | NC 10 | MILE MARKER 19.8 TO MILE MARKER 27.1. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | CATAWBA | 12 | Greater Hickory MPO |  | Region F |  | HSIP | CONSTRUCTION | 467000
HS-2012I | Highway | Safety | NC 10 | MILE MARKER 11.9 TO MILE MARKER 15.0. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | CATAWBA | 12 | Greater Hickory MPO |  | Region F |  | HSIP | CONSTRUCTION | 227000
HS-2012J | Highway | Safety | NC 275 | MILE MARKER 5.1 TO MILE MARKER 9.7. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 152000
HS-2012K | Highway | Safety | NC 150 | MILE MARKER 11.4 TO MILE MARKER 11.9. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Region F |  | HSIP | CONSTRUCTION | 25000
HS-2012L | Highway | Safety | NC 18 | MILE MARKER 13.5 TO MILE MARKER 18.6. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 186000
HS-2012M | Highway | Safety | NC 10 | MILE MARKER 0.0 TO MILE MARKER 2.2 IN LINCOLN COUNTY AND MILE MARKER 0.0 TO MILE MARKER 11.0 IN CATAWBA COUNTY. INSTALL CENTERLINE AND SHOULDER RUMBLE STRIPS. |  | CATAWBA, LINCOLN | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F |  | HSIP | CONSTRUCTION | 525000
HS-2013 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2013A | Highway | Safety | US 321 | BRIDGES #366 AND #367 AT THE CATAWBA COUNTY LINE. INSTALL GUARDRAIL. | 0.19 | BURKE | 13 | Greater Hickory MPO | COMPLETE | Statewide Mobility |  | HSIP | CONSTRUCTION | 92000
HS-2013B | Highway | Safety | NC 226 | US 19E TO SR 1250 (SNOW CREEK ROAD). UPGRADE GUARDRAIL. | 6.04 | MITCHELL | 13 | High Country RPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 290000
HS-2013C | Highway | Safety | NC 181 | US 64 TO SR 1405 (BROWN MOUNTAIN BEACH ROAD). UPGRADE GUARDRAIL. | 11.35 | BURKE | 13 | Greater Hickory MPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 195000
HS-2013D | Highway | Safety | NC 226 | SR 1250 (SNOW CREEK ROAD) TO NC 261. UPGRADE GUARDRAIL. | 3.36 | MITCHELL | 13 | High Country RPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 272000
HS-2013E | Highway | Safety | US 64/NC 18 | NC 181 TO CALDWELL COUNTY LINE. UPGRADE GUARDRAIL. | 7.49 | BURKE | 13 | Greater Hickory MPO | COMPLETE | Region G |  | HSIP | CONSTRUCTION | 385000
HS-2013F | Highway | Safety | US 321, US 70, US 19E, US 221A | UPGRADE GUARDRAIL. |  | BURKE, MITCHELL, RUTHERFORD | 13 | Greater Hickory MPO, Foothills RPO, High Country RPO | COMPLETE | Statewide Mobility |  | HSIP | CONSTRUCTION | 348000
HS-2013G | Highway | Safety | SR 1510 (HUDLOW ROAD) | US 221A TO NC 64. UPGRADE GUARDRAIL. | 5.39 | RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. | Division 13 |  | HSIP | CONSTRUCTION | 497000
HS-2013H | Highway | Safety | US 221 | NC 226/ US 221 BUS TO US 70. IMPROVE PAVEMENT. | 2.49 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 530000
HS-2013I | Highway | Safety | SR 1318 (BIG LAUREL ROAD) | SR 1340 TO SR 1636 NEAR MARS HILL. INSTALL GUARDRAIL. | 8.59 | MADISON | 13 | Land-of-Sky RPO |  | Division 13 |  | HSIP | CONSTRUCTION | 507000
HS-2013J | Highway | Safety | US 19W | SR 1454 TO SR 1382 NEAR BURNSVILLE. INSTALL GUARDRAIL. | 5.07 | YANCEY | 13 | High Country RPO |  | Region G |  | HSIP | CONSTRUCTION | 731000 | FY 2025: 168000
HS-2013K | Highway | Safety | SR 1003 (REEMS CREEK ROAD) | SR 2106 TO SR 2114 NEAR WEAVERVILLE. INSTALL GUARDRAIL. | 3.61 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 274000
HS-2013L | Highway | Safety | NC 226 | US 19E TO NC 261 NEAR SPRUCE PINE. INSTALL GUARDRAIL. | 9.4 | MITCHELL | 13 | High Country RPO |  | Region G |  | HSIP | CONSTRUCTION | 590000
HS-2013M | Highway | Safety | SR 1135 (OLD FORT/ SUGARHILL ROAD) | SR 1103 TO SR 1001 NEAR OLD FORT. INSTALL GUARDRAIL. | 8.95 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | HSIP | CONSTRUCTION | 890000
HS-2013N | Highway | Safety | SR 1006 (BOSTIC-SUNSHINE HIGHWAY) | SR 1007 TO NC 226 NEAR BOSTIC. INSTALL GUARDRAIL. | 9.78 | RUTHERFORD | 13 | Foothills RPO |  | Division 13 |  | HSIP | CONSTRUCTION | 875000
HS-2013O | Highway | Safety | SR 3075 (ONTEORA BOULEVARD) | BRIDGE #100460 OVER I-40. CONSTRUCT SIDEWALK AND UPGRADE BRIDGE RAIL. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 395000 | FY 2025: 395000
HS-2013P | Highway | Safety | NC 63 | SR 1220 (SOUTH TURKEY CREEK ROAD) NEAR LEICESTER. CONSTRUCT TURN LANE. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2025: 5000
HS-2013P | Highway | Safety | NC 63 | SR 1220 (SOUTH TURKEY CREEK ROAD) NEAR LEICESTER. CONSTRUCT TURN LANE. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 715000 | FY 2026: 310000; FY 2027: 405000
HS-2013Q | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ON VARIOUS PRIMARY AND SECONDARY TWO LANE ROADWAYS AND FOUR LANE ROADWAYS. |  | BUNCOMBE, McDOWELL, YANCEY, MADISON, BURKE, RUTHERFORD, MITCHELL | 13 | French Broad River MPO, Foothills RPO, High Country RPO, Land-of-Sky RPO, Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 3337000 | FY 2025: 767000; FY 2026: 2027000; FY 2027: 543000
HS-2013R | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ON VARIOUS PRIMARY AND SECONDARY TWO LANE ROADWAYS. |  | BURKE, MADISON, RUTHERFORD, McDOWELL | 13 | Foothills RPO, Greater Hickory MPO, Land-of-Sky RPO, French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 2966000 | FY 2025: 1914000; FY 2026: 322000
HS-2014 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2014A | Highway | Safety | US 64/NC 28 | INSTALL CENTERLINE RUMBLESTRIPS, LONG LIFE PAVEMENT MARKINGS, AND INTERMITTMENT PAVED SHOULDERS FROM SR 1560 TO SR 1533, NEAR FRANKLIN. | 5.76 | MACON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 1200000
HS-2014AA | Highway | Safety | US 64 | SR 1147 (OAK FOREST ROAD) NEAR HAYESVILLE. EXTEND TWO-WAY LEFT TURN LANE. | 0.5 | CLAY | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 51000 | FY 2025: 18000
HS-2014AB | Highway | Safety | NC 108 (MILLS STREET) | SR 1534 (PEAK STREET). INSTALL PEDESTRIAN SIGNALS AND UPGRADE CURB RAMP. | 0.5 | POLK | 14 | Foothills RPO |  | Region G |  | HSIP | CONSTRUCTION | 168000 | FY 2025: 84000
HS-2014AC | Highway | Safety | US 276 (GREENVILLE HIGHWAY) | SR 1118 (GALLIMORE ROAD). INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Region G |  | HSIP | CONSTRUCTION | 200000
HS-2014AD | Highway | Safety | SR 1356 (SAVANNAH DRIVE) | US 23 BUSINESS TO NICOL ARMS ROAD. CONSTRUCT SIDEWALK. | 0.12 | JACKSON | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 110000 | FY 2025: 110000
HS-2014B | Highway | Safety | SR 1157 (CULLOWHEE MOUNTAIN ROAD) | INSTALL GUARDRAIL FROM MILEPOST 2.6 TO 6.6, NEAR CULLOWHEE. | 4.02 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | HSIP | CONSTRUCTION | 110000
HS-2014C | Highway | Safety | VARIOUS | INSTALL SNOWPLOWABLE MARKERS AND PAVEMENT MARKINGS FOR WRONG WAY RAMP ARROWS ON VARIOUS FREEWAY RAMPS. | 0.5 | HAYWOOD, HENDERSON, MACON, POLK, SWAIN | 14 | Southwestern RPO, Foothills RPO, French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 50000
HS-2014D | Highway | Safety | SR 1325 (CENTENNIAL DRIVE) | INSTALL RECTANGULAR RAPID FLASHING BEACONS (RRFB) AT THREE MIDBLOCK CROSSINGS NEAR SR 1169 (CENTRAL DRIVE). | 0.5 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | HSIP | CONSTRUCTION | 59000
HS-2014E | Highway | Safety | US 74 | IMPROVE PAVEMENT FROM SR 1392 TO EAST OF SR 1388 AND FROM JACKSON COUNTY LINE TO BRIDGES 107 AND 110. | 9.77 | HAYWOOD, JACKSON | 14 | French Broad River MPO, Southwestern RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | HSIP | CONSTRUCTION | 975000
HS-2014F | Highway | Safety | SR 1100 (OLD HIGHWAY 64 WEST) | SR 1135 (SETTAWIG ROAD) NEAR BRASSTOWN. INSTALL GUARDRAIL ON CULVERT. | 0.5 | CLAY | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | HSIP | CONSTRUCTION | 45000
HS-2014G | Highway | Safety | NC 143 | LONG HUNGRY ROAD INTERSECTION. IMPROVE SUPERELEVATION. | 0.5 | GRAHAM | 14 | Southwestern RPO |  | Region G |  | HSIP | RIGHT-OF-WAY | 2000
HS-2014G | Highway | Safety | NC 143 | LONG HUNGRY ROAD INTERSECTION. IMPROVE SUPERELEVATION. | 0.5 | GRAHAM | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 515000 | FY 2025: 5000; FY 2026: 510000
HS-2014H | Highway | Safety | VARIOUS | US 23 BUSINESS (HAYWOOD ROAD) AT CHURCH STREET AND SR 1557 (FRONT STREET) AT SR 1558 (DEPOT STREET). INSTALL RECTANGULAR RAPID FLASHING BEACON (RRFB) AND UPGRADE CURB RAMPS. | 0.5 | JACKSON | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 96000
HS-2014I | Highway | Safety | US 25 BUSINESS (ASHEVILLE HIGHWAY) | HENDERSONVILLE CITY LIMIT TO SR 1534. INSTALL RUMBLE STRIPS WITH LONG LIFE PAVEMENT MARKINGS. | 4.3 | HENDERSON | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 349000
HS-2014J | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS SECONDARY ROUTES. |  | HAYWOOD, POLK | 14 | French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | Division 14 |  | HSIP | CONSTRUCTION | 2570000 | FY 2025: 437000
HS-2014K | Highway | Safety | US 19 | HOLSTON VILLAGE ROAD AND SR 1197 (GOLF COURSE ROAD). UPGRADE INTERSECTIONS. | 0.5 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 110000 | FY 2025: 110000
HS-2014L | Highway | Safety | US 64 | SR 1574 (FRUITLAND ROAD), SR 1006 (HOWARD GAP ROAD), SR 1519 (THOMPSON STREET)/ SR 1751 (FREEMAN STREET), SR 1749 (ORR'S CAMP ROAD)/ SR 1634 (CAROLINA AVENUE). UPGRADE INTERSECTIONS. | 0.5 | HENDERSON | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 570000
HS-2014M | Highway | Safety | US 64 (ASHEVILLE HIGHWAY) | SR 1592 (HOSPITAL DRIVE)/ STRAUS PARKWAY. UPGRADE INTERSECTION. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO, French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 225000 | FY 2025: 114000
HS-2014O | Highway | Safety | US 64 | SR 1586 (SOUTH MILLS GAP ROAD)/ TUTTLE ROAD. INSTALL TRAFFIC SIGNAL. | 0.5 | HENDERSON | 14 | French Broad River MPO |  | Region G |  | HSIP | RIGHT-OF-WAY | 20000
HS-2014O | Highway | Safety | US 64 | SR 1586 (SOUTH MILLS GAP ROAD)/ TUTTLE ROAD. INSTALL TRAFFIC SIGNAL. | 0.5 | HENDERSON | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 75000
HS-2014P | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS PRIMARY AND SECONDARY ROUTES. |  | MACON, CHEROKEE, JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 2955000 | FY 2025: 1696000
HS-2014Q | Highway | Safety | US 64, US 25 BUSINESS | UPGRADE SIGNAL SYSTEM AT 33 INTERSECTIONS ALONG US 64 AND US 25 BUSINESS. |  | HENDERSON | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 225000
HS-2014R | Highway | Safety | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS ALONG VARIOUS PRIMARY AND SECONDARY ROUTES. |  | HAYWOOD, HENDERSON, JACKSON, POLK, TRANSYLVANIA | 14 | Foothills RPO, French Broad River MPO, Land-of-Sky RPO, Southwestern RPO | UNDER CONSTRUCTION. | Region G |  | HSIP | CONSTRUCTION | 1225000
HS-2014S | Highway | Safety | US 19 | JACKSON COUNTY TO MAGGIE VALLEY. INSTALL LONG LIFE PAVEMENT MARKINGS. | 3.5 | HAYWOOD | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 263000
HS-2014T | Highway | Safety | US 19 | SR 1336 TO JACKSON COUNTY. INSTALL RUMBLE STRIPES AND LONG LIFE PAVEMENT MARKINGS. | 5.15 | SWAIN | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 364000
HS-2014U | Highway | Safety | US 19 | CHEROKEE COUNTY TO SWAIN COUNTY. INSTALL RUMBLE STRIPES AND LONG LIFE PAVEMENT MARKINGS. | 2.61 | MACON | 14 | Southwestern RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 175000
HS-2014V | Highway | Safety | SR 1564 (BRASSTOWN ROAD) | JOHN C. CAMPBELL FOLK SCHOOL. INSTALL FOUR RECTANGULAR RAPID FLASHING BEACONS AND CONSTRUCT CONCRETE LANDING PADS. | 0.49 | CHEROKEE | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 61000
HS-2014W | Highway | Safety | US 64 (MURPHY ROAD) | SR 1146 (PATTON ROAD); SR 1442 (OLD MURPHY ROAD) NEAR FRANKLIN. CONSTRUCT DIRECTIONAL LEFTOVER WITH U-TURN BULBOUTS. |  | MACON | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 955000 | FY 2025: 955000
HS-2014X | Highway | Safety | US 64/US 74 | NC 60 NEAR MURPHY. CONSTRUCT DIRECTIONAL LEFTOVER WITH U-TURN BULBOUTS. | 0.5 | CHEROKEE | 14 | Southwestern RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 525000 | FY 2025: 520000
HS-2014Y | Highway | Safety | US 19 (DELLWOOD ROAD) | NORTH LAKESHORE DRIVE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | HAYWOOD | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 210000 | FY 2025: 210000
HS-2014Z | Highway | Safety | SR 1337 (WEST DEEP CREEK ROAD) | SR 1338. INSTALL PEDESTRIAN ACCOMMODATIONS. | 0.5 | SWAIN | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 71000 | FY 2025: 71000
HS-2015 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HS-2015DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | VRU | ENGINEERING | 14205000 | FY 2025: 2100000; FY 2026: 2100000; FY 2027: 2100000; FY 2028: 2100000; FY 2029: 2100000
HS-2015REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | VRU | ENGINEERING | 14205000 | FY 2025: 2100000; FY 2026: 2100000; FY 2027: 2100000; FY 2028: 2100000; FY 2029: 2100000
HS-2015SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | VRU | ENGINEERING | 18940000 | FY 2025: 2800000; FY 2026: 2800000; FY 2027: 2800000; FY 2028: 2800000; FY 2029: 2800000
HS-2016 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO
HS-2016DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Division 1 |  | VRU | CONSTRUCTION | 300000
HS-2016REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A |  | VRU | CONSTRUCTION | 300000
HS-2016SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2017 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO
HS-2017DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Division 2 |  | VRU | CONSTRUCTION | 300000
HS-2017REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Region B |  | VRU | CONSTRUCTION | 300000
HS-2017SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2018 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 3 EXCEPT IN GRAND STRAND MPO. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO
HS-2018DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM EXCLUDING GRAND STRAND MPO. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO |  | Division 3 |  | VRU | CONSTRUCTION | 300000
HS-2018REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM EXCLUDING GRAND STRAND MPO. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO |  | Region B |  | VRU | CONSTRUCTION | 300000
HS-2018SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM EXCLUDING GRAND STRAND MPO. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2019 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO
HS-2019DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Division 4 |  | VRU | CONSTRUCTION | 300000
HS-2019REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Region A |  | VRU | CONSTRUCTION | 300000
HS-2019SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2020 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO
HS-2020DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | VRU | CONSTRUCTION | 300000
HS-2020REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Region C |  | VRU | CONSTRUCTION | 300000
HS-2020SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2021 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO
HS-2021DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Division 6 |  | VRU | CONSTRUCTION | 300000
HS-2021REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Region C |  | VRU | CONSTRUCTION | 300000
HS-2021SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2022 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO
HS-2022DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Division 7 |  | VRU | CONSTRUCTION | 300000
HS-2022REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Region D |  | VRU | CONSTRUCTION | 300000
HS-2022SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2023 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO
HS-2023DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO |  | Division 8 |  | VRU | CONSTRUCTION | 300000
HS-2023REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO |  | Region E |  | VRU | CONSTRUCTION | 300000
HS-2023SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2024 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO
HS-2024DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Division 9 |  | VRU | CONSTRUCTION | 300000
HS-2024REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Region D |  | VRU | CONSTRUCTION | 300000
HS-2024SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2025 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO
HS-2025DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Division 10 |  | VRU | CONSTRUCTION | 300000
HS-2025REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Region E |  | VRU | CONSTRUCTION | 300000
HS-2025SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2026 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO
HS-2026DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO |  | Division 11 |  | VRU | CONSTRUCTION | 300000
HS-2026REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO |  | Region F |  | VRU | CONSTRUCTION | 300000
HS-2026SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2027 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO
HS-2027DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO |  | Division 12 |  | VRU | CONSTRUCTION | 300000
HS-2027REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO |  | Region F |  | VRU | CONSTRUCTION | 300000
HS-2027SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2028 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO
HS-2028DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO |  | Division 13 |  | VRU | CONSTRUCTION | 300000
HS-2028REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO |  | Region G |  | VRU | CONSTRUCTION | 300000
HS-2028SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2029 | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO
HS-2029DIV | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO |  | Division 14 |  | VRU | CONSTRUCTION | 300000
HS-2029REG | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO |  | Region G |  | VRU | CONSTRUCTION | 300000
HS-2029SW | Highway | Safety | VARIOUS | VULNERABLE ROAD USER PEDESTRIAN / BICYCLE IMPROVEMENT PROGRAM. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO |  | Statewide Mobility |  | VRU | CONSTRUCTION | 400000
HS-2401 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2401A | Highway | Safety | US 17 | US 17 BUSINESS / NC 343 INTERSECTION. MODIFY THE MEDIAN OPENING AND INSTALL TRAFFIC SIGNAL. | 0.5 | CAMDEN | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 1086000 | FY 2025: 1086000
HS-2401B | Highway | Safety | VARIOUS | PRIMARY ROUTES IN DIVISION 1. UPGRADE GUARDRAIL END UNITS. |  | HERTFORD, CURRITUCK, MARTIN, DARE, GATES, BERTIE, NORTHAMPTON, CAMDEN | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A |  | HSIP | CONSTRUCTION | 491000 | FY 2025: 491000
HS-2401C | Highway | Safety | US 64; US 17 BYPASS; US 17; NC 11; US 13 | INSTALL WRONG WAY PAVEMENT MARKINGS, MARKERS, AND SIGNS AT RAMPS. |  | WASHINGTON, MARTIN, PASQUOTANK, CHOWAN, TYRRELL, BERTIE, HERTFORD | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO |  | Region A |  | HSIP | CONSTRUCTION | 170000 | FY 2025: 170000
HS-2401D | Highway | Safety | NC 11 | SR 1212 (SHORT CUT ROAD) TO US 158. INSTALL RUMBLE STRIPS AND PAVEMENT MARKERS. |  | HERTFORD | 1 | Peanut Belt RPO |  | Region A |  | HSIP | CONSTRUCTION | 300000 | FY 2025: 300000
HS-2401E | Highway | Safety | NC 186 | GARYSBURG TO THE VIRGINIA STATE LINE, EXCLUDING THE SEABOARD TOWN LIMITS. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | NORTHAMPTON | 1 | Peanut Belt RPO |  | Region A |  | HSIP | CONSTRUCTION | 500000 | FY 2025: 500000
HS-2401F | Highway | Safety | US 17 BUSINESS (EHRINGHAUS STREET) | NC 344 (HALSTEAD BOULEVARD) INTERSECTION IN ELIZABETH CITY. INSTALL AUDIBLE PEDESTRIAN SIGNALS. |  | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 12000 | FY 2025: 12000
HS-2401G | Highway | Safety | US 17 | CHOWAN COUNTY LINE TO SR 1101 (BEAR SWAMP ROAD). INSTALL RUMBLE STRIPS. | 4 | PERQUIMANS | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 160000 | FY 2025: 160000
HS-2401H | Highway | Safety | US 17 BUSINESS | SR 1001 (BEAR GRASS ROAD) AND US 13 / US 64 EASTBOUND RAMP INTERSECTIONS IN WILLIAMSTON. CONSTRUCT REDUCED CONFLICT INTERSECTION. |  | MARTIN | 1 | Mid-East RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 100000 | FY 2026: 100000
HS-2401H | Highway | Safety | US 17 BUSINESS | SR 1001 (BEAR GRASS ROAD) AND US 13 / US 64 EASTBOUND RAMP INTERSECTIONS IN WILLIAMSTON. CONSTRUCT REDUCED CONFLICT INTERSECTION. |  | MARTIN | 1 | Mid-East RPO |  | Region A |  | HSIP | UTILITIES | 30000 | FY 2026: 30000
HS-2401H | Highway | Safety | US 17 BUSINESS | SR 1001 (BEAR GRASS ROAD) AND US 13 / US 64 EASTBOUND RAMP INTERSECTIONS IN WILLIAMSTON. CONSTRUCT REDUCED CONFLICT INTERSECTION. |  | MARTIN | 1 | Mid-East RPO |  | Region A |  | HSIP | CONSTRUCTION | 1050000 | FY 2027: 1050000
HS-2401I | Highway | Safety | US 158 | SR 1206 (THE WOODS ROAD) / DOGWOOD TRAIL INTERSECTION IN KITTY HAWK. INSTALL CURB, GUTTER, RAMPS AND CROSSWALKS. |  | DARE | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 113000 | FY 2025: 113000
HS-2401J | Highway | Safety | US 158 | SR 1186 (WALNUT ISLAND BOULEVARD) TO SR 1131 (POPLAR BRANCH ROAD) IN GRANDY. INSTALL PEDESTRIAN SIGNAL HEADS, CROSSWALKS, AND SIDEWALKS. | 0.25 | CURRITUCK | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 185000 | FY 2025: 185000
HS-2401K | Highway | Safety | US 158 | NC 168 TO WRIGHT BROTHERS MEMORIAL BRIDGE, AND US 158 TO NORTH OF LARK DRIVE. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 40 | CURRITUCK | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 635000 | FY 2025: 635000
HS-2401L | Highway | Safety | NC 12 (VIRGINIA DARE TRAIL) | NEPTUNE DRIVE INTERSECTION IN KILL DEVIL HILLS. REMOVE EXISTING CROSSWALK, INSTALL NEW CROSSWALK WITH PEDESTRIAN HEADS, AND REVISE SIGNAL. |  | DARE | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 100000 | FY 2025: 100000
HS-2401M | Highway | Safety | NC 344 | TANGLEWOOD PARKWAY TO MOUNT EVEREST DRIVE IN ELIZABETH CITY. REMOVE PORTION OF MEDIAN ISLAND AND INSTALL PEDESTRIAN ACCOMMODATIONS. | 0.36 | PASQUOTANK | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 90000 | FY 2025: 90000
HS-2401N | Highway | Safety | NC 168 | SR 1229 (BAXTER LANE) INTERSECTION AND CURRITUCK SAND COMPANY ACCESS NORTH OF MOYOCK. INSTALL TRAFFIC SIGNAL. |  | CURRITUCK | 1 | Albemarle RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 325000 | FY 2025: 325000
HS-2401O | Highway | Safety | NC 34 | US 158 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 9 | CURRITUCK, CAMDEN | 1 | Albemarle RPO |  | Region A |  | HSIP | CONSTRUCTION | 290000 | FY 2025: 290000
HS-2401P | Highway | Safety | US 158 / 258 | AT SR 1157 (POWELL ROAD) NEAR MURFREESBORO. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. |  | HERTFORD | 1 | Peanut Belt RPO | HF FUNDS REPRESENT HIGH IMPACT-LOW COST DIVISION FUNDS. | Region A |  | HSIP | CONSTRUCTION | 1400000 | FY 2026: 1400000
HS-2401P | Highway | Safety | US 158 / 258 | AT SR 1157 (POWELL ROAD) NEAR MURFREESBORO. UPGRADE ROADWAY TO REDUCED CONFLICT INTERSECTION. |  | HERTFORD | 1 | Peanut Belt RPO | HF FUNDS REPRESENT HIGH IMPACT-LOW COST DIVISION FUNDS. | Region A |  | HF | CONSTRUCTION | 500000 | FY 2026: 500000
HS-2401Q | Highway | Safety | US 64; US 158; NC 32 | VARIOUS LOCATIONS. INSTALL RUMBLE STRIPES AND SNOW PLOWABLE PAVEMENT MARKERS. |  | NORTHAMPTON, CHOWAN, GATES, TYRRELL | 1 | Albemarle RPO, Peanut Belt RPO |  | Region A |  | HSIP | CONSTRUCTION | 1950000 | FY 2025: 1950000
HS-2402 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2402A | Highway | Safety | US 258 BUSINESS | COOPERATIVE WAY / SHARON LANE INTERSECTION IN FARMVILLE. INSTALL ALL WAY STOP. |  | PITT | 2 | Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 125000
HS-2402B | Highway | Safety | US 17 | 1.1 MILES NORTH OF ONSLOW COUNTY LINE TO 2000 FEET SOUTH OF NC 58 IN JONES COUNTY; 0.25 MILES NORTH OF SR 1433 (ANTIOCH ROAD) TO 0.3 MILES NORTH OF SR 1134 (OLD NEW BERN ROAD) IN BEAUFORT COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 26.5 | CRAVEN, JONES, BEAUFORT | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 655000 | FY 2025: 655000
HS-2402C | Highway | Safety | NC 33 | SR 1240 (MAYO ROAD) TO 1625 FEET WEST OF SR 1002 (BAY CITY ROAD) IN BEAUFORT COUNTY; 600 FEET WEST OF SR 1965 (MAIN STREET EXTENSION) TO 700 FEET EAST OF SR 1136 (GRAY ROAD) IN CHOCOWINITY; 525 FEET WEST OF SR 1143 (TAYLOR ROAD) TO 300 FEET EAST OF SR 1568 (CALVERT STREET) IN PITT COUNTY; FRANK EVANS LANE TO SR 2405 (RIVERCREST DRIVE) IN PITT COUNTY; US 264 INTERCHANGE IN GREENVILLE TO NC 42 IN EDGECOMBE COUNTY. INSTALL RUMBLE STRIPS. | 56 | BEAUFORT, PITT, EDGECOMBE, PAMLICO | 2, 4 | Mid-East RPO, Greenville Urban Area MPO, Upper Coastal Plain RPO |  | Region A, B |  | HSIP | CONSTRUCTION | 1400000 | FY 2025: 1400000
HS-2402D | Highway | Safety | SR 1598 (10TH STREET) | ANDERSON STREET INTERSECTION IN GREENVILLE. INSTALL A PEDESTRIAN HYBRID BEACON. |  | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | HSIP | CONSTRUCTION | 175000 | FY 2025: 175000
HS-2402E | Highway | Safety | NC 58 | LOON DRIVE / EMERALD PLANTATION ROAD; MANGROVE DRIVE; BOGUE INLET DRIVE INTERSECTIONS IN EMERALD ISLE. IMPLEMENT A LEADING PEDESTRIAN INTERVAL AT THE SIGNALIZED INTERSECTIONS. |  | CARTERET | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 9000 | FY 2025: 9000
HS-2402F | Highway | Safety | NC 43 | SR 2241 (IVY ROAD) AND SR 1753 (STOKESTOWN - ST. JOHN ROAD) INTERSECTIONS SOUTH OF GREENVILLE. INSTALL TRAFFIC SIGNALS AT BOTH INTERSECTIONS AND CONSTRUCT LEFT TURN LANES ON SR 2241 (IVY ROAD). |  | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 100000 | FY 2025: 100000
HS-2402F | Highway | Safety | NC 43 | SR 2241 (IVY ROAD) AND SR 1753 (STOKESTOWN - ST. JOHN ROAD) INTERSECTIONS SOUTH OF GREENVILLE. INSTALL TRAFFIC SIGNALS AT BOTH INTERSECTIONS AND CONSTRUCT LEFT TURN LANES ON SR 2241 (IVY ROAD). |  | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | UTILITIES | 500000 | FY 2025: 500000
HS-2402F | Highway | Safety | NC 43 | SR 2241 (IVY ROAD) AND SR 1753 (STOKESTOWN - ST. JOHN ROAD) INTERSECTIONS SOUTH OF GREENVILLE. INSTALL TRAFFIC SIGNALS AT BOTH INTERSECTIONS AND CONSTRUCT LEFT TURN LANES ON SR 2241 (IVY ROAD). |  | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 736000 | FY 2026: 736000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (SPEIGHT SPEED FARM ROAD) / SR 1207 (NASH JOYNER ROAD) INTERSECTION IN GREENVILLE. CONSTRUCT REDUCED CONFLICT INTERSECTION WITH RIGHT TURN LANES. |  | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 150000 | FY 2025: 150000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (SPEIGHT SPEED FARM ROAD) / SR 1207 (NASH JOYNER ROAD) INTERSECTION IN GREENVILLE. CONSTRUCT REDUCED CONFLICT INTERSECTION WITH RIGHT TURN LANES. |  | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | UTILITIES | 300000 | FY 2025: 300000
HS-2402G | Highway | Safety | US 13 / US 264 | SR 1124 (SPEIGHT SPEED FARM ROAD) / SR 1207 (NASH JOYNER ROAD) INTERSECTION IN GREENVILLE. CONSTRUCT REDUCED CONFLICT INTERSECTION WITH RIGHT TURN LANES. |  | PITT | 2 | Greenville Urban Area MPO, Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 950000 | FY 2026: 950000
HS-2402H | Highway | Safety | NC 102 (THIRD STREET) ; SR 1149 (LEE STREET) | SR 1149 (LEE STREET) INTERSECTION IN AYDEN ; SECOND STREET INTERSECTION IN AYDEN. UPGRADE TRAFFIC SIGNALS AND INSTALL / UPGRADE PEDESTRIAN SIGNALS AND OTHER ACCOMMODATIONS. |  | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 72000 | FY 2025: 72000
HS-2402I | Highway | Safety | SR 1124 (NINE MILE ROAD) ; SR 1756 (LAKE ROAD) | NC 24 TO PARKER COURT IN NEWPORT; SR 1124 (NINE MILE ROAD / NINE FOOT ROAD) IN CARTERET COUNTY TO SR 1745 (MILLER BOULEVARD) IN CRAVEN COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 13.5 | CARTERET, CRAVEN | 2 | Down East RPO |  | Division 2 |  | HSIP | CONSTRUCTION | 325000 | FY 2025: 325000
HS-2402J | Highway | Safety | SR 1395 (VERNON AVENUE) | GREENBRIAR ROAD INTERSECTION IN KINSTON. INSTALL / UPGRADE PEDESTRIAN SIGNALS AND OTHER PEDESTRIAN ACCOMMODATIONS. |  | LENOIR | 2 | Eastern Carolina RPO |  | Division 2 |  | HSIP | RIGHT-OF-WAY | 8000 | FY 2025: 8000
HS-2402J | Highway | Safety | SR 1395 (VERNON AVENUE) | GREENBRIAR ROAD INTERSECTION IN KINSTON. INSTALL / UPGRADE PEDESTRIAN SIGNALS AND OTHER PEDESTRIAN ACCOMMODATIONS. |  | LENOIR | 2 | Eastern Carolina RPO |  | Division 2 |  | HSIP | CONSTRUCTION | 113000 | FY 2025: 113000
HS-2402K | Highway | Safety | US 17 BUSINESS (CAROLINA AVENUE) | WASHINGTON STREET INTERSECTION IN WASHINGTON. INSTALL CHANNELIZATION, PEDESTRIAN SIGNALS, AND OTHER ACCOMMODATIONS. |  | BEAUFORT | 2 | Mid-East RPO |  | Region B |  | HSIP | CONSTRUCTION | 97000 | FY 2025: 97000
HS-2402L | Highway | Safety | NC 101 | SR 1212 (AIRPORT ROAD) NEAR BEAUFORT TO OUTER BANKS DRIVE NEAR HAVELOCK. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 19.3 | CARTERET, CRAVEN | 2 | Down East RPO |  | Region B |  | HSIP | CONSTRUCTION | 350000 | FY 2025: 350000
HS-2402M | Highway | Safety | VARIOUS | PRIMARY ROUTES THROUGHOUT DIVISION 2. REPLACE GUARDRAIL END UNITS. |  | CARTERET, CRAVEN, BEAUFORT, LENOIR | 2 | Down East RPO, Mid-East RPO, New Bern Area MPO, Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 504000 | FY 2025: 504000
HS-2402N | Highway | Safety | SR 1598 (10TH STREET) | 5TH STREET INTERSECTION IN GREENVILLE. INSTALL / UPGRADE TRAFFIC SIGNALS, PAVEMENT MARKINGS, PEDESTRIAN SIGNALS, AND OTHER ACCOMMODATIONS. |  | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | HSIP | RIGHT-OF-WAY | 3000 | FY 2025: 3000
HS-2402N | Highway | Safety | SR 1598 (10TH STREET) | 5TH STREET INTERSECTION IN GREENVILLE. INSTALL / UPGRADE TRAFFIC SIGNALS, PAVEMENT MARKINGS, PEDESTRIAN SIGNALS, AND OTHER ACCOMMODATIONS. |  | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | HSIP | CONSTRUCTION | 253000 | FY 2025: 253000
HS-2402O | Highway | Safety | NC 43 | US 264 INTERCHANGE RAMPS. CONSTRUCT ROUNDABOUTS. |  | PITT | 2 |  |  | Region B |  | HSIP | UTILITIES | 200000 | FY 2025: 200000
HS-2402O | Highway | Safety | NC 43 | US 264 INTERCHANGE RAMPS. CONSTRUCT ROUNDABOUTS. |  | PITT | 2 |  |  | Region B |  | HSIP | CONSTRUCTION | 388000 | FY 2025: 388000
HS-2402P | Highway | Safety | NC 101 | SR 1392 (ADAMS CREEK ROAD) INTERSECTION. IMPROVE INTERSECTION WITH CHANNELIZATION AND SUPPLEMENTAL STOP SIGN INSTALLATION. |  | CARTERET | 2 |  |  | Region B |  | HSIP | CONSTRUCTION | 49000 | FY 2025: 49000
HS-2402Q | Highway | Safety | NC 11/43/903 (MEMORIAL DRIVE) | ARLINGTON BOULEVARD INTERSECTION. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND SIDEWALK. |  | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 6000 | FY 2025: 6000
HS-2402Q | Highway | Safety | NC 11/43/903 (MEMORIAL DRIVE) | ARLINGTON BOULEVARD INTERSECTION. REVISE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND SIDEWALK. |  | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 142000 | FY 2025: 142000
HS-2402R | Highway | Safety | US 258 (WESLEY CHURCH ROAD) | US 264 TO I-587 EASTBOUND RAMPS. INSTALL RUMBLE STRIPES. |  | PITT | 2 | Greenville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 80000 | FY 2025: 80000
HS-2402S | Highway | Safety | NC 58 | NORTHWEST OF SR 1109 (PELETIER LOOP ROAD) SOUTHERN INTERSECTION IN CARTERET COUNTY TO SOUTHEASTERN MUNICIPAL LIMIT OF MAYSVILLE IN JONES COUNTY; EAST OF SR 1338 (GOSHEN LANE) TO SOUTHERN MUNICIPAL LIMIT OF TRENTON IN JONES COUNTY; EAST OF SR 1124 (GREENTOWN ROAD) IN JONES COUNTY TO SR 1900 (COLLIER LOFTIN ROAD) IN LENOIR COUNTY. INSTALL RUMBLE STRIPES. |  | JONES, LENOIR, CARTERET | 2 |  |  | Region B |  | HSIP | CONSTRUCTION | 1115000 | FY 2025: 1115000
HS-2402T | Highway | Safety | US 70 | SR 1429 (OLGA ROAD) TO NC 12; NC 12 FROM US 70 TO SR 1388 (LOLA ROAD). INSTALL RUMBLE STRIPES. |  | CARTERET | 2 |  |  | Region B |  | HSIP | CONSTRUCTION | 675000 | FY 2025: 675000
HS-2402U | Highway | Safety | NC 903 | LAGRANGE TOWN LIMITS IN LENOIR COUNTY TO SR 1104 (HULL ROAD) IN GREENE COUNTY;US 13/258 IN GREENE COUNTY TO NC 11 IN PITT COUNTY; US 13/NC 11 TO MARTIN COUNTY LINE IN PITT COUNTY. INSTALL RUMBLE STRIPES. |  | PITT, GREENE, LENOIR | 2 |  |  | Region B |  | HSIP | CONSTRUCTION | 950000 | FY 2025: 950000
HS-2402V | Highway | Safety | NC 58 | NORTH OF SR 1745 (CUNNINGHAM ROAD) IN LENOIR COUNTY TO NORTHWEST OF CAROLINA DRIVE IN GREENE COUNTY; NORTHWESTERN INTERSECTION OF US 13 TO WILSON COUNTY LINE IN GREENE COUNTY. INSTALL RUMBLE STRIPES. |  | GREENE, LENOIR | 2 |  |  | Region B |  | HSIP | CONSTRUCTION | 660000 | FY 2025: 660000
HS-2402W | Highway | Safety | US 264 | NC 32 TO THE WESTERN TOWN LIMITS OF PANTEGO. INSTALL RUMBLE STRIPES. |  | BEAUFORT | 2 |  |  | Region B |  | HSIP | CONSTRUCTION | 575000 | FY 2025: 575000
HS-2403 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2403A | Highway | Safety | SR 1216 (16TH STREET); SR 1217 (17TH STREET) | QUEEN STREET AND CASTLE STREET INTERSECTIONS; QUEEN STREET INTERSECTION IN WILMINGTON. INSTALL CROSSWALKS AND OTHER PEDESTRIAN IMPROVEMENTS. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 403000 | FY 2025: 403000
HS-2403B | Highway | Safety | NC 53; US 117; NC 111 | VARIOUS LOCATIONS ALONG ROUTES. INSTALL CENTER AND EDGELINE SINUSOIDAL RUMBLE STRIPS. | 63.83 | ONSLOW, PENDER, SAMPSON, DUPLIN, NEW HANOVER | 3 | Cape Fear RPO, Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 6230000 | FY 2026: 6230000
HS-2403C | Highway | Safety | NC 111 | ONSLOW COUNTY LINE TO NC 41 ; NC 41 / NC 241 IN BEULAVILLE TO NC 11 ; NC 11 / NC 903 TO WAYNE COUNTY LINE. INSTALL CENTERLINE AND SHOULDER SINUSOIDAL RUMBLE STRIPS. | 27.8 | DUPLIN | 3 | Eastern Carolina RPO |  | Region B |  | HSIP | CONSTRUCTION | 1360000 | FY 2025: 1360000
HS-2403D | Highway | Safety | SR 1336 (SIDBURY ROAD) | SR 1318 (BLUE CLAY ROAD) TO US 17 NORTH OF WILMINGTON. INSTALL CENTERLINE AND SHOULDER SINUSOIDAL RUMBLE STRIPS WITH BICYCLE PATTERN. | 7.2 | NEW HANOVER, PENDER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 421000 | FY 2025: 421000
HS-2403E | Highway | Safety | US 17 ; US 258 ; US 421 ; NC 24 ; NC 87 | VARIOUS LOCATIONS IN DIVISION 3. UPGRADE GUARDRAIL END UNITS. |  | ONSLOW, DUPLIN, BRUNSWICK, NEW HANOVER, PENDER, SAMPSON | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Eastern Carolina RPO, Cape Fear RPO, Mid-Carolina RPO, Grand Strand Area Transportation Study |  | Region B |  | HSIP | CONSTRUCTION | 306000 | FY 2025: 306000
HS-2403F | Highway | Safety | NC 53 (WESTERN BOULEVARD) | AT CAROLINA FOREST BOULEVARD AND NORTH PLAIN ROAD IN JACKSONVILLE. INSTALL NEAR SIDE SIGNAL HEADS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 35000 | FY 2025: 35000
HS-2403G | Highway | Safety | US 17/76 (OLEANDER DRIVE) | AT COUNTRY CLUB ROAD IN WILMINGTON. INSTALL NEAR SIDE SIGNAL HEAD AND UPGRADE TRAFFIC SIGNAL. | 0.5 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 36000 | FY 2025: 36000
HS-2403H | Highway | Safety | US 17 BUSINESS (NORTH MARINE BOULEVARD) | AT MCDANIEL DRIVE AND WORKSHOP LANE IN JACKSONVILLE. INSTALL NEAR SIDE SIGNAL HEADS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 23000 | FY 2025: 23000
HS-2403I | Highway | Safety | NC 172 | AT SR 1500 (STARLING ROAD) NEAR HUBERT. INSTALL TRAFFIC SIGNAL. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2403I | Highway | Safety | NC 172 | AT SR 1500 (STARLING ROAD) NEAR HUBERT. INSTALL TRAFFIC SIGNAL. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | UTILITIES | 2000 | FY 2026: 2000
HS-2403I | Highway | Safety | NC 172 | AT SR 1500 (STARLING ROAD) NEAR HUBERT. INSTALL TRAFFIC SIGNAL. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | HSIP | CONSTRUCTION | 378000 | FY 2026: 378000
HS-2403J | Highway | Safety | SR 1403 (COUNTRY CLUB ROAD) | AT ACADEMIC DRIVE IN JACKSONVILLE. INSTALL TRAFFIC SIGNAL, PEDESTRIAN SIGNALS, AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2403J | Highway | Safety | SR 1403 (COUNTRY CLUB ROAD) | AT ACADEMIC DRIVE IN JACKSONVILLE. INSTALL TRAFFIC SIGNAL, PEDESTRIAN SIGNALS, AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | UTILITIES | 2000 | FY 2026: 2000
HS-2403J | Highway | Safety | SR 1403 (COUNTRY CLUB ROAD) | AT ACADEMIC DRIVE IN JACKSONVILLE. INSTALL TRAFFIC SIGNAL, PEDESTRIAN SIGNALS, AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | HSIP | CONSTRUCTION | 505000 | FY 2026: 505000
HS-2403K | Highway | Safety | US 17 | AT SR 1561 (SLOOP POINT ROAD) NORTHEAST OF HAMPSTEAD. INSTALL TRAFFIC SIGNAL. | 0.5 | PENDER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2403K | Highway | Safety | US 17 | AT SR 1561 (SLOOP POINT ROAD) NORTHEAST OF HAMPSTEAD. INSTALL TRAFFIC SIGNAL. | 0.5 | PENDER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | UTILITIES | 2000 | FY 2026: 2000
HS-2403K | Highway | Safety | US 17 | AT SR 1561 (SLOOP POINT ROAD) NORTHEAST OF HAMPSTEAD. INSTALL TRAFFIC SIGNAL. | 0.5 | PENDER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 223000 | FY 2026: 223000
HS-2404 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2404A | Highway | Safety | NC 55 | SR 1006 (GRANTHAM SCHOOL ROAD) INTERSECTION. REALIGN INTERSECTION. | 0.5 | WAYNE | 4 | Eastern Carolina RPO |  | Region A |  | HSIP | RIGHT-OF-WAY | 75000 | FY 2025: 75000
HS-2404A | Highway | Safety | NC 55 | SR 1006 (GRANTHAM SCHOOL ROAD) INTERSECTION. REALIGN INTERSECTION. | 0.5 | WAYNE | 4 | Eastern Carolina RPO |  | Region A |  | HSIP | UTILITIES | 96000 | FY 2025: 96000
HS-2404A | Highway | Safety | NC 55 | SR 1006 (GRANTHAM SCHOOL ROAD) INTERSECTION. REALIGN INTERSECTION. | 0.5 | WAYNE | 4 | Eastern Carolina RPO |  | Region A |  | HSIP | CONSTRUCTION | 524000 | FY 2026: 524000
HS-2404B | Highway | Safety | NC 210 | HARNETT COUNTY LINE TO NC 50 AND SR 1382 (NORTH PLEASANT-COATES ROAD) TO SR 1010 (CLEVELAND ROAD). INSTALL RUMBLE STRIPS AND SNOWPLOWABLE PAVEMENT MARKERS. | 17 | JOHNSTON | 4 | Capital Area MPO, Upper Coastal Plain RPO |  | Region A |  | HSIP | CONSTRUCTION | 567000 | FY 2025: 567000
HS-2404C | Highway | Safety | NC 55 | 0.27 MILES WEST OF LENOIR COUNTY LINE TO MOUNT OLIVE CITY LIMITS AND SR 1135 (COUNTRY CLUB ROAD) TO SAMPSON COUNTY LINE. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 23.5 | WAYNE | 4 | Eastern Carolina RPO |  | Region A |  | HSIP | CONSTRUCTION | 806000 | FY 2025: 806000
HS-2404D | Highway | Safety | US 70 BUSINESS / US 117 BUSINESS (ASH STREET) | SR 1925 (JOHN STREET) AND US 117 BUSINESS (WILLIAM STREET) INTERSECTIONS IN GOLDSBORO. INSTALL / REVISE PEDESTRIAN ACCOMODATIONS INCLUDING TRAFFIC SIGNALS, PEDESTRIAN SIGNALS, AND CROSSWALK IMPROVEMENTS. |  | WAYNE | 4 | Goldsboro Urban Area MPO |  | Region A |  | HSIP | CONSTRUCTION | 100000 | FY 2025: 100000
HS-2404E | Highway | Safety | VARIOUS | SECONDARY ROADS IN NASH COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | NASH | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Division 4
HS-2405 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2405A | Highway | Safety | US 158 | US 158 BUSINESS (WILLIAMSBORO STREET) AT US 158 (OXFORD LOOP ROAD) AND SR 1646 (SE INDUSTRY DRIVE). UPGRADE TRAFFIC SIGNAL. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 43000 | FY 2025: 43000
HS-2405AA | Highway | Safety | US 70/US 401/NC 50 (WILMINGTON STREET) | SR 1370/SR 2684 (TRYON ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C |  | HSIP | UTILITIES | 2000 | FY 2025: 2000
HS-2405AA | Highway | Safety | US 70/US 401/NC 50 (WILMINGTON STREET) | SR 1370/SR 2684 (TRYON ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 270000 | FY 2025: 270000
HS-2405AB | Highway | Safety | SR 2000 (FALLS OF NEUSE ROAD) | NORTH BEND DRIVE INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2025: 2000
HS-2405AB | Highway | Safety | SR 2000 (FALLS OF NEUSE ROAD) | NORTH BEND DRIVE INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 3000 | FY 2025: 3000
HS-2405AB | Highway | Safety | SR 2000 (FALLS OF NEUSE ROAD) | NORTH BEND DRIVE INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 114000 | FY 2025: 114000
HS-2405AC | Highway | Safety | SR 2000 (FALLS OF NEUSE ROAD) | NEWTON ROAD INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2025: 2000
HS-2405AC | Highway | Safety | SR 2000 (FALLS OF NEUSE ROAD) | NEWTON ROAD INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 3000 | FY 2025: 3000
HS-2405AC | Highway | Safety | SR 2000 (FALLS OF NEUSE ROAD) | NEWTON ROAD INTERSECTION. UPGRADE TRAFFIC SIGNAL, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 135000 | FY 2025: 135000
HS-2405AD | Highway | Safety | US 501 (ROXBORO ROAD / DURHAM ROAD) | SR 1002 (MASON ROAD)/SR 1631 (SNOW HILL ROAD) TO PERSON COUNTY LINE; PERSON CO., US 501 FROM DURHAM COUNTY LINE TO TO 1,100 FEET SOUTH OF SR 1147 (BESSIE DANIEL ROAD), EXCLUDING 5-LANE SECTIONS. INSTALL RUMBLE STRIPS. | 16 | DURHAM, PERSON | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 115000 | FY 2025: 115000
HS-2405AE | Highway | Safety | US 15 | I-85 TO VIRGINIA STATE LINE. INSTALL RUMBLE STRIPS. | 37 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 1105000 | FY 2025: 1105000
HS-2405AF | Highway | Safety | US 1 | NC 96 TO CHAPPELL LANE. INSTALL RUMBLE STRIPS. | 12.7 | FRANKLIN, VANCE | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 77000 | FY 2025: 77000
HS-2405AG | Highway | Safety | NC 39 | NC 97 IN WAKE COUNTY TO VIRGINIA STATE LINE. INSTALL RUMBLE STRIPS. | 22.5 | VANCE, FRANKLIN, WAKE | 5 | Kerr-Tar RPO, Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 1705000 | FY 2025: 1705000
HS-2405AH | Highway | Safety | NC 54 (MIAMI BOULEVARD) | SR 1978 (HOPSON ROAD) INTERSECTION. CONSTRUCT MULTI-USE PATH ALONG NC 54 NORTH OF THE INTERSECTION AND UPGRADE CROSSWALKS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 150000 | FY 2026: 150000
HS-2405AI | Highway | Safety | SR 3008 (EDENTON STREET) | HARRINGTON STREET INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS AND HIGH VISIBILITY CROSSWALKS AND CONNECT TO RALEIGH SIGNAL SYSTEM. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 20000 | FY 2025: 20000
HS-2405AI | Highway | Safety | SR 3008 (EDENTON STREET) | HARRINGTON STREET INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS AND HIGH VISIBILITY CROSSWALKS AND CONNECT TO RALEIGH SIGNAL SYSTEM. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 20000 | FY 2025: 20000
HS-2405AI | Highway | Safety | SR 3008 (EDENTON STREET) | HARRINGTON STREET INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS AND HIGH VISIBILITY CROSSWALKS AND CONNECT TO RALEIGH SIGNAL SYSTEM. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 300000 | FY 2026: 300000
HS-2405AJ | Highway | Safety | SR 1152 (HOLLY SPRINGS ROAD) | SR 4089 (WINDING OAK WAY)/YMCA DRIVEWAY. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 12000 | FY 2025: 12000
HS-2405AJ | Highway | Safety | SR 1152 (HOLLY SPRINGS ROAD) | SR 4089 (WINDING OAK WAY)/YMCA DRIVEWAY. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 6000 | FY 2025: 6000
HS-2405AJ | Highway | Safety | SR 1152 (HOLLY SPRINGS ROAD) | SR 4089 (WINDING OAK WAY)/YMCA DRIVEWAY. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 248000 | FY 2026: 248000
HS-2405AK | Highway | Safety | SR 1004 (GARNER ROAD) | SR 2684 (TRYON ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL, AND INSTALL PEDESTRIAN SIGNALS, CURB RAMPS, AND CROSSWALKS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 8000 | FY 2025: 8000
HS-2405AK | Highway | Safety | SR 1004 (GARNER ROAD) | SR 2684 (TRYON ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL, AND INSTALL PEDESTRIAN SIGNALS, CURB RAMPS, AND CROSSWALKS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 145000 | FY 2025: 145000
HS-2405AL | Highway | Safety | NC 96 (EAST MAIN STREET) | CROSS STREET INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS. | 0.5 | FRANKLIN | 5 | Capital Area MPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2405AL | Highway | Safety | NC 96 (EAST MAIN STREET) | CROSS STREET INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS. | 0.5 | FRANKLIN | 5 | Capital Area MPO |  | Region C |  | HSIP | UTILITIES | 10000 | FY 2026: 10000
HS-2405AL | Highway | Safety | NC 96 (EAST MAIN STREET) | CROSS STREET INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNALS. | 0.5 | FRANKLIN | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 165000 | FY 2027: 165000
HS-2405AM | Highway | Safety | US 158 | HARDWOOD DRIVE IN PERSON COUNTY (MP 11.495) TO US TOBACCO COOPERATIVE DRIVEWAY IN GRANVILLE COUNTY (MP 15.230). INSTALL RUMBLE STRIPES. | 3.7 | GRANVILLE, PERSON | 5 | Kerr-Tar RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 1331000 | FY 2025: 1331000
HS-2405AN | Highway | Safety | SR 3009 (EDWARDS MILL ROAD) | SR 1728 (WADE AVENUE) RAMPS. UPGRADE TRAFFIC SIGNAL, INSTALL PEDESTRIAN SIGNALS, AND INSTALL RECTANGULAR RAPID FLASHING BEACONS AT SLIP RAMPS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 185000 | FY 2026: 185000
HS-2405AO | Highway | Safety | VARIOUS | VARIOUS INTERSECTIONS IN ROXBORO. UPGRADE PEDESTRIAN IMPROVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, SIDEWALK, LEADING PEDESRIAN INTERVAL, AND/OR TRAFFIC SIGNAL UPGRADES. | 0.5 | PERSON | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2405AO | Highway | Safety | VARIOUS | VARIOUS INTERSECTIONS IN ROXBORO. UPGRADE PEDESTRIAN IMPROVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, SIDEWALK, LEADING PEDESRIAN INTERVAL, AND/OR TRAFFIC SIGNAL UPGRADES. | 0.5 | PERSON | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | UTILITIES | 20000 | FY 2026: 20000
HS-2405AO | Highway | Safety | VARIOUS | VARIOUS INTERSECTIONS IN ROXBORO. UPGRADE PEDESTRIAN IMPROVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, SIDEWALK, LEADING PEDESRIAN INTERVAL, AND/OR TRAFFIC SIGNAL UPGRADES. | 0.5 | PERSON | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 943000 | FY 2027: 943000
HS-2405AP | Highway | Safety | VARIOUS | VARIOUS INTERSECTIONS IN HENDERSON. UPGRADE VARIOUS INTERSECTIONS IN HENDERSON. PEDESTRIAN IMPROVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, SIDEWALK, LEADING PEDESRIAN INTERVAL, AND/OR TRAFFIC SIGNAL UPGRADES. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2405AP | Highway | Safety | VARIOUS | VARIOUS INTERSECTIONS IN HENDERSON. UPGRADE VARIOUS INTERSECTIONS IN HENDERSON. PEDESTRIAN IMPROVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, SIDEWALK, LEADING PEDESRIAN INTERVAL, AND/OR TRAFFIC SIGNAL UPGRADES. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | UTILITIES | 20000 | FY 2026: 20000
HS-2405AP | Highway | Safety | VARIOUS | VARIOUS INTERSECTIONS IN HENDERSON. UPGRADE VARIOUS INTERSECTIONS IN HENDERSON. PEDESTRIAN IMPROVEMENTS INCLUDING CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, SIDEWALK, LEADING PEDESRIAN INTERVAL, AND/OR TRAFFIC SIGNAL UPGRADES. | 0.5 | VANCE | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 1255000 | FY 2027: 1255000
HS-2405AQ | Highway | Safety | SR 1835 (PINECREST ROAD) | GROVE BARTON ROAD/TOSCANA DRIVE INTERSECTION. INSTALL TRAFFIC SIGNAL AND INTERSECTION PEDESTRIAN IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2025: 30000
HS-2405AQ | Highway | Safety | SR 1835 (PINECREST ROAD) | GROVE BARTON ROAD/TOSCANA DRIVE INTERSECTION. INSTALL TRAFFIC SIGNAL AND INTERSECTION PEDESTRIAN IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 5000 | FY 2026: 5000
HS-2405AQ | Highway | Safety | SR 1835 (PINECREST ROAD) | GROVE BARTON ROAD/TOSCANA DRIVE INTERSECTION. INSTALL TRAFFIC SIGNAL AND INTERSECTION PEDESTRIAN IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 340000 | FY 2026: 340000
HS-2405AR | Highway | Safety | VARIOUS | DOWNTOWN RALEIGH PEDESTRIAN STUDY PHASE II. PEDESTRIAN IMPROVEMENTS AT MULTIPLE EXISTING CROSSWALKS INCLUDING PEDESTRIAN CURB EXTENSIONS, RAISED CROSSWALKS, AND MEDIAN REFUGE ISLANDS. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2026: 5000
HS-2405AR | Highway | Safety | VARIOUS | DOWNTOWN RALEIGH PEDESTRIAN STUDY PHASE II. PEDESTRIAN IMPROVEMENTS AT MULTIPLE EXISTING CROSSWALKS INCLUDING PEDESTRIAN CURB EXTENSIONS, RAISED CROSSWALKS, AND MEDIAN REFUGE ISLANDS. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 5000 | FY 2026: 5000
HS-2405AR | Highway | Safety | VARIOUS | DOWNTOWN RALEIGH PEDESTRIAN STUDY PHASE II. PEDESTRIAN IMPROVEMENTS AT MULTIPLE EXISTING CROSSWALKS INCLUDING PEDESTRIAN CURB EXTENSIONS, RAISED CROSSWALKS, AND MEDIAN REFUGE ISLANDS. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 1020000 | FY 2026: 1020000
HS-2405AS | Highway | Safety | US 1 (CAPITAL BOULEVARD) | CALVARY DRIVE INTERSECTION. CONSTRUCT SIGNAL AND CROSSWALK UPGRADES AND INSTALL MEDIAN FENCE. | 0.5 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 395000 | FY 2025: 395000
HS-2405B | Highway | Safety | NC 157 (GUESS ROAD) | NC 157 (GUESS ROAD) FROM DURHAM MUNICIPAL LIMITS TO ORANGE COUNTY LINE. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 223000 | FY 2025: 223000
HS-2405C | Highway | Safety | VARIOUS | US 401 IN FRANKLIN COUNTY. NC 42 IN WAKE COUNTY. NC 56 IN FRANKLIN AND GRANVILLE COUNTY. NC 96 IN WAKE AND GRANVILLE COUNTY. SR 1006 IN WAKE COUNTY AND NC 50 IN WAKE AND GRANVILLE COUNTY. INSTALL LONG LIFE PAVEMENT MARKINGS. |  | WAKE, FRANKLIN, GRANVILLE | 5 | Capital Area MPO, Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 1315000 | FY 2025: 14000; FY 2026: 1301000
HS-2405D | Highway | Safety | SR 1656 (TRINITY ROAD) | SR 1656 (TRINITY ROAD) AT SR 3009 (EDWARDS MILL ROAD). UPGRADE TRAFFIC SIGNAL TO PROVIDE PEDESTRIAN ACCOMMODATIONS AND CROSSWALKS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 16000 | FY 2025: 16000
HS-2405D | Highway | Safety | SR 1656 (TRINITY ROAD) | SR 1656 (TRINITY ROAD) AT SR 3009 (EDWARDS MILL ROAD). UPGRADE TRAFFIC SIGNAL TO PROVIDE PEDESTRIAN ACCOMMODATIONS AND CROSSWALKS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 125000 | FY 2025: 125000
HS-2405E | Highway | Safety | US 70 (GLENWOOD ROAD) | US 70 (GLENWOOD AVENUE) AT SR 1820 (LEAD MINE ROAD)/SR 1670 (BLUE RIDGE ROAD). UPGRADE TRAFFIC SIGNAL TO PROVIDE PEDESTRIAN ACCOMMODATIONS AND CROSSWALKS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 175000 | FY 2025: 175000
HS-2405F | Highway | Safety | VARIOUS | VARIOUS SECONDARY ROUTES INSTALL LONG LIFE PAVEMENT MARKINGS. |  | GRANVILLE, VANCE, PERSON | 5 | Kerr-Tar RPO |  | Division 5 |  | HSIP | CONSTRUCTION | 1850000
HS-2405G | Highway | Safety | SR 1349 (DILLARD DRIVE) | SR 1349 (DILLARD DRIVE) AT DILLARD DRVIE MIDDLE SCHOOL / ORABELLE COURT. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 8000 | FY 2025: 8000
HS-2405G | Highway | Safety | SR 1349 (DILLARD DRIVE) | SR 1349 (DILLARD DRIVE) AT DILLARD DRVIE MIDDLE SCHOOL / ORABELLE COURT. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 30000 | FY 2025: 30000
HS-2405G | Highway | Safety | SR 1349 (DILLARD DRIVE) | SR 1349 (DILLARD DRIVE) AT DILLARD DRVIE MIDDLE SCHOOL / ORABELLE COURT. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 297000 | FY 2025: 297000
HS-2405H | Highway | Safety | SR 2049 (FORESTVILLE ROAD) | SR 2049 (FORESTVILLE ROAD) AT CASHEW DRIVE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000
HS-2405H | Highway | Safety | SR 2049 (FORESTVILLE ROAD) | SR 2049 (FORESTVILLE ROAD) AT CASHEW DRIVE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 20000
HS-2405H | Highway | Safety | SR 2049 (FORESTVILLE ROAD) | SR 2049 (FORESTVILLE ROAD) AT CASHEW DRIVE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 243000 | FY 2025: 243000
HS-2405I | Highway | Safety | SR 1110 (BARBEE CHAPEL ROAD) | SR 1110 (BARBEE CHAPEL ROAD) AT DOWNING CREEK PARKWAY/HALES WOOD ROAD. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2025: 2000
HS-2405I | Highway | Safety | SR 1110 (BARBEE CHAPEL ROAD) | SR 1110 (BARBEE CHAPEL ROAD) AT DOWNING CREEK PARKWAY/HALES WOOD ROAD. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | UTILITIES | 2000 | FY 2025: 2000
HS-2405I | Highway | Safety | SR 1110 (BARBEE CHAPEL ROAD) | SR 1110 (BARBEE CHAPEL ROAD) AT DOWNING CREEK PARKWAY/HALES WOOD ROAD. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 120000 | FY 2025: 120000
HS-2405J | Highway | Safety | US 70-401 (SOUTH SAUNDERS STREET) | US 70-401 (SOUTH SAUNDERS STREET) AT I-440 / I-40 INTERCHANGE. UPGRADE RAMP TRAFFIC SIGNALS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 360000 | FY 2025: 360000
HS-2405K | Highway | Safety | SR 2026 (NORTH PERSON STREET) | POLK STREET INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS AND HIGH VISIBILITY CROSSWALKS AND CONNECT TO THE RALEIGH SIGNAL SYSTEM. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2025: 2000
HS-2405K | Highway | Safety | SR 2026 (NORTH PERSON STREET) | POLK STREET INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN SIGNALS AND HIGH VISIBILITY CROSSWALKS AND CONNECT TO THE RALEIGH SIGNAL SYSTEM. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 150000 | FY 2026: 150000
HS-2405L | Highway | Safety | VARIOUS | ALL FREEWAY RAMP LOCATIONS IN DIVISION 5. BRING WRONG WAY DRIVER DETERRENCE MARKINGS UP TO STANDARD. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Kerr-Tar RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 950000 | FY 2025: 950000
HS-2405M | Highway | Safety | US 501 BUSINESS | MAYNARD AVENUE INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS AND CONNECT TO THE DURHAM SIGNAL SYSTEM. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 25000 | FY 2025: 25000
HS-2405M | Highway | Safety | US 501 BUSINESS | MAYNARD AVENUE INTERSECTION. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS AND CONNECT TO THE DURHAM SIGNAL SYSTEM. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 177000 | FY 2025: 2000; FY 2026: 175000
HS-2405N | Highway | Safety | NC 96 (MARTIN LUTHER KING JR. AVENUE) | SR 1646 (E. INDUSTRY DRIVE) INTERSECTION. INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | GRANVILLE | 5 | Kerr-Tar RPO |  | Region C |  | HSIP | CONSTRUCTION | 284000 | FY 2025: 284000
HS-2405O | Highway | Safety | SR 2754 (KENNEBEC ROAD) | SR 2763 (MAUDE STEWART ROAD) INTERSECTION. INSTALL ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 50000 | FY 2025: 50000
HS-2405O | Highway | Safety | SR 2754 (KENNEBEC ROAD) | SR 2763 (MAUDE STEWART ROAD) INTERSECTION. INSTALL ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 50000 | FY 2025: 50000
HS-2405O | Highway | Safety | SR 2754 (KENNEBEC ROAD) | SR 2763 (MAUDE STEWART ROAD) INTERSECTION. INSTALL ROUNDABOUT. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 560000 | FY 2025: 6000; FY 2026: 554000
HS-2405P | Highway | Safety | US 501 (ROXBORO ROAD) | RIPPLING STREAM ROAD INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2025: 5000
HS-2405P | Highway | Safety | US 501 (ROXBORO ROAD) | RIPPLING STREAM ROAD INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | UTILITIES | 5000 | FY 2025: 5000
HS-2405P | Highway | Safety | US 501 (ROXBORO ROAD) | RIPPLING STREAM ROAD INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | HSIP | CONSTRUCTION | 123000 | FY 2025: 123000
HS-2405Q | Highway | Safety | SR 5144 (HERITAGE LAKE ROAD) | HERITAGE HEIGHTS LANE INTERSECTION. CROSSWALK AND SIDEWALK IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 2000 | FY 2025: 2000
HS-2405Q | Highway | Safety | SR 5144 (HERITAGE LAKE ROAD) | HERITAGE HEIGHTS LANE INTERSECTION. CROSSWALK AND SIDEWALK IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 2000 | FY 2025: 2000
HS-2405Q | Highway | Safety | SR 5144 (HERITAGE LAKE ROAD) | HERITAGE HEIGHTS LANE INTERSECTION. CROSSWALK AND SIDEWALK IMPROVEMENTS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 130000 | FY 2025: 130000
HS-2405R | Highway | Safety | SR 3067 (TW ALEXANDER DRIVE) | BRIER CLUB LANE/SALEM GLEN LANE INTERSECTION. UPGRADE TRAFFIC SIGNAL AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 8000 | FY 2025: 8000
HS-2405R | Highway | Safety | SR 3067 (TW ALEXANDER DRIVE) | BRIER CLUB LANE/SALEM GLEN LANE INTERSECTION. UPGRADE TRAFFIC SIGNAL AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 3000 | FY 2025: 3000
HS-2405R | Highway | Safety | SR 3067 (TW ALEXANDER DRIVE) | BRIER CLUB LANE/SALEM GLEN LANE INTERSECTION. UPGRADE TRAFFIC SIGNAL AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 125000 | FY 2025: 125000
HS-2405S | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | GARNER ROAD TO HAYWOOD STREET. UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 3000 | FY 2025: 3000
HS-2405S | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | GARNER ROAD TO HAYWOOD STREET. UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 5000 | FY 2025: 5000
HS-2405S | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | GARNER ROAD TO HAYWOOD STREET. UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 440000 | FY 2025: 440000
HS-2405T | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | SR 3670 (BLOUNT ST) TO SOUTH EAST STREET. UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2025: 5000
HS-2405T | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | SR 3670 (BLOUNT ST) TO SOUTH EAST STREET. UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 3000 | FY 2025: 3000
HS-2405T | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | SR 3670 (BLOUNT ST) TO SOUTH EAST STREET. UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.25 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 385000 | FY 2026: 385000
HS-2405U | Highway | Safety | SR 1652 (HARRISON AVENUE) | SR 3081 (CHAPEL HILL ROAD) INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN SIGNAL AND OTHER PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 80000 | FY 2025: 80000
HS-2405V | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | GREGG STREET TO ROCK QUARRY ROAD. INSTALL/UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 15000 | FY 2025: 15000
HS-2405V | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | GREGG STREET TO ROCK QUARRY ROAD. INSTALL/UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 5000 | FY 2025: 5000
HS-2405V | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | GREGG STREET TO ROCK QUARRY ROAD. INSTALL/UPGRADE TRAFFIC SIGNALS AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 405000 | FY 2025: 405000
HS-2405W | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | RALEIGH BOULEVARD TO POOLE ROAD. UPGRADE TRAFFIC SIGNALS, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS, AND INSTALL LIGHTING. | 1 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2025: 5000
HS-2405W | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | RALEIGH BOULEVARD TO POOLE ROAD. UPGRADE TRAFFIC SIGNALS, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS, AND INSTALL LIGHTING. | 1 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | UTILITIES | 10000 | FY 2025: 10000
HS-2405W | Highway | Safety | SR 4363 (MARTIN LUTHER KING JR BOULEVARD) | RALEIGH BOULEVARD TO POOLE ROAD. UPGRADE TRAFFIC SIGNALS, INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS, AND INSTALL LIGHTING. | 1 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 470000 | FY 2026: 470000
HS-2405X | Highway | Safety | US 70 (GLENWOOD AVENUE) | HILBURN DRIVE / GLENWWOOD FOREST DRIVE INTERSECTION. INSTALL/UPGRADE CROSSWALKS, PEDESTRIAN SIGNALS, AND SIDEWALK. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C |  | HSIP | UTILITIES | 2000 | FY 2025: 2000
HS-2405X | Highway | Safety | US 70 (GLENWOOD AVENUE) | HILBURN DRIVE / GLENWWOOD FOREST DRIVE INTERSECTION. INSTALL/UPGRADE CROSSWALKS, PEDESTRIAN SIGNALS, AND SIDEWALK. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 227000 | FY 2025: 227000
HS-2405Y | Highway | Safety | SR 2026 (HAMMOND ROAD) | RUSH STREET INTERSECTION. UPGRADE TRAFFIC SIGNALS AND INSTALL/UPGRADE PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Division 5 |  | HSIP | CONSTRUCTION | 183000 | FY 2025: 183000
HS-2405Z | Highway | Safety | US 70/401/NC 50 (WILMINGTON STREET) | CHAPANOKE ROAD INTERSECTION. UPGRADE TRAFFIC SIGNAL AND PEDESTRIAN ACCOMMODATIONS. | 0.5 | WAKE | 5 | Capital Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 89000 | FY 2025: 89000
HS-2406 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2406A | Highway | Safety | NC 87 | MILE MARKER 1.033 TO MILE MARKER 6.933 NEAR RIEGELWOOD. INSTALL RUMBLE STRIPS AND PAVEMENT MARKERS. | 5.9 | COLUMBUS | 6 | Cape Fear RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 290000 | FY 2025: 290000
HS-2406B | Highway | Safety | US 501 | NC 130 INTERSECTION IN RAEMON. REALIGN INTERSECTION, REMOVE SLIP LANES, AND ADD RIGHT TURN LANE. |  | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2025: 30000
HS-2406B | Highway | Safety | US 501 | NC 130 INTERSECTION IN RAEMON. REALIGN INTERSECTION, REMOVE SLIP LANES, AND ADD RIGHT TURN LANE. |  | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | UTILITIES | 5000 | FY 2025: 5000
HS-2406B | Highway | Safety | US 501 | NC 130 INTERSECTION IN RAEMON. REALIGN INTERSECTION, REMOVE SLIP LANES, AND ADD RIGHT TURN LANE. |  | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 1075000 | FY 2026: 1075000
HS-2406C | Highway | Safety | US 401 (RAMSEY STREET) | AT NORTHGATE SHOPPING CENTER IN FAYETTEVILLE. INSTALL CROSSWALK, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, AND UPGRADE TRAFFIC SIGNAL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 330000 | FY 2025: 330000
HS-2406D | Highway | Safety | US 401 BUSINESS (RAMSEY STREET) | LANGDON STREET AND COLONIAL DRIVE INTERSECTIONS IN FAYETTEVILLE. INSTALL CROSSWALK, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, AND UPGRADE TRAFFIC SIGNAL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 280000 | FY 2025: 280000
HS-2406E | Highway | Safety | US 701 | SR 1806 (MERCER MILL ROAD), SWANZY STREET, AND KING STREET INTERSECTIONS IN ELIZABETHTOWN. INSTALL CROSSWALKS, PEDESTRIAN SIGNAL HEADS, AND UPGRADE TRAFFIC SIGNALS. |  | BLADEN | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 715000 | FY 2025: 715000
HS-2406F | Highway | Safety | US 401 (RAMSEY STREET) | TREETOP DRIVE INTERSECTION IN FAYETTEVILLE. INSTALL / UPGRADE CROSSWALKS, PEDESTRIAN SIGNAL HEADS, CURB RAMPS, AND UPGRADE TRAFFIC SIGNAL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 200000 | FY 2025: 200000
HS-2406G | Highway | Safety | US 701 | MILEPOST 1.96 TO 9.46 IN BLADEN COUNTY, MILEPOST 2.57 TO 15.48 AND MILEPOST 19.97 TO 30.35 IN COLUMBUS COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. | 30.79 | COLUMBUS, BLADEN | 6 | Cape Fear RPO, Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 970000 | FY 2025: 970000
HS-2406HA | Highway | Safety | NC 87 | ONSLOW COUNTY LINE TO NC 41 ; NC 41 / NC 241 IN BEULAVILLE TO NC 11 ; NC 11 / NC 903 TO WAYNE COUNTY LINE. INSTALL CENTERLINE AND SHOULDER SINUSOIDAL RUMBLE STRIPS. |  | BLADEN | 6 | Mid-Carolina RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 340000 | FY 2025: 340000
HS-2406HB | Highway | Safety | NC 87 | COLUMBUS COUNTY LINE TO SR 1725 (BRADDY PLANTATION ROAD) BLADEN COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | BLADEN | 6 | Mid-Carolina RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 300000 | FY 2025: 300000
HS-2406I | Highway | Safety | VARIOUS | ROUTES IN BLADEN, COLUMBUS, AND CUMBERLAND COUNTIES. UPGRADE 60 GUARDRAIL END UNITS. |  | CUMBERLAND, COLUMBUS, BLADEN | 6 | Fayetteville Area MPO, Cape Fear RPO, Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 609000 | FY 2025: 609000
HS-2406J | Highway | Safety | NC 130 ; NC 410 | MILEPOST 0 TO MILEPOST 17.04 ; MILEPOST 2.62 TO 13.6. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | HSIP | CONSTRUCTION | 890000 | FY 2025: 890000
HS-2406K | Highway | Safety | US 301 | MILEPOST 0 TO 1.674 IN CUMBERLAND COUNTY AND MILEPOST 6.171 TO 9.703 IN HARNETT COUNTY. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | HARNETT, CUMBERLAND | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 280000 | FY 2025: 280000
HS-2406L | Highway | Safety | US 301 | MILEPOST 24.42 TO 32.52 AND MILEPOST 33.865 TO 40.92. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 670000 | FY 2025: 670000
HS-2406M | Highway | Safety | NC 130 | MILEPOST 10.14 TO 22.23; MILEPOST 5.785 TO 19.004. INSTALL RUMBLE STRIPS AND PAVEMENT MARKINGS. |  | ROBESON | 6 | Lumber River RPO |  | Region C |  | HSIP | CONSTRUCTION | 1110000 | FY 2026: 1110000
HS-2406N | Highway | Safety | NC 87 | NC 131 INTERSECTION IN TARHEEL. INSTALL TRAFFIC SIGNAL. |  | BLADEN | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2025: 5000
HS-2406N | Highway | Safety | NC 87 | NC 131 INTERSECTION IN TARHEEL. INSTALL TRAFFIC SIGNAL. |  | BLADEN | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | UTILITIES | 130000 | FY 2025: 130000
HS-2406N | Highway | Safety | NC 87 | NC 131 INTERSECTION IN TARHEEL. INSTALL TRAFFIC SIGNAL. |  | BLADEN | 6 | Mid-Carolina RPO |  | Region C |  | HSIP | CONSTRUCTION | 510000 | FY 2025: 510000
HS-2406O | Highway | Safety | US 401 (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD) INTERSECTION IN FAYETTEVILLE. REVISE TRAFFIC SIGNAL, AND INSTALL CROSSWALKS AND PEDESTRIAN SIGNAL HEADS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 260000 | FY 2025: 260000
HS-2406P | Highway | Safety | US 401 BUSINESS (ROBESON STREET) | SR 1168 (WHITFIELD STREET) INTERSECTION IN FAYETTEVILLE. REVISE TRAFFIC SIGNAL, AND INSTALL CROSSWALKS AND PEDESTRIAN SIGNAL HEADS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Region C |  | HSIP | CONSTRUCTION | 180000 | FY 2026: 180000
HS-2406Q | Highway | Safety | NC 410 (BROWN STREET) | FIRST AVENUE INTERSECTION IN CHADBOURN. UPGRADE TRAFFIC SIGNAL WITH PEDESTRIAN HEADS. |  | COLUMBUS | 6 | Cape Fear RPO |  | Region C |  | HSIP | CONSTRUCTION | 85000 | FY 2025: 85000
HS-2406R | Highway | Safety | SR 1404 (MORGANTON ROAD) | MCPHERSON CHURCH ROAD. INSTALL/UPGRADE CROSSWALKS, CROSSWALK RAMPS SIGNALIZED PEDESTRIAN HEADS, AND TRAFFIC SIGNAL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6
HS-2406S | Highway | Safety | US 401 (SKIBO ROAD) | NC 24-87 (BRAGG BOULEVARD) EASTBOUND RAMPS (SWAIN STREET). INSTALL/UPGRADE CROSSWALKS AND TRAFFIC SIGNAL. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility
HS-2407 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2407A | Highway | Safety | SR 2526 (SUMMIT AVENUE) | TEXTILE DRIVE INTERSECTION. INSTALL PEDESTRIAN SIGNAL HEADS, CROSSWALK, AND OTHER INSTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | UTILITIES | 5000
HS-2407A | Highway | Safety | SR 2526 (SUMMIT AVENUE) | TEXTILE DRIVE INTERSECTION. INSTALL PEDESTRIAN SIGNAL HEADS, CROSSWALK, AND OTHER INSTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 70000 | FY 2025: 70000
HS-2407B | Highway | Safety | SR 1007 (RANDLEMAN ROAD) | WEBSTER ROAD INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | RIGHT-OF-WAY | 5000 | FY 2025: 5000
HS-2407B | Highway | Safety | SR 1007 (RANDLEMAN ROAD) | WEBSTER ROAD INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | UTILITIES | 40000 | FY 2025: 40000
HS-2407B | Highway | Safety | SR 1007 (RANDLEMAN ROAD) | WEBSTER ROAD INTERSECTION. INSTALL TRAFFIC SIGNAL. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | HSIP | CONSTRUCTION | 145000 | FY 2026: 145000
HS-2407C | Highway | Safety | US 29 NORTHBOUND | SR 2613 (NORTH O'HENRY BOULEVARD) IN THE VICINITY OF JOE BROWN DRIVE; SR 2937 (NORTH O'HENRY BOULEVARD) IN THE VICINITY OF THE FLEA MARKET; SR 2622/SR 5235 (CORBIN ROAD). CLOSE DIRECTIONAL LEFTOVERS. | 0.9 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 615000 | FY 2027: 615000
HS-2408 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2408A | Highway | Safety | NC 751; SR 1008 (FARRINGTON POINT ROAD) | NC 751 FROM US 64 TO DURHAM COUNTY LINE; SR 1008 (FARRINGTON POINT ROAD) FROM SR 1972 (PEA RIDGE ROAD) TO ORANGE COUNTY LINE. INSTALL RUMBLE STRIPS. | 21.8 | CHATHAM | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO |  | Region E |  | HSIP | CONSTRUCTION | 695000 | FY 2025: 695000
HS-2408B | Highway | Safety | US 1 | SR 2026 (YOUNGS ROAD) INTERSECTION. INSTALL REDUCED CONFLICT INTERSECTION. | 0.5 | MOORE | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 25000 | FY 2025: 25000
HS-2408B | Highway | Safety | US 1 | SR 2026 (YOUNGS ROAD) INTERSECTION. INSTALL REDUCED CONFLICT INTERSECTION. | 0.5 | MOORE | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 25000 | FY 2025: 25000
HS-2408B | Highway | Safety | US 1 | SR 2026 (YOUNGS ROAD) INTERSECTION. INSTALL REDUCED CONFLICT INTERSECTION. | 0.5 | MOORE | 8 | Central Pines RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 825000 | FY 2026: 825000
HS-2409 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2409A | Highway | Safety | NC 150 | SR 2983 (FISHEL ROAD) INTERSECTION SOUTH OF WINSTON-SALEM. CONSTRUCT REDUCED CONFLICT INTERSECTION. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D |  | HSIP | UTILITIES | 50000 | FY 2025: 50000
HS-2409A | Highway | Safety | NC 150 | SR 2983 (FISHEL ROAD) INTERSECTION SOUTH OF WINSTON-SALEM. CONSTRUCT REDUCED CONFLICT INTERSECTION. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D |  | HSIP | CONSTRUCTION | 1100000 | FY 2025: 1100000
HS-2409B | Highway | Safety | SR 1002 (OLD CONCORD ROAD) | MARTIN LUTHER KING JR. AVENUE SOUTH INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL/UPGRADE PEDESTRIAN SIGNALS AND OTHER PEDESTRIAN ACCOMMODATIONS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | UTILITIES | 30000 | FY 2025: 30000
HS-2409B | Highway | Safety | SR 1002 (OLD CONCORD ROAD) | MARTIN LUTHER KING JR. AVENUE SOUTH INTERSECTION. UPGRADE TRAFFIC SIGNAL AND INSTALL/UPGRADE PEDESTRIAN SIGNALS AND OTHER PEDESTRIAN ACCOMMODATIONS. | 0.5 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Division 9 |  | HSIP | CONSTRUCTION | 160000 | FY 2026: 160000
HS-2409C | Highway | Safety | SR 1725 (UNIVERSITY PARKWAY) | WEST 14TH STREET INTERSECTION IN WINSTON-SALEM. UPGRADE TRAFFIC SIGNAL, INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS, AND MODIFY SIDEWALK AND MEDIAN. | 0.5 | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | HSIP | CONSTRUCTION | 515000 | FY 2025: 515000
HS-2410 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2410A | Highway | Safety | SR 1790 (WINECOFF SCHOOL ROAD) | NEAR WINCOFF ELEMENTARY SCHOOL IN CONCORD. INSTALL PEDESTRIAN ACCOMODATIONS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 10000 | FY 2026: 10000
HS-2410A | Highway | Safety | SR 1790 (WINECOFF SCHOOL ROAD) | NEAR WINCOFF ELEMENTARY SCHOOL IN CONCORD. INSTALL PEDESTRIAN ACCOMODATIONS. | 0.5 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | HSIP | CONSTRUCTION | 97000 | FY 2028: 97000
HS-2410B | Highway | Safety | SR 3300 (7TH STREET) | BASCOM STREET / CAMERON AVENUE IN CHARLOTTE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 25000 | FY 2026: 25000
HS-2410B | Highway | Safety | SR 3300 (7TH STREET) | BASCOM STREET / CAMERON AVENUE IN CHARLOTTE. INSTALL TRAFFIC SIGNAL WITH PEDESTRIAN ACCOMMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 233000 | FY 2028: 233000
HS-2410C | Highway | Safety | SR 3624 (REA ROAD) | PIPER GLEN DRIVE AND BEVINGTON PLACE INTERSECTIONS IN CHARLOTTE. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN ACCOMMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | RIGHT-OF-WAY | 1000 | FY 2026: 1000
HS-2410C | Highway | Safety | SR 3624 (REA ROAD) | PIPER GLEN DRIVE AND BEVINGTON PLACE INTERSECTIONS IN CHARLOTTE. UPGRADE TRAFFIC SIGNAL AND INSTALL PEDESTRIAN ACCOMMODATIONS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 317000 | FY 2028: 317000
HS-2410D | Highway | Safety | US 29 (CONCORD PARKWAY) | SR 2894 (BRUTON SMITH BOULEVARD) INTERSECTION IN CONCORD. INSTALL PEDESTRIAN SIGNAL UPGRADES. |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Region E |  | HSIP | CONSTRUCTION | 29000 | FY 2025: 29000
HS-2410E | Highway | Safety | SR 3687 (PARK ROAD) | JIM HYNES CIRCLE INTERSECTION IN CHARLOTTE. INSTALL PEDESTRIAN SIGNAL. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 36000 | FY 2025: 36000
HS-2410F | Highway | Safety | US 74 | ANSON HIGH SCHOOL ROAD INTERSECTION IN WADESBORO. INSTALL CROSSWALK, CURB RAMPS, AND GUARDRAIL. |  | ANSON | 10 | Rocky River RPO |  | Statewide Mobility |  | HSIP | RIGHT-OF-WAY | 6000 | FY 2026: 6000
HS-2410F | Highway | Safety | US 74 | ANSON HIGH SCHOOL ROAD INTERSECTION IN WADESBORO. INSTALL CROSSWALK, CURB RAMPS, AND GUARDRAIL. |  | ANSON | 10 | Rocky River RPO |  | Statewide Mobility |  | HSIP | UTILITIES | 6000 | FY 2027: 6000
HS-2410F | Highway | Safety | US 74 | ANSON HIGH SCHOOL ROAD INTERSECTION IN WADESBORO. INSTALL CROSSWALK, CURB RAMPS, AND GUARDRAIL. |  | ANSON | 10 | Rocky River RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 184000 | FY 2027: 184000
HS-2410G | Highway | Safety | SR 2935 | COVE CREEK DRIVE INTERSECTION IN CHARLOTTE. CONSTRUCT DIRECTIONAL CROSSVER. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 482000 | FY 2025: 482000
HS-2410H | Highway | Safety | NC 51 | PALOMINO DRIVE/ HOODS VILLAGE DRIVE INTERSECTION IN MINT HILL. CONSTRUCT DIRECTIONAL CROSSOVER. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 260000 | FY 2026: 260000
HS-2410H | Highway | Safety | NC 51 | PALOMINO DRIVE/ HOODS VILLAGE DRIVE INTERSECTION IN MINT HILL. CONSTRUCT DIRECTIONAL CROSSOVER. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | UTILITIES | 15000 | FY 2026: 15000
HS-2410H | Highway | Safety | NC 51 | PALOMINO DRIVE/ HOODS VILLAGE DRIVE INTERSECTION IN MINT HILL. CONSTRUCT DIRECTIONAL CROSSOVER. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 848000 | FY 2028: 848000
HS-2410I | Highway | Safety | NC 73 | SR 1425 (NELSON MOUNTAIN ROAD)/ SR 1243 (CANE ROAD) INTERSECTION NEAR ALBEMARLE. REALIGN INTERSECTION AND CONSTRUCT TURN LANES. |  | STANLY | 10 | Rocky River RPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 125000 | FY 2026: 125000
HS-2410I | Highway | Safety | NC 73 | SR 1425 (NELSON MOUNTAIN ROAD)/ SR 1243 (CANE ROAD) INTERSECTION NEAR ALBEMARLE. REALIGN INTERSECTION AND CONSTRUCT TURN LANES. |  | STANLY | 10 | Rocky River RPO |  | Region E |  | HSIP | UTILITIES | 65000 | FY 2026: 65000
HS-2410I | Highway | Safety | NC 73 | SR 1425 (NELSON MOUNTAIN ROAD)/ SR 1243 (CANE ROAD) INTERSECTION NEAR ALBEMARLE. REALIGN INTERSECTION AND CONSTRUCT TURN LANES. |  | STANLY | 10 | Rocky River RPO |  | Region E |  | HSIP | CONSTRUCTION | 912000 | FY 2028: 912000
HS-2410J | Highway | Safety | NC 51; SR 3468 (WEDDINGTON ROAD) | FULLWOOD LANE INTERSECTION IN MATTHEWS; SOCRATES ACADEMY. CONSTRUCT SIDEWALKS AND INSTALL PEDESTRIAN IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | RIGHT-OF-WAY | 15000 | FY 2025: 15000
HS-2410J | Highway | Safety | NC 51; SR 3468 (WEDDINGTON ROAD) | FULLWOOD LANE INTERSECTION IN MATTHEWS; SOCRATES ACADEMY. CONSTRUCT SIDEWALKS AND INSTALL PEDESTRIAN IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | UTILITIES | 5000 | FY 2026: 5000
HS-2410J | Highway | Safety | NC 51; SR 3468 (WEDDINGTON ROAD) | FULLWOOD LANE INTERSECTION IN MATTHEWS; SOCRATES ACADEMY. CONSTRUCT SIDEWALKS AND INSTALL PEDESTRIAN IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Region E |  | HSIP | CONSTRUCTION | 277000 | FY 2027: 277000
HS-2410K | Highway | Safety | SR 3448 (PLEASANT PLAINS ROAD) | SQUIRREL LAKE PARK ENTRANCE INTERSECTION IN MATTHEWS. CONSTRUCT SIDEWALKS AND INSTALL PEDESTRIAN IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | UTILITIES | 10000 | FY 2025: 10000
HS-2410K | Highway | Safety | SR 3448 (PLEASANT PLAINS ROAD) | SQUIRREL LAKE PARK ENTRANCE INTERSECTION IN MATTHEWS. CONSTRUCT SIDEWALKS AND INSTALL PEDESTRIAN IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 101000 | FY 2026: 101000
HS-2410L | Highway | Safety | VARIOUS | INSTALL SIGNAL AT VARIOUS LOCATION ON SECONDARY ROUTES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 1153000 | FY 2025: 1153000
HS-2410M | Highway | Safety | SR 1313 (JOE KERR ROAD) AND SR 3486 (WHEATFIELD DR | INSTALL PEDESTRIAN SIGNS AND CROSSWALK. |  | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | ENGINEERING | 30000 | FY 2025: 30000
HS-2410M | Highway | Safety | SR 1313 (JOE KERR ROAD) AND SR 3486 (WHEATFIELD DR | INSTALL PEDESTRIAN SIGNS AND CROSSWALK. |  | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | UTILITIES | 10000 | FY 2025: 10000
HS-2410M | Highway | Safety | SR 1313 (JOE KERR ROAD) AND SR 3486 (WHEATFIELD DR | INSTALL PEDESTRIAN SIGNS AND CROSSWALK. |  | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | HSIP | CONSTRUCTION | 90000 | FY 2026: 90000
HS-2411 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2411A | Highway | Safety | SR 1143 (NEW BROWNS FORD ROAD) | BRIDGE 960093 OVER YADKIN RIVER. INSTALL GUARDRAIL. |  | WILKES | 11 | High Country RPO |  | Division 11 |  | HSIP | CONSTRUCTION | 36000 | FY 2025: 36000
HS-2411B | Highway | Safety | I-77 | VARIOUS LOCATIONS. UPGRADE GUARDRAIL END UNITS. |  | YADKIN, SURRY | 11 | Northwest Piedmont RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 152000 | FY 2025: 152000
HS-2412 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2413 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2413A | Highway | Safety | US 64 / NC 18; US 64 / US 74 | MORGANTON NORTHEAST MUNICIPAL LIMIT TO BURKE COUNTY LINE; SR 1008 (BILLS CREEK ROAD) TO RUTHERFORDTON WESTERN MUNICIPAL LIMIT. INSTALL LONG LIFE PAVEMENT MARKINGS. | 17.46 | RUTHERFORD, BURKE | 13 | Foothills RPO, Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 675000 | FY 2025: 499000; FY 2026: 176000
HS-2413B | Highway | Safety | US 64 | RUTHERFORDTON NORTHEAST MUNICIPAL LIMIT TO MORGANTON SOUTHWEST MUNICIPAL LIMIT. INSTALL LONG LIFE PAVEMENT MARKINGS. | 28.03 | RUTHERFORD, BURKE, McDOWELL | 13 | Foothills RPO, Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 775000 | FY 2025: 573000; FY 2026: 202000
HS-2413C | Highway | Safety | US 221 | US 221 BUSINESS TO NORTH OF NC 226 NEAR MARION. INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | McDOWELL | 13 | Foothills RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 445000 | FY 2026: 445000
HS-2413D | Highway | Safety | US 70 | MILE MARKER 7.424 TO MILE MARKER 15.422 AND MILE MARKER 20.237 TO MILE MARKER 27.443 NEAR MARION. INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | McDOWELL | 13 | Foothills RPO |  | Region G |  | HSIP | CONSTRUCTION | 690000 | FY 2026: 690000
HS-2413E | Highway | Safety | US 70 | INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | BURKE | 13 | Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 270000 | FY 2026: 270000
HS-2413F | Highway | Safety | NC 226 | BAKERSVILLE AND SPRUCE PINE. INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | MITCHELL | 13 | High Country RPO |  | Region G |  | HSIP | CONSTRUCTION | 350000 | FY 2026: 350000
HS-2413G | Highway | Safety | SR 3136 (CANE CREEK ROAD) | SR 3116 (MILLS GAP ROAD) TO US 74 ALTERNATE NEAR FAIRVIEW. INSTALL RUMBLESTRIPES AND 6" LONG LIFE PAVEMENT MARKINGS. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 235000 | FY 2026: 235000
HS-2413H | Highway | Safety | VARIOUS | PRIMARY AND SECONDARY ROUTES IN DIVISION 13. INSTALL HORIZONTAL ALIGNMENT WARNING SIGNS. |  | BURKE | 13 | Greater Hickory MPO |  | Region G |  | HSIP | CONSTRUCTION | 438000 | FY 2026: 438000
HS-2413I | Highway | Safety | SR 1002 (OLD LEICESTER HIGHWAY) | NC 63 TO SR 1607 NEAR LEICESTER. INSTALL GUARDRAIL. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 267000 | FY 2025: 267000
HS-2413J | Highway | Safety | SR 1727 (MONTICELLO ROAD) | SR 1882 (NEW STOCK ROAD) TO EAST OF NC 251 (OLD MARSHALL HIGHWAY). INSTALL GUARDRAIL. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | HSIP | CONSTRUCTION | 300000 | FY 2025: 300000
HS-2413K | Highway | Safety | US 19 / US 23 / US 74 ALT (SMOKEY PARK HIGHWAY) | I-40 TO COOPER BOULEVARD. INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND SIDEWALK. | 26.2 | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | HSIP | UTILITIES | 25000 | FY 2025: 25000
HS-2413K | Highway | Safety | US 19 / US 23 / US 74 ALT (SMOKEY PARK HIGHWAY) | I-40 TO COOPER BOULEVARD. INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND SIDEWALK. | 26.2 | BUNCOMBE | 13 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 905000 | FY 2025: 905000
HS-2413L | Highway | Safety | I-40 | BUNCOMBE COUNTY LINE TO BURKE COUNTY LINE. UPGRADE GUARDRAIL END UNITS. |  | McDOWELL | 13 | Foothills RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 200000 | FY 2025: 200000
HS-2413M | Highway | Safety | US 221 | RUTHERFORD COUNTY LINE TO AVERY COUNTY LINE. UPGRADE GUARDRAIL END UNITS. |  | McDOWELL | 13 | Foothills RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 645000 | FY 2025: 645000
HS-2414 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2414A | Highway | Safety | US 19 / US 74 | NANTAHALA OUTDOORS CENTER/ APPALACHIAN TRAIL NEAR SR 1103 NEAR WESSER. INSTALL PEDESTRIAN RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | SWAIN | 14 | Southwestern RPO |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 48000 | FY 2025: 48000
HS-2414B | Highway | Safety | US 19 BUSINESS | SR 1424 (CONNAHETTA STREET) AND MAPLE STREET INTERSECTIONS. INSTALL PEDESTRIAN RECTANGULAR RAPID FLASHING BEACONS. | 0.5 | CHEROKEE | 14 | Southwestern RPO |  | Region G |  | HSIP | CONSTRUCTION | 75000 | FY 2025: 75000
HS-2414C | Highway | Safety | US 64 (6TH AVENUE W.) | NORTH OAK STREET INTERSECTION IN HENDERSONVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACON WITH ADVANCED FLASHERS AND ACTUATED CROSSWALK LIGHTING. |  | HENDERSON | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 50000 | FY 2025: 50000
HS-2414D | Highway | Safety | SR 1668 (FULTON ROAD) | US 64 TO SR 1667 NEAR FRANKLIN. INSTALL GUARDRAIL. |  | MACON | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 190000 | FY 2025: 190000
HS-2414E | Highway | Safety | SR 1372 (LOWER BURNINGTOWN ROAD) | SR 1474 (SALDEER MOUNTAIN ROAD) TO SR 1392 (MIDDLE BURNINGTOWN ROAD) NEAR FRANKLIN. INSTALL GUARDRAIL. |  | MACON | 14 | Southwestern RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 375000 | FY 2025: 375000
HS-2414F | Highway | Safety | NC 191 (HAYWOOD ROAD) | RIDGEWOOD BOULEVARD / WHITMIRE STREET INTERSECTION IN HENDERSONVILLE. INSTALL RECTANGULAR RAPID FLASHING BEACON AND ACTUATED CROSSWALK LIGHTING. |  | HENDERSON | 14 | French Broad River MPO |  | Region G |  | HSIP | CONSTRUCTION | 43000 | FY 2025: 43000
HS-2414G | Highway | Safety | SR 1512 (ECUSTA ROAD) | ECUSTA BYPASS INTERSECTION IN BREVARD. INSTALL RECTANGULAR RAPID FLASHING BEACON AND ACTUATED CROSSWALK LIGHTING. |  | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Division 14 |  | HSIP | CONSTRUCTION | 35000 | FY 2025: 35000
HS-2414H | Highway | Safety | US 64 | MILE MARKER 5 TO MILE MARKER 13 AND MILE MARKER 25 TO MILE MARKER 31 NEAR BREVARD. INSTALL RUMBLE STRIPES WITH 6" LONG LIFE PAVEMENT MARKINGS. |  | TRANSYLVANIA | 14 | Land-of-Sky RPO |  | Region G |  | HSIP | CONSTRUCTION | 580000 | FY 2025: 580000
HS-2420 | Highway | Safety | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HS-2420DIV | Highway | Safety | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 15300000 | FY 2025: 2550000; FY 2026: 2550000; FY 2027: 2550000; FY 2028: 2550000; FY 2029: 2550000
HS-2420REG | Highway | Safety | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 15300000 | FY 2025: 2550000; FY 2026: 2550000; FY 2027: 2550000; FY 2028: 2550000; FY 2029: 2550000
HS-2420SW | Highway | Safety | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 20400000 | FY 2025: 3400000; FY 2026: 3400000; FY 2027: 3400000; FY 2028: 3400000; FY 2029: 3400000
HS-2421 | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HS-2421DIV | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 24000000 | FY 2025: 4500000; FY 2026: 4500000; FY 2027: 4500000; FY 2028: 4500000; FY 2029: 4500000
HS-2421REG | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 24000000 | FY 2025: 4500000; FY 2026: 4500000; FY 2027: 4500000; FY 2028: 4500000; FY 2029: 4500000
HS-2421SW | Highway | Safety | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 32000000 | FY 2025: 6000000; FY 2026: 6000000; FY 2027: 6000000; FY 2028: 6000000; FY 2029: 6000000
HS-2422 | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT
HS-2422DIV | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 15000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
HS-2422REG | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 18500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 5000000 | 1500000 | 1500000
HS-2422SW | Highway | Safety | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 20000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
HS-2601 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2602 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2603 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2604 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Peanut Belt RPO, Capital Area MPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2605 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2606 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Cape Fear RPO, Lumber River RPO, Fayetteville Area MPO, Capital Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2607 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2608 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2609 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2610 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2611 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2612 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2613 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-2614 | Highway | Safety | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
HS-9999 | Highway | Safety | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT
HS-9999DIV | Highway | Safety | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | HSIP | CONSTRUCTION | 276783000 | 13338000 | 19860000 | 23674000 | 24644000 | 24900000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000
HS-9999REG | Highway | Safety | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | HSIP | CONSTRUCTION | 276833000 | 13388000 | 19860000 | 23674000 | 24644000 | 24900000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000
HS-9999SW | Highway | Safety | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | HSIP | CONSTRUCTION | 369110000 | 17850000 | 26480000 | 31566000 | 32858000 | 33200000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000
HV-0001 | Highway | National Electric Vehicle Infrastructure | VARIOUS | CONSTRUCTION OF ELECTRIC VEHICLE SUPPLY EQUIPMENT ALONG NORTH CAROLINA'S ALTERNATIVE CORRIDORS AND NEVI PLANNING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | NEVI | ENGINEERING | 9371000 | FY 2025: 5199000; FY 2026: 2000000
HV-0001 | Highway | National Electric Vehicle Infrastructure | VARIOUS | CONSTRUCTION OF ELECTRIC VEHICLE SUPPLY EQUIPMENT ALONG NORTH CAROLINA'S ALTERNATIVE CORRIDORS AND NEVI PLANNING. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | NEVI | CONSTRUCTION | 95010000 | FY 2025: 75000000; FY 2026: 20000000
HV-9999 | Highway | National Electric Vehicle Infrastructure | VARIOUS | NATIONAL ELECTRIC VEHICLE INFRASTRUCTURE PROGRAM (NEVI) - UNPROGRAMMED BALANCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | NEVI | CONSTRUCTION | 6925000 | FY 2025: 0; FY 2026: 6925000
I-0305 | Highway | STI (Prioritization) | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES AND UPGRADE INTERCHANGES. | 7.8 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH U-5845
I-0305A | Highway | STI (Prioritization) | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | 7.81 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO | PROJECT FUNDED FOR PRELIMINARY ENGINEERING ONLY. | Not Funded |  | NHP | RIGHT-OF-WAY | 17900000 | [11 empty] | 17900000
I-0305A | Highway | STI (Prioritization) | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | 7.81 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO | PROJECT FUNDED FOR PRELIMINARY ENGINEERING ONLY. | Not Funded |  | NHP | UTILITIES | 1200000 | [11 empty] | 1200000
I-0305A | Highway | STI (Prioritization) | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | 7.81 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO | PROJECT FUNDED FOR PRELIMINARY ENGINEERING ONLY. | Not Funded |  | NHP | CONSTRUCTION | 120898000 | [11 empty] | 120898000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 52800000 | FY 2030: 7040000; FY 2031: 16896000; FY 2032: 16896000; FY 2033: 1408000; FY 2034: 10560000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | NHP | UTILITIES | 1200000 | FY 2030: 600000; FY 2031: 600000
I-0305B | Highway | STI (Prioritization) | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5967. | Statewide Mobility |  | NHP | CONSTRUCTION | 101000000 | FY 2033: 38295000; FY 2034: 38927000; FY 2035: 18583000 | 5195000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | NHP | RIGHT-OF-WAY | 11800000 | [11 empty] | 11800000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | NHP | UTILITIES | 3100000 | [11 empty] | 3100000
I-0305C | Highway | STI (Prioritization) | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | 1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | SCOPE PREVIOUSLY INCLUDED UNDER I-5984. | Not Funded |  | NHP | CONSTRUCTION | 56500000 | [11 empty] | 56500000
I-0911 | Highway | STI (Prioritization) | I-40 | WEST OF NC 801 IN BERMUDA RUN TO WEST OF SR 1122 (JONESTOWN ROAD) IN WINSTON-SALEM. ADD LANES. | 7 | FORSYTH, DAVIE | 9 | Winston-Salem Area TPO | PARTS B AND C COMPLETE
I-0911A | Highway | STI (Prioritization) | I-40 | WEST OF NC 801 IN DAVIE COUNTY TO SR 1101 (HARPER ROAD) IN FORSYTH COUNTY. | 2.33 | DAVIE, FORSYTH | 9 | Winston-Salem Area TPO | COMPLETE; DESIGN-BUILD PROJECT; BUILD NC BONDS: $27.889 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region D |  | T | BUILD NC CON | 35894000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2393000 | 2392000
I-0914 | Highway | Pre-STI (Historic) | I-85 | US 158 (MILE POST 213.5) IN VANCE COUNTY TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION AND SIGN UPGRADES. | 19 | WARREN, VANCE | 5 | Kerr-Tar RPO |  | Pre-STI (Transition)
I-0914BA | Highway | Transition | I-85 | SOUTH OF US 158 IN VANCE COUNTY TO NORTH OF SR 1237 (MANSON DREWRY ROAD) IN WARREN COUNTY | 5.81 | VANCE, WARREN | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
I-0914BB | Highway | Transition | I-85 | NORTH OF SR 1237 (MANSON DREWRY ROAD) TO VIRGINIA STATE LINE | 7.72 | WARREN | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
I-0914BC | Highway | Pre-STI (Historic) | I-85 | ITS DEPLOYMENT FOR PARTS BA AND BB |  | WARREN, VANCE | 5 | Kerr-Tar RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
I-2304 | Highway | Pre-STI (Historic) | I-85 | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO US 29 / US 52 / US 70 / BUSINESS 85 IN DAVIDSON COUNTY. ADDITIONAL LANES AND YADKIN RIVER BRIDGE RECONSTRUCTION. (PROJECT INCLUDES B-3833). | 6.8 | DAVIDSON, ROWAN | 9 | High Point Urban Area MPO, Cabarrus-Rowan MPO | INCLUDES B-3833; TIGER AWARD / INTERSTATE MAINTENANCE DISCRETIONARY FUNDING $11.7 MILLION; GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS | Pre-STI (Transition)
I-2304AC | Highway | Pre-STI (Historic) | I-85 | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO NORTH OF NC 150 IN DAVIDSON COUNTY, INCLUDING YADKIN RIVER BRIDGE |  | DAVIDSON, ROWAN | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC | Exempt |  | NHP | GARVEE ROW | 1066000
I-2304AC | Highway | Pre-STI (Historic) | I-85 | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO NORTH OF NC 150 IN DAVIDSON COUNTY, INCLUDING YADKIN RIVER BRIDGE |  | DAVIDSON, ROWAN | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; AND $111.7 MILLION FOR CONSTRUCTION, SECTION AC | Exempt |  | NHP | GARVEE CON | 8220000
I-2304AD | Highway | Pre-STI (Historic) | I-85 | NORTH OF NC 150 TO US 29-70-52/BUSINESS 85 IN DAVIDSON COUNTY |  | DAVIDSON | 9 | High Point Urban Area MPO | COMPLETE; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021 | Pre-STI (Transition) |  | NHP | GARVEE ROW | 984000
I-2304AF | Highway | Transition | I-85 | IMPLEMENTATION OF INTELLIGENT TRANSPORTATION SYSTEM (ITS) |  | DAVIDSON, ROWAN | 9 | Cabarrus-Rowan MPO, High Point Urban Area MPO | COMPLETE | Pre-STI (Transition)
I-2513 | Highway | STI (Prioritization) | I-26/I-240 | I-26 CONNECTOR, I-40 TO US 19/US 23. CONSTRUCT MULTI-LANE FREEWAY, PART ON NEW LOCATION. | 4.7 | BUNCOMBE | 13 | French Broad River MPO
I-2513AA | Highway | Interstate Maintenance | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 1.39 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHFP | RIGHT-OF-WAY | 2000000 | FY 2025: 200000; FY 2026: 200000
I-2513AA | Highway | Interstate Maintenance | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 1.39 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHFP | UTILITIES | 100000
I-2513AA | Highway | Interstate Maintenance | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 1.39 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | HP | CONSTRUCTION | 4001000 | FY 2025: 1616000; FY 2026: 1188000; FY 2027: 840000; FY 2028: 317000
I-2513AA | Highway | Interstate Maintenance | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 1.39 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHFP | CONSTRUCTION | 11649000 | FY 2025: 4706000; FY 2026: 3459000; FY 2027: 2445000; FY 2028: 923000
I-2513AA | Highway | Interstate Maintenance | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | 1.39 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AB. $4M IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 67379000 | FY 2025: 27408000; FY 2026: 20004000; FY 2027: 14143000; FY 2028: 5340000
I-2513AB | Highway | STI (Prioritization) | I-26, I-40 | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | 1 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Region G |  | NHP | RIGHT-OF-WAY | 3400000 | FY 2025: 340000; FY 2026: 340000
I-2513AB | Highway | STI (Prioritization) | I-26, I-40 | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | 1 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Region G |  | NHP | UTILITIES | 100000
I-2513AB | Highway | STI (Prioritization) | I-26, I-40 | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | 1 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Region G |  | HP | CONSTRUCTION | 6249000 | FY 2025: 3307000; FY 2026: 2165000; FY 2027: 715000
I-2513AB | Highway | STI (Prioritization) | I-26, I-40 | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NORTHBOUND RAMP. | 1 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513AA. $6.25 IN HP FUNDS REPRESENT FEDERAL EARMARK, DEMO ID NC197 FROM FY 2023 APPROPRIATIONS ACT. RIGHT-OF-WAY IN PROGRESS. | Region G |  | NHP | CONSTRUCTION | 33259000 | FY 2025: 17692000; FY 2026: 11521000; FY 2027: 3803000
I-2513AC | Highway | STI (Prioritization) | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 1.85 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | BUILD NC ROW | 8820000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000 | 588000
I-2513AC | Highway | STI (Prioritization) | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 1.85 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | RIGHT-OF-WAY | 33149000 | FY 2025: 4000000
I-2513AC | Highway | STI (Prioritization) | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 1.85 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | UTILITIES | 3750000
I-2513AC | Highway | STI (Prioritization) | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 1.85 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | BUILD NC CON | 68625000 |  |  |  |  | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 36600000
I-2513AC | Highway | STI (Prioritization) | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 1.85 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | BUILD NC CON | 68625000 |  |  |  | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 32025000
I-2513AC | Highway | STI (Prioritization) | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | 1.85 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.85M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE). $45M FOR CONSTRUCTION, PAYBACK FY 2028-2042 (FY 2028/ YR 8 SALE); $45M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029/ YR 9 SALE); | Region G |  | T | CONSTRUCTION | 127400000 | FY 2027: 23914000; FY 2028: 15872000; FY 2029: 7176000; FY 2030: 45654000; FY 2031: 34784000
I-2513B | Highway | STI (Prioritization) | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET). | 2.75 | BUNCOMBE | 13 | French Broad River MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 150700000 | FY 2025: 52745000; FY 2026: 52745000; FY 2027: 15070000; FY 2028: 15070000
I-2513B | Highway | STI (Prioritization) | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET). | 2.75 | BUNCOMBE | 13 | French Broad River MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | UTILITIES | 24100000 | FY 2025: 10845000; FY 2026: 10845000; FY 2027: 1205000
I-2513B | Highway | STI (Prioritization) | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET). | 2.75 | BUNCOMBE | 13 | French Broad River MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | GARVEE CON | 304995000 |  |  | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 121998000
I-2513B | Highway | STI (Prioritization) | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET). | 2.75 | BUNCOMBE | 13 | French Broad River MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | GARVEE CON | 304995000 |  |  |  |  | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 162664000
I-2513B | Highway | STI (Prioritization) | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY STREET). | 2.75 | BUNCOMBE | 13 | French Broad River MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041; $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043; TO BE LET WITH I-2513D. | Statewide Mobility |  | NHP | CONSTRUCTION | 636000000 | 82880000 | 103600000 | 27920000 | 227920000 | 17560000 | 124320000 | 41440000
I-2513C | Highway | STI (Prioritization) | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS. | 1 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 8900000 | [11 empty] | 8900000
I-2513C | Highway | STI (Prioritization) | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS. | 1 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | NHP | UTILITIES | 13400000 | [11 empty] | 13400000
I-2513C | Highway | STI (Prioritization) | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS. | 1 | BUNCOMBE | 13 | French Broad River MPO |  | Not Funded |  | NHP | CONSTRUCTION | 261701000 | [11 empty] | 261701000
I-2513D | Highway | STI (Prioritization) | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET). | 1.44 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | Division 13 |  | BGANY | RIGHT-OF-WAY | 24900000 | FY 2025: 8715000; FY 2026: 8715000; FY 2027: 2490000; FY 2028: 2490000
I-2513D | Highway | STI (Prioritization) | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET). | 1.44 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | Division 13 |  | BGANY | UTILITIES | 3300000 | FY 2025: 1485000; FY 2026: 1485000; FY 2027: 165000
I-2513D | Highway | STI (Prioritization) | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET). | 1.44 | BUNCOMBE | 13 | French Broad River MPO | TO BE LET WITH I-2513B. | Division 13 |  | BGANY | CONSTRUCTION | 21600000 | FY 2025: 11481000; FY 2026: 5952000; FY 2027: 456000
I-2808 | Highway | Interstate Maintenance | I-77 | SOUTH OF SR 1125 (MILE MARKER 71) IN YADKIN COUNTY TO US 21 BYPASS (MILE MARKER 83.5) IN SURRY COUNTY (EXIT 83). PAVEMENT REHABILITATION. | 12 | YADKIN, SURRY | 11 | Northwest Piedmont RPO | SECTION A - GARVEE BOND FUNDING $35 MILLION; PAYBACK FY 2007 - FY 2018. SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
I-2808A | Highway | Pre-STI (Historic) | I-77 | SOUTH OF SR 1125 (ASHBURY CHURCH ROAD-MILEPOST 71) TO US 21 IN YADKIN COUNTY (EXIT 79) | 6.592 | YADKIN | 11 | Northwest Piedmont RPO | COMPLETE | Pre-STI (Transition)
I-2808B | Highway | Interstate Maintenance | I-77 | US 21 IN YADKIN COUNTY (EXIT 79) TO US 21 BYPASS (EXIT 83) IN SURRY COUNTY | 0 | YADKIN, SURRY | 11 | Northwest Piedmont RPO | SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
I-3306 | Highway | STI (Prioritization) | I-40 | I-85 IN ORANGE COUNTY TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM COUNTY. WIDEN TO SIX LANES AND INSTALL ITS. | 20.7 | ORANGE, DURHAM | 5, 7 | Durham-Chapel Hill-Carrboro MPO
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 11.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 10724000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 11.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | NHP | UTILITIES | 628000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 11.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | NHP | GARVEE CON | 65637000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4373000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 11.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | NHP | CONSTRUCTION | 220928000 | FY 2025: 54202000
I-3306A | Highway | STI (Prioritization) | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | 11.73 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 | Statewide Mobility |  | T(M) | CONSTRUCTION | 17000000
I-3306AC | Highway | STI (Prioritization) | I-40 | NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTIONS FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | 0.47 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | NHP | RIGHT-OF-WAY | 1400000 | FY 2025: 1400000
I-3306AC | Highway | STI (Prioritization) | I-40 | NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTIONS FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | 0.47 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | NHP | UTILITIES | 670000 | FY 2025: 670000
I-3306AC | Highway | STI (Prioritization) | I-40 | NC 86 INTERSECTION. UPGRADE TO A REDUCED CONFLICT INTERSECTIONS FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | 0.47 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | NHP | CONSTRUCTION | 8900000 | FY 2026: 1780000; FY 2027: 3560000; FY 2028: 3560000
I-3306AD | Highway | STI (Prioritization) | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. TOWING CONTRACT FOR I-3306A CONSTRUCTION. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | CONSTRUCTION | 2280000
I-3306B | Highway | Pre-STI (Historic) | I-40 | ORANGE COUNTY LINE TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM | 10.626 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | COMPLETE
I-3318 | Highway | Interstate Maintenance | I-95 | US 70 (EXIT 97) TO US 301 (EXIT 107). PAVEMENT AND BRIDGE REHABILITATION. | 10.7 | JOHNSTON | 4 | Upper Coastal Plain RPO
I-3318A | Highway | Interstate Maintenance | I-95 | US 70 (EXIT 97) TO NORTH OF SR 1001 (MILE MARKER 100). | 2.859 | JOHNSTON | 4 | Upper Coastal Plain RPO | COMPLETED.
I-3318BB | Highway | Transition | I-95 | REPLACE BRIDGE NO. 114 AND BRIDGE NO. 116 AND APPROACHES OVER LITTLE RIVER. |  | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Pre-STI (Transition)
I-3802 | Highway | STI (Prioritization) | I-85 | NC 73 IN CABARRUS COUNTY (EXIT 55) TO US 29 / US 601 CONNECTOR (EXIT 68) IN ROWAN COUNTY. WIDEN TO EIGHT LANES. | 13.6 | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | PROJECT COMPLETED. SEGMENT B INCLUDES B-5365 AND I-3610
I-3802A | Highway | Transition | I-85 | NC 73 IN CABARRUS COUNTY (EXIT 55) TO SR 2180 (LANE STREET) IN CABARRUS COUNTY. | 7.35 | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition)
I-3802AA | Highway | Pre-STI (Historic) | I-85 | ITS FOR I-3802 A | 7.35 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | CMAQ | CONSTRUCTION | 498000
I-3802AA | Highway | Pre-STI (Historic) | I-85 | ITS FOR I-3802 A | 7.35 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | CRPDA | CONSTRUCTION | 972000
I-3802AA | Highway | Pre-STI (Historic) | I-85 | ITS FOR I-3802 A | 7.35 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | CRPDA | CONSTRUCTION | 548000
I-3802AA | Highway | Pre-STI (Historic) | I-85 | ITS FOR I-3802 A | 7.35 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 137000
I-3802AA | Highway | Pre-STI (Historic) | I-85 | ITS FOR I-3802 A | 7.35 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 125000
I-3802AA | Highway | Pre-STI (Historic) | I-85 | ITS FOR I-3802 A | 7.35 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE | Pre-STI (Transition) |  | T(M) | CONSTRUCTION | 243000
I-3802B | Highway | STI (Prioritization) | I-85 | SR 2180 (LANE STREET) IN CABARRUS COUNTY TO US 29 / US 601 CONNECTOR IN ROWAN COUNTY | 6.49 | ROWAN | 9 | Cabarrus-Rowan MPO | COMPLETE - DESIGN-BUILD PROJECT | Statewide Mobility
I-3803B | Highway | Pre-STI (Historic) | I-85 | SOUTH OF SR 2894 (CONCORD MILLS - BRUTON SMITH BOULEVARD) TO NC 73 IN CABARRUS COUNTY. WIDEN TO 8-LANES. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | Pre-STI (Transition) |  | NHP | GARVEE CON | 22592000
I-3803BA | Highway | Transition | I-85 | ITS FOR I-3803B |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Pre-STI (Transition)
I-3804 | Highway | STI (Prioritization) | I-85 | SR 1221 (OLD BEATTY FORD ROAD) NEAR LANDIS. CONVERT GRADE SEPARATION TO INTERCHANGE. | 1 | ROWAN | 9 | Cabarrus-Rowan MPO | INCLUDED IN I-3802B - DESIGN-BUILD PROJECT | Division 9
I-3819 | Highway | STI (Prioritization) | I-40/I-77 | STATESVILLE, MODIFICATION OF I-40/I-77 INTERCHANGE AREA. | 1 | IREDELL | 12 | Charlotte Regional TPO | GARVEE BOND FUNDING - SEGMENT A: $10M FOR CONSTRUCTION, PAYBACK FY 2012-2023
I-3819A | Highway | Pre-STI (Historic) | I-40/I-77 | INITIAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 1 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE. SEE PARENT PROJECT FOR GARVEE DETAILS. | Pre-STI (Transition) |  | NHP | GARVEE CON | 4388000
I-3819B | Highway | STI (Prioritization) | I-40/I-77 | FINAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 1 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | RIGHT-OF-WAY | 840000 | FY 2025: 840000
I-3819B | Highway | STI (Prioritization) | I-40/I-77 | FINAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 1 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | BUILD NC CON | 142590000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000 | 9506000
I-3819B | Highway | STI (Prioritization) | I-40/I-77 | FINAL I-40/I-77 INTERCHANGE IMPROVEMENTS | 1 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Statewide Mobility |  | T | CONSTRUCTION | 217775000
I-4400 | Highway | STI (Prioritization) | I-26 | US 25 TO NC 280. WIDEN TO ADD ADDITIONAL LANES. | 13.6 | HENDERSON, BUNCOMBE | 13, 14 | French Broad River MPO
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 TO US 64 | 4.64 | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 1600000 | [11 empty] | 1600000
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 TO US 64 | 4.64 | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | NHP | UTILITIES | 500000 | [11 empty] | 500000
I-4400A | Highway | STI (Prioritization) | I-26 | US 25 TO US 64 | 4.64 | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | NHP | CONSTRUCTION | 114800000 | [11 empty] | 114800000
I-4400BA | Highway | STI (Prioritization) | I-26 | US 64 INTERCHANGE IMPROVEMENTS | 1 | HENDERSON | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 400000
I-4400BA | Highway | STI (Prioritization) | I-26 | US 64 INTERCHANGE IMPROVEMENTS | 1 | HENDERSON | 14 | French Broad River MPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 143200000
I-4400BB | Highway | STI (Prioritization) | I-26 | US 64 TO US 25 BUSINESS | 5.73 | HENDERSON | 14 | French Broad River MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $43,911,307 FOR CONSTRUCTION, PAYBACK FY 2019-2033 | Statewide Mobility |  | NHP | GARVEE CON | 52752000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000 | 3768000
I-4400C | Highway | STI (Prioritization) | I-26 | US 25 BUSINESS TO NC 280 | 3.29 | HENDERSON, BUNCOMBE | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035 | Region G |  | NHP | GARVEE CON | 36036000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000 | 2574000
I-4400C | Highway | STI (Prioritization) | I-26 | US 25 BUSINESS TO NC 280 | 3.29 | HENDERSON, BUNCOMBE | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035 | Region G |  | NHP | GARVEE CON | 25740000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000
I-4409 | Highway | STI (Prioritization) | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40 / SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 1 | BUNCOMBE | 13 | French Broad River MPO | NC BUILD BOND FUNDING: $15M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE) | Division 13 |  | NHP | RIGHT-OF-WAY | 6300000 | FY 2025: 3360000; FY 2026: 630000; FY 2027: 630000
I-4409 | Highway | STI (Prioritization) | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40 / SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 1 | BUNCOMBE | 13 | French Broad River MPO | NC BUILD BOND FUNDING: $15M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE) | Division 13 |  | NHP | UTILITIES | 900000 | FY 2025: 450000
I-4409 | Highway | STI (Prioritization) | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40 / SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 1 | BUNCOMBE | 13 | French Broad River MPO | NC BUILD BOND FUNDING: $15M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE) | Division 13 |  | T | BUILD NC CON | 22875000 |  |  | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 9150000
I-4409 | Highway | STI (Prioritization) | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40 / SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713 (SOUTH BLUE RIDGE ROAD). | 1 | BUNCOMBE | 13 | French Broad River MPO | NC BUILD BOND FUNDING: $15M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE) | Division 13 |  | T | CONSTRUCTION | 19100000 | FY 2026: 4113000; FY 2027: 532000; FY 2028: 11051000; FY 2029: 3404000
I-4700 | Highway | STI (Prioritization) | I-26 | NC 280 (EXIT 40) TO I-40 AT ASHEVILLE. ADD ADDITIONAL LANES. | 9.32 | BUNCOMBE, HENDERSON | 13, 14 | French Broad River MPO | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033 | Statewide Mobility |  | NHP | GARVEE CON | 62468000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000 | 4462000
I-4729 | Highway | STI (Prioritization) | I-26 | US 74/NC 108 INTERCHANGE (EXIT 67). REVISE INTERCHANGE AND CONSTRUCT IMPROVEMENTS TO NC 108. |  | POLK | 14 | Foothills RPO
I-4729A | Highway | STI (Prioritization) | I-26 | REVISE THE I-26/US 74/NC 108 INTERCHANGE. CONSTRUCT RAMPS FROM I-26 WESTBOUND TO US 74 EASTBOUND, AND FROM US 74 WESTBOUND TO I-26 EASTBOUND. | 1 | POLK | 14 | Foothills RPO | COMPLETE | Region G
I-4729B | Highway | STI (Prioritization) | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. |  | POLK | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | T | RIGHT-OF-WAY | 10200000 | FY 2030: 1250000; FY 2031: 2500000; FY 2032: 1250000
I-4729B | Highway | STI (Prioritization) | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. |  | POLK | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | T | UTILITIES | 2000000 | FY 2030: 1000000
I-4729B | Highway | STI (Prioritization) | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. |  | POLK | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | T | CONSTRUCTION | 33600000 | FY 2033: 6384000; FY 2034: 16464000; FY 2035: 10752000
I-4739 | Highway | STI (Prioritization) | I-40 | ACCESS IMPROVEMENTS IN THE VICINITY OF EXISTING I-40/NC 42 INTERCHANGE (EXIT 312). | 1 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033. | Statewide Mobility |  | NHP | GARVEE ROW | 19305000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000 | 1287000
I-4739 | Highway | STI (Prioritization) | I-40 | ACCESS IMPROVEMENTS IN THE VICINITY OF EXISTING I-40/NC 42 INTERCHANGE (EXIT 312). | 1 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK FY 2019 - 2033. | Statewide Mobility |  | NHP | CONSTRUCTION | 40137000
I-4744 | Highway | Pre-STI (Historic) | I-40 | SR 1728 (WADE AVENUE) TO I-440 / US 1 / US 64. WIDEN TO SIX LANES. | 4 | WAKE | 5 | Capital Area MPO | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020 | Pre-STI (Transition) |  | NHP | GARVEE CON | 4635000
I-4759 | Highway | STI (Prioritization) | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 1.52 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGANY | GARVEE ROW | 1582000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000
I-4759 | Highway | STI (Prioritization) | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 1.52 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGANY | RIGHT-OF-WAY | 10000000
I-4759 | Highway | STI (Prioritization) | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 1.52 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGDA | RIGHT-OF-WAY | 4000000
I-4759 | Highway | STI (Prioritization) | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 1.52 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGANY | UTILITIES | 700000
I-4759 | Highway | STI (Prioritization) | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 (MONTE VISTA ROAD) AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | 1.52 | BUNCOMBE | 13 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033 | Statewide Mobility |  | BGANY | CONSTRUCTION | 88899000 | FY 2030: 7776000; FY 2031: 28618000; FY 2032: 25376000; FY 2033: 18776000; FY 2034: 8353000
I-4759A | Highway | STI (Prioritization) | I-40, SR 1228 (LIBERTY ROAD) | CLEARING ONLY. |  | BUNCOMBE | 13 | French Broad River MPO |  | Statewide Mobility |  | BGANY | CONSTRUCTION | 500000 | FY 2029: 500000
I-4906 | Highway | Pre-STI (Historic) | I-95 | CUMBERLAND COUNTY LINE TO THE JOHNSTON COUNTY LINE. PAVEMENT REPAIR. | 8.8 | HARNETT | 6 | Mid-Carolina RPO | COMPLETED. GARVEE BOND FUNDING $3.15 MILLION; PAYBACK FY 2008 - FY 2019. | Pre-STI (Transition)
I-5000 | Highway | STI (Prioritization) | I-85 | I-85/US 321. GEOMETRIC SAFETY IMPROVEMENTS TO INTERCHANGE. | 0.17 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | Statewide Mobility
I-5106 | Highway | Pre-STI (Historic) | I-77 | MILE MARKER 57.83 TO MILE POST 61.74. PAVEMENT REHABILITATION. | 3.9 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020 | Pre-STI (Transition) |  | NHP | GARVEE CON | 439000
I-5110 | Highway | Transition | FUTURE I-73 | NC 68 TO GREENSBORO WESTERN LOOP. SIX-LANE FREEWAY ON NEW LOCATION. | 3 | GUILFORD | 7 | Greensboro Urban Area MPO | COMBINED WITH R-2413A AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION | Pre-STI (Transition)
I-5111 | Highway | STI (Prioritization) | I-40 | I-440 / US 64 (EXIT 301) TO NC 42 (EXIT 312). ADD 2 GENERAL-PURPOSE LANES IN EACH DIRECTION. | 10.71 | WAKE, JOHNSTON | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. GARVEE BOND FUNDING: $15M FOR RIGHT-OF-WAY, PAYBACK 2019-2033.
I-5111REG | Highway | STI (Prioritization) | I-40 | WAKE COUNTY LINE TO NC 42. | 1.55 | JOHNSTON | 4 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region A |  | NHP | GARVEE ROW | 3479000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000 | 232000
I-5111REG | Highway | STI (Prioritization) | I-40 | WAKE COUNTY LINE TO NC 42. | 1.55 | JOHNSTON | 4 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region A |  | NHP | CONSTRUCTION | 23795000
I-5111SW | Highway | STI (Prioritization) | I-40 | I-440 / US 64 (EXIT 301) TO JOHNSTON COUNTY LINE. | 9.18 | WAKE | 5 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Statewide Mobility |  | NHP | GARVEE ROW | 15826000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000 | 1055000
I-5111SW | Highway | STI (Prioritization) | I-40 | I-440 / US 64 (EXIT 301) TO JOHNSTON COUNTY LINE. | 9.18 | WAKE | 5 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Statewide Mobility |  | NHP | CONSTRUCTION | 108398000
I-5111SW | Highway | STI (Prioritization) | I-40 | I-440 / US 64 (EXIT 301) TO JOHNSTON COUNTY LINE. | 9.18 | WAKE | 5 | Capital Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Statewide Mobility |  | NHP | CONSTRUCTION | 20000000
I-5504 | Highway | STI (Prioritization) | I-26 | NC 191 (BREVARD ROAD). UPGRADE INTERCHANGE. | 1 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION AS DESIGN-BUILD PROJECT | Statewide Mobility
I-5506 | Highway | STI (Prioritization) | I-40 | SR 1002 (AVIATION PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 1002 TO SR 3015 (AIRPORT BOULEVARD). | 1 | WAKE | 5 | Capital Area MPO | PROJECT COMPLETE. | Statewide Mobility
I-5507 | Highway | STI (Prioritization) | I-485 | I-485, I-77 SOUTH OF CHARLOTTE TO US 74 (INDEPENDENCE BOULEVARD). ADD ONE EXPRESS LANE IN EACH DIRECTION. TOLL PROJECT. | 16.62 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT | Statewide Mobility |  | T | CONSTRUCTION | 458656000 | FY 2025: 54000000
I-5700 | Highway | STI (Prioritization) | I-40 | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | 2.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | Statewide Mobility |  | NHP | GARVEE CON | 12870000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000
I-5700 | Highway | STI (Prioritization) | I-40 | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | 2.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | Statewide Mobility |  | NHP | CONSTRUCTION | 35530000
I-5700 | Highway | STI (Prioritization) | I-40 | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BOULEVARD) TO I-540. | 2.5 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 3333000
I-5701 | Highway | STI (Prioritization) | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | 4.44 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703. | Statewide Mobility |  | NHP | UTILITIES | 3400000 | FY 2027: 1700000; FY 2028: 1700000
I-5701 | Highway | STI (Prioritization) | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | 4.44 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703. | Statewide Mobility |  | NHP | CONSTRUCTION | 161000000 | FY 2027: 8050000; FY 2028: 38237000; FY 2029: 38237000; FY 2030: 38238000; FY 2031: 38238000
I-5703 | Highway | STI (Prioritization) | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 35000000 | FY 2027: 3500000; FY 2028: 12250000; FY 2029: 12250000; FY 2030: 3500000; FY 2031: 3500000
I-5703 | Highway | STI (Prioritization) | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | UTILITIES | 7200000 | FY 2027: 2400000; FY 2028: 2400000; FY 2029: 2400000
I-5703 | Highway | STI (Prioritization) | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | GARVEE CON | 152505000 |  |  |  |  | 10167000 | 10167000 | 10167000 | 10167000 | 10167000 | 10167000 | 10167000 | 81336000
I-5703 | Highway | STI (Prioritization) | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | 1 | WAKE | 5 | Capital Area MPO | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701; GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | CONSTRUCTION | 170191000 | FY 2027: 13500000; FY 2028: 64173000; FY 2029: 0; FY 2030: 28345000; FY 2031: 64173000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (ALSTON AVENUE) TO I-885 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | 0.53 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 800000 | FY 2025: 800000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (ALSTON AVENUE) TO I-885 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | 0.53 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | UTILITIES | 190000 | FY 2025: 190000
I-5707 | Highway | STI (Prioritization) | I-40 | NC 55 (ALSTON AVENUE) TO I-885 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | 0.53 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 9299000 | FY 2027: 2195000; FY 2028: 5812000; FY 2029: 1292000
I-5708 | Highway | STI (Prioritization) | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 1 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | Statewide Mobility |  | NHP | GARVEE ROW | 1736000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000 | 124000
I-5708 | Highway | STI (Prioritization) | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 1 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | Statewide Mobility |  | NHP | UTILITIES | 2000000
I-5708 | Highway | STI (Prioritization) | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 1 | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033 | Statewide Mobility |  | NHP | CONSTRUCTION | 20580000 | FY 2026: 7695000; FY 2027: 10859000; FY 2028: 2026000
I-5711 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1007 (MEBANE-OAKS ROAD) IN MEBANE. INTERCHANGE IMPROVEMENTS. | 1 | ALAMANCE | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION; | Statewide Mobility |  | NHP | CONSTRUCTION | 9830000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 13900000 | FY 2028: 3753000; FY 2029: 6553000; FY 2030: 1390000; FY 2031: 1102000; FY 2032: 1102000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHP | UTILITIES | 1100000 | FY 2028: 550000; FY 2029: 550000
I-5712 | Highway | STI (Prioritization) | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 27600000 | FY 2031: 14440000; FY 2032: 10615000; FY 2033: 2545000
I-5714 | Highway | STI (Prioritization) | I-77 | SR 2136 (GILEAD ROAD) INTERCHANGE. UPGRADE EXISTING INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Statewide Mobility
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 19000000 | FY 2025: 7019000; FY 2026: 1899000; FY 2027: 1899000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | UTILITIES | 3000000
I-5715 | Highway | STI (Prioritization) | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 79901000 | FY 2027: 27096000; FY 2028: 28090000; FY 2029: 16450000; FY 2030: 8265000
I-5716 | Highway | STI (Prioritization) | I-40 | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 1 | CATAWBA | 12 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS | Statewide Mobility |  | NHP | CONSTRUCTION | 12300000 | FY 2026: 2348000; FY 2027: 7544000; FY 2028: 2408000
I-5718 | Highway | STI (Prioritization) | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT I-277 INTERCHANGES. TOLL PROJECT. | 11.2 | MECKLENBURG | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 1508000000 | FY 2029: 1508000000
I-5718 | Highway | STI (Prioritization) | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT I-277 INTERCHANGES. TOLL PROJECT. | 11.2 | MECKLENBURG | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | BOND R | UTILITIES | 42000000 | FY 2029: 42000000
I-5718 | Highway | STI (Prioritization) | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT I-277 INTERCHANGES. TOLL PROJECT. | 11.2 | MECKLENBURG | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | NHP | GARVEE CON | 91497000 | FY 2033: 10167000; FY 2034: 10167000; FY 2035: 10167000 | 60996000
I-5718 | Highway | STI (Prioritization) | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT I-277 INTERCHANGES. TOLL PROJECT. | 11.2 | MECKLENBURG | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | NHP | GARVEE CON | 152505000 | FY 2035: 10167000 | 142338000
I-5718 | Highway | STI (Prioritization) | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT I-277 INTERCHANGES. TOLL PROJECT. | 11.2 | MECKLENBURG | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | NHP | GARVEE CON | 101665000 | FY 2031: 10167000; FY 2032: 10167000; FY 2033: 10167000; FY 2034: 10167000; FY 2035: 10167000 | 50830000
I-5718 | Highway | STI (Prioritization) | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT I-277 INTERCHANGES. TOLL PROJECT. | 11.2 | MECKLENBURG | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | NHP | CONSTRUCTION | 300000000 | FY 2031: 0; FY 2032: 100000000; FY 2033: 0; FY 2034: 100000000; FY 2035: 0 | 100000000
I-5718 | Highway | STI (Prioritization) | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES AND RECONSTRUCT I-277 INTERCHANGES. TOLL PROJECT. | 11.2 | MECKLENBURG | 10 | Charlotte Regional TPO | GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK FY 2031-2045; $100M FOR CONSTRUCTION, PAYBACK FY 2033-2047; $100M FOR CONSTRUCTION, PAYBACK FY 2035-2049. | Statewide Mobility |  | BOND R | CONSTRUCTION | 2058900000 | FY 2029: 2058900000
I-5719 | Highway | STI (Prioritization) | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | 9.8 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS). DP FUNDING REPRESENTS FEDERAL 2022 INFRA GRANT. | Statewide Mobility
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). WIDEN TO EIGHT LANES. | 6.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 50438000 | FY 2029: 5044000; FY 2030: 17653000; FY 2031: 17653000; FY 2032: 5044000; FY 2033: 5044000
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). WIDEN TO EIGHT LANES. | 6.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | UTILITIES | 12300000 | FY 2029: 3690000; FY 2030: 6765000; FY 2031: 1845000
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). WIDEN TO EIGHT LANES. | 6.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | GARVEE CON | 304995000 |  |  |  |  | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 162664000
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). WIDEN TO EIGHT LANES. | 6.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | NHP | CONSTRUCTION | 210808000 | FY 2029: 0; FY 2030: 54082000; FY 2031: 95800000; FY 2032: 36016000; FY 2033: 24910000
I-5719A | Highway | STI (Prioritization) | I-85 | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). WIDEN TO EIGHT LANES. | 6.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2029-2043. | Statewide Mobility |  | T | CONSTRUCTION | 87394000 | FY 2029: 0; FY 2030: 0; FY 2031: 43697000; FY 2032: 43697000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | DP | RIGHT-OF-WAY | 15000000 | FY 2025: 1899000; FY 2026: 6645000; FY 2027: 6456000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 4982000 | FY 2025: 0; FY 2026: 0; FY 2027: 236000; FY 2028: 2373000; FY 2029: 2373000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | T(M) | RIGHT-OF-WAY | 3750000 | FY 2025: 475000; FY 2026: 1661000; FY 2027: 1614000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | DP | UTILITIES | 15000000 | FY 2025: 11496000; FY 2026: 3504000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | NHP | UTILITIES | 29150000 | FY 2025: 0; FY 2026: 21965000; FY 2027: 7185000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | T(M) | UTILITIES | 3750000 | FY 2025: 2874000; FY 2026: 876000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | NHP | GARVEE CON | 304995000 |  |  | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 20333000 | 121998000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | DP | CONSTRUCTION | 52344000 | FY 2025: 25312000; FY 2026: 27032000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | NHP | CONSTRUCTION | 130070000 | FY 2025: 0; FY 2026: 92770000; FY 2027: 0; FY 2028: 0; FY 2029: 37300000
I-5719B | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. WIDEN TO EIGHT LANES. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. GARVEE BOND FUNDING: $200M FOR CONSTRUCTION, PAYBACK FY 2027-2041. | Statewide Mobility |  | T(M) | CONSTRUCTION | 13086000 | FY 2025: 6328000; FY 2026: 6758000
I-5719C | Highway | STI (Prioritization) | I-85 | RECONSTRUCTION OF THE PIEDMONT NORTHERN RAILROAD BRIDGE, TWO NORFOLK SOUTHERN RAILROAD BRIDGES, AND SR 2213 (GROVE STREET) BRIDGE WITHIN THE LIMITS OF SECTION A. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 3531000 | FY 2026: 353000; FY 2027: 1236000; FY 2028: 1236000; FY 2029: 353000; FY 2030: 353000
I-5719C | Highway | STI (Prioritization) | I-85 | RECONSTRUCTION OF THE PIEDMONT NORTHERN RAILROAD BRIDGE, TWO NORFOLK SOUTHERN RAILROAD BRIDGES, AND SR 2213 (GROVE STREET) BRIDGE WITHIN THE LIMITS OF SECTION A. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T | UTILITIES | 2600000 | FY 2026: 650000; FY 2027: 1300000; FY 2028: 650000
I-5719C | Highway | STI (Prioritization) | I-85 | RECONSTRUCTION OF THE PIEDMONT NORTHERN RAILROAD BRIDGE, TWO NORFOLK SOUTHERN RAILROAD BRIDGES, AND SR 2213 (GROVE STREET) BRIDGE WITHIN THE LIMITS OF SECTION A. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 23241000 | FY 2026: 1859000; FY 2027: 4416000; FY 2028: 5113000; FY 2029: 5578000; FY 2030: 6275000
I-5719C | Highway | STI (Prioritization) | I-85 | RECONSTRUCTION OF THE PIEDMONT NORTHERN RAILROAD BRIDGE, TWO NORFOLK SOUTHERN RAILROAD BRIDGES, AND SR 2213 (GROVE STREET) BRIDGE WITHIN THE LIMITS OF SECTION A. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 209159000 | FY 2026: 16733000; FY 2027: 39740000; FY 2028: 46015000; FY 2029: 50198000; FY 2030: 56473000
I-5719D | Highway | STI (Prioritization) | I-85 | IMPLEMENT FLOOD RISK, VULNERABILITY ASSESSMENT, AND FLOOD WARNING SYSTEM ALONG THE I-85 CORRIDOR. |  | GASTON, CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | IMPLEMENTATION | 160000 | FY 2025: 160000
I-5719D | Highway | STI (Prioritization) | I-85 | IMPLEMENT FLOOD RISK, VULNERABILITY ASSESSMENT, AND FLOOD WARNING SYSTEM ALONG THE I-85 CORRIDOR. |  | GASTON, CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | IMPLEMENTATION | 40000 | FY 2025: 40000
I-5719E | Highway | STI (Prioritization) | I-85 | INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR |  | GASTON, CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | ENGINEERING | 112000 | FY 2025: 112000
I-5719E | Highway | STI (Prioritization) | I-85 | INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR |  | GASTON, CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | ENGINEERING | 28000 | FY 2025: 28000
I-5719E | Highway | STI (Prioritization) | I-85 | INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR |  | GASTON, CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 448000 | FY 2025: 448000
I-5719E | Highway | STI (Prioritization) | I-85 | INSTALL ELECTRIC VEHICLE CHARGING PORTS ALONG THE I-85 CORRIDOR |  | GASTON, CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | CONSTRUCTION | 112000 | FY 2025: 112000
I-5719FA | Highway | STI (Prioritization) | I-85 | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT AND INCIDENT MANAGEMENT. | 6.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 3280000 | FY 2028: 3280000
I-5719FA | Highway | STI (Prioritization) | I-85 | US 321 TO NC 7 (MCADENVILLE ROAD / MAIN STREET). INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT AND INCIDENT MANAGEMENT. | 6.6 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | T(M) | CONSTRUCTION | 820000 | FY 2028: 820000
I-5719FB | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT AND INCIDENT MANAGEMENT. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 5720000 | FY 2025: 5720000
I-5719FB | Highway | STI (Prioritization) | I-85 | NC 7 (MCADENVILLE ROAD / MAIN STREET) TO NC 273. INSTALL AND IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM COMPONENTS INCLUDING ACTIVE TRAFFIC MANAGEMENT AND INCIDENT MANAGEMENT. | 3.4 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1430000 | FY 2025: 1430000
I-5719FC | Highway | STI (Prioritization) | I-85 | SOUTH CAROLINA STATE LINE TO US 74. INSTALL BROADBAND. | 9.5 | CLEVELAND, GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 5640000 | FY 2025: 5640000
I-5719FC | Highway | STI (Prioritization) | I-85 | SOUTH CAROLINA STATE LINE TO US 74. INSTALL BROADBAND. | 9.5 | CLEVELAND, GASTON | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1410000 | FY 2025: 1410000
I-5719FD | Highway | STI (Prioritization) | I-85 | SOUTH CAROLINA STATE LINE TO NC 273. IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM STATEWIDE RESILIENCE, CONNECTED VEHICLE TECHNOLOGY, AND TRAVELER INFORMATION. | 26.8 | GASTON, CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 5576000 | FY 2025: 5576000
I-5719FD | Highway | STI (Prioritization) | I-85 | SOUTH CAROLINA STATE LINE TO NC 273. IMPLEMENT INTELLIGENT TRANSPORTATION SYSTEM STATEWIDE RESILIENCE, CONNECTED VEHICLE TECHNOLOGY, AND TRAVELER INFORMATION. | 26.8 | GASTON, CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS 2022 INFRA GRANT. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1394000 | FY 2025: 1394000
I-5740 | Highway | Interstate Maintenance | I-85 | SR 2205 (OLD US 64) TO 0.4 MILES NORTH OF US 64. PAVEMENT REHABILITATION. | 2.6 | DAVIDSON | 9 | High Point Urban Area MPO | COMPLETE | Statewide Mobility
I-5740A | Highway | Bridges | I-85 | REHABILITATE BRIDGE 280181 AND BRIDGE 280182. | 0.25 | DAVIDSON | 9 | High Point Urban Area MPO | COMPLETE | Statewide Mobility
I-5746 | Highway | Interstate Maintenance | I-277 | I-77 TO EAST 10TH STREET. RESURFACING AND BRIDGE REHABILITATION. | 3.5 | MECKLENBURG | 10 | Charlotte Regional TPO
I-5746A | Highway | Interstate Maintenance | I-277 (BELK FREEWAY) | I-77 TO EAST STONEWALL STREET. BRIDGE REHABILITATION. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE | Statewide Mobility
I-5746B | Highway | Interstate Maintenance | I-277 (BELK FREEWAY) | EAST STONEWALL STREET TO EAST 10TH STREET. BRIDGE REHABILITATION. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE | Statewide Mobility
I-5746C | Highway | Interstate Maintenance | I-277 (BROOKSHIRE FREEWAY) | I-77 TO EAST 10TH STREET. RESURFACE ROADWAY AND REHABILITATE BRIDGES FROM JOHNSON STREET TO EAST 10TH STREET. | 1.75 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 29400000
I-5769 | Highway | Interstate Maintenance | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | GARVEE CON | 3915000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000 | 261000
I-5769 | Highway | Interstate Maintenance | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 300000
I-5769 | Highway | Interstate Maintenance | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1875000
I-5769 | Highway | Interstate Maintenance | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 240000
I-5769 | Highway | Interstate Maintenance | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 60000
I-5769 | Highway | Interstate Maintenance | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 10069000
I-5769 | Highway | Interstate Maintenance | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 60000
I-5769 | Highway | Interstate Maintenance | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | 1.11 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 1013000
I-5786 | Highway | Interstate Maintenance | I-95 | SOUTH OF SR 1001 (LIZZIE MILL ROAD) TO THE JOHNSTON/WILSON COUNTY LINE NORTH OF NC 222. PAVEMENT REHABILITATION. | 11.75 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility
I-5786A | Highway | Interstate Maintenance | I-95 | REPLACE BRIDGE 500117 ON SR 2399 (TRUCK STOP ROAD) OVER I-95 AND ADJUST SERVICE ROADS AND APPROACHES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Statewide Mobility
I-5795 | Highway | Interstate Maintenance | I-40 | 0.3 MILE EAST OF SR 3153 (HANES MALL BOULEVARD) TO 0.9 MILE EAST OF NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM AND SR 2747 (CLEMMONSVILLE ROAD) IN WINSTON-SALEM TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION AND REHABILITATION OF BRIDGES 330161, 330162, 330444, 330448, 330449,330508, AND 330509. | 13.66 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHFP | CONSTRUCTION | 11318000
I-5795 | Highway | Interstate Maintenance | I-40 | 0.3 MILE EAST OF SR 3153 (HANES MALL BOULEVARD) TO 0.9 MILE EAST OF NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM AND SR 2747 (CLEMMONSVILLE ROAD) IN WINSTON-SALEM TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION AND REHABILITATION OF BRIDGES 330161, 330162, 330444, 330448, 330449,330508, AND 330509. | 13.66 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 12496000
I-5796 | Highway | Interstate Maintenance | I-85 | 0.1 MILE NORTH OF SR 5901 (BILLY GRAHAM PKWY) TO 0.3 MILE SOUTH OF NC 16 AT MILE MARKER 35.93. PAVEMENT REHABILITATION. | 2.92 | MECKLENBURG | 10 | Charlotte Regional TPO | TO BE LET WITH I-5770 - UNDER CONSTRUCTION | Statewide Mobility
I-5805 | Highway | Interstate Maintenance | I-40 | SR 2158 (OLD MOCKSVILLE ROAD) TO DAVIE COUNTY LINE. PAVEMENT REHABILITATION. | 8.26 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 70501000 | FY 2030: 17543000; FY 2031: 23670000; FY 2032: 17603000; FY 2033: 11685000
I-5821 | Highway | Interstate Maintenance | I-85 | RANDOLPH COUNTY LINE TO SR 1113 (KIVETT DRIVE). PAVEMENT REHABILITATION. | 4.5 | GUILFORD | 7 | High Point Urban Area MPO | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789 | Statewide Mobility
I-5826 | Highway | Interstate Maintenance | I-85 | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | 13.93 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | GARVEE CON | 2580000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000 | 172000
I-5826 | Highway | Interstate Maintenance | I-85 | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | 13.93 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 5694000
I-5826 | Highway | Interstate Maintenance | I-85 | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | 13.93 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION - I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 666000
I-5828 | Highway | Interstate Maintenance | I-485 | I-77 TO NC 49. PAVEMENT REHABILITATION. REHABILITATE BRIDGES 590661, 590662, 590663, 590664, AND 590643. | 56.03 | MECKLENBURG | 10 | Charlotte Regional TPO | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS | Statewide Mobility |  | NHPIM | CONSTRUCTION | 9050000 | FY 2029: 6091000; FY 2030: 2959000
I-5828 | Highway | Interstate Maintenance | I-485 | I-77 TO NC 49. PAVEMENT REHABILITATION. REHABILITATE BRIDGES 590661, 590662, 590663, 590664, AND 590643. | 56.03 | MECKLENBURG | 10 | Charlotte Regional TPO | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS | Statewide Mobility |  | HFB | CONSTRUCTION | 2900000 | FY 2029: 1952000; FY 2030: 948000
I-5829 | Highway | Interstate Maintenance | I-77 | MILE MARKER 91 TO MILE MARKER 95. PAVEMENT REHABILITATION. | 4.39 | SURRY | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION
I-5829A | Highway | Interstate Maintenance | I-77 | MILE MARKER 91 TO MILE MARKER 95. DIAMOND GRINDING | 4.39 | SURRY | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 3600000
I-5831 | Highway | Interstate Maintenance | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. PAVEMENT AND BRIDGE REHABILITATION. | 9 | MADISON | 13 | Land-of-Sky RPO
I-5831A | Highway | Interstate Maintenance | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. REPLACE CURB AND DRAINAGE BOXES, AND REHABILITATE BRIDGES. | 9.04 | MADISON | 13 | Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 10054000
I-5831B | Highway | Interstate Maintenance | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. REHABILITATE PAVEMENT. | 9.04 | MADISON | 13 | Land-of-Sky RPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 18900000 | FY 2025: 6237000; FY 2026: 10584000; FY 2027: 2079000
I-5834 | Highway | Interstate Maintenance | I-40 | MILE MARKER 27 TO MILE MARKER 34. PAVEMENT REHABILITATION. | 7 | HAYWOOD | 14 | French Broad River MPO, Land-of-Sky RPO | 6-13-2022: $2.566M IN NHPIM FUNDS SWITCHED WITH $2.566M IN BGDA AS PART OF FUND SWAP.
I-5834A | Highway | Interstate Maintenance | I-40 | MILE MARKER 27 TO MILE MARKER 30. PAVEMENT REHABILITATION. | 3 | HAYWOOD | 14 | French Broad River MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4733000
I-5834A | Highway | Interstate Maintenance | I-40 | MILE MARKER 27 TO MILE MARKER 30. PAVEMENT REHABILITATION. | 3 | HAYWOOD | 14 | French Broad River MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 2566000
I-5834B | Highway | Interstate Maintenance | I-40 | MILE MARKER 30 TO MILE MARKER 34. PAVEMENT REHABILITATION. | 4 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13475000
I-5834B | Highway | Interstate Maintenance | I-40 | MILE MARKER 30 TO MILE MARKER 34. PAVEMENT REHABILITATION. | 4 | HAYWOOD | 14 | French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | PROTCT | CONSTRUCTION | 483000
I-5838 | Highway | Interstate Maintenance | I-85 | REHABIILITATE BRIDGES 590203 (I-85 NB) AND 590204 (I-85 SB) OVER SEABOARD COASTLINE RAILROAD. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1031000
I-5850 | Highway | Interstate Maintenance | I-95 | NORTH OF US 301 (MILE MARKER 22) TO CUMBERLAND COUNTY LINE (MILE MARKER 40). PAVEMENT REHABILITATION. | 15.7 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO |  | Statewide Mobility
I-5850A | Highway | Interstate Maintenance | I-95 | BRIDGE REHABILITATION, MEDIAN DRAINAGE, AND CONTROL OF ACCESS FENCE. | 17.99 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | COMPLETED. | Statewide Mobility
I-5850B | Highway | Interstate Maintenance | I-95 | PAVEMENT REHABILITATION. | 18.97 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. | Statewide Mobility
I-5852 | Highway | Interstate Maintenance | I-73 | I-85 TO SR 2085 (BRYAN BOULEVARD) IN GREENSBORO. PAVEMENT AND BRIDGE REHABILITATION. | 10.7 | GUILFORD | 7 | Greensboro Urban Area MPO
I-5852A | Highway | Interstate Maintenance | I-73 / US 421 | I-85 TO I-40 | 6.62 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility
I-5852B | Highway | Interstate Maintenance | I-73 / I-840 | I-40 TO SR 2085 (BRYAN BOULEVARD) | 3.26 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility
I-5858 | Highway | Interstate Maintenance | I-85 | US 29 / US 601 IN CHINA GROVE TO US 601 (JAKE ALEXANDER BOULEVARD) IN SALISBURY AND FROM SOUTH OF US 52 IN SALISBURY TO NORTH OF SR 2120 (LONG FERRY ROAD) IN SPENCER. PAVEMENT REHABILITATION. | 1.08 | ROWAN | 9 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033 | Statewide Mobility |  | NHPIM | GARVEE CON | 12012000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000 | 858000
I-5861 | Highway | Interstate Maintenance | I-485 | PAVEMENT AND BRIDGE REHABILITATION AT OAKDALE ROAD INTERCHANGE AT MILEMARKER 17.2. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1256000
I-5864 | Highway | Interstate Maintenance | I-77 | MILEMARKER 71.8 TO MILEMARKER 75.8. PAVEMENT REHABILITATION. | 2.08 | YADKIN | 11 | Northwest Piedmont RPO | COMBINE WITH I-5865 FOR LETTING. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6285000 | FY 2028: 2453000; FY 2029: 3832000
I-5865 | Highway | Interstate Maintenance | I-77 | MILEMARKER 75.8 TO US 21 (EXIT 79). PAVEMENT REHABILITATION. | 1.89 | YADKIN | 11 | Northwest Piedmont RPO | COMBINE WITH I-5864 FOR LETTING. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2990000 | FY 2030: 1967000; FY 2031: 1023000
I-5873 | Highway | STI (Prioritization) | I-40 | NC 54 IN RALEIGH. INTERCHANGE IMPROVEMENTS. | 1 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Region C
I-5877 | Highway | STI (Prioritization) | I-95 | SR 1811 (BUD HAWKINS ROAD) (EXIT 70) AND SR 1001 (LONG BRANCH ROAD) (EXIT 71). IMPROVE INTERCHANGES. | 1 | HARNETT | 6 | Mid-Carolina RPO | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 3304000 | FY 2025: 1304000
I-5877 | Highway | STI (Prioritization) | I-95 | SR 1811 (BUD HAWKINS ROAD) (EXIT 70) AND SR 1001 (LONG BRANCH ROAD) (EXIT 71). IMPROVE INTERCHANGES. | 1 | HARNETT | 6 | Mid-Carolina RPO | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 69733000
I-5878 | Highway | STI (Prioritization) | I-95 | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). IMPROVE INTERCHANGES. | 1 | HARNETT | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 78860000 | FY 2025: 18199000; FY 2026: 14500000; FY 2027: 3770000
I-5878A | Highway | STI (Prioritization) | I-95 | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). CLEARING FOR UTILITIES. |  | HARNETT | 6 | Mid-Carolina RPO | COMPLETED. | Statewide Mobility |  | T | CONSTRUCTION | 139000
I-5879 | Highway | STI (Prioritization) | I-95 | SR 1536 (CARTHAGE ROAD/WEST CARTHAGE ROAD) (EXIT 19). IMPROVE INTERCHANGE. | 1 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C. | Division 6 |  | NHP | CONSTRUCTION | 15028000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | 1 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | NHP | RIGHT-OF-WAY | 3600000 | FY 2025: 576000; FY 2026: 360000; FY 2027: 360000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | 1 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | NHP | UTILITIES | 1400000
I-5880 | Highway | STI (Prioritization) | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | 1 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | NHP | CONSTRUCTION | 26600000 | FY 2025: 9926000; FY 2026: 11187000; FY 2027: 5487000
I-5883 | Highway | STI (Prioritization) | I-95 | SR 1808 (JONESBORO ROAD) (EXIT 75) AND SR 1709 (HODGES CHAPEL ROAD) (EXIT 77). IMPROVE INTERCHANGES. | 1 | HARNETT | 6 | Mid-Carolina RPO | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 100613000 | FY 2025: 41719000; FY 2026: 0; FY 2027: 4810000
I-5888 | Highway | Interstate Maintenance | I-40 | MILE MARKER 37 TO MILE MARKER 44. REHABILIATE PAVEMENT AND BRIDGES. | 6.5 | BUNCOMBE | 13 | French Broad River MPO |  | Statewide Mobility
I-5888A | Highway | Interstate Maintenance | I-40 | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE PAVEMENT AND BRIDGES. | 6.73 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE | Statewide Mobility
I-5888B | Highway | Interstate Maintenance | I-40 | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE BRIDGES. | 7.17 | BUNCOMBE | 13 | French Broad River MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6900000 | FY 2027: 4485000; FY 2028: 2415000
I-5889 | Highway | Interstate Maintenance | I-40 | MILE MARKER 44 TO MILE MARKER 50. REHABILTATE PAVEMENT AND PRESERVE BRIDGES. | 4 | BUNCOMBE | 13 | French Broad River MPO
I-5889A | Highway | Interstate Maintenance | I-40 | MILE MARKER 46 TO MILE MARKER 50. PRESERVE BRIDGES. | 4.65 | BUNCOMBE | 13 | French Broad River MPO | COMPLETED | Statewide Mobility
I-5889B | Highway | Interstate Maintenance | I-40 | MILE MARKER 44 TO MILE MARKER 50. REHABILITATE PAVEMENT AND PRESERVE BRIDGES 100352, 100356, 100344, 100347, 100339, AND 100334. | 4.62 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 32186000 | FY 2025: 6079000
I-5889B | Highway | Interstate Maintenance | I-40 | MILE MARKER 44 TO MILE MARKER 50. REHABILITATE PAVEMENT AND PRESERVE BRIDGES 100352, 100356, 100344, 100347, 100339, AND 100334. | 4.62 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 4000000
I-5890 | Highway | Interstate Maintenance | I-40 | MILEMARKER 55 TO MILEMARKER 67.5. PAVEMENT REHABILITATION. | 11.99 | BUNCOMBE | 13 | French Broad River MPO | COMPLETE - GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033. | Statewide Mobility |  | NHPIM | GARVEE CON | 23160000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000 | 1544000
I-5891 | Highway | Interstate Maintenance | I-40 | MILE MARKER 93 TO MILE MARKER 119. REHABILITATE PAVEMENT AND BRIDGES. | 23.92 | BURKE | 13 | Greater Hickory MPO
I-5891A | Highway | Interstate Maintenance | I-40 | MILE MARKER 93 TO MILE MARKER 119. REHABILITATE PAVEMENT. | 25.73 | BURKE | 13 | Greater Hickory MPO | COMPLETE | Statewide Mobility
I-5891B | Highway | Interstate Maintenance | I-40 | MILE MARKER 93 TO MILE MARKER 119. REHABILITATE BRIDGES. | 26.03 | BURKE | 13 | Greater Hickory MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4000000 | FY 2029: 2421000; FY 2030: 1579000
I-5898 | Highway | STI (Prioritization) | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | 1 | ROCKINGHAM | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | RIGHT-OF-WAY | 1500000
I-5898 | Highway | STI (Prioritization) | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | 1 | ROCKINGHAM | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | UTILITIES | 1600000
I-5898 | Highway | STI (Prioritization) | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | 1 | ROCKINGHAM | 7 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Region D |  | T | CONSTRUCTION | 23000000 | FY 2025: 230000; FY 2026: 13110000; FY 2027: 7130000; FY 2028: 2530000
I-5900 | Highway | Interstate Maintenance | I-40 | MILE MARKER 73 TO MILE MARKER 81. PAVEMENT REHABILITATION. | 12.99 | McDOWELL | 13 | Foothills RPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 23750000 | FY 2027: 8665000; FY 2028: 10980000; FY 2029: 4105000
I-5900 | Highway | Interstate Maintenance | I-40 | MILE MARKER 73 TO MILE MARKER 81. PAVEMENT REHABILITATION. | 12.99 | McDOWELL | 13 | Foothills RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1350000 | FY 2027: 493000; FY 2028: 624000; FY 2029: 233000
I-5901 | Highway | Interstate Maintenance | I-240 | MILEMARKER 4 TO MILEMARKER 9. PAVEMENT REHABILITATION. | 4.69 | BUNCOMBE | 13 | French Broad River MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 20908000 | FY 2027: 7265000; FY 2028: 9377000; FY 2029: 4266000
I-5902 | Highway | Interstate Maintenance | I-485 | SR 1786 TO NC 27. BRIDGE REHABILITATION. | 0.65 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1600000 | FY 2028: 16000; FY 2029: 1584000
I-5904 | Highway | Interstate Maintenance | I-485 | BLAIR ROAD TO IDLEWILD ROAD. PAVEMENT REHABILITATION | 6.19 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | GARVEE CON | 7785000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000 | 519000
I-5904 | Highway | Interstate Maintenance | I-485 | BLAIR ROAD TO IDLEWILD ROAD. PAVEMENT REHABILITATION | 6.19 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETED - GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 2016000
I-5905 | Highway | Interstate Maintenance | I-85 | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | 2 | MECKLENBURG | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 3067000
I-5905 | Highway | Interstate Maintenance | I-85 | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | 2 | MECKLENBURG | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 13217000
I-5905 | Highway | Interstate Maintenance | I-85 | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | 2 | MECKLENBURG | 10 | Charlotte Regional TPO | COMBINED WITH I-5906. UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 3304000
I-5907 | Highway | Interstate Maintenance | I-74 | I-77 TO US 601. PAVEMENT REHABILITATION. | 6.28 | SURRY | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 5543000
I-5912 | Highway | Interstate Maintenance | I-77 | US 21 IN YADKIN COUNTY (EXIT 79) TO MILEMARKER 83.4 IN SURRY COUNTY . PAVEMENT REHABILITATION. | 4.36 | YADKIN, SURRY | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION | Statewide Mobility
I-5915 | Highway | Interstate Maintenance | I-40 | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT AND BRIDGE REHABILITATION. | 19.5 | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO
I-5915A | Highway | Interstate Maintenance | I-40 | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT REHABILITATION. | 32.62 | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | COMPLETE | Statewide Mobility
I-5915B | Highway | Interstate Maintenance | I-40 | BRIDGE REHABILITATION. |  | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2153000
I-5915B | Highway | Interstate Maintenance | I-40 | BRIDGE REHABILITATION. |  | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 7319000
I-5915B | Highway | Interstate Maintenance | I-40 | BRIDGE REHABILITATION. |  | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP. UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2368000
I-5918 | Highway | Interstate Maintenance | I-77 | MILEMARKER 36.5 TO MILEMARKER 50.0. PAVEMENT REHABILITATION. | 13.55 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 14237000 | FY 2025: 7762000; FY 2026: 4814000; FY 2027: 1519000
I-5918 | Highway | Interstate Maintenance | I-77 | MILEMARKER 36.5 TO MILEMARKER 50.0. PAVEMENT REHABILITATION. | 13.55 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 7570000 | FY 2025: 7570000
I-5918 | Highway | Interstate Maintenance | I-77 | MILEMARKER 36.5 TO MILEMARKER 50.0. PAVEMENT REHABILITATION. | 13.55 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | PROTCT | CONSTRUCTION | 8394000 | FY 2025: 4576000; FY 2026: 2838000; FY 2027: 896000
I-5919 | Highway | Interstate Maintenance | I-77 | MILEMARKER 53.7 TO MILEMARKER 56.8. PAVEMENT REHABILITATION. | 3.1 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 2837000 | FY 2025: 1217000; FY 2026: 1299000; FY 2027: 321000
I-5919 | Highway | Interstate Maintenance | I-77 | MILEMARKER 53.7 TO MILEMARKER 56.8. PAVEMENT REHABILITATION. | 3.1 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 9463000 | FY 2025: 4059000; FY 2026: 4333000; FY 2027: 1071000
I-5920 | Highway | Interstate Maintenance | I-77 | MILE MARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | 10.41 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 3025000 | FY 2028: 1113000; FY 2029: 1352000; FY 2030: 560000
I-5920 | Highway | Interstate Maintenance | I-77 | MILE MARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | 10.41 | IREDELL | 12 | Charlotte Regional TPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 16249000 | FY 2028: 5978000; FY 2029: 7264000; FY 2030: 3007000
I-5921 | Highway | Interstate Maintenance | I-85 | CLEVELAND COUNTY LINE TO MILE MARKER 14. PAVEMENT REHABILITATION. | 5.91 | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 16830000 | FY 2027: 5921000; FY 2028: 8215000; FY 2029: 2694000
I-5924 | Highway | Interstate Maintenance | I-40 | MILE MARKER 15 TO MILE MARKER 20.5. PAVEMENT REHABILITATION. | 5.5 | HAYWOOD | 14 | Land-of-Sky RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 10899000 | FY 2028: 4025000; FY 2029: 5344000; FY 2030: 1530000
I-5925 | Highway | Interstate Maintenance | I-26 | MILE MARKER 50 TO POLK COUNTY LINE. PAVEMENT REHABILITATION. | 7.96 | HENDERSON | 14 | French Broad River MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 15200000 | FY 2027: 5623000; FY 2028: 7440000; FY 2029: 2137000
I-5926 | Highway | Interstate Maintenance | I-26 | HENDERSON COUNTY LINE TO MILE MARKER 65. PAVEMENT REHABILITATION. | 7.05 | POLK | 14 | Foothills RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13998000 | FY 2027: 5178000; FY 2028: 6852000; FY 2029: 1968000
I-5927 | Highway | Interstate Maintenance | I-26 | MILE MARKER 65 TO SOUTH CAROLINA STATE LINE. PAVEMENT REHABILITATION. | 6.06 | POLK | 14 | Foothills RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 21600000 | FY 2025: 4204000
I-5928 | Highway | Interstate Maintenance | I-40 | MILE MARKER 34 TO BUNCOMBE COUNTY LINE. PAVEMENT REHABILITATION. | 2.74 | HAYWOOD | 14 | French Broad River MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 8750000 | FY 2030: 3737000; FY 2031: 4426000; FY 2032: 587000
I-5932 | Highway | Interstate Maintenance | I-95 | NC 481 (MILE MARKER 154) TO MILE MARKER 167. PAVEMENT REHABILITATION. | 18 | HALIFAX | 4 | Peanut Belt RPO
I-5932A | Highway | Interstate Maintenance | I-95 | NC 561 (MILE MARKER 160) TO MILE MARKER 167. | 7.19 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 9593000
I-5932B | Highway | Interstate Maintenance | I-95 | NC 481 (MILE MARKER 154) TO NC 561 (MILE MARKER 160). | 6.83 | HALIFAX | 4 | Peanut Belt RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 8223000
I-5934 | Highway | Interstate Maintenance | I-95 | SR 1770 (SUNSET AVENUE) (MILE MARKER 137.4) TO SR 1544 (NORTH HALIFAX ROAD) (MILE MARKER 142.1). PAVEMENT AND BRIDGE REHABILITATION. | 3.92 | NASH | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 9000000 | FY 2026: 90000; FY 2027: 8910000
I-5936 | Highway | Interstate Maintenance | I-95 | JOHNSTON COUNTY LINE (MILE MARKER 108.2) TO NORTH OF SR 1116 (GOVERNOR HUNT ROAD) (MILE MARKER 114.5). PAVEMENT REHABILITATION. | 6.41 | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 3303000
I-5939 | Highway | Interstate Maintenance | I-95 | SOUTH CAROLINA STATE LINE (MILE MARKER 0.0) TO I-74 (MILE MARKER 13). PAVEMENT REHABILITATION. | 5.49 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | BGIM | CONSTRUCTION | 23898000
I-5940 | Highway | Interstate Maintenance | I-40 | DUPLIN COUNTY LINE (MILE MARKER 360) TO WEST OF US 117 (MILE MARKER 390). PAVEMENT AND BRIDGE REHABILITATION. | 35.89 | DUPLIN, PENDER | 3 | Eastern Carolina RPO, Cape Fear RPO | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION. | Statewide Mobility |  | BGIM | GARVEE CON | 28826000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000 | 2059000
I-5940 | Highway | Interstate Maintenance | I-40 | DUPLIN COUNTY LINE (MILE MARKER 360) TO WEST OF US 117 (MILE MARKER 390). PAVEMENT AND BRIDGE REHABILITATION. | 35.89 | DUPLIN, PENDER | 3 | Eastern Carolina RPO, Cape Fear RPO | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION. | Statewide Mobility |  | BGIM | CONSTRUCTION | 750000
I-5941 | Highway | Interstate Maintenance | I-85 | ORANGE COUNTY LINE TO US 15 / US 501 IN DURHAM. PAVEMENT REHABILITATION | 2.49 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1614000
I-5941 | Highway | Interstate Maintenance | I-85 | ORANGE COUNTY LINE TO US 15 / US 501 IN DURHAM. PAVEMENT REHABILITATION | 2.49 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 11875000 | FY 2025: 1798000
I-5943 | Highway | Interstate Maintenance | I-40 | SR 1728 (WADE AVENUE) TO I-440 / US 1 IN RALEIGH. PAVEMENT AND BRIDGE REHABILITATION. | 3.84 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 18419000
I-5944 | Highway | Interstate Maintenance | I-87 / US 64 / US 264 | I-440 IN RALEIGH TO SR 1003 (ROLESVILLE ROAD). PAVEMENT REHABILITATION. | 9.91 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 28600000 | FY 2031: 11633000; FY 2032: 11840000; FY 2033: 5127000
I-5945 | Highway | Interstate Maintenance | I-540 | TRIANGLE TOWNE CENTER BOULEVARD IN RALEIGH TO I-495 / US 64 / US 264 IN KNIGHTDALE. PAVEMENT REHABILITATION. | 8.97 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 27900000 | FY 2031: 10510000; FY 2032: 11692000; FY 2033: 5698000
I-5946 | Highway | Interstate Maintenance | I-73 / I-74 | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | 10.5 | RICHMOND | 8 | Lumber River RPO
I-5946A | Highway | Interstate Maintenance | I-73/I-74 | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO SR 1455 (FIRE TOWER ROAD). PAVEMENT REHABILITATION. | 3.23 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION - LET WITH I-5947B | Statewide Mobility
I-5946B | Highway | Interstate Maintenance | I-73/I-74 | SR 1455 (FIRE TOWER ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | 6.86 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | BGIM | CONSTRUCTION | 6812000
I-5947 | Highway | Interstate Maintenance | I-73 / I-74 / US 220 | MONTGOMERY COUNTY LINE TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | 24.5 | MONTGOMERY | 8 | Piedmont Triad RPO
I-5947A | Highway | Interstate Maintenance | I-73/74 | MONTGOMERY COUNTY LINE TO NC 211. PAVEMENT REHABILITATION. | 8.92 | MONTGOMERY | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | BGIM | CONSTRUCTION | 19300000 | FY 2027: 7766000; FY 2028: 9245000; FY 2029: 2289000
I-5947B | Highway | Interstate Maintenance | I-73/74 | NC 211 TO NC 24/27. PAVEMENT REHABILITATION. | 5.05 | MONTGOMERY | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION - LET WITH I-5946A | Statewide Mobility |  | BGIM | CONSTRUCTION | 6900000
I-5947C | Highway | Interstate Maintenance | I-73/74 | NC 24/27 TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | 10.51 | MONTGOMERY | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | BGIM | CONSTRUCTION | 17600000 | FY 2028: 7706000; FY 2029: 8771000; FY 2030: 1123000
I-5948 | Highway | Interstate Maintenance | I-73 / I-74 / US 220 | MONTGOMERY COUNTY LINE TO NORTH OF SR 1462 (PARK DRIVE) IN ASHEBORO. PAVEMENT REHABILITATION. | 15.72 | RANDOLPH | 8 | Piedmont Triad RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 26700000 | FY 2028: 10265000; FY 2029: 12862000; FY 2030: 3573000
I-5950 | Highway | Interstate Maintenance | I-85 | I-285 / US 29 / US 52 / US 70 TO NORTH OF US 64. PAVEMENT REHABILITATION. | 9.58 | DAVIDSON | 9 | High Point Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 28542000
I-5952 | Highway | Interstate Maintenance | I-40 | SR 1101 (HARPER ROAD) IN CLEMMONS TO EAST OF US 421 / BUSINESS 40 IN WINSTON-SALEM. PAVEMENT REHABILITATION. | 5.97 | FORSYTH | 9 | Winston-Salem Area TPO | UNDER CONSTRUCTION. DELETE I-5952A. WORK ACCOMPLISHED UNDER I-5795. | Statewide Mobility
I-5953 | Highway | Interstate Maintenance | I-785 / I-840 | I-85 TO US 70. PAVEMENT REHABILITATION. | 2.14 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Statewide Mobility
I-5955 | Highway | Interstate Maintenance | I-40 | SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. PAVEMENT REHABILITATION. | 5 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5965 AND B-5356 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13224000 | FY 2025: 3211000
I-5955A | Highway | Interstate Maintenance | I-40 | SOUTH BUFFALO CREEK BRIDGE EAST OF US 220 (FREEMAN MILL ROAD) TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. REHABILITATE BRIDGES 400678, 400367, 400364, 400357, 400349, 400348, 400340, 400339, 400336, 400329, 400327, 400299, 400291, AND 400285. | 5.01 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 10099000 | FY 2025: 5999000; FY 2026: 644000
I-5958 | Highway | Interstate Maintenance | I-40 / I-85 | WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1006 (ORANGE GROVE ROAD). PAVEMENT REHABILITATION. | 6.74 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO |  | Statewide Mobility |  | NHFP | CONSTRUCTION | 9288000 | FY 2027: 6563000; FY 2028: 2725000
I-5958 | Highway | Interstate Maintenance | I-40 / I-85 | WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1006 (ORANGE GROVE ROAD). PAVEMENT REHABILITATION. | 6.74 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 212000 | FY 2027: 150000; FY 2028: 62000
I-5962 | Highway | STI (Prioritization) | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 1 | IREDELL | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 3000000 | FY 2028: 1029000; FY 2029: 1371000; FY 2030: 300000; FY 2031: 300000
I-5962 | Highway | STI (Prioritization) | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 1 | IREDELL | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | Statewide Mobility |  | NHP | UTILITIES | 500000 | FY 2028: 500000
I-5962 | Highway | STI (Prioritization) | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 1 | IREDELL | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | Statewide Mobility |  | NHP | CONSTRUCTION | 58959000 | FY 2031: 590000; FY 2032: 24698000; FY 2033: 21115000; FY 2034: 12556000
I-5962 | Highway | STI (Prioritization) | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | 1 | IREDELL | 12 | Charlotte Regional TPO | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE | Statewide Mobility |  | O | CONSTRUCTION | 2240000 | FY 2031: 22000; FY 2032: 917000; FY 2033: 878000; FY 2034: 423000
I-5964 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | ELM-EUGENE STREET IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 1100000 | FY 2025: 567000; FY 2026: 533000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | 2.87 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 11000000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | 2.87 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 3732000
I-5965 | Highway | STI (Prioritization) | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | 2.87 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH B-5356 AND B-5718 | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 109201000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | 2.33 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 430000 | FY 2029: 430000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | 2.33 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | UTILITIES | 200000 | FY 2029: 200000
I-5966 | Highway | STI (Prioritization) | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | 2.33 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 73700000 | FY 2032: 21517000; FY 2033: 25331000; FY 2034: 17785000; FY 2035: 9067000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | 2.53 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | RIGHT-OF-WAY | 4700000 | FY 2028: 1847000; FY 2029: 2213000; FY 2030: 320000; FY 2031: 320000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | 2.53 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | UTILITIES | 20000 | FY 2028: 20000
I-5968 | Highway | STI (Prioritization) | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | 2.53 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHP | CONSTRUCTION | 34800000 | FY 2031: 16698000; FY 2032: 14219000; FY 2033: 3883000
I-5972 | Highway | STI (Prioritization) | I-95 | US 70 BUSINESS. UPGRADE INTERCHANGE. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS | Region A |  | NHP | CONSTRUCTION | 43182000 | FY 2025: 14843000; FY 2026: 6882000
I-5973 | Highway | STI (Prioritization) | I-485 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | Region E |  | T | UTILITIES | 195000
I-5973 | Highway | STI (Prioritization) | I-485 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | Region E |  | T | BUILD NC CON | 2040000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000 | 136000
I-5973 | Highway | STI (Prioritization) | I-485 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,580,327 FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE) | Region E |  | T | CONSTRUCTION | 4420000 | FY 2025: 1130000
I-5974 | Highway | STI (Prioritization) | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Region A |  | NHP | RIGHT-OF-WAY | 7276000 | FY 2026: 1690000; FY 2027: 2253000; FY 2028: 1877000; FY 2029: 728000; FY 2030: 728000
I-5974 | Highway | STI (Prioritization) | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Region A |  | NHP | UTILITIES | 1400000 | FY 2026: 700000; FY 2027: 700000
I-5974 | Highway | STI (Prioritization) | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Region A |  | NHP | CONSTRUCTION | 73500000 | FY 2029: 735000; FY 2030: 31605000; FY 2031: 21315000; FY 2032: 14700000; FY 2033: 5145000
I-5979 | Highway | STI (Prioritization) | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | 1 | RICHMOND | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | NHP | RIGHT-OF-WAY | 500000
I-5979 | Highway | STI (Prioritization) | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | 1 | RICHMOND | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | NHP | UTILITIES | 210000
I-5979 | Highway | STI (Prioritization) | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | 1 | RICHMOND | 8 | Lumber River RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | NHP | CONSTRUCTION | 8800000 | FY 2025: 4282000; FY 2026: 4518000
I-5981 | Highway | STI (Prioritization) | I-40 | I-74 US 311 IN WINSTON-SALEM TO US 421 / BUSINESS 40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | 10.1 | FORSYTH, GUILFORD | 7, 9 | Winston-Salem Area TPO, High Point Urban Area MPO
I-5986 | Highway | STI (Prioritization) | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 26 | CUMBERLAND, HARNETT, JOHNSTON | 4, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Upper Coastal Plain RPO
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 15.76 | CUMBERLAND, HARNETT | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 21073000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 15.76 | CUMBERLAND, HARNETT | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | UTILITIES | 2000000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 15.76 | CUMBERLAND, HARNETT | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | NHP | CONSTRUCTION | 18000000 | FY 2025: 18000000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 15.76 | CUMBERLAND, HARNETT | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 375400000 | FY 2026: 15000000
I-5986A | Highway | STI (Prioritization) | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | 15.76 | CUMBERLAND, HARNETT | 6 | Mid-Carolina RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | PROTCT | CONSTRUCTION | 32000000 | FY 2025: 32000000
I-5986B | Highway | STI (Prioritization) | I-95 | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 10.72 | HARNETT, JOHNSTON | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | Statewide Mobility |  | T | RIGHT-OF-WAY | 42100000
I-5986B | Highway | STI (Prioritization) | I-95 | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 10.72 | HARNETT, JOHNSTON | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | Statewide Mobility |  | T | UTILITIES | 700000
I-5986B | Highway | STI (Prioritization) | I-95 | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | 10.72 | HARNETT, JOHNSTON | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5878 AND I-5883. | Statewide Mobility |  | T | CONSTRUCTION | 92456000 | FY 2025: 21337000; FY 2026: 17000000; FY 2027: 19420000
I-5986BA | Highway | STI (Prioritization) | I-95 | SR 1001 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). CLEARING FOR UTILITIES. | 10.72 | HARNETT, JOHNSTON | 4, 6 | Mid-Carolina RPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 144000
I-5986C | Highway | Other | I-95 | INSTALL BROADBAND FIBER ALONG I-95 FROM SOUTH CAROLINA LINE TO VIRGINIA STATE LINE. | 181.34 | ROBESON, CUMBERLAND, JOHNSTON, NASH, HALIFAX, WILSON, HARNETT, NORTHAMPTON | 1, 4, 6 | Upper Coastal Plain RPO, Lumber River RPO, Peanut Belt RPO, Fayetteville Area MPO, Mid-Carolina RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | DP | CONSTRUCTION | 16600000
I-5986C | Highway | Other | I-95 | INSTALL BROADBAND FIBER ALONG I-95 FROM SOUTH CAROLINA LINE TO VIRGINIA STATE LINE. | 181.34 | ROBESON, CUMBERLAND, JOHNSTON, NASH, HALIFAX, WILSON, HARNETT, NORTHAMPTON | 1, 4, 6 | Upper Coastal Plain RPO, Lumber River RPO, Peanut Belt RPO, Fayetteville Area MPO, Mid-Carolina RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 25567000 | FY 2025: 7500000
I-5987 | Highway | STI (Prioritization) | I-95 | SOUTH OF US 301 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 15.7 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. AA BREAK: O FUNDS REPRESENT WEIGH STATION FUNDING. | Region C
I-5987A | Highway | STI (Prioritization) | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 10.24 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | RIGHT-OF-WAY | 3395000
I-5987A | Highway | STI (Prioritization) | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 10.24 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | UTILITIES | 3075000
I-5987A | Highway | STI (Prioritization) | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 10.24 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | BUILD NC CON | 75930000 | 5062000 | 5062000 | 5062000 | 5062000 | 5062000 | 5062000 | 5062000 | 5062000 | 5062000 | 5062000 | 5062000 | 5062000
I-5987A | Highway | STI (Prioritization) | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 10.24 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | BUILD NC CON | 64050000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 17080000
I-5987A | Highway | STI (Prioritization) | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 10.24 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | BUILD NC CON | 45750000 |  | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 15250000
I-5987A | Highway | STI (Prioritization) | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | 10.24 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $59,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | CONSTRUCTION | 153079000 | FY 2025: 26179000; FY 2026: 26816000; FY 2027: 42612000
I-5987AA | Highway | STI (Prioritization) | I-95 | CONSTRUCT WEIGH IN MOTION STATION. | 2 | ROBESON | 6 | Lumber River RPO | O FUNDS REPRESENT STATE PRIMARY MAINTENANCE FUNDS FOR WEIGH STATIONS. | Region C |  | O | CONSTRUCTION | 4800000 | FY 2027: 4800000
I-5987B | Highway | STI (Prioritization) | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6.28 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | RIGHT-OF-WAY | 3581000
I-5987B | Highway | STI (Prioritization) | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6.28 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | UTILITIES | 2624000
I-5987B | Highway | STI (Prioritization) | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6.28 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | BUILD NC CON | 45750000 |  | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 15250000
I-5987B | Highway | STI (Prioritization) | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6.28 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | BUILD NC CON | 86250000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000 | 5750000
I-5987B | Highway | STI (Prioritization) | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6.28 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | BUILD NC CON | 64050000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 17080000
I-5987B | Highway | STI (Prioritization) | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | 6.28 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $67,021,814 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $42,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE); $30,000,000 FOR CONSTRUCTION PAYBACK 2026-2040 (FY 2026 / YR 6 SALE) | Region C |  | T | CONSTRUCTION | 186346000 | FY 2025: 29581000; FY 2026: 31820000; FY 2027: 65551000
I-5987C | Highway | STI (Prioritization) | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 16.52 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO |  | Region C |  | DP | ENGINEERING | 250000
I-5987C | Highway | STI (Prioritization) | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 16.52 | ROBESON | 6 | Lumber River RPO, Fayetteville Area MPO |  | Region C |  | T | ENGINEERING | 65000
I-5990 | Highway | STI (Prioritization) | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | 1 | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | NHP | RIGHT-OF-WAY | 2500000 | FY 2025: 1556000; FY 2026: 444000; FY 2027: 250000; FY 2028: 250000
I-5990 | Highway | STI (Prioritization) | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | 1 | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | NHP | UTILITIES | 1100000 | FY 2025: 550000; FY 2026: 550000
I-5990 | Highway | STI (Prioritization) | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | 1 | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | NHP | CONSTRUCTION | 35000000 | FY 2026: 11666000; FY 2027: 11667000; FY 2028: 11667000
I-5992 | Highway | Interstate Maintenance | I-77 | MILE MARKER 11 TO MILE MARKER 20 AND MILE MARKER 24.5 TO MILE MARKER 37. REHABILITATE PAVEMENT. | 21.27 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | UNDER CONSTRUCTION | Statewide Mobility
I-5993 | Highway | Interstate Maintenance | I-40 | US 15 / US 501 TO EAST OF NC 147. PAVEMENT REHABILITATION. | 9.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | TO BE LET WITH I-5994 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 17557000 | FY 2026: 5978000; FY 2027: 6285000; FY 2028: 4158000; FY 2029: 1136000
I-5993 | Highway | Interstate Maintenance | I-40 | US 15 / US 501 TO EAST OF NC 147. PAVEMENT REHABILITATION. | 9.24 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | TO BE LET WITH I-5994 | Statewide Mobility |  | NHFP | CONSTRUCTION | 20574000 | FY 2026: 6733000; FY 2027: 7079000; FY 2028: 4683000; FY 2029: 2079000
I-5995 | Highway | Interstate Maintenance | I-40 | EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | 9.37 | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | Combined with I-5996. | Statewide Mobility |  | NHFP | CONSTRUCTION | 9924000 | FY 2026: 2880000; FY 2027: 3665000; FY 2028: 2491000; FY 2029: 888000
I-5995 | Highway | Interstate Maintenance | I-40 | EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | 9.37 | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | Combined with I-5996. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 44676000 | FY 2026: 12966000; FY 2027: 16498000; FY 2028: 11214000; FY 2029: 3998000
I-5997 | Highway | Interstate Maintenance | I-440 / US 1 | SR 1728 (WADE AVENUE) TO SR 2000 (WAKE FOREST ROAD) IN RALEIGH. PAVEMENT REHABILITATION. | 4.85 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 23100000 | FY 2025: 8100000
I-5998 | Highway | Interstate Maintenance | I-540 | I-40 IN DURHAM TO US 70 IN RALEIGH. PAVEMENT REHABILITATION. | 4.25 | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5999 AND I-6000 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 24500000 | FY 2026: 10000000; FY 2027: 10677000; FY 2028: 3823000
I-5999 | Highway | Interstate Maintenance | I-540 | US 70 (GLENWOOD AVENUE) TO EAST OF TRIANGLE TOWN BOULEVARD IN RALEIGH. PAVEMENT REHABILITATION. | 12.53 | WAKE | 5 | Capital Area MPO | COORDINATE WITH I-5998 AND I-6000; | Statewide Mobility |  | NHPIM | CONSTRUCTION | 12511000 | FY 2025: 2511000
I-6000 | Highway | Interstate Maintenance | I-540 | I-40 IN DURHAM TO US 1 IN RALEIGH. BRIDGE PRESERVATION / REHABILITATION. | 16.34 | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | COORDINATE WITH I-5998 AND I-5999 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 7610000 | FY 2029: 5526000; FY 2030: 2084000
I-6001 | Highway | Interstate Maintenance | I-87 / FUTURE I-87 / US 64 / US 264 | SR 1003 (ROLESVILLE ROAD) TO NASH COUNTY LINE. PAVEMENT REHABILITATION. | 13.38 | WAKE, FRANKLIN | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 40400000 | FY 2025: 404000; FY 2026: 18584000; FY 2027: 13332000; FY 2028: 8080000
I-6003 | Highway | Interstate Maintenance | I-40 | SR 1436 (PINEBROOK SCHOOL ROAD) TO WEST OF NC 801. PAVEMENT REHABILITATION. | 4.76 | DAVIE | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHPIM | CONSTRUCTION | 7677000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | NHP | RIGHT-OF-WAY | 5700000 | FY 2027: 3419000; FY 2028: 1141000; FY 2029: 570000; FY 2030: 570000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | NHP | UTILITIES | 120000 | FY 2027: 120000
I-6004 | Highway | STI (Prioritization) | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | 1 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | NHP | CONSTRUCTION | 21300000 | FY 2030: 8101000; FY 2031: 13199000
I-6009 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 700000
I-6009 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 100000
I-6009 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | 0.5 | ALAMANCE | 7 | Burlington-Graham MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 1990000
I-6011 | Highway | STI (Prioritization) | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | 22.71 | COLUMBUS, ROBESON | 6 | Cape Fear RPO, Lumber River RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 179000 | [11 empty] | 179000
I-6011 | Highway | STI (Prioritization) | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | 22.71 | COLUMBUS, ROBESON | 6 | Cape Fear RPO, Lumber River RPO |  | Not Funded |  | T | UTILITIES | 1469000 | [11 empty] | 1469000
I-6011 | Highway | STI (Prioritization) | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | 22.71 | COLUMBUS, ROBESON | 6 | Cape Fear RPO, Lumber River RPO |  | Not Funded |  | T | CONSTRUCTION | 169100000 | [11 empty] | 169100000
I-6011A | Highway | STI (Prioritization) | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | BGLT5 | RIGHT-OF-WAY | 150000 | FY 2025: 150000
I-6011A | Highway | STI (Prioritization) | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | BGLT5 | UTILITIES | 200000 | FY 2025: 200000
I-6011A | Highway | STI (Prioritization) | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | 0.5 | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | BGLT5 | CONSTRUCTION | 8900000 | FY 2027: 5619000; FY 2028: 3281000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4200000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 900000
I-6012 | Highway | STI (Prioritization) | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 47000000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 900000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 200000
I-6013 | Highway | STI (Prioritization) | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 16000000
I-6015 | Highway | STI (Prioritization) | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 8400000
I-6015 | Highway | STI (Prioritization) | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1100000
I-6015 | Highway | STI (Prioritization) | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 9999000
I-6016 | Highway | STI (Prioritization) | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | HF FUNDS ARE CONTINGENCY FUNDS. | Statewide Mobility |  | HF | RIGHT-OF-WAY | 2000000 | FY 2025: 1438000; FY 2026: 160000; FY 2027: 200000; FY 2028: 200000
I-6016 | Highway | STI (Prioritization) | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | HF FUNDS ARE CONTINGENCY FUNDS. | Statewide Mobility |  | HF | UTILITIES | 970000 | FY 2025: 485000
I-6016 | Highway | STI (Prioritization) | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | HF FUNDS ARE CONTINGENCY FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 5000000 | FY 2028: 5000000
I-6016 | Highway | STI (Prioritization) | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO | HF FUNDS ARE CONTINGENCY FUNDS. | Statewide Mobility |  | HF | CONSTRUCTION | 41600000 | FY 2026: 17888000; FY 2027: 16224000; FY 2028: 7488000
I-6016A | Highway | Other | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. CLEARING ONLY. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Highway Fund |  | HF | CONSTRUCTION | 200000 | FY 2025: 162000; FY 2026: 36000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 14900000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 4700000
I-6019 | Highway | STI (Prioritization) | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 20701000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 56900000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2300000
I-6020 | Highway | STI (Prioritization) | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 72900000
I-6028 | Highway | Interstate Maintenance | US 13/US 64 (FUTURE I-87) | EDGECOMBE COUNTY LINE TO US 13/17 AND US 64 INTERCHANGE. PAVEMENT REHABILITATION. | 18.56 | MARTIN | 1 | Mid-East RPO | "A" BREAK DELETED, WORK WAS COMPLETED WITH CONTRACT RESURFACING. | Statewide Mobility
I-6028B | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | US 64 ALTERNATE TO NC 125. | 4.7 | MARTIN | 1 | Mid-East RPO | COMPLETED. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6073000
I-6028C | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | NC 125 TO US 13/17 AND US 64 INTERCHANGE. | 4.11 | MARTIN | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 6000000
I-6029 | Highway | Interstate Maintenance | US 17 (FUTURE I-87) | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | 10.29 | PASQUOTANK | 1 | Albemarle RPO | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | Statewide Mobility |  | NHPIM | GARVEE CON | 4125000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000 | 275000
I-6029 | Highway | Interstate Maintenance | US 17 (FUTURE I-87) | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | 10.29 | PASQUOTANK | 1 | Albemarle RPO | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | Statewide Mobility |  | NHP | CONSTRUCTION | 5625000
I-6029 | Highway | Interstate Maintenance | US 17 (FUTURE I-87) | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | 10.29 | PASQUOTANK | 1 | Albemarle RPO | COMPLETED. GARVEE BOND FUNDING: $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2136000
I-6032 | Highway | Interstate Maintenance | US 264 (FUTURE I-587) | PITT COUNTY LINE TO WILSON COUNTY LINE. PAVEMENT REHABILITATION. | 4.18 | GREENE | 2 | Eastern Carolina RPO | COMPLETED. LET WITH I-6035. GARVEE BOND FUNDING: $4,020,000 FOR CON, PAYBACK FY 2019-2033. | Statewide Mobility |  | NHPIM | GARVEE CON | 4830000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000
I-6035 | Highway | Interstate Maintenance | US 264/US 258 (FUTURE I-587) | GREENE COUNTY LINE TO SR 1467 (STANTONSBURG ROAD) INTERCHANGE (GREENVILLE SOUTHWEST BYPASS). PAVEMENT REHABILITATION. | 13.19 | PITT | 2 | Mid-East RPO, Greenville Urban Area MPO | COMPLETE. LET WITH I-6032. GARVEE BOND FUNDING $12M FOR CON, PAYBACK FY 2019-2033. | Statewide Mobility |  | NHPIM | GARVEE CON | 14420000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000 | 1030000
I-6036 | Highway | Interstate Maintenance | I-140 | US 17 TO NORTH OF US 74. PAVEMENT REHABILITATION. | 5.08 | BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 11080000 | FY 2025: 4543000
I-6037 | Highway | Interstate Maintenance | I-140 | US 421 TO I-40. PAVEMENT AND BRIDGE REHABILITATION. | 6.79 | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | NHPIM | CONSTRUCTION | 7300000 | FY 2028: 4300000; FY 2029: 3000000
I-6039 | Highway | Interstate Maintenance | I-40 | I-40 FROM END I-40 (MILE MARKER 420) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | 11.88 | NEW HANOVER, PENDER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHFP | CONSTRUCTION | 6775000 | FY 2025: 1237000
I-6039 | Highway | Interstate Maintenance | I-40 | I-40 FROM END I-40 (MILE MARKER 420) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | 11.88 | NEW HANOVER, PENDER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 16229000 | FY 2025: 3253000
I-6040 | Highway | Interstate Maintenance | I-40 | WEST OF US 117 (MILE MARKER 388) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | 15.05 | PENDER | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 19768000
I-6041 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | SR 1225 (KINGSBORO ROAD) TO NC 33. PAVEMENT REHABILITATION. | 10.18 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | HP | CONSTRUCTION | 7000000
I-6041 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | SR 1225 (KINGSBORO ROAD) TO NC 33. PAVEMENT REHABILITATION. | 10.18 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 11909000 | FY 2025: 3811000; FY 2026: 476000
I-6041 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | SR 1225 (KINGSBORO ROAD) TO NC 33. PAVEMENT REHABILITATION. | 10.18 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1750000
I-6041A | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | REHABILITATE BRIDGES 320104, 320155, 320148, 320153, 320154, 320156, 320157, 320320, 320325, AND 320326. |  | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 4000000
I-6042 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | NC 33 TO MARTIN COUNTY LINE. PAVEMENT REHABILITATION. | 10.45 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | HP | CONSTRUCTION | 5300000
I-6042 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | NC 33 TO MARTIN COUNTY LINE. PAVEMENT REHABILITATION. | 10.45 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 13075000
I-6042 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | NC 33 TO MARTIN COUNTY LINE. PAVEMENT REHABILITATION. | 10.45 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. HP FUNDS REPRESENT FEDERAL EARMARK FUNDS. DEMO ID NC196. | Statewide Mobility |  | T(M) | CONSTRUCTION | 1325000
I-6042A | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | REHABILITATE BRIDGE 320327 AND 320328. |  | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 300000
I-6044 | Highway | Interstate Maintenance | US 70 (FUTURE I-42) | SR 1003 (BUFFALO ROAD) TO WAYNE COUNTY LINE. PAVEMENT REHABILITATION. | 13.32 | JOHNSTON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132 FOR CONSTRUCTION, PAYBACK FY 2019-2033. | Statewide Mobility |  | NHPIM | GARVEE CON | 6090000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000 | 435000
I-6045 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | SR 1306 (SOUTH OLD FRANKLIN ROAD) TO SR 1603 (OLD CARRIAGE ROAD). PAVEMENT REHABILITATION. | 11.12 | NASH | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 835000 | FY 2025: 267000
I-6045 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | SR 1306 (SOUTH OLD FRANKLIN ROAD) TO SR 1603 (OLD CARRIAGE ROAD). PAVEMENT REHABILITATION. | 11.12 | NASH | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHFP | CONSTRUCTION | 15825000 | FY 2025: 3393000
I-6045A | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | BRIDGE REHABILITATION FOR 630072 AND 630074. |  | NASH | 4 | Upper Coastal Plain RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 520000
I-6046 | Highway | Interstate Maintenance | US 64 (FUTURE I-87) | SR 1603 (OLD CARRIAGE ROAD) TO SR 1225 (KINGSBORO ROAD). PAVEMENT REHABILITATION. | 12.63 | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 24006000
I-6047 | Highway | Interstate Maintenance | I-795 | WILSON COUNTY LINE TO SR 2075 (ASH STREET). UPGRADE GUARDRAIL, SHOULDER AND MEDIAN REPAIRS. | 13.55 | WAYNE | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034. | Statewide Mobility |  | NHPIM | GARVEE CON | 4860000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000 | 324000
I-6047 | Highway | Interstate Maintenance | I-795 | WILSON COUNTY LINE TO SR 2075 (ASH STREET). UPGRADE GUARDRAIL, SHOULDER AND MEDIAN REPAIRS. | 13.55 | WAYNE | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3,775,252 FOR CONSTRUCTION, PAYBACK FY 2020-2034. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2033000
I-6048 | Highway | Interstate Maintenance | US 117 (FUTURE I-795) | US 70 TO DUPLIN COUNTY LINE. PAVEMENT AND BRIDGE REHABILITATION. | 16.69 | WAYNE | 4 | Eastern Carolina RPO, Goldsboro Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 7942000
I-6052 | Highway | Interstate Maintenance | I-277 (BROOKSHIRE FREEWAY) | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 1245000
I-6052 | Highway | Interstate Maintenance | I-277 (BROOKSHIRE FREEWAY) | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION. | Statewide Mobility |  | BGDA | CONSTRUCTION | 11840000
I-6052 | Highway | Interstate Maintenance | I-277 (BROOKSHIRE FREEWAY) | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | 0.32 | MECKLENBURG | 10 | Charlotte Regional TPO | $11,840,000 IN NHPIM FUNDS SWITCHED WITH $11,840,000 IN BGDA AS PART OF FUND SWAPS IN 2022 AND 2023. UNDER CONSTRUCTION. | Statewide Mobility |  | T(M) | CONSTRUCTION | 2960000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 26973000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 655000
I-6053 | Highway | STI (Prioritization) | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 24300000
I-6055 | Highway | STI (Prioritization) | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 9.84 | SCOTLAND, RICHMOND | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 43000000
I-6055 | Highway | STI (Prioritization) | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 9.84 | SCOTLAND, RICHMOND | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 8500000
I-6055 | Highway | STI (Prioritization) | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 9.84 | SCOTLAND, RICHMOND | 8 | Lumber River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 224100000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 1 | ALAMANCE | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | T | RIGHT-OF-WAY | 2000000 | FY 2025: 2000000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 1 | ALAMANCE | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | T | UTILITIES | 2500000 | FY 2025: 2500000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 1 | ALAMANCE | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | T | BUILD NC CON | 10680000 |  |  | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 4272000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 1 | ALAMANCE | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | T | CONSTRUCTION | 11700000 | FY 2026: 4862000; FY 2027: 1041000; FY 2028: 5797000
I-6059 | Highway | STI (Prioritization) | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | 1 | ALAMANCE | 7 | Burlington-Graham MPO | "HF" FUNDS REPRESENT $10M LEGISLATIVE APPROPRIATION. BUILD NC BONDS: $7M FOR CONSTRUCTION - PAYBACK 2027-2041 (FY 2027 / YR 7 SALE) | Division 7 |  | HF | CONSTRUCTION | 10000000 | FY 2025: 10000000
I-6061 | Highway | STI (Prioritization) | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 1999000
I-6061 | Highway | STI (Prioritization) | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2000000
I-6061 | Highway | STI (Prioritization) | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | 1 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 26300000
I-6063 | Highway | Interstate Maintenance | I-40 | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | 4.96 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | GARVEE CON | 6435000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000 | 429000
I-6063 | Highway | Interstate Maintenance | I-40 | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | 4.96 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | NHPIM | CONSTRUCTION | 22120000
I-6063 | Highway | Interstate Maintenance | I-40 | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | 4.96 | BUNCOMBE | 13 | French Broad River MPO | UNDER CONSTRUCTION - GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034 | Statewide Mobility |  | T(M) | CONSTRUCTION | 1667000
I-6064 | Highway | STI (Prioritization) | I-95 | MILE MARKER 13 TO MILE MARKER 22. WIDEN TO EIGHT LANES AND PAVEMENT REHABILITATION. | 9 | ROBESON | 6 | Lumber River RPO | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. PROJECT LET WITH I-5879.
I-6064A | Highway | STI (Prioritization) | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 5.75 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | DP | RIGHT-OF-WAY | 2470000
I-6064A | Highway | STI (Prioritization) | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 5.75 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T | RIGHT-OF-WAY | 617000
I-6064A | Highway | STI (Prioritization) | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 5.75 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | DP | UTILITIES | 2600000
I-6064A | Highway | STI (Prioritization) | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 5.75 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T | UTILITIES | 3850000
I-6064A | Highway | STI (Prioritization) | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 5.75 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | DP | CONSTRUCTION | 16930000
I-6064A | Highway | STI (Prioritization) | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN TO EIGHT LANES. | 5.75 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 201441000 | FY 2025: 47888000; FY 2026: 90000000; FY 2027: 19000000
I-6064B | Highway | STI (Prioritization) | I-95 | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN TO EIGHT LANES. | 2.79 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | RIGHT-OF-WAY | 8688000 | FY 2025: 1259000
I-6064B | Highway | STI (Prioritization) | I-95 | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN TO EIGHT LANES. | 2.79 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | UTILITIES | 3425000
I-6064B | Highway | STI (Prioritization) | I-95 | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN TO EIGHT LANES. | 2.79 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 85946000 | FY 2025: 11171000; FY 2026: 40000000; FY 2027: 8000000
I-6064C | Highway | Interstate Maintenance | I-95 | MILE MARKER 13 TO MILE MARKER 22. PAVEMENT REHABILITATION. | 9 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Statewide Mobility |  | NHPIM | CONSTRUCTION | 131492000 | FY 2025: 23874000
I-6064D | Highway | Other | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 9.01 | ROBESON | 6 | Lumber River RPO |  | Statewide Mobility |  | DP | ENGINEERING | 250000
I-6064D | Highway | Other | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | 9.01 | ROBESON | 6 | Lumber River RPO |  | Statewide Mobility |  | T | ENGINEERING | 65000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | BGDA | ENGINEERING | 760000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | BGDA | ENGINEERING | 96000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | BGDA | ENGINEERING | 600000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(M) | ENGINEERING | 150000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | BA | ENGINEERING | 190000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(M) | ENGINEERING | 24000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | BGDA | RIGHT-OF-WAY | 80000 | FY 2025: 80000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(M) | RIGHT-OF-WAY | 20000 | FY 2025: 20000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(M) | CONSTRUCTION | 9017000 | FY 2027: 1161000; FY 2028: 4128000; FY 2029: 2497000; FY 2030: 1231000
I-6065 | Highway | Locally Selected | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | 16.38 | MECKLENBURG, IREDELL | 10, 12 | Charlotte Regional TPO | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP. | Exempt |  | T(DA) | CONSTRUCTION | 36063000 | FY 2027: 4644000; FY 2028: 16509000; FY 2029: 9987000; FY 2030: 4923000
M-0219 | Highway | Other | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility
M-0219DIV | Highway | Other | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 1200000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
M-0219REG | Highway | Other | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 1200000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
M-0219SW | Highway | Other | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 1600000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
M-0376 | Highway | Other | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS
M-0376DIV | Highway | Other | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 4320000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000
M-0376REG | Highway | Other | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 4320000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000
M-0376SW | Highway | Other | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 5670000 | 360000 | 270000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000
M-0379 | Highway | Bridges | VARIOUS | SCOUR EVALUATION PROGRAM OF EXISTING BRIDGES. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99
M-0391 | Highway | Other | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS
M-0391DIV | Highway | Other | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 1920000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
M-0391REG | Highway | Other | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 1920000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
M-0391SW | Highway | Other | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 2560000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000
M-0392 | Highway | Other | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS
M-0392DIV | Highway | Other | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 768000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000
M-0392REG | Highway | Other | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 768000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000
M-0392SW | Highway | Other | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 1024000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | IMPLEMENTATION | 800000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | IMPLEMENTATION | 800000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | IMPLEMENTATION | 800000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | IMPLEMENTATION | 1000000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | BGOFF | IMPLEMENTATION | 800000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | L | IMPLEMENTATION | 200000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | L | IMPLEMENTATION | 200000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | L | IMPLEMENTATION | 200000
M-0414 | Highway | Bridges | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | L | IMPLEMENTATION | 200000
M-0418 | Highway | Bridges | VARIOUS | STORM WATER RUNOFF. RESEARCH, DESIGN, CONSTRUCT, MAINTAIN AND MONITOR STORM WATER DRAINAGE FROM 50 BRIDGES OVER WATERWAYS. (HB 2346, SECTION 25.18) |  | STATEWIDE | 99 | STATEWIDE PROJECT | UNDER CONSTRUCTION | Division 99
M-0426 | Highway | Other | VARIOUS | STATEWIDE TRAINING, EDUCATION, AND WORKFORCE DEVELOPMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT | AUTHORIZED UNDER 23 U.S.C. 504e
M-0426DIV |  |  | VARIOUS | STATEWIDE TRAINING, EDUCATION, AND WORKFORCE DEVELOPMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | NHP | ENGINEERING | 1140000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000
M-0426REG |  |  | VARIOUS | STATEWIDE TRAINING, EDUCATION, AND WORKFORCE DEVELOPMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | NHP | ENGINEERING | 1140000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000
M-0426SW |  |  | VARIOUS | STATEWIDE TRAINING, EDUCATION, AND WORKFORCE DEVELOPMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | NHP | ENGINEERING | 1520000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
M-0451 | Highway | Other | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0451DIV | Highway | Other | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 1203000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000
M-0451REG | Highway | Other | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 1203000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000
M-0451SW | Highway | Other | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 1606000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000
M-0452 | Highway | Other | VARIOUS | TOLLING/FINANCIAL FEASIBILITY STUDIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 3200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
M-0460 | Highway | Other | VARIOUS | NATIONAL SUMMER TRANSPORTATION INSTITUTE (NSTI). |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | O | ENGINEERING | 2400000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
M-0478 | Highway | Other | VARIOUS | ON-THE-JOB TRAINING PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | O | ENGINEERING | 6000000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
M-0479 | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0479A | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0479ADIV | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 7200000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
M-0479AREG | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 7200000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
M-0479ASW | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
M-0479B | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0479BDIV | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 2400000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
M-0479BREG | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 2400000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
M-0479BSW | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 3200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
M-0479DIV | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 24000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
M-0479REG | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 24000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
M-0479SW | Highway | Other | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 32000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
M-0480 | Highway | Other | VARIOUS | DISADVANTAGED BUSINESS ENTERPRISE (DBE) TRAINING AND SUPPORTIVE SERVICES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | O | ENGINEERING | 3600000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
M-0482 | Highway | Other | VARIOUS | FEDERAL STATE TRANSPORTATION INNOVATION COUNCIL (STIC) INCENTIVE FUNDED PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT | DP FUNDS REPRESENT FEDERAL STIC FUNDS. | Exempt |  | DP | IMPLEMENTATION | 400000 | FY 2025: 100000; FY 2026: 100000
M-0482 | Highway | Other | VARIOUS | FEDERAL STATE TRANSPORTATION INNOVATION COUNCIL (STIC) INCENTIVE FUNDED PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT | DP FUNDS REPRESENT FEDERAL STIC FUNDS. | Exempt |  | HF(M) | IMPLEMENTATION | 100000 | FY 2025: 25000; FY 2026: 25000
M-0505 | Highway | Other | VARIOUS | TRANSPORTATION PROGRAM MANAGEMENT UNIT (TPMU) OVERSIGHT FOR LOCALLY-ADMINISTERED PROJECTS INCLUDING PREPARATION OF AGREEMENTS AND FUNDING AUTHORIZATION REQUESTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 5000000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
M-0510 | Bike & Ped | Other | VARIOUS | NATIONAL RECREATIONAL TRAILS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  | TA | CONSTRUCTION | 19200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000
M-0515 | Highway | Other | VARIOUS | RIGHT-OF-WAY BRANCH, REVIEW OF LOCAL PUBLIC AGENCY (LPA) PROJECTS BY THE APPRAISAL SECTION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | RIGHT-OF-WAY | 4000000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
M-0534 | Highway | Other | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS
M-0534DIV | Highway | Other | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
M-0534REG | Highway | Other | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 9600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
M-0534SW | Highway | Other | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 12800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000
M-0539 | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0539DIV | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | MITIGATION | 43200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000
M-0539REG | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | MITIGATION | 43200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000
M-0539SW | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | MITIGATION | 57600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000
M-0552A | Highway | Other | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0552ADIV | Highway | Other | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 750000 | FY 2025: 300000
M-0552AREG | Highway | Other | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 750000 | FY 2025: 300000
M-0552ASW | Highway | Other | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 1000000 | FY 2025: 400000
M-0552B | Highway | Other | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0552BDIV | Highway | Other | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 924000 | FY 2025: 300000
M-0552BREG | Highway | Other | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 924000 | FY 2025: 300000
M-0552BSW | Highway | Other | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 1232000 | FY 2025: 400000
M-0552C | Highway | Other | VARIOUS | DIGITAL DELIVERY INITIATIVE. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0552CDIV | Highway | Other | VARIOUS | DIGITAL DELIVERY INITIATIVE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 150000
M-0552CREG | Highway | Other | VARIOUS | DIGITAL DELIVERY INITIATIVE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 150000
M-0552CSW | Highway | Other | VARIOUS | DIGITAL DELIVERY INITIATIVE. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 200000
M-0553A | Highway | Other | VARIOUS | TECHNICAL SERVICES. PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0553ADIV | Highway | Other | VARIOUS | INTEGRATED PROJECT DELIVERY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | T | ENGINEERING | 4350000 | FY 2025: 600000
M-0553AREG | Highway | Other | VARIOUS | INTEGRATED PROJECT DELIVERY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | T | ENGINEERING | 4350000 | FY 2025: 600000
M-0553ASW | Highway | Other | VARIOUS | INTEGRATED PROJECT DELIVERY. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | T | ENGINEERING | 5800000 | FY 2025: 800000
M-0553B | Highway | Other | VARIOUS | TECHNICAL SERVICES. PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0553BDIV | Highway | Other | VARIOUS | TRAINING AND SPECIAL PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | T | ENGINEERING | 3000000 | FY 2025: 1200000
M-0553BREG | Highway | Other | VARIOUS | TRAINING AND SPECIAL PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | T | ENGINEERING | 3000000 | FY 2025: 1200000
M-0553BSW | Highway | Other | VARIOUS | TRAINING AND SPECIAL PROJECTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Exempt |  | T | ENGINEERING | 4000000 | FY 2025: 1600000
M-0554 | Highway | Other | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0554DIV | Highway | Other | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 105000000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
M-0554REG | Highway | Other | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 105000000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
M-0554SW | Highway | Other | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 140000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000
M-0555 | Highway | Other | VARIOUS | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0555DIV | Highway | Other | VARIOUS | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | UTILITIES | 1365000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000
M-0555REG | Highway | Other | VARIOUS | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | UTILITIES | 1365000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000 | 105000
M-0555SW | Highway | Other | VARIOUS | UTILITY ENCROACHMENT AND ADMINISTRATIVE ACTIVITIES. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | UTILITIES | 1820000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000
M-0556 | Highway | Other | STATEWIDE | ADVANCED RIGHT-OF-WAY ACQUISITION ACCOUNT. REVOLVING ACCOUNT TO FUND ADVANCED RIGHT-OF-WAY ACQUISITION. FUNDS TO BE REPAID FROM THE STIP PROJECT AT THE TIME THE PROJECT IS FUNDED. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 6000000
M-0563 | Highway | Other | STATEWIDE | PROTECT FORMULA PLANNING FUNDING FOR RESILIENCE PROGRAM. |  | STATEWIDE | 99 | STATEWIDE PROJECT
M-0563A | Highway | Other | STATEWIDE | HAZARD CHARACTERIZATION AND WARNING TOOLS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | PROTCT | ENGINEERING | 3360000 | FY 2025: 840000; FY 2026: 840000
M-0563B | Highway | Other | STATEWIDE | HAZARD CORRIDOR VULNERABILITY ASSESSMENTS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | PROTCT | ENGINEERING | 1400000 | FY 2025: 350000; FY 2026: 350000
M-0563C | Highway | Other | STATEWIDE | GEOTECHNICAL ASSET MANAGEMENT (GAM) DATABASE AND LANDSLIDE MITIGATION PLANNING |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | PROTCT | ENGINEERING | 2240000 | FY 2025: 560000; FY 2026: 560000
M-0563D | Highway | Other | STATEWIDE | LIDAR DATA COLLECTION |  | ALAMANCE, CUMBERLAND, DURHAM, GUILFORD, WAKE, CASWELL, CHATHAM, GRANVILLE, HARNETT, HOKE, LEE, MONTGOMERY, MOORE, ORANGE, PERSON, RANDOLPH, RICHMOND, ROCKINGHAM, SCOTLAND | 5, 6, 7, 8 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO, Fayetteville Area MPO, Greensboro Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, High Point Urban Area MPO, Kerr-Tar RPO, Lumber River RPO, Mid-Carolina RPO, Northwest Piedmont RPO, Piedmont T |  | Statewide Mobility |  | PROTCT | ENGINEERING | 1285000
M-0563E | Highway | Other | STATEWIDE | RESILIENCE PROGRAM REPORTING, MANAGEMENT AND SUPPORT |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | PROTCT | ENGINEERING | 2550000 | FY 2025: 850000; FY 2026: 850000
P-2918 | Rail | Other | PIEDMONT CORRIDOR | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "HF" FUNDING REFLECTS STATE RAIL FUNDS | Exempt |  | CMAQ | OPERATIONS | 14069000
P-2918 | Rail | Other | PIEDMONT CORRIDOR | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "HF" FUNDING REFLECTS STATE RAIL FUNDS | Exempt |  | CMAQ | OPERATIONS | 7226000
P-2918 | Rail | Other | PIEDMONT CORRIDOR | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "HF" FUNDING REFLECTS STATE RAIL FUNDS | Exempt |  | HF | OPERATIONS | 1806000
P-2918 | Rail | Other | PIEDMONT CORRIDOR | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "HF" FUNDING REFLECTS STATE RAIL FUNDS | Exempt |  | HF | OPERATIONS | 3517000
P-2918A | Rail | Other | PIEDMONT CORRIDOR | EQUIPMENT REBUILD - 2 F59PHI LOCOMOTIVES |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-2918B | Rail | Other | PIEDMONT CORRIDOR | PURCHASE 2 USED LOCOMOTIVES |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | COMPLETE
P-2918C | Rail | Other | PIEDMONT CORRIDOR | EQUIPMENT REHABILITATION - 3 LOCOMOTIVES |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-2918D | Rail | Other | PIEDMONT CORRIDOR | EQUIPMENT REHABILITATION - 3 PASSENGER CARS |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | COMPLETE
P-2918E | Rail | Other | PIEDMONT CORRIDOR | PASSENGER TRAIN SECURITY SYSTEM, CCTV DATA NETWORK AND GENERATORS |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-2918F | Rail | Other | PIEDMONT CORRIDOR | CRISP CHARLOTTE MAINTENANCE FACILITY - TRACK EXTENSION AND SHOP BUILDING |  | MECKLENBURG | 10 | Charlotte Regional TPO | IN PROGRESS
P-2918G | Rail | Other | PIEDMONT CORRIDOR | PURCHASE 4 USED PASSENGER CARS AND REHABILITATE 7 PASSENGER CARS |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-2918H | Rail | Other | PIEDMONT CORRIDOR | CAPITAL YARD PHASE 1 IMPROVEMENTS - EXTEND TRACKS 1 AND 2, MAJOR WORK TRACK 3 |  | WAKE | 5 | Capital Area MPO | IN PROGRESS
P-2918I | Rail | Other | PIEDMONT CORRIDOR | EQUIP 9 STATIONS AND PLATFORMS WITH ADA/FRA PIDS |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS
P-5200 | Rail | Other | PIEDMONT AND NORTHERN RAILROAD | RAIL CORRIDOR BETWEEN GASTONIA AND MOUNT HOLLY INCLUDING THE BELMONT SPUR. REACTIVATION OF RAIL CORRIDOR |  | GASTON, MECKLENBURG | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO
P-5200A | Rail | Other | P & N CORRIDOR REACTIVATION | CROSSING SIGNAL CONSTRUCTION. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
P-5200B | Rail | Other | P & N CORRIDOR REACTIVATION | CROSSING SIGN/PAVEMENT MARKING INSTALLATION. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
P-5200C | Rail | Other | P & N CORRIDOR REACTIVATION | RAIL TRACK CONSTRUCTION ENGINEERING OVERSIGHT. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
P-5200D | Rail | Pre-STI (Historic) | P & N CORRIDOR REACTIVIATION | BELMONT SPUR. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | BGANY | RIGHT-OF-WAY | 50000 | FY 2025: 50000
P-5200D | Rail | Pre-STI (Historic) | P & N CORRIDOR REACTIVIATION | BELMONT SPUR. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Pre-STI (Transition) |  | BGANY | CONSTRUCTION | 850000 | FY 2025: 850000
P-5200EA | Rail | Other | P & N CORRIDOR REACTIVATION | THRIFT DEPOT RELOCATION. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5200EB | Rail | Other | P & N CORRIDOR REACTIVATION | THRIFT DEPOT STABILIZATION. |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5205 | Rail | Pre-STI (Historic) | PIEDMONT CORRIDOR | GRAHAM TO HAW RIVER. SIDING AND CURVE REALIGNMENT. |  | ALAMANCE | 7 | Burlington-Graham MPO | COMPLETED | Pre-STI (Transition)
P-5208 | Rail | Pre-STI (Historic) | PIEDMONT CORRIDOR | PIEDMONT CORRIDOR, RESTORE DOUBLE TRACK, HAYDOCK TO JUNKER. |  | CABARRUS, MECKLENBURG | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5500 | Rail | Pre-STI (Historic) | NCRR | RALEIGH UNION STATION PROJECT - PHASE I. CONSTRUCT RALEIGH TRAIN STATION AND ASSOCIATED RAIL TRACK AND SIDING IMPROVEMENTS TO INCREASE PASSENGER AND FREIGHT CAPACITY. |  | WAKE | 5 | Capital Area MPO | DP FUNDS - FEDERAL TIGER GRANT; O FUNDS - STATE LEGISLATIVE ALLOCATION FOR RAIL; PROJECT INCLUDES IN-KIND PROPERTY CONTRIBUTION BY TRIANGLE TRANSIT (CONTINGENT ON TT BOARD OF TRUSTEES APPROVAL) - 4 PARCELS TOTALING 3.5 ACRES WITH TAX VALUE OF $2.9 MILLION | Pre-STI (Transition)
P-5500A | Rail | Transition | NCRR | CSXT S-LINE, TRACK AND SIGNAL IMPROVEMENTS - BOYLAN WYE CROSSOVER |  | WAKE | 5 | Capital Area MPO | DELETED - WORK TO BE ACCOMPLISHED UNDER P-5005D.
P-5500B | Rail | Pre-STI (Historic) | NCRR | STATION SITE WORK |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5500C | Rail | Pre-STI (Historic) | NCRR | TRACK IMPROVEMENTS |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
P-5602 | Rail | Other | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS
P-5602DIV | Rail | Other | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 4800000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
P-5602REG | Rail | Other | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 4800000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
P-5602SW | Rail | Other | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 6400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000
P-5700 | Rail | STI (Prioritization) | NORFOLK SOUTHERN MAINLINE | NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION | Division 7 |  | T | CONSTRUCTION | 850000 | FY 2026: 850000
P-5700 | Rail | STI (Prioritization) | NORFOLK SOUTHERN MAINLINE | NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION | Division 7 |  | O | CONSTRUCTION | 850000 | FY 2026: 850000
P-5701 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PLATFORM, PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION. "OTHER" FUNDING REFLECTS PARTICIPATION BY TRIANGLE TRANSIT. | Division 7
P-5701A | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | T | CONSTRUCTION | 6290000
P-5701A | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | O | CONSTRUCTION | 570000
P-5701B | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT STATION PLATFORM AND REALIGN CURVE AT MILEPOST 41.4. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | T | CONSTRUCTION | 1000000 | FY 2025: 500000; FY 2026: 500000
P-5705 | Rail | STI (Prioritization) | CHARLOTTE | CHARLOTTE GATEWAY STATION. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL PRIIA GRANT AWARD = $2,578,000
P-5705A | Rail | STI (Prioritization) | CHARLOTTE | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | DP | RIGHT-OF-WAY | 500000
P-5705A | Rail | STI (Prioritization) | CHARLOTTE | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | DP | CONSTRUCTION | 2578000 | FY 2025: 908000
P-5705A | Rail | STI (Prioritization) | CHARLOTTE | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 10422000 | FY 2025: 1964000
P-5705B | Rail | STI (Prioritization) | CHARLOTTE | CHARLOTTE GATEWAY STATION - RIGHT-OF-WAY |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E
P-5705BA | Rail | STI (Prioritization) | CHARLOTTE | CHARLOTTE GATEWAY STATION - TRACK, STRUCTURE, AND SIGNALS |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E
P-5705BB | Rail | STI (Prioritization) | CHARLOTTE | CHARLOTTE GATEWAY STATION - PLATFORM AND CANOPY |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E
P-5706 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | 6.9 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 9328000 | FY 2025: 1518000; FY 2026: 1518000; FY 2027: 2276000; FY 2028: 933000; FY 2029: 933000
P-5706 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | 6.9 | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT OF WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 65999000 | FY 2030: 8249000; FY 2031: 22195000; FY 2032: 17867000; FY 2033: 12322000; FY 2034: 5366000
P-5707 | Rail | STI (Prioritization) | CSX S LINE | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | RIGHT-OF-WAY | 7000000 | FY 2025: 7000000
P-5707 | Rail | STI (Prioritization) | CSX S LINE | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | CONSTRUCTION | 42500000 | FY 2025: 425000; FY 2026: 16575000; FY 2027: 14025000; FY 2028: 9775000; FY 2029: 1700000
P-5709 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS | Region D |  | T | RIGHT-OF-WAY | 3484000
P-5709 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS | Region D |  | T | UTILITIES | 1566000
P-5709 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS | Region D |  | T | CONSTRUCTION | 25795000 | FY 2026: 10787000; FY 2027: 9916000; FY 2028: 5092000
P-5709 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. RIGHT-OF-WAY IN PROGRESS | Region D |  | O | CONSTRUCTION | 1005000 | FY 2026: 1005000
P-5711 | Rail | Other | CSX A LINE | CONSTRUCT FREIGHT RAIL AND INTERMODAL TERMINAL INFRASTRUCTURE (CCX) ALONG NATIONAL GATEWAY CORRIDOR. | 12 | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO, Upper Coastal Plain RPO |  | Statewide Mobility
P-5711A | Rail | Other | CSX A LINE | CCX INTERMODAL TERMINAL AND TRACK IMPROVEMENTS. |  | EDGECOMBE | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 43100000
P-5711C | Rail | Other | CSX A LINE | HIGHWAY IMPROVEMENTS |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility
P-5713 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | Statewide Mobility |  | T | RIGHT-OF-WAY | 3431000 | FY 2025: 858000; FY 2026: 1715000; FY 2027: 858000
P-5713 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | Statewide Mobility |  | T | UTILITIES | 952000 | FY 2025: 952000
P-5713 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | Statewide Mobility |  | T | CONSTRUCTION | 17532000 | FY 2026: 2851000; FY 2027: 10793000; FY 2028: 3888000
P-5713 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION | Statewide Mobility |  | O | CONSTRUCTION | 268000 | FY 2027: 148000; FY 2028: 105000; FY 2029: 15000
P-5714 | Rail | STI (Prioritization) | NCRR NORFOLK SOUTHERN | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION | Region D |  | T | CONSTRUCTION | 1600000 | FY 2027: 1600000
P-5714 | Rail | STI (Prioritization) | NCRR NORFOLK SOUTHERN | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION | Region D |  | O | CONSTRUCTION | 1500000 | FY 2027: 1500000
P-5715 | Rail | STI (Prioritization) | CSX | CROSSING 630607N AT NEW HOPE CHURCH ROAD IN RALEIGH. CONSTRUCT GRADE SEPARATION. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS | Region C |  | T | CONSTRUCTION | 23700000 | FY 2025: 4977000; FY 2026: 10191000; FY 2027: 6636000; FY 2028: 1896000
P-5717 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T | RIGHT-OF-WAY | 4378000
P-5717 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T | UTILITIES | 1878000
P-5717 | Rail | STI (Prioritization) | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | T | CONSTRUCTION | 34900000 | FY 2026: 5935000; FY 2027: 14018000; FY 2028: 9719000; FY 2029: 5228000
P-5718 | Rail | STI (Prioritization) | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  | T | RIGHT-OF-WAY | 37300000 | FY 2028: 9325000; FY 2029: 18650000; FY 2030: 9325000
P-5718 | Rail | STI (Prioritization) | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  | T | UTILITIES | 4500000 | FY 2028: 2250000; FY 2029: 2250000
P-5718 | Rail | STI (Prioritization) | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  | T | CONSTRUCTION | 40548000 | FY 2031: 11532000; FY 2032: 14539000; FY 2033: 9809000; FY 2034: 4668000
P-5718 | Rail | STI (Prioritization) | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734. | Region C |  | O | CONSTRUCTION | 1452000 | FY 2031: 1452000
P-5719 | Rail | STI (Prioritization) | PIEDMONT CORRIDOR | PURCHASE AND REFURBISH RAIL CARS FOR PIEDMONT SERVICE EXPANSION. |  | GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | 5, 7, 8, 9, 10 | Cabarrus-Rowan MPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO, Burlington-Graham MPO, Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP FOR STATE OF GOOD REPAIR GRANT
P-5719A | Rail | STI (Prioritization) | PIEDMONT CORRIDOR | ACQUIRE AND REBUILD 2 ADDITIONAL LOCOMOTIVES. |  | GUILFORD, WAKE, MECKLENBURG | 5, 7, 10 | Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | COMPLETE | Exempt
P-5719B | Rail | STI (Prioritization) | PIEDMONT CORRIDOR | ACQUIRE AND REFURBISH 2 COACH AND 1 LOUNGE/BAGGAGE RAIL CARS. |  | GUILFORD, WAKE, MECKLENBURG | 5, 7, 10 | Greensboro Urban Area MPO, Capital Area MPO, Charlotte Regional TPO | IN PROGRESS | Exempt
P-5719C | Rail | STI (Prioritization) | PIEDMONT CORRIDOR | NEW TRAINS AND MAINTENANCE FACILITY. |  | DAVIDSON, ALAMANCE, CABARRUS, DURHAM, GUILFORD, MECKLENBURG, ORANGE, ROWAN, WAKE | 5, 7, 9, 10 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO |  | Region C, D, E |  | DP | CONSTRUCTION | 156888000 | FY 2026: 156888000
P-5719C | Rail | STI (Prioritization) | PIEDMONT CORRIDOR | NEW TRAINS AND MAINTENANCE FACILITY. |  | DAVIDSON, ALAMANCE, CABARRUS, DURHAM, GUILFORD, MECKLENBURG, ORANGE, ROWAN, WAKE | 5, 7, 9, 10 | Capital Area MPO, High Point Urban Area MPO, Burlington-Graham MPO, Cabarrus-Rowan MPO, Charlotte Regional TPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO |  | Region C, D, E |  | T | CONSTRUCTION | 55640000 | FY 2026: 27820000; FY 2027: 27820000
P-5720 | Rail | STI (Prioritization) | CSX | CROSSING 630601X AT SR 2006 (DURANT ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307 | Region C |  | T | CONSTRUCTION | 21914000 | FY 2025: 9930000; FY 2026: 7407000; FY 2027: 4299000
P-5721 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. |  | GUILFORD | 7 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | T | CONSTRUCTION | 2035000 | FY 2026: 102000; FY 2027: 1933000
P-5721 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. |  | GUILFORD | 7 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | O | CONSTRUCTION | 2035000 | FY 2026: 2035000
P-5722 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD TRACK. |  | DAVIDSON | 9 | High Point Urban Area MPO | "O" FUNDING REPRESENTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. | Region D |  | T | CONSTRUCTION | 1019000 | FY 2027: 51000; FY 2028: 968000
P-5722 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD TRACK. |  | DAVIDSON | 9 | High Point Urban Area MPO | "O" FUNDING REPRESENTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION. | Region D |  | O | CONSTRUCTION | 1019000 | FY 2027: 1019000
P-5724 | Rail | Economic Development | CSX | RAIL SPUR FOR INDUSTRIAL ACCESS. CONSTRUCT SPINE TRACK AND TURNOUTS, AND REHABILITATE EXISTING TRACK SECTIONS. |  | SCOTLAND | 8 | Lumber River RPO | UNDER CONSTRUCTION; THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CSX; "O" FUNDING INCLUDES PARTICIPATION BY NORTH CAROLINA RAILROAD, LAURINBURG-MAXTON AIRPORT, RAIL INDUSTRIIAL ACCESS PROGRAM, AND COMMUNITY DEVELOPMENT BLOCK GRANT PROGRAM | Division 8
P-5725 | Rail | STI (Prioritization) | KANNAPOLIS | CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL, SIGNALING EQUIPMENT. |  | CABARRUS | 10 | Cabarrus-Rowan MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | CONSTRUCTION | 13500000 | FY 2025: 135000; FY 2026: 7560000; FY 2027: 4455000; FY 2028: 1350000
P-5726 | Rail | STI (Prioritization) | RAILROAD NORFOLK SOUTHERN | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | T | CONSTRUCTION | 13600000 | FY 2026: 1584000; FY 2027: 6939000; FY 2028: 4477000; FY 2029: 600000
P-5726A | Rail | STI (Prioritization) | NORFOLK SOUTHERN | SALISBURY TRAIN STATION SECOND PLATFORM AND PEDESTRIAN UNDERPASS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | T | CONSTRUCTION | 2500000 | FY 2025: 1015000; FY 2026: 1485000
P-5726B | Rail | STI (Prioritization) | NORFOLK SOUTHERN | SALISBURY NORFOLK SOUTHERN CROSSOVER RELOCATION. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D |  | T | CONSTRUCTION | 4000000 | FY 2025: 1432000; FY 2026: 2568000
P-5730 | Rail | STI (Prioritization) | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. |  | MECKLENBURG | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN. | Region E |  | T | RIGHT-OF-WAY | 13600000 | FY 2030: 3400000; FY 2031: 6800000; FY 2032: 3400000
P-5730 | Rail | STI (Prioritization) | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. |  | MECKLENBURG | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN. | Region E |  | T | CONSTRUCTION | 27465000 | FY 2033: 9499000; FY 2034: 10626000; FY 2035: 5633000 | 1707000
P-5730 | Rail | STI (Prioritization) | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. |  | MECKLENBURG | 10 | Charlotte Regional TPO | "O" FUNDS REPRESENT FUNDS FROM NORFOLK SOUTHERN. | Region E |  | O | CONSTRUCTION | 835000 | FY 2033: 8000; FY 2034: 408000; FY 2035: 101000 | 318000
P-5731 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. |  | DAVIDSON | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Division 9 |  | T | RIGHT-OF-WAY | 2400000 | FY 2025: 2400000
P-5731 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. |  | DAVIDSON | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Division 9 |  | L | RIGHT-OF-WAY | 4500000 | FY 2025: 4500000
P-5731 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. |  | DAVIDSON | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Division 9 |  | DP | CONSTRUCTION | 14050000 | FY 2026: 4356000; FY 2027: 5198000; FY 2028: 3512000; FY 2029: 984000
P-5731 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. |  | DAVIDSON | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Division 9 |  | T | CONSTRUCTION | 8550000 | FY 2026: 2839000; FY 2027: 2967000; FY 2028: 1979000; FY 2029: 765000
P-5731 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. |  | DAVIDSON | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Division 9 |  | L | CONSTRUCTION | 27200000 | FY 2026: 8742000; FY 2027: 9434000; FY 2028: 7050000; FY 2029: 1974000
P-5732 | Rail | Other | NCRR | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTI-MODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. |  | DAVIDSON | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Exempt |  | DP | CONSTRUCTION | 10950000 | FY 2025: 10950000
P-5732 | Rail | Other | NCRR | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTI-MODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. |  | DAVIDSON | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Exempt |  | O | CONSTRUCTION | 2138000 | FY 2025: 2138000
P-5732 | Rail | Other | NCRR | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTI-MODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. |  | DAVIDSON | 9 | High Point Urban Area MPO | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT | Exempt |  | L | CONSTRUCTION | 2612000 | FY 2025: 2612000
P-5733 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. |  | ROWAN | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | CMAQ | ENGINEERING | 523000
P-5733 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. |  | ROWAN | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | T | ENGINEERING | 197000
P-5733 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. |  | ROWAN | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | CMAQ | RIGHT-OF-WAY | 1454000 | FY 2025: 1454000
P-5733 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. |  | ROWAN | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | T | RIGHT-OF-WAY | 546000 | FY 2025: 546000
P-5733 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. |  | ROWAN | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | CMAQ | CONSTRUCTION | 6542000 | FY 2026: 3454000; FY 2027: 2754000; FY 2028: 334000
P-5733 | Rail | STI (Prioritization) | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. |  | ROWAN | 9 | Cabarrus-Rowan MPO | 2024 CMAQ AWARD AMOUNT IS $8,520,440, T FUNDS ARE USED AS LOCAL MATCH FOR CMAQ AWARD. PROJECT WAS SELECTED IN P5.0. | Division 9 |  | T | CONSTRUCTION | 2457000 | FY 2026: 1297000; FY 2027: 1034000; FY 2028: 126000
P-5734 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  | T | RIGHT-OF-WAY | 23400000 | FY 2028: 5850000; FY 2029: 11700000; FY 2030: 5850000
P-5734 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  | T | UTILITIES | 960000 | FY 2028: 960000
P-5734 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  | T | CONSTRUCTION | 28765000 | FY 2031: 4576000; FY 2032: 11927000; FY 2033: 8187000; FY 2034: 4075000
P-5734 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718. | Statewide Mobility |  | O | CONSTRUCTION | 835000 | FY 2031: 835000
P-5735 | Rail | STI (Prioritization) | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 3500000
P-5735 | Rail | STI (Prioritization) | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 11890000
P-5735 | Rail | STI (Prioritization) | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 810000
P-5736 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | T | RIGHT-OF-WAY | 200000 | FY 2030: 200000
P-5736 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | T | CONSTRUCTION | 4896000 | FY 2031: 3725000; FY 2032: 1171000
P-5736 | Rail | STI (Prioritization) | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Statewide Mobility |  | O | CONSTRUCTION | 4000 | FY 2031: 4000
P-5737 | Rail | STI (Prioritization) | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  | T | RIGHT-OF-WAY | 6111000
P-5737 | Rail | STI (Prioritization) | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  | T | UTILITIES | 1228000
P-5737 | Rail | STI (Prioritization) | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  | DP | CONSTRUCTION | 10000000 | FY 2026: 10000000
P-5737 | Rail | STI (Prioritization) | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. |  | WAKE | 5 | Capital Area MPO | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP GRANT. | Statewide Mobility |  | T | CONSTRUCTION | 15100000 | FY 2027: 3303000; FY 2028: 8032000; FY 2029: 3765000
P-5740 | Rail | STI (Prioritization) | CSX SE LINE | WILMINGTON BELTLINE SPEED IMPROVEMENT PROJECT. | 13 | NEW HANOVER, BRUNSWICK | 3 | Wilmington Urban Area MPO | DP FUNDS REPRESENT FEDERAL CRISI GRANT. | Statewide Mobility
P-5740A | Rail | STI (Prioritization) | CSX SE LINE | TIE AND RAIL REHABILITATION, CURVE REALIGNMENT, AND UPGRADE RAIL BRIDGES. |  | NEW HANOVER, BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | DP | CONSTRUCTION | 15522000
P-5740A | Rail | STI (Prioritization) | CSX SE LINE | TIE AND RAIL REHABILITATION, CURVE REALIGNMENT, AND UPGRADE RAIL BRIDGES. |  | NEW HANOVER, BRUNSWICK | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. | Statewide Mobility |  | T | CONSTRUCTION | 17478000 | FY 2025: 6350000
P-5740B | Rail | STI (Prioritization) | CSX SE LINE | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 2600000
P-5740B | Rail | STI (Prioritization) | CSX SE LINE | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | DP | CONSTRUCTION | 2543000 | FY 2025: 301000; FY 2026: 2033000; FY 2027: 209000
P-5740B | Rail | STI (Prioritization) | CSX SE LINE | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 1807000 | FY 2025: 289000; FY 2026: 1355000; FY 2027: 163000
P-5740C | Rail | STI (Prioritization) | CSX SE LINE | INSTALLATION OF RAILROAD GRADE CROSSING SIGNALS AND GATES AT VARIOUS AT-GRADE CROSSINGS. |  | NEW HANOVER, BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | DP | CONSTRUCTION | 5792000 | FY 2025: 5792000
P-5740C | Rail | STI (Prioritization) | CSX SE LINE | INSTALLATION OF RAILROAD GRADE CROSSING SIGNALS AND GATES AT VARIOUS AT-GRADE CROSSINGS. |  | NEW HANOVER, BRUNSWICK | 3 | Wilmington Urban Area MPO |  | Statewide Mobility |  | T | CONSTRUCTION | 4108000 | FY 2025: 2054000; FY 2026: 2054000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. |  | UNION | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | DP | RIGHT-OF-WAY | 31000 | FY 2025: 8000; FY 2026: 15000; FY 2027: 8000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. |  | UNION | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | T | RIGHT-OF-WAY | 5820000 | FY 2025: 1455000; FY 2026: 2910000; FY 2027: 1455000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. |  | UNION | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | T | UTILITIES | 826000 | FY 2025: 826000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. |  | UNION | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | DP | CONSTRUCTION | 3110000 | FY 2028: 1804000; FY 2029: 1193000; FY 2030: 113000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. |  | UNION | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | T | CONSTRUCTION | 19740000 | FY 2028: 6843000; FY 2029: 9901000; FY 2030: 2996000
P-5744 | Rail | STI (Prioritization) | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPARATION. |  | UNION | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX. | Statewide Mobility |  | O | CONSTRUCTION | 250000 | FY 2028: 145000; FY 2029: 96000; FY 2030: 9000
P-5747 | Rail | STI (Prioritization) | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Region D |  | T | RIGHT-OF-WAY | 2300000 | FY 2026: 575000; FY 2027: 1150000; FY 2028: 575000
P-5747 | Rail | STI (Prioritization) | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Region D |  | T | CONSTRUCTION | 23658000 | FY 2028: 237000; FY 2029: 15717000; FY 2030: 6070000; FY 2031: 1634000
P-5747 | Rail | STI (Prioritization) | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Region D |  | O | CONSTRUCTION | 1242000 | FY 2028: 1242000
P-5748 | Rail | STI (Prioritization) | CSX SG LINE | CONSTRUCT RAIL SIDING AND GRADE SEPARATION IN VICINITY OF SR 1300 (HELMS ROAD) AND CLOSE AT-GRADE CROSSINGS AT SR 1300 (HELMS ROAD) AND SR 1432 (TORY PATH). |  | UNION | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS; OTHER FUNDING PROVIDED BY CSX.
P-5748A | Rail | STI (Prioritization) | CSX SG LINE | CONSTRUCT RAIL SIDING IN WAXHAW |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region E |  | T | CONSTRUCTION | 5894000 | FY 2025: 1938000; FY 2026: 354000
P-5748B | Rail | STI (Prioritization) | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). |  | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | RIGHT-OF-WAY | 5000000
P-5748B | Rail | STI (Prioritization) | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). |  | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | UTILITIES | 378000
P-5748B | Rail | STI (Prioritization) | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). |  | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | DP | CONSTRUCTION | 4700000 | FY 2026: 47000; FY 2027: 2397000; FY 2028: 1598000; FY 2029: 658000
P-5748B | Rail | STI (Prioritization) | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). |  | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T | CONSTRUCTION | 19251000 | FY 2026: 193000; FY 2027: 9818000; FY 2028: 6545000; FY 2029: 2695000
P-5748B | Rail | STI (Prioritization) | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). |  | UNION | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | O | CONSTRUCTION | 251000 | FY 2026: 3000; FY 2027: 128000; FY 2028: 85000; FY 2029: 35000
P-5750 | Rail | STI (Prioritization) | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON |  | ANSON | 10 | Rocky River RPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
P-5750A | Rail | STI (Prioritization) | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. |  | ANSON | 10 | Rocky River RPO |  | Region E |  | DP | CONSTRUCTION | 3200000 | FY 2025: 1584000; FY 2026: 471000
P-5750A | Rail | STI (Prioritization) | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. |  | ANSON | 10 | Rocky River RPO |  | Region E |  | T | CONSTRUCTION | 9837000 | FY 2025: 4868000; FY 2026: 1449000
P-5750B | Rail | STI (Prioritization) | CSX SF LINE | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. |  | ANSON | 10 | Rocky River RPO |  | Region E |  | T | RIGHT-OF-WAY | 2000000 | FY 2029: 2000000
P-5750B | Rail | STI (Prioritization) | CSX SF LINE | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. |  | ANSON | 10 | Rocky River RPO |  | Region E |  | T | CONSTRUCTION | 16380000 | FY 2031: 2910000; FY 2032: 8531000; FY 2033: 4265000; FY 2034: 674000
P-5751 | Rail | STI (Prioritization) | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. |  | DAVIDSON | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5000000
P-5751 | Rail | STI (Prioritization) | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. |  | DAVIDSON | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 21294000
P-5751 | Rail | STI (Prioritization) | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. |  | DAVIDSON | 9 | High Point Urban Area MPO | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION | Division 9 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | O | CONSTRUCTION | 709000
P-5753 | Rail | Other | CSX S-LINE | CSX S-LINE FROM RALEIGH TO VIRGINIA STATE LINE AND CSX SA-LINE FROM RALEIGH TO WELDON. AQUIRE RIGHT OF WAY, UPGRADE EXISTING TRACK AND CONSTRUCT NEW TRACK. | 50 | FRANKLIN, VANCE, WAKE, WARREN | 5 | Capital Area MPO, Kerr-Tar RPO
P-5753A | Rail | Other | CSX S-LINE, CSX SA-LINE. | RALEIGH TO NC 98. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AA | Rail | Other | CSX S-LINE | RALEIGH UNION STATION TO NC 98 - S-LINE RAIL IMPROVEMENTS. | 28.66 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AE | Rail | Other | CSX S-LINE | HARGETT STREET, MORGAN STREET AND CAPITAL BOULEVARD ROADWAY IMPROVEMENTS AND PEDESTRIAN OVERPASS AT JONES STREET. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AF | Rail | Other | CSX S-LINE | WHITAKER MILL ROAD ROADWAY IMPROVEMENTS. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AG | Rail | Other | CSX S-LINE | HIGHWOODS BOULEVARD GRADE SEPERATION. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility
P-5753AH | Rail | Other | CSX S-LINE | GRESHAM LAKE AND LIGON MILL GRADE SEPARATIONS AND ROADWAY IMPROVEMENTS AT SEAWELL AND FRIENDSHIP CHAPEL ROAD. |  | WAKE | 5 | Capital Area MPO |  | Statewide Mobility
P-5753B | Rail | Other | CSX S-LINE | NC 98 TO FRANKLINTON. |  | WAKE, FRANKLIN, VANCE | 5 | Capital Area MPO, Kerr-Tar RPO |  | Statewide Mobility
P-5753BA | Rail | Other | CSX S-LINE | NC 98 TO FRANKLINTON - S-LINE RAIL IMPROVEMENTS. | 16.88 | WAKE, FRANKLIN | 5 | Capital Area MPO |  | Statewide Mobility
P-5753BD | Rail | Other | CSX S-LINE | HOLDING AVENUE GRADE SEPARATION, ELM AVENUE IMPROVEMENTS AND BRICK STREET PEDESTRIAN CROSSING. |  | FRANKLIN | 5 | Capital Area MPO |  | Statewide Mobility
P-5753BE | Rail | Other | CSX S-LINE | MAIN STREET AND NC 96 BYPASS GRADE SEPARATION AND YOUNGSVILLE ROADWAY IMPROVEMENTS. |  | FRANKLIN | 5 | Capital Area MPO |  | Statewide Mobility
P-5753BF | Rail | Other | CSX S-LINE | BERT WINSTON ROAD AND CEDAR CREEK ROAD GRADE SEPARATION AND FRANKLINTON ROADWAY IMPROVEMENTS. |  | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753BG | Rail | Other | CSX S-LINE | SOUTH KITRELL ROADWAY IMPROVEMENTS. |  | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753BH | Rail | Other | CSX S-LINE | NORTH KITRELL ROADWAY IMPROVEMENTS INLCUDING MCCLANAHAN GRADE SEPARATION AND PETER GILL ROAD. |  | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753C | Rail | Other | CSX S-LINE | FRANKLINTON TO RIDGEWAY. |  | VANCE, WARREN | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CA | Rail | Other | CSX S-LINE | FRANKLINTON TO RIDGEWAY - S-LINE RAIL IMPROVEMENTS. | 36.46 | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CD | Rail | Other | CSX S-LINE | BEAR POND ROAD GRADE SEPARATION. |  | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CE | Rail | Other | CSX S-LINE | JP TAYLOR ROAD GRADE SEPARATION AND SOUTH HENDERSON ROADWAY IMPROVEMENTS. |  | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CF | Rail | Other | CSX S-LINE | ALEXANDER AVENUE GRADE SEPARATION AND DABNEY DRIVE ROADWAY IMPROVEMENTS. |  | VANCE | 5 | Kerr-Tar RPO |  | Region C |  | T | RIGHT-OF-WAY | 9000000 | FY 2030: 2250000; FY 2031: 2250000; FY 2032: 2250000; FY 2033: 2250000
P-5753CF | Rail | Other | CSX S-LINE | ALEXANDER AVENUE GRADE SEPARATION AND DABNEY DRIVE ROADWAY IMPROVEMENTS. |  | VANCE | 5 | Kerr-Tar RPO |  | Region C |  | T | UTILITIES | 800000 | FY 2030: 800000
P-5753CF | Rail | Other | CSX S-LINE | ALEXANDER AVENUE GRADE SEPARATION AND DABNEY DRIVE ROADWAY IMPROVEMENTS. |  | VANCE | 5 | Kerr-Tar RPO |  | Region C |  | T | CONSTRUCTION | 20000000 | FY 2033: 5000000; FY 2034: 5000000; FY 2035: 5000000 | 5000000
P-5753CG | Rail | Other | CSX S-LINE | ANDREWS GRADE SEPARATION AND DOWNTOWN ROADWAY IMPROVEMENTS. |  | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CH | Rail | Other | CSX S-LINE | WARRENTON ROAD IMPROVEMENTS AND GREYSTONE GRADE SEPARATION. |  | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CI | Rail | Other | CSX S-LINE | BROOKSTONE ROAD GRADE SEPARATION AND CARROLL STREET GRADE SEPARATION. |  | VANCE | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753CJ | Rail | Other | CSX S-LINE | MANSON AXTELL ROAD GRADE SEPARATION. |  | WARREN | 5 |  |  | Statewide Mobility
P-5753D | Rail | Other | CSX S-LINE | RIDGEWAY TO PASCHALL |  | WARREN | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753DA | Rail | Other | CSX S-LINE | RIDGEWAY TO THE VA STATE LINE - S-LINE RAIL IMPROVEMENTS. | 13.51 | WARREN | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753DC | Rail | Other | CSX S-LINE | SOUL CITY BOULEVARD ROADWAY IMPROVEMENTS INCLUDING DREWRY GRADE SEPARATION. |  | WARREN | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753DD | Rail | Other | CSX S-LINE | NORLINA ROADWAY IMPROVEMENTS. |  | WARREN | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5753DE | Rail | Other | CSX S-LINE | WISE ROADWAY IMPROVEMENTS INCLUDING FELTS ROAD. |  | WARREN | 5 | Kerr-Tar RPO |  | Statewide Mobility
P-5754 | Rail | Other | SR 2623 (TRAILER DRIVE) | IMPROVE AT-GRADE CROSSING WITH NORFOLK SOUTHERN RAILROAD (CROSSING NUMBER 910 618A, MP O4.11) |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN | Exempt |  | O | ENGINEERING | 50000
P-5754 | Rail | Other | SR 2623 (TRAILER DRIVE) | IMPROVE AT-GRADE CROSSING WITH NORFOLK SOUTHERN RAILROAD (CROSSING NUMBER 910 618A, MP O4.11) |  | MECKLENBURG | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN | Exempt |  | O | CONSTRUCTION | 1200000
R-0204 | Highway | STI (Prioritization) | US 221 - NC 226 | SR 1434 TO SR 1153. WIDEN TO MULTI-LANES, WITH A BYPASS OF MARION. | 12.4 | McDOWELL | 13 | Foothills RPO
R-0204A | Highway | Pre-STI (Historic) | US 221 - NC 226 | SR 1434 NORTH OF MARION TO US 221-NC 226 BUSINESS |  | McDOWELL | 13 | Foothills RPO | COMPLETE
R-0204B | Highway | Pre-STI (Historic) | US 221 (MARION BYPASS) | US 221-NC 226 BUSINESS TO SOUTH OF SOUTHERN RAILWAY. |  | McDOWELL | 13 | Foothills RPO | COMPLETE
R-0204C | Highway | Pre-STI (Historic) | US 221 (MARION BYPASS) | SOUTH OF SOUTHERN RAILWAY TO US 221-NC 226 INTERSECTION SOUTH OF MARION | 0.5 | McDOWELL | 13 | Foothills RPO | COMPLETE
R-0204D | Highway | STI (Prioritization) | US 221 | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | 0.5 | McDOWELL | 13 | Foothills RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3000000 | [11 empty] | 3000000
R-0204D | Highway | STI (Prioritization) | US 221 | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | 0.5 | McDOWELL | 13 | Foothills RPO |  | Not Funded |  | T | UTILITIES | 500000 | [11 empty] | 500000
R-0204D | Highway | STI (Prioritization) | US 221 | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | 0.5 | McDOWELL | 13 | Foothills RPO |  | Not Funded |  | T | CONSTRUCTION | 32500000 | [11 empty] | 32500000
R-0204EA | Highway | STI (Prioritization) | US 221 | I-40 INTERCHANGE. IMPROVE INTERCHANGE. | 2.13 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 20100000 | FY 2026: 202000; FY 2027: 6224000; FY 2028: 6224000; FY 2029: 3430000; FY 2030: 4020000
R-0204EA | Highway | STI (Prioritization) | US 221 | I-40 INTERCHANGE. IMPROVE INTERCHANGE. | 2.13 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | BGANY | UTILITIES | 1600000 | FY 2026: 800000; FY 2027: 800000
R-0204EA | Highway | STI (Prioritization) | US 221 | I-40 INTERCHANGE. IMPROVE INTERCHANGE. | 2.13 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | BGANY | CONSTRUCTION | 42700000 | FY 2029: 6335000; FY 2030: 12822000; FY 2031: 11317000; FY 2032: 8449000; FY 2033: 3777000
R-0204EB | Highway | STI (Prioritization) | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | 2.13 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | BGANY | RIGHT-OF-WAY | 4000000 | FY 2030: 40000; FY 2031: 1239000; FY 2032: 1239000; FY 2033: 682000; FY 2034: 800000
R-0204EB | Highway | STI (Prioritization) | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | 2.13 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | BGANY | UTILITIES | 2200000 | FY 2030: 1100000; FY 2031: 1100000
R-0204EB | Highway | STI (Prioritization) | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | 2.13 | McDOWELL | 13 | Foothills RPO |  | Division 13 |  | BGANY | CONSTRUCTION | 33400000 | FY 2033: 4955000; FY 2034: 10029000; FY 2035: 8852000 | 9564000
R-0211EC | Highway | STI (Prioritization) | I-485 | SR 3468 (WEDDINGTON ROAD). CONSTRUCT INTERCHANGE. | 1 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | T | CONSTRUCTION | 9000000
R-0623 | Highway | Transition | NC 24 / NC 27 | TROY BYPASS, WEST OF SR 1138 (DAIRY ROAD) TO EAST OF LITTLE RIVER. FOUR LANES, PART ON NEW LOCATION. | 5.42 | MONTGOMERY | 8 | Piedmont Triad RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
R-1015 | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 10.1 | CRAVEN | 2 | Down East RPO, New Bern Area MPO | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8M FOR RIGHT-OF-WAY, $2.2M FOR UTILITIES, AND $100M FOR CONSTRUCTION, PAYBACK FY 2019 - 2033.
R-1015DIV | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | NHP | GARVEE ROW | 2445000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000
R-1015DIV | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | NHP | GARVEE UTL | 1425000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000
R-1015DIV | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | T(M) | RIGHT-OF-WAY | 158000
R-1015DIV | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | T(M) | UTILITIES | 92000
R-1015DIV | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | NHP | GARVEE CON | 60060000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000
R-1015DIV | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | NHP | CONSTRUCTION | 25732000
R-1015DIV | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Division 2 |  | T(M) | CONSTRUCTION | 28380000
R-1015REG | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | NHP | GARVEE ROW | 2445000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000 | 163000
R-1015REG | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | NHP | GARVEE UTL | 1425000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000
R-1015REG | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | T(M) | RIGHT-OF-WAY | 158000
R-1015REG | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | T(M) | UTILITIES | 92000
R-1015REG | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | NHP | GARVEE CON | 60060000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000
R-1015REG | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | NHP | CONSTRUCTION | 25731000
R-1015REG | Highway | STI (Prioritization) | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 12.31 | CRAVEN | 2 | New Bern Area MPO | SEE PARENT PROJECT FOR GARVEE DETAILS. | Region B |  | T(M) | CONSTRUCTION | 19916000
R-2220 | Highway | STI (Prioritization) | US 64 | US 64, EAST OF I-85 BUSINESS IN LEXINGTON TO ASHEBORO BYPASS. WIDEN TO MULTI-LANES. |  | DAVIDSON, RANDOLPH | 8, 9 | High Point Urban Area MPO, Piedmont Triad RPO
R-2220A | Highway | STI (Prioritization) | US 64 | US 64, I-85 BUSINESS IN LEXINGTON TO EAST OF I-85. |  | DAVIDSON | 9 | High Point Urban Area MPO | COMPLETE
R-2220B | Highway | STI (Prioritization) | US 64 | I-85 EAST OF LEXINGTON TO NC 109 |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 30992000 | [11 empty] | 30992000
R-2220B | Highway | STI (Prioritization) | US 64 | I-85 EAST OF LEXINGTON TO NC 109 |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Not Funded |  | T | UTILITIES | 5635000 | [11 empty] | 5635000
R-2220B | Highway | STI (Prioritization) | US 64 | I-85 EAST OF LEXINGTON TO NC 109 |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 40572000 | [11 empty] | 40572000
R-2220C | Highway | STI (Prioritization) | US 64 | NC 109 TO SR 1409 (LAKE PARK ROAD) |  | RANDOLPH, DAVIDSON | 8, 9 |  |  | Not Funded |  | T | RIGHT-OF-WAY | 13746000 | [11 empty] | 13746000
R-2220C | Highway | STI (Prioritization) | US 64 | NC 109 TO SR 1409 (LAKE PARK ROAD) |  | RANDOLPH, DAVIDSON | 8, 9 |  |  | Not Funded |  | T | UTILITIES | 1650000 | [11 empty] | 1650000
R-2220C | Highway | STI (Prioritization) | US 64 | NC 109 TO SR 1409 (LAKE PARK ROAD) |  | RANDOLPH, DAVIDSON | 8, 9 |  |  | Not Funded |  | T | CONSTRUCTION | 56452000 | [11 empty] | 56452000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | 6.56 | RANDOLPH | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 11100000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | 6.56 | RANDOLPH | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 5000000
R-2220DA | Highway | STI (Prioritization) | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | 6.56 | RANDOLPH | 8 | Piedmont Triad RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 117100000
R-2233 | Highway | STI (Prioritization) | US 221 | SOUTH CAROLINA STATE LINE TO NORTH OF SR 1366 (ROPER LOOP ROAD). WIDEN TO MULTI-LANES WITH BYPASS OF RUTHERFORDTON ON NEW LOCATION. | 18.2 | RUTHERFORD | 13 | Foothills RPO
R-2233AA | Highway | Pre-STI (Historic) | US 221 | SOUTH CAROLINA STATE LINE TO SOUTH OF FLOYD'S CREEK | 3.3 | RUTHERFORD | 13 | Foothills RPO | COMPLETE | Division 13
R-2233AB | Highway | Pre-STI (Historic) | US 221 | SOUTH OF FLOYD'S CREEK TO NORTH OF US 74 BYPASS | 6.2 | RUTHERFORD | 13 | Foothills RPO | COMPLETE
R-2233BA | Highway | STI (Prioritization) | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 4.52 | RUTHERFORD | 13 | Foothills RPO | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 13 |  | T | RIGHT-OF-WAY | 18100000 | FY 2025: 2228000; FY 2026: 4455000; FY 2027: 4455000; FY 2028: 3342000; FY 2029: 3620000
R-2233BA | Highway | STI (Prioritization) | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 4.52 | RUTHERFORD | 13 | Foothills RPO | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 13 |  | T | UTILITIES | 3000000 | FY 2025: 1500000; FY 2026: 1500000
R-2233BA | Highway | STI (Prioritization) | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 4.52 | RUTHERFORD | 13 | Foothills RPO | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 13 |  | T | BUILD NC CON | 45750000 |  |  |  | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 3050000 | 21350000
R-2233BA | Highway | STI (Prioritization) | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | 4.52 | RUTHERFORD | 13 | Foothills RPO | NC BUILD BOND FUNDING: $30M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 13 |  | T | CONSTRUCTION | 115200000 | FY 2028: 0; FY 2029: 17916000; FY 2030: 37752000; FY 2031: 33396000; FY 2032: 26136000
R-2233BB | Highway | STI (Prioritization) | US 221 | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | 3.51 | RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 13 |  | T | RIGHT-OF-WAY | 20000000
R-2233BB | Highway | STI (Prioritization) | US 221 | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | 3.51 | RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 13 |  | T | BUILD NC CON | 32175000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000 | 2145000
R-2233BB | Highway | STI (Prioritization) | US 221 | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | 3.51 | RUTHERFORD | 13 | Foothills RPO | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 13 |  | T | CONSTRUCTION | 100622000 | FY 2025: 26091000; FY 2026: 26488000; FY 2027: 15000000
R-2246 | Highway | STI (Prioritization) | GEORGE LILES PARKWAY | NC 49 TO SOUTH OF I-85. WIDEN TO FOUR LANES DIVIDED, SOME NEW LOCATION. | 6.5 | CABARRUS | 10 | Cabarrus-Rowan MPO
R-2246A | Highway | STI (Prioritization) | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD). | 1.59 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 4100000
R-2246A | Highway | STI (Prioritization) | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD). | 1.59 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 8800000
R-2246A | Highway | STI (Prioritization) | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD). | 1.59 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 42100000
R-2246B | Highway | Pre-STI (Historic) | GEORGE LILES PARKWAY | SR 1304 (ROBERTA ROAD) TO SR 1431 (WEDDINGTON ROAD). | 2.98 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE
R-2246C | Highway | Pre-STI (Historic) | GEORGE LILES PARKWAY | SR 1431 (WEDDINGTON ROAD) TO SOUTH OF I-85. | 1.236 | CABARRUS | 10 | Cabarrus-Rowan MPO | COMPLETE
R-2247 | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, I-40 TO US 52. FOUR LANE EXPRESSWAY ON NEW LOCATION., INCLUDING ITS DEPLOYMENT. | 17.4 | FORSYTH | 9 | Winston-Salem Area TPO
R-2247A | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | 1.95 | FORSYTH | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 13200000 | [11 empty] | 13200000
R-2247A | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | 1.95 | FORSYTH | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | UTILITIES | 18900000 | [11 empty] | 18900000
R-2247A | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | 1.95 | FORSYTH | 9 | Winston-Salem Area TPO |  | Not Funded |  | NHP | CONSTRUCTION | 39101000 | [11 empty] | 39101000
R-2247B | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | 1.43 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 31900000
R-2247B | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | 1.43 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3000000
R-2247B | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | 1.43 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 149499000
R-2247CA | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | 1 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 500000
R-2247CA | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | 1 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 261000
R-2247CA | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | 1 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 140900000
R-2247CB | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | 3.24 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 11000000
R-2247CB | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | 3.24 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 14000000
R-2247CB | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | 3.24 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 92002000
R-2247CC | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, MUDDY CREEK. REPLACE BRIDGE NO. 221 AND BRIDGE NO. 222 |  | FORSYTH | 9 | Winston-Salem Area TPO | COMPLETE - WORK ACCOMPLISHED UNDER B-4507
R-2247CD | Highway | STI (Prioritization) | SR 1891 / NON-SYSTEM (PEACE HAVEN ROAD) | SR 1891 / NON-SYSTEM (PEACE HAVEN ROAD) - US 421 INTERCHANGE AND APPROACHES | 1 | FORSYTH | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247EC | Statewide Mobility
R-2247D | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | 4.61 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D |  | T | RIGHT-OF-WAY | 2299000 | FY 2028: 438000; FY 2029: 1051000; FY 2030: 350000; FY 2031: 230000; FY 2032: 230000
R-2247D | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | 4.61 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D |  | T | UTILITIES | 6500000 | FY 2028: 3250000; FY 2029: 3250000
R-2247D | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | 4.61 | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D |  | T | CONSTRUCTION | 159100000 | FY 2031: 28638000; FY 2032: 54094000; FY 2033: 41366000; FY 2034: 30229000; FY 2035: 4773000
R-2247EA | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | 4.53 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE) | Region D |  | T | RIGHT-OF-WAY | 19700000 | FY 2027: 5000000; FY 2028: 3579000; FY 2029: 6136000; FY 2030: 2045000; FY 2031: 2940000
R-2247EA | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | 4.53 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE) | Region D |  | T | UTILITIES | 6700000 | FY 2027: 3350000; FY 2028: 3350000
R-2247EA | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | 4.53 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE) | Region D |  | T | BUILD NC CON | 41175000 | FY 2030: 2745000; FY 2031: 2745000; FY 2032: 2745000; FY 2033: 2745000; FY 2034: 2745000; FY 2035: 2745000 | 24705000
R-2247EA | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | 4.53 | FORSYTH | 9 | Winston-Salem Area TPO | BUILD NC BONDS: $27M FOR CONSTRUCTION - PAYBACK 2030-2044 (FY 2030 / YR 10 SALE) | Region D |  | NHP | CONSTRUCTION | 243400000 | FY 2030: 35192000; FY 2031: 67600000; FY 2032: 56784000; FY 2033: 43264000; FY 2034: 40560000
R-2247EB | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE AT US 52 | 2.3 | FORSYTH | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032 | Statewide Mobility |  | T | RIGHT-OF-WAY | 517000 | FY 2025: 517000
R-2247EB | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE AT US 52 | 2.3 | FORSYTH | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032 | Statewide Mobility |  | NHP | GARVEE CON | 83655000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000 | 6435000
R-2247EB | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE AT US 52 | 2.3 | FORSYTH | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032 | Statewide Mobility |  | BGDA | CONSTRUCTION | 3082000
R-2247EC | Highway | STI (Prioritization) | US 52 / FUTURE I-74 | NC 65 INTERCHANGE. RECONSTRUCT INTERCHANGE. | 1 | FORSYTH | 9 | Winston-Salem Area TPO | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247CD | Statewide Mobility
R-2250 | Highway | Pre-STI (Historic) | NC 11/NC 903 (GREENVILLE SOUTHWEST BYPASS) | NC 11 TO US 264 (GREENVILLE BYPASS). CONSTRUCT FOUR LANE DIVIDED FACILITY ON NEW LOCATION WITH BYPASS OF WINTERVILLE. | 11.25 | PITT | 2 | Greenville Urban Area MPO | UNDER CONSTRUCTION. | Pre-STI (Transition) |  | T | CONSTRUCTION | 750000
R-2303 | Highway | STI (Prioritization) | NC 24 | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO I-40 IN DUPLIN COUNTY AT WARSAW. FOUR LANES DIVIDED, PART ON NEW LOCATION. | 39.7 | SAMPSON, CUMBERLAND, DUPLIN | 3, 6 | Mid-Carolina RPO, Fayetteville Area MPO, Eastern Carolina RPO
R-2303A | Highway | Pre-STI (Historic) | NC 24 | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO SR 1853 (JOHN NUNNERY ROAD). | 6.15 | CUMBERLAND | 6 | Mid-Carolina RPO, Fayetteville Area MPO | COMPLETED. | Pre-STI (Transition)
R-2303B | Highway | Pre-STI (Historic) | NC 24 | SR 1853 (JOHN NUNNERY ROAD) IN CUMBERLAND COUNTY TO SR 1404 (DOWDY ROAD) IN SAMPSON COUNTY. | 6.95 | SAMPSON, CUMBERLAND | 3, 6 | Mid-Carolina RPO | COMPLETED. | Pre-STI (Transition)
R-2303C | Highway | Transition | NC 24 | SR 1404 (DOWDY ROAD) TO SR 1303 (MITCHELL LOOP ROAD). | 6.12 | SAMPSON | 3 | Mid-Carolina RPO | COMPLETED. | Pre-STI (Transition)
R-2303D | Highway | Transition | NC 24 | SR 1303 (MITCHELL LOOP ROAD) TO US 421/US 701/SR 1296 (SUNSET AVENUE). | 6.9 | SAMPSON | 3 | Mid-Carolina RPO | COMPLETED. | Pre-STI (Transition)
R-2303DA | Highway | Pre-STI (Historic) | NC 24 | WEST OF SR 1262 (AIRPORT ROAD) TO EAST OF US 421. |  | SAMPSON | 3 | Mid-Carolina RPO | COMPLETED.
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 4.77 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | ENGINEERING | 4395000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 4.77 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | ENGINEERING | 660000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 4.77 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | BUILD NC ROW | 4395000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000 | 293000
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 4.77 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | BUILD NC CON | 25455000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000 | 1697000
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 4.77 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | BUILD NC CON | 5955000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000 | 397000
R-2303E | Highway | STI (Prioritization) | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | 4.77 | SAMPSON | 3 | Mid-Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 3 |  | T | CONSTRUCTION | 6986000
R-2303F | Highway | STI (Prioritization) | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | 9.61 | SAMPSON, DUPLIN | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | Not Funded |  | T | RIGHT-OF-WAY | 35700000 | [11 empty] | 35700000
R-2303F | Highway | STI (Prioritization) | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | 9.61 | SAMPSON, DUPLIN | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | Not Funded |  | T | UTILITIES | 2300000 | [11 empty] | 2300000
R-2303F | Highway | STI (Prioritization) | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | 9.61 | SAMPSON, DUPLIN | 3 | Mid-Carolina RPO, Eastern Carolina RPO | PLANNING/DESIGN IN PROGRESS. | Not Funded |  | T | CONSTRUCTION | 338100000 | [11 empty] | 338100000
R-2307 | Highway | STI (Prioritization) | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO US 21. WIDEN TO MULTI-LANES. | 14.8 | CATAWBA, IREDELL, LINCOLN | 12 | Greater Hickory MPO, Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | SEGMENT B INCORPORATES WORK PREVIOUSLY UNDER I-5717.
R-2307A | Highway | STI (Prioritization) | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 7.94 | CATAWBA, LINCOLN | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 155000000
R-2307A | Highway | STI (Prioritization) | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 7.94 | CATAWBA, LINCOLN | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9500000
R-2307A | Highway | STI (Prioritization) | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | 7.94 | CATAWBA, LINCOLN | 12 | Greater Hickory MPO, Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 207200000
R-2307B | Highway | STI (Prioritization) | NC 150 | SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | 6.9 | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION FUNDED WITH TOLL CREDITS. BUILD NC BONDS: $50M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); $22.5M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE) | Region F |  | T | BUILD NC CON | 76245000 |  |  | 5083000 | 5083000 | 5083000 | 5083000 | 5083000 | 5083000 | 5083000 | 5083000 | 5083000 | 30498000
R-2307B | Highway | STI (Prioritization) | NC 150 | SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | 6.9 | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION FUNDED WITH TOLL CREDITS. BUILD NC BONDS: $50M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); $22.5M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE) | Region F |  | T | BUILD NC CON | 34320000 |  |  |  |  | 2288000 | 2288000 | 2288000 | 2288000 | 2288000 | 2288000 | 2288000 | 18304000
R-2307B | Highway | STI (Prioritization) | NC 150 | SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | 6.9 | IREDELL, CATAWBA | 12 | Charlotte Regional TPO, Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. CONSTRUCTION FUNDED WITH TOLL CREDITS. BUILD NC BONDS: $50M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE); $22.5M FOR CONSTRUCTION, PAYBACK FY 2029-2043 (FY 2029 / YR 9 SALE) | Region F |  | T | CONSTRUCTION | 216771000 | FY 2025: 60533000; FY 2026: 72386000; FY 2027: 13699000; FY 2028: 52117000; FY 2029: 18036000
R-2307BA | Highway | STI (Prioritization) | NC 150 | GOOD LUCK LANE TO MORRISON PLANTATION PARKWAY. EXTEND EASTBOUND RIGHT AND THROUGH LANE. | 0.28 | IREDELL | 12 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Region F |  | T | CONSTRUCTION | 1600000
R-2409C | Highway | Transition | US 64 | WEST OF NC 281 N NEAR LAKE TOXAWAY TO INDIAN CREEK. WIDENING AND REALIGNMENT. | 1.44 | TRANSYLVANIA | 14 | Land-of-Sky RPO | COMPLETE | Pre-STI (Transition)
R-2413 | Highway | Pre-STI (Historic) | FUTURE I-73 | NC 68 AT SR 2011 (EDGEFIELD ROAD) IN GUILFORD COUNTY TO US 220-NC 68 INTERSECTION IN ROCKINGHAM COUNTY. FOUR-LANE FREEWAY, ON NEW LOCATION, NC 68 TO US 220 AND FOUR LANES ALONG US 220 TO NC 68 IN ROCKINGHAM COUNTY. | 12.1 | GUILFORD, ROCKINGHAM | 7 | Greensboro Urban Area MPO, Piedmont Triad RPO |  | Pre-STI (Transition)
R-2413A | Highway | Transition | FUTURE I-73 | FOUR LANES AT SR 2011 (EDGEFIELD ROAD) TO SR 2127 (BROOK BANK ROAD) | 4 | GUILFORD | 7 | Greensboro Urban Area MPO | COMBINED WITH I-5110 AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION |  |  | T | CONSTRUCTION | 55000
R-2413B | Highway | Transition | FUTURE I-73 | SR 2127 (BROOK BANK ROAD) TO HAW RIVER | 4.4 | GUILFORD | 7 | Greensboro Urban Area MPO | COMBINED WITH I-5110 AND R-2413A FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
R-2413C | Highway | Pre-STI (Historic) | US 220 / FUTURE I-73 | HAW RIVER TO NC 68-US 220 INTERSECTION | 5.071 | ROCKINGHAM, GUILFORD | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO | UNDER CONSTRUCTION
R-2413CA | Highway | Pre-STI (Historic) | US 220 / FUTURE I-73 | NC 68 INTERSECTION - CONVERT AT-GRADE INTERSECTION TO INTERCHANGE | 1 | ROCKINGHAM | 7 | Piedmont Triad RPO | IN PROGRESS | Pre-STI (Transition)
R-2501 | Highway | STI (Prioritization) | US 1 | SOUTH CAROLINA STATE LINE TO SR 1001 (MARSTON ROAD). WIDEN TO FOUR LANES WITH VARIABLE WIDTH MEDIAN WITH BYPASS OF ROCKINGHAM ON NEW LOCATION. | 24.1 | RICHMOND | 8 | Lumber River RPO
R-2501A | Highway | STI (Prioritization) | US 1 | SOUTH CAROLINA STATE LINE TO SR 1104 (OSBORNE ROAD) | 5.089 | RICHMOND | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | RIGHT-OF-WAY | 4500000 | [11 empty] | 4500000
R-2501A | Highway | STI (Prioritization) | US 1 | SOUTH CAROLINA STATE LINE TO SR 1104 (OSBORNE ROAD) | 5.089 | RICHMOND | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | CONSTRUCTION | 25700000 | [11 empty] | 25700000
R-2501BA | Highway | STI (Prioritization) | US 1 | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | 5.282 | RICHMOND | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | RIGHT-OF-WAY | 5519000 | [11 empty] | 5519000
R-2501BA | Highway | STI (Prioritization) | US 1 | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | 5.282 | RICHMOND | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | UTILITIES | 908000 | [11 empty] | 908000
R-2501BA | Highway | STI (Prioritization) | US 1 | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | 5.282 | RICHMOND | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | CONSTRUCTION | 40501000 | [11 empty] | 40501000
R-2501BB | Highway | STI (Prioritization) | US 1 | US 74 BYPASS TO US 74 BUSINESS | 4.07 | RICHMOND | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | RIGHT-OF-WAY | 13300000 | [11 empty] | 13300000
R-2501BB | Highway | STI (Prioritization) | US 1 | US 74 BYPASS TO US 74 BUSINESS | 4.07 | RICHMOND | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | UTILITIES | 2523000 | [11 empty] | 2523000
R-2501BB | Highway | STI (Prioritization) | US 1 | US 74 BYPASS TO US 74 BUSINESS | 4.07 | RICHMOND | 8 | Lumber River RPO | SCHEDULED FOR REPRIORITIZATION | Not Funded |  | T | CONSTRUCTION | 67699000 | [11 empty] | 67699000
R-2501BC | Highway | STI (Prioritization) | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | 7.15 | RICHMOND | 8 | Lumber River RPO | COORDINATE WITH R-5928 | Not Funded |  | T | RIGHT-OF-WAY | 24248000 | [11 empty] | 24248000
R-2501BC | Highway | STI (Prioritization) | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | 7.15 | RICHMOND | 8 | Lumber River RPO | COORDINATE WITH R-5928 | Not Funded |  | T | UTILITIES | 6950000 | [11 empty] | 6950000
R-2501BC | Highway | STI (Prioritization) | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | 7.15 | RICHMOND | 8 | Lumber River RPO | COORDINATE WITH R-5928 | Not Funded |  | T | CONSTRUCTION | 101101000 | [11 empty] | 101101000
R-2501C | Highway | STI (Prioritization) | US 1 | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | 3.43 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 8 |  | T | ENGINEERING | 217000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 49000
R-2501C | Highway | STI (Prioritization) | US 1 | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | 3.43 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 8 |  | T | BUILD NC CON | 9015000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000
R-2501C | Highway | STI (Prioritization) | US 1 | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | 3.43 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 8 |  | T | BUILD NC CON | 3960000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 300000
R-2511 | Highway | STI (Prioritization) | US 17 | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | 10.01 | MARTIN, BEAUFORT | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1, 2 |  | T | RIGHT-OF-WAY | 10471000 | FY 2025: 1221000
R-2511 | Highway | STI (Prioritization) | US 17 | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | 10.01 | MARTIN, BEAUFORT | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1, 2 |  | T | UTILITIES | 2200000
R-2511 | Highway | STI (Prioritization) | US 17 | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO FOUR LANES. | 10.01 | MARTIN, BEAUFORT | 1, 2 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1, 2 |  | T | CONSTRUCTION | 99343000 | FY 2025: 20862000; FY 2026: 19901000; FY 2027: 15000000
R-2513 | Highway | STI (Prioritization) | US 17 | NC 43 TO SR 1438 (SPRUILL TOWN ROAD). WIDEN TO MULTI-LANES. | 15.2 | CRAVEN | 2 | Down East RPO
R-2513A | Highway | STI (Prioritization) | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | 1.86 | CRAVEN | 2 | Down East RPO |  | Division 2 |  | T | RIGHT-OF-WAY | 3001000 | FY 2030: 655000; FY 2031: 873000; FY 2032: 873000; FY 2033: 300000; FY 2034: 300000
R-2513A | Highway | STI (Prioritization) | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | 1.86 | CRAVEN | 2 | Down East RPO |  | Division 2 |  | T | UTILITIES | 2400000 | FY 2030: 1200000; FY 2031: 1200000
R-2513A | Highway | STI (Prioritization) | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | 1.86 | CRAVEN | 2 | Down East RPO |  | Division 2 |  | T | CONSTRUCTION | 24600000 | FY 2033: 246000; FY 2034: 13530000; FY 2035: 9102000 | 1722000
R-2513B | Highway | STI (Prioritization) | US 17 | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5800000 | [11 empty] | 5800000
R-2513B | Highway | STI (Prioritization) | US 17 | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | UTILITIES | 800000 | [11 empty] | 800000
R-2513B | Highway | STI (Prioritization) | US 17 | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | CONSTRUCTION | 16300000 | [11 empty] | 16300000
R-2513C | Highway | STI (Prioritization) | US 17 | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 2300000 | [11 empty] | 2300000
R-2513C | Highway | STI (Prioritization) | US 17 | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | UTILITIES | 600000 | [11 empty] | 600000
R-2513C | Highway | STI (Prioritization) | US 17 | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | CONSTRUCTION | 11300000 | [11 empty] | 11300000
R-2513D | Highway | STI (Prioritization) | US 17 | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 4600000 | [11 empty] | 4600000
R-2513D | Highway | STI (Prioritization) | US 17 | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | UTILITIES | 600000 | [11 empty] | 600000
R-2513D | Highway | STI (Prioritization) | US 17 | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. |  | CRAVEN | 2 | Down East RPO |  | Not Funded |  | T | CONSTRUCTION | 21000000 | [11 empty] | 21000000
R-2513E | Highway | STI (Prioritization) | US 17 | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). |  | BEAUFORT | 2 | Mid-East RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 4600000 | [11 empty] | 4600000
R-2513E | Highway | STI (Prioritization) | US 17 | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). |  | BEAUFORT | 2 | Mid-East RPO |  | Not Funded |  | T | UTILITIES | 600000 | [11 empty] | 600000
R-2513E | Highway | STI (Prioritization) | US 17 | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). |  | BEAUFORT | 2 | Mid-East RPO |  | Not Funded |  | T | CONSTRUCTION | 18300000 | [11 empty] | 18300000
R-2514 | Highway | Pre-STI (Historic) | US 17 | MULTI-LANES NORTH OF JACKSONVILLE TO NEW BERN BYPASS. WIDEN TO MULTI-LANES WITH BYPASSES OF BELGRADE, MAYSVILLE AND POLLOCKSVILLE ON NEW LOCATION. | 22.1 | JONES, ONSLOW | 2, 3 | Down East RPO, Jacksonville Urban Area MPO
R-2514A | Highway | Pre-STI (Historic) | US 17 | MULTI-LANE SECTION NORTH OF JACKSONVILLE TO SOUTH OF BELGRADE. | 6.17 | ONSLOW | 3 | Jacksonville Urban Area MPO | COMPLETED. | Pre-STI (Transition)
R-2514B | Highway | Transition | US 17 | SOUTH OF BELGRADE TO NORTH OF MAYSVILLE. | 4.36 | ONSLOW, JONES | 2, 3 | Jacksonville Urban Area MPO, Down East RPO | COMPLETED. | Pre-STI (Transition) |  | T | CONSTRUCTION | 6000
R-2514C | Highway | Transition | US 17 | NORTH OF MAYSVILLE TO SOUTH OF NC 58. | 5.66 | JONES | 2 | Down East RPO | COMPLETED. | Pre-STI (Transition)
R-2514D | Highway | Transition | US 17 | SOUTH OF NC 58 TO THE NEW BERN BYPASS. | 5.8 | JONES | 2 | Down East RPO | COMPLETED. | Pre-STI (Transition)
R-2527 | Highway | STI (Prioritization) | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 9.1 | MONTGOMERY | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region E |  | T | ENGINEERING | 7802000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 522000
R-2527 | Highway | STI (Prioritization) | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 9.1 | MONTGOMERY | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region E |  | T | BUILD NC ROW | 854000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 57000 | 56000
R-2527 | Highway | STI (Prioritization) | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO A FOUR LANE DIVIDED FACILITY. | 9.1 | MONTGOMERY | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE) | Region E |  | BGLT5 | CONSTRUCTION | 131500000 | FY 2027: 1315000; FY 2028: 38135000; FY 2029: 36820000; FY 2030: 31560000; FY 2031: 23670000
R-2530 | Highway | STI (Prioritization) | NC 24/NC 27 | SR 1963 (ST. MARTIN ROAD) IN ALBEMARLE TO NC 73. WIDEN TO MULTI- LANES. (COORDINATE WITH B-4974). | 8.9 | STANLY | 10 | Rocky River RPO
R-2530A | Highway | Safety | NC 24-27 | SR 1963 (ST. MARTIN ROAD) TO BIRD ROAD IN ALBEMARLE. |  | STANLY | 10 | Rocky River RPO | COMPLETE
R-2530B | Highway | STI (Prioritization) | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER. | 6.1 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | ENGINEERING | 7620000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000
R-2530B | Highway | STI (Prioritization) | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER. | 6.1 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | ENGINEERING | 420000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000
R-2530B | Highway | STI (Prioritization) | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER. | 6.1 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC ROW | 5700000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000
R-2530B | Highway | STI (Prioritization) | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER. | 6.1 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC UTL | 3600000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
R-2530B | Highway | STI (Prioritization) | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER. | 6.1 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC CON | 15015000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000 | 1001000
R-2530B | Highway | STI (Prioritization) | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER. | 6.1 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC CON | 47640000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000 | 3176000
R-2530B | Highway | STI (Prioritization) | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER. | 6.1 | STANLY | 10 | Rocky River RPO | UNDER CONSTRUCTION - BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $331,023 FOR PE, $37.013 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | CONSTRUCTION | 34306000 | FY 2025: 6392000
R-2536 | Highway | Pre-STI (Historic) | US 64 | ASHEBORO SOUTHERN BYPASS, US 64 WEST TO US 64 EAST. FOUR-LANE FREEWAY ON NEW LOCATION WITH INTERCHANGES AT US 220, NC 49 AND ZOO ACCESS AT NC 159. | 12.76 | RANDOLPH | 8 | Piedmont Triad RPO | COMPLETE. | Pre-STI (Transition)
R-2555 | Highway | STI (Prioritization) | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO EAST OF SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | 3.4 | MECKLENBURG | 10 | Charlotte Regional TPO
R-2555A | Highway | STI (Prioritization) | SR 5544 (WEST CATAWBA AVENUE) | SR 2151 (JETTON ROAD) TO SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | 0.9 | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE
R-2555B | Highway | STI (Prioritization) | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 2.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE). | Division 10 |  | T | RIGHT-OF-WAY | 5000000 | FY 2026: 5000000
R-2555B | Highway | STI (Prioritization) | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 2.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE). | Division 10 |  | T | UTILITIES | 4000000 | FY 2026: 4000000
R-2555B | Highway | STI (Prioritization) | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 2.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE). | Division 10 |  | T | BUILD NC CON | 15255000 |  |  | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 6102000
R-2555B | Highway | STI (Prioritization) | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 2.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE). | Division 10 |  | T | CONSTRUCTION | 23400000 | FY 2027: 2000000; FY 2028: 7945000; FY 2029: 9802000; FY 2030: 3653000
R-2555B | Highway | STI (Prioritization) | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | 2.35 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $10M FOR CONSTRUCTION, PAYBACK FY 2027-2041 (FY 2027 / YR 7 SALE). | Division 10 |  | L | CONSTRUCTION | 1200000 | FY 2027: 0; FY 2028: 447000; FY 2029: 548000; FY 2030: 205000
R-2561 | Highway | STI (Prioritization) | NC 87 | ELIZABETHTOWN BYPASS IN BLADEN COUNTY TO US 74/US 76 IN COLUMBUS COUNTY. WIDEN TO MULTI-LANES. | 30.2 | BLADEN, COLUMBUS | 6 | Cape Fear RPO, Mid-Carolina RPO
R-2561A | Highway | STI (Prioritization) | NC 87 | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. |  | BLADEN, COLUMBUS | 6 | Mid-Carolina RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 23000000 | [11 empty] | 23000000
R-2561A | Highway | STI (Prioritization) | NC 87 | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. |  | BLADEN, COLUMBUS | 6 | Mid-Carolina RPO |  | Not Funded |  | T | UTILITIES | 8300000 | [11 empty] | 8300000
R-2561A | Highway | STI (Prioritization) | NC 87 | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. |  | BLADEN, COLUMBUS | 6 | Mid-Carolina RPO |  | Not Funded |  | T | CONSTRUCTION | 157400000 | [11 empty] | 157400000
R-2561B | Highway | STI (Prioritization) | NC 87 | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. |  | BLADEN | 6 | Cape Fear RPO, Mid-Carolina RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 18800000 | [11 empty] | 18800000
R-2561B | Highway | STI (Prioritization) | NC 87 | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. |  | BLADEN | 6 | Cape Fear RPO, Mid-Carolina RPO |  | Not Funded |  | T | UTILITIES | 6900000 | [11 empty] | 6900000
R-2561B | Highway | STI (Prioritization) | NC 87 | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. |  | BLADEN | 6 | Cape Fear RPO, Mid-Carolina RPO |  | Not Funded |  | T | CONSTRUCTION | 100800000 | [11 empty] | 100800000
R-2561C | Highway | STI (Prioritization) | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | 5.99 | COLUMBUS | 6 | Cape Fear RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 26511000 | [11 empty] | 26511000
R-2561C | Highway | STI (Prioritization) | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | 5.99 | COLUMBUS | 6 | Cape Fear RPO |  | Not Funded |  | T | UTILITIES | 4488000 | [11 empty] | 4488000
R-2561C | Highway | STI (Prioritization) | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | 5.99 | COLUMBUS | 6 | Cape Fear RPO |  | Not Funded |  | T | CONSTRUCTION | 85799000 | [11 empty] | 85799000
R-2561CA | Highway | STI (Prioritization) | NC 87 | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | 1 | COLUMBUS | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T | RIGHT-OF-WAY | 3904000 | FY 2025: 600000
R-2561CA | Highway | STI (Prioritization) | NC 87 | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | 1 | COLUMBUS | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T | UTILITIES | 3000000
R-2561CA | Highway | STI (Prioritization) | NC 87 | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | 1 | COLUMBUS | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | BGLT5 | CONSTRUCTION | 41376000 | FY 2025: 10446000; FY 2026: 3945000
R-2561CB | Highway | STI (Prioritization) | NC 87 | CONSTRUCT DETOUR ROUTE. |  | COLUMBUS | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 1756000
R-2566 | Highway | STI (Prioritization) | NC 105 | US 221 TO SR 1107 (NC 105 BYPASS) IN BOONE. WIDEN TO MULTI-LANES. | 14.8 | WATAUGA, AVERY | 11 | High Country RPO
R-2566A | Highway | STI (Prioritization) | NC 105 | US 221 IN AVERY COUNTY TO SR 1136 (CLARKS CREEK ROAD) IN WATAUGA COUNTY. |  | AVERY, WATAUGA | 11 | High Country RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 1000000 | [11 empty] | 1000000
R-2566A | Highway | STI (Prioritization) | NC 105 | US 221 IN AVERY COUNTY TO SR 1136 (CLARKS CREEK ROAD) IN WATAUGA COUNTY. |  | AVERY, WATAUGA | 11 | High Country RPO |  | Not Funded |  | T | CONSTRUCTION | 60351000 | [11 empty] | 42457000
R-2566B | Highway | STI (Prioritization) | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 5.49 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region F |  | T | BUILD NC ROW | 240000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
R-2566B | Highway | STI (Prioritization) | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 5.49 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region F |  | T | RIGHT-OF-WAY | 13030000 | FY 2025: 4000000; FY 2026: 3000000
R-2566B | Highway | STI (Prioritization) | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 5.49 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region F |  | T | UTILITIES | 13700000
R-2566B | Highway | STI (Prioritization) | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | 5.49 | WATAUGA | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $189,756 FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region F |  | NHP | CONSTRUCTION | 117000000 | FY 2030: 23400000; FY 2031: 35100000; FY 2032: 28080000; FY 2033: 21060000; FY 2034: 9360000
R-2566BA | Highway | STI (Prioritization) | NC 105 | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). |  | WATAUGA | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 11 |  | T | UTILITIES | 2850000
R-2566BA | Highway | STI (Prioritization) | NC 105 | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). |  | WATAUGA | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 11 |  | T | BUILD NC CON | 7980000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000 | 532000
R-2566BA | Highway | STI (Prioritization) | NC 105 | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). |  | WATAUGA | 11 | High Country RPO | WITHIN THE LIMITS OF R-2566 B. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Division 11 |  | T | CONSTRUCTION | 15700000 | FY 2025: 4282000
R-2566BB | Highway | STI (Prioritization) | NC 105 | SR 1658 (OLD SHULLS MILL ROAD) INTERSECTION. REALIGN SR 1658 (OLD SHULLS MILL ROAD). | 0.5 | WATAUGA | 11 | High Country RPO | UNDER CONSTRUCTION. | Region F |  | T | CONSTRUCTION | 1600000 | FY 2025: 501000; FY 2026: 1099000
R-2576 | Highway | STI (Prioritization) | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. TOLL PROJECT. | 6.93 | CURRITUCK | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2026-2040. | Division 1 |  | BOND R | RIGHT-OF-WAY | 16496000 | FY 2026: 165000; FY 2027: 6434000; FY 2028: 6597000; FY 2029: 1650000; FY 2030: 1650000
R-2576 | Highway | STI (Prioritization) | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. TOLL PROJECT. | 6.93 | CURRITUCK | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2026-2040. | Division 1 |  | BOND R | UTILITIES | 17412000 | FY 2026: 8706000; FY 2027: 8706000
R-2576 | Highway | STI (Prioritization) | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. TOLL PROJECT. | 6.93 | CURRITUCK | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2026-2040. | Division 1 |  | BGANY | GARVEE CON | 167280000 |  | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 11152000 | 55760000
R-2576 | Highway | STI (Prioritization) | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. TOLL PROJECT. | 6.93 | CURRITUCK | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2026-2040. | Division 1 |  | T(M) | CONSTRUCTION | 43327000 | FY 2026: 10831000; FY 2027: 10832000; FY 2028: 10832000; FY 2029: 10832000
R-2576 | Highway | STI (Prioritization) | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. TOLL PROJECT. | 6.93 | CURRITUCK | 1 | Albemarle RPO | DESIGN BUILD PROJECT. NORTH CAROLINA TURNPIKE AUTHORITY PROJECT. GARVEE BOND FUNDING: $130M FOR CONSTRUCTION PAYBACK FY 2026-2040. | Division 1 |  | BOND R | CONSTRUCTION | 223397000 | FY 2026: 55849000; FY 2027: 55849000; FY 2028: 55849000; FY 2029: 55850000
R-2577 | Highway | STI (Prioritization) | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS IN WINSTON-SALEM TO US 220 IN STOKESDALE. WIDEN TO A FOUR LANE DIVIDED FACILITY | 18.8 | FORSYTH, GUILFORD | 7, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO
R-2577A | Highway | STI (Prioritization) | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 5.21 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | RIGHT-OF-WAY | 36300000
R-2577A | Highway | STI (Prioritization) | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 5.21 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | UTILITIES | 469000
R-2577A | Highway | STI (Prioritization) | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 5.21 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | BUILD NC CON | 30495000 |  | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 10165000
R-2577A | Highway | STI (Prioritization) | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 5.21 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | BUILD NC CON | 68625000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 4575000 | 18300000
R-2577A | Highway | STI (Prioritization) | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 5.21 | FORSYTH | 9 | Winston-Salem Area TPO | RIGHT OF WAY IN PROGRESS. BUILD NC BOND FUNDING: $45,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE), $20,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Region D |  | T | CONSTRUCTION | 29600000 | FY 2025: 0; FY 2026: 0; FY 2027: 16356000; FY 2028: 12298000
R-2577B | Highway | STI (Prioritization) | US 158 | SR 1965 (BELEWS CREEK ROAD) TO NORTH OF SR 1969 (PINEY GROVE ROAD)/SR 1962 (KERNERSVILLE ROAD). WIDEN TO MULTI-LANES. | 7.53 | FORSYTH | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 38800000 | [11 empty] | 38800000
R-2577B | Highway | STI (Prioritization) | US 158 | SR 1965 (BELEWS CREEK ROAD) TO NORTH OF SR 1969 (PINEY GROVE ROAD)/SR 1962 (KERNERSVILLE ROAD). WIDEN TO MULTI-LANES. | 7.53 | FORSYTH | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | UTILITIES | 9700000 | [11 empty] | 9700000
R-2577B | Highway | STI (Prioritization) | US 158 | SR 1965 (BELEWS CREEK ROAD) TO NORTH OF SR 1969 (PINEY GROVE ROAD)/SR 1962 (KERNERSVILLE ROAD). WIDEN TO MULTI-LANES. | 7.53 | FORSYTH | 9 | Winston-Salem Area TPO |  | Not Funded |  | T | CONSTRUCTION | 60300000 | [11 empty] | 60300000
R-2577C | Highway | STI (Prioritization) | US 158 | NORTH OF SR 1969 (PINEY GROVE ROAD) / SR 1962 (KERNERSVILLE ROAD) IN FORSYTH COUNTY TO US 220 IN GUILFORD COUNTY. WIDEN TO MULTI-LANES. | 5.89 | GUILFORD, FORSYTH | 7, 9 | Greensboro Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T | RIGHT-OF-WAY | 74608000 | [11 empty] | 74608000
R-2577C | Highway | STI (Prioritization) | US 158 | NORTH OF SR 1969 (PINEY GROVE ROAD) / SR 1962 (KERNERSVILLE ROAD) IN FORSYTH COUNTY TO US 220 IN GUILFORD COUNTY. WIDEN TO MULTI-LANES. | 5.89 | GUILFORD, FORSYTH | 7, 9 | Greensboro Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T | UTILITIES | 625000 | [11 empty] | 625000
R-2577C | Highway | STI (Prioritization) | US 158 | NORTH OF SR 1969 (PINEY GROVE ROAD) / SR 1962 (KERNERSVILLE ROAD) IN FORSYTH COUNTY TO US 220 IN GUILFORD COUNTY. WIDEN TO MULTI-LANES. | 5.89 | GUILFORD, FORSYTH | 7, 9 | Greensboro Urban Area MPO, Winston-Salem Area TPO |  | Not Funded |  | T | CONSTRUCTION | 48400000 | [11 empty] | 48400000
R-2582 | Highway | STI (Prioritization) | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. WIDEN TO MULTI-LANES WITH BYPASS OF JACKSON, SOME NEW LOCATION. | 15.2 | NORTHAMPTON | 1 | Peanut Belt RPO
R-2582A | Highway | STI (Prioritization) | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 7.94 | NORTHAMPTON | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | ENGINEERING | 3690000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000 | 246000
R-2582A | Highway | STI (Prioritization) | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 7.94 | NORTHAMPTON | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | ENGINEERING | 5130000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000 | 342000
R-2582A | Highway | STI (Prioritization) | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 7.94 | NORTHAMPTON | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | BUILD NC ROW | 3345000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000
R-2582A | Highway | STI (Prioritization) | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 7.94 | NORTHAMPTON | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | BUILD NC CON | 41265000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000 | 2751000
R-2582A | Highway | STI (Prioritization) | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 7.94 | NORTHAMPTON | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | BUILD NC CON | 15330000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000 | 1022000
R-2582A | Highway | STI (Prioritization) | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | 7.94 | NORTHAMPTON | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $32,061,742.71 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 1 |  | T | CONSTRUCTION | 50214000 | FY 2025: 17250000; FY 2026: 3000000
R-2582B | Highway | STI (Prioritization) | US 158/NC 46 | SR 1312 (ST. JOHN CHURCH ROAD) TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. | 7.4 | NORTHAMPTON | 1 | Peanut Belt RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5400000 | [11 empty] | 5400000
R-2582B | Highway | STI (Prioritization) | US 158/NC 46 | SR 1312 (ST. JOHN CHURCH ROAD) TO SR 1333 (MOUNT CARMEL CHURCH ROAD) EAST OF JACKSON. | 7.4 | NORTHAMPTON | 1 | Peanut Belt RPO |  | Not Funded |  | T | CONSTRUCTION | 61400000 | [11 empty] | 61400000
R-2588 | Highway | STI (Prioritization) | NC 191 | US 25 IN HENDERSONVILLE TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | 7.2 | HENDERSON | 14 | French Broad River MPO
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 TO SR 1381 (MOUNTAIN ROAD). WIDEN TO MULTI-LANES. |  | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | BGANY | RIGHT-OF-WAY | 15200000 | [11 empty] | 15200000
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 TO SR 1381 (MOUNTAIN ROAD). WIDEN TO MULTI-LANES. |  | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | BGANY | UTILITIES | 1800000 | [11 empty] | 1800000
R-2588A | Highway | STI (Prioritization) | NC 191 | US 25 TO SR 1381 (MOUNTAIN ROAD). WIDEN TO MULTI-LANES. |  | HENDERSON | 14 | French Broad River MPO |  | Not Funded |  | BGANY | CONSTRUCTION | 18800000 | [11 empty] | 18800000
R-2588B | Highway | STI (Prioritization) | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | 4.41 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). | Division 14 |  | T | RIGHT-OF-WAY | 9500000
R-2588B | Highway | STI (Prioritization) | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | 4.41 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). | Division 14 |  | NHP | UTILITIES | 15500000
R-2588B | Highway | STI (Prioritization) | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | 4.41 | HENDERSON | 14 | French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901). | Division 14 |  | T | CONSTRUCTION | 148300000 | FY 2029: 28177000; FY 2030: 40041000; FY 2031: 32626000; FY 2032: 25211000; FY 2033: 22245000
R-2588BA | Highway | STI (Prioritization) | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280. CLEARING FOR UTILITIES. WIDEN TO MULTI-LANES. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | T | CONSTRUCTION | 556000 | FY 2025: 556000
R-2603 | Highway | Transition | NC 268 | NC 18 TO SR 1966 (AIRPORT ROAD). CONSTRUCT SIDEWALK FROM NC 18 TO SHAVER STREET. WIDEN TO FIVE-LANES FROM SHAVER STREET TO FAIRPLAINS ROAD. WIDEN TO FOUR-LANES DIVIDED FROM FAIRPLAINS ROAD TO SR 1966 (AIRPORT ROAD). | 3.27 | WILKES | 11 | High Country RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
R-2612 | Highway | Pre-STI (Historic) | US 421 | SR 3389 (WOODY MILL ROAD) AND SR 3418 (NEELLEY ROAD) SOUTH OF GREENSBORO. CONVERT AT-GRADE INTERSECTIONS TO INTERCHANGES. | 2 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Exempt
R-2612B | Highway | Transition | US 421 | SR 3418 (NEELLEY ROAD) INTERSECTION SOUTH OF GREENSBORO | 0.901 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION | Pre-STI (Transition)
R-2615 | Highway | STI (Prioritization) | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | 3.55 | WATAUGA | 11 | High Country RPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 40901000
R-2615 | Highway | STI (Prioritization) | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | 3.55 | WATAUGA | 11 | High Country RPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2900000
R-2615 | Highway | STI (Prioritization) | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | 3.55 | WATAUGA | 11 | High Country RPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 78300000
R-2632 | Highway | STI (Prioritization) | NC 73 | US 21 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 4.3 | MECKLENBURG | 10 | Charlotte Regional TPO | COORDINATE WITH R-5706A & B. $7.273M IN NHP FUNDS SWITCHED WITH $7.237M IN BGDA AS PART OF FUND SWAP 8-9-22.
R-2632AA | Highway | STI (Prioritization) | NC 73 | US 21 TO NC 115. WIDEN TO MULTI-LANES. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 2.67 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | NHP | RIGHT-OF-WAY | 8300000 | FY 2025: 2213000; FY 2026: 2030000; FY 2027: 1660000
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 2.67 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | NHP | UTILITIES | 5100000
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 2.67 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | NHP | CONSTRUCTION | 63462000 | FY 2026: 635000; FY 2027: 26654000; FY 2028: 19674000; FY 2029: 11423000; FY 2030: 5076000
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 2.67 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | BGDA | CONSTRUCTION | 5790000 | FY 2026: 58000; FY 2027: 2432000; FY 2028: 1795000; FY 2029: 1042000; FY 2030: 463000
R-2632AB | Highway | STI (Prioritization) | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO FOUR LANES. | 2.67 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. | Region E |  | T(M) | CONSTRUCTION | 1448000 | FY 2026: 14000; FY 2027: 608000; FY 2028: 449000; FY 2029: 261000; FY 2030: 116000
R-2632AC | Highway | Pre-STI (Historic) | NC 73 | NC 73 AT NC 115. CONVERT RIGHT TURN LANE ON NC 115 SOUTHBOUND TO A THROUGH LANE AND WIDEN FOR MERGING TAPER. |  | MECKLENBURG | 10 | Charlotte Regional TPO | COMPLETE | Pre-STI (Transition)
R-2633 | Highway | Pre-STI (Historic) | I-140/US 17 (WILMINGTON BYPASS) | US 17 SOUTH OF NC 87 IN BRUNSWICK COUNTY TO I-40 IN NEW HANOVER COUNTY. FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | 20.2 | BRUNSWICK, NEW HANOVER | 3 | Wilmington Urban Area MPO
R-2633AA | Highway | Pre-STI (Historic) | I-140/US 17 WILMINGTON BYPASS | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. | 5.3 | BRUNSWICK, NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED. GARVEE BOND FUNDING: $31.05M FOR CONSTRUCTION, PAYBACK 2010 - 2021. | Pre-STI (Transition) |  | NHP | GARVEE CON | 6810000
R-2633AB | Highway | Pre-STI (Historic) | I-140/US 17 WILMINGTON BYPASS | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. |  | BRUNSWICK, NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED.
R-2633BA | Highway | Transition | I-140/US 17 WILMINGTON BYPASS | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO SR 1430 (CEDAR HILL ROAD). | 7.6 | BRUNSWICK | 3 | Wilmington Urban Area MPO | COMPLETED. GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK 2014 - 2025. | Pre-STI (Transition) |  | NHP | GARVEE CON | 30750000 | FY 2025: 5125000
R-2633BB | Highway | Pre-STI (Historic) | I-140/US 17 WILMINGTON BYPASS | SR 1430 (CEDAR HILL ROAD) TO WEST OF US 421 NORTH OF WILMINGTON. |  | NEW HANOVER, BRUNSWICK | 3 | Wilmington Urban Area MPO | COMPLETED. GARVEE BOND FUNDING: $100M FOR CONSTRUCTION, PAYBACK 2013 - 2024. | Pre-STI (Transition) |  | NHP | GARVEE CON | 51250000
R-2633BC | Highway | Pre-STI (Historic) | I-140/US 17 WILMINGTON BYPASS | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO WEST OF US 421 NORTH OF WILMINGTON. |  | BRUNSWICK, NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED.
R-2633CA | Highway | Pre-STI (Historic) | I-140/US 17 WILMINGTON BYPASS | WEST OF US 421 NORTH OF WILMINGTON TO WEST OF NC 133. | 3.6 | NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED.
R-2633CB | Highway | Pre-STI (Historic) | I-140/US 17 WILMINGTON BYPASS | WEST OF NC 133 TO US 117. | 3.544 | NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED.
R-2633CC | Highway | Pre-STI (Historic) | I-140/US 17 WILMINGTON BYPASS | US 117 TO EAST OF I-40 SOUTH OF CASTLE HAYNE. | 0.85 | NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED.
R-2633D | Highway | Pre-STI (Historic) | I-140/US 17 WILMINGTON BYPASS | IMPLEMENTATION OF INTELLIGENT TRANSPORTATION SYSTEMS (ITS). | 20.13 | BRUNSWICK, NEW HANOVER | 3 | Wilmington Urban Area MPO | COMPLETED. | Pre-STI (Transition)
R-2707 | Highway | STI (Prioritization) | US 74 (SHELBY BYPASS) | FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | 18.6 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO
R-2707A | Highway | Pre-STI (Historic) | US 74 SHELBY BYPASS | WEST OF SR 1162 (PEACHTREE ROAD) TO EAST OF SR 1315 (PLATO LEE ROAD). RIGHT-OF-WAY ONLY. | 3.9 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE
R-2707AB | Highway | Transition | US 74 SHELBY BYPASS | EAST OF SR 1318 (KIMBRELL ROAD) TO EAST OF SR 1315 (PLATO LEE ROAD). GRADING AND STRUCTURES | 2.68 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE | Pre-STI (Transition)
R-2707B | Highway | Transition | US 74 SHELBY BYPASS | EAST OF SR 1315 (PLATO LEE ROAD) TO EAST OF NC 226. GRADING AND STRUCTURES | 2.58 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE | Pre-STI (Transition)
R-2707C | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | 5.42 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Region F |  | T | ENGINEERING | 75000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
R-2707C | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | 5.42 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Region F |  | T | BUILD NC CON | 14595000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000 | 973000
R-2707C | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | 5.42 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $19.996M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Region F |  | T | BUILD NC CON | 25740000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000
R-2707D | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 4.26 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | BUILD NC ROW | 1290000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000
R-2707D | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 4.26 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | RIGHT-OF-WAY | 19394000
R-2707D | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 4.26 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | BUILD NC CON | 61005000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 16268000
R-2707D | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 4.26 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | BUILD NC CON | 61005000 | 4067000 | 4067000 | 4067000 | 4067000 | 8134000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 12201000
R-2707D | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | 4.26 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $40M FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Region F |  | T | CONSTRUCTION | 154192000 | FY 2025: 15535000; FY 2026: 45728000; FY 2027: 32950000; FY 2028: 16781000
R-2707E | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 (LONG BRANCH ROAD) TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | 3.03 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). R-2707E CONSTRUCTION FUNDED UNDER R-2707D. | Region F |  | T | BUILD NC ROW | 1290000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000
R-2707E | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 (LONG BRANCH ROAD) TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | 3.03 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). R-2707E CONSTRUCTION FUNDED UNDER R-2707D. | Region F |  | T | RIGHT-OF-WAY | 34242000 | FY 2025: 307000
R-2707E | Highway | STI (Prioritization) | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 (LONG BRANCH ROAD) TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | 3.03 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). R-2707E CONSTRUCTION FUNDED UNDER R-2707D. | Region F |  | T | UTILITIES | 5300000 | FY 2025: 2600000
R-2707F | Highway | Pre-STI (Historic) | US 74 SHELBY BYPASS | EAST OF SR 1318 (KIMBRELL ROAD) TO EAST OF NC 226. PAVING | 5.27 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | COMPLETE | Pre-STI (Transition)
R-2721 | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), NC 55 (SOUTH) TO EAST OF US 401 SOUTH. FREEWAY ON NEW LOCATION. TOLL PROJECT. | 7.8 | WAKE | 5 | Capital Area MPO | COORDINATE WITH U-5746; NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT | Statewide Mobility
R-2721A | Highway | STI (Prioritization) | NC 540 | NC 55 BYPASS TO EAST OF SR 1152 (HOLLY SPRINGS ROAD). CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 2.84 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHP | CONSTRUCTION | 79500000
R-2721B | Highway | STI (Prioritization) | NC 540 | EAST OF SR 1152 (HOLLY SPRINGS ROAD) TO EAST OF US 401. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 5.37 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION | Statewide Mobility |  | NHP | CONSTRUCTION | 63000000
R-2814 | Highway | STI (Prioritization) | US 401 | NORTH OF SR 2044 (LIGON MILL ROAD) TO NC 39 IN LOUISBURG. WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY, SOME NEW LOCATION. | 18.5 | FRANKLIN, WAKE | 5 | Capital Area MPO, Kerr-Tar RPO | GARVEE BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
R-2814A | Highway | Pre-STI (Historic) | US 401 | SR 2044 (LIGON MILL ROAD) TO NORTH OF SR 2225 (LOUISBURY ROAD) | 2.237 | WAKE | 5 | Capital Area MPO | COMPLETE
R-2814B | Highway | Pre-STI (Historic) | US 401 | ROLESVILLE BYPASS, NORTH OF SR 2225 (LOUISBURY ROAD) TO NC 96 ON NEW LOCATION | 6.401 | WAKE | 5 | Capital Area MPO | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022 | Pre-STI (Transition) |  | BGANY | GARVEE ROW | 1727000
R-2814B | Highway | Pre-STI (Historic) | US 401 | ROLESVILLE BYPASS, NORTH OF SR 2225 (LOUISBURY ROAD) TO NC 96 ON NEW LOCATION | 6.401 | WAKE | 5 | Capital Area MPO | COMPLETE; GARVEE BOND FUNDING $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022 | Pre-STI (Transition) |  | BGANY | GARVEE CON | 7083000
R-2814C | Highway | STI (Prioritization) | US 401 | NC 96 TO SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) | 5.98 | FRANKLIN, WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION; GARVEE BOND FUNDING $33 MILLION FOR CONSTRUCTION - PAYBACK FY 2018 - FY 2032 | Division 5 |  | BGLT5 | GARVEE CON | 36803000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000 | 2831000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | 5.31 | FRANKLIN | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | RIGHT-OF-WAY | 12400000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | 5.31 | FRANKLIN | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | UTILITIES | 3500000
R-2814D | Highway | STI (Prioritization) | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | 5.31 | FRANKLIN | 5 | Capital Area MPO, Kerr-Tar RPO |  | Division 5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 64500000
R-2814E | Highway | Pre-STI (Historic) | US 401 | SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG TO NC 39 IN LOUISBURG | 1.022 | FRANKLIN | 5 | Kerr-Tar RPO | COMPLETE
R-2822 | Highway | STI (Prioritization) | NC 143 | NC 143, WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. |  | GRAHAM | 14 | Southwestern RPO
R-2822A | Highway | Pre-STI (Historic) | NC 143 | NC 143 BUSINESS, SOUTH OF SR 1115 TO NORTH OF SR 1125 |  | GRAHAM | 14 | Southwestern RPO | COMPLETE
R-2822B | Highway | STI (Prioritization) | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 4.94 | GRAHAM | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | RIGHT-OF-WAY | 1100000 | FY 2025: 246000; FY 2026: 246000; FY 2027: 220000
R-2822B | Highway | STI (Prioritization) | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 4.94 | GRAHAM | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Region G |  | T | UTILITIES | 1900000
R-2822BA | Highway | STI (Prioritization) | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | 4.94 | GRAHAM | 14 | Southwestern RPO |  | Region G |  | T | CONSTRUCTION | 40000000 | FY 2030: 400000; FY 2031: 13200000; FY 2032: 12000000; FY 2033: 8800000; FY 2034: 5600000
R-2822BB | Highway | STI (Prioritization) | NC 143 | BRIDGE 370013 OVER SNOWBIRD CREEK . REPLACE BRIDGE. |  | GRAHAM | 14 | Southwestern RPO |  | Region G |  | T | CONSTRUCTION | 33500000 | FY 2027: 335000; FY 2028: 11055000; FY 2029: 10050000; FY 2030: 7370000; FY 2031: 4690000
R-2828 | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), EAST OF US 401 TO I-40. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 8.64 | WAKE, JOHNSTON | 4, 5 | Capital Area MPO | UNDER CONSTRUCTION. COORDINATE WITH I-5111. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT. | Statewide Mobility |  | NHP | CONSTRUCTION | 135750000
R-2829 | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | EASTERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), I-40 TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 10.8 | WAKE | 5 | Capital Area MPO |  | Statewide Mobility |  | T | RIGHT-OF-WAY | 1133000 | FY 2025: 1133000
R-2829A | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 6.42 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 41809000 | FY 2025: 10452000; FY 2026: 20905000; FY 2027: 10452000
R-2829A | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 6.42 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | UTILITIES | 3544000 | FY 2025: 1772000; FY 2026: 1772000
R-2829A | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 6.42 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | NHP | GARVEE CON | 228750000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 61000000
R-2829A | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 6.42 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | T(M) | CONSTRUCTION | 50000000 | FY 2025: 12500000; FY 2026: 12500000; FY 2027: 12500000; FY 2028: 12500000
R-2829A | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | I-40 TO SOUTH OF ROCK QUARRY ROAD. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 6.42 | WAKE | 5 | Capital Area MPO | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | CONSTRUCTION | 140400000 | FY 2025: 140400000
R-2829B | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 3.82 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | RIGHT-OF-WAY | 33806000 | FY 2025: 8445000; FY 2026: 16890000; FY 2027: 8471000
R-2829B | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 3.82 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | UTILITIES | 500000 | FY 2025: 250000; FY 2026: 250000
R-2829B | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 3.82 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | NHP | GARVEE CON | 228750000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 15250000 | 61000000
R-2829B | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 3.82 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | T(M) | CONSTRUCTION | 50000000 | FY 2025: 12500000; FY 2026: 12500000; FY 2027: 12500000; FY 2028: 12500000
R-2829B | Highway | STI (Prioritization) | NEW ROUTE (FUTURE NC 540) | SOUTH OF ROCK QUARRY ROAD TO I-87 / US 64 / US 264 BYPASS. CONSTRUCT FREEWAY ON NEW LOCATION. TOLL PROJECT. | 3.82 | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION. NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $150 MILLION FOR CONSTRUCTION - PAYBACK 2025-2039 | Statewide Mobility |  | BOND R | CONSTRUCTION | 230902000 | FY 2025: 230902000
R-2915 | Highway | STI (Prioritization) | US 221 | US 421 IN WATAUGA COUNTY TO US 221 BUSINESS/NC 88 IN JEFFERSON. WIDEN TO FOUR LANES DIVIDED. | 16.1 | ASHE, WATAUGA | 11 | High Country RPO
R-2915A | Highway | Transition | US 221 | US 421 IN WATAUGA COUNTY TO SR 1003 (IDLEWILD ROAD) IN ASHE COUNTY | 3.6 | ASHE, WATAUGA | 11 | High Country RPO | COMPLETE | Pre-STI (Transition)
R-2915B | Highway | Transition | US 221 | SR 1003 (IDLEWILD ROAD) TO NORTH OF SOUTH FORK NEW RIVER | 1 | ASHE | 11 | High Country RPO | COMPLETE | Pre-STI (Transition)
R-2915C | Highway | STI (Prioritization) | US 221 | NORTH OF SOUTH FORK NEW RIVER TO SOUTH OF NC 194 | 4.2 | ASHE | 11 | High Country RPO | COMPLETE | Division 11 |  | BGLT5 | CONSTRUCTION | 19700000
R-2915D | Highway | Transition | US 221 | SOUTH OF NC 194 TO US 221 BYPASS | 3.8 | ASHE | 11 | High Country RPO | COMPLETE | Pre-STI (Transition)
R-2915E | Highway | STI (Prioritization) | US 221 | US 221 BYPASS TO US 221 BUSINESS/NC 88 IN JEFFERSON | 3.55 | ASHE | 11 | High Country RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 11 |  | T | BUILD NC CON | 27615000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000 | 1841000
R-2915E | Highway | STI (Prioritization) | US 221 | US 221 BYPASS TO US 221 BUSINESS/NC 88 IN JEFFERSON | 3.55 | ASHE | 11 | High Country RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $21.452 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 11 |  | T | CONSTRUCTION | 17069000
R-3100 | Highway | STI (Prioritization) | NC 16 | SR 1895 TO SR 1800 SOUTHEAST OF NEWTON. WIDEN TO FOUR LANES. | 9.1 | CATAWBA | 12 | Greater Hickory MPO
R-3100A | Highway | STI (Prioritization) | NC 16 | SR 1895 (TOWER ROAD) TO SR 1814 (CALDWELL ROAD) | 4.41 | CATAWBA | 12 | Greater Hickory MPO | COMPLETE; BUILD NC BOND FUNDING: $33.028 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE). | Division 12 |  | T | BUILD NC CON | 42510000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000 | 2834000
R-3100B | Highway | STI (Prioritization) | NC 16 | SR 1814 (CALDWELL ROAD) TO SR 1801 (CLAREMONT ROAD) | 3.75 | CATAWBA | 12 | Greater Hickory MPO | COMPLETE. | Division 12
R-3100C | Highway | Pre-STI (Historic) | NC 16 | SR 1801 (CLAREMONT ROAD) TO SR 1800 (CALEB SETZER ROAD) | 0.653 | CATAWBA | 12 | Greater Hickory MPO | COMPLETE.
R-3300 | Highway | STI (Prioritization) | US 17 (HAMPSTEAD BYPASS) | US 17 BYPASS SOUTH OF HAMPSTEAD TO US 17 NORTH OF HAMPSTEAD. CONSTRUCT FREEWAY ON NEW LOCATION. | 12.3 | NEW HANOVER, PENDER | 3 | Wilmington Urban Area MPO
R-3300A | Highway | STI (Prioritization) | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | 6.87 | PENDER, NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Region B |  | T | RIGHT-OF-WAY | 10000000 | FY 2025: 5000000; FY 2026: 5000000
R-3300A | Highway | STI (Prioritization) | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | 6.87 | PENDER, NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Region B |  | T | BUILD NC CON | 61005000 |  |  | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 4067000 | 24402000
R-3300A | Highway | STI (Prioritization) | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | 6.87 | PENDER, NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Region B |  | T | BUILD NC CON | 57945000 |  |  |  |  | 3863000 | 3863000 | 3863000 | 3863000 | 3863000 | 3863000 | 3863000 | 27041000
R-3300A | Highway | STI (Prioritization) | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | 6.87 | PENDER, NEW HANOVER | 3 | Wilmington Urban Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $40,000,000 FOR CONSTRUCTION PAYBACK 2027-2041 (FY 2027 / YR 7 SALE); $38,000,000 FOR CONSTRUCTION PAYBACK 2029-2043 (FY 2029 / YR 9 SALE). | Region B |  | T | CONSTRUCTION | 144000000 | FY 2026: 51060000; FY 2027: 13280000; FY 2028: 48840000; FY 2029: 0; FY 2030: 30820000
R-3300B | Highway | STI (Prioritization) | US 17 | NC 210 TO US 17 NORTH OF HAMPSTEAD. | 5.45 | PENDER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). | Region B |  | T | RIGHT-OF-WAY | 5000000 | FY 2025: 5000000
R-3300B | Highway | STI (Prioritization) | US 17 | NC 210 TO US 17 NORTH OF HAMPSTEAD. | 5.45 | PENDER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). | Region B |  | T | BUILD NC CON | 71820000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000 | 4788000
R-3300B | Highway | STI (Prioritization) | US 17 | NC 210 TO US 17 NORTH OF HAMPSTEAD. | 5.45 | PENDER | 3 | Wilmington Urban Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). | Region B |  | T | CONSTRUCTION | 157732000 | FY 2025: 42709000; FY 2026: 56709000; FY 2027: 9000000
R-3403 | Highway | STI (Prioritization) | US 17 | MILLS STREET IN BRIDGETON TO NC 43. WIDEN TO MULTI-LANES. | 9.8 | CRAVEN | 2 | Down East RPO, New Bern Area MPO |  | Region B
R-3403AA | Highway | Pre-STI (Historic) | US 17 | MILLS STREET IN BRIDGETON TO NORTH "C" STREET. |  | CRAVEN | 2 | Down East RPO | COMPLETED.
R-3403AB | Highway | Pre-STI (Historic) | US 17 | NORTH "C" STREET TO NORTH OF SR 1433 (ANTIOCH ROAD). |  | CRAVEN | 2 | Down East RPO | COMPLETED.
R-3403B | Highway | STI (Prioritization) | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | 7.19 | CRAVEN | 2 | Down East RPO, New Bern Area MPO |  | Region B |  | T | RIGHT-OF-WAY | 5999000 | FY 2030: 1309000; FY 2031: 1745000; FY 2032: 1745000; FY 2033: 600000; FY 2034: 600000
R-3403B | Highway | STI (Prioritization) | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | 7.19 | CRAVEN | 2 | Down East RPO, New Bern Area MPO |  | Region B |  | T | UTILITIES | 4100000 | FY 2030: 2050000; FY 2031: 2050000
R-3403B | Highway | STI (Prioritization) | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | 7.19 | CRAVEN | 2 | Down East RPO, New Bern Area MPO |  | Region B |  | T | CONSTRUCTION | 129100000 | FY 2033: 1291000; FY 2034: 43894000; FY 2035: 38730000 | 45185000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 8.64 | JOHNSTON | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  | T | BUILD NC ROW | 30500000 |  |  |  | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 2033000 | 14236000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 8.64 | JOHNSTON | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  | T | RIGHT-OF-WAY | 35900000 | FY 2027: 12777000; FY 2028: 5554000; FY 2029: 6389000; FY 2030: 5590000; FY 2031: 5590000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 8.64 | JOHNSTON | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  | T | UTILITIES | 10500000 | FY 2027: 5250000; FY 2028: 5250000
R-3410 | Highway | STI (Prioritization) | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | 8.64 | JOHNSTON | 4 | Capital Area MPO | BUILD NC BOND FUNDING: $20,000,000 FOR RIGHT-OF-WAY PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Region A |  | BGANY | CONSTRUCTION | 156900000 | FY 2031: 34518000; FY 2032: 50208000; FY 2033: 37656000; FY 2034: 26673000; FY 2035: 7845000
R-3421 | Highway | STI (Prioritization) | US 220 / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS. FOUR LANES DIVIDED ON NEW LOCATION. | 10.5 | RICHMOND | 8 | Lumber River RPO | BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
R-3421A | Highway | STI (Prioritization) | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 2.61 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC ROW | 5495000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 366000 | 371000
R-3421A | Highway | STI (Prioritization) | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 2.61 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC CON | 8965000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 560000 | 375000 | 375000 | 375000
R-3421A | Highway | STI (Prioritization) | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 2.61 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC CON | 65983000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4399000 | 4397000
R-3421A | Highway | STI (Prioritization) | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | 2.61 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | CONSTRUCTION | 31909000
R-3421B | Highway | STI (Prioritization) | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) TO SOUTHWEST OF SR 1304 (HARRINGTON ROAD) | 9.25 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | BUILD NC CON | 39179000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2612000 | 2611000
R-3421B | Highway | STI (Prioritization) | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) TO SOUTHWEST OF SR 1304 (HARRINGTON ROAD) | 9.25 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region E |  | T | CONSTRUCTION | 44500000
R-3421C | Highway | Transition | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, 0.2 MILES SOUTHWEST OF SR 1304 (HARRINGTON ROAD) TO I-73 / I-74 INTERCHANGE SOUTH OF ELLERBE | 0.84 | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION | Pre-STI (Transition)
R-3421CA | Highway | STI (Prioritization) | US 220/I-73/I-74 | SR 1336 (BILLY COVINGTON ROAD) |  | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | RIGHT-OF-WAY | 75000
R-3421CA | Highway | STI (Prioritization) | US 220/I-73/I-74 | SR 1336 (BILLY COVINGTON ROAD) |  | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | UTILITIES | 25000
R-3421CA | Highway | STI (Prioritization) | US 220/I-73/I-74 | SR 1336 (BILLY COVINGTON ROAD) |  | RICHMOND | 8 | Lumber River RPO | UNDER CONSTRUCTION | Statewide Mobility |  | T | CONSTRUCTION | 532000 | FY 2025: 527000
R-3430 | Highway | STI (Prioritization) | SR 1001 (MALCOLM BLVD/ CONNELLY SPRINGS ROAD) | US 70 TO SR 1933 (SOUTH-WEST BOULEVARD) IN LENOIR. MODERNIZE ROADWAY TO INCLUDE BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | 10 | CALDWELL, BURKE | 11, 13 | Greater Hickory MPO
R-3430A | Highway | STI (Prioritization) | SR 1001 (MALCOLM BOULEVARD) | US 70 TO CATAWBA RIVER. |  | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 10000000 | [11 empty] | 10000000
R-3430A | Highway | STI (Prioritization) | SR 1001 (MALCOLM BOULEVARD) | US 70 TO CATAWBA RIVER. |  | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | T | UTILITIES | 1600000 | [11 empty] | 1600000
R-3430A | Highway | STI (Prioritization) | SR 1001 (MALCOLM BOULEVARD) | US 70 TO CATAWBA RIVER. |  | BURKE | 13 | Greater Hickory MPO |  | Not Funded |  | T | CONSTRUCTION | 20000000 | [11 empty] | 20000000
R-3430B | Highway | Bridges | SR 1001 (CONNELLY SPRINGS ROAD) | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | 0.25 | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Highway Fund |  | HFB | RIGHT-OF-WAY | 880000
R-3430B | Highway | Bridges | SR 1001 (CONNELLY SPRINGS ROAD) | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | 0.25 | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Highway Fund |  | HFB | UTILITIES | 370000
R-3430B | Highway | Bridges | SR 1001 (CONNELLY SPRINGS ROAD) | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | 0.25 | BURKE | 13 | Greater Hickory MPO | RIGHT-OF-WAY IN PROGRESS. | Highway Fund |  | HFB | CONSTRUCTION | 22902000 | FY 2026: 3368000; FY 2027: 10088000; FY 2028: 7421000; FY 2029: 2025000
R-3430C | Highway | STI (Prioritization) | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | 7.04 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | RIGHT-OF-WAY | 27500000 | FY 2030: 667000; FY 2031: 8000000; FY 2032: 8000000; FY 2033: 5333000; FY 2034: 5500000
R-3430C | Highway | STI (Prioritization) | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | 7.04 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | UTILITIES | 4000000 | FY 2030: 2000000; FY 2031: 2000000
R-3430C | Highway | STI (Prioritization) | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | 7.04 | CALDWELL | 11 | Greater Hickory MPO |  | Division 11 |  | BGANY | CONSTRUCTION | 101600000 | FY 2034: 10356000; FY 2035: 35151000 | 56093000
R-3603 | Highway | STI (Prioritization) | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | 3.7 | ALEXANDER, CATAWBA | 12 | Greater Hickory MPO
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | 3.67 | ALEXANDER, CATAWBA | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | BGANY | RIGHT-OF-WAY | 16200000 | FY 2030: 5891000; FY 2031: 7069000; FY 2032: 1620000; FY 2033: 1620000
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | 3.67 | ALEXANDER, CATAWBA | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | BGANY | UTILITIES | 7300000 | FY 2030: 3650000; FY 2031: 3650000
R-3603A | Highway | STI (Prioritization) | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | 3.67 | ALEXANDER, CATAWBA | 12 | Greater Hickory MPO | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). | Division 12 |  | BGANY | CONSTRUCTION | 115699000 | FY 2034: 21965000; FY 2035: 34539000 | 59195000
R-3608 | Highway | STI (Prioritization) | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | 1.36 | FRANKLIN | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | Region C |  | T | RIGHT-OF-WAY | 8500000 | FY 2030: 850000; FY 2031: 2975000; FY 2032: 2975000; FY 2033: 850000; FY 2034: 850000
R-3608 | Highway | STI (Prioritization) | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | 1.36 | FRANKLIN | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | Region C |  | T | UTILITIES | 3400000 | FY 2030: 1133000; FY 2031: 1133000; FY 2032: 1134000
R-3608 | Highway | STI (Prioritization) | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTI-LANES. | 1.36 | FRANKLIN | 5 | Kerr-Tar RPO | COORDINATE WITH U-6024 | Region C |  | T | CONSTRUCTION | 35000000 | FY 2033: 8750000; FY 2034: 12250000; FY 2035: 8750000 | 5250000
R-3822 | Highway | STI (Prioritization) | NEW ROUTE | NC 125 TO SOUTH OF US 158. CONSTRUCT THREE LANE FACILITY ON NEW LOCATION. | 1.49 | HALIFAX | 4 | Peanut Belt RPO | COMPLETE. COMBINED FOR LETTING WITH U-5725. CONSTRUCTION FUNDS SHOWN UNDER U-5725. | Division 4
R-3825 | Highway | STI (Prioritization) | NC 42 | US 70 TO SR 1003 (BUFFALO ROAD). WIDEN TO MULTI-LANES. | 6.1 | JOHNSTON | 4 | Capital Area MPO
R-3825A | Highway | Pre-STI (Historic) | NC 42 | US 70 AT CLAYTON TO EAST OF SR 1902 (GLEN LAUREL ROAD). | 1.5 | JOHNSTON | 4 | Capital Area MPO | COMPLETED.
R-3825B | Highway | STI (Prioritization) | NC 42 | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | 4.35 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | BUILD NC CON | 20895000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000 | 1393000
R-3825B | Highway | STI (Prioritization) | NC 42 | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | 4.35 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | BUILD NC CON | 22755000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000 | 1517000
R-3825B | Highway | STI (Prioritization) | NC 42 | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | 4.35 | JOHNSTON | 4 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 4 |  | T | CONSTRUCTION | 24798000
R-3830 | Highway | STI (Prioritization) | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | 5.57 | LEE | 8 | Central Pines RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | Division 8 |  | T | BUILD NC ROW | 10228000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 680000
R-3830 | Highway | STI (Prioritization) | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | 5.57 | LEE | 8 | Central Pines RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | Division 8 |  | T | BUILD NC CON | 14490000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 966000 | 1932000
R-3830 | Highway | STI (Prioritization) | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO A FOUR LANE DIVIDED FACILITY FROM US 421 TO NC 42 (AVENTS FERRY ROAD) AND WIDEN TO THREE LANES FROM NC 42 (AVENTS FERRY ROAD) TO SR 1538 (E. HARRINGTON AVENUE). | 5.57 | LEE | 8 | Central Pines RPO | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $11.262 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE) | Division 8 |  | T | CONSTRUCTION | 59609000 | FY 2025: 18427000; FY 2026: 6378000
R-3830A | Highway | STI (Prioritization) | NC 42 | RAILROAD MITIGATION |  | LEE | 8 | Central Pines RPO | UNDER CONSTRUCTION | Division 8 |  | T | CONSTRUCTION | 1900000
R-3833 | Highway | STI (Prioritization) | SR 1100 (BRAWLEY SCHOOL ROAD) | SR 1177 (CHUCKWOOD ROAD) TO US 21. WIDEN TO MULTI-LANES WITH INTERCHANGE AT I-77. | 5.9 | IREDELL | 12 | Charlotte Regional TPO | $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE.
R-3833A | Highway | Pre-STI (Historic) | SR 1100 (BRAWLEY SCHOOL ROAD) | SR 1177 (CHUCKWOOD ROAD) TO SR 1109 (CENTRE CHURCH ROAD). WIDEN TO MULTI-LANES. | 3.9 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE
R-3833B | Highway | Pre-STI (Historic) | SR 1100 (BRAWLEY SCHOOL ROAD) | SR 1109 (CENTRE CHURCH ROAD) TO I-77. WIDEN TO MULTI-LANES. | 1.1 | IREDELL | 12 | Charlotte Regional TPO | COMPLETE
R-3833C | Highway | STI (Prioritization) | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21. WIDEN TO MULTI-LANES. | 1 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Division 12 |  | T | RIGHT-OF-WAY | 5610000
R-3833C | Highway | STI (Prioritization) | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21. WIDEN TO MULTI-LANES. | 1 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Division 12 |  | T | UTILITIES | 1950000 | FY 2025: 1950000
R-3833C | Highway | STI (Prioritization) | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21. WIDEN TO MULTI-LANES. | 1 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Division 12 |  | T | BUILD NC CON | 22875000 | 1525000 | 1525000 | 1525000 | 1525000 | 3050000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 4575000
R-3833C | Highway | STI (Prioritization) | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21. WIDEN TO MULTI-LANES. | 1 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Division 12 |  | T | CONSTRUCTION | 9861000
R-3833C | Highway | STI (Prioritization) | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21. WIDEN TO MULTI-LANES. | 1 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Division 12 |  | T | CONSTRUCTION | 13136000 | FY 2025: 5000000; FY 2026: 7894000; FY 2027: 242000
R-3833C | Highway | STI (Prioritization) | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21. WIDEN TO MULTI-LANES. | 1 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING $15,000,000 FOR CON, PAYBACK FY 2025-2039 (FY 2025 / YR 5 SALE); | Division 12 |  | L | CONSTRUCTION | 890000
R-4045 | Highway | STI (Prioritization) | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 1.35 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | Region F |  | T | RIGHT-OF-WAY | 16000000 | FY 2025: 10000000; FY 2026: 5500000
R-4045 | Highway | STI (Prioritization) | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 1.35 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | Region F |  | T | UTILITIES | 5600000
R-4045 | Highway | STI (Prioritization) | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 1.35 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | Region F |  | DP | CONSTRUCTION | 23239000 | FY 2025: 7575000; FY 2026: 2530000
R-4045 | Highway | STI (Prioritization) | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | 1.35 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT. UNDER CONSTRUCTION. | Region F |  | T | CONSTRUCTION | 38352000 | FY 2025: 12750000; FY 2026: 3629000
R-4436DIV | Highway | Other | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  | BGANY | CONSTRUCTION | 900000
R-4436REG | Highway | Other | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Region SW |  | BGANY | CONSTRUCTION | 900000
R-4436SW | Highway | Other | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Statewide Mobility |  | BGANY | CONSTRUCTION | 1200000
R-4463 | Highway | Pre-STI (Historic) | NC 43 CONNECTOR | NC 43/NC 55 TO US 17 IN NEW BERN. CONSTRUCT ROUTE ON NEW LOCATION WITH INTERCHANGE AT US 70. | 4.2 | CRAVEN | 2 | New Bern Area MPO
R-4463A | Highway | STI (Prioritization) | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2.29 | CRAVEN | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | ENGINEERING | 1725000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000
R-4463A | Highway | STI (Prioritization) | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2.29 | CRAVEN | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | BUILD NC ROW | 240000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
R-4463A | Highway | STI (Prioritization) | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2.29 | CRAVEN | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | RIGHT-OF-WAY | 7783000
R-4463A | Highway | STI (Prioritization) | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2.29 | CRAVEN | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | UTILITIES | 1350000
R-4463A | Highway | STI (Prioritization) | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US 17/US 70. | 2.29 | CRAVEN | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | CONSTRUCTION | 43400000 | FY 2026: 15624000; FY 2027: 14756000; FY 2028: 9982000; FY 2029: 3038000
R-4463AA | Highway | Transition | NC 43 CONNECTOR | SOUTH OF US17/US 70 TO US 70. | 2.5 | CRAVEN | 2 | New Bern Area MPO | COMPLETED.
R-4463B | Highway | Economic Development | NC 43 CONNECTOR | US 70 TO NC 43/NC 55. |  | CRAVEN | 2 | New Bern Area MPO | COMPLETED. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR BOSCH CORPORATION.
R-4467 | Highway | Pre-STI (Historic) | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 0.82 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | ENGINEERING | 2415000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000 | 161000
R-4467 | Highway | Pre-STI (Historic) | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 0.82 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | BUILD NC CON | 3570000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000 | 238000
R-4467 | Highway | Pre-STI (Historic) | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 0.82 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | BUILD NC CON | 49035000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000 | 3269000
R-4467 | Highway | Pre-STI (Historic) | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | 0.82 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Region A |  | T | CONSTRUCTION | 12907000
R-4705 | Highway | STI (Prioritization) | SR 1142 (PRISON CAMP ROAD) | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | 9.58 | MARTIN | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | BGANY | RIGHT-OF-WAY | 200000
R-4705 | Highway | STI (Prioritization) | SR 1142 (PRISON CAMP ROAD) | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | 9.58 | MARTIN | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | BGANY | UTILITIES | 2100000
R-4705 | Highway | STI (Prioritization) | SR 1142 (PRISON CAMP ROAD) | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | 9.58 | MARTIN | 1 | Mid-East RPO | UNDER CONSTRUCTION. | Division 1 |  | BGANY | CONSTRUCTION | 48147000 | FY 2025: 7535000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  | T | ENGINEERING | 4019000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000 | 268000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  | T | BUILD NC ROW | 5824000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000 | 416000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  | T | BUILD NC CON | 32288000 | 2018000 | 2018000 | 2018000 | 2018000 | 2018000 | 2018000 | 2018000 | 2018000 | 4036000 | 2018000 | 2018000 | 2018000
R-4707 | Highway | STI (Prioritization) | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | 1 | GUILFORD | 7 | Greensboro Urban Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $23.524 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE) | Region D |  | T | CONSTRUCTION | 29816000 | FY 2025: 2667000
R-4753 | Highway | STI (Prioritization) | NC 107 | SR 1002 TO NC 281. UPGRADE EXISTING ROADWAY. | 4.01 | JACKSON | 14 | Southwestern RPO | UNDER CONSTRUCTION | Division 14
R-5014 | Highway | STI (Prioritization) | SR 1217 (COLLINGTON ROAD) | DEAD END TO US 158 (CROATON HIGHWAY) IN KILL DEVIL HILLS. OPERATIONAL-SAFETY IMPROVEMENTS. | 4.35 | DARE | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | BGANY | CONSTRUCTION | 22368000
R-5020 | Highway | STI (Prioritization) | US 701 BYPASS (MADISON STREET- POWELL BOULEVARD) | SOUTH OF SR 1166 (PLEASANT PLAINS ROAD) TO NORTH OF US 74/US 76 BYPASS IN WHITEVILLE. WIDEN TO MULTI-LANE FACILITY. | 3.92 | COLUMBUS | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS.
R-5020A | Highway | STI (Prioritization) | US 701 BYPASS | SR 1166 (PLEASANT PLAINS CHURCH ROAD) TO SR 1437 (VIRGIL AVENUE). | 2.18 | COLUMBUS | 6 | Cape Fear RPO | RIGHT-OF-WAY IN PROGRESS. | Region C |  | NHP | CONSTRUCTION | 65600000 | FY 2030: 656000; FY 2031: 24928000; FY 2032: 19680000; FY 2033: 14432000; FY 2034: 5904000
R-5020B | Highway | STI (Prioritization) | US 701 BYPASS | SR 1437 (VIRGIL AVENUE) TO US 74/US 76. | 1.74 | COLUMBUS | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 6 |  | T | CONSTRUCTION | 32485000
R-5021 | Highway | STI (Prioritization) | NC 211 | SR 1500 (MIDWAY ROAD) TO NC 87. WIDEN TO FOUR LANES. | 6.55 | BRUNSWICK | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGANY | UTILITIES | 10850000
R-5021 | Highway | STI (Prioritization) | NC 211 | SR 1500 (MIDWAY ROAD) TO NC 87. WIDEN TO FOUR LANES. | 6.55 | BRUNSWICK | 3 | Cape Fear RPO | UNDER CONSTRUCTION. | Division 3 |  | BGANY | CONSTRUCTION | 239876000 | FY 2025: 24649000; FY 2026: 8285000
R-5100 | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | I-77 TO NC 150. WIDEN TO FOUR LANES. | 3.2 | IREDELL | 12 | Charlotte Regional TPO | COORDINATE WITH U-5817.
R-5100A | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 2.35 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $22M CON PAYBACK FY 28-44 (FY 28/YR 8 SALE). | Division 12 |  | T | ENGINEERING | 600000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
R-5100A | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 2.35 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $22M CON PAYBACK FY 28-44 (FY 28/YR 8 SALE). | Division 12 |  | T | BUILD NC ROW | 195000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000
R-5100A | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 2.35 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $22M CON PAYBACK FY 28-44 (FY 28/YR 8 SALE). | Division 12 |  | T | BUILD NC ROW | 3855000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000 | 257000
R-5100A | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 2.35 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $22M CON PAYBACK FY 28-44 (FY 28/YR 8 SALE). | Division 12 |  | T | RIGHT-OF-WAY | 7650000
R-5100A | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 2.35 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $22M CON PAYBACK FY 28-44 (FY 28/YR 8 SALE). | Division 12 |  | T | UTILITIES | 5300000
R-5100A | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 2.35 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $22M CON PAYBACK FY 28-44 (FY 28/YR 8 SALE). | Division 12 |  | T | BUILD NC CON | 33510000 |  |  |  | 2234000 | 2234000 | 2234000 | 2234000 | 2234000 | 2234000 | 2234000 | 2234000 | 15638000
R-5100A | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO FOUR LANES. | 2.35 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $466,370 PE, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $142,461 ROW, PAYBACK FY 20-34 (FY 19/YR 1 SALE); $3M ROW, PAYBACK FY 22-36 (FY 22/YR 4 SALE); $22M CON PAYBACK FY 28-44 (FY 28/YR 8 SALE). | Division 12 |  | T | CONSTRUCTION | 34899000 | FY 2027: 11753000; FY 2028: 0; FY 2029: 11624000; FY 2030: 11522000
R-5100B | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 0.87 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | T | BUILD NC ROW | 2565000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000 | 171000
R-5100B | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 0.87 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | T | BUILD NC ROW | 450000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
R-5100B | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 0.87 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | T | RIGHT-OF-WAY | 6500000
R-5100B | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 0.87 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | T | UTILITIES | 1300000
R-5100B | Highway | STI (Prioritization) | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO FOUR LANES. | 0.87 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE). | Division 12 |  | BGANY | CONSTRUCTION | 9600000 | FY 2026: 1920000; FY 2027: 6144000; FY 2028: 1536000
R-5113 | Highway | STI (Prioritization) | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | 4.62 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 64800000
R-5113 | Highway | STI (Prioritization) | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | 4.62 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 16500000
R-5113 | Highway | STI (Prioritization) | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | 4.62 | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 57501000
R-5311 | Highway | STI (Prioritization) | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. WIDEN TO MULTI-LANES. | 7.8 | HERTFORD | 1 | Peanut Belt RPO
R-5311A | Highway | STI (Prioritization) | US 13/NC 11 | WEST OF MODLIN ROAD TO EAST OF NC 11/SR 1213 (OLD NC 11 ROAD). CONSTRUCT GRADE SEPARATION AT SR 1130 (MODLIN ROAD) AND INTERCHANGE AT OLD NC 11/SR 1213 (OLD NC 11 ROAD). | 1 | HERTFORD | 1 | Peanut Belt RPO | COMPLETED. | Statewide Mobility
R-5311B | Highway | STI (Prioritization) | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | 7.77 | HERTFORD | 1 | Peanut Belt RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6301000
R-5311B | Highway | STI (Prioritization) | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | 7.77 | HERTFORD | 1 | Peanut Belt RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3000000
R-5311B | Highway | STI (Prioritization) | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | 7.77 | HERTFORD | 1 | Peanut Belt RPO |  | Region A | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 193400000
R-5500 | Highway | Other | VARIOUS | INDIAN RESERVATION ROAD (IRR) PROGRAM. ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED BY EASTERN BAND OF CHEROKEE INDIANS. |  | JACKSON, SWAIN | 14 | Southwestern RPO | PROGRAM IN PROGRESS | Exempt
R-5600 | Highway | STI (Prioritization) | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.85 | JACKSON | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  | T | BUILD NC ROW | 25740000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000 | 1716000
R-5600 | Highway | STI (Prioritization) | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.85 | JACKSON | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  | T | RIGHT-OF-WAY | 44700000 | FY 2025: 9000000
R-5600 | Highway | STI (Prioritization) | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.85 | JACKSON | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  | T | UTILITIES | 7200000
R-5600 | Highway | STI (Prioritization) | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO WEST OF MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 1.85 | JACKSON | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $20M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE). | Region G |  | BG5T50 | CONSTRUCTION | 101900000 | FY 2025: 1019000; FY 2026: 36684000; FY 2027: 26494000; FY 2028: 20380000; FY 2029: 17323000
R-5605 | Highway | STI (Prioritization) | DAVIDSON RIVER VILLAGE CONNECTOR | US 64 TO US 276/US 64 IN PISGAH FOREST. | 0.75 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2.592M FOR CON, PAYBACK FY 2020-2034 (FY 2019/ YR 1 SALE) | Division 14 |  | T | BUILD NC CON | 3345000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000 | 223000
R-5701 | Highway | STI (Prioritization) | NC 53 | US 117 BUSINESS (WALKER STREET / WILMINGTON STREET). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO | L FUNDS REPRESENT PROPERTY DONATED BY THE TOWN OF BURGAW. | Region B |  | T | RIGHT-OF-WAY | 165000 | FY 2025: 165000
R-5701 | Highway | STI (Prioritization) | NC 53 | US 117 BUSINESS (WALKER STREET / WILMINGTON STREET). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO | L FUNDS REPRESENT PROPERTY DONATED BY THE TOWN OF BURGAW. | Region B |  | L | RIGHT-OF-WAY | 45000 | FY 2025: 45000
R-5701 | Highway | STI (Prioritization) | NC 53 | US 117 BUSINESS (WALKER STREET / WILMINGTON STREET). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO | L FUNDS REPRESENT PROPERTY DONATED BY THE TOWN OF BURGAW. | Region B |  | T | UTILITIES | 180000 | FY 2025: 180000
R-5701 | Highway | STI (Prioritization) | NC 53 | US 117 BUSINESS (WALKER STREET / WILMINGTON STREET). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO | L FUNDS REPRESENT PROPERTY DONATED BY THE TOWN OF BURGAW. | Region B |  | T | CONSTRUCTION | 2800000 | FY 2027: 28000; FY 2028: 2772000
R-5703 | Highway | STI (Prioritization) | NC 148 (CF HARVEY PARKWAY) | NC 58 TO NC 11. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 4.07 | LENOIR | 2 | Eastern Carolina RPO | COMPLETE. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | Region B |  | T | BUILD NC CON | 46275000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000 | 3085000
R-5703 | Highway | STI (Prioritization) | NC 148 (CF HARVEY PARKWAY) | NC 58 TO NC 11. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | 4.07 | LENOIR | 2 | Eastern Carolina RPO | COMPLETE. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | Region B |  | T | CONSTRUCTION | 28334000
R-5704 | Highway | STI (Prioritization) | NC 87 | SR 1998 (WENTWORTH STREET) / SR 1001 (SANDY CROSS ROAD). INTERSECTION REALIGNMENT. | 0.5 | ROCKINGHAM | 7 | Piedmont Triad RPO | UNDER CONSTRUCTION | Region D
R-5705 | Highway | STI (Prioritization) | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 42 IN FUQUAY-VARINA. WIDEN TO MULTI-LANES. PART ON NEW LOCATION. | 10 | HARNETT, WAKE | 5, 6 | Capital Area MPO
R-5705A | Highway | STI (Prioritization) | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | 4.02 | HARNETT | 6 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 6 |  | T | RIGHT-OF-WAY | 36835000 | FY 2025: 4000000; FY 2026: 4000000
R-5705A | Highway | STI (Prioritization) | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | 4.02 | HARNETT | 6 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 6 |  | T | UTILITIES | 3800000
R-5705A | Highway | STI (Prioritization) | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | 4.02 | HARNETT | 6 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 6 |  | T | BUILD NC CON | 22875000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 1525000 | 6100000
R-5705A | Highway | STI (Prioritization) | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | 4.02 | HARNETT | 6 | Capital Area MPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 6 |  | T | CONSTRUCTION | 33441000 | FY 2025: 5000000; FY 2026: 12294000; FY 2027: 5275000
R-5705B | Highway | STI (Prioritization) | NC 55 | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | 4.99 | WAKE, HARNETT | 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. | Region C |  | T | RIGHT-OF-WAY | 35171000 | FY 2025: 5000000; FY 2026: 5000000
R-5705B | Highway | STI (Prioritization) | NC 55 | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | 4.99 | WAKE, HARNETT | 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. | Region C |  | T | UTILITIES | 1300000
R-5705B | Highway | STI (Prioritization) | NC 55 | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | 4.99 | WAKE, HARNETT | 5, 6 | Capital Area MPO | UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 70722000 | FY 2025: 21217000; FY 2026: 8487000
R-5705C | Highway | STI (Prioritization) | NC 55 | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. |  | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 8170000 | [11 empty] | 8170000
R-5705C | Highway | STI (Prioritization) | NC 55 | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. |  | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | UTILITIES | 1386000 | [11 empty] | 1386000
R-5705C | Highway | STI (Prioritization) | NC 55 | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. |  | WAKE | 5 | Capital Area MPO |  | Not Funded |  | T | CONSTRUCTION | 17900000 | [11 empty] | 17900000
R-5706 | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO US 29. WIDEN TO MULTI-LANES. | 10.9 | CABARRUS, MECKLENBURG | 10 | Cabarrus-Rowan MPO, Charlotte Regional TPO | COORDINATE WITH R-2632AB.
R-5706A | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | 2.35 | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Region E |  | NHP | RIGHT-OF-WAY | 12000000 | FY 2025: 1011000; FY 2026: 3032000; FY 2027: 3032000; FY 2028: 2525000; FY 2029: 2400000
R-5706A | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | 2.35 | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Region E |  | NHP | UTILITIES | 6200000 | FY 2025: 2067000; FY 2026: 2067000; FY 2027: 2066000
R-5706A | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | 2.35 | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO |  | Region E |  | NHP | CONSTRUCTION | 53100000 | FY 2029: 531000; FY 2030: 26550000; FY 2031: 16461000; FY 2032: 9558000
R-5706BA | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO I-85. | 6.07 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 26000000 | [11 empty] | 26000000
R-5706BA | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO I-85. | 6.07 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | UTILITIES | 6500000 | [11 empty] | 6500000
R-5706BA | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO I-85. | 6.07 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | CONSTRUCTION | 139000000 | [11 empty] | 139000000
R-5706BB | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | I-85 TO US 29. | 2.79 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 11220000 | [11 empty] | 11220000
R-5706BB | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | I-85 TO US 29. | 2.79 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 5280000 | [11 empty] | 5280000
R-5706BB | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | I-85 TO US 29. | 2.79 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | UTILITIES | 8000000 | [11 empty] | 8000000
R-5706BB | Highway | STI (Prioritization) | NC 73 (DAVIDSON HIGHWAY) | I-85 TO US 29. | 2.79 | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | CONSTRUCTION | 50700000 | [11 empty] | 50700000
R-5707 | Highway | STI (Prioritization) | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 0.5 | GRANVILLE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region C |  | T | ENGINEERING | 989000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 65000
R-5707 | Highway | STI (Prioritization) | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 0.5 | GRANVILLE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region C |  | T | BUILD NC CON | 1009000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 71000
R-5707 | Highway | STI (Prioritization) | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 0.5 | GRANVILLE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region C |  | T | BUILD NC CON | 3451000 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000 | 231000
R-5707 | Highway | STI (Prioritization) | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | 0.5 | GRANVILLE | 5 | Capital Area MPO | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE) | Region C |  | T | CONSTRUCTION | 528000
R-5709 | Highway | STI (Prioritization) | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTI-LANES. | 15.36 | HOKE, MOORE | 8 | Lumber River RPO, Sandhills MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | RIGHT-OF-WAY | 59423000
R-5709 | Highway | STI (Prioritization) | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTI-LANES. | 15.36 | HOKE, MOORE | 8 | Lumber River RPO, Sandhills MPO | RIGHT-OF-WAY IN PROGRESS | Region E |  | T | UTILITIES | 4976000
R-5709A | Highway | STI (Prioritization) | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. CLEARING, GRUBBING, AND EROSION CONTROL. | 15.36 | HOKE, MOORE | 8 | Lumber River RPO, Sandhills MPO | UNDER CONSTRUCTION. | Region E |  | T | CONSTRUCTION | 17625000
R-5709A | Highway | STI (Prioritization) | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. CLEARING, GRUBBING, AND EROSION CONTROL. | 15.36 | HOKE, MOORE | 8 | Lumber River RPO, Sandhills MPO | UNDER CONSTRUCTION. | Region E |  | T | CONSTRUCTION | 13000000 | FY 2025: 12750000
R-5709B | Highway | STI (Prioritization) | NC 211 | US 15/US 501 IN ABERDEEN TO 0.40 MILES NORTH OF SR 1225 (ASHEMONT ROAD). WIDEN TO MULTI-LANES. | 5.9 | HOKE, MOORE | 8 | Lumber River RPO, Sandhills MPO |  | Region E |  | T | CONSTRUCTION | 114200000 | FY 2029: 1340000; FY 2030: 37620000; FY 2031: 31920000; FY 2032: 23940000; FY 2033: 19380000
R-5709C | Highway | STI (Prioritization) | NC 211 | 0.40 MILES NORTH OF SR 1225 (ASHEMONT ROAD) TO EAST OF SR 1244 (WEST PALMER STREET)/SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTI-LANES. | 9.46 | HOKE | 8 | Lumber River RPO |  | Region E |  | T | CONSTRUCTION | 139700000 | FY 2025: 16764000; FY 2026: 37719000; FY 2027: 32131000; FY 2028: 25146000; FY 2029: 27940000
R-5711 | Highway | STI (Prioritization) | US 21 | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | RIGHT-OF-WAY | 100000
R-5711 | Highway | STI (Prioritization) | US 21 | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | 0.5 | IREDELL | 12 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | CONSTRUCTION | 2950000 | FY 2025: 2216000; FY 2026: 734000
R-5712 | Highway | STI (Prioritization) | NC 16 BUSINESS | SR 1439 (UNITY CHURCH ROAD)/SR 1387 (TRIANGLE CIRCLE). ADD TURN LANES. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | UTILITIES | 1200000 | FY 2025: 1200000
R-5712 | Highway | STI (Prioritization) | NC 16 BUSINESS | SR 1439 (UNITY CHURCH ROAD)/SR 1387 (TRIANGLE CIRCLE). ADD TURN LANES. | 0.5 | LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | CONSTRUCTION | 2300000 | FY 2025: 1176000; FY 2026: 1124000
R-5713 | Highway | STI (Prioritization) | US 74 | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | 5.96 | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Region F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 3200000
R-5714 | Highway | STI (Prioritization) | US 601 | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | 0.98 | SURRY | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | RIGHT-OF-WAY | 10950000
R-5714 | Highway | STI (Prioritization) | US 601 | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | 0.98 | SURRY | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | UTILITIES | 1200000
R-5714 | Highway | STI (Prioritization) | US 601 | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | 0.98 | SURRY | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Region F |  | T | CONSTRUCTION | 29800000 | FY 2030: 5960000; FY 2032: 11920000; FY 2033: 8344000; FY 2034: 3576000
R-5717 | Highway | STI (Prioritization) | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN EXISTING LANES, WIDEN EXISTING SHOULDERS, AND INTERSECTION IMPROVEMENTS. | 11 | CAMDEN, CURRITUCK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 1 |  | T | BUILD NC CON | 18300000 |  | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 6100000
R-5717 | Highway | STI (Prioritization) | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN EXISTING LANES, WIDEN EXISTING SHOULDERS, AND INTERSECTION IMPROVEMENTS. | 11 | CAMDEN, CURRITUCK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 1 |  | T | CONSTRUCTION | 25700000 | FY 2026: 0; FY 2027: 10997000; FY 2028: 9802000; FY 2029: 4901000
R-5717A | Highway | STI (Prioritization) | SR 1224 (OLD SWAMP ROAD) | 0.15 SOUTH OF SR 1225 (LILLY ROAD) TO 0.25 MILES NORTH OF SR 1225 (LILLY ROAD). | 0.4 | CAMDEN | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1
R-5717B | Highway | STI (Prioritization) | SR 1224 (OLD SWAMP ROAD) | REPLACE BRIDGE 140013 OVER JOYCE CREEK. |  | CAMDEN | 1 | Albemarle RPO |  | Division 1 |  | T | CONSTRUCTION | 1900000 | FY 2026: 1900000
R-5718 | Highway | STI (Prioritization) | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 1.27 | JOHNSTON | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Division 4 |  | T | RIGHT-OF-WAY | 8537000
R-5718 | Highway | STI (Prioritization) | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 1.27 | JOHNSTON | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Division 4 |  | T | UTILITIES | 1190000
R-5718 | Highway | STI (Prioritization) | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 1.27 | JOHNSTON | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Division 4 |  | T | BUILD NC CON | 7620000 |  |  | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 3048000
R-5718 | Highway | STI (Prioritization) | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | 1.27 | JOHNSTON | 4 | Upper Coastal Plain RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2027 - 2041 (FY 2027 / YR 7 SALE). | Division 4 |  | T | CONSTRUCTION | 13001000 | FY 2026: 6120000; FY 2027: 3100000; FY 2028: 3781000
R-5720 | Highway | STI (Prioritization) | SR 1770 (EASTERN AVENUE) | SR 1003 (RED OAK ROAD) TO SR 1603 (OLD CARRIAGE ROAD) IN ROCKY MOUNT. WIDEN TO MULTI-LANES. | 2.41 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTION FUNDS SHOWN UNDER U-5026. | Division 4 |  | T | RIGHT-OF-WAY | 12252000
R-5720 | Highway | STI (Prioritization) | SR 1770 (EASTERN AVENUE) | SR 1003 (RED OAK ROAD) TO SR 1603 (OLD CARRIAGE ROAD) IN ROCKY MOUNT. WIDEN TO MULTI-LANES. | 2.41 | NASH | 4 | Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTION FUNDS SHOWN UNDER U-5026. | Division 4 |  | T | UTILITIES | 1470000
R-5721 | Highway | STI (Prioritization) | NC 73 | NC 16 IN LINCOLN COUNTY TO SR 5544 (WEST CATAWBA AVENUE) IN MECKLENBURG COUNTY. WIDEN TO MULTI-LANES. | 9.7 | MECKLENBURG, LINCOLN | 10, 12 | Charlotte Regional TPO, Gaston-Cleveland-Lincoln MPO | COORDINATE WITH U-5765.
R-5721A | Highway | STI (Prioritization) | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. WIDEN TO MULTI-LANES. | 5.57 | LINCOLN, MECKLENBURG | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO |  | Region E, F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 69900000
R-5721A | Highway | STI (Prioritization) | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. WIDEN TO MULTI-LANES. | 5.57 | LINCOLN, MECKLENBURG | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO |  | Region E, F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 9300000
R-5721A | Highway | STI (Prioritization) | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. WIDEN TO MULTI-LANES. | 5.57 | LINCOLN, MECKLENBURG | 10, 12 | Gaston-Cleveland-Lincoln MPO, Charlotte Regional TPO |  | Region E, F | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 189600000
R-5721B | Highway | STI (Prioritization) | NC 73 | VANCE ROAD EXTENSION/ BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). WIDEN TO MULTI-LANES. | 1.88 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | Region E |  | BA | RIGHT-OF-WAY | 14569000 | FY 2025: 1570000; FY 2026: 1606000; FY 2027: 1439000; FY 2028: 1177000
R-5721B | Highway | STI (Prioritization) | NC 73 | VANCE ROAD EXTENSION/ BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). WIDEN TO MULTI-LANES. | 1.88 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | Region E |  | BA | RIGHT-OF-WAY | 131000
R-5721B | Highway | STI (Prioritization) | NC 73 | VANCE ROAD EXTENSION/ BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). WIDEN TO MULTI-LANES. | 1.88 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | Region E |  | T | RIGHT-OF-WAY | 701000
R-5721B | Highway | STI (Prioritization) | NC 73 | VANCE ROAD EXTENSION/ BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). WIDEN TO MULTI-LANES. | 1.88 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | Region E |  | BA | UTILITIES | 3000000 | FY 2025: 1500000
R-5721B | Highway | STI (Prioritization) | NC 73 | VANCE ROAD EXTENSION/ BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). WIDEN TO MULTI-LANES. | 1.88 | MECKLENBURG | 10 | Charlotte Regional TPO | RIGHT-OF-WAY IN PROGRESS. $5.923M IN T FUNDS SWITCHED WITH $5.923M IN BA FOR ROW AS PART OF FUND SWAP 8-9-22. | Region E |  | T | CONSTRUCTION | 59299000 | FY 2029: 19542000; FY 2030: 20751000; FY 2031: 12381000; FY 2032: 6625000
R-5724 | Highway | STI (Prioritization) | US 15 / US 501 | SOUTH OF US 64 BUSINESS TO POWELL PLACE LANE IN PITTSBORO. WIDEN TO MULTI-LANES, MILL AND RESURFACE, AND CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. | 1.9 | CHATHAM | 8 | Central Pines RPO |  | Division 8
R-5724A | Highway | STI (Prioritization) | US 15 / US 501 | US 15 / US 501, SOUTH OF US 64 BUSINESS TO NORTH OF US 64 BUSINESS. CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. |  | CHATHAM | 8 | Central Pines RPO | UNDER CONSTRUCTION | Division 8 |  | T | CONSTRUCTION | 4000000
R-5724B | Highway | STI (Prioritization) | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | 1.79 | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | RIGHT-OF-WAY | 3900000 | FY 2025: 924000; FY 2026: 390000; FY 2027: 390000
R-5724B | Highway | STI (Prioritization) | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | 1.79 | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | UTILITIES | 1300000
R-5724B | Highway | STI (Prioritization) | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | 1.79 | CHATHAM | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 18300000 | FY 2026: 183000; FY 2027: 12261000; FY 2028: 5856000
R-5725 | Highway | STI (Prioritization) | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH U-6127. UNDER CONSTRUCTION | Region D |  | T | RIGHT-OF-WAY | 1287000
R-5725 | Highway | STI (Prioritization) | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH U-6127. UNDER CONSTRUCTION | Region D |  | T | RIGHT-OF-WAY | 93000 | FY 2025: 73000
R-5725 | Highway | STI (Prioritization) | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH U-6127. UNDER CONSTRUCTION | Region D |  | T | UTILITIES | 500000
R-5725 | Highway | STI (Prioritization) | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | 0.5 | GUILFORD | 7 | Greensboro Urban Area MPO | COORDINATE WITH U-6127. UNDER CONSTRUCTION | Region D |  | T | CONSTRUCTION | 7300000 | FY 2025: 1994000
R-5726 | Highway | STI (Prioritization) | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO A FOUR LANE DIVIDED FACILITY. | 4.09 | MOORE | 8 | Central Pines RPO | UNDER CONSTRUCTION | Region E |  | T | CONSTRUCTION | 49200000 | FY 2025: 12081000; FY 2026: 17141000; FY 2027: 12738000; FY 2028: 7240000
R-5726A | Highway | STI (Prioritization) | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). CLEARING, GRUBBING, AND EROSION CONTROL. | 4.09 | MOORE | 8 | Central Pines RPO |  | Region E |  | T | CONSTRUCTION | 5679000
R-5727 | Highway | STI (Prioritization) | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 3.02 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 19901000
R-5727 | Highway | STI (Prioritization) | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 3.02 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1300000
R-5727 | Highway | STI (Prioritization) | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | 3.02 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 115000000
R-5728 | Highway | STI (Prioritization) | US 601 | SOUTH SALISBURY STREET IN MOCKSVILLE. INTERSECTION IMPROVEMENTS. | 0.5 | DAVIE | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | Region D
R-5730 | Highway | STI (Prioritization) | SR 1605 (OLD US 421) | SR 1146 (SHACKTOWN ROAD) TO SR 1711 (SPEER BRIDGE ROAD). CONSTRUCT NEW ROADWAY TO REALIGN SR 1605 WITH SR 1711 AND CONSTRUCT A ROUNDABOUT AT THE INTERSECTION WITH SR 1146. | 0.18 | YADKIN | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Division 11 |  | T | CONSTRUCTION | 3216000
R-5734 | Highway | STI (Prioritization) | US 23/US 441 | US 64 TO SR 1649 (PRENTISS BRIDGE ROAD). IMPLEMENT ACCESS MANAGEMENT STRATEGIES. | 3.2 | MACON | 14 | Southwestern RPO | SEGMENT A INCLUDES THE REPLACEMENT OF BRIDGE 314 FORMERLY SCHEDULED TO BE REPLACED UNDER 17BP.14.R.154
R-5734A | Highway | STI (Prioritization) | US 23/US 441 | US 64 TO SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE). | 0.82 | MACON | 14 | Southwestern RPO | COMPLETE; BUILD NC BOND FUNDING: $1.788 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $9.797 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 14 |  | T | ENGINEERING | 2310000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000
R-5734A | Highway | STI (Prioritization) | US 23/US 441 | US 64 TO SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE). | 0.82 | MACON | 14 | Southwestern RPO | COMPLETE; BUILD NC BOND FUNDING: $1.788 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $9.797 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE) | Division 14 |  | T | BUILD NC CON | 12600000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000 | 840000
R-5734B | Highway | STI (Prioritization) | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | 2.42 | MACON | 14 | Southwestern RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 13800000 | [11 empty] | 13800000
R-5734B | Highway | STI (Prioritization) | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | 2.42 | MACON | 14 | Southwestern RPO |  | Not Funded |  | T | UTILITIES | 3200000 | [11 empty] | 3200000
R-5734B | Highway | STI (Prioritization) | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | 2.42 | MACON | 14 | Southwestern RPO |  | Not Funded |  | T | CONSTRUCTION | 26600000 | [11 empty] | 26600000
R-5734C | Highway | STI (Prioritization) | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | 9 | MACON | 14 | Southwestern RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 5000000 | [11 empty] | 5000000
R-5734C | Highway | STI (Prioritization) | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | 9 | MACON | 14 | Southwestern RPO |  | Not Funded |  | T | UTILITIES | 600000 | [11 empty] | 600000
R-5734C | Highway | STI (Prioritization) | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | 9 | MACON | 14 | Southwestern RPO |  | Not Funded |  | T | CONSTRUCTION | 53600000 | [11 empty] | 53600000
R-5735 | Highway | STI (Prioritization) | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 0.07 | CHEROKEE | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | Division 14 |  | T | ENGINEERING | 30000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
R-5735 | Highway | STI (Prioritization) | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 0.07 | CHEROKEE | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | Division 14 |  | T | ENGINEERING | 2670000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000 | 178000
R-5735 | Highway | STI (Prioritization) | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 0.07 | CHEROKEE | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | Division 14 |  | T | BUILD NC ROW | 4815000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000 | 321000
R-5735 | Highway | STI (Prioritization) | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 0.07 | CHEROKEE | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | Division 14 |  | T | BUILD NC CON | 5805000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000
R-5735 | Highway | STI (Prioritization) | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 0.07 | CHEROKEE | 14 | Southwestern RPO | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $7.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE) | Division 14 |  | T | BUILD NC CON | 9585000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000 | 639000
R-5735A | Highway | STI (Prioritization) | US 19/US 74/US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | 0.73 | CHEROKEE | 14 | Southwestern RPO | CLEARING ONLY. | Division 14
R-5736 | Highway | STI (Prioritization) | US 601 | SR 1301 (MADISON ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | 1.52 | DAVIE | 9 | Northwest Piedmont RPO |  | Division 9 |  | BGANY | RIGHT-OF-WAY | 6400000 | FY 2029: 488000; FY 2030: 2926000; FY 2031: 1706000; FY 2032: 640000; FY 2033: 640000
R-5736 | Highway | STI (Prioritization) | US 601 | SR 1301 (MADISON ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | 1.52 | DAVIE | 9 | Northwest Piedmont RPO |  | Division 9 |  | BGANY | UTILITIES | 800000 | FY 2029: 800000
R-5736 | Highway | STI (Prioritization) | US 601 | SR 1301 (MADISON ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTI-LANES. | 1.52 | DAVIE | 9 | Northwest Piedmont RPO |  | Division 9 |  | BGANY | CONSTRUCTION | 32100000 | FY 2032: 7797000; FY 2033: 14485000; FY 2034: 9818000
R-5737 | Highway | STI (Prioritization) | US 29 / US 70 / BUSINESS 85 | SR 1798 (OLD GREENSBORO ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | DAVIDSON | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION; INCLUDES PARTICIPATION BY DAVIDSON COUNTY COMMUNITY COLLEGE | Division 9 |  | T | CONSTRUCTION | 29777000 | FY 2025: 1915000
R-5738 | Highway | STI (Prioritization) | SR 1208 (WEST KITTY HAWK ROAD) | SR 1210 (BOB PERRY ROAD) TO IVY LANE. UPGRADE FACILITY AND REPLACE BRIDGE 270040. | 1.01 | DARE | 1 | Albemarle RPO | COMPLETED. BUILD NC BOND FUNDING: $3,561,232 FOR CONSTRUCTION PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE). | Division 1 |  | T | BUILD NC CON | 4646000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 | 306000
R-5739 | Highway | STI (Prioritization) | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 10.41 | NORTHAMPTON | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 1 |  | T | RIGHT-OF-WAY | 5065000
R-5739 | Highway | STI (Prioritization) | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 10.41 | NORTHAMPTON | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 1 |  | T | UTILITIES | 2300000
R-5739 | Highway | STI (Prioritization) | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 10.41 | NORTHAMPTON | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 1 |  | T | BUILD NC CON | 18300000 |  | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 1220000 | 6100000
R-5739 | Highway | STI (Prioritization) | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING LANES AND SHOULDERS. | 10.41 | NORTHAMPTON | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 6 SALE). | Division 1 |  | T | CONSTRUCTION | 21199000 | FY 2025: 5507000; FY 2026: 599000; FY 2027: 9417000; FY 2028: 5676000
R-5740 | Highway | STI (Prioritization) | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 4.39 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 1 |  | T | ENGINEERING | 1035000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000 | 69000
R-5740 | Highway | STI (Prioritization) | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 4.39 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 1 |  | T | BUILD NC ROW | 765000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000 | 51000
R-5740 | Highway | STI (Prioritization) | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 4.39 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 1 |  | T | UTILITIES | 140000
R-5740 | Highway | STI (Prioritization) | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | 4.39 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Division 1 |  | T | CONSTRUCTION | 5841000
R-5742 | Highway | STI (Prioritization) | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | CLAY | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 14 |  | T | ENGINEERING | 2490000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000
R-5742 | Highway | STI (Prioritization) | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | CLAY | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 14 |  | T | ENGINEERING | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
R-5742 | Highway | STI (Prioritization) | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | CLAY | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 14 |  | T | BUILD NC ROW | 540000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000
R-5742 | Highway | STI (Prioritization) | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | CLAY | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 14 |  | T | BUILD NC CON | 17085000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000 | 1139000
R-5742 | Highway | STI (Prioritization) | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | CLAY | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 14 |  | T | BUILD NC CON | 10992000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000 | 687000
R-5742 | Highway | STI (Prioritization) | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | CLAY | 14 | Southwestern RPO | COMPLETE - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE). | Division 14 |  | T | CONSTRUCTION | 4770000
R-5742A | Highway | STI (Prioritization) | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | 4.15 | CLAY | 14 | Southwestern RPO | CLEARING ONLY. | Division 14
R-5745 | Highway | STI (Prioritization) | US 64/NC 90/NC 18 (WILKESBORO BLVD) | INTERSECTION OF US 64/NC 90/NC 18 (WILKESBORO BOULEVARD) AND US 64/NC 90 (TAYLORSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | COMPLETE; BUILD NC BOND FUNDING: $1.313M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE) | Division 11 |  | T | BUILD NC CON | 1695000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000 | 113000
R-5751 | Highway | STI (Prioritization) | US 74 | NC 72/NC 130. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T | RIGHT-OF-WAY | 325000
R-5751 | Highway | STI (Prioritization) | US 74 | NC 72/NC 130. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | ROBESON | 6 | Lumber River RPO | UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 28286000 | FY 2025: 9334000; FY 2026: 8960000; FY 2027: 4000000
R-5753 | Highway | Other | VARIOUS | FEDERAL LANDS TRANSPORTATION PROGRAM (FLTP) AND EMERGENCY RELIEF FOR FEDERALLY OWNED ROADS (ERFO). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO FEDERAL LANDS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | PROGRAM IN PROGRESS | Exempt |  | ERFO | CONSTRUCTION | 7339000 | FY 2025: 677000; FY 2027: 5992000
R-5753 | Highway | Other | VARIOUS | FEDERAL LANDS TRANSPORTATION PROGRAM (FLTP) AND EMERGENCY RELIEF FOR FEDERALLY OWNED ROADS (ERFO). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO FEDERAL LANDS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | PROGRAM IN PROGRESS | Exempt |  | FLTP | CONSTRUCTION | 95853000 | FY 2025: 18844000; FY 2026: 5977000; FY 2027: 23024000; FY 2028: 4486000
R-5753A | Highway | Other | VARIOUS | DEPLOYMENT OF AUTOMATED SHUTTLE AT WRIGHT BROTHERS NATIONAL MEMORIAL. |  | DARE | 1 | Albemarle RPO |  | Exempt |  | FLTP | IMPLEMENTATION | 95000
R-5757 | Highway | STI (Prioritization) | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | 24.3 | NORTHAMPTON | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | BGLT5 | RIGHT-OF-WAY | 3200000
R-5757 | Highway | STI (Prioritization) | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | 24.3 | NORTHAMPTON | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | BGLT5 | UTILITIES | 4122000
R-5757A | Highway | STI (Prioritization) | NC 305 | HERTFORD COUNTY LINE TO NORTH OF SR 1503 (LASKER ROAD). UPGRADE ROADWAY. | 10.33 | NORTHAMPTON | 1 | Peanut Belt RPO |  | Division 1 |  | BGLT5 | CONSTRUCTION | 25600000 | FY 2026: 256000; FY 2027: 12151000; FY 2028: 8417000; FY 2029: 4776000
R-5757B | Highway | STI (Prioritization) | NC 305 | NORTH OF SR 1503 (LASKER ROAD) TO SEABOARD TOWN LIMITS. UPGRADE ROADWAY. | 13.97 | NORTHAMPTON | 1 | Peanut Belt RPO |  | Division 1 |  | BGLT5 | CONSTRUCTION | 29100000 | FY 2026: 291000; FY 2027: 13082000; FY 2028: 9183000; FY 2029: 6544000
R-5759 | Highway | STI (Prioritization) | NC 115 | US 421 TO 2ND STREET. WIDEN TO TWO LANES WITH MEDIAN. CONSTRUCT BIKE LANES AND SIDEWALKS. | 2.98 | WILKES | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $14M FOR CON PAYBACK FY 2026-2042 (FY 2026 / YR6 SALE) | Division 11 |  | T | ENGINEERING | 1365000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000 | 91000
R-5759 | Highway | STI (Prioritization) | NC 115 | US 421 TO 2ND STREET. WIDEN TO TWO LANES WITH MEDIAN. CONSTRUCT BIKE LANES AND SIDEWALKS. | 2.98 | WILKES | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $14M FOR CON PAYBACK FY 2026-2042 (FY 2026 / YR6 SALE) | Division 11 |  | T | BUILD NC ROW | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
R-5759 | Highway | STI (Prioritization) | NC 115 | US 421 TO 2ND STREET. WIDEN TO TWO LANES WITH MEDIAN. CONSTRUCT BIKE LANES AND SIDEWALKS. | 2.98 | WILKES | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $14M FOR CON PAYBACK FY 2026-2042 (FY 2026 / YR6 SALE) | Division 11 |  | T | RIGHT-OF-WAY | 12600000
R-5759 | Highway | STI (Prioritization) | NC 115 | US 421 TO 2ND STREET. WIDEN TO TWO LANES WITH MEDIAN. CONSTRUCT BIKE LANES AND SIDEWALKS. | 2.98 | WILKES | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $14M FOR CON PAYBACK FY 2026-2042 (FY 2026 / YR6 SALE) | Division 11 |  | T | UTILITIES | 900000
R-5759 | Highway | STI (Prioritization) | NC 115 | US 421 TO 2ND STREET. WIDEN TO TWO LANES WITH MEDIAN. CONSTRUCT BIKE LANES AND SIDEWALKS. | 2.98 | WILKES | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $14M FOR CON PAYBACK FY 2026-2042 (FY 2026 / YR6 SALE) | Division 11 |  | T | BUILD NC CON | 21345000 |  | 1423000 | 1423000 | 1423000 | 1423000 | 1423000 | 1423000 | 1423000 | 1423000 | 1423000 | 1423000 | 7115000
R-5759 | Highway | STI (Prioritization) | NC 115 | US 421 TO 2ND STREET. WIDEN TO TWO LANES WITH MEDIAN. CONSTRUCT BIKE LANES AND SIDEWALKS. | 2.98 | WILKES | 11 | High Country RPO | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $14M FOR CON PAYBACK FY 2026-2042 (FY 2026 / YR6 SALE) | Division 11 |  | T | CONSTRUCTION | 36600000 | FY 2026: 0; FY 2027: 13005000; FY 2028: 13972000; FY 2029: 9623000
R-5761 | Highway | STI (Prioritization) | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | 0.65 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 2200000
R-5761 | Highway | STI (Prioritization) | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | 0.65 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 740000
R-5761 | Highway | STI (Prioritization) | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | 0.65 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 20800000
R-5762 | Highway | STI (Prioritization) | NC 16 | INTERSECTION OF NC 16 AND SR 1609 (COUNTY HOME ROAD). CONSTRUCT INTERSECTION IMPROVMENTS. | 0.5 | ALEXANDER | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | T | RIGHT-OF-WAY | 120000
R-5762 | Highway | STI (Prioritization) | NC 16 | INTERSECTION OF NC 16 AND SR 1609 (COUNTY HOME ROAD). CONSTRUCT INTERSECTION IMPROVMENTS. | 0.5 | ALEXANDER | 12 | Greater Hickory MPO | UNDER CONSTRUCTION. | Division 12 |  | T | CONSTRUCTION | 885000
R-5763 | Highway | STI (Prioritization) | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 3.67 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $17.8M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 14 |  | T | RIGHT-OF-WAY | 17400000 | FY 2025: 5000000
R-5763 | Highway | STI (Prioritization) | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 3.67 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $17.8M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 14 |  | T | UTILITIES | 1200000
R-5763 | Highway | STI (Prioritization) | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 3.67 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $17.8M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 14 |  | T | BUILD NC CON | 27150000 | FY 2030: 1810000; FY 2031: 1810000; FY 2032: 1810000; FY 2033: 1810000; FY 2034: 1810000; FY 2035: 1810000 | 16290000
R-5763 | Highway | STI (Prioritization) | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | 3.67 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS. NC BUILD BONDS: $17.8M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 14 |  | T | CONSTRUCTION | 40301000 | FY 2029: 13316000; FY 2030: 3076000; FY 2031: 15170000; FY 2032: 8739000
R-5766 | Highway | STI (Prioritization) | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO US 158 / US 29 BUSINESS (FREEWAY DRIVE) IN REIDSVILLE. UPGRADE ROADWAY. |  | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | BGANY | RIGHT-OF-WAY | 18600000 | FY 2030: 186000; FY 2031: 8502000; FY 2032: 6192000; FY 2033: 1860000; FY 2034: 1860000
R-5766 | Highway | STI (Prioritization) | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO US 158 / US 29 BUSINESS (FREEWAY DRIVE) IN REIDSVILLE. UPGRADE ROADWAY. |  | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | BGANY | UTILITIES | 4800000 | FY 2030: 2400000; FY 2031: 2400000
R-5766 | Highway | STI (Prioritization) | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO US 158 / US 29 BUSINESS (FREEWAY DRIVE) IN REIDSVILLE. UPGRADE ROADWAY. |  | ROCKINGHAM | 7 | Piedmont Triad RPO |  | Division 7 |  | BGANY | CONSTRUCTION | 34400000 | FY 2033: 8600000; FY 2034: 8600000; FY 2035: 8600000 | 8600000
R-5768 | Highway | STI (Prioritization) | US 311 | NC 65 IN WALNUT COVE. UPGRADE INTERSECTION AND IMPROVE RAILROAD CROSSING. | 0.5 | STOKES | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | Division 9 |  | BGLT5 | CONSTRUCTION | 5570000
R-5768 | Highway | STI (Prioritization) | US 311 | NC 65 IN WALNUT COVE. UPGRADE INTERSECTION AND IMPROVE RAILROAD CROSSING. | 0.5 | STOKES | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | Division 9 |  | T | CONSTRUCTION | 1393000
R-5772 | Highway | STI (Prioritization) | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 1.27 | WILKES | 11 | High Country RPO | BUILD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | RIGHT-OF-WAY | 3500000 | FY 2026: 1200000; FY 2027: 1600000; FY 2028: 350000; FY 2029: 350000
R-5772 | Highway | STI (Prioritization) | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 1.27 | WILKES | 11 | High Country RPO | BUILD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | UTILITIES | 1900000 | FY 2026: 950000; FY 2027: 950000
R-5772 | Highway | STI (Prioritization) | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 1.27 | WILKES | 11 | High Country RPO | BUILD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | BUILD NC CON | 13725000 |  |  |  | 915000 | 915000 | 915000 | 915000 | 915000 | 915000 | 915000 | 915000 | 6405000
R-5772 | Highway | STI (Prioritization) | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | 1.27 | WILKES | 11 | High Country RPO | BUILD NC BOND FUNDING: $9,000,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | CONSTRUCTION | 12200000 | FY 2027: 3180000; FY 2028: 1600000; FY 2029: 7420000
R-5775 | Highway | Locally Selected | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - HF(M) IS SPOT SAFETY (SS-4911 AL); | Exempt |  | BGDA | CONSTRUCTION | 1548000
R-5775 | Highway | Locally Selected | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - HF(M) IS SPOT SAFETY (SS-4911 AL); | Exempt |  | BGDA | CONSTRUCTION | 640000
R-5775 | Highway | Locally Selected | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - HF(M) IS SPOT SAFETY (SS-4911 AL); | Exempt |  | HF(M) | CONSTRUCTION | 160000
R-5775 | Highway | Locally Selected | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | CALDWELL | 11 | Greater Hickory MPO | UNDER CONSTRUCTION. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - HF(M) IS SPOT SAFETY (SS-4911 AL); | Exempt |  | HF(M) | CONSTRUCTION | 387000
R-5777 | Highway | STI (Prioritization) | US 70 | SR 1124 (GRANTHAM ROAD) TO THE PROPOSED US 70 HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY. | 8.6 | CRAVEN | 2 | New Bern Area MPO
R-5777A | Highway | STI (Prioritization) | US 70 | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713. | Statewide Mobility |  | T | RIGHT-OF-WAY | 47438000
R-5777A | Highway | STI (Prioritization) | US 70 | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713. | Statewide Mobility |  | T | UTILITIES | 300000
R-5777A | Highway | STI (Prioritization) | US 70 | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713. | Statewide Mobility |  | T | CONSTRUCTION | 50778000 | FY 2025: 15220000
R-5777B | Highway | STI (Prioritization) | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | ENGINEERING | 105000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000
R-5777B | Highway | STI (Prioritization) | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | BUILD NC ROW | 15000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
R-5777B | Highway | STI (Prioritization) | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | RIGHT-OF-WAY | 47432000
R-5777B | Highway | STI (Prioritization) | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | UTILITIES | 300000
R-5777B | Highway | STI (Prioritization) | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CRAVEN | 2 | New Bern Area MPO | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH R-5777A AND U-5713. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE). | Region B |  | T | CONSTRUCTION | 50778000 | FY 2025: 15220000
R-5777C | Highway | STI (Prioritization) | US 70 | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | 6.88 | CRAVEN | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 49129000 | FY 2025: 31651000; FY 2026: 7913000; FY 2027: 2913000
R-5777C | Highway | STI (Prioritization) | US 70 | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | 6.88 | CRAVEN | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | UTILITIES | 20586000 | FY 2025: 10486000
R-5777C | Highway | STI (Prioritization) | US 70 | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | 6.88 | CRAVEN | 2 | New Bern Area MPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 278703000 | FY 2025: 61314000; FY 2026: 58528000; FY 2027: 55741000; FY 2028: 30000000
R-5777D | Highway | STI (Prioritization) | US 70 | INSTALL BROADBAND FIBER ALONG US 70 FROM I-40 TO PORT OF MOREHEAD CITY. | 138.47 | CRAVEN, JOHNSTON, WAYNE, LENOIR, CARTERET, WAKE | 2, 4, 5 | Down East RPO, Eastern Carolina RPO, New Bern Area MPO, Upper Coastal Plain RPO, Goldsboro Urban Area MPO, Capital Area MPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5986C, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | DP | CONSTRUCTION | 11400000
R-5777D | Highway | STI (Prioritization) | US 70 | INSTALL BROADBAND FIBER ALONG US 70 FROM I-40 TO PORT OF MOREHEAD CITY. | 138.47 | CRAVEN, JOHNSTON, WAYNE, LENOIR, CARTERET, WAKE | 2, 4, 5 | Down East RPO, Eastern Carolina RPO, New Bern Area MPO, Upper Coastal Plain RPO, Goldsboro Urban Area MPO, Capital Area MPO | UNDER CONSTRUCTION. LETTING TO BE COMBINED WITH I-5986C, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. | Statewide Mobility |  | T | CONSTRUCTION | 22100000
R-5779 | Highway | STI (Prioritization) | SR 1631 (CROSSROADS PARKWAY) | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | 0.31 | MADISON | 13 | French Broad River MPO | COMPLETE. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170) | Division 13 |  | ADHSL | CONSTRUCTION | 1611000
R-5779 | Highway | STI (Prioritization) | SR 1631 (CROSSROADS PARKWAY) | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | 0.31 | MADISON | 13 | French Broad River MPO | COMPLETE. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170) | Division 13 |  | T | CONSTRUCTION | 1510000
R-5779 | Highway | STI (Prioritization) | SR 1631 (CROSSROADS PARKWAY) | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | 0.31 | MADISON | 13 | French Broad River MPO | COMPLETE. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170) | Division 13 |  | O | CONSTRUCTION | 950000
R-5781 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 1 |  | TA | CONSTRUCTION | 2880000
R-5781 | Bike & Ped | Other | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 1 |  | HF | CONSTRUCTION | 720000
R-5782 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 2 |  | TA | CONSTRUCTION | 2880000
R-5782 | Bike & Ped | Other | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 2 |  | HF | CONSTRUCTION | 720000
R-5783 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 3 |  | TA | CONSTRUCTION | 2880000
R-5783 | Bike & Ped | Other | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 3 |  | HF | CONSTRUCTION | 720000
R-5784 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 4 |  | TA | CONSTRUCTION | 2880000
R-5784 | Bike & Ped | Other | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 4 |  | HF | CONSTRUCTION | 720000
R-5785 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS | Division 5 |  | TA | CONSTRUCTION | 880000
R-5785 | Bike & Ped | Other | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS | Division 5 |  | HF | CONSTRUCTION | 220000
R-5786 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 6 |  | TA | CONSTRUCTION | 2880000
R-5786 | Bike & Ped | Other | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | UNDER CONSTRUCTION. "HF" FUNDS REFLECT STATE HIGHWAY FUNDS. | Division 6 |  | HF | CONSTRUCTION | 720000
R-5787 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS | Division 7 |  | TA | CONSTRUCTION | 3600000
R-5787 | Bike & Ped | Other | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS | Division 7 |  | HF | CONSTRUCTION | 900000
R-5788 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS | Division 8 |  | TA | CONSTRUCTION | 2880000
R-5788 | Bike & Ped | Other | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS | Division 8 |  | HF | CONSTRUCTION | 720000
R-5789 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS | Division 9 |  | TA | CONSTRUCTION | 2880000
R-5789 | Bike & Ped | Other | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | IN PROGRESS; "HF" FUNDS REFLECT STATE HIGHWAY FUNDS | Division 9 |  | HF | CONSTRUCTION | 720000
R-5790 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS | Division 10 |  | TA | CONSTRUCTION | 2880000
R-5790 | Bike & Ped | Other | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS | Division 10 |  | HF | CONSTRUCTION | 720000
R-5791 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS | Division 11 |  | TA | CONSTRUCTION | 2880000
R-5791 | Bike & Ped | Other | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS | Division 11 |  | HF | CONSTRUCTION | 720000
R-5792 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS | Division 12 |  | TA | CONSTRUCTION | 2880000
R-5792 | Bike & Ped | Other | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS | Division 12 |  | HF | CONSTRUCTION | 720000
R-5793 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS. HSIP FUNDS TO BE USED ON R-5793KB. | Division 13 |  | TA | CONSTRUCTION | 5123000
R-5793 | Bike & Ped | Other | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS. HSIP FUNDS TO BE USED ON R-5793KB. | Division 13 |  | HF | CONSTRUCTION | 1281000
R-5794 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS | Division 14 |  | TA | CONSTRUCTION | 2880000
R-5794 | Bike & Ped | Other | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | UNDER CONSTRUCTION. "HF" FUNDS ARE STATE HIGHWAY FUNDS | Division 14 |  | HF | CONSTRUCTION | 720000
R-5795 | Highway | STI (Prioritization) | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | 0.69 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Region A |  | T | RIGHT-OF-WAY | 2800000 | FY 2030: 672000; FY 2031: 1344000; FY 2032: 224000; FY 2033: 280000; FY 2034: 280000
R-5795 | Highway | STI (Prioritization) | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | 0.69 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Region A |  | T | UTILITIES | 7200000 | FY 2030: 3600000; FY 2031: 3600000
R-5795 | Highway | STI (Prioritization) | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | 0.69 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Region A |  | T | CONSTRUCTION | 13400000 | FY 2033: 4902000; FY 2034: 6245000; FY 2035: 2253000
R-5796 | Highway | STI (Prioritization) | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 0.78 | HERTFORD | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. | Region A |  | T | RIGHT-OF-WAY | 2574000 | FY 2025: 1236000; FY 2026: 257000; FY 2027: 257000
R-5796 | Highway | STI (Prioritization) | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 0.78 | HERTFORD | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. | Region A |  | T | UTILITIES | 2000000 | FY 2025: 1000000
R-5796 | Highway | STI (Prioritization) | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO THREE LANES. | 0.78 | HERTFORD | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. INCLUDES B-5605. | Region A |  | T | CONSTRUCTION | 17900000 | FY 2026: 5000000; FY 2027: 6635000; FY 2028: 6265000
R-5797 | Highway | STI (Prioritization) | US 74 | SR 1506 (BOARDMAN ROAD). UPGRADE AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | COLUMBUS | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 18620000
R-5798 | Highway | STI (Prioritization) | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | 2.87 | ANSON | 10 | Rocky River RPO |  | Statewide Mobility |  | BGLT5 | RIGHT-OF-WAY | 14800000 | FY 2029: 2072000; FY 2030: 3552000; FY 2031: 3552000; FY 2032: 2664000; FY 2033: 2960000
R-5798 | Highway | STI (Prioritization) | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | 2.87 | ANSON | 10 | Rocky River RPO |  | Statewide Mobility |  | BGLT5 | UTILITIES | 4900000 | FY 2029: 2450000; FY 2030: 2450000
R-5798 | Highway | STI (Prioritization) | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | 2.87 | ANSON | 10 | Rocky River RPO |  | Statewide Mobility |  | BGLT5 | CONSTRUCTION | 65100000 | FY 2032: 9765000; FY 2033: 31899000; FY 2034: 18228000; FY 2035: 5208000
R-5799 | Highway | STI (Prioritization) | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region G |  | T | BUILD NC ROW | 1290000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000 | 86000
R-5799 | Highway | STI (Prioritization) | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region G |  | T | RIGHT-OF-WAY | 4600000
R-5799 | Highway | STI (Prioritization) | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region G |  | T | UTILITIES | 600000
R-5799 | Highway | STI (Prioritization) | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | 0.5 | TRANSYLVANIA | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE) | Region G |  | T | CONSTRUCTION | 23651000 | FY 2025: 10803000; FY 2026: 4839000
R-5800 | Highway | STI (Prioritization) | US 64/ US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | 1.17 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | T | RIGHT-OF-WAY | 14800000 | FY 2025: 1974000; FY 2026: 1480000; FY 2027: 1480000
R-5800 | Highway | STI (Prioritization) | US 64/ US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | 1.17 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | T | UTILITIES | 4400000
R-5800 | Highway | STI (Prioritization) | US 64/ US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | 1.17 | TRANSYLVANIA | 14 | Land-of-Sky RPO | RIGHT-OF-WAY IN PROGRESS | Region G |  | BG5T50 | CONSTRUCTION | 32500000 | FY 2030: 12675000; FY 2031: 12675000; FY 2032: 7150000
R-5806 | Highway | STI (Prioritization) | SR 1336 (HARVEY POINT ROAD) | US 17 TO SR 1350 (CHURCHES LANE). MODERNIZE ROADWAY. | 6.13 | PERQUIMANS | 1 | Albemarle RPO | UNDER CONSTRUCTION. | Division 1 |  | BGLT5 | CONSTRUCTION | 5170000
R-5807 | Highway | STI (Prioritization) | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 6.82 | CAMDEN | 1 | Albemarle RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 1 |  | BGANY | RIGHT-OF-WAY | 2000000 | FY 2025: 2000000
R-5807 | Highway | STI (Prioritization) | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 6.82 | CAMDEN | 1 | Albemarle RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 1 |  | BGANY | UTILITIES | 9600000 | FY 2025: 4800000; FY 2026: 4800000
R-5807 | Highway | STI (Prioritization) | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 6.82 | CAMDEN | 1 | Albemarle RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 1 |  | T | BUILD NC CON | 15255000 |  |  |  | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 1017000 | 7119000
R-5807 | Highway | STI (Prioritization) | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | 6.82 | CAMDEN | 1 | Albemarle RPO | BUILD NC BOND FUNDING: $10,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 1 |  | T | CONSTRUCTION | 17600000 | FY 2028: 0; FY 2029: 10976000; FY 2030: 6624000
R-5808 | Highway | STI (Prioritization) | US 158 | SR 1002 (ACORN HILL ROAD) TO PASQUOTANK COUNTY LINE. MODERNIZE ROADWAY. | 3.99 | GATES, PASQUOTANK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | NHP | RIGHT-OF-WAY | 143000
R-5808 | Highway | STI (Prioritization) | US 158 | SR 1002 (ACORN HILL ROAD) TO PASQUOTANK COUNTY LINE. MODERNIZE ROADWAY. | 3.99 | GATES, PASQUOTANK | 1 | Albemarle RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | BGLT5 | CONSTRUCTION | 19701000 | FY 2025: 5352000; FY 2026: 8687000; FY 2027: 5662000
R-5809 | Highway | STI (Prioritization) | NC 45 | HERTFORD COUNTY LINE TO WASHINGTON COUNTY LINE. MODERNIZE ROADWAY. | 24.8 | BERTIE | 1 | Peanut Belt RPO
R-5809A | Highway | STI (Prioritization) | NC 45 | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. MODERNIZE ROADWAY. | 9.26 | BERTIE | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | T | RIGHT-OF-WAY | 315000
R-5809A | Highway | STI (Prioritization) | NC 45 | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. MODERNIZE ROADWAY. | 9.26 | BERTIE | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | T | UTILITIES | 150000
R-5809A | Highway | STI (Prioritization) | NC 45 | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. MODERNIZE ROADWAY. | 9.26 | BERTIE | 1 | Peanut Belt RPO | RIGHT-OF-WAY IN PROGRESS. | Division 1 |  | BGLT5 | CONSTRUCTION | 13201000 | FY 2025: 132000; FY 2026: 6855000; FY 2027: 5593000; FY 2028: 621000
R-5809B | Highway | STI (Prioritization) | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. MODERNIZE ROADWAY. | 12.41 | BERTIE | 1 | Peanut Belt RPO |  | Division 1 |  | BGLT5 | RIGHT-OF-WAY | 4420000 | FY 2025: 453000; FY 2026: 1088000; FY 2027: 1088000; FY 2028: 907000; FY 2029: 884000
R-5809B | Highway | STI (Prioritization) | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. MODERNIZE ROADWAY. | 12.41 | BERTIE | 1 | Peanut Belt RPO |  | Division 1 |  | BGLT5 | UTILITIES | 12944000 | FY 2025: 6472000; FY 2026: 6472000
R-5809B | Highway | STI (Prioritization) | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. MODERNIZE ROADWAY. | 12.41 | BERTIE | 1 | Peanut Belt RPO |  | Division 1 |  | BGLT5 | CONSTRUCTION | 33000000 | FY 2028: 330000; FY 2029: 14520000; FY 2030: 10230000; FY 2031: 7920000
R-5809C | Highway | STI (Prioritization) | NC 45 | SOUTHERN CITY LIMITS OF COLERAIN TO HERTFORD COUNTY LINE. MODERNIZE ROADWAY. | 3.15 | BERTIE | 1 | Peanut Belt RPO | COMPLETED. | Division 1
R-5810 | Highway | STI (Prioritization) | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | 2.01 | MARTIN | 1 | Mid-East RPO |  | Division 1 |  | T | RIGHT-OF-WAY | 250000 | FY 2025: 250000
R-5810 | Highway | STI (Prioritization) | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | 2.01 | MARTIN | 1 | Mid-East RPO |  | Division 1 |  | T | UTILITIES | 80000 | FY 2025: 80000
R-5810 | Highway | STI (Prioritization) | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | 2.01 | MARTIN | 1 | Mid-East RPO |  | Division 1 |  | BGANY | CONSTRUCTION | 13300000 | FY 2027: 6384000; FY 2028: 5586000; FY 2029: 1330000
R-5811 | Highway | STI (Prioritization) | NC 461 | NC 45 TO END OF STATE MAINTENANCE. MODERNIZE ROADWAY. | 4.05 | HERTFORD | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | Division 1 |  | T | CONSTRUCTION | 5252000
R-5812 | Highway | STI (Prioritization) | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 1.18 | GREENE | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 2 |  | T | ENGINEERING | 60000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
R-5812 | Highway | STI (Prioritization) | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 1.18 | GREENE | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 2 |  | T | ENGINEERING | 1230000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000
R-5812 | Highway | STI (Prioritization) | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 1.18 | GREENE | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 2 |  | T | BUILD NC CON | 4050000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000
R-5812 | Highway | STI (Prioritization) | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 1.18 | GREENE | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 2 |  | T | BUILD NC CON | 4455000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000 | 297000
R-5812 | Highway | STI (Prioritization) | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 1.18 | GREENE | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 2 |  | T | CONSTRUCTION | 640000
R-5812 | Highway | STI (Prioritization) | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | 1.18 | GREENE | 2 | Eastern Carolina RPO | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE). | Division 2 |  | L | CONSTRUCTION | 20000
R-5814 | Highway | STI (Prioritization) | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | 4.79 | LENOIR, GREENE | 2 | Eastern Carolina RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 11900000
R-5814 | Highway | STI (Prioritization) | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | 4.79 | LENOIR, GREENE | 2 | Eastern Carolina RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3400000
R-5814 | Highway | STI (Prioritization) | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | 4.79 | LENOIR, GREENE | 2 | Eastern Carolina RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 61700000
R-5816 | Highway | STI (Prioritization) | NC 58 (WEST FORT MACON) | ATLANTIC BEACH CAUSEWAY. ADD RIGHT TURN LANE. |  | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | T | RIGHT-OF-WAY | 600000
R-5816 | Highway | STI (Prioritization) | NC 58 (WEST FORT MACON) | ATLANTIC BEACH CAUSEWAY. ADD RIGHT TURN LANE. |  | CARTERET | 2 | Down East RPO | UNDER CONSTRUCTION. | Region B |  | T | CONSTRUCTION | 2170000
R-5819 | Highway | STI (Prioritization) | US 74/US 76 | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | 3 | COLUMBUS | 6 | Cape Fear RPO | COMBINE WITH R-5820. UNDER CONSTRUCTION. | Region C |  | T | RIGHT-OF-WAY | 346000
R-5819 | Highway | STI (Prioritization) | US 74/US 76 | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | 3 | COLUMBUS | 6 | Cape Fear RPO | COMBINE WITH R-5820. UNDER CONSTRUCTION. | Region C |  | T | UTILITIES | 129000
R-5819 | Highway | STI (Prioritization) | US 74/US 76 | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | 3 | COLUMBUS | 6 | Cape Fear RPO | COMBINE WITH R-5820. UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 11665000 | FY 2025: 1274000
R-5819A | Highway | STI (Prioritization) | US 74 / 76 | ADVANCED CONSTRUCTION OF TEMPORARY REDUCED CONFLICT INTERSECTIONS AT SR 1735 (CHAUNCEY TOWN ROAD) AND SR 1740 (OLD LAKE ROAD). | 0.5 | COLUMBUS | 6 | Cape Fear RPO | UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 2300000
R-5820 | Highway | STI (Prioritization) | US 74/US 76 | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | COLUMBUS | 6 | Cape Fear RPO | COMBINE WITH R-5819. UNDER CONSTRUCTION. | Region C |  | T | RIGHT-OF-WAY | 1184000 | FY 2025: 127000
R-5820 | Highway | STI (Prioritization) | US 74/US 76 | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | COLUMBUS | 6 | Cape Fear RPO | COMBINE WITH R-5819. UNDER CONSTRUCTION. | Region C |  | T | UTILITIES | 1297000
R-5820 | Highway | STI (Prioritization) | US 74/US 76 | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | COLUMBUS | 6 | Cape Fear RPO | COMBINE WITH R-5819. UNDER CONSTRUCTION. | Region C |  | T | CONSTRUCTION | 50713000 | FY 2025: 5538000; FY 2026: 5000000
R-5821 | Highway | STI (Prioritization) | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS, AND IMPROVE SR 1006 INTERSECTION. | 6.1 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO, Central Pines RPO
R-5821B | Highway | STI (Prioritization) | NC 54 | SR 1006 (ORANGE GROVE ROAD). INTERSECTION IMPROVEMENTS. | 0.5 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION | Division 7
R-5822 | Highway | STI (Prioritization) | NC 86 | US 158 TO SR 1500 (OLD NC HIGHWAY 86) 1.2 MILES SOUTH OF THE VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | 7.7 | CASWELL | 7 | Piedmont Triad RPO | SCOPE INCLUDES SPOT ID H170625 | Region D |  | BGLT5 | RIGHT-OF-WAY | 440000 | FY 2025: 440000
R-5822 | Highway | STI (Prioritization) | NC 86 | US 158 TO SR 1500 (OLD NC HIGHWAY 86) 1.2 MILES SOUTH OF THE VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | 7.7 | CASWELL | 7 | Piedmont Triad RPO | SCOPE INCLUDES SPOT ID H170625 | Region D |  | BGLT5 | UTILITIES | 1300000 | FY 2025: 1300000
R-5822 | Highway | STI (Prioritization) | NC 86 | US 158 TO SR 1500 (OLD NC HIGHWAY 86) 1.2 MILES SOUTH OF THE VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | 7.7 | CASWELL | 7 | Piedmont Triad RPO | SCOPE INCLUDES SPOT ID H170625 | Region D |  | BGLT5 | CONSTRUCTION | 26600000 | FY 2026: 10491000; FY 2027: 11986000; FY 2028: 4123000
R-5823 | Highway | STI (Prioritization) | NC 65 / NC 68 | US 158 IN STOKESDALE IN GUILFORD COUNTY TO I-73 / US 220 IN ROCKINGHAM COUNTY. MULTIPLE INTERSECTION IMPROVEMENTS ALONG CORRIDOR. | 3.61 | ROCKINGHAM, GUILFORD | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | Division 7 |  | BGLT5 | RIGHT-OF-WAY | 10500000 | FY 2030: 800000; FY 2031: 4800000; FY 2032: 2800000; FY 2033: 1050000; FY 2034: 1050000
R-5823 | Highway | STI (Prioritization) | NC 65 / NC 68 | US 158 IN STOKESDALE IN GUILFORD COUNTY TO I-73 / US 220 IN ROCKINGHAM COUNTY. MULTIPLE INTERSECTION IMPROVEMENTS ALONG CORRIDOR. | 3.61 | ROCKINGHAM, GUILFORD | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | Division 7 |  | BGLT5 | UTILITIES | 424000 | FY 2030: 424000
R-5823 | Highway | STI (Prioritization) | NC 65 / NC 68 | US 158 IN STOKESDALE IN GUILFORD COUNTY TO I-73 / US 220 IN ROCKINGHAM COUNTY. MULTIPLE INTERSECTION IMPROVEMENTS ALONG CORRIDOR. | 3.61 | ROCKINGHAM, GUILFORD | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | Division 7 |  | BGLT5 | CONSTRUCTION | 29200000 | FY 2032: 5442000; FY 2033: 14108000; FY 2034: 7076000; FY 2035: 2574000
R-5824 | Highway | STI (Prioritization) | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | 11.75 | MOORE | 8 | Central Pines RPO |  | Region E |  | BGLT5 | RIGHT-OF-WAY | 1800000 | FY 2025: 1505000; FY 2026: 295000
R-5824 | Highway | STI (Prioritization) | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | 11.75 | MOORE | 8 | Central Pines RPO |  | Region E |  | BGLT5 | UTILITIES | 900000 | FY 2026: 450000; FY 2027: 450000
R-5824 | Highway | STI (Prioritization) | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | 11.75 | MOORE | 8 | Central Pines RPO |  | Region E |  | BGLT5 | CONSTRUCTION | 12000000 | FY 2030: 4320000; FY 2031: 5640000; FY 2032: 2040000
R-5825 | Highway | STI (Prioritization) | NC 751 | SR 1731 (O'KELLY CHAPEL ROAD). UPGRADE AND REALIGN INTERSECTION. | 0.5 | CHATHAM | 8 | Durham-Chapel Hill-Carrboro MPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 1264000 | FY 2025: 13000
R-5826 | Highway | STI (Prioritization) | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO NC 24 / NC 27. UPGRADE ROADWAY, INCLUDING PAVED SHOULDERS, TURN LANES AND SIGNALS. | 8 | MONTGOMERY | 8 | Piedmont Triad RPO
R-5826A | Highway | STI (Prioritization) | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). |  | MONTGOMERY | 8 | Piedmont Triad RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3700000 | [11 empty] | 3700000
R-5826A | Highway | STI (Prioritization) | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). |  | MONTGOMERY | 8 | Piedmont Triad RPO |  | Not Funded |  | T | UTILITIES | 250000 | [11 empty] | 250000
R-5826A | Highway | STI (Prioritization) | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). |  | MONTGOMERY | 8 | Piedmont Triad RPO |  | Not Funded |  | T | CONSTRUCTION | 9200000 | [11 empty] | 9200000
R-5826B | Highway | STI (Prioritization) | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | 2.61 | MONTGOMERY | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | RIGHT-OF-WAY | 438000
R-5826B | Highway | STI (Prioritization) | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | 2.61 | MONTGOMERY | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | UTILITIES | 240000
R-5826B | Highway | STI (Prioritization) | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | 2.61 | MONTGOMERY | 8 | Piedmont Triad RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | BGLT5 | CONSTRUCTION | 13200000 | FY 2026: 4918000; FY 2027: 6288000; FY 2028: 1994000
R-5826C | Highway | STI (Prioritization) | NC 109 | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. |  | MONTGOMERY | 8 | Piedmont Triad RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 3000000 | [11 empty] | 3000000
R-5826C | Highway | STI (Prioritization) | NC 109 | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. |  | MONTGOMERY | 8 | Piedmont Triad RPO |  | Not Funded |  | T | UTILITIES | 299000 | [11 empty] | 299000
R-5826C | Highway | STI (Prioritization) | NC 109 | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. |  | MONTGOMERY | 8 | Piedmont Triad RPO |  | Not Funded |  | T | CONSTRUCTION | 18000000 | [11 empty] | 18000000
R-5828 | Highway | STI (Prioritization) | US 311 (NORTH MAIN STREET) | SR 1918 (FIRST STREET) IN WALNUT COVE. CONSTRUCT ROUNDABOUT. |  | STOKES | 9 | Northwest Piedmont RPO | UNDER CONSTRUCTION | Division 9 |  | T | CONSTRUCTION | 3050000
R-5830 | Highway | STI (Prioritization) | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 0.87 | WATAUGA | 11 | High Country RPO | BUILD NC BOND FUNDING: $8,500,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | RIGHT-OF-WAY | 3900000 | FY 2025: 112000; FY 2026: 1337000; FY 2027: 1337000; FY 2028: 334000; FY 2029: 780000
R-5830 | Highway | STI (Prioritization) | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 0.87 | WATAUGA | 11 | High Country RPO | BUILD NC BOND FUNDING: $8,500,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | UTILITIES | 560000 | FY 2025: 560000
R-5830 | Highway | STI (Prioritization) | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 0.87 | WATAUGA | 11 | High Country RPO | BUILD NC BOND FUNDING: $8,500,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | BUILD NC CON | 12960000 |  |  |  | 864000 | 864000 | 864000 | 864000 | 864000 | 864000 | 864000 | 864000 | 6048000
R-5830 | Highway | STI (Prioritization) | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | 0.87 | WATAUGA | 11 | High Country RPO | BUILD NC BOND FUNDING: $8,500,000 FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | CONSTRUCTION | 14700000 | FY 2028: 0; FY 2029: 7428000; FY 2030: 6440000; FY 2031: 832000
R-5831 | Highway | STI (Prioritization) | AVENUE) US 601 (CAROLINA | NC 67 (MAIN STREET) INTERSECTION. UPGRADE INTERSECTION. | 0.5 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | UTILITIES | 650000
R-5831 | Highway | STI (Prioritization) | AVENUE) US 601 (CAROLINA | NC 67 (MAIN STREET) INTERSECTION. UPGRADE INTERSECTION. | 0.5 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 11 |  | T | CONSTRUCTION | 3900000 | FY 2025: 2035000; FY 2026: 1865000
R-5832 | Highway | STI (Prioritization) | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | 3.76 | ASHE | 11 | High Country RPO |  | Division 11 |  | BGLT5 | RIGHT-OF-WAY | 12801000 | FY 2025: 1241000; FY 2026: 3724000; FY 2027: 3724000; FY 2028: 1552000; FY 2029: 2560000
R-5832 | Highway | STI (Prioritization) | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | 3.76 | ASHE | 11 | High Country RPO |  | Division 11 |  | BGLT5 | UTILITIES | 4600000 | FY 2025: 2300000; FY 2026: 2300000
R-5832 | Highway | STI (Prioritization) | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | 3.76 | ASHE | 11 | High Country RPO |  | Division 11 |  | BGLT5 | CONSTRUCTION | 32701000 | FY 2028: 7881000; FY 2029: 12309000; FY 2030: 8750000; FY 2031: 3761000
R-5836 | Highway | STI (Prioritization) | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 7.19 | SURRY | 11 | Northwest Piedmont RPO | NC BUILD BOND FUNDING: $35.5M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | BGLT5 | RIGHT-OF-WAY | 3100000 | FY 2026: 354000; FY 2027: 1417000; FY 2028: 709000; FY 2029: 310000; FY 2030: 310000
R-5836 | Highway | STI (Prioritization) | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 7.19 | SURRY | 11 | Northwest Piedmont RPO | NC BUILD BOND FUNDING: $35.5M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | BGLT5 | UTILITIES | 1700000 | FY 2026: 850000; FY 2027: 850000
R-5836 | Highway | STI (Prioritization) | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 7.19 | SURRY | 11 | Northwest Piedmont RPO | NC BUILD BOND FUNDING: $35.5M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | BUILD NC CON | 54135000 |  |  |  | 3609000 | 3609000 | 3609000 | 3609000 | 3609000 | 3609000 | 3609000 | 3609000 | 25263000
R-5836 | Highway | STI (Prioritization) | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | 7.19 | SURRY | 11 | Northwest Piedmont RPO | NC BUILD BOND FUNDING: $35.5M FOR CONSTRUCTION PAYBACK 2028 - 2042 (FY 2028 / YR 8 SALE). | Division 11 |  | T | CONSTRUCTION | 127700000 | FY 2028: 0; FY 2029: 32020000; FY 2030: 30912000; FY 2031: 32384000; FY 2032: 32384000
R-5839 | Highway | STI (Prioritization) | NC 28 (FONTANA ROAD) | US 129 TO NC 143. UPGRADE ROADWAY. | 20.4 | GRAHAM, SWAIN | 14 | Southwestern RPO
R-5839A | Highway | STI (Prioritization) | NC 28 | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. |  | SWAIN | 14 | Southwestern RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 1520000 | [11 empty] | 1520000
R-5839A | Highway | STI (Prioritization) | NC 28 | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. |  | SWAIN | 14 | Southwestern RPO |  | Not Funded |  | T | UTILITIES | 200000 | [11 empty] | 200000
R-5839A | Highway | STI (Prioritization) | NC 28 | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. |  | SWAIN | 14 | Southwestern RPO |  | Not Funded |  | T | CONSTRUCTION | 312700000 | [11 empty] | 312700000
R-5839BA | Highway | STI (Prioritization) | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | 1.14 | GRAHAM | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 100000
R-5839BA | Highway | STI (Prioritization) | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | 1.14 | GRAHAM | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 200000
R-5839BA | Highway | STI (Prioritization) | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | 1.14 | GRAHAM | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 17801000
R-5839BB | Highway | STI (Prioritization) | NC 28 | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 46332000 | [11 empty] | 46332000
R-5839BB | Highway | STI (Prioritization) | NC 28 | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | UTILITIES | 80000 | [11 empty] | 80000
R-5839BB | Highway | STI (Prioritization) | NC 28 | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | CONSTRUCTION | 37000000 | [11 empty] | 37000000
R-5839C | Highway | STI (Prioritization) | NC 28 | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 90000 | [11 empty] | 90000
R-5839C | Highway | STI (Prioritization) | NC 28 | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | UTILITIES | 20000 | [11 empty] | 20000
R-5839C | Highway | STI (Prioritization) | NC 28 | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | CONSTRUCTION | 58300000 | [11 empty] | 58300000
R-5839D | Highway | STI (Prioritization) | NC 28 | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 730000 | [11 empty] | 730000
R-5839D | Highway | STI (Prioritization) | NC 28 | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | UTILITIES | 80000 | [11 empty] | 80000
R-5839D | Highway | STI (Prioritization) | NC 28 | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | CONSTRUCTION | 57500000 | [11 empty] | 57500000
R-5839E | Highway | STI (Prioritization) | NC 28 | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | RIGHT-OF-WAY | 60000 | [11 empty] | 60000
R-5839E | Highway | STI (Prioritization) | NC 28 | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | UTILITIES | 100000 | [11 empty] | 100000
R-5839E | Highway | STI (Prioritization) | NC 28 | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. |  | GRAHAM | 14 | Southwestern RPO |  | Not Funded |  | T | CONSTRUCTION | 22000000 | [11 empty] | 22000000
R-5840 | Highway | STI (Prioritization) | NC 9 | US 74 TO NC 108. CONSTRUCT PAVED SHOULDERS. | 3.07 | POLK | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | T | RIGHT-OF-WAY | 2200000
R-5840 | Highway | STI (Prioritization) | NC 9 | US 74 TO NC 108. CONSTRUCT PAVED SHOULDERS. | 3.07 | POLK | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | T | UTILITIES | 1300000
R-5840 | Highway | STI (Prioritization) | NC 9 | US 74 TO NC 108. CONSTRUCT PAVED SHOULDERS. | 3.07 | POLK | 14 | Foothills RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | T | CONSTRUCTION | 13799000 | FY 2029: 5419000; FY 2030: 5930000; FY 2031: 2450000
R-5843 | Highway | STI (Prioritization) | SR 1321 (BRYSON WALK), SR 1336 (DEPOT STREET) | SR 1323 (SLOPE STREET) TO SR 1336 (DEEP CREEK ROAD). IMPROVE INTERSECTIONS. | 0.73 | SWAIN | 14 | Southwestern RPO | UNDER CONSTRUCTION. | Division 14 |  | T | CONSTRUCTION | 3629000
R-5849 | Highway | Pre-STI (Historic) | NEW ROUTE | CONSTRUCT IMPROVEMENTS TO SR 1313 (WASHBURN SWITCH ROAD) AND A NEW 3-LANE ROAD OFF SR 1313 (WASHBURN SWITCH ROAD) FOR ACCESS TO NEW INDUSTRIAL SITES. |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | UNDER CONSTRUCTION | Division 12
R-5853 | Highway | STI (Prioritization) | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | 3.64 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | BGANY | RIGHT-OF-WAY | 3500000 | FY 2025: 420000; FY 2026: 1680000; FY 2027: 700000; FY 2028: 350000; FY 2029: 350000
R-5853 | Highway | STI (Prioritization) | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | 3.64 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | BGANY | UTILITIES | 1900000 | FY 2025: 950000; FY 2026: 950000
R-5853 | Highway | STI (Prioritization) | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | 3.64 | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | BGANY | CONSTRUCTION | 8799000 | FY 2027: 3311000; FY 2028: 4343000; FY 2029: 1145000
R-5854 | Highway | STI (Prioritization) | SR 1410 (FARMINGTON ROAD) | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | 1 | DAVIE | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | RIGHT-OF-WAY | 100000
R-5854 | Highway | STI (Prioritization) | SR 1410 (FARMINGTON ROAD) | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | 1 | DAVIE | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | UTILITIES | 200000
R-5854 | Highway | STI (Prioritization) | SR 1410 (FARMINGTON ROAD) | SR 1410 FARMINGTON ROAD AT US 158 INTERSECTION IN DAVIE COUNTY. CONSTRUCT ROUNDABOUT. | 1 | DAVIE | 9 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS | Division 9 |  | T | CONSTRUCTION | 1500000 | FY 2025: 1500000
R-5857 | Highway | STI (Prioritization) | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 1 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 770000
R-5857 | Highway | STI (Prioritization) | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 1 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | UTILITIES | 325000
R-5857 | Highway | STI (Prioritization) | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO REDUCED CONFLICT INTERSECTIONS. | 1 | BRUNSWICK | 3 | Grand Strand Area Transportation Study | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | CONSTRUCTION | 26199000 | FY 2026: 10730000; FY 2027: 10092000; FY 2028: 5377000
R-5858 | Highway | STI (Prioritization) | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | 1 | CARTERET | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | RIGHT-OF-WAY | 750000
R-5858 | Highway | STI (Prioritization) | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | 1 | CARTERET | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | T | UTILITIES | 125000
R-5858 | Highway | STI (Prioritization) | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | 1 | CARTERET | 2 | Down East RPO | RIGHT-OF-WAY IN PROGRESS. | Statewide Mobility |  | NHP | CONSTRUCTION | 8400000 | FY 2026: 1349000; FY 2027: 5393000; FY 2028: 1658000
R-5860 | Highway | STI (Prioritization) | US 52 | PROPOSED MISENHEIMER BYPASS TO GRANITE QUARRY BYPASS.WIDEN TO 3-LANE ROADWAY. | 4.54 | ROWAN, CABARRUS | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10
R-5860A | Highway | STI (Prioritization) | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. WIDEN TO 3-LANE ROADWAY. | 4.54 | ROWAN, CABARRUS | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 24400000
R-5860A | Highway | STI (Prioritization) | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. WIDEN TO 3-LANE ROADWAY. | 4.54 | ROWAN, CABARRUS | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 4900000
R-5860A | Highway | STI (Prioritization) | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. WIDEN TO 3-LANE ROADWAY. | 4.54 | ROWAN, CABARRUS | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 50500000
R-5860B | Highway | STI (Prioritization) | US 52 | PROPOSED ROCKWELL BYPASS. CONSTRUCT 3-LANE FACILITY ON NEW LOCATION. | 3.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 8200000 | [11 empty] | 8200000
R-5860B | Highway | STI (Prioritization) | US 52 | PROPOSED ROCKWELL BYPASS. CONSTRUCT 3-LANE FACILITY ON NEW LOCATION. | 3.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | UTILITIES | 500000 | [11 empty] | 500000
R-5860B | Highway | STI (Prioritization) | US 52 | PROPOSED ROCKWELL BYPASS. CONSTRUCT 3-LANE FACILITY ON NEW LOCATION. | 3.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | CONSTRUCTION | 22300000 | [11 empty] | 22300000
R-5860C | Highway | STI (Prioritization) | US 52 | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT 3-LANE FACILITY ON NEW LOCATION. | 4.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 5500000 | [11 empty] | 5500000
R-5860C | Highway | STI (Prioritization) | US 52 | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT 3-LANE FACILITY ON NEW LOCATION. | 4.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | UTILITIES | 900000 | [11 empty] | 900000
R-5860C | Highway | STI (Prioritization) | US 52 | PROPOSED GRANITE QUARRY BYPASS. CONSTRUCT 3-LANE FACILITY ON NEW LOCATION. | 4.63 | ROWAN | 9 | Cabarrus-Rowan MPO |  | Not Funded |  | NHP | CONSTRUCTION | 36500000 | [11 empty] | 36500000
R-5861 | Highway | STI (Prioritization) | US 19/129 | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | 3.8 | CHEROKEE | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | T | RIGHT-OF-WAY | 11400000
R-5861 | Highway | STI (Prioritization) | US 19/129 | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | 3.8 | CHEROKEE | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | T | UTILITIES | 1850000
R-5861 | Highway | STI (Prioritization) | US 19/129 | GEORGIA STATE LINE TO US 64. MODERNIZE ROADWAY TO INCLUDE ADDITIONAL PAVED SHOULDERS AND REALIGNMENT TO IMPROVE ROADWAY GEOMETRY. | 3.8 | CHEROKEE | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | BGLT5 | CONSTRUCTION | 77933000 | FY 2025: 20021000; FY 2026: 15616000; FY 2027: 10945000; FY 2028: 2616000
R-5863 | Highway | STI (Prioritization) | US 64 BUSINESS | US 64 TO SR 1307 (MAIN STREET). UPGRADE ROADWAY. | 1.19 | CLAY | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | T | RIGHT-OF-WAY | 4200000
R-5863 | Highway | STI (Prioritization) | US 64 BUSINESS | US 64 TO SR 1307 (MAIN STREET). UPGRADE ROADWAY. | 1.19 | CLAY | 14 | Southwestern RPO | RIGHT-OF-WAY IN PROGRESS. | Division 14 |  | T | CONSTRUCTION | 13900000 | FY 2026: 4726000; FY 2027: 6255000; FY 2028: 2919000
R-5863A | Highway | STI (Prioritization) | US 64 | US 64 BUSINESS INTERSECTION (WESTERN) IN HAYESVILLE. INSTALL TRAFFIC SIGNAL. |  | CLAY | 14 | Southwestern RPO |  | Division 14 |  | T | CONSTRUCTION | 330000 | FY 2025: 330000
R-5865 | Highway | Federal Lands Access Program | US 276 | US 64 TO AVERY CREEK TRAIL HEAD. WIDEN TO 3-LANES WITH BICYCLE LANES. NC FLAP DOT 276(1). | 2.2 | TRANSYLVANIA | 14 | Land-of-Sky RPO | HF(M) FROM DIVISION 14 MAINTENANCE FUNDING; FLAP PROJECTS NC 35 AND NC 63. | Exempt |  | FLAP | ENGINEERING | 2520000
R-5865 | Highway | Federal Lands Access Program | US 276 | US 64 TO AVERY CREEK TRAIL HEAD. WIDEN TO 3-LANES WITH BICYCLE LANES. NC FLAP DOT 276(1). | 2.2 | TRANSYLVANIA | 14 | Land-of-Sky RPO | HF(M) FROM DIVISION 14 MAINTENANCE FUNDING; FLAP PROJECTS NC 35 AND NC 63. | Exempt |  | HF(M) | ENGINEERING | 630000
R-5866 | Highway | Economic Development | NC 87 | IMPROVE ROADWAY FOR SMITHFIELD FOODS PROCESSING CENTER. | 1.2 | BLADEN | 6 | Mid-Carolina RPO | COMPLETED. THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR SMITHFIELD FOODS PROCESSING. | Region C |  | T | CONSTRUCTION | 1042000
R-5868 | Highway | Economic Development | NEW ROUTE | SR 1252 (DUNBAR ROAD) TO SR 1225 (KINGSBORO ROAD). CONSTRUCT TWO LANE ROAD ON NEW LOCATION AND IMPROVEMENTS TO SR 1225 TO SERVE KINGSBORO MEGASITE. | 2.5 | EDGECOMBE | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. THIS IN AN ECONOMIC DEVELOPMENT PROJECT FOR TRIANGLE TYRE. | Division 4
R-5869 | Highway | STI (Prioritization) | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY AND CONVERT INTERSECTIONS TO INTERCHANGES. | 6 | PERQUIMANS | 1 | Albemarle RPO
R-5869A | Highway | STI (Prioritization) | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 29300000
R-5869A | Highway | STI (Prioritization) | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 2600000
R-5869A | Highway | STI (Prioritization) | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WYNNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | 1 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 58074000
R-5869B | Highway | STI (Prioritization) | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 5301000
R-5869B | Highway | STI (Prioritization) | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 880000
R-5869B | Highway | STI (Prioritization) | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 53900000
R-5869C | Highway | STI (Prioritization) | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. |  | PERQUIMANS | 1 | Albemarle RPO | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | RIGHT-OF-WAY | 3500000 | [11 empty] | 3500000
R-5869C | Highway | STI (Prioritization) | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. |  | PERQUIMANS | 1 | Albemarle RPO | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | UTILITIES | 1000000 | [11 empty] | 1000000
R-5869C | Highway | STI (Prioritization) | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. |  | PERQUIMANS | 1 | Albemarle RPO | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY. | Not Funded |  | NHP | CONSTRUCTION | 135000000 | [11 empty] | 135000000
R-5870 | Highway | Appalachian Development Highway System | ALEXANDER COUNTY | CONSTRUCT ACCESS ROAD INTO ALEXANDER INDUSTRIAL PARK. | 0.49 | ALEXANDER | 12 | Greater Hickory MPO | COMPLETE - ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING. | Exempt |  | ADHSL | CONSTRUCTION | 1175000
R-5870 | Highway | Appalachian Development Highway System | ALEXANDER COUNTY | CONSTRUCT ACCESS ROAD INTO ALEXANDER INDUSTRIAL PARK. | 0.49 | ALEXANDER | 12 | Greater Hickory MPO | COMPLETE - ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING. | Exempt |  | T | CONSTRUCTION | 500000
R-5878 | Highway | STI (Prioritization) | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 11.3 | ANSON | 10 | Rocky River RPO
R-5878A | Highway | STI (Prioritization) | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. |  | ANSON | 10 | Rocky River RPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 4000000 | [11 empty] | 4000000
R-5878A | Highway | STI (Prioritization) | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. |  | ANSON | 10 | Rocky River RPO |  | Not Funded |  | NHP | UTILITIES | 600000 | [11 empty] | 600000
R-5878A | Highway | STI (Prioritization) | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. |  | ANSON | 10 | Rocky River RPO |  | Not Funded |  | NHP | CONSTRUCTION | 104300000 | [11 empty] | 81052000
R-5878B | Highway | STI (Prioritization) | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 6.44 | ANSON | 10 | Rocky River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 31100000
R-5878B | Highway | STI (Prioritization) | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 6.44 | ANSON | 10 | Rocky River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3200000
R-5878B | Highway | STI (Prioritization) | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | 6.44 | ANSON | 10 | Rocky River RPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 315700000
R-5879 | Highway | STI (Prioritization) | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | 0.5 | MARTIN | 1 | Mid-East RPO |  | Region A |  | NHP | RIGHT-OF-WAY | 140000 | FY 2028: 140000
R-5879 | Highway | STI (Prioritization) | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | 0.5 | MARTIN | 1 | Mid-East RPO |  | Region A |  | NHP | UTILITIES | 970000 | FY 2028: 970000
R-5879 | Highway | STI (Prioritization) | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | 0.5 | MARTIN | 1 | Mid-East RPO |  | Region A |  | NHP | CONSTRUCTION | 5000000 | FY 2031: 5000000
R-5881 | Highway | STI (Prioritization) | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION. | 0.5 | JACKSON | 14 | Southwestern RPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 14900000
R-5881 | Highway | STI (Prioritization) | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION. | 0.5 | JACKSON | 14 | Southwestern RPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 2100000
R-5881 | Highway | STI (Prioritization) | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION. | 0.5 | JACKSON | 14 | Southwestern RPO |  | Region G | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4300000
R-5885 | Highway | STI (Prioritization) | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.91 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 61900000 | [11 empty] | 61900000
R-5885 | Highway | STI (Prioritization) | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.91 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | UTILITIES | 5200000 | [11 empty] | 5200000
R-5885 | Highway | STI (Prioritization) | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT REDUCED CONFLICT INTERSECTIONS. | 2.91 | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Not Funded |  | NHP | CONSTRUCTION | 47400000 | [11 empty] | 47400000
R-5885A | Highway | STI (Prioritization) | NC 24 (WEST CORBETT AVENUE) | REPLACE CULVERT EAST OF WEST SHORE DRIVE. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | NHP | RIGHT-OF-WAY | 115000 | FY 2025: 115000
R-5885A | Highway | STI (Prioritization) | NC 24 (WEST CORBETT AVENUE) | REPLACE CULVERT EAST OF WEST SHORE DRIVE. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | NHP | UTILITIES | 84000 | FY 2025: 84000
R-5885A | Highway | STI (Prioritization) | NC 24 (WEST CORBETT AVENUE) | REPLACE CULVERT EAST OF WEST SHORE DRIVE. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Region B |  | NHP | CONSTRUCTION | 1500000 | FY 2027: 486000; FY 2028: 1014000
R-5887 | Highway | STI (Prioritization) | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CHATHAM | 8 | Central Pines RPO |  | Region E |  | NHP | RIGHT-OF-WAY | 6400000 | FY 2030: 1327000; FY 2031: 1517000; FY 2032: 2276000; FY 2033: 640000; FY 2034: 640000
R-5887 | Highway | STI (Prioritization) | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CHATHAM | 8 | Central Pines RPO |  | Region E |  | NHP | UTILITIES | 3000000 | FY 2030: 1500000; FY 2031: 1500000
R-5887 | Highway | STI (Prioritization) | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | CHATHAM | 8 | Central Pines RPO |  | Region E |  | NHP | CONSTRUCTION | 62300000 | FY 2032: 8099000; FY 2033: 23051000; FY 2034: 18067000; FY 2035: 13083000
R-5888 | Highway | STI (Prioritization) | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | 1.85 | ROBESON | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 900000
R-5888 | Highway | STI (Prioritization) | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | 1.85 | ROBESON | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 300000
R-5888 | Highway | STI (Prioritization) | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | 1.85 | ROBESON | 6 | Lumber River RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5800000
R-5889 | Highway | STI (Prioritization) | US 29 (FUTURE I-785) | NORTH OF I-785 IN GREENSBORO TO US 158 / NC 14 IN REIDSVILLE. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 15.59 | ROCKINGHAM, GUILFORD | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | Region D
R-5889A | Highway | STI (Prioritization) | US 29 (FUTURE I-785) | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 4.48 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D |  | T | RIGHT-OF-WAY | 17066000 | FY 2027: 4267000; FY 2028: 8532000; FY 2029: 4267000
R-5889A | Highway | STI (Prioritization) | US 29 (FUTURE I-785) | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 4.48 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D |  | T | UTILITIES | 1876000 | FY 2027: 938000; FY 2028: 938000
R-5889A | Highway | STI (Prioritization) | US 29 (FUTURE I-785) | NORTH OF I-785 TO NC 150. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | 4.48 | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D |  | T | CONSTRUCTION | 69701000 | FY 2030: 10569000; FY 2031: 27391000; FY 2032: 17356000; FY 2033: 9260000; FY 2034: 5125000
R-5889B | Highway | STI (Prioritization) | US 29 (FUTURE I-785) | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE TO INTERSTATE STANDARDS. | 11.12 | ROCKINGHAM, GUILFORD | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | Not Funded |  | T | RIGHT-OF-WAY | 9364000 | [11 empty] | 9364000
R-5889B | Highway | STI (Prioritization) | US 29 (FUTURE I-785) | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE TO INTERSTATE STANDARDS. | 11.12 | ROCKINGHAM, GUILFORD | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | Not Funded |  | T | UTILITIES | 5430000 | [11 empty] | 5430000
R-5889B | Highway | STI (Prioritization) | US 29 (FUTURE I-785) | NC 150 TO US 158 / NC 14 IN REIDSVILLE. UPGRADE TO INTERSTATE STANDARDS. | 11.12 | ROCKINGHAM, GUILFORD | 7 | Piedmont Triad RPO, Greensboro Urban Area MPO |  | Not Funded |  | T | CONSTRUCTION | 116450000 | [11 empty] | 116450000
R-5891 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | MOORE | 8 | Sandhills MPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | RIGHT-OF-WAY | 3700000
R-5891 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | MOORE | 8 | Sandhills MPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | UTILITIES | 1100000
R-5891 | Highway | STI (Prioritization) | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | 1 | MOORE | 8 | Sandhills MPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BG50200 | CONSTRUCTION | 39400000
R-5892 | Highway | STI (Prioritization) | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | 2.76 | MOORE | 8 | Sandhills MPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 8200000
R-5892 | Highway | STI (Prioritization) | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | 2.76 | MOORE | 8 | Sandhills MPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1892000
R-5892 | Highway | STI (Prioritization) | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | 2.76 | MOORE | 8 | Sandhills MPO |  | Region E | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 43200000
R-5893 | Highway | STI (Prioritization) | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO FOUR LANES. | 2.28 | FRANKLIN | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 6000000
R-5893 | Highway | STI (Prioritization) | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO FOUR LANES. | 2.28 | FRANKLIN | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 3200000
R-5893 | Highway | STI (Prioritization) | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO FOUR LANES. | 2.28 | FRANKLIN | 5 | Kerr-Tar RPO |  | Region C | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 36300000
R-5899 | Highway | STI (Prioritization) | NC 210 | SR 1560 (WATTS LANDING ROAD). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO |  | Division 3 |  | BGANY | RIGHT-OF-WAY | 1200000 | FY 2025: 332000; FY 2026: 443000; FY 2027: 185000; FY 2028: 120000; FY 2029: 120000
R-5899 | Highway | STI (Prioritization) | NC 210 | SR 1560 (WATTS LANDING ROAD). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO |  | Division 3 |  | BGANY | UTILITIES | 210000 | FY 2025: 210000
R-5899 | Highway | STI (Prioritization) | NC 210 | SR 1560 (WATTS LANDING ROAD). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO |  | Division 3 |  | BGANY | CONSTRUCTION | 5600000 | FY 2027: 2744000; FY 2028: 2856000
R-5900 | Highway | STI (Prioritization) | NC 50/NC 210 | SR 1534 (BELT ROAD). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO | BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 3 |  | T | RIGHT-OF-WAY | 4600000 | FY 2025: 1557000; FY 2026: 1698000; FY 2027: 425000; FY 2028: 460000; FY 2029: 460000
R-5900 | Highway | STI (Prioritization) | NC 50/NC 210 | SR 1534 (BELT ROAD). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO | BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 3 |  | T | UTILITIES | 310000 | FY 2025: 310000
R-5900 | Highway | STI (Prioritization) | NC 50/NC 210 | SR 1534 (BELT ROAD). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO | BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 3 |  | T | BUILD NC CON | 12195000 |  |  |  | 813000 | 813000 | 813000 | 813000 | 813000 | 813000 | 813000 | 813000 | 5691000
R-5900 | Highway | STI (Prioritization) | NC 50/NC 210 | SR 1534 (BELT ROAD). IMPROVE INTERSECTION. | 0.5 | PENDER | 3 | Cape Fear RPO | BUILD NC BOND FUNDING: $8,000,000 FOR CONSTRUCTION PAYBACK 2028-2042 (FY 2028 / YR 8 SALE). | Division 3 |  | T | CONSTRUCTION | 11500000 | FY 2028: 0; FY 2029: 6820000; FY 2030: 4680000
R-5901 | Highway | STI (Prioritization) | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | 0.5 | SURRY | 11 | Northwest Piedmont RPO |  | Region F |  | BGLT5 | RIGHT-OF-WAY | 370000
R-5901 | Highway | STI (Prioritization) | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | 0.5 | SURRY | 11 | Northwest Piedmont RPO |  | Region F |  | BGLT5 | UTILITIES | 410000
R-5901 | Highway | STI (Prioritization) | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | 0.5 | SURRY | 11 | Northwest Piedmont RPO |  | Region F |  | BGLT5 | CONSTRUCTION | 7701000 | FY 2025: 2234000; FY 2026: 4235000; FY 2027: 1232000
R-5905 | Highway | STI (Prioritization) | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | 3.81 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGLT5 | RIGHT-OF-WAY | 19400000 | FY 2026: 3394000; FY 2027: 5821000; FY 2028: 5821000; FY 2029: 483000; FY 2030: 3881000
R-5905 | Highway | STI (Prioritization) | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | 3.81 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGLT5 | UTILITIES | 28399000 | FY 2026: 9466000; FY 2027: 9466000; FY 2028: 9467000
R-5905 | Highway | STI (Prioritization) | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | 3.81 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGLT5 | CONSTRUCTION | 53401000 | FY 2029: 16666000; FY 2030: 18805000; FY 2031: 13074000; FY 2032: 4856000
R-5906 | Highway | STI (Prioritization) | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | 13.52 | WILKES | 11 | High Country RPO |  | Division 11 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 60200000
R-5906 | Highway | STI (Prioritization) | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | 13.52 | WILKES | 11 | High Country RPO |  | Division 11 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 8200000
R-5906 | Highway | STI (Prioritization) | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | 13.52 | WILKES | 11 | High Country RPO |  | Division 11 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 118900000
R-5907 | Highway | STI (Prioritization) | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | 2.81 | JACKSON | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | RIGHT-OF-WAY | 3500000
R-5907 | Highway | STI (Prioritization) | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | 2.81 | JACKSON | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | UTILITIES | 200000
R-5907 | Highway | STI (Prioritization) | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | 2.81 | JACKSON | 14 | Southwestern RPO |  | Division 14 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGLT5 | CONSTRUCTION | 35000000
R-5909 | Highway | STI (Prioritization) | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 1.19 | YADKIN | 11 | Northwest Piedmont RPO | NC BUILD BONDS: $4M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 11 |  | T | RIGHT-OF-WAY | 1901000 | FY 2027: 415000; FY 2028: 553000; FY 2029: 553000; FY 2030: 190000; FY 2031: 190000
R-5909 | Highway | STI (Prioritization) | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 1.19 | YADKIN | 11 | Northwest Piedmont RPO | NC BUILD BONDS: $4M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 11 |  | T | UTILITIES | 2300000 | FY 2027: 1150000; FY 2028: 1150000
R-5909 | Highway | STI (Prioritization) | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 1.19 | YADKIN | 11 | Northwest Piedmont RPO | NC BUILD BONDS: $4M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 11 |  | T | BUILD NC CON | 6105000 | FY 2030: 407000; FY 2031: 407000; FY 2032: 407000; FY 2033: 407000; FY 2034: 407000; FY 2035: 407000 | 3663000
R-5909 | Highway | STI (Prioritization) | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | 1.19 | YADKIN | 11 | Northwest Piedmont RPO | NC BUILD BONDS: $4M ON CONSTRUCTION PAYBACK 2030-2044 (SALE 10 / FY 2030). | Division 11 |  | T | CONSTRUCTION | 7000000 | FY 2030: 110000; FY 2031: 4137000; FY 2032: 2753000
R-5910 | Highway | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Division 11 |  | BGLT5 | RIGHT-OF-WAY | 900000
R-5910 | Highway | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Division 11 |  | BGLT5 | UTILITIES | 400000
R-5910 | Highway | STI (Prioritization) | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | 0.5 | SURRY | 11 | Northwest Piedmont RPO | UNDER CONSTRUCTION. | Division 11 |  | BGLT5 | CONSTRUCTION | 1700000
R-5911 | Highway | STI (Prioritization) | US 19E | NC 194 INTERSECTION. CONSTRUCT RIGHT TURN LANE FROM US 19E NORTHBOUND TO NC 194 EASTBOUND. | 0.5 | AVERY | 11 | High Country RPO | UNDER CONSTRUCTION. | Division 11 |  | BGLT5 | RIGHT-OF-WAY | 200000
R-5911 | Highway | STI (Prioritization) | US 19E | NC 194 INTERSECTION. CONSTRUCT RIGHT TURN LANE FROM US 19E NORTHBOUND TO NC 194 EASTBOUND. | 0.5 | AVERY | 11 | High Country RPO | UNDER CONSTRUCTION. | Division 11 |  | BGLT5 | CONSTRUCTION | 1200000
R-5912 | Highway | STI (Prioritization) | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | T | RIGHT-OF-WAY | 600000
R-5912 | Highway | STI (Prioritization) | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | T | UTILITIES | 400000
R-5912 | Highway | STI (Prioritization) | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 0.5 | YADKIN | 11 | Northwest Piedmont RPO | RIGHT-OF-WAY IN PROGRESS. | Division 11 |  | T | CONSTRUCTION | 1500000 | FY 2025: 1485000
R-5913 | Highway | STI (Prioritization) | NC 67; US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN EXISTING TWO LANE ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS; REHABILITATE BRIDGE 850021 OVER YADKIN RIVER AND WIDEN SIDEWALKS. | 0.35 | YADKIN, SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGLT5 | RIGHT-OF-WAY | 1100000 | FY 2025: 11000; FY 2026: 539000; FY 2027: 330000; FY 2028: 110000; FY 2029: 110000
R-5913 | Highway | STI (Prioritization) | NC 67; US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN EXISTING TWO LANE ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS; REHABILITATE BRIDGE 850021 OVER YADKIN RIVER AND WIDEN SIDEWALKS. | 0.35 | YADKIN, SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGLT5 | UTILITIES | 280000 | FY 2025: 280000
R-5913 | Highway | STI (Prioritization) | NC 67; US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN EXISTING TWO LANE ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS; REHABILITATE BRIDGE 850021 OVER YADKIN RIVER AND WIDEN SIDEWALKS. | 0.35 | YADKIN, SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGLT5 | CONSTRUCTION | 4550000 | FY 2027: 1940000; FY 2028: 2301000; FY 2029: 309000
R-5913 | Highway | STI (Prioritization) | NC 67; US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN EXISTING TWO LANE ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS; REHABILITATE BRIDGE 850021 OVER YADKIN RIVER AND WIDEN SIDEWALKS. | 0.35 | YADKIN, SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | HFB | CONSTRUCTION | 1250000 | FY 2027: 533000; FY 2028: 632000; FY 2029: 85000
R-5914 | Highway | STI (Prioritization) | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | 10.55 | YADKIN | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGLT5 | RIGHT-OF-WAY | 9000000 | FY 2028: 873000; FY 2029: 2618000; FY 2030: 2618000; FY 2031: 1091000; FY 2032: 1800000
R-5914 | Highway | STI (Prioritization) | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | 10.55 | YADKIN | 11 | Northwest Piedmont RPO |  | Division 11 |  | BGLT5 | UTILITIES | 14800000 | FY 2028: 4933000; FY 2029: 4933000; FY 2030: 4934000
R-5914 | Highway | STI (Prioritization) | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | 10.55 | YADKIN | 11 | Northwest Piedmont RPO |  | Division 11 |  | T | CONSTRUCTION | 92100000 | FY 2031: 9464000; FY 2032: 52252000; FY 2033: 23284000; FY 2034: 7100000
R-5915 | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | US 421/321 WEST OF BOONE TO US 421 EAST OF BOONE. CONSTRUCT FREEWAY ON NEW LOCATION SOUTH OF BOONE. | 10.42 | WATAUGA | 11 | High Country RPO |  | Division 11
R-5915A | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | 2.25 | WATAUGA | 11 | High Country RPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 81700000 | [11 empty] | 81700000
R-5915A | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | 2.25 | WATAUGA | 11 | High Country RPO |  | Not Funded |  | NHP | UTILITIES | 400000 | [11 empty] | 400000
R-5915A | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | 2.25 | WATAUGA | 11 | High Country RPO |  | Not Funded |  | NHP | CONSTRUCTION | 165600000 | [11 empty] | 165600000
R-5915B | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | 3.62 | WATAUGA | 11 | High Country RPO |  | Division 11 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 84801000
R-5915B | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | 3.62 | WATAUGA | 11 | High Country RPO |  | Division 11 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 600000
R-5915B | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | 3.62 | WATAUGA | 11 | High Country RPO |  | Division 11 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 346200000
R-5915C | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | 4.55 | WATAUGA | 11 | High Country RPO |  | Not Funded |  | NHP | RIGHT-OF-WAY | 133800000 | [11 empty] | 133800000
R-5915C | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | 4.55 | WATAUGA | 11 | High Country RPO |  | Not Funded |  | NHP | UTILITIES | 400000 | [11 empty] | 400000
R-5915C | Highway | STI (Prioritization) | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | 4.55 | WATAUGA | 11 | High Country RPO |  | Not Funded |  | NHP | CONSTRUCTION | 384600000 | [11 empty] | 384600000
R-5921 | Highway | STI (Prioritization) | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | 5.87 | HAYWOOD | 14 | Land-of-Sky RPO, French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. FUND CONSTRUCTION WITH TOLL CREDITS. | Division 14 |  | BGANY | RIGHT-OF-WAY | 8400000 | FY 2025: 840000; FY 2026: 840000
R-5921 | Highway | STI (Prioritization) | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | 5.87 | HAYWOOD | 14 | Land-of-Sky RPO, French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. FUND CONSTRUCTION WITH TOLL CREDITS. | Division 14 |  | BGANY | UTILITIES | 3200000
R-5921 | Highway | STI (Prioritization) | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | 5.87 | HAYWOOD | 14 | Land-of-Sky RPO, French Broad River MPO | RIGHT-OF-WAY IN PROGRESS. FUND CONSTRUCTION WITH TOLL CREDITS. | Division 14 |  | BGANY | CONSTRUCTION | 42000000 | FY 2025: 13020000; FY 2026: 15120000; FY 2027: 10080000; FY 2028: 3780000
R-5927 | Highway | STI (Prioritization) | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | 3.7 | MOORE | 8 | Sandhills MPO, Central Pines RPO |  | Division 8 |  | T | RIGHT-OF-WAY | 1300000 | FY 2027: 76000; FY 2028: 304000; FY 2029: 304000; FY 2030: 304000; FY 2031: 312000
R-5927 | Highway | STI (Prioritization) | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | 3.7 | MOORE | 8 | Sandhills MPO, Central Pines RPO |  | Division 8 |  | T | UTILITIES | 3900000 | FY 2027: 1950000; FY 2028: 1950000
R-5927 | Highway | STI (Prioritization) | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTI-LANES. | 3.7 | MOORE | 8 | Sandhills MPO, Central Pines RPO |  | Division 8 |  | T | CONSTRUCTION | 48100000 | FY 2031: 13550000; FY 2032: 16491000; FY 2033: 11837000; FY 2034: 6222000
R-5929 | Highway | STI (Prioritization) | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | 0.5 | MOORE | 8 | Central Pines RPO | COORDINATE WITH U-3628 | Division 8 |  | T | RIGHT-OF-WAY | 280000 | FY 2026: 280000
R-5929 | Highway | STI (Prioritization) | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | 0.5 | MOORE | 8 | Central Pines RPO | COORDINATE WITH U-3628 | Division 8 |  | T | UTILITIES | 280000 | FY 2026: 280000
R-5929 | Highway | STI (Prioritization) | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | 0.5 | MOORE | 8 | Central Pines RPO | COORDINATE WITH U-3628 | Division 8 |  | T | CONSTRUCTION | 4800000 | FY 2028: 3611000; FY 2029: 1189000
R-5930 | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 2.52 | CHATHAM | 8 | Central Pines RPO | "O" FUNDING REFLECTS LOCAL PARTICIPATION. | Division 8 |  | T | RIGHT-OF-WAY | 1693000
R-5930 | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 2.52 | CHATHAM | 8 | Central Pines RPO | "O" FUNDING REFLECTS LOCAL PARTICIPATION. | Division 8 |  | O | RIGHT-OF-WAY | 2000000
R-5930 | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 2.52 | CHATHAM | 8 | Central Pines RPO | "O" FUNDING REFLECTS LOCAL PARTICIPATION. | Division 8 |  | T | UTILITIES | 360000
R-5930A | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | NORTHERN TERMINUS OF EXISTING CHATHAM PARK WAY JUST NORTH OF US 64 TO NORTH OF PROPOSED GRANT DRIVE. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.11 | CHATHAM | 8 | Central Pines RPO | UNDER CONSTRUCTION | Division 8 |  | T | CONSTRUCTION | 12801000 | FY 2025: 5777000; FY 2026: 2376000
R-5930A | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | NORTHERN TERMINUS OF EXISTING CHATHAM PARK WAY JUST NORTH OF US 64 TO NORTH OF PROPOSED GRANT DRIVE. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.11 | CHATHAM | 8 | Central Pines RPO | UNDER CONSTRUCTION | Division 8 |  | O | CONSTRUCTION | 7000000 | FY 2025: 6000000
R-5930B | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | NORTH OF PROPOSED GRANT DRIVE TO US 15/ US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | 1.41 | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | T | CONSTRUCTION | 27700000 | FY 2025: 3020000; FY 2026: 11557000; FY 2027: 8754000; FY 2028: 4369000
R-5936 | Highway | STI (Prioritization) | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | 4.19 | WASHINGTON | 1 | Albemarle RPO |  | Division 1 |  | T | RIGHT-OF-WAY | 820000 | FY 2028: 820000
R-5936 | Highway | STI (Prioritization) | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | 4.19 | WASHINGTON | 1 | Albemarle RPO |  | Division 1 |  | T | UTILITIES | 120000 | FY 2028: 120000
R-5936 | Highway | STI (Prioritization) | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | 4.19 | WASHINGTON | 1 | Albemarle RPO |  | Division 1 |  | T | CONSTRUCTION | 38000000 | FY 2030: 9120000; FY 2031: 13300000; FY 2032: 9880000; FY 2033: 5700000
R-5937 | Highway | STI (Prioritization) | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | 2.12 | WASHINGTON | 1 | Albemarle RPO |  | Division 1 |  | T | RIGHT-OF-WAY | 1400000 | FY 2028: 1400000
R-5937 | Highway | STI (Prioritization) | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | 2.12 | WASHINGTON | 1 | Albemarle RPO |  | Division 1 |  | T | UTILITIES | 340000 | FY 2028: 340000
R-5937 | Highway | STI (Prioritization) | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | 2.12 | WASHINGTON | 1 | Albemarle RPO |  | Division 1 |  | T | CONSTRUCTION | 21600000 | FY 2032: 4752000; FY 2033: 10800000; FY 2034: 6048000
R-5938 | Highway | STI (Prioritization) | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | 17.27 | GATES, CHOWAN | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 48640000
R-5938 | Highway | STI (Prioritization) | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | 17.27 | GATES, CHOWAN | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 15700000
R-5938 | Highway | STI (Prioritization) | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | 17.27 | GATES, CHOWAN | 1 | Albemarle RPO |  | Division 1 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 160600000
R-5939 | Highway | STI (Prioritization) | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | 4.38 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 |  | T | RIGHT-OF-WAY | 1400000 | FY 2028: 153000; FY 2029: 611000; FY 2030: 356000; FY 2031: 140000; FY 2032: 140000
R-5939 | Highway | STI (Prioritization) | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | 4.38 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 |  | T | UTILITIES | 1700000 | FY 2028: 1700000
R-5939 | Highway | STI (Prioritization) | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO SR 1329 (WOODVILLE ROAD). MODERNIZE ROADWAY. | 4.38 | PERQUIMANS | 1 | Albemarle RPO |  | Division 1 |  | T | CONSTRUCTION | 26000000 | FY 2030: 5720000; FY 2031: 12480000; FY 2032: 7800000
R-5940 | Highway | STI (Prioritization) | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | 14.34 | TYRRELL | 1 | Albemarle RPO |  | Division 1 |  | NHP | RIGHT-OF-WAY | 1400000 | FY 2028: 1400000
R-5940 | Highway | STI (Prioritization) | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | 14.34 | TYRRELL | 1 | Albemarle RPO |  | Division 1 |  | NHP | UTILITIES | 6000000 | FY 2028: 3000000; FY 2029: 3000000
R-5940 | Highway | STI (Prioritization) | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | 14.34 | TYRRELL | 1 | Albemarle RPO |  | Division 1 |  | NHP | CONSTRUCTION | 64900000 | FY 2032: 9735000; FY 2033: 22066000; FY 2034: 17523000; FY 2035: 15576000
R-5941 | Highway | STI (Prioritization) | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | 1.3 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 7400000
R-5941 | Highway | STI (Prioritization) | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | 1.3 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 930000
R-5941 | Highway | STI (Prioritization) | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | 1.3 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 4000000
R-5943 | Highway | STI (Prioritization) | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | 0.5 | GREENE | 2 | Eastern Carolina RPO |  | Division 2 |  | BGLT5 | RIGHT-OF-WAY | 4700000 | FY 2026: 94000; FY 2027: 1316000; FY 2028: 1316000; FY 2029: 987000; FY 2030: 987000
R-5943 | Highway | STI (Prioritization) | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | 0.5 | GREENE | 2 | Eastern Carolina RPO |  | Division 2 |  | BGLT5 | UTILITIES | 600000 | FY 2026: 600000
R-5943 | Highway | STI (Prioritization) | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | 0.5 | GREENE | 2 | Eastern Carolina RPO |  | Division 2 |  | BGLT5 | CONSTRUCTION | 10500000 | FY 2028: 5145000; FY 2029: 5355000
R-5944 | Highway | STI (Prioritization) | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | 0.5 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 650000
R-5944 | Highway | STI (Prioritization) | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | 0.5 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 100000
R-5944 | Highway | STI (Prioritization) | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | 0.5 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 5300000
R-5945 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | 1.8 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 18400000
R-5945 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | 1.8 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 5700000
R-5945 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | 1.8 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 27700000
R-5946 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | 0.5 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | RIGHT-OF-WAY | 4900000
R-5946 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | 0.5 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | UTILITIES | 700000
R-5946 | Highway | STI (Prioritization) | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | 0.5 | CARTERET | 2 | Down East RPO |  | Division 2 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | NHP | CONSTRUCTION | 4300000
R-5949 | Highway | STI (Prioritization) | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | 1.77 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T | RIGHT-OF-WAY | 1901000 | FY 2029: 290000; FY 2030: 869000; FY 2031: 362000; FY 2032: 190000; FY 2033: 190000
R-5949 | Highway | STI (Prioritization) | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | 1.77 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T | UTILITIES | 2600000 | FY 2029: 1300000; FY 2030: 1300000
R-5949 | Highway | STI (Prioritization) | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | 1.77 | EDGECOMBE | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T | CONSTRUCTION | 54000000 | FY 2031: 10800000; FY 2032: 24840000; FY 2033: 16200000; FY 2034: 2160000
R-5950 | Highway | STI (Prioritization) | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | 0.29 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T | RIGHT-OF-WAY | 2000000 | FY 2029: 480000; FY 2030: 960000; FY 2031: 160000; FY 2032: 200000; FY 2033: 200000
R-5950 | Highway | STI (Prioritization) | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | 0.29 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T | UTILITIES | 1700000 | FY 2029: 1700000
R-5950 | Highway | STI (Prioritization) | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | 0.29 | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | T | CONSTRUCTION | 5600000 | FY 2031: 3416000; FY 2032: 2184000
R-5956 | Highway | STI (Prioritization) | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) ITO SR 2123 (CAUDLE ROAD) IN ASHEBORO. WIDEN TO MULTI-LANES. | 3.6 | RANDOLPH | 8 | Piedmont Triad RPO | COORDINATE WITH U-6006 | Division 8
R-5958 | Highway | STI (Prioritization) | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | 0.5 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | T | RIGHT-OF-WAY | 320000 | FY 2025: 320000
R-5958 | Highway | STI (Prioritization) | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | 0.5 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | T | UTILITIES | 265000 | FY 2026: 265000
R-5958 | Highway | STI (Prioritization) | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | 0.5 | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | T | CONSTRUCTION | 1900000 | FY 2027: 18000; FY 2028: 1882000
R-5959 | Highway | STI (Prioritization) | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | 0.5 | LEE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | RIGHT-OF-WAY | 1900000 | FY 2025: 665000; FY 2026: 855000; FY 2027: 190000; FY 2028: 190000
R-5959 | Highway | STI (Prioritization) | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | 0.5 | LEE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | UTILITIES | 660000 | FY 2025: 660000
R-5959 | Highway | STI (Prioritization) | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | 0.5 | LEE | 8 | Central Pines RPO | RIGHT-OF-WAY IN PROGRESS | Division 8 |  | T | CONSTRUCTION | 7100000 | FY 2026: 2566000; FY 2027: 3648000; FY 2028: 886000
R-5963 | Highway | STI (Prioritization) | (CHATHAM PARK WAY) NEW ROUTE | US 15 / US 501 / NC 87 TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 3.03 | CHATHAM | 8 | Central Pines RPO | Former R-5963B merged into R-5963A. BUILD NC BONDS: $6M FOR CONSTRUCTION - PAYBACK 2028-2042 (FY 2028 / YR 8 SALE)
R-5963A | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 15 / US 501 SOUTH OF PITTSBORO TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 1.33 | CHATHAM | 8 | Central Pines RPO | BUILD NC BOND FUNDING: $22,806,281 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 8 |  | T | RIGHT-OF-WAY | 6259000 | FY 2025: 5007000; FY 2026: 626000; FY 2027: 626000
R-5963A | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 15 / US 501 SOUTH OF PITTSBORO TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 1.33 | CHATHAM | 8 | Central Pines RPO | BUILD NC BOND FUNDING: $22,806,281 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 8 |  | T | UTILITIES | 62000 | FY 2025: 62000
R-5963A | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 15 / US 501 SOUTH OF PITTSBORO TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 1.33 | CHATHAM | 8 | Central Pines RPO | BUILD NC BOND FUNDING: $22,806,281 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 8 |  | T | BUILD NC CON | 10680000 |  |  |  | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 712000 | 4984000
R-5963A | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 15 / US 501 SOUTH OF PITTSBORO TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 1.33 | CHATHAM | 8 | Central Pines RPO | BUILD NC BOND FUNDING: $22,806,281 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 8 |  | T | BUILD NC CON | 34785000 | 2319000 | 2319000 | 2319000 | 2319000 | 2319000 | 2319000 | 2319000 | 2319000 | 2319000 | 2319000 | 2319000 | 9276000
R-5963A | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 15 / US 501 SOUTH OF PITTSBORO TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | 1.33 | CHATHAM | 8 | Central Pines RPO | BUILD NC BOND FUNDING: $22,806,281 FOR CONSTRUCTION PAYBACK 2025 - 2039 (FY 2025 / YR 5 SALE). | Division 8 |  | T | CONSTRUCTION | 37294000 | FY 2025: 0; FY 2026: 4295000; FY 2027: 18508000; FY 2028: 7220000; FY 2029: 7271000
R-5963C | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 64 BUSINESS TO JUST NORTH OF US 64. WIDEN EXISTING 2-LANE ROADWAY TO 4-LANES. | 1.22 | CHATHAM | 8 | Central Pines RPO |  | Not Funded |  | T | UTILITIES | 30000 | [11 empty] | 30000
R-5963C | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | US 64 BUSINESS TO JUST NORTH OF US 64. WIDEN EXISTING 2-LANE ROADWAY TO 4-LANES. | 1.22 | CHATHAM | 8 | Central Pines RPO |  | Not Funded |  | T | CONSTRUCTION | 32100000 | [11 empty] | 32100000
R-5963D | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | CONSTRUCTION OF NEW WESTBOUND ON-RAMP FROM CHATHAM PARK WAY TO US 64 AND REALIGNMENT OF SUTTLES ROAD TO NEW INTERSECTION WITH CHATHAM PARK WAY. | 0.5 | CHATHAM | 8 | Central Pines RPO | ROW BEING DONATED BY TOWN OF PITTSBORO | Division 8 |  | T | RIGHT-OF-WAY | 500000
R-5963D | Highway | STI (Prioritization) | NEW ROUTE (CHATHAM PARK WAY) | CONSTRUCTION OF NEW WESTBOUND ON-RAMP FROM CHATHAM PARK WAY TO US 64 AND REALIGNMENT OF SUTTLES ROAD TO NEW INTERSECTION WITH CHATHAM PARK WAY. | 0.5 | CHATHAM | 8 | Central Pines RPO | ROW BEING DONATED BY TOWN OF PITTSBORO | Division 8 |  | T | CONSTRUCTION | 6700000 | FY 2025: 4958000; FY 2026: 1072000
R-5964 | Highway | Appalachian Development Highway System | NEW ROUTE | CONSTRUCT ACCESS ROAD TO UNIVERSAL PROPERTY. | 0.17 | McDOWELL | 13 | Foothills RPO | UNDER CONSTRUCTION. ARC # 19098; AWARD AMOUNT = $987,112 | Exempt |  | ADHSL | CONSTRUCTION | 922000
R-5965 | Highway | Economic Development | VARIOUS | VARIOUS IMPROVEMENTS AROUND TOWN OF OAKBORO. | 3.4 | STANLY | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. TOTAL AWARD AMOUNT = $4,400,279
R-5965A | Highway | Economic Development | VARIOUS | NC 205/SR 1108 (LIGHTHOUSE ROAD)/SR 1109 (BUSTER ROAD) INTERSECTION AND SR 1110 (SWIFT ROAD) AT CHARLOTTE PIPE FACILITY. IMPROVE INTERSECTIONS. | 0.5 | STANLY | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. | Division 10 |  | T | RIGHT-OF-WAY | 120000
R-5965A | Highway | Economic Development | VARIOUS | NC 205/SR 1108 (LIGHTHOUSE ROAD)/SR 1109 (BUSTER ROAD) INTERSECTION AND SR 1110 (SWIFT ROAD) AT CHARLOTTE PIPE FACILITY. IMPROVE INTERSECTIONS. | 0.5 | STANLY | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. | Division 10 |  | T | CONSTRUCTION | 2405000
R-5965B | Highway | Economic Development | VARIOUS | SR 1107 (SILVER ROAD)/SR 1108 (LIGHTHOUSE ROAD) AND SR 1107 (SILVER ROAD)/SR 1110 (SWIFT ROAD) INTERSECTIONS. IMPROVE INTERSECTIONS. SR 1107 (SILVER ROAD), SR 1108 (LIGHTHOUSE ROAD) AND SR 1110 (SWIFT ROAD). VARIOUS ROADWAY IMPROVEMENTS INCLUDING FULL DEPTH RECLAMATION. |  | STANLY | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. | Division 10 |  | T | RIGHT-OF-WAY | 250000
R-5965B | Highway | Economic Development | VARIOUS | SR 1107 (SILVER ROAD)/SR 1108 (LIGHTHOUSE ROAD) AND SR 1107 (SILVER ROAD)/SR 1110 (SWIFT ROAD) INTERSECTIONS. IMPROVE INTERSECTIONS. SR 1107 (SILVER ROAD), SR 1108 (LIGHTHOUSE ROAD) AND SR 1110 (SWIFT ROAD). VARIOUS ROADWAY IMPROVEMENTS INCLUDING FULL DEPTH RECLAMATION. |  | STANLY | 10 | Rocky River RPO | THIS IS AN ECONOMIC DEVELOPMENT PROJECT FOR CHARLOTTE PIPE - UNDER CONSTRUCTION. | Division 10 |  | T | CONSTRUCTION | 1586000
R-5966 | Highway | Other | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. |  | CHEROKEE, GRAHAM, JACKSON, SWAIN | 14 | Southwestern RPO | PROGRAM IN PROGRESS | Exempt |  | FTTP | CONSTRUCTION | 937000 | FY 2027: 937000
R-5966 | Highway | Other | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. |  | CHEROKEE, GRAHAM, JACKSON, SWAIN | 14 | Southwestern RPO | PROGRAM IN PROGRESS | Exempt |  | FTTP | CONSTRUCTION | 1309000 | FY 2026: 1309000
R-5966 | Highway | Other | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. |  | CHEROKEE, GRAHAM, JACKSON, SWAIN | 14 | Southwestern RPO | PROGRAM IN PROGRESS | Exempt |  | FTTP | CONSTRUCTION | 7183000
R-5966 | Highway | Other | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. |  | CHEROKEE, GRAHAM, JACKSON, SWAIN | 14 | Southwestern RPO | PROGRAM IN PROGRESS | Exempt |  | FTTP | CONSTRUCTION | 16061000 | FY 2025: 5598000
R-5967 | Highway | Appalachian Development Highway System | SR 1687 (GOAT FARM ROAD) | IMPROVE EXISTING SR 1687 (GOAT FARM ROAD) ACCESS ROAD INTO THE PROPOSED INDUSTRIAL PARK. | 0.88 | BURKE | 13 | Greater Hickory MPO | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY. UNDER CONSTRUCTION. | Exempt |  | ADHSL | CONSTRUCTION | 1076000
R-5967 | Highway | Appalachian Development Highway System | SR 1687 (GOAT FARM ROAD) | IMPROVE EXISTING SR 1687 (GOAT FARM ROAD) ACCESS ROAD INTO THE PROPOSED INDUSTRIAL PARK. | 0.88 | BURKE | 13 | Greater Hickory MPO | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY. UNDER CONSTRUCTION. | Exempt |  | L | CONSTRUCTION | 1076000
R-5968 | Highway | Other | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY. |  | STATEWIDE | 99 | STATEWIDE PROJECT
R-5968DIV | Highway | Other | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Division 99 |  | BGANY | CONSTRUCTION | 14400000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000
R-5968REG | Highway | Other | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Region SW |  | BGANY | CONSTRUCTION | 14400000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000
R-5968SW | Highway | Other | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS | Statewide Mobility |  | BGANY | CONSTRUCTION | 19200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000
R-9999WM | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS
R-9999WMDIV | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | NHP | MITIGATION | 150000
R-9999WMDIV | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | MITIGATION | 150000
R-9999WMREG | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | NHP | MITIGATION | 150000
R-9999WMREG | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | MITIGATION | 150000
R-9999WMSW | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | NHP | MITIGATION | 200000
R-9999WMSW | Highway | Other | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | MITIGATION | 200000
RC-2000 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES PROGRAM ADMINISTRATION |  | STATEWIDE | 99 | STATEWIDE PROJECT | PROGRAMMED FOR PLANNING ONLY. | Statewide Mobility
RC-2001 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 1
RC-2002 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO |  | Division 2
RC-2002A | Rail | Rail-Highway Grade Crossing Closure | EAST STREET | CLOSURE OF EAST STREET AT CSX (CROSSING 628 794Y) IN BETHEL. |  | PITT | 2 | Mid-East RPO |  | Division 2 |  | RR | CONSTRUCTION | 560000
RC-2003 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 3
RC-2004 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO |  | Division 4
RC-2004A | Rail | Rail-Highway Grade Crossing Closure | SR 1163 (GOLDSBORO STREET) | AT-GRADE CROSSING IMPROVEMENTS AT CSX (CROSSING 629 847Y) IN WILSON. |  | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | RIGHT-OF-WAY | 50000
RC-2004A | Rail | Rail-Highway Grade Crossing Closure | SR 1163 (GOLDSBORO STREET) | AT-GRADE CROSSING IMPROVEMENTS AT CSX (CROSSING 629 847Y) IN WILSON. |  | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | UTILITIES | 50000 | FY 2025: 50000
RC-2004A | Rail | Rail-Highway Grade Crossing Closure | SR 1163 (GOLDSBORO STREET) | AT-GRADE CROSSING IMPROVEMENTS AT CSX (CROSSING 629 847Y) IN WILSON. |  | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 1200000 | FY 2026: 408000; FY 2027: 792000
RC-2004B | Rail | Rail-Highway Grade Crossing Closure | SR 2383 (PRESTON STREET) | CLOSURE OF SR 2383 (PRESTON STREET) AT CSX (CROSSING 629 950L) IN SELMA. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | RIGHT-OF-WAY | 50000 | FY 2025: 50000
RC-2004B | Rail | Rail-Highway Grade Crossing Closure | SR 2383 (PRESTON STREET) | CLOSURE OF SR 2383 (PRESTON STREET) AT CSX (CROSSING 629 950L) IN SELMA. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | UTILITIES | 20000 | FY 2025: 20000
RC-2004B | Rail | Rail-Highway Grade Crossing Closure | SR 2383 (PRESTON STREET) | CLOSURE OF SR 2383 (PRESTON STREET) AT CSX (CROSSING 629 950L) IN SELMA. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 500000 | FY 2026: 337000; FY 2027: 163000
RC-2005 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 5
RC-2006 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 6
RC-2007 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 7
RC-2008 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 8
RC-2009 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 9
RC-2010 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 10
RC-2010A | Rail | Rail-Highway Grade Crossing Closure | SR 1758, STEWART STREET, SR 1762 | IMPROVE CROSSINGS AT SR 1758 (NORTH MAIN STREET) AND SR 1762 ( BIVENS STREET). CLOSE THE STEWART STREET CROSSING. |  | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | RR | RIGHT-OF-WAY | 500000 | FY 2025: 500000
RC-2010A | Rail | Rail-Highway Grade Crossing Closure | SR 1758, STEWART STREET, SR 1762 | IMPROVE CROSSINGS AT SR 1758 (NORTH MAIN STREET) AND SR 1762 ( BIVENS STREET). CLOSE THE STEWART STREET CROSSING. |  | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | RR | CONSTRUCTION | 3000000 | FY 2025: 2147000; FY 2026: 853000
RC-2011 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 11
RC-2012 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 12
RC-2013 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 13
RC-2014 | Rail | Rail-Highway Grade Crossing Closure | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED. | Division 14
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | DP | ENGINEERING | 400000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | BGDA | ENGINEERING | 398000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | L | ENGINEERING | 400000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | L | ENGINEERING | 100000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | DP | RIGHT-OF-WAY | 160000 | FY 2025: 160000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | L | RIGHT-OF-WAY | 160000 | FY 2025: 160000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | DP | CONSTRUCTION | 3930000 | FY 2025: 3930000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | BGDA | CONSTRUCTION | 3818000 | FY 2025: 3818000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | L | CONSTRUCTION | 955000 | FY 2025: 955000
RL-0001 | Rail | Locally Selected | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | 0.3 | IREDELL | 12 | Charlotte Regional TPO | DP REPRESENTS FEDERAL CRISI GRANT FUNDS. STBG-DA FUNDS ARE EXEMPT SINCE THE PROJECT IS AN ELIGIBLE STATEWIDE MOBILITY PROJECT. | Region F |  | L | CONSTRUCTION | 3930000 | FY 2025: 3930000
RL-0002 | Rail | Locally Selected | CHARLOTTE RAILYARD PINEVILLE RAILYARD | GRANTS TO REPLACE AGING DIESEL ENGINES (GRADE). |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CMAQ | CONSTRUCTION | 3815000 | FY 2025: 3815000
RL-0002 | Rail | Locally Selected | CHARLOTTE RAILYARD PINEVILLE RAILYARD | GRANTS TO REPLACE AGING DIESEL ENGINES (GRADE). |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 1635000 | FY 2025: 1635000
RP-0001 | Rail | STI (Prioritization) | CSX SF LINE | SR 1007 (ROCKY RIVER ROAD), SR 1009 (OLD CHARLOTTE HIGHWAY) IN MONROE. CONSTRUCT TWO RAIL-HIGHWAY GRADE SEPARATIONS. |  | UNION | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | RIGHT-OF-WAY | 7800000
RP-0001 | Rail | STI (Prioritization) | CSX SF LINE | SR 1007 (ROCKY RIVER ROAD), SR 1009 (OLD CHARLOTTE HIGHWAY) IN MONROE. CONSTRUCT TWO RAIL-HIGHWAY GRADE SEPARATIONS. |  | UNION | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | UTILITIES | 210000
RP-0001 | Rail | STI (Prioritization) | CSX SF LINE | SR 1007 (ROCKY RIVER ROAD), SR 1009 (OLD CHARLOTTE HIGHWAY) IN MONROE. CONSTRUCT TWO RAIL-HIGHWAY GRADE SEPARATIONS. |  | UNION | 10 | Charlotte Regional TPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | BGANY | CONSTRUCTION | 34000000
RP-0002 | Rail | STI (Prioritization) | CSX A LINE | HAY STREET CROSSING IN FAYETTEVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING #629881F IN FAYETTEVILLE |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 13600000
RP-0002 | Rail | STI (Prioritization) | CSX A LINE | HAY STREET CROSSING IN FAYETTEVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING #629881F IN FAYETTEVILLE |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1600000
RP-0002 | Rail | STI (Prioritization) | CSX A LINE | HAY STREET CROSSING IN FAYETTEVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING #629881F IN FAYETTEVILLE |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Statewide Mobility | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 34000000
RP-0003 | Rail | STI (Prioritization) | NCRR / NS NC LINE | SR 1549 (MACKAY ROAD) INTERSECTION IN GREENSBORO (CROSSING #722359X). CONSTRUCT MACKAY ROAD GRADE SEPARATION. INCLUDES RELOCATING ATWATER DRIVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 8400000
RP-0003 | Rail | STI (Prioritization) | NCRR / NS NC LINE | SR 1549 (MACKAY ROAD) INTERSECTION IN GREENSBORO (CROSSING #722359X). CONSTRUCT MACKAY ROAD GRADE SEPARATION. INCLUDES RELOCATING ATWATER DRIVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1000000
RP-0003 | Rail | STI (Prioritization) | NCRR / NS NC LINE | SR 1549 (MACKAY ROAD) INTERSECTION IN GREENSBORO (CROSSING #722359X). CONSTRUCT MACKAY ROAD GRADE SEPARATION. INCLUDES RELOCATING ATWATER DRIVE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 21000000
RP-0004 | Rail | STI (Prioritization) | NCRR / NS MAIN LINE | SR 1332 (SCIENTIFIC STREET) INTERSECTION IN JAMESTOWN. CONSTRUCT GRADE SEPARATION AND CLOSURE OF EXISTING AT-GRADE CROSSING (#722352A). |  | GUILFORD | 7 | High Point Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 5100000
RP-0004 | Rail | STI (Prioritization) | NCRR / NS MAIN LINE | SR 1332 (SCIENTIFIC STREET) INTERSECTION IN JAMESTOWN. CONSTRUCT GRADE SEPARATION AND CLOSURE OF EXISTING AT-GRADE CROSSING (#722352A). |  | GUILFORD | 7 | High Point Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 100000
RP-0004 | Rail | STI (Prioritization) | NCRR / NS MAIN LINE | SR 1332 (SCIENTIFIC STREET) INTERSECTION IN JAMESTOWN. CONSTRUCT GRADE SEPARATION AND CLOSURE OF EXISTING AT-GRADE CROSSING (#722352A). |  | GUILFORD | 7 | High Point Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 17000000
RP-0005 | Rail | STI (Prioritization) | NC RR / NS NC LINE | SR 1120 (MT. WILLING ROAD) INTERSECTION IN EFLAND. REALING SR 1120 (MT. WILLING ROAD) TO LINE UP WITH EFLAND CEDAR GROVE ROAD AT US 70 AND CLOSE AT-GRADE CROSSING (CROSSING NUMBER 735145T) AND CONSTRUCT BRIDGE OVER THIS LINE. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 4200000
RP-0005 | Rail | STI (Prioritization) | NC RR / NS NC LINE | SR 1120 (MT. WILLING ROAD) INTERSECTION IN EFLAND. REALING SR 1120 (MT. WILLING ROAD) TO LINE UP WITH EFLAND CEDAR GROVE ROAD AT US 70 AND CLOSE AT-GRADE CROSSING (CROSSING NUMBER 735145T) AND CONSTRUCT BRIDGE OVER THIS LINE. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 100000
RP-0005 | Rail | STI (Prioritization) | NC RR / NS NC LINE | SR 1120 (MT. WILLING ROAD) INTERSECTION IN EFLAND. REALING SR 1120 (MT. WILLING ROAD) TO LINE UP WITH EFLAND CEDAR GROVE ROAD AT US 70 AND CLOSE AT-GRADE CROSSING (CROSSING NUMBER 735145T) AND CONSTRUCT BRIDGE OVER THIS LINE. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 14000000
RP-0006 | Rail | STI (Prioritization) | NCRR / NS MAIN LINE | SR 2120 (LONG FERRY RD). CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING #715307NR. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 4500000
RP-0006 | Rail | STI (Prioritization) | NCRR / NS MAIN LINE | SR 2120 (LONG FERRY RD). CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING #715307NR. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 700000
RP-0006 | Rail | STI (Prioritization) | NCRR / NS MAIN LINE | SR 2120 (LONG FERRY RD). CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING #715307NR. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 15000000
RP-0007 | Rail | STI (Prioritization) | NCRR/NS MAINLINE | SR 1352 (OAKDALE ROAD). CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING #722355V. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | RIGHT-OF-WAY | 12000000
RP-0007 | Rail | STI (Prioritization) | NCRR/NS MAINLINE | SR 1352 (OAKDALE ROAD). CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING #722355V. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | UTILITIES | 1400000
RP-0007 | Rail | STI (Prioritization) | NCRR/NS MAINLINE | SR 1352 (OAKDALE ROAD). CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING #722355V. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Region D | FUNDED FOR PRELIMINARY ENGINEERING ONLY | T | CONSTRUCTION | 30000000
RX-2000 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS PROGRAM ADMINISTRATION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | PROGRAMMED FOR PLANNING ONLY. | Statewide Mobility
RX-2001 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1
RX-2001A | Rail | Rail-Highway Grade Crossing Improvement | SR 1409 (HALL SIDING ROAD) | NCVA CROSSING 642347G IN AHOSKIE. |  | HERTFORD | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | Division 1 |  | RR | ENGINEERING | 20000 | FY 2025: 20000
RX-2001A | Rail | Rail-Highway Grade Crossing Improvement | SR 1409 (HALL SIDING ROAD) | NCVA CROSSING 642347G IN AHOSKIE. |  | HERTFORD | 1 | Peanut Belt RPO | UNDER CONSTRUCTION. | Division 1 |  | RR | CONSTRUCTION | 355000 | FY 2025: 355000
RX-2002 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2
RX-2002B | Rail | Rail-Highway Grade Crossing Improvement | SR 1704 (FOURTEENTH STREET) | CLNA CROSSING 465488D IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | RR | CONSTRUCTION | 345000 | FY 2025: 345000
RX-2002C | Rail | Rail-Highway Grade Crossing Improvement | US 264 ALTERNATE (GREENVILLE BOULEVARD) | CLNA CROSSING 465489K IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | RR | CONSTRUCTION | 345000 | FY 2025: 345000
RX-2002D | Rail | Rail-Highway Grade Crossing Improvement | LINCOLN STREET | NORFOLK SOUTHERN CROSSING 722766G IN KINSTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | LENOIR | 2 | Eastern Carolina RPO |  | Division 2 |  | RR | CONSTRUCTION | 411000 | FY 2025: 276000; FY 2026: 135000
RX-2002E | Rail | Rail-Highway Grade Crossing Improvement | SR 1530 (AIRPORT ROAD) | CSX CROSSING 641860P IN GREENVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | PITT | 2 | Greenville Urban Area MPO |  | Division 2 |  | RR | CONSTRUCTION | 530000 | FY 2027: 356000; FY 2028: 174000
RX-2003 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Jacksonville Urban Area MPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3
RX-2004 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 4
RX-2004A | Rail | Rail-Highway Grade Crossing Improvement | SR 1163 (GOLDSBORO STREET / HERRING AVENUE) | CSX CROSSING 629847Y IN WILSON. INSTALL ACTIVE WARNING DEVICES. |  | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 800000 | FY 2025: 540000; FY 2026: 260000
RX-2004B | Rail | Rail-Highway Grade Crossing Improvement | SR 1100 (CHICOPEE ROAD) | CSX CROSSING 629847Y IN WILSON. INSTALL ACTIVE WARNING DEVICES. |  | WILSON | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | Division 4 |  | RR | CONSTRUCTION | 650000
RX-2004C | Rail | Rail-Highway Grade Crossing Improvement | SR 1357 (GILBERT ROAD) | CSX CROSSING 629731X NEAR BENSON. INSTALL ACTIVE WARNING DEVICES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 600000 | FY 2025: 96000
RX-2004D | Rail | Rail-Highway Grade Crossing Improvement | PARRISH DRIVE | CSX CROSSING 629739C IN BENSON. CONSTRUCT SAFETY IMPROVEMENTS. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 500000 | FY 2025: 500000
RX-2004E | Rail | Rail-Highway Grade Crossing Improvement | SR 1329 (VAN SLYKE ROAD) | CSX CROSSING 629843W IN WILSON. CONSTRUCT SAFETY IMPROVEMENTS. |  | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 650000 | FY 2025: 650000
RX-2004F | Rail | Rail-Highway Grade Crossing Improvement | BAIN STREET | NORFOLK SOUTHERN CROSSING 722874X IN GOLDSBORO. CONSTRUCT SAFETY IMPROVEMENTS. |  | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | RR | CONSTRUCTION | 417000 | FY 2025: 296000; FY 2026: 121000
RX-2004G | Rail | Rail-Highway Grade Crossing Improvement | SR 2130 (MAIN STREET) | CSX CROSSING 629943B IN MICRO. CONSTRUCT SAFETY IMPROVEMENTS. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 417000 | FY 2025: 296000; FY 2026: 121000
RX-2004H | Rail | Rail-Highway Grade Crossing Improvement | SR 1709 (STALLINGS STREET) | NORFOLK SOUTHERN CROSSING 735396M IN CLAYTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | JOHNSTON | 4 | Capital Area MPO |  | Division 4 |  | RR | CONSTRUCTION | 475000 | FY 2025: 337000; FY 2026: 138000
RX-2004I | Rail | Rail-Highway Grade Crossing Improvement | GREEN STREET | CSX CROSSING 629849M IN WILSON. CONSTRUCT SAFETY IMPROVEMENTS. |  | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 417000 | FY 2025: 296000; FY 2026: 121000
RX-2004J | Rail | Rail-Highway Grade Crossing Improvement | SR 2339 (BAGLEY ROAD) | CSX CROSSING 629939L IN KENLY. CONSTRUCT SAFETY IMPROVEMENTS. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 434000 | FY 2026: 308000; FY 2027: 126000
RX-2004K | Rail | Rail-Highway Grade Crossing Improvement | LEE STREET | CSX CROSSING 629964U IN SMITHFIELD. CONSTRUCT SAFETY IMPROVEMENTS. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 388000 | FY 2027: 275000; FY 2028: 113000
RX-2004L | Rail | Rail-Highway Grade Crossing Improvement | SR 2500 (WALLPAT ROAD) | CSX CROSSING 629966H IN SMITHFIELD. CONSTRUCT SAFETY IMPROVEMENTS. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 388000 | FY 2027: 275000; FY 2028: 113000
RX-2004M | Rail | Rail-Highway Grade Crossing Improvement | JEFFERSON STREET | NORFOLK SOUTHERN CROSSING 722868U IN GOLDSBORO. CONSTRUCT SAFETY IMPROVEMENTS. |  | WAYNE | 4 | Goldsboro Urban Area MPO |  | Division 4 |  | RR | CONSTRUCTION | 411000 | FY 2027: 291000; FY 2028: 120000
RX-2005 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 5
RX-2006 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6
RX-2006A | Rail | Rail-Highway Grade Crossing Improvement | SR 1714 (CHURCH STREET) | CSX CROSSING 629869Y IN WADE. INSTALL ACTIVE WARNING DEVICES. |  | CUMBERLAND | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | Division 6 |  | RR | CONSTRUCTION | 800000
RX-2006B | Rail | Rail-Highway Grade Crossing Improvement | SR 1154 (UNION SCHOOL ROAD) | CSX CROSSING 629606K NEAR PEMBROKE. INSTALL ACTIVE WARNING DEVICES. |  | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | RR | CONSTRUCTION | 1450000 | FY 2025: 410000
RX-2006C | Rail | Rail-Highway Grade Crossing Improvement | HARNETT STREET | CSX CROSSING 629751J IN DUNN. CONSTRUCT SAFETY IMPROVEMENTS. |  | HARNETT | 6 | Mid-Carolina RPO |  | Division 6 |  | RR | CONSTRUCTION | 446000 | FY 2025: 291000; FY 2026: 155000
RX-2006D | Rail | Rail-Highway Grade Crossing Improvement | EDGERTON STREET | CSX CROSSING 629752R IN DUNN. CONSTRUCT SAFETY IMPROVEMENTS. |  | HARNETT | 6 | Mid-Carolina RPO |  | Division 6 |  | RR | CONSTRUCTION | 446000 | FY 2025: 291000; FY 2026: 155000
RX-2006E | Rail | Rail-Highway Grade Crossing Improvement | NC 41 (MARTIN LUTHER KING JR. DRIVE) | CSX CROSSING 631029P IN LUMBERTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | RR | CONSTRUCTION | 446000 | FY 2026: 291000; FY 2027: 155000
RX-2006F | Rail | Rail-Highway Grade Crossing Improvement | US 401 (MAIN STREET) | RFR CROSSING 465860F IN LILLINGTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | HARNETT | 6 | Mid-Carolina RPO |  | Division 6 |  | RR | CONSTRUCTION | 345000 | FY 2026: 225000; FY 2027: 120000
RX-2006G | Rail | Rail-Highway Grade Crossing Improvement | SR 1748 (CRENSHAW ROAD) | CSX CROSSING 629581S IN REX. CONSTRUCT SAFETY IMPROVEMENTS. |  | ROBESON | 6 | Lumber River RPO |  | Division 6 |  | RR | CONSTRUCTION | 417000 | FY 2027: 272000; FY 2028: 145000
RX-2007 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 7
RX-2007A | Rail | Rail-Highway Grade Crossing Improvement | SR 2748 (SPRINGWOOD AVENUE) | NORFOLK SOUTHERN RAILROAD CROSSING 722990L IN GIBSONVILLE. INSTALL ACTIVE WARNING DEVICES. |  | GUILFORD | 7 | Burlington-Graham MPO | UNDER CONSTRUCTION | Division 7 |  | RR | CONSTRUCTION | 500000
RX-2007B | Rail | Rail-Highway Grade Crossing Improvement | SR 1120 (MOUNT WILLING ROAD) | NORFOLK SOUTHERN RAILROAD CROSSING 735145T NEAR EFLAND. INSTALL ACTIVE WARNING DEVICES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | RR | CONSTRUCTION | 800000 | FY 2025: 447000; FY 2026: 353000
RX-2007C | Rail | Rail-Highway Grade Crossing Improvement | SR 2531 (HILLCROFT ROAD) | NORFOLK SOUTHERN RAILROAD CROSSING 722545Y NEAR GREENSBORO. INSTALL ACTIVE WARNING DEVICES. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Division 7 |  | RR | CONSTRUCTION | 800000
RX-2008 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 8
RX-2008A | Rail | Rail-Highway Grade Crossing Improvement | SR 1916 (CORINTH ROAD) | CSX CROSSING 630723C NEAR HAYWOOD. INSTALL ACTIVE WARNING DEVICES. |  | CHATHAM | 8 | Central Pines RPO |  | Division 8 |  | RR | CONSTRUCTION | 800000 | FY 2025: 261000
RX-2008B | Rail | Rail-Highway Grade Crossing Improvement | LS (SOUTH STREET) | ACWR CROSSING 722526U IN ABERDEEN. CONSTRUCT SAFETY IMPROVEMENTS. |  | MOORE | 8 | Sandhills MPO |  | Division 8 |  | RR | CONSTRUCTION | 1832000 | FY 2025: 604000; FY 2026: 1228000
RX-2008C | Rail | Rail-Highway Grade Crossing Improvement | SR 1925 (BILTMORE DRIVE) | CSX CROSSING 630856U IN ROCKINGHAM. CONSTRUCT SAFETY IMPROVEMENTS. |  | RICHMOND | 8 | Lumber River RPO |  | Division 8 |  | RR | CONSTRUCTION | 446000 | FY 2025: 283000; FY 2026: 163000
RX-2008D | Rail | Rail-Highway Grade Crossing Improvement | SR 1003 (ARABIA ROAD) | AR CROSSING 847348H IN DUNDARRACH. CONSTRUCT SAFETY IMPROVEMENTS. |  | HOKE | 8 | Lumber River RPO |  | Division 8 |  | RR | CONSTRUCTION | 345000 | FY 2025: 219000; FY 2026: 126000
RX-2008E | Rail | Rail-Highway Grade Crossing Improvement | US 1 BUSINESS (CARTHAGE STREET / CHARLOTTE AVENUE) | ATW CROSSING 721059F IN SANFORD. CONSTRUCT SAFETY IMPROVEMENTS. |  | LEE | 8 | Central Pines RPO |  | Division 8 |  | RR | CONSTRUCTION | 450000 | FY 2025: 285000; FY 2026: 165000
RX-2008F | Rail | Rail-Highway Grade Crossing Improvement | SR 2502 (JULIAN AIRPORT ROAD) | NORFOLK SOUTHERN CROSSING 720943W IN LIBERTY. CONSTRUCT SAFETY IMPROVEMENTS. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Division 8 |  | RR | CONSTRUCTION | 411000 | FY 2026: 261000; FY 2027: 150000
RX-2009 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 9
RX-2009A | Rail | Rail-Highway Grade Crossing Improvement | LS (FIRST STREET) | WSS CROSSING 849955C IN DENTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Division 9 |  | RR | CONSTRUCTION | 303000 | FY 2025: 217000; FY 2026: 86000
RX-2009B | Rail | Rail-Highway Grade Crossing Improvement | SR 2385 (WALKERTOWN-GUTHRIE ROAD) | NORFOLK SOUTHERN CROSSING 722063Y IN WALKERTOWN. CONSTRUCT SAFETY IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | RR | CONSTRUCTION | 411000 | FY 2025: 264000; FY 2026: 147000
RX-2009C | Rail | Rail-Highway Grade Crossing Improvement | SR 2381 (WILLSTON ROAD) | NORFOLK SOUTHERN CROSSING 470210K IN WALKERTOWN. CONSTRUCT SAFETY IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | RR | CONSTRUCTION | 601000 | FY 2026: 344000; FY 2027: 257000
RX-2009D | Rail | Rail-Highway Grade Crossing Improvement | SR 1686 (SHATTALON DRIVE) | NORFOLK SOUTHERN CROSSING 722024H IN WINSTON-SALEM. CONSTRUCT SAFETY IMPROVEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | RR | CONSTRUCTION | 492000 | FY 2027: 282000; FY 2028: 210000
RX-2010 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 10
RX-2010A | Rail | Rail-Highway Grade Crossing Improvement | SR 3522 (WEDDINGTON ROAD) | CSX CROSSING 631587H NEAR MONROE. CONSTRUCT SAFETY IMPROVEMENTS. |  | UNION | 10 | Charlotte Regional TPO | UNDER CONSTRUCTION. | Division 10 |  | RR | CONSTRUCTION | 800000
RX-2010B | Rail | Rail-Highway Grade Crossing Improvement | SR 1714 (STANBACK FERRY ICE PLANT ROAD) | CSX CROSSING 631750C NEAR WADESBORO. CONSTRUCT SAFETY IMPROVEMENTS. |  | ANSON | 10 | Rocky River RPO | UNDER CONSTRUCTION. | Division 10 |  | RR | CONSTRUCTION | 800000
RX-2010C | Rail | Rail-Highway Grade Crossing Improvement | SR 1008 (INDIAN TRAIL ROAD) | CSX CROSSING 631928Y IN INDIAN TRAIL. CONSTRUCT SAFETY IMPROVEMENTS. |  | UNION | 10 | Charlotte Regional TPO |  | Division 10 |  | RR | CONSTRUCTION | 388000 | FY 2026: 252000; FY 2027: 136000
RX-2010D | Rail | Rail-Highway Grade Crossing Improvement | PECAN AVENUE | CSX CROSSING 631391N IN CHARLOTTE. CONSTRUCT SAFETY IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | RR | CONSTRUCTION | 388000 | FY 2026: 252000; FY 2027: 136000
RX-2010E | Rail | Rail-Highway Grade Crossing Improvement | INDUSTRIAL DRIVE | NSR CROSSING 716055T IN PINEVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | RR | CONSTRUCTION | 451000 | FY 2027: 293000; FY 2028: 158000
RX-2011 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 11
RX-2012 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 12
RX-2012A | Rail | Rail-Highway Grade Crossing Improvement | LINBERGER STREET | CSX CROSSING 631872G IN SHELBY. CONSTRUCT SAFETY IMPROVEMENTS. |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | RR | CONSTRUCTION | 474000 | FY 2025: 292000; FY 2026: 182000
RX-2012B | Rail | Rail-Highway Grade Crossing Improvement | WALL STREET | NSR CROSSING 729686G IN STATESVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | RR | CONSTRUCTION | 474000 | FY 2025: 292000; FY 2026: 182000
RX-2012C | Rail | Rail-Highway Grade Crossing Improvement | CENTER STREET | NSR CROSSING 729571M IN HICKORY. CONSTRUCT SAFETY IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | RR | CONSTRUCTION | 492000 | FY 2025: 267000; FY 2026: 225000
RX-2012D | Rail | Rail-Highway Grade Crossing Improvement | OPAL STREET | NSR CROSSING 729684T IN STATESVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | RR | CONSTRUCTION | 474000 | FY 2025: 292000; FY 2026: 182000
RX-2012E | Rail | Rail-Highway Grade Crossing Improvement | SR 2263 (MARGRACE ROAD) | NSR CROSSING 716273A IN KINGS MOUNTAIN. CONSTRUCT SAFETY IMPROVEMENTS. |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | RR | CONSTRUCTION | 555000 | FY 2026: 301000; FY 2027: 254000
RX-2012F | Rail | Rail-Highway Grade Crossing Improvement | SR 1358 (FOURTH STREET SOUTHWEST) | NSR CROSSING 729568E IN HICKORY. CONSTRUCT SAFETY IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | RR | CONSTRUCTION | 492000 | FY 2026: 267000; FY 2027: 225000
RX-2012G | Rail | Rail-Highway Grade Crossing Improvement | SR 1735 (RANKIN AVENUE/ MOUNT OLIVE CHURCH ROAD) | NSR CROSSING 729612P IN NEWTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | CATAWBA | 12 | Greater Hickory MPO |  | Division 12 |  | RR | CONSTRUCTION | 492000 | FY 2027: 267000; FY 2028: 225000
RX-2012H | Rail | Rail-Highway Grade Crossing Improvement | SR 2412 (LITTLE MOUNTAIN ROAD) | NSR CROSSING 729966J IN GASTONIA. CONSTRUCT SAFETY IMPROVEMENTS. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | RR | CONSTRUCTION | 556000 | FY 2027: 302000; FY 2028: 254000
RX-2013 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 13
RX-2013A | Rail | Rail-Highway Grade Crossing Improvement | SR 1319 (JOHNSTON BOULEVARD) | BLU CROSSING 720399N IN ASHEVILLE. CONSTRUCT SAFETY IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | RR | CONSTRUCTION | 294000 | FY 2025: 141000; FY 2026: 153000
RX-2013B | Rail | Rail-Highway Grade Crossing Improvement | NC 9 (BROADWAY STREET) | NSR CROSSING 726262P IN BLACK MOUNTAIN. CONSTRUCT SAFETY IMPROVEMENTS. |  | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | RR | CONSTRUCTION | 492000 | FY 2025: 214000; FY 2026: 278000
RX-2013C | Rail | Rail-Highway Grade Crossing Improvement | HOGAN STREET | NSR CROSSING 729506G IN MORGANTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | BURKE | 13 | Greater Hickory MPO |  | Division 13 |  | RR | CONSTRUCTION | 451000 | FY 2026: 196000; FY 2027: 255000
RX-2014 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 14
RX-2014A | Rail | Rail-Highway Grade Crossing Improvement | NC 215 (BLACKWELL DRIVE) | BLU CROSSING 720349K IN CANTON. CONSTRUCT SAFETY IMPROVEMENTS. |  | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 345000 | FY 2026: 192000; FY 2027: 153000
RX-2100 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | PASSENGER RAIL CROSSING SAFETY IMPROVEMENT INVENTORY PROGRAM |  | STATEWIDE | 99 | STATEWIDE PROJECT | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY | Division 99 |  | RR | ENGINEERING | 2500000 | FY 2025: 500000
RX-2401 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1
RX-2401A | Rail | Rail-Highway Grade Crossing Improvement | SR 1101 (MAIN STREET) | NCVA CROSSING 629828U IN AHOSKIE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | HERTFORD | 1 | Peanut Belt RPO |  | Division 1 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2402 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2
RX-2402A | Rail | Rail-Highway Grade Crossing Improvement | US 258 BUSINESS (MAIN STREET) | CLNA CROSSING 465540F IN FARMVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | PITT | 2 | Mid-East RPO |  | Division 2 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2402B | Rail | Rail-Highway Grade Crossing Improvement | SR 1139 (WILSON STREET / MOYE-TURNAGE ROAD) | CLNA CROSSING 465535J IN FARMVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | PITT | 2 | Mid-East RPO |  | Division 2 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2402C | Rail | Rail-Highway Grade Crossing Improvement | US 264 (MARLBORO ROAD) | CLNA CROSSING 465544H IN FARMVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | PITT | 2 | Mid-East RPO |  | Division 2 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2403 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3
RX-2404 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, WAYNE, WILSON, HALIFAX, NASH | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2404A | Rail | Rail-Highway Grade Crossing Improvement | NC 58 | CLNA CROSSING 465577V IN STANTONSBURG. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2404B | Rail | Rail-Highway Grade Crossing Improvement | SR 1607 (CHARLESTON STREET) | CLNA CROSSING 465596A IN WILSON. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2404C | Rail | Rail-Highway Grade Crossing Improvement | TARBORO STREET ANNEX | CLNA CROSSING 465604P IN WILSON. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | WILSON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2405 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2406 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6
RX-2406A | Rail | Rail-Highway Grade Crossing Improvement | SR 1305 (SANDY BLUFF ROAD) | RJCS CROSSING 629312A IN TABOR CITY. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | COLUMBUS | 6 | Cape Fear RPO |  | Division 6 |  | RR | CONSTRUCTION | 425000 | FY 2026: 425000
RX-2406B | Rail | Rail-Highway Grade Crossing Improvement | US 401 | RFCC CROSSING 465843P IN ANGIER. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | HARNETT | 6 | Capital Area MPO |  | Division 6 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2406C | Rail | Rail-Highway Grade Crossing Improvement | SR 2311 (GILLESPIE STREET) | AR CROSSING 847218L IN FAYETTEVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2406D | Rail | Rail-Highway Grade Crossing Improvement | WINSLOW | AR CROSSING 847215R IN FAYETTEVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2407 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2408 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Sandhills MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2408A | Rail | Rail-Highway Grade Crossing Improvement | US 220 ALT (MAIN STREET) | IMPROVEMENTS TO ACWR CROSSING 466027X IN STAR. |  | MONTGOMERY | 8 | Piedmont Triad RPO |  | Division 8 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2408B | Rail | Rail-Highway Grade Crossing Improvement | ELDORADO STREET | IMPROVEMENTS TO ACWR CROSSING 728934A IN TROY. |  | MONTGOMERY | 8 | Piedmont Triad RPO |  | Division 8 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2409 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2409A | Rail | Rail-Highway Grade Crossing Improvement | SR 1101 (WILDLIFE RECREATION AREA ACCESS ROAD) | IMPROVEMENTS TO WSS CROSSING 849835L IN SOUTHMONT. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Division 9 |  | RR | CONSTRUCTION | 475000 | FY 2026: 475000
RX-2410 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2410A | Rail | Rail-Highway Grade Crossing Improvement | OLD CHARLOTTE HIGHWAY | WSS CROSSING 849910V IN ALBEMARLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | STANLY | 10 | Rocky River RPO |  | Division 10 |  | RR | CONSTRUCTION | 450000 | FY 2026: 450000
RX-2410B | Rail | Rail-Highway Grade Crossing Improvement | SR 2940 (EASTWAY DRIVE) | ACWR CROSSING 726797N IN CHARLOTTE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2410C | Rail | Rail-Highway Grade Crossing Improvement | SR 2805 (HARRISBURG HIGHWAY) | ACWR CROSSING 726808Y IN CHARLOTTE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2410D | Rail | Rail-Highway Grade Crossing Improvement | TIPPERARY PLACE | ACWR CROSSING 726798V IN CHARLOTTE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | MECKLENBURG | 10 | Charlotte Regional TPO |  | Division 10 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2411 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2411A | Rail | Rail-Highway Grade Crossing Improvement | US 52 BYPASS (ANDY GRIFFITH PARKWAY) | YVRR CROSSING 721996Y IN MOUNT AIRY. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | SURRY | 11 | Northwest Piedmont RPO |  | Division 11 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2412 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2412A | Rail | Rail-Highway Grade Crossing Improvement | SR 1639 (MEACHAM ROAD) | ARC CROSSING 865740U IN STATESVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | IREDELL | 12 | Charlotte Regional TPO |  | Division 12 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2413 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2413A | Rail | Rail-Highway Grade Crossing Improvement | BEAR CREEK ROAD | BLU CROSSING 720397A IN ASHEVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2413B | Rail | Rail-Highway Grade Crossing Improvement | SR 3541 (BUCK SHOALS ROAD) | BLU CROSSING 720637E IN ASHEVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2413C | Rail | Rail-Highway Grade Crossing Improvement | SR 1128 (LINDSEY ROAD) | BLU CROSSING 720381D IN CANDLER. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | BUNCOMBE | 13 | French Broad River MPO |  | Division 13 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2414 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2414A | Rail | Rail-Highway Grade Crossing Improvement | FIFTH AVENUE | BLU CROSSING 720654V IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2414B | Rail | Rail-Highway Grade Crossing Improvement | SR 1633 (INDUSTRIAL PARK ROAD) | BLU CROSSING 729533D IN BALFOUR. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2414C | Rail | Rail-Highway Grade Crossing Improvement | RAY AVENUE | BLU CROSSING 729542C IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. | 0.5 | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2027: 400000
RX-2414D | Rail | Rail-Highway Grade Crossing Improvement | NC 215 (BLACKWELL DRIVE) | BLU CROSSING 720349K IN CANTON. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 345000 | FY 2025: 192000; FY 2026: 153000
RX-2414E | Rail | Rail-Highway Grade Crossing Improvement | SEVENTH AVENUE | BLU CROSSING 720651A IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2414F | Rail | Rail-Highway Grade Crossing Improvement | SR 1176 (WHITTIER DEPOT ROAD) | GSM CROSSING 720218G IN WHITTIER. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | SWAIN | 14 | Southwestern RPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2414G | Rail | Rail-Highway Grade Crossing Improvement | SR 1527 (JONES COVE ROAD) | BLU CROSSING 720335C IN CLYDE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2414H | Rail | Rail-Highway Grade Crossing Improvement | SR 1503 (MAIN STREET) | BLU CROSSING 729541V IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2414I | Rail | Rail-Highway Grade Crossing Improvement | SR 1695 (NAPLES ROAD) | BLU CROSSING 720650T IN NAPLES. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2414J | Rail | Rail-Highway Grade Crossing Improvement | FOURTH AVENUE | BLU CROSSING 720655C IN HENDERSONVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | HENDERSON | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2414K | Rail | Rail-Highway Grade Crossing Improvement | HAZELWOOD AVENUE | BLU CROSSING 720305K IN WAYNESVILLE. IMPROVE HIGHWAY-RAIL GRADE CROSSING SAFETY. |  | HAYWOOD | 14 | French Broad River MPO |  | Division 14 |  | RR | CONSTRUCTION | 400000 | FY 2026: 400000
RX-2601 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. |  | BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | 1 | Albemarle RPO, Peanut Belt RPO, Mid-East RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 1
RX-2602 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. |  | BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | 2 | Down East RPO, Eastern Carolina RPO, Greenville Urban Area MPO, Mid-East RPO, New Bern Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 2
RX-2603 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. |  | DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | 3 | Cape Fear RPO, Eastern Carolina RPO, Mid-Carolina RPO, Wilmington Urban Area MPO, Down East RPO, Jacksonville Urban Area MPO, Grand Strand Area Transportation Study | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 3
RX-2604 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. |  | EDGECOMBE, JOHNSTON, WAYNE, WILSON, HALIFAX, NASH | 4 | Upper Coastal Plain RPO, Eastern Carolina RPO, Goldsboro Urban Area MPO, Peanut Belt RPO, Rocky Mount Urban Area MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2605 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. |  | DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | 5 | Kerr-Tar RPO, Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2606 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. |  | BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | 6 | Mid-Carolina RPO, Fayetteville Area MPO, Cape Fear RPO, Lumber River RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED. | Division 6
RX-2607 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. |  | ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | 7 | Piedmont Triad RPO, Burlington-Graham MPO, Durham-Chapel Hill-Carrboro MPO, Greensboro Urban Area MPO, High Point Urban Area MPO, Central Pines RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2608 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. |  | CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | 8 | Lumber River RPO, Central Pines RPO, Piedmont Triad RPO, High Point Urban Area MPO, Durham-Chapel Hill-Carrboro MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2609 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. |  | DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | 9 | Northwest Piedmont RPO, Winston-Salem Area TPO, High Point Urban Area MPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2610 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. |  | ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | 10 | Rocky River RPO, Charlotte Regional TPO, Cabarrus-Rowan MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2611 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. |  | CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | 11 | High Country RPO, Northwest Piedmont RPO, Greater Hickory MPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2612 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. |  | ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2613 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. |  | BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-2614 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. |  | CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE PROGRAMMED IN THE FUTURE AS NEEDED.
RX-9999 | Rail | Rail-Highway Grade Crossing Improvement | VARIOUS | RAILWAY-HIGHWAY CROSSINGS PROGRAM - UNPROGRAMMED BALANCE |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | RR | CONSTRUCTION | 85008000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000 | 7084000
SM-6215 | Highway | Safety | VARIOUS | SCHOOL TRAFFIC ANALYSIS FOR NEW, RELOCATED AND EXPANDING SCHOOLS. |  | STATEWIDE | 99 | STATEWIDE PROJECT
SM-6215DIV | Highway | Safety | VARIOUS | SCHOOL TRAFFIC ANALYSIS FOR NEW, RELOCATED AND EXPANDING SCHOOLS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Division 99 |  | T | ENGINEERING | 1800000 | FY 2025: 300000; FY 2026: 300000; FY 2027: 300000; FY 2028: 300000; FY 2029: 300000
SM-6215REG | Highway | Safety | VARIOUS | SCHOOL TRAFFIC ANALYSIS FOR NEW, RELOCATED AND EXPANDING SCHOOLS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Region SW |  | T | ENGINEERING | 1800000 | FY 2025: 300000; FY 2026: 300000; FY 2027: 300000; FY 2028: 300000; FY 2029: 300000
SM-6215SW | Highway | Safety | VARIOUS | SCHOOL TRAFFIC ANALYSIS FOR NEW, RELOCATED AND EXPANDING SCHOOLS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Statewide Mobility |  | T | ENGINEERING | 2400000 | FY 2025: 400000; FY 2026: 400000; FY 2027: 400000; FY 2028: 400000; FY 2029: 400000
SR-5001 | Bike & Ped | Other | VARIOUS | SAFE ROUTES TO SCHOOL PROGRAM. PROJECTS TO IMPROVE SAFETY, REDUCE TRAFFIC, FUEL CONSUMPTION AND AIR POLLUTION IN VICINITY OF SCHOOLS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | IN PROGRESS - $200,800 IN STPDA FUNDS ALLOCATED TO SR-5001C | Division 99
TA-4710 | Public Transportation (Transit) | Capital (Non-STI) | CATS | REPLACEMENT BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL PROGRAM | Public Transit |  | S | CAPITAL | 2726000
TA-4710 | Public Transportation (Transit) | Capital (Non-STI) | CATS | REPLACEMENT BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL PROGRAM | Public Transit |  | L | CAPITAL | 2726000
TA-4710 | Public Transportation (Transit) | Capital (Non-STI) | CATS | REPLACEMENT BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL PROGRAM | Public Transit |  | 5339 | CAPITAL | 6300000
TA-4710 | Public Transportation (Transit) | Capital (Non-STI) | CATS | REPLACEMENT BUS |  | MECKLENBURG | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL PROGRAM | Public Transit |  | 5307 | CAPITAL | 15500000
TA-4711 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 1971000 | FY 2025: 211000
TA-4711 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1971000 | FY 2025: 211000
TA-4711 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 25831000 | FY 2025: 1686000
TA-4726 | Public Transportation (Transit) | Capital (Non-STI) | CHAPEL HILL TRANSIT | REPLACEMENT BUSES |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 1936000
TA-4726 | Public Transportation (Transit) | Capital (Non-STI) | CHAPEL HILL TRANSIT | REPLACEMENT BUSES |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1936000
TA-4726 | Public Transportation (Transit) | Capital (Non-STI) | CHAPEL HILL TRANSIT | REPLACEMENT BUSES |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 9956000
TA-4726 | Public Transportation (Transit) | Capital (Non-STI) | CHAPEL HILL TRANSIT | REPLACEMENT BUSES |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 37313000
TA-4726A | Public Transportation (Transit) | Capital (Non-STI) | CHAPEL HILL TRANSIT | 3 REPLACEMENT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY CHAPEL HILL TRANSIT | Division 7
TA-4743A | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 36000
TA-4743A | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 40000
TA-4743A | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 6224000
TA-4743B | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 267000
TA-4743B | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 630000
TA-4743B | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 3526000
TA-4743B | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 348000
TA-4748 | Public Transportation (Transit) | Capital (Non-STI) | CHAPEL HILL TRANSIT | REPLACEMENT - PARATRANSIT VEHICLE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4421000
TA-4767 | Public Transportation (Transit) | Capital (Non-STI) | GTA | REPLACEMENT PARATRANSIT BUSES |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | L | CAPITAL | 813000 | FY 2025: 104000; FY 2026: 104000; FY 2027: 104000; FY 2028: 104000
TA-4767 | Public Transportation (Transit) | Capital (Non-STI) | GTA | REPLACEMENT PARATRANSIT BUSES |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | 5309 | CAPITAL | 4598000 | FY 2025: 588000; FY 2026: 588000; FY 2027: 588000; FY 2028: 588000
TA-4771 | Public Transportation (Transit) | Capital (Non-STI) | GTA | CLEAN DIESEL REPLACEMENT BUSES |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | CMAQ | CAPITAL | 5466000
TA-4771 | Public Transportation (Transit) | Capital (Non-STI) | GTA | CLEAN DIESEL REPLACEMENT BUSES |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 1678000
TA-4771 | Public Transportation (Transit) | Capital (Non-STI) | GTA | CLEAN DIESEL REPLACEMENT BUSES |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1768000
TA-4774A |  |  | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTATIVE MAINTENANCE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L(M) | OPERATIONS | 375000 | FY 2025: 125000; FY 2026: 125000
TA-4774A |  |  | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTATIVE MAINTENANCE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5307 | OPERATIONS | 1500000 | FY 2025: 500000; FY 2026: 500000
TA-4818A | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L(M) | CAPITAL | 192000
TA-4818A | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5339 | CAPITAL | 269000
TA-4818A | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 6949000
TA-4818B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | S | CAPITAL | 96000
TA-4818B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | CAPITAL | 583000
TA-4818B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | CAPITAL | 96000
TA-4818B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | 5307 | CAPITAL | 2333000
TA-4818B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | 5307 | CAPITAL | 5337000
TA-4903 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | REPLACEMENT BUS AND BUS FACILITIES |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 4330000
TA-4903 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | REPLACEMENT BUS AND BUS FACILITIES |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5339 | CAPITAL | 12087000
TA-4903A | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | CMAQ | CAPITAL | 8100000
TA-4903A | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | S | CAPITAL | 684000
TA-4903A | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 688000
TA-4903A | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1980000
TA-4923 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | REPLACEMENT BUS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY | Division 5 |  | L | CAPITAL | 166000
TA-4923 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | REPLACEMENT BUS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY | Division 5 |  | 5307 | CAPITAL | 4332000
TA-4923 | Public Transportation (Transit) | Capital (Non-STI) | GODURHAM | REPLACEMENT BUS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY | Division 5 |  | 5339 | CAPITAL | 1686000
TA-4928 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | S | CAPITAL | 72000
TA-4928 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | CAPITAL | 240000 | FY 2025: 84000
TA-4928 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5307 | CAPITAL | 1614000 | FY 2025: 336000
TA-4929 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ALEXANDER |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | S | CAPITAL | 90000
TA-4929 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ALEXANDER |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | CAPITAL | 319000
TA-4929 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ALEXANDER |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | CAPITAL | 1864000
TA-4943 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | S | CAPITAL | 176000 | FY 2025: 16000; FY 2026: 16000; FY 2027: 16000
TA-4943 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 176000 | FY 2025: 16000; FY 2026: 16000; FY 2027: 16000
TA-4943 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 2728000 | FY 2025: 125000; FY 2026: 125000; FY 2027: 125000
TA-4944 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | REPLACEMENT BUS - FIXED ROUTE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 566000 | FY 2025: 63000; FY 2026: 63000; FY 2027: 63000
TA-4944 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | REPLACEMENT BUS - FIXED ROUTE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 3884000 | FY 2025: 250000; FY 2026: 250000; FY 2027: 250000
TA-4948A | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 609000
TA-4948A | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 672000
TA-4948A | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 6961000
TA-4960 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 405000 | FY 2025: 58000
TA-4960 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 405000 | FY 2025: 58000
TA-4960 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 5561000 | FY 2025: 460000
TA-4979 | Public Transportation (Transit) | Capital (Non-STI) | CHAPEL HILL TRANSIT | REPLACEMENT VAN |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4061000
TA-5019A | Public Transportation (Transit) | Capital (Non-STI) | CHAPEL HILL TRANSIT | PARATRANSIT VEHICLES, BUS REFURBISHMENT, AND BUS SHELTERS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY CHAPEL HILL TRANSIT | Division 5
TA-5116 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | GORALEIGH PARK AND RIDE AT POOLE ROAD. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 455000
TA-5123A | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 270000
TA-5123A | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 946000
TA-5123A | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 15488000
TA-5123A | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | REPLACEMENT BUS AND ROLLING CAPITAL. |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 2702000
TA-5123B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | EXPANSION BUS |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 540000
TA-5123B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | EXPANSION BUS |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 540000
TA-5123B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | EXPANSION BUS |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 18466000
TA-5128A | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - CAPITAL |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 850000
TA-5128A | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - CAPITAL |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | CAPITAL | 3400000
TA-5128B | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - OPERATING |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1305000
TA-5128B | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - OPERATING |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | OPERATIONS | 1305000
TA-5128C | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | ADMINISTRATION OF 5310 PROGRAM |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | ADMINISTRATIVE | 340000
TA-5130A | Public Transportation (Transit) | Capital (Non-STI) | CONCORD KANNAPOLIS AREA TRANSIT | TO SUPPORT THE PURCHASE OF ROUTINE CAPITAL: BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, VEHICLES ETC USING SECTION 5339 FUNDS AT A FEDERAL SHARE OF $200,000 AND LOCAL SHARE OF $50,000. |  | CABARRUS, ROWAN | 9, 10 |  |  | Public Transit |  | L | CAPITAL | 200000
TA-5130A | Public Transportation (Transit) | Capital (Non-STI) | CONCORD KANNAPOLIS AREA TRANSIT | TO SUPPORT THE PURCHASE OF ROUTINE CAPITAL: BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, VEHICLES ETC USING SECTION 5339 FUNDS AT A FEDERAL SHARE OF $200,000 AND LOCAL SHARE OF $50,000. |  | CABARRUS, ROWAN | 9, 10 |  |  | Public Transit |  | 5339 | CAPITAL | 800000
TA-5130B | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | 5339 BUS AND BUS FACILITIES - EXPANSION VEHICLES |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 726000
TA-5130B | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT / CONCORD | 5339 BUS AND BUS FACILITIES - EXPANSION VEHICLES |  | CABARRUS | 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 2900000
TA-5139 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (NON-TRADITIONAL) |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 224000
TA-5139 | Public Transportation (Transit) | Capital (Non-STI) | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (NON-TRADITIONAL) |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5310 | CAPITAL | 897000
TA-5140 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | BUS REPLACEMENT |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 2225000
TA-5140 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | BUS REPLACEMENT |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 2225000
TA-5140 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | BUS REPLACEMENT |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 15250000
TA-5165 | Public Transportation (Transit) | Capital (Non-STI) | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | TA-5165 RURAL VEHICLE REPLACEMENT. |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 207000
TA-5165 | Public Transportation (Transit) | Capital (Non-STI) | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | TA-5165 RURAL VEHICLE REPLACEMENT. |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1166000
TA-5173 | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT/ CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Public Transit |  | S | CAPITAL | 850000
TA-5173 | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT/ CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Public Transit |  | L | CAPITAL | 850000
TA-5173 | Public Transportation (Transit) | Capital (Non-STI) | RIDER TRANSIT/ CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Public Transit |  | 5307 | CAPITAL | 6800000
TA-5181 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF SALISBURY | REPLACMENT BUSES |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 366000
TA-5181 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF SALISBURY | REPLACMENT BUSES |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1647000
TA-5181 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF SALISBURY | REPLACMENT BUSES |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 13176000
TA-5182 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF SALISBURY | EXPANSION VEHICLE (ADA PARATRANSIT, ADMINISTRATION) |  | ROWAN | 9 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 560000
TA-5182 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF SALISBURY | EXPANSION VEHICLE (ADA PARATRANSIT, ADMINISTRATION) |  | ROWAN | 9 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 2240000
TA-5185 | Public Transportation (Transit) | Capital (Non-STI) | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE |  | GASTON, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | T | CAPITAL | 6000
TA-5185 | Public Transportation (Transit) | Capital (Non-STI) | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE |  | GASTON, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | L | CAPITAL | 6000
TA-5185 | Public Transportation (Transit) | Capital (Non-STI) | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE |  | GASTON, LINCOLN | 12 | Gaston-Cleveland-Lincoln MPO |  | Division 12 |  | 5310 | CAPITAL | 50000
TA-5186 | Public Transportation (Transit) | Capital (Non-STI) | GO RALEIGH | SIX EXPANSION BUSES FOR ADDING ROUTE EXPANSION SERVICE. |  | WAKE | 5 | Capital Area MPO | ACQUISITION IN PROGRESS BY GO RALEIGH | Division 5
TA-5202 | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | ADA EXPANSION BUS |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 2208000
TA-5202 | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | ADA EXPANSION BUS |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 720000
TA-5202 | Public Transportation (Transit) | Capital (Non-STI) | CAPITAL AREA TRANSIT | ADA EXPANSION BUS |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 1200000
TA-5221 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 23000
TA-5221 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 326000
TA-5221 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 972000
TA-5222 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 166000
TA-5222 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 302000
TA-5222 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5309 | CAPITAL | 542000
TA-5222 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 1540000
TA-5223 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | S | CAPITAL | 607000
TA-5223 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 607000
TA-5223 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5339 | CAPITAL | 4856000
TA-5224 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT TROLLEY |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5339 | CAPITAL | 700000
TA-5229 | Public Transportation (Transit) | Capital (Non-STI) | APPLE COUNTRY TRANSIT | REPLACEMENT TRANSIT VEHICLE ACQUISITION |  | HENDERSON | 14 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 152000
TA-5229 | Public Transportation (Transit) | Capital (Non-STI) | APPLE COUNTRY TRANSIT | REPLACEMENT TRANSIT VEHICLE ACQUISITION |  | HENDERSON | 14 | French Broad River MPO |  | Public Transit |  | 5307 | CAPITAL | 606000
TA-6149 | Public Transportation (Transit) | Capital (Non-STI) | UNION COUNTY | 5307 FUNDS TO REH/REN EQUIPMENT FFY20-21 (20-SU-089) |  | UNION | 10 | Charlotte Regional TPO | ADD FUNDING TO FY20 | Public Transit |  | L | CAPITAL | 3000
TA-6149 | Public Transportation (Transit) | Capital (Non-STI) | UNION COUNTY | 5307 FUNDS TO REH/REN EQUIPMENT FFY20-21 (20-SU-089) |  | UNION | 10 | Charlotte Regional TPO | ADD FUNDING TO FY20 | Public Transit |  | 5307 | CAPITAL | 14000
TA-6322 | Public Transportation (Transit) | Capital (Non-STI) | LINK TRANSIT | IMPROVEMENTS, BUS SHELTERS, CONSTRUCTION, ENGINEERING AND DESIGN. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 216000
TA-6322 | Public Transportation (Transit) | Capital (Non-STI) | LINK TRANSIT | IMPROVEMENTS, BUS SHELTERS, CONSTRUCTION, ENGINEERING AND DESIGN. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 865000
TA-6507 | Public Transportation (Transit) | Capital (Non-STI) | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 184000
TA-6507 | Public Transportation (Transit) | Capital (Non-STI) | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 161000
TA-6507 | Public Transportation (Transit) | Capital (Non-STI) | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | CAPITAL | 2589000
TA-6626 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | ART BUSES AND OTHER ROUTINE CAPITAL ITEMS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 363000
TA-6626 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | ART BUSES AND OTHER ROUTINE CAPITAL ITEMS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5339 | CAPITAL | 1451000
TA-6665 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5311 CAPITAL PROJECTS FOR RURAL AREAS |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | S | CAPITAL | 15850000
TA-6665 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5311 CAPITAL PROJECTS FOR RURAL AREAS |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | L | CAPITAL | 11200000
TA-6665 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5311 CAPITAL PROJECTS FOR RURAL AREAS |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5311 | CAPITAL | 69749000
TA-6666 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339 BUS AND BUS FACILITIES |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 6750000
TA-6668 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | PURCHASE EXPANSION VEHICLES FOR DRX ROUTE. |  | WAKE, DURHAM | 5 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN ACQUISITION | Region C
TA-6669 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | PURCHASE EXPANSION VEHICLES FOR CRX ROUTE. |  | WAKE, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | IN ACQUISITION | Region C, D
TA-6670 | Public Transportation (Transit) | Capital (Non-STI) | RANDOLPH- MONTGOMERY RESTORE | PURCHASE ADDITIONAL 20-FOOT LIGHT TRANSIT VEHICLES. |  | RANDOLPH | 8 | Piedmont Triad RPO | IN ACQUISITION | Region E
TA-6671 | Public Transportation (Transit) | Capital (Non-STI) | RANDOLPH- MONTGOMERY RESTORE | PURCHASE 20-FT LIGHT TRANSIT VEHICLES FOR SERVICE EXPANSION. |  | MONTGOMERY | 8 | Piedmont Triad RPO | IN ACQUISITION | Region E
TA-6672 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE 6 BUSES FOR THE UNIVERSITY TO CONCORD MILLS BUS ROUTE. |  | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS | Region E |  | T | CAPITAL | 300000
TA-6672 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE 6 BUSES FOR THE UNIVERSITY TO CONCORD MILLS BUS ROUTE. |  | MECKLENBURG, CABARRUS | 10 | Charlotte Regional TPO, Cabarrus-Rowan MPO | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS | Region E |  | O | CAPITAL | 2700000
TA-6673 | Public Transportation (Transit) | STI (Prioritization) | MECKLENBURG COUNTY | EXPAND PARATRANSIT FLEET BY PURCHASING ADDITIONAL BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS | Division 10 |  | T | CAPITAL | 250000
TA-6673 | Public Transportation (Transit) | STI (Prioritization) | MECKLENBURG COUNTY | EXPAND PARATRANSIT FLEET BY PURCHASING ADDITIONAL BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS | Division 10 |  | O | CAPITAL | 2250000
TA-6674 | Public Transportation (Transit) | Capital (Non-STI) | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. |  | ASHE | 11 | High Country RPO |  | Division 11 |  | T | CAPITAL | 8000
TA-6674 | Public Transportation (Transit) | Capital (Non-STI) | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. |  | ASHE | 11 | High Country RPO |  | Division 11 |  | L | CAPITAL | 8000
TA-6674 | Public Transportation (Transit) | Capital (Non-STI) | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. |  | ASHE | 11 | High Country RPO |  | Division 11 |  | 5311 | CAPITAL | 60000
TA-6679 | Public Transportation (Transit) | Capital (Non-STI) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE ONE EXPANSION 40-FT BUS. |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN ACQUISITION | Region D
TA-6681 | Public Transportation (Transit) | STI (Prioritization) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 |  | FORSYTH, SURRY | 9, 11 | Northwest Piedmont RPO, Winston-Salem Area TPO |  | Region D, F |  | T | CAPITAL | 47000
TA-6681 | Public Transportation (Transit) | STI (Prioritization) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 |  | FORSYTH, SURRY | 9, 11 | Northwest Piedmont RPO, Winston-Salem Area TPO |  | Region D, F |  | L | CAPITAL | 47000
TA-6681 | Public Transportation (Transit) | STI (Prioritization) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 |  | FORSYTH, SURRY | 9, 11 | Northwest Piedmont RPO, Winston-Salem Area TPO |  | Region D, F |  | FEDT | CAPITAL | 372000
TA-6682 | Public Transportation (Transit) | Capital (Non-STI) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | WINSTON-SALEM EXPRESS. PURCHASE ONE EXPANSION 40-FT BUS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Region D
TA-6685 | Public Transportation (Transit) | STI (Prioritization) | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | T | CONSTRUCTION | 49000 | FY 2026: 49000
TA-6685 | Public Transportation (Transit) | STI (Prioritization) | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | L | CONSTRUCTION | 49000 | FY 2026: 49000
TA-6685 | Public Transportation (Transit) | STI (Prioritization) | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Division 6 |  | FEDT | CONSTRUCTION | 392000 | FY 2026: 392000
TA-6690 | Public Transportation (Transit) | Capital (Non-STI) | REGIONAL TRANSPORTATION PIEDMONT AUTHORITY FOR | REPLACEMENT VEHICLES. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 91000 | FY 2025: 10000; FY 2026: 10000; FY 2027: 10000; FY 2028: 10000
TA-6690 | Public Transportation (Transit) | Capital (Non-STI) | REGIONAL TRANSPORTATION PIEDMONT AUTHORITY FOR | REPLACEMENT VEHICLES. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5339 | CAPITAL | 408000 | FY 2025: 40000; FY 2026: 40000; FY 2027: 40000; FY 2028: 40000
TA-6700 | Public Transportation (Transit) | Locally Selected | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADA |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 150000
TA-6700 | Public Transportation (Transit) | Locally Selected | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADA |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 30000
TA-6701 | Public Transportation (Transit) | Capital (Non-STI) | BUNCOMBE MOUNTAIN MOBILITY - | REPLACEMENT VANS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 110000
TA-6701 | Public Transportation (Transit) | Capital (Non-STI) | BUNCOMBE MOUNTAIN MOBILITY - | REPLACEMENT VANS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5307 | CAPITAL | 434000
TA-6703 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT LO-NO TRANSIT VEHICLE PURCHASE |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 5117000
TA-6703 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT LO-NO TRANSIT VEHICLE PURCHASE |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5339 | CAPITAL | 1453000
TA-6706 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE REGIONAL | INNOVATIVE COORDINATED ACCESS AND MOBILITY PILOT PROGRAM VEHICLES |  | MECKLENBURG | 10 | Charlotte Regional TPO | ADD PROJECT TA-6706 TO STIP FOR FY 20. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF CRTPO MPO | Public Transit |  | L | CAPITAL | 28000
TA-6706 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE REGIONAL | INNOVATIVE COORDINATED ACCESS AND MOBILITY PILOT PROGRAM VEHICLES |  | MECKLENBURG | 10 | Charlotte Regional TPO | ADD PROJECT TA-6706 TO STIP FOR FY 20. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF CRTPO MPO | Public Transit |  | 5310 | CAPITAL | 112000
TA-6707 | Public Transportation (Transit) | Capital (Non-STI) | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | PLANNING | 252000 | FY 2025: 84000; FY 2026: 84000
TA-6707 | Public Transportation (Transit) | Capital (Non-STI) | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5307 | PLANNING | 1008000 | FY 2025: 336000; FY 2026: 336000
TA-6707 | Public Transportation (Transit) | Capital (Non-STI) | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | CAPITAL | 588000 | FY 2025: 84000
TA-6707 | Public Transportation (Transit) | Capital (Non-STI) | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5307 | CAPITAL | 2352000 | FY 2025: 336000
TA-6711 | Public Transportation (Transit) | STI (Prioritization) | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. |  | VANCE | 5 | Kerr-Tar RPO |  | Region C |  | T | CAPITAL | 6000
TA-6711 | Public Transportation (Transit) | STI (Prioritization) | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. |  | VANCE | 5 | Kerr-Tar RPO |  | Region C |  | L | CAPITAL | 6000
TA-6711 | Public Transportation (Transit) | STI (Prioritization) | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. |  | VANCE | 5 | Kerr-Tar RPO |  | Region C |  | FEDT | CAPITAL | 44000
TA-6713 | Public Transportation (Transit) | STI (Prioritization) | ICATS INTERCOUNTY EXPRESS BUS | PURCHASE 3 OVER-THE-ROAD COACH BUSES AND 5 SETS OF BUS STOP SHELTERS TO EXPAND INTERCOUNTY SERVICE BETWEEN STATESVILLE, TROUTMAN, MOORESVILLE, AND CATS ROUTES BETWEEN HUNTERSVILLE AND CHARLOTTE. |  | IREDELL, MECKLENBURG | 10, 12 | Charlotte Regional TPO |  | Region E, F |  | T | CONSTRUCTION | 1000000
TA-6714 | Public Transportation (Transit) | Capital (Non-STI) | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT | Public Transit |  | CMAQ | CAPITAL | 416000
TA-6714 | Public Transportation (Transit) | Capital (Non-STI) | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT | Public Transit |  | CMAQ | CAPITAL | 1145000
TA-6714 | Public Transportation (Transit) | Capital (Non-STI) | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT | Public Transit |  | S | CAPITAL | 729000
TA-6714 | Public Transportation (Transit) | Capital (Non-STI) | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT | Public Transit |  | L | CAPITAL | 531000
TA-6714 | Public Transportation (Transit) | Capital (Non-STI) | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE |  | GUILFORD | 7 | Greensboro Urban Area MPO | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT | Public Transit |  | 5339 | CAPITAL | 3009000
TA-6717 | Public Transportation (Transit) | STI (Prioritization) | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. |  | CARTERET | 2 | Down East RPO |  | Division 2 |  | T | CONSTRUCTION | 7000
TA-6717 | Public Transportation (Transit) | STI (Prioritization) | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. |  | CARTERET | 2 | Down East RPO |  | Division 2 |  | L | CONSTRUCTION | 7000
TA-6717 | Public Transportation (Transit) | STI (Prioritization) | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. |  | CARTERET | 2 | Down East RPO |  | Division 2 |  | 5311 | CONSTRUCTION | 56000
TA-6718 | Public Transportation (Transit) | STI (Prioritization) | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. |  | CARTERET | 2 | Down East RPO |  | Division 2 |  | T | CONSTRUCTION | 7000
TA-6718 | Public Transportation (Transit) | STI (Prioritization) | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. |  | CARTERET | 2 | Down East RPO |  | Division 2 |  | L | CONSTRUCTION | 7000
TA-6718 | Public Transportation (Transit) | STI (Prioritization) | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. |  | CARTERET | 2 | Down East RPO |  | Division 2 |  | 5311 | CONSTRUCTION | 56000
TA-6719 | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | CHATHAM TRANSIT NETWORK. PURCHASE 3 NEW RAMP-EQIPPED MINIVANS. |  | CHATHAM | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO |  | Division 8 |  | T | CAPITAL | 127000
TA-6719 | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | CHATHAM TRANSIT NETWORK. PURCHASE 3 NEW RAMP-EQIPPED MINIVANS. |  | CHATHAM | 8 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO |  | Division 8 |  | L | CAPITAL | 14000
TA-6720 | Public Transportation (Transit) | STI (Prioritization) | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO, Capital Area MPO |  | Division 4 |  | T | CONSTRUCTION | 33000 | FY 2026: 33000
TA-6720 | Public Transportation (Transit) | STI (Prioritization) | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO, Capital Area MPO |  | Division 4 |  | L | CONSTRUCTION | 33000 | FY 2026: 33000
TA-6720 | Public Transportation (Transit) | STI (Prioritization) | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO, Capital Area MPO |  | Division 4 |  | 5311 | CONSTRUCTION | 264000 | FY 2026: 264000
TA-6721 | Public Transportation (Transit) | STI (Prioritization) | ORANGE PUBLIC TRANSIT | PURCHASE TWO (2) LIGHT TRANSIT VEHICLES |  | ORANGE | 7 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGANY | CAPITAL | 98000
TA-6721 | Public Transportation (Transit) | STI (Prioritization) | ORANGE PUBLIC TRANSIT | PURCHASE TWO (2) LIGHT TRANSIT VEHICLES |  | ORANGE | 7 | Central Pines RPO, Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CAPITAL | 11000
TA-6722 | Public Transportation (Transit) | STI (Prioritization) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE VEHICLES FOR VANPOOL FLEET EXPANSION. |  | FORSYTH, GUILFORD, RANDOLPH | 7, 8, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO, High Point Urban Area MPO |  | Division 7, 8, 9 |  | T | CONSTRUCTION | 90000
TA-6722 | Public Transportation (Transit) | STI (Prioritization) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE VEHICLES FOR VANPOOL FLEET EXPANSION. |  | FORSYTH, GUILFORD, RANDOLPH | 7, 8, 9 | Winston-Salem Area TPO, Greensboro Urban Area MPO, High Point Urban Area MPO |  | Division 7, 8, 9 |  | L | CONSTRUCTION | 10000
TA-6723 | Public Transportation (Transit) | STI (Prioritization) | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. |  | YANCEY | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | Division 13 |  | T | ENGINEERING | 140000
TA-6723 | Public Transportation (Transit) | STI (Prioritization) | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. |  | YANCEY | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | Division 13 |  | L | ENGINEERING | 15000
TA-6723 | Public Transportation (Transit) | STI (Prioritization) | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. |  | YANCEY | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | Division 13 |  | T | CONSTRUCTION | 90000
TA-6723 | Public Transportation (Transit) | STI (Prioritization) | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. |  | YANCEY | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | Division 13 |  | T | CONSTRUCTION | 2021000
TA-6723 | Public Transportation (Transit) | STI (Prioritization) | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. |  | YANCEY | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | Division 13 |  | L | CONSTRUCTION | 224000
TA-6723 | Public Transportation (Transit) | STI (Prioritization) | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. |  | YANCEY | 13 | High Country RPO | LOCAL FUNDING PROVIDED BY YANCEY COUNTY | Division 13 |  | L | CONSTRUCTION | 10000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | BGDA | ENGINEERING | 1121000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | T(M) | ENGINEERING | 238000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | L(M) | ENGINEERING | 151000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | CMAQ | RIGHT-OF-WAY | 290000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | BGDA | RIGHT-OF-WAY | 663000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | T(M) | RIGHT-OF-WAY | 104000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | T(M) | RIGHT-OF-WAY | 73000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | L(M) | RIGHT-OF-WAY | 98000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | L(M) | RIGHT-OF-WAY | 29000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | CMAQ | CONSTRUCTION | 7354000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | T(M) | CONSTRUCTION | 1560000
TA-6724 | Public Transportation (Transit) | STI (Prioritization) | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. |  | MECKLENBURG | 10 | Charlotte Regional TPO | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; T(M) IS HIGHWAY TRUST FUNDS | Division 10 |  | L(M) | CONSTRUCTION | 991000
TA-6729 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | CMAQ | CAPITAL | 400000
TA-6729 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 350000 | FY 2025: 150000
TA-6729 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1000000 | FY 2025: 600000
TA-6731 | Public Transportation (Transit) | Capital (Non-STI) | ORANGE PUBLIC TRANSIT | PURCHASE NEW BUS < 30'. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | FED | CAPITAL | 45000
TA-6731 | Public Transportation (Transit) | Capital (Non-STI) | ORANGE PUBLIC TRANSIT | PURCHASE NEW BUS < 30'. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | CAPITAL | 11000
TA-6732 | Public Transportation (Transit) | Capital (Non-STI) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | VEHICLE REPLACEMENT AND EXPANSION |  | GUILFORD | 7 | Greensboro Urban Area MPO | PROJECT ADDED AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | L | CONSTRUCTION | 1700000
TA-6732 | Public Transportation (Transit) | Capital (Non-STI) | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | VEHICLE REPLACEMENT AND EXPANSION |  | GUILFORD | 7 | Greensboro Urban Area MPO | PROJECT ADDED AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | 5339 | CONSTRUCTION | 6780000
TA-6733 | Public Transportation (Transit) | Planning | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | L | PLANNING | 50000
TA-6733 | Public Transportation (Transit) | Planning | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5307 | PLANNING | 200000
TA-6733 | Public Transportation (Transit) | Planning | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | S | CAPITAL | 70000
TA-6733 | Public Transportation (Transit) | Planning | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | L | CAPITAL | 276000
TA-6733 | Public Transportation (Transit) | Planning | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5309 | CAPITAL | 475000
TA-6733 | Public Transportation (Transit) | Planning | LINK TRANSIT | PLANNING FOR TRANSIT FACILITY FEASIBILITY STUDY AND SHORT RANGE TRANSIT PLAN. |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TA-6733 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5307 | CAPITAL | 1029000
TC-0003 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | CAPITAL | 137000
TC-0003 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | CAPITAL | 137000
TC-0003 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | CAPITAL | 1097000
TC-0005 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | CONSTRUCTION | 750000
TC-0005 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5339 | CONSTRUCTION | 3000000
TC-0006 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | CONSTRUCTION | 384000
TC-0006 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5339 | CONSTRUCTION | 1435000
TC-0007 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR CONSTRUCTION PROJECT |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | CAPITAL | 787000
TC-0007 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR CONSTRUCTION PROJECT |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5339 | CAPITAL | 3189000
TC-0008 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | CAPITAL | 3375000
TC-0008 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5339 | CAPITAL | 9950000
TC-0010 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | CONSTRUCTION | 2734000
TC-0010 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5339 | CONSTRUCTION | 10835000
TC-0011 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5339 | CONSTRUCTION | 719000
TC-0011 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | CAPITAL | 2298000
TC-0011 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5339 | CAPITAL | 6391000
TC-0012 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT TO PURCHASE ELECTRIC BUSES AND CHARGING STATIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | CAPITAL | 1398000
TC-0012 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5339(b) DISCRETIONARY GRANT TO PURCHASE ELECTRIC BUSES AND CHARGING STATIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5339 | CAPITAL | 5494000
TC-0013 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | MOBILITY FROM ALL GRANT OPPORTUNITY FROM THE FTA.5310 DISCRETIONARY GRANT AWARDED BY FTA. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | CAPITAL | 70000
TC-0013 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | MOBILITY FROM ALL GRANT OPPORTUNITY FROM THE FTA.5310 DISCRETIONARY GRANT AWARDED BY FTA. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5310 | CAPITAL | 280000
TC-0014 | Public Transportation (Transit) | Capital (Non-STI) | CATS | EXPANSION VANPOOL |  | MECKLENBURG | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND | Public Transit |  | S | CAPITAL | 17000
TC-0014 | Public Transportation (Transit) | Capital (Non-STI) | CATS | EXPANSION VANPOOL |  | MECKLENBURG | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND | Public Transit |  | L | CAPITAL | 17000
TC-0014 | Public Transportation (Transit) | Capital (Non-STI) | CATS | EXPANSION VANPOOL |  | MECKLENBURG | 10 | Charlotte Regional TPO | "L" REFLECTS CATS CAPITAL FUND | Public Transit |  | 5307 | CAPITAL | 140000
TC-0015 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | GORALEIGH CAPITAL PROJECTS (PASSENGER AMENITIES, PEDESTRIAN CONNECTIONS, FACILITY MAINTENANCE, UPGRADE AND UPKEEPS ETC) |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 1816000
TC-0015 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | GORALEIGH CAPITAL PROJECTS (PASSENGER AMENITIES, PEDESTRIAN CONNECTIONS, FACILITY MAINTENANCE, UPGRADE AND UPKEEPS ETC) |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 9106000
TC-0016 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | ENGINEERING | 55000
TC-0016 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 55000
TC-0016 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | RIGHT-OF-WAY | 6000
TC-0016 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | RIGHT-OF-WAY | 6000
TC-0016 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | CONSTRUCTION | 275000
TC-0016 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 275000
TC-0017 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | ENGINEERING | 65000
TC-0017 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 65000
TC-0017 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | RIGHT-OF-WAY | 7000
TC-0017 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | RIGHT-OF-WAY | 7000
TC-0017 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | CONSTRUCTION | 165000
TC-0017 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 165000
TC-0018 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL AND URBAN AREAS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | CAPITAL | 1026000
TC-0018 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL AND URBAN AREAS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | CAPITAL | 1118000
TC-0018 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL AND URBAN AREAS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5310 | CAPITAL | 5811000
TC-0019 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | CAPITAL | 1715000
TC-0019 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | CAPITAL | 1715000
TC-0019 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | CAPITAL | 13717000
TC-0020 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON FY 24 GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | CAPITAL | 65000
TC-0020 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON FY 24 GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | CAPITAL | 40000
TC-0020 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON FY 24 GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5309 | CAPITAL | 320000
TC-0021 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5339 STATEWIDE RURAL |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | BGDA | PLANNING | 273000
TC-0021 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5339 STATEWIDE RURAL |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | CAPITAL | 14025000
TC-0021 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5339 STATEWIDE RURAL |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | CAPITAL | 2667000
TC-0021 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5339 STATEWIDE RURAL |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5339 | CAPITAL | 26436000
TC-0022 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | CAPITAL | 188000
TC-0022 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | CAPITAL | 188000
TC-0022 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | ADTAP | CAPITAL | 1504000
TC-0023 | Public Transportation (Transit) | Capital (Non-STI) | SALISBURY TRANSIT ( CITY OF SALISBURY) | REPLACE FOUR TRANSIT BUSES THAT HAVE EXCEEDED THEIR USEFUL LIFE, AND REPLACE VEHICLE RELATED EQUIPMENT SUCH AS FARE BOXES, DESTINATION SIGNS, CAMERA SYSTEMS, AND AUTOMATED VOICE ANNUNCIATION SYSTEMS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Public Transit |  | L | CAPITAL | 720000 | FY 2025: 120000; FY 2026: 120000
TC-0023 | Public Transportation (Transit) | Capital (Non-STI) | SALISBURY TRANSIT ( CITY OF SALISBURY) | REPLACE FOUR TRANSIT BUSES THAT HAVE EXCEEDED THEIR USEFUL LIFE, AND REPLACE VEHICLE RELATED EQUIPMENT SUCH AS FARE BOXES, DESTINATION SIGNS, CAMERA SYSTEMS, AND AUTOMATED VOICE ANNUNCIATION SYSTEMS. |  | ROWAN | 9 | Cabarrus-Rowan MPO |  | Public Transit |  | 5339(b) | CAPITAL | 3840000 | FY 2025: 640000; FY 2026: 640000
TC-0024 | Public Transportation (Transit) | Capital (Non-STI) | CATS | CITY LYNX GOLD LINE - AMERICAN RESCUE PLAN SMALL STARTS |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | 5309 | CAPITAL | 11122000
TC-0025 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON-SALEM TRANSIT AUTHORITY | PURCHASE ONE LARGE HYBRID-DIESEL REPLACEMENT BUS AND ONE SMALL HYBRID-DIESEL REPLACEMENT BUS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | CAPITAL | 984000 | FY 2025: 984000
TC-0025 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON-SALEM TRANSIT AUTHORITY | PURCHASE ONE LARGE HYBRID-DIESEL REPLACEMENT BUS AND ONE SMALL HYBRID-DIESEL REPLACEMENT BUS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | CAPITAL | 246000 | FY 2025: 246000
TC-0026 | Public Transportation (Transit) | Capital (Non-STI) | NCDOT | FEDERAL AMERICAN RESCUE PLAN (ARP) FUNDS FOR CAPITAL |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | ARP | CAPITAL | 500000
TC-0027 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | BGDA | PLANNING | 339000
TC-0027 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | PLANNING | 85000
TC-0027 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 40000 | FY 2025: 20000
TC-0027 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5339 | CAPITAL | 100000 | FY 2025: 100000
TC-0027 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY (WAVE) | PASSANGER AMENITY UPGRADES (INSTALLATION OF TRANSIT SHELTERS AND BENCHES) STBGP- $339,000. TRANSIT AUTHORITY WILL INSTALL SHELTERS, LIGHTING AND LANDING PLATFORMS ALONG EXISTING ROUTES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5309 | CAPITAL | 100000
TC-0028 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | VEHICLES, BUS STOPS |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | CAPITAL | 40000 | FY 2025: 20000
TC-0028 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | VEHICLES, BUS STOPS |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5339 | CAPITAL | 200000 | FY 2025: 100000
TC-0031 | Public Transportation (Transit) | Capital (Non-STI) | INTEGRATED MOBILITY DIVISION | THE PROJECT WILL EXPAND ON-DEMAND TRANSIT SERVICES FOR UP TO 11 RURAL COMMUNITIES ACROSS NORTH CAROLINA. THIS PROJECT WILL EMPLOY TWO PRIMARY ON-DEMAND SERVICE MODELS: SOFTWARE AS A SERVICE (SAAS) AND TURNKEY, ALSO REFERRED TO AS TRANSPORTATION AS A SERVICE (TAAS). |  | WILSON, LEE, ROWAN, BRUNSWICK, NEW HANOVER, PENDER, JOHNSTON, ALAMANCE, ROCKINGHAM, McDOWELL, MONTGOMERY, EDGECOMBE, FRANKLIN, GRANVILLE, NASH, RANDOLPH, VANCE, WARREN | 3, 4, 5, 7, 8, 9, 13 | Wilmington Urban Area MPO, Upper Coastal Plain RPO, Piedmont Triad RPO, Greensboro Urban Area MPO, Winston-Salem Area TPO, Kerr-Tar RPO, Foothills RPO |  | Public Transit |  | S | CAPITAL | 10000000
TC-0031 | Public Transportation (Transit) | Capital (Non-STI) | INTEGRATED MOBILITY DIVISION | THE PROJECT WILL EXPAND ON-DEMAND TRANSIT SERVICES FOR UP TO 11 RURAL COMMUNITIES ACROSS NORTH CAROLINA. THIS PROJECT WILL EMPLOY TWO PRIMARY ON-DEMAND SERVICE MODELS: SOFTWARE AS A SERVICE (SAAS) AND TURNKEY, ALSO REFERRED TO AS TRANSPORTATION AS A SERVICE (TAAS). |  | WILSON, LEE, ROWAN, BRUNSWICK, NEW HANOVER, PENDER, JOHNSTON, ALAMANCE, ROCKINGHAM, McDOWELL, MONTGOMERY, EDGECOMBE, FRANKLIN, GRANVILLE, NASH, RANDOLPH, VANCE, WARREN | 3, 4, 5, 7, 8, 9, 13 | Wilmington Urban Area MPO, Upper Coastal Plain RPO, Piedmont Triad RPO, Greensboro Urban Area MPO, Winston-Salem Area TPO, Kerr-Tar RPO, Foothills RPO |  | Public Transit |  | L | CAPITAL | 5000000
TC-0031 | Public Transportation (Transit) | Capital (Non-STI) | INTEGRATED MOBILITY DIVISION | THE PROJECT WILL EXPAND ON-DEMAND TRANSIT SERVICES FOR UP TO 11 RURAL COMMUNITIES ACROSS NORTH CAROLINA. THIS PROJECT WILL EMPLOY TWO PRIMARY ON-DEMAND SERVICE MODELS: SOFTWARE AS A SERVICE (SAAS) AND TURNKEY, ALSO REFERRED TO AS TRANSPORTATION AS A SERVICE (TAAS). |  | WILSON, LEE, ROWAN, BRUNSWICK, NEW HANOVER, PENDER, JOHNSTON, ALAMANCE, ROCKINGHAM, McDOWELL, MONTGOMERY, EDGECOMBE, FRANKLIN, GRANVILLE, NASH, RANDOLPH, VANCE, WARREN | 3, 4, 5, 7, 8, 9, 13 | Wilmington Urban Area MPO, Upper Coastal Plain RPO, Piedmont Triad RPO, Greensboro Urban Area MPO, Winston-Salem Area TPO, Kerr-Tar RPO, Foothills RPO |  | Public Transit |  | RTAP | CAPITAL | 10400000
TC-0032 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | CAPITAL | 40000 | FY 2025: 20000
TC-0032 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5339 | CAPITAL | 200000 | FY 2025: 100000
TC-0033 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | TC-0033 - ROLLING STOCK |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | CAPITAL | 40000 | FY 2025: 20000
TC-0033 | Public Transportation (Transit) | Capital (Non-STI) | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | TC-0033 - ROLLING STOCK |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5309 | CAPITAL | 200000 | FY 2025: 100000
TC-0034 | Public Transportation (Transit) | Capital (Non-STI) | LINK TRANSIT | THIS FUNDING PROVIDES FOR THE DESIGN, ENGINEERING AND CONSTRUCTION OF TRANSIT MAINTENANCE FACILITY AND TRANSIT TRANSFER HUB TO SUPPORT THE LINK TRANSIT SYSTEM. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | S | CAPITAL | 160000 | FY 2025: 70000; FY 2026: 20000; FY 2027: 20000
TC-0034 | Public Transportation (Transit) | Capital (Non-STI) | LINK TRANSIT | THIS FUNDING PROVIDES FOR THE DESIGN, ENGINEERING AND CONSTRUCTION OF TRANSIT MAINTENANCE FACILITY AND TRANSIT TRANSFER HUB TO SUPPORT THE LINK TRANSIT SYSTEM. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 160000 | FY 2025: 70000; FY 2026: 20000; FY 2027: 20000
TC-0034 | Public Transportation (Transit) | Capital (Non-STI) | LINK TRANSIT | THIS FUNDING PROVIDES FOR THE DESIGN, ENGINEERING AND CONSTRUCTION OF TRANSIT MAINTENANCE FACILITY AND TRANSIT TRANSFER HUB TO SUPPORT THE LINK TRANSIT SYSTEM. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 1600000 | FY 2025: 700000; FY 2026: 200000; FY 2027: 200000
TC-0035 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | ACQUIRE BATTERY-ELECTRIC BUSES, HYBRID BUSES, BUS CHARGERS, MANAGEMENT SYSTEMS, TRAINING, AND EQUIPMENT. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | L | OPERATIONS | 26456000 | FY 2025: 26393000
TC-0035 | Public Transportation (Transit) | Capital (Non-STI) | CHARLOTTE AREA TRANSIT SYSTEM | ACQUIRE BATTERY-ELECTRIC BUSES, HYBRID BUSES, BUS CHARGERS, MANAGEMENT SYSTEMS, TRAINING, AND EQUIPMENT. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | 5339(b) | OPERATIONS | 31143000 | FY 2025: 30891000
TC-5004 | Public Transportation (Transit) | Capital (Non-STI) | STATEWIDE | 5311 ADTAP |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUMODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | ADTAP | CAPITAL | 3392000
TC-5100 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | MOBILITY MANAGEMENT |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 60000 | FY 2025: 6000; FY 2026: 6000
TC-5100 | Public Transportation (Transit) | Capital (Non-STI) | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | MOBILITY MANAGEMENT |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 240000 | FY 2025: 24000; FY 2026: 24000
TD-4701 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 3660000 | FY 2025: 366000
TD-4701 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 3660000 | FY 2025: 366000
TD-4701 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CONSTRUCTION | 45971000 | FY 2025: 2926000
TD-4702 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - TRANSIT CENTER - UPGRADES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 127000 | FY 2025: 12000
TD-4702 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - TRANSIT CENTER - UPGRADES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 127000 | FY 2025: 12000
TD-4702 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - TRANSIT CENTER - UPGRADES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CONSTRUCTION | 4666000 | FY 2025: 96000
TD-4904 | Public Transportation (Transit) | STI (Prioritization) | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | T | CONSTRUCTION | 599000 | FY 2025: 144000
TD-4904 | Public Transportation (Transit) | STI (Prioritization) | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 1310000
TD-4904 | Public Transportation (Transit) | STI (Prioritization) | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | 5309 | CONSTRUCTION | 4500000
TD-4904 | Public Transportation (Transit) | STI (Prioritization) | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Division 3 |  | 5307 | CONSTRUCTION | 4950000
TD-4912 | Public Transportation (Transit) | STI (Prioritization) | GO RALEIGH TRANSIT | US 64 BUSINESS (NEW HOPE ROAD) IN RALEIGH. CONSTRUCT TRANSFER FACILITY. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY GO RALEIGH | Division 5
TD-5155 | Public Transportation (Transit) | Locally Selected | ORANGE PUBLIC TRANSIT | 1 REPLACEMENT LTV (25') AND RADIO, VEHICLE LETTERING AND LOGOS, AND ON-BOARD CAMERA. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY ORANGE PUBLIC TRANSIT | Division 7 |  | BGDA | CAPITAL | 62000
TD-5155 | Public Transportation (Transit) | Locally Selected | ORANGE PUBLIC TRANSIT | 1 REPLACEMENT LTV (25') AND RADIO, VEHICLE LETTERING AND LOGOS, AND ON-BOARD CAMERA. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY ORANGE PUBLIC TRANSIT | Division 7 |  | L | CAPITAL | 15000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. |  | WAKE | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | L | ENGINEERING | 2500000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. |  | WAKE | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | DP | CONSTRUCTION | 1000000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. |  | WAKE | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | T | CONSTRUCTION | 700000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. |  | WAKE | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | L | CONSTRUCTION | 60955000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. |  | WAKE | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | 5307 | CONSTRUCTION | 2000000
TD-5264B | Public Transportation (Transit) | STI (Prioritization) | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. |  | WAKE | 5 | Capital Area MPO | DP REPRESENTS THE FTA COMMUNITY PROJECT FUNDING PROGRAM GRANT 2023 | Division 5 |  | 5339(b) | CONSTRUCTION | 11787000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | L | PLANNING | 26000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | 5339(b) | PLANNING | 104000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | DP | CONSTRUCTION | 20000000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | T | CONSTRUCTION | 8860000 | FY 2025: 2215000; FY 2026: 2215000; FY 2027: 2215000; FY 2028: 2215000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | O | CONSTRUCTION | 24300000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | L | CONSTRUCTION | 205000 | FY 2025: 205000
TD-5269 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. |  | WAKE | 5 | Capital Area MPO | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH | Division 5 |  | 5339(b) | CONSTRUCTION | 820000 | FY 2025: 820000
TD-5272 | Public Transportation (Transit) | STI (Prioritization) | GO RALEIGH TRANSIT | SOUTH WILMINGTON STREET AT PECAN ROAD IN RALEIGH. CONSTRUCT OFF-STREET TRANSFER FACILITY. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY GO RALEIGH | Division 5
TD-5273 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE TRANSIT | ROUGEMONT PARK-AND-RIDE. PROFESSIONAL SERVICES AND PROPERTY ACQUISITION. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY TRIANGLE TRANSIT | Exempt |  | BGDA | CONSTRUCTION | 116000
TD-5273 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE TRANSIT | ROUGEMONT PARK-AND-RIDE. PROFESSIONAL SERVICES AND PROPERTY ACQUISITION. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS BY TRIANGLE TRANSIT | Exempt |  | L | CONSTRUCTION | 61000
TD-5279 | Public Transportation (Transit) | Capital (Non-STI) | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | S | CAPITAL | 373000
TD-5279 | Public Transportation (Transit) | Capital (Non-STI) | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | L | CAPITAL | 373000
TD-5279 | Public Transportation (Transit) | Capital (Non-STI) | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT |  | GUILFORD | 7 | Greensboro Urban Area MPO | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO | Public Transit |  | 5339 | CAPITAL | 1538000
TD-5281 | Public Transportation (Transit) | STI (Prioritization) | TAR RIVER TRANSIT | ENLARGE DRIVERS BREAKROOM |  | NASH | 4 | Rocky Mount Urban Area MPO |  | Division 4 |  | T | CAPITAL | 15000 | FY 2025: 15000
TD-5283 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM / HI-TRAN HIGH POINT TRANSIT | BUILDING / FACILITY RENOVATION AND UPGRADE FOR PARATRANSIT ADMINISTRATION. |  | GUILFORD | 7 | High Point Urban Area MPO | N PROGRESS | Region D
TD-5284 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | T | CONSTRUCTION | 36000
TD-5284 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | L | CONSTRUCTION | 36000
TD-5284 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Region D |  | 5307 | CONSTRUCTION | 288000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE | EXPAND EXISTING GARAGE FACILITY IN MORRISVILLE. |  | WAKE | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  | L | PLANNING | 24000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE | EXPAND EXISTING GARAGE FACILITY IN MORRISVILLE. |  | WAKE | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  | 5339(b) | PLANNING | 96000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE | EXPAND EXISTING GARAGE FACILITY IN MORRISVILLE. |  | WAKE | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 163000 | FY 2025: 163000
TD-5285 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE | EXPAND EXISTING GARAGE FACILITY IN MORRISVILLE. |  | WAKE | 5 | Capital Area MPO | IN PROGRESS | Public Transit |  | 5339(b) | CONSTRUCTION | 652000 | FY 2025: 652000
TD-5286 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | T | CONSTRUCTION | 159000
TD-5286 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | L | CONSTRUCTION | 159000
TD-5286 | Public Transportation (Transit) | STI (Prioritization) | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C |  | 5307 | CONSTRUCTION | 1272000
TD-5287 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE | PARK AND RIDE LOT AT SR 1774 (DISTRICT DRIVE). ADD SPACES, IMPROVE LIGHTING AND CONSTRUCT SHELTERS. |  | WAKE | 5 | Capital Area MPO | IN PROGRESS | Region C
TD-5293 | Public Transportation (Transit) | Capital (Non-STI) | GO RALEIGH | INTERSECTION OF SR 2298 (EDENTON STREET) AND NORTH SALISBURY STREET IN RALEIGH. CONSTRUCT BUS STOP SHELTER. |  | WAKE | 5 | Capital Area MPO | UNDER CONSTRUCTION BY GO TRIANGLE | Region C
TD-5294 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE | NC 98 (HOLLOWAY STREET) TRANSIT CORRIDOR. CONSTRUCT ACCESS AND BUS STOP IMPROVEMENTS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY GO TRIANGLE | Region C
TD-5295 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE | TOWN OF HILLSBOROUGH. CONSTRUCT PARK-AND-RIDE LOT. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY GO TRIANGLE | Region D |  | S | CONSTRUCTION | 120000
TD-5295 | Public Transportation (Transit) | Capital (Non-STI) | GO TRIANGLE | TOWN OF HILLSBOROUGH. CONSTRUCT PARK-AND-RIDE LOT. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | UNDER CONSTRUCTION BY GO TRIANGLE | Region D |  | L | CONSTRUCTION | 800000
TD-5302 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF SALISBURY | PREVENTIVE MAINTENANCE FOR BUS AND BUS FACILITY, FACILITY IMPROVEMENTS AND REPAIRS, AUTOMATIC BUS WASHER, SHOP EQUIPMENT, FUELING SYSTEM, SECURITY GATE UPGRADE, |  | ROWAN | 9 |  |  | Public Transit |  | L | CAPITAL | 567000
TD-5302 | Public Transportation (Transit) | Capital (Non-STI) | CITY OF SALISBURY | PREVENTIVE MAINTENANCE FOR BUS AND BUS FACILITY, FACILITY IMPROVEMENTS AND REPAIRS, AUTOMATIC BUS WASHER, SHOP EQUIPMENT, FUELING SYSTEM, SECURITY GATE UPGRADE, |  | ROWAN | 9 |  |  | Public Transit |  | 5339 | CAPITAL | 2268000
TD-5303 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON SALEM TRANSIT | FTA SECTION 5339 BUS AND BUS FACILITIES GRANT |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 1337000 | FY 2025: 110000; FY 2026: 110000; FY 2027: 110000
TD-5303 | Public Transportation (Transit) | Capital (Non-STI) | WINSTON SALEM TRANSIT | FTA SECTION 5339 BUS AND BUS FACILITIES GRANT |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5339 | CAPITAL | 6970000 | FY 2025: 620000; FY 2026: 620000; FY 2027: 620000
TD-5304 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | BUS STOP IMPROVEMENTS |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 3273000
TD-5305 | Public Transportation (Transit) | Capital (Non-STI) | CARY TRANSIT/C-TRAN | DOWNTOWN CARY MULTI-MODAL FACILITY. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 44200000
TD-5307 | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 1500000 | FY 2027: 1500000
TD-5307 | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | T | CONSTRUCTION | 1750000 | FY 2028: 875000; FY 2029: 875000
TD-5307 | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | O | CONSTRUCTION | 1750000 | FY 2028: 875000; FY 2029: 875000
TD-5307 | Public Transportation (Transit) | STI (Prioritization) | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 3158000 | FY 2028: 3158000
TD-5308 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. |  | WAKE | 5 | Capital Area MPO | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. | Public Transit |  | L | PLANNING | 4350000
TD-5308 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. |  | WAKE | 5 | Capital Area MPO | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. | Public Transit |  | L | RIGHT-OF-WAY | 2750000
TD-5308 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. |  | WAKE | 5 | Capital Area MPO | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. | Public Transit |  | DP | CONSTRUCTION | 9966000
TD-5308 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. |  | WAKE | 5 | Capital Area MPO | "DP" FUNDS REPRESENT RAISE GRANT FUNDS AWARDED DIRECTLY TO CITY OF RALIEGH. | Public Transit |  | L | CONSTRUCTION | 13800000
TD-5309 | Public Transportation (Transit) | Locally Selected | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SITES IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE PE |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 601000
TD-5309 | Public Transportation (Transit) | Locally Selected | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SITES IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE PE |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 151000
TD-5309A | Public Transportation (Transit) | Locally Selected | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOPS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE ROW |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 200000
TD-5309A | Public Transportation (Transit) | Locally Selected | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOPS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE ROW |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 50000
TD-5309B | Public Transportation (Transit) | Locally Selected | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SIGHTS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE CON |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 1200000
TD-5309B | Public Transportation (Transit) | Locally Selected | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SIGHTS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE CON |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 300000
TD-5314 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | EXISTING PARK AND RIDE IMPROVEMENTS |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 1105000 | FY 2025: 57000
TD-5315 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | BUILD NEW PARK AND RIDE AT HILLSBOROUGH ST AND I-440 IN RALEIGH. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 2220000
TD-5315 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | BUILD NEW PARK AND RIDE AT HILLSBOROUGH ST AND I-440 IN RALEIGH. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 5200000
TD-5316 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | BUILD NEW PARK AND RIDE AT CREEDMOOR AND I-540 OR AT FALLS OF NEUSE AND I-540 IN RALEIGH. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 1100000
TD-5316 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | BUILD NEW PARK AND RIDE AT CREEDMOOR AND I-540 OR AT FALLS OF NEUSE AND I-540 IN RALEIGH. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 1500000
TD-5317 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | GORALEIGH CONSTRUCTION OF PARK AND RIDE IN ROLESVILLE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 55000
TD-5318 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 547000
TD-5318 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | RIGHT-OF-WAY | 2249000 | FY 2025: 1125000; FY 2026: 562000
TD-5318 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 2989000 | FY 2025: 2989000
TD-5319 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT CRABTREE VALLEY MALL |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 324000
TD-5320 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT TRIANGLE TOWNE CENTER |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 324000
TD-6322 | Public Transportation (Transit) | Capital (Non-STI) | BURLINGTON | CAPITAL FOR PEDESTRIAN IMPROVEMENTS FOR FIXED ROUTR SERVICES |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | L | CAPITAL | 10000
TD-6322 | Public Transportation (Transit) | Capital (Non-STI) | BURLINGTON | CAPITAL FOR PEDESTRIAN IMPROVEMENTS FOR FIXED ROUTR SERVICES |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5307 | CAPITAL | 50000
TE-4901 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 191328000
TE-4901 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 93279000
TE-4901 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5309 | CONSTRUCTION | 820908000
TE-4902 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CONSTRUCTION | 100000
TE-4902 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | FED | CONSTRUCTION | 48068000
TE-4902 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CONSTRUCTION | 100000
TE-4902 | Public Transportation (Transit) | Capital (Non-STI) | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CONSTRUCTION | 800000
TE-4903A | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | FIXED GUIDEWAY - LIGHT RAIL SERVICE- CARY/RALEIGH |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO |  | Public Transit |  | FED | CONSTRUCTION | 1502000000
TE-4903B | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | FIXED GUIDEWAY - COMMUTER RAIL SERVICE- DURHAM/RALEIGH |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | FED | CONSTRUCTION | 666000
TG-0002 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | STATEWIDE | FY21 5307 SBUS CAPITAL |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | CAPITAL | 21000
TG-0004 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | STATEWIDE | FY21 5307 SBUS CAPITAL |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | CAPITAL | 168000
TG-0005 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | STATEWIDE | FY21 5307 SBUS CAPITAL |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | CAPITAL | 168000
TG-0006 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | STATEWIDE | FY21 5307 SBUS CAPITAL |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | CAPITAL | 52000
TG-0006 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | STATEWIDE | FY21 5307 SBUS CAPITAL |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | CAPITAL | 329000
TG-0010 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE BATTERY ELECTRIC BUSES, CHARGING STATIONS, ONSITE TRAINING AND STARTUP SUPPORT AND TESTING |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 3724000
TG-0010 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE BATTERY ELECTRIC BUSES, CHARGING STATIONS, ONSITE TRAINING AND STARTUP SUPPORT AND TESTING |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | 5339 | CAPITAL | 3724000
TG-0011 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF ASHEVILLE | BUSES AND BUS FACILITIES - BUS STOP IMPROVEMENT PROGRAM |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 250000
TG-0011 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF ASHEVILLE | BUSES AND BUS FACILITIES - BUS STOP IMPROVEMENT PROGRAM |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5339 | CAPITAL | 1000000
TG-0012 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | ROUTINE CAPITAL/PREVENTATIVE, MAINTENANCE/PASSENGER AMENITIES/MOBILITY MANAGEMENT |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 451000 | FY 2025: 94000; FY 2026: 94000; FY 2027: 94000; FY 2028: 94000
TG-0012 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | ROUTINE CAPITAL/PREVENTATIVE, MAINTENANCE/PASSENGER AMENITIES/MOBILITY MANAGEMENT |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 1812000 | FY 2025: 378000; FY 2026: 378000; FY 2027: 378000; FY 2028: 378000
TG-0013 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GORALEIGH | FIXED ROUTE PREVENTATIVE MAINTENANCE |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 1920000
TG-0013 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GORALEIGH | FIXED ROUTE PREVENTATIVE MAINTENANCE |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 7680000
TG-0014B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | CAPITAL |  | GUILFORD, ALAMANCE | 7 | Burlington-Graham MPO, High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 247000 | FY 2025: 41000; FY 2026: 41000; FY 2027: 41000; FY 2028: 41000
TG-0014B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | CAPITAL |  | GUILFORD, ALAMANCE | 7 | Burlington-Graham MPO, High Point Urban Area MPO |  | Public Transit |  | 5339 | CAPITAL | 1001000 | FY 2025: 167000; FY 2026: 167000; FY 2027: 167000; FY 2028: 167000
TG-0015 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GORALEIGH | GORALEIGH CAPITAL PROJECTS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 4401000
TG-0019 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GTA | ROUTINE CAPITAL: FAREBOXES, CAMERA SYSTEMS, APCs, AND DELIVERY FOR ASSET TRANSFER OF USED BUSES; DEPOT TICKET MACHINES: REALTIME SHELTER SIGNAGE; AND BUS SHELTERS. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 670000 | FY 2025: 134000; FY 2026: 134000; FY 2027: 134000; FY 2028: 134000
TG-0019 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GTA | ROUTINE CAPITAL: FAREBOXES, CAMERA SYSTEMS, APCs, AND DELIVERY FOR ASSET TRANSFER OF USED BUSES; DEPOT TICKET MACHINES: REALTIME SHELTER SIGNAGE; AND BUS SHELTERS. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5309 | CAPITAL | 2680000 | FY 2025: 536000; FY 2026: 536000; FY 2027: 536000; FY 2028: 536000
TG-0020 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | BUS FACILITIES CAPITAL IMPROVEMENTS - ACQUIRE OR REPLACE EQUIPMENT AND SUSTEMS IN THE WAVE TRANSIT OPERATIONS AND MAINTENANCE FACILITY. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 48000
TG-0020 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | BUS FACILITIES CAPITAL IMPROVEMENTS - ACQUIRE OR REPLACE EQUIPMENT AND SUSTEMS IN THE WAVE TRANSIT OPERATIONS AND MAINTENANCE FACILITY. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5309 | CAPITAL | 191000
TG-0021 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | DAVIDSON COUNTY TRANSPORTATION SYSTEM | ROUTINE CAPITAL/PREVENTATIVE MAINTENANCE FOR OPERATIONS IN THOMASVILLE, NC. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 72000 | FY 2025: 12000; FY 2026: 12000; FY 2027: 12000; FY 2028: 12000
TG-0021 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | DAVIDSON COUNTY TRANSPORTATION SYSTEM | ROUTINE CAPITAL/PREVENTATIVE MAINTENANCE FOR OPERATIONS IN THOMASVILLE, NC. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Public Transit |  | 5317 | CAPITAL | 288000 | FY 2025: 48000; FY 2026: 48000; FY 2027: 48000; FY 2028: 48000
TG-0022 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | HIGH POINT TRANSIT SYSTEM | MAINTENANCE FACILITY RENOVATION. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CONSTRUCTION | 300000
TG-0022 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | HIGH POINT TRANSIT SYSTEM | MAINTENANCE FACILITY RENOVATION. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | 5339 | CONSTRUCTION | 1200000
TG-0023 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PURCHASE REPLACEMENT BUSES. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  |  |  | L | CAPITAL | 25000 | FY 2025: 25000
TG-0023 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PURCHASE REPLACEMENT BUSES. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  |  |  | 5339 | CAPITAL | 100000 | FY 2025: 100000
TG-0024 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | HIGH POINT TRANSIT SYSTEM | REPLACEMENT PARATRANSIT BUSES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 275000 | FY 2026: 165000
TG-0024 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | HIGH POINT TRANSIT SYSTEM | REPLACEMENT PARATRANSIT BUSES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1100000 | FY 2026: 660000
TG-0025 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | HIGH POINT TRANSIT SYSTEM | NEW SPARE PARATRANSIT BUSES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 55000
TG-0025 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | HIGH POINT TRANSIT SYSTEM | NEW SPARE PARATRANSIT BUSES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 220000
TG-0026 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PURCHASE CNG BUSES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 572000 | FY 2025: 572000
TG-0026 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PURCHASE CNG BUSES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5339(b) | CAPITAL | 2860000 | FY 2025: 2860000
TG-0027 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GOTRIANGLE | CONSTRUCT 11 BUS STOPS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | CPF | ENGINEERING | 900000 | FY 2025: 900000
TG-0027 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GOTRIANGLE | CONSTRUCT 11 BUS STOPS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 236000 | FY 2025: 236000
TG-4726 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 4858000 | FY 2025: 704000
TG-4726 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | FMOD | CAPITAL | 1250000
TG-4726 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 29710000 | FY 2025: 2815000
TG-4729B | Public Transportation (Transit) | Operations and Maintenance | GORALEIGH | GORALEIGH ADA PARATRANSIT SERVICE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 2500000
TG-4729B | Public Transportation (Transit) | Operations and Maintenance | GORALEIGH | GORALEIGH ADA PARATRANSIT SERVICE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 2500000
TG-4731B | Public Transportation (Transit) | Operations and Maintenance | CHAPEL HILL TRANSIT | PREVENTIVE MAINTENANCE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 3720000
TG-4731B | Public Transportation (Transit) | Operations and Maintenance | CHAPEL HILL TRANSIT | PREVENTIVE MAINTENANCE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 24837000
TG-4732A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 432000
TG-4732A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 3488000
TG-4732B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 78000
TG-4732B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 810000
TG-4738 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GODURHAM | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | CMAQ | CAPITAL | 260000
TG-4738 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GODURHAM | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1952000 | FY 2025: 200000; FY 2026: 200000; FY 2027: 200000; FY 2028: 200000
TG-4738 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GODURHAM | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 926000
TG-4738 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GODURHAM | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 10927000 | FY 2025: 800000; FY 2026: 800000; FY 2027: 800000; FY 2028: 800000
TG-4738A | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | PREVENTIVE MAINTENANCE |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 9750000 | FY 2025: 750000; FY 2026: 750000; FY 2027: 750000; FY 2028: 750000
TG-4738A | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | PREVENTIVE MAINTENANCE |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 60860000 | FY 2025: 3000000; FY 2026: 3000000; FY 2027: 3000000; FY 2028: 3000000
TG-4752A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 48000
TG-4752A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 607000
TG-4752B | Public Transportation (Transit) | Operations and Maintenance | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | PREVENTIVE MAINTENANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 414000
TG-4752B | Public Transportation (Transit) | Operations and Maintenance | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | PREVENTIVE MAINTENANCE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 2468000
TG-4752C | Public Transportation (Transit) | Operations and Maintenance | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 280000
TG-4752C | Public Transportation (Transit) | Operations and Maintenance | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 1774000
TG-4759 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GREENSBORO TRANSIT AGENCY | PREVENTIVE MAINTENANCE |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 6270000 | FY 2025: 776000; FY 2026: 776000; FY 2027: 776000; FY 2028: 776000
TG-4759 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GREENSBORO TRANSIT AGENCY | PREVENTIVE MAINTENANCE |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 25073000 | FY 2025: 3103000; FY 2026: 3103000; FY 2027: 3103000; FY 2028: 3103000
TG-4767 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GREENVILLE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 938000
TG-4767 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GREENVILLE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 6800000
TG-4774 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 120000 | FY 2025: 20000
TG-4774 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1098000 | FY 2025: 220000
TG-4774A | Public Transportation (Transit) | Operations and Maintenance | REGIONAL TRANSPORTATION WESTERN PIEDMONT | PREVENTIVE MAINTENANCE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 820000 | FY 2025: 10000
TG-4774A | Public Transportation (Transit) | Operations and Maintenance | REGIONAL TRANSPORTATION WESTERN PIEDMONT | PREVENTIVE MAINTENANCE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 5345000 | FY 2025: 110000
TG-4774B | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE ‐ ADA PARATRANSIT SERVICE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | OPERATIONS | 78000 | FY 2025: 39000
TG-4774B | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE ‐ ADA PARATRANSIT SERVICE |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5307 | OPERATIONS | 858000 | FY 2025: 429000
TG-4785A | Public Transportation (Transit) | Operations and Maintenance | TAR RIVER TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 180000
TG-4785A | Public Transportation (Transit) | Operations and Maintenance | TAR RIVER TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 1176000
TG-4785B | Public Transportation (Transit) | Operations and Maintenance | TAR RIVER TRANSIT | PREVENTIVE MAINTENANCE |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 800000
TG-4785B | Public Transportation (Transit) | Operations and Maintenance | TAR RIVER TRANSIT | PREVENTIVE MAINTENANCE |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 5647000
TG-4792B | Public Transportation (Transit) | Operations and Maintenance | GORALEIGH | ADA PARATRANSIT SERVICE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 6289000
TG-4792B | Public Transportation (Transit) | Operations and Maintenance | GORALEIGH | ADA PARATRANSIT SERVICE |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 11938000
TG-4814 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM / HI-TRAN HIGH POINT TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC ($40K CAPITAL COST OF CONTRACTING). |  | GUILFORD, DAVIDSON, RANDOLPH | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 860000 | FY 2025: 47000; FY 2026: 47000; FY 2027: 47000; FY 2028: 47000
TG-4814 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM / HI-TRAN HIGH POINT TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC ($40K CAPITAL COST OF CONTRACTING). |  | GUILFORD, DAVIDSON, RANDOLPH | 7, 8, 9 | High Point Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4270000 | FY 2025: 190000; FY 2026: 190000; FY 2027: 190000; FY 2028: 190000
TG-4821B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GOTRIANGLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1535000
TG-4821B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GOTRIANGLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1688000
TG-4821B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GOTRIANGLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 6753000
TG-4821B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GOTRIANGLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES |  | WAKE, DURHAM, ORANGE | 5, 7 | Capital Area MPO, Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 15079000
TG-4827 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 901000 | FY 2025: 83000
TG-4827 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 5045000 | FY 2025: 331000
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 23820000
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | OPERATIONS | 1210000
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 36100000
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 10660000 | FY 2025: 3620000
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 6700000 | FY 2025: 2300000
TG-4935A | Public Transportation (Transit) | Operations and Maintenance | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5309 | CAPITAL | 595000 | FY 2025: 200000
TG-4951 | Public Transportation (Transit) | Operations and Maintenance | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | SMAP | OPERATIONS | 2463000
TG-4951 | Public Transportation (Transit) | Operations and Maintenance | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1304000
TG-4951 | Public Transportation (Transit) | Operations and Maintenance | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 3010000
TG-4952 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | NON-FIXED ROUTE ADA PARATRANSIT |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 185000 | FY 2025: 20000; FY 2026: 20000; FY 2027: 20000
TG-4952 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | NON-FIXED ROUTE ADA PARATRANSIT |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 742000 | FY 2025: 80000; FY 2026: 80000; FY 2027: 80000
TG-4957 | Public Transportation (Transit) | Operations and Maintenance | AUTHORITY GREENSBORO TRANSIT | OPERATING-ADA PARATRANSIT SERVICE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 4442000 | FY 2025: 662000; FY 2026: 662000; FY 2027: 662000; FY 2028: 662000
TG-4957 | Public Transportation (Transit) | Operations and Maintenance | AUTHORITY GREENSBORO TRANSIT | OPERATING-ADA PARATRANSIT SERVICE. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 11582000 | FY 2025: 662000; FY 2026: 662000; FY 2027: 662000; FY 2028: 662000
TG-5026 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CARTS | TG-5026 LEASE OF TABLETS |  | CRAVEN | 2 | New Bern Area MPO |  | Public Transit |  | L | ADMINISTRATIVE | 0
TG-5026 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CARTS | TG-5026 LEASE OF TABLETS |  | CRAVEN | 2 | New Bern Area MPO |  | Public Transit |  | 5307 | ADMINISTRATIVE | 0
TG-5103A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1000000
TG-5103A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 6243000
TG-5103B | Public Transportation (Transit) | Operations and Maintenance | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - ADA SERVICES |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 544000
TG-5103B | Public Transportation (Transit) | Operations and Maintenance | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - ADA SERVICES |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 2902000
TG-5103C | Public Transportation (Transit) | Operations and Maintenance | RIDER TRANSIT / CONCORD | PREVENTIVE MAINTENANCE |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 2350000
TG-5103C | Public Transportation (Transit) | Operations and Maintenance | RIDER TRANSIT / CONCORD | PREVENTIVE MAINTENANCE |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 12625000
TG-5105 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 525000 | FY 2025: 14000; FY 2026: 14000; FY 2027: 14000; FY 2028: 14000
TG-5105 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 3327000 | FY 2025: 56000; FY 2026: 56000; FY 2027: 56000; FY 2028: 56000
TG-5105 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 90000
TG-5107B | Public Transportation (Transit) | Operations and Maintenance | GREENVILLE AREA TRANSIT | PREVENTIVE MAINTENANCE |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1085000
TG-5107B | Public Transportation (Transit) | Operations and Maintenance | GREENVILLE AREA TRANSIT | PREVENTIVE MAINTENANCE |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 7632000
TG-5107C | Public Transportation (Transit) | Operations and Maintenance | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 298000
TG-5107C | Public Transportation (Transit) | Operations and Maintenance | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE |  | PITT | 2 | Greenville Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 2036000
TG-5109 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 574000
TG-5109 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 507000 | FY 2025: 55000; FY 2026: 55000; FY 2027: 55000
TG-5109 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 2021000 | FY 2025: 219000; FY 2026: 219000; FY 2027: 219000
TG-5118A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | STATE OF GOOD REPAIR - RAIL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 4825000 | FY 2025: 371000; FY 2026: 702000; FY 2027: 723000 | 1697000
TG-5118A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | STATE OF GOOD REPAIR - RAIL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 8395000 | FY 2025: 371000; FY 2026: 702000; FY 2027: 723000 | 1697000
TG-5118A | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | STATE OF GOOD REPAIR - RAIL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 52080000 | FY 2025: 2965000; FY 2026: 5612000; FY 2027: 5718000 | 13368000
TG-5118B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | LIGHT RAIL VEHICLE OVERHAUL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 4138000 | FY 2025: 406000
TG-5118B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | LIGHT RAIL VEHICLE OVERHAUL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 26542000 | FY 2025: 1624000
TG-5118B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | LIGHT RAIL VEHICLE OVERHAUL |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5337 | CAPITAL | 2410000
TG-5119 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | PREVENTIVE MAINTENANCE - RAIL, BUS AND FACILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 13047000 | FY 2025: 882000
TG-5119 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM CHARLOTTE AREA TRANSIT | PREVENTIVE MAINTENANCE - RAIL, BUS AND FACILITIES |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 82330000 | FY 2025: 3528000
TG-5122 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CARTS | TG-5122 SHORT RANGE PLANNING |  | CRAVEN | 2 | New Bern Area MPO |  | Public Transit |  | L | PLANNING | 0
TG-5122 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CARTS | TG-5122 SHORT RANGE PLANNING |  | CRAVEN | 2 | New Bern Area MPO |  | Public Transit |  | 5307 | PLANNING | 0
TG-5126 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 9062000 | FY 2025: 1214000; FY 2026: 1214000; FY 2027: 1214000
TG-5126 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | OPERATIONS | 11490000 | FY 2025: 1214000; FY 2026: 1214000; FY 2027: 1214000
TG-5220 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | S | CAPITAL | 39000 | FY 2025: 4000; FY 2026: 4000; FY 2027: 4000
TG-5220 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 39000 | FY 2025: 4000; FY 2026: 4000; FY 2027: 4000
TG-5220 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 400000 | FY 2025: 32000; FY 2026: 32000; FY 2027: 33000
TG-5224A | Public Transportation (Transit) | Operations and Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | PREVENTIVE MAINTENANCE |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 2325000
TG-5224A | Public Transportation (Transit) | Operations and Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | PREVENTIVE MAINTENANCE |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | OPERATIONS | 14874000
TG-5224C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | CAPITAL | 123000
TG-5224C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 306000
TG-5224C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 2052000
TG-5224D | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - SUPPORT VEHICLE |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Public Transit |  | L | CAPITAL | 60000
TG-5224D | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - SUPPORT VEHICLE |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Public Transit |  | 5307 | CAPITAL | 240000
TG-5224E | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - ADA SERVICES |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 595000
TG-5224E | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - ADA SERVICES |  | CUMBERLAND | 6 | Fayetteville Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 2365000
TG-5225 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | ROUTINE CAPITAL-BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 44000 | FY 2025: 4000; FY 2026: 4000; FY 2027: 4000
TG-5225 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | ROUTINE CAPITAL-BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 723000 | FY 2025: 16000; FY 2026: 16000; FY 2027: 16000
TG-5225C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | MOBILITY MANAGEMENT |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | L | CAPITAL | 158000 | FY 2025: 17000; FY 2026: 17000; FY 2027: 17000
TG-5225C | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | JACKSONVILLE TRANSIT | MOBILITY MANAGEMENT |  | ONSLOW | 3 | Jacksonville Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 732000 | FY 2025: 69000; FY 2026: 69000; FY 2027: 69000
TG-5232 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF SALISBURY | PREVENTIVE MAINTENANCE - BUS, FACILITIES |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 996000 | FY 2025: 83000; FY 2026: 83000; FY 2027: 83000
TG-5232 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF SALISBURY | PREVENTIVE MAINTENANCE - BUS, FACILITIES |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 4008000 | FY 2025: 334000; FY 2026: 334000; FY 2027: 334000
TG-5233 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF SALISBURY | BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC. |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 448000
TG-5233 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF SALISBURY | BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC. |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1792000
TG-5235 | Public Transportation (Transit) | Locally Selected | GO TRIANGLE | SAFETY AND SECURITY - CAMERAS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Division 5 |  | BGDA | CAPITAL | 137000
TG-5235 | Public Transportation (Transit) | Locally Selected | GO TRIANGLE | SAFETY AND SECURITY - CAMERAS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Division 5 |  | L | CAPITAL | 34000
TG-5241 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WINSTON SALEM TRANSIT | PREVENTIVE MAINTENANCE |  | FORSYTH | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 8420000 | FY 2025: 585000; FY 2026: 585000; FY 2027: 585000
TG-5241 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WINSTON SALEM TRANSIT | PREVENTIVE MAINTENANCE |  | FORSYTH | 9 | Winston-Salem Area TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 37216000 | FY 2025: 2337000; FY 2026: 2337000; FY 2027: 2337000
TG-5243 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE PREVENTATIVE MAINTENACE PROJECT WILL ENSURE THE FTA FUNDED ASSESTS ARE MAINTAINED TO THE FTA STATE OF GOOD REPAIR REQUIREMENTS AND THAT SERVICE CONTINUES WITHOUT DISRUPTION. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 225000
TG-5243 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE PREVENTATIVE MAINTENACE PROJECT WILL ENSURE THE FTA FUNDED ASSESTS ARE MAINTAINED TO THE FTA STATE OF GOOD REPAIR REQUIREMENTS AND THAT SERVICE CONTINUES WITHOUT DISRUPTION. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 900000
TG-5245 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | PREVENTIVE MAINTENANCE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 1222000 | FY 2025: 215000
TG-5245 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | PREVENTIVE MAINTENANCE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 4282000 | FY 2025: 860000
TG-5246 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE OPERATING ASSISTANCE PROJECT WILL ALLOW THE CONTINUATION OF COMPLEMENTARY PARATRANSIT SERVICE TO TWO COUNTIES AND FOUR MUNICIPLITIES WITHIN THE UZA. |  | BRUNSWICK, NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 216000 | FY 2025: 70000
TG-5246 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE OPERATING ASSISTANCE PROJECT WILL ALLOW THE CONTINUATION OF COMPLEMENTARY PARATRANSIT SERVICE TO TWO COUNTIES AND FOUR MUNICIPLITIES WITHIN THE UZA. |  | BRUNSWICK, NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 877000 | FY 2025: 280000
TG-5255 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GO TRIANGLE | ESTABLISH NEIGHBORHOOD TRANSIT CENTERS IN DURHAM. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | IN PROGRESS | Region C
TG-5255B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | VARIOUS | NEIGHBORHOOD TRANSIT CENTER IN SOUTH DURHAM IN CONNECTION WITH SOUTHPOINT PARK-AND-RIDE FACILITY. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C
TG-5255E | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | VARIOUS | NEIGHBORHOOD TRANSIT CENTER IN SOUTHWEST DURHAM IN CONNECTION WITH PATTERSON PLACE T PARK-AND-RIDE FACILITY. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Region C
TG-5256 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | PREVENTIVE MAINTENANCE |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 72000
TG-5256 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | PREVENTIVE MAINTENANCE |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 280000
TG-5257 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | ADA/PARATRANSIT |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 137000 | FY 2025: 3000; FY 2026: 3000
TG-5257 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | ADA/PARATRANSIT |  | CRAVEN | 2 | New Bern Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 533000 | FY 2025: 10000; FY 2026: 10000
TG-5260 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF SALISBURY | ROUTINE CAPITAL - ADA SERVICES |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 212000 | FY 2025: 18000; FY 2026: 18000; FY 2027: 18000
TG-5260 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF SALISBURY | ROUTINE CAPITAL - ADA SERVICES |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 826000 | FY 2025: 70000; FY 2026: 70000; FY 2027: 70000
TG-6137B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PASSENGER AMENITIES, PARTS, EQUIPMENT, PREVENTIVE MAINTENANCE, AND CAPITAL COST OF CONTRACTING. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 200000 | FY 2025: 25000
TG-6137B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PASSENGER AMENITIES, PARTS, EQUIPMENT, PREVENTIVE MAINTENANCE, AND CAPITAL COST OF CONTRACTING. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 800000 | FY 2025: 100000
TG-6143 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 64000
TG-6143 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 528000
TG-6143 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | CAPITAL | 7000
TG-6146 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | CAPITAL | 545000
TG-6173B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PREVENTIVE MAINTENANCE, SECURITY AND PESSENGER AMENITIES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | L | CAPITAL | 206000 | FY 2025: 28000; FY 2026: 28000; FY 2027: 28000; FY 2028: 28000
TG-6173B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PREVENTIVE MAINTENANCE, SECURITY AND PESSENGER AMENITIES. |  | GUILFORD | 7 | High Point Urban Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1290000 | FY 2025: 115000; FY 2026: 115000; FY 2027: 115000; FY 2028: 115000
TG-6177 | Public Transportation (Transit) | STI (Prioritization) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | T | CONSTRUCTION | 6000
TG-6177 | Public Transportation (Transit) | STI (Prioritization) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CONSTRUCTION | 6000
TG-6177 | Public Transportation (Transit) | STI (Prioritization) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 54000
TG-6179 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF SALISBURY | AVL SYSTEM |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 448000
TG-6179 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF SALISBURY | AVL SYSTEM |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5339 | CAPITAL | 1792000
TG-6181 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | APPLE COUNTRY TRANSIT | TRANSIT ROUTINE CAPITAL COST OF CONTRACTING |  | HENDERSON | 14 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 2677000 | FY 2025: 63000
TG-6181 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | APPLE COUNTRY TRANSIT | TRANSIT ROUTINE CAPITAL COST OF CONTRACTING |  | HENDERSON | 14 | French Broad River MPO |  | Public Transit |  | 5307 | CAPITAL | 2199000 | FY 2025: 252000
TG-6183A | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | ADA PARATRANSIT SERVICE |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | OPERATIONS | 221000
TG-6183A | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | ADA PARATRANSIT SERVICE |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | OPERATIONS | 884000
TG-6183B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF ASHEVILLE | TRANSIT PREVENTATIVE MAINTENANCE |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 1811000 | FY 2025: 392000
TG-6183B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CITY OF ASHEVILLE | TRANSIT PREVENTATIVE MAINTENANCE |  | BUNCOMBE | 13 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 7324000 | FY 2025: 1650000
TG-6184B | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | PREVENTATIVE MAINTENANCE |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | OPERATIONS | 437000 | FY 2025: 80000
TG-6184B | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | PREVENTATIVE MAINTENANCE |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | OPERATIONS | 1448000 | FY 2025: 20000
TG-6185 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | CAPITAL | 344000 | FY 2025: 38000; FY 2026: 38000; FY 2027: 38000; FY 2028: 38000
TG-6185 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL. |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5307 | CAPITAL | 1445000 | FY 2025: 152000; FY 2026: 152000; FY 2027: 152000; FY 2028: 152000
TG-6187 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS – CAPITAL PROGRAM |  | MECKLENBURG, ALAMANCE, CABARRUS, CUMBERLAND, DAVIDSON, GUILFORD, HARNETT, HOKE, IREDELL, ORANGE, UNION | 6, 7, 8, 9, 10, 12 | Charlotte Regional TPO, Cabarrus-Rowan MPO, Burlington-Graham MPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 751000
TG-6187 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS – CAPITAL PROGRAM |  | MECKLENBURG, ALAMANCE, CABARRUS, CUMBERLAND, DAVIDSON, GUILFORD, HARNETT, HOKE, IREDELL, ORANGE, UNION | 6, 7, 8, 9, 10, 12 | Charlotte Regional TPO, Cabarrus-Rowan MPO, Burlington-Graham MPO, Fayetteville Area MPO, High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | 5307 | CAPITAL | 3000000
TG-6731 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WINSTON SALEM TRANSIT |  |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | CMAQ | CAPITAL | 2430000
TG-6731 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WINSTON SALEM TRANSIT |  |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 609000
TG-6783 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL, PASSENGER SHELTERS, PASSENGER AMENITIES, SHOP EQUIPMENT, SPARE PARTS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 411000 | FY 2025: 44000; FY 2026: 44000; FY 2027: 44000; FY 2028: 44000
TG-6783 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL, PASSENGER SHELTERS, PASSENGER AMENITIES, SHOP EQUIPMENT, SPARE PARTS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | CAPITAL | 1644000 | FY 2025: 176000; FY 2026: 176000; FY 2027: 176000; FY 2028: 176000
TG-6784 | Public Transportation (Transit) | Locally Selected | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PREVENTIVE MAINTENANCE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CONSTRUCTION | 350000
TG-6784 | Public Transportation (Transit) | Locally Selected | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PREVENTIVE MAINTENANCE |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CONSTRUCTION | 70000
TG-6786 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY BUNCOMBE - BUNCOMBE COUNTY TRANSIT ROUTINE CAPITAL COST OF CONTRACTING. |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 816000
TG-6786 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY BUNCOMBE - BUNCOMBE COUNTY TRANSIT ROUTINE CAPITAL COST OF CONTRACTING. |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 5307 | CAPITAL | 1600000
TG-6788 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WAYNESVILLE | MOUNTAIN PROJECTS ( HAYWOOD COUNTY) DEVIATED FIXED ROUTE CAPITAL AND CARES FUNDS. |  | HAYWOOD | 14 | French Broad River MPO |  | Public Transit |  | L | CAPITAL | 289000 | FY 2025: 41000; FY 2026: 41000; FY 2027: 41000; FY 2028: 41000
TG-6788 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WAYNESVILLE | MOUNTAIN PROJECTS ( HAYWOOD COUNTY) DEVIATED FIXED ROUTE CAPITAL AND CARES FUNDS. |  | HAYWOOD | 14 | French Broad River MPO |  | Public Transit |  | 5307 | CAPITAL | 1193000 | FY 2025: 163000; FY 2026: 163000; FY 2027: 163000; FY 2028: 163000
TG-6789 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CABARRUS COUNTY | CAPITAL FOR CABARRUS COUNTY THROUGH THE CITY OF CONCORD |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Public Transit |  | L | CAPITAL | 416000 | FY 2025: 50000; FY 2026: 52000; FY 2027: 54000
TG-6789 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | CABARRUS COUNTY | CAPITAL FOR CABARRUS COUNTY THROUGH THE CITY OF CONCORD |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Public Transit |  | 5307 | CAPITAL | 2077000 | FY 2025: 250000; FY 2026: 260000; FY 2027: 270000
TG-6790 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | MECKLENBURG TRANSPORTATION | 5307 FUNDING FOR FY20-21 (20-LU-051) |  | MECKLENBURG | 10 | Charlotte Regional TPO | ADDING FFY20-21 | Public Transit |  | L | CAPITAL | 545000
TG-6790 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | MECKLENBURG TRANSPORTATION | 5307 FUNDING FOR FY20-21 (20-LU-051) |  | MECKLENBURG | 10 | Charlotte Regional TPO | ADDING FFY20-21 | Public Transit |  | 5307 | CAPITAL | 1035000
TG-6791 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GORALEIGH | CAPITAL COST OF CONTRACTING |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 1000000
TG-6791 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GORALEIGH | CAPITAL COST OF CONTRACTING |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 4000000
TG-6792 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GASTON TRANSIT | TRANSIT ENHANCEMENTS - PEDESTRIAN WALKWAYS |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | CONSTRUCTION | 622000
TG-6792 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | GASTON TRANSIT | TRANSIT ENHANCEMENTS - PEDESTRIAN WALKWAYS |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | CONSTRUCTION | 2485000
TG-6798 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER |  | CATAWBA | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 227000 | FY 2025: 32000
TG-6798 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER |  | CATAWBA | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 901000 | FY 2025: 126000
TG-6799 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTIVE MAINTANENCE |  | CATAWBA | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | CAPITAL | 879000 | FY 2025: 120000
TG-6799 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTIVE MAINTANENCE |  | CATAWBA | 12 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | CAPITAL | 3515000 | FY 2025: 480000
TG-6800 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, COMPUTER HARDWARE AND SOFTWARE, AVL SOFTWARE, ETC. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | CAPITAL | 534000 | FY 2025: 96000; FY 2026: 96000
TG-6800 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, COMPUTER HARDWARE AND SOFTWARE, AVL SOFTWARE, ETC. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | CAPITAL | 2135000 | FY 2025: 384000; FY 2026: 384000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | PLANNING | 50000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | PLANNING | 50000 | FY 2026: 50000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | PLANNING | 50000 | FY 2025: 50000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | PLANNING | 200000 | FY 2026: 200000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | PLANNING | 200000 | FY 2025: 200000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | PLANNING | 200000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 50000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 50000 | FY 2025: 50000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 364000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | L | OPERATIONS | 50000 | FY 2026: 50000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 200000 | FY 2025: 200000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 200000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 1453000
TG-6801 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT. |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 | Public Transit |  | 5307 | OPERATIONS | 200000 | FY 2026: 200000
TG-6802 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE-ADA PARATRANSIT |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | L | OPERATIONS | 70000 | FY 2025: 10000
TG-6802 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE-ADA PARATRANSIT |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5310 | OPERATIONS | 280000 | FY 2025: 40000
TG-6804 | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | TRANSIT APP |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | L | OPERATIONS | 13000
TG-6804 | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | TRANSIT APP |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO. | Public Transit |  | 5307 | OPERATIONS | 50000
TG-6808B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | DAVIDSON COUNTY | PREVENTIVE MAINTENANCE |  | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | L | CONSTRUCTION | 81672000
TG-6808B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | DAVIDSON COUNTY | PREVENTIVE MAINTENANCE |  | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | 5307 | CONSTRUCTION | 326688000
TG-6809 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | DAVIDSON COUNTY | ROUTINE CAPITAL - PASSENGER SHELTERS, PASSENGER AMENITIESA, SHOP EQUIPMENT, SPARE PARTS, CAPITAL COST OF CONTRACTING, ETC. |  | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | L | CONSTRUCTION | 40836000
TG-6809 | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | DAVIDSON COUNTY | ROUTINE CAPITAL - PASSENGER SHELTERS, PASSENGER AMENITIESA, SHOP EQUIPMENT, SPARE PARTS, CAPITAL COST OF CONTRACTING, ETC. |  | DAVIDSON | 9 | High Point Urban Area MPO, Winston-Salem Area TPO |  | Public Transit |  | 5307 | CONSTRUCTION | 163344000
TG-6811B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. |  | ALAMANCE, GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Public Transit |  | FED | CAPITAL | 37000
TG-6811B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. |  | ALAMANCE, GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 59000 | FY 2025: 10000; FY 2026: 10000; FY 2027: 10000; FY 2028: 10000
TG-6811B | Public Transportation (Transit) | Routine Capital and Preventive Maintenance | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. |  | ALAMANCE, GUILFORD, ORANGE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 200000 | FY 2025: 40000; FY 2026: 40000; FY 2027: 40000; FY 2028: 40000
TG-6812A | Public Transportation (Transit) | Operations and Maintenance | BURLINGTON | ADA SERVICES |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | L | OPERATIONS | 42000
TG-6812A | Public Transportation (Transit) | Operations and Maintenance | BURLINGTON | ADA SERVICES |  | ALAMANCE | 7 | Burlington-Graham MPO | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO. | Public Transit |  | 5307 | OPERATIONS | 169000
TG-6814 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | PURCHASE AND INSTALL SIGNAGE AT DESIGNATED LOCATIONS ALONG I-540 AND I-40 FOR BUS ON SHOULDER SYSTEM. (BOSS) UTILIZE EASTBOUND SHOULDER OF I-540 BETWEEN NC-147 AND CAPITAL BLVD AND EASTBOUND ON I-40 BETWEEN WADE AVENUE AND S SAUNDERS STREET. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | BGDA | CAPITAL | 123000
TG-6814 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | PURCHASE AND INSTALL SIGNAGE AT DESIGNATED LOCATIONS ALONG I-540 AND I-40 FOR BUS ON SHOULDER SYSTEM. (BOSS) UTILIZE EASTBOUND SHOULDER OF I-540 BETWEEN NC-147 AND CAPITAL BLVD AND EASTBOUND ON I-40 BETWEEN WADE AVENUE AND S SAUNDERS STREET. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CAPITAL | 331000
TG-6815 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | DESIGN, PURCHASE, AND INSTALL NEW AMENITIES AT 13 BUS STOP LOCATIONS ALONG ROUTES IN WAKE COUNTY,UPGRADES INCLUDE SHELTERS, BENCH, PAD, OR SOME COMBINATIONS |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CAPITAL | 259000
TG-6815 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | DESIGN, PURCHASE, AND INSTALL NEW AMENITIES AT 13 BUS STOP LOCATIONS ALONG ROUTES IN WAKE COUNTY,UPGRADES INCLUDE SHELTERS, BENCH, PAD, OR SOME COMBINATIONS |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CAPITAL | 648000
TG-6816 | Public Transportation (Transit) | Locally Selected | GORALEIGH | DEVELOPED ENHANCED TRANSFER POINTS THROUGHOUT GO RALEIGH SYSTEM IN LOCATION WITH HIGH RIDERSHIP (75 + BOARDINGS PER DAY) |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CAPITAL | 788000
TG-6816 | Public Transportation (Transit) | Locally Selected | GORALEIGH | DEVELOPED ENHANCED TRANSFER POINTS THROUGHOUT GO RALEIGH SYSTEM IN LOCATION WITH HIGH RIDERSHIP (75 + BOARDINGS PER DAY) |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CAPITAL | 397000
TI-6101 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE |  | CALDWELL, CATAWBA, LINCOLN, MECKLENBURG, WATAUGA | 10, 11, 12 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 1952000
TI-6101 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE |  | CALDWELL, CATAWBA, LINCOLN, MECKLENBURG, WATAUGA | 10, 11, 12 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 848000
TI-6101 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE |  | CALDWELL, CATAWBA, LINCOLN, MECKLENBURG, WATAUGA | 10, 11, 12 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 6023000
TI-6102 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON |  | CUMBERLAND, MOORE, ANSON, HOKE, RICHMOND, UNION | 6, 8, 10 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 2120000
TI-6102 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON |  | CUMBERLAND, MOORE, ANSON, HOKE, RICHMOND, UNION | 6, 8, 10 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 928000
TI-6102 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON |  | CUMBERLAND, MOORE, ANSON, HOKE, RICHMOND, UNION | 6, 8, 10 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 7470000
TI-6103 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE |  | FORSYTH, GUILFORD, WATAUGA, WILKES, YADKIN | 7, 9, 11 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 2674000
TI-6103 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE |  | FORSYTH, GUILFORD, WATAUGA, WILKES, YADKIN | 7, 9, 11 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 1486000
TI-6103 | Public Transportation (Transit) | Operations and Maintenance | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE |  | FORSYTH, GUILFORD, WATAUGA, WILKES, YADKIN | 7, 9, 11 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 8642000
TI-6104 | Public Transportation (Transit) | Operations and Maintenance | GREYHOUND LINES | INTERCITY BUS FROM RALEIGH TO NORFOLK, VA VIA ELIZABETH CITY ALONG US 64, US 301, US 264, AND US 17 WITH STOPS AT RALEIGH, ROCKY MOUNT, WILSON, GREENVILLE, WASHINGTON, WILLIAMSTON, EDENTON, AND ELIZABETH CITY |  | BEAUFORT, PASQUOTANK, PITT, WILSON, BERTIE, CHOWAN, EDGECOMBE, FRANKLIN, MARTIN, NASH, PERQUIMANS, WAKE | 1, 2, 4, 5 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 9248000
TI-6104 | Public Transportation (Transit) | Operations and Maintenance | GREYHOUND LINES | INTERCITY BUS FROM RALEIGH TO NORFOLK, VA VIA ELIZABETH CITY ALONG US 64, US 301, US 264, AND US 17 WITH STOPS AT RALEIGH, ROCKY MOUNT, WILSON, GREENVILLE, WASHINGTON, WILLIAMSTON, EDENTON, AND ELIZABETH CITY |  | BEAUFORT, PASQUOTANK, PITT, WILSON, BERTIE, CHOWAN, EDGECOMBE, FRANKLIN, MARTIN, NASH, PERQUIMANS, WAKE | 1, 2, 4, 5 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 19025000
TI-6109 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5311(F) INTERCITY BUS FUNDS FOR FTA GANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5311 | OPERATIONS | 2698000
TK-4900Z | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5311 STATE ADMINISTRATION AND 5311 STATE ADMINISTRATION |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5311 | ADMINISTRATIVE | 3080000
TK-4902 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | STATE ADMINISTRATION OF APPALACHIAN DEVELOPMENT TRANSPORTATION ASSISTANCE PROGRAM |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | ADTAP | ADMINISTRATIVE | 235000
TK-5176 | Public Transportation (Transit) | Operations and Maintenance | APPLE COUNTRY TRANSIT | ADMINISTRATION |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 53000
TK-5176 | Public Transportation (Transit) | Operations and Maintenance | APPLE COUNTRY TRANSIT | ADMINISTRATION |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 159000
TK-5176 | Public Transportation (Transit) | Operations and Maintenance | APPLE COUNTRY TRANSIT | ADMINISTRATION |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1658000
TK-5176 | Public Transportation (Transit) | Operations and Maintenance | APPLE COUNTRY TRANSIT | ADMINISTRATION |  | HENDERSON | 14 | French Broad River MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 270000
TK-5178 | Public Transportation (Transit) | Operations and Maintenance | CITY OF WILSON | ADMINISTRATION |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 135000
TK-5178 | Public Transportation (Transit) | Operations and Maintenance | CITY OF WILSON | ADMINISTRATION |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 405000
TK-5178 | Public Transportation (Transit) | Operations and Maintenance | CITY OF WILSON | ADMINISTRATION |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 4023000
TK-5179 | Public Transportation (Transit) | Operations and Maintenance | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 123000
TK-5179 | Public Transportation (Transit) | Operations and Maintenance | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 376000
TK-5179 | Public Transportation (Transit) | Operations and Maintenance | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION |  | WAYNE | 4 | Goldsboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 3878000
TK-5180 | Public Transportation (Transit) | Operations and Maintenance | TAR RIVER TRANSIT | ADMINISTRATION |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 82000
TK-5180 | Public Transportation (Transit) | Operations and Maintenance | TAR RIVER TRANSIT | ADMINISTRATION |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 239000
TK-5180 | Public Transportation (Transit) | Operations and Maintenance | TAR RIVER TRANSIT | ADMINISTRATION |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2549000
TK-6103 | Public Transportation (Transit) | Operations and Maintenance | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION |  | ALAMANCE | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 1638000
TK-6103 | Public Transportation (Transit) | Operations and Maintenance | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION |  | ALAMANCE | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 410000
TK-6103 | Public Transportation (Transit) | Operations and Maintenance | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION |  | ALAMANCE | 7 | Burlington-Graham MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2834000
TK-6104 | Public Transportation (Transit) | Operations and Maintenance | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION |  | CAMDEN, CHOWAN, CURRITUCK, PASQUOTANK, PERQUIMANS | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 169000
TK-6104 | Public Transportation (Transit) | Operations and Maintenance | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION |  | CAMDEN, CHOWAN, CURRITUCK, PASQUOTANK, PERQUIMANS | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 500000
TK-6104 | Public Transportation (Transit) | Operations and Maintenance | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION |  | CAMDEN, CHOWAN, CURRITUCK, PASQUOTANK, PERQUIMANS | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 5197000
TK-6105 | Public Transportation (Transit) | Operations and Maintenance | ALLEGHANY COUNTY | ADMINISTRATION |  | ALLEGHANY | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 64000
TK-6105 | Public Transportation (Transit) | Operations and Maintenance | ALLEGHANY COUNTY | ADMINISTRATION |  | ALLEGHANY | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 184000
TK-6105 | Public Transportation (Transit) | Operations and Maintenance | ALLEGHANY COUNTY | ADMINISTRATION |  | ALLEGHANY | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1914000
TK-6106 | Public Transportation (Transit) | Operations and Maintenance | ANSON COUNTY | ADMINISTRATION |  | ANSON | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 80000
TK-6106 | Public Transportation (Transit) | Operations and Maintenance | ANSON COUNTY | ADMINISTRATION |  | ANSON | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 248000
TK-6106 | Public Transportation (Transit) | Operations and Maintenance | ANSON COUNTY | ADMINISTRATION |  | ANSON | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2539000
TK-6107 | Public Transportation (Transit) | Operations and Maintenance | APPALCART | ADMINISTRATION |  | WATAUGA | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 184000
TK-6107 | Public Transportation (Transit) | Operations and Maintenance | APPALCART | ADMINISTRATION |  | WATAUGA | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 560000
TK-6107 | Public Transportation (Transit) | Operations and Maintenance | APPALCART | ADMINISTRATION |  | WATAUGA | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 5814000
TK-6108 | Public Transportation (Transit) | Operations and Maintenance | ASHE COUNTY TRANSPORTATION | ADMINISTRATION |  | ASHE | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 80000
TK-6108 | Public Transportation (Transit) | Operations and Maintenance | ASHE COUNTY TRANSPORTATION | ADMINISTRATION |  | ASHE | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 232000
TK-6108 | Public Transportation (Transit) | Operations and Maintenance | ASHE COUNTY TRANSPORTATION | ADMINISTRATION |  | ASHE | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2426000
TK-6110 | Public Transportation (Transit) | Operations and Maintenance | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION |  | BEAUFORT | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 56000
TK-6110 | Public Transportation (Transit) | Operations and Maintenance | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION |  | BEAUFORT | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 168000
TK-6110 | Public Transportation (Transit) | Operations and Maintenance | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION |  | BEAUFORT | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1745000
TK-6111 | Public Transportation (Transit) | Operations and Maintenance | BLADEN COUNTY | ADMINISTRATION |  | BLADEN | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 48000
TK-6111 | Public Transportation (Transit) | Operations and Maintenance | BLADEN COUNTY | ADMINISTRATION |  | BLADEN | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 144000
TK-6111 | Public Transportation (Transit) | Operations and Maintenance | BLADEN COUNTY | ADMINISTRATION |  | BLADEN | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1515000
TK-6112 | Public Transportation (Transit) | Operations and Maintenance | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION |  | BRUNSWICK | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 73000
TK-6112 | Public Transportation (Transit) | Operations and Maintenance | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION |  | BRUNSWICK | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 218000
TK-6112 | Public Transportation (Transit) | Operations and Maintenance | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION |  | BRUNSWICK | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2214000
TK-6115 | Public Transportation (Transit) | Operations and Maintenance | CARTERET COUNTY | ADMINISTRATION |  | CARTERET | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 11000
TK-6115 | Public Transportation (Transit) | Operations and Maintenance | CARTERET COUNTY | ADMINISTRATION |  | CARTERET | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 32000
TK-6115 | Public Transportation (Transit) | Operations and Maintenance | CARTERET COUNTY | ADMINISTRATION |  | CARTERET | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1409000
TK-6115 | Public Transportation (Transit) | Operations and Maintenance | CARTERET COUNTY | ADMINISTRATION |  | CARTERET | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 446000
TK-6116 | Public Transportation (Transit) | Operations and Maintenance | CASWELL COUNTY | ADMINISTRATION |  | CASWELL | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 30000
TK-6116 | Public Transportation (Transit) | Operations and Maintenance | CASWELL COUNTY | ADMINISTRATION |  | CASWELL | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 68000
TK-6116 | Public Transportation (Transit) | Operations and Maintenance | CASWELL COUNTY | ADMINISTRATION |  | CASWELL | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 669000
TK-6116 | Public Transportation (Transit) | Operations and Maintenance | CASWELL COUNTY | ADMINISTRATION |  | CASWELL | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 18000
TK-6116 | Public Transportation (Transit) | Operations and Maintenance | CASWELL COUNTY | ADMINISTRATION |  | CASWELL | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 68000
TK-6116 | Public Transportation (Transit) | Operations and Maintenance | CASWELL COUNTY | ADMINISTRATION |  | CASWELL | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 715000
TK-6117 | Public Transportation (Transit) | Operations and Maintenance | CHATHAM TRANSIT NETWORK | ADMINISTRATION |  | CHATHAM | 8 | Central Pines RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 96000
TK-6117 | Public Transportation (Transit) | Operations and Maintenance | CHATHAM TRANSIT NETWORK | ADMINISTRATION |  | CHATHAM | 8 | Central Pines RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 287000
TK-6117 | Public Transportation (Transit) | Operations and Maintenance | CHATHAM TRANSIT NETWORK | ADMINISTRATION |  | CHATHAM | 8 | Central Pines RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2915000
TK-6118 | Public Transportation (Transit) | Operations and Maintenance | CHEROKEE COUNTY | ADMINISTRATION |  | CHEROKEE | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 72000
TK-6118 | Public Transportation (Transit) | Operations and Maintenance | CHEROKEE COUNTY | ADMINISTRATION |  | CHEROKEE | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 216000
TK-6118 | Public Transportation (Transit) | Operations and Maintenance | CHEROKEE COUNTY | ADMINISTRATION |  | CHEROKEE | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2217000
TK-6119 | Public Transportation (Transit) | Operations and Maintenance | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | BERTIE, HALIFAX, HERTFORD, NORTHAMPTON | 1, 4 | Peanut Belt RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 200000
TK-6119 | Public Transportation (Transit) | Operations and Maintenance | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | BERTIE, HALIFAX, HERTFORD, NORTHAMPTON | 1, 4 | Peanut Belt RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 592000
TK-6119 | Public Transportation (Transit) | Operations and Maintenance | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | BERTIE, HALIFAX, HERTFORD, NORTHAMPTON | 1, 4 | Peanut Belt RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 5712000
TK-6120 | Public Transportation (Transit) | Operations and Maintenance | CLAY COUNTY | ADMINISTRATION |  | CLAY | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 73000
TK-6120 | Public Transportation (Transit) | Operations and Maintenance | CLAY COUNTY | ADMINISTRATION |  | CLAY | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 213000
TK-6120 | Public Transportation (Transit) | Operations and Maintenance | CLAY COUNTY | ADMINISTRATION |  | CLAY | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2211000
TK-6121 | Public Transportation (Transit) | Operations and Maintenance | COLUMBUS COUNTY | ADMINISTRATION |  | COLUMBUS | 6 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 72000
TK-6121 | Public Transportation (Transit) | Operations and Maintenance | COLUMBUS COUNTY | ADMINISTRATION |  | COLUMBUS | 6 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 208000
TK-6121 | Public Transportation (Transit) | Operations and Maintenance | COLUMBUS COUNTY | ADMINISTRATION |  | COLUMBUS | 6 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2128000
TK-6122 | Public Transportation (Transit) | Operations and Maintenance | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION |  | CRAVEN | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 45000
TK-6122 | Public Transportation (Transit) | Operations and Maintenance | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION |  | CRAVEN | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 48000
TK-6122 | Public Transportation (Transit) | Operations and Maintenance | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION |  | CRAVEN | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 3955000
TK-6122 | Public Transportation (Transit) | Operations and Maintenance | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION |  | CRAVEN | 2 | Down East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 678000
TK-6123 | Public Transportation (Transit) | Operations and Maintenance | CUMBERLAND COUNTY | ADMINISTRATION |  | CUMBERLAND | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 388000
TK-6123 | Public Transportation (Transit) | Operations and Maintenance | CUMBERLAND COUNTY | ADMINISTRATION |  | CUMBERLAND | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 93000
TK-6123 | Public Transportation (Transit) | Operations and Maintenance | CUMBERLAND COUNTY | ADMINISTRATION |  | CUMBERLAND | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 620000
TK-6124 | Public Transportation (Transit) | Operations and Maintenance | DARE COUNTY | ADMINISTRATION |  | DARE | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 48000
TK-6124 | Public Transportation (Transit) | Operations and Maintenance | DARE COUNTY | ADMINISTRATION |  | DARE | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 152000
TK-6124 | Public Transportation (Transit) | Operations and Maintenance | DARE COUNTY | ADMINISTRATION |  | DARE | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1588000
TK-6125 | Public Transportation (Transit) | Operations and Maintenance | DAVIDSON COUNTY | ADMINISTRATION |  | DAVIDSON | 9 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 137000
TK-6125 | Public Transportation (Transit) | Operations and Maintenance | DAVIDSON COUNTY | ADMINISTRATION |  | DAVIDSON | 9 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 243000
TK-6125 | Public Transportation (Transit) | Operations and Maintenance | DAVIDSON COUNTY | ADMINISTRATION |  | DAVIDSON | 9 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2511000
TK-6126 | Public Transportation (Transit) | Operations and Maintenance | DURHAM COUNTY ACCESS | ADMINISTRATION |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 69000
TK-6126 | Public Transportation (Transit) | Operations and Maintenance | DURHAM COUNTY ACCESS | ADMINISTRATION |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 13000
TK-6126 | Public Transportation (Transit) | Operations and Maintenance | DURHAM COUNTY ACCESS | ADMINISTRATION |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 838000
TK-6126 | Public Transportation (Transit) | Operations and Maintenance | DURHAM COUNTY ACCESS | ADMINISTRATION |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 163000
TK-6127 | Public Transportation (Transit) | Operations and Maintenance | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION |  | CHEROKEE, GRAHAM, JACKSON, SWAIN | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 137000
TK-6127 | Public Transportation (Transit) | Operations and Maintenance | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION |  | CHEROKEE, GRAHAM, JACKSON, SWAIN | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 48000
TK-6127 | Public Transportation (Transit) | Operations and Maintenance | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION |  | CHEROKEE, GRAHAM, JACKSON, SWAIN | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1461000
TK-6128 | Public Transportation (Transit) | Operations and Maintenance | GASTON COUNTY ACCESS | ADMINISTRATION |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 769000
TK-6128 | Public Transportation (Transit) | Operations and Maintenance | GASTON COUNTY ACCESS | ADMINISTRATION |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 275000
TK-6128 | Public Transportation (Transit) | Operations and Maintenance | GASTON COUNTY ACCESS | ADMINISTRATION |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2125000
TK-6129 | Public Transportation (Transit) | Operations and Maintenance | GATES COUNTY | ADMINISTRATION |  | GATES | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1632000
TK-6129 | Public Transportation (Transit) | Operations and Maintenance | GATES COUNTY | ADMINISTRATION |  | GATES | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 272000
TK-6131 | Public Transportation (Transit) | Operations and Maintenance | GREENE COUNTY | ADMINISTRATION |  | GREENE | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 47000
TK-6131 | Public Transportation (Transit) | Operations and Maintenance | GREENE COUNTY | ADMINISTRATION |  | GREENE | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 135000
TK-6131 | Public Transportation (Transit) | Operations and Maintenance | GREENE COUNTY | ADMINISTRATION |  | GREENE | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1425000
TK-6132 | Public Transportation (Transit) | Operations and Maintenance | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 928000
TK-6132 | Public Transportation (Transit) | Operations and Maintenance | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 264000
TK-6132 | Public Transportation (Transit) | Operations and Maintenance | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION |  | GUILFORD | 7 | Greensboro Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1927000
TK-6133 | Public Transportation (Transit) | Operations and Maintenance | HARNETT COUNTY | ADMINISTRATION |  | HARNETT | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 88000
TK-6133 | Public Transportation (Transit) | Operations and Maintenance | HARNETT COUNTY | ADMINISTRATION |  | HARNETT | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 264000
TK-6133 | Public Transportation (Transit) | Operations and Maintenance | HARNETT COUNTY | ADMINISTRATION |  | HARNETT | 6 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2700000
TK-6135 | Public Transportation (Transit) | Operations and Maintenance | HYDE COUNTY NON-PROFIT | ADMINISTRATION |  | HYDE | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 40000
TK-6135 | Public Transportation (Transit) | Operations and Maintenance | HYDE COUNTY NON-PROFIT | ADMINISTRATION |  | HYDE | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 120000
TK-6135 | Public Transportation (Transit) | Operations and Maintenance | HYDE COUNTY NON-PROFIT | ADMINISTRATION |  | HYDE | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1264000
TK-6137 | Public Transportation (Transit) | Operations and Maintenance | JACKSON COUNTY | ADMINISTRATION |  | JACKSON | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 72000
TK-6137 | Public Transportation (Transit) | Operations and Maintenance | JACKSON COUNTY | ADMINISTRATION |  | JACKSON | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 224000
TK-6137 | Public Transportation (Transit) | Operations and Maintenance | JACKSON COUNTY | ADMINISTRATION |  | JACKSON | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2336000
TK-6138 | Public Transportation (Transit) | Operations and Maintenance | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | JOHNSTON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 120000
TK-6138 | Public Transportation (Transit) | Operations and Maintenance | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | JOHNSTON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 352000
TK-6138 | Public Transportation (Transit) | Operations and Maintenance | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | JOHNSTON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 3644000
TK-6139 | Public Transportation (Transit) | Operations and Maintenance | KERR AREA TRANSPORTATION | ADMINISTRATION |  | FRANKLIN, GRANVILLE, VANCE, WARREN | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 208000
TK-6139 | Public Transportation (Transit) | Operations and Maintenance | KERR AREA TRANSPORTATION | ADMINISTRATION |  | FRANKLIN, GRANVILLE, VANCE, WARREN | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 616000
TK-6139 | Public Transportation (Transit) | Operations and Maintenance | KERR AREA TRANSPORTATION | ADMINISTRATION |  | FRANKLIN, GRANVILLE, VANCE, WARREN | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 6319000
TK-6140 | Public Transportation (Transit) | Operations and Maintenance | LEE COUNTY | ADMINISTRATION |  | LEE | 8 | Central Pines RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 64000
TK-6140 | Public Transportation (Transit) | Operations and Maintenance | LEE COUNTY | ADMINISTRATION |  | LEE | 8 | Central Pines RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 192000
TK-6140 | Public Transportation (Transit) | Operations and Maintenance | LEE COUNTY | ADMINISTRATION |  | LEE | 8 | Central Pines RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1958000
TK-6141 | Public Transportation (Transit) | Operations and Maintenance | LINCOLN COUNTY | ADMINISTRATION |  | LINCOLN | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 263000
TK-6141 | Public Transportation (Transit) | Operations and Maintenance | LINCOLN COUNTY | ADMINISTRATION |  | LINCOLN | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 275000
TK-6141 | Public Transportation (Transit) | Operations and Maintenance | LINCOLN COUNTY | ADMINISTRATION |  | LINCOLN | 12 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2523000
TK-6142 | Public Transportation (Transit) | Operations and Maintenance | MACON COUNTY | ADMINISTRATION |  | MACON | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 79000
TK-6142 | Public Transportation (Transit) | Operations and Maintenance | MACON COUNTY | ADMINISTRATION |  | MACON | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 231000
TK-6142 | Public Transportation (Transit) | Operations and Maintenance | MACON COUNTY | ADMINISTRATION |  | MACON | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2503000
TK-6143 | Public Transportation (Transit) | Operations and Maintenance | MADISON COUNTY TRANSPORTATION | ADMINISTRATION |  | MADISON | 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 56000
TK-6143 | Public Transportation (Transit) | Operations and Maintenance | MADISON COUNTY TRANSPORTATION | ADMINISTRATION |  | MADISON | 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 160000
TK-6143 | Public Transportation (Transit) | Operations and Maintenance | MADISON COUNTY TRANSPORTATION | ADMINISTRATION |  | MADISON | 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1691000
TK-6144 | Public Transportation (Transit) | Operations and Maintenance | MARTIN COUNTY | ADMINISTRATION |  | MARTIN | 1 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 72000
TK-6144 | Public Transportation (Transit) | Operations and Maintenance | MARTIN COUNTY | ADMINISTRATION |  | MARTIN | 1 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 216000
TK-6144 | Public Transportation (Transit) | Operations and Maintenance | MARTIN COUNTY | ADMINISTRATION |  | MARTIN | 1 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2241000
TK-6145 | Public Transportation (Transit) | Operations and Maintenance | MECKLENBURG TRANSPORTATION | ADMINISTRATION |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 1508000
TK-6145 | Public Transportation (Transit) | Operations and Maintenance | MECKLENBURG TRANSPORTATION | ADMINISTRATION |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 291000
TK-6145 | Public Transportation (Transit) | Operations and Maintenance | MECKLENBURG TRANSPORTATION | ADMINISTRATION |  | MECKLENBURG | 10 | Charlotte Regional TPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1680000
TK-6146 | Public Transportation (Transit) | Operations and Maintenance | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION |  | MITCHELL | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 72000
TK-6146 | Public Transportation (Transit) | Operations and Maintenance | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION |  | MITCHELL | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 216000
TK-6146 | Public Transportation (Transit) | Operations and Maintenance | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION |  | MITCHELL | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2257000
TK-6147 | Public Transportation (Transit) | Operations and Maintenance | MOORE COUNTY | ADMINISTRATION |  | MOORE | 8 | Central Pines RPO, Sandhills MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 96000
TK-6147 | Public Transportation (Transit) | Operations and Maintenance | MOORE COUNTY | ADMINISTRATION |  | MOORE | 8 | Central Pines RPO, Sandhills MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 288000
TK-6147 | Public Transportation (Transit) | Operations and Maintenance | MOORE COUNTY | ADMINISTRATION |  | MOORE | 8 | Central Pines RPO, Sandhills MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2505000
TK-6147 | Public Transportation (Transit) | Operations and Maintenance | MOORE COUNTY | ADMINISTRATION |  | MOORE | 8 | Central Pines RPO, Sandhills MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 482000
TK-6148 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION |  | BUNCOMBE | 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 1359000
TK-6148 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION |  | BUNCOMBE | 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 529000
TK-6148 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION |  | BUNCOMBE | 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5309 | OPERATIONS | 199000
TK-6148 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION |  | BUNCOMBE | 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 3184000
TK-6148 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION |  | BUNCOMBE | 13 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 881000
TK-6149 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN PROJECTS, INC. | ADMINISTRATION |  | HAYWOOD | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 152000
TK-6149 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN PROJECTS, INC. | ADMINISTRATION |  | HAYWOOD | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 276000
TK-6149 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN PROJECTS, INC. | ADMINISTRATION |  | HAYWOOD | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2365000
TK-6149 | Public Transportation (Transit) | Operations and Maintenance | MOUNTAIN PROJECTS, INC. | ADMINISTRATION |  | HAYWOOD | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 471000
TK-6151 | Public Transportation (Transit) | Operations and Maintenance | ORANGE PUBLIC TRANSIT | ADMINISTRATION |  | ORANGE | 7 | Central Pines RPO |  | Public Transit |  | S | OPERATIONS | 296000
TK-6151 | Public Transportation (Transit) | Operations and Maintenance | ORANGE PUBLIC TRANSIT | ADMINISTRATION |  | ORANGE | 7 | Central Pines RPO |  | Public Transit |  | L | OPERATIONS | 221000
TK-6151 | Public Transportation (Transit) | Operations and Maintenance | ORANGE PUBLIC TRANSIT | ADMINISTRATION |  | ORANGE | 7 | Central Pines RPO |  | Public Transit |  | 5311 | OPERATIONS | 1694000
TK-6151 | Public Transportation (Transit) | Operations and Maintenance | ORANGE PUBLIC TRANSIT | ADMINISTRATION |  | ORANGE | 7 | Central Pines RPO |  | Public Transit |  | 5311 | ADMINISTRATIVE | 370000
TK-6152 | Public Transportation (Transit) | Operations and Maintenance | PENDER ADULT SERVICES, INC. | ADMINISTRATION |  | PENDER | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 48000
TK-6152 | Public Transportation (Transit) | Operations and Maintenance | PENDER ADULT SERVICES, INC. | ADMINISTRATION |  | PENDER | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 144000
TK-6152 | Public Transportation (Transit) | Operations and Maintenance | PENDER ADULT SERVICES, INC. | ADMINISTRATION |  | PENDER | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1245000
TK-6152 | Public Transportation (Transit) | Operations and Maintenance | PENDER ADULT SERVICES, INC. | ADMINISTRATION |  | PENDER | 3 | Cape Fear RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 235000
TK-6153 | Public Transportation (Transit) | Operations and Maintenance | PERSON COUNTY | ADMINISTRATION |  | PERSON | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 66000
TK-6153 | Public Transportation (Transit) | Operations and Maintenance | PERSON COUNTY | ADMINISTRATION |  | PERSON | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 204000
TK-6153 | Public Transportation (Transit) | Operations and Maintenance | PERSON COUNTY | ADMINISTRATION |  | PERSON | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1822000
TK-6153 | Public Transportation (Transit) | Operations and Maintenance | PERSON COUNTY | ADMINISTRATION |  | PERSON | 5 | Kerr-Tar RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 151000
TK-6154 | Public Transportation (Transit) | Operations and Maintenance | PITT COUNTY | ADMINISTRATION |  | PITT | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 163000
TK-6154 | Public Transportation (Transit) | Operations and Maintenance | PITT COUNTY | ADMINISTRATION |  | PITT | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 213000
TK-6154 | Public Transportation (Transit) | Operations and Maintenance | PITT COUNTY | ADMINISTRATION |  | PITT | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1769000
TK-6154 | Public Transportation (Transit) | Operations and Maintenance | PITT COUNTY | ADMINISTRATION |  | PITT | 2 | Mid-East RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 358000
TK-6155 | Public Transportation (Transit) | Operations and Maintenance | POLK COUNTY TRANSPORTATION | ADMINISTRATION |  | POLK | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 73000
TK-6155 | Public Transportation (Transit) | Operations and Maintenance | POLK COUNTY TRANSPORTATION | ADMINISTRATION |  | POLK | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 227000
TK-6155 | Public Transportation (Transit) | Operations and Maintenance | POLK COUNTY TRANSPORTATION | ADMINISTRATION |  | POLK | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2035000
TK-6155 | Public Transportation (Transit) | Operations and Maintenance | POLK COUNTY TRANSPORTATION | ADMINISTRATION |  | POLK | 14 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 368000
TK-6156 | Public Transportation (Transit) | Operations and Maintenance | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION |  | MONTGOMERY, RANDOLPH | 8 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 136000
TK-6156 | Public Transportation (Transit) | Operations and Maintenance | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION |  | MONTGOMERY, RANDOLPH | 8 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 415000
TK-6156 | Public Transportation (Transit) | Operations and Maintenance | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION |  | MONTGOMERY, RANDOLPH | 8 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 3601000
TK-6156 | Public Transportation (Transit) | Operations and Maintenance | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION |  | MONTGOMERY, RANDOLPH | 8 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 674000
TK-6158 | Public Transportation (Transit) | Operations and Maintenance | ROBESON COUNTY | ADMINISTRATION |  | ROBESON | 6 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 80000
TK-6158 | Public Transportation (Transit) | Operations and Maintenance | ROBESON COUNTY | ADMINISTRATION |  | ROBESON | 6 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 240000
TK-6158 | Public Transportation (Transit) | Operations and Maintenance | ROBESON COUNTY | ADMINISTRATION |  | ROBESON | 6 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2080000
TK-6158 | Public Transportation (Transit) | Operations and Maintenance | ROBESON COUNTY | ADMINISTRATION |  | ROBESON | 6 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 400000
TK-6159 | Public Transportation (Transit) | Operations and Maintenance | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | ROCKINGHAM | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 72000
TK-6159 | Public Transportation (Transit) | Operations and Maintenance | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | ROCKINGHAM | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 208000
TK-6159 | Public Transportation (Transit) | Operations and Maintenance | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | ROCKINGHAM | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1841000
TK-6159 | Public Transportation (Transit) | Operations and Maintenance | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION |  | ROCKINGHAM | 7 | Piedmont Triad RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 352000
TK-6160 | Public Transportation (Transit) | Operations and Maintenance | ROWAN COUNTY | ADMINISTRATION |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 93000
TK-6160 | Public Transportation (Transit) | Operations and Maintenance | ROWAN COUNTY | ADMINISTRATION |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 215000
TK-6160 | Public Transportation (Transit) | Operations and Maintenance | ROWAN COUNTY | ADMINISTRATION |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1885000
TK-6160 | Public Transportation (Transit) | Operations and Maintenance | ROWAN COUNTY | ADMINISTRATION |  | ROWAN | 9 | Cabarrus-Rowan MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 362000
TK-6161 | Public Transportation (Transit) | Operations and Maintenance | RUTHERFORD COUNTY | ADMINISTRATION |  | RUTHERFORD | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 80000
TK-6161 | Public Transportation (Transit) | Operations and Maintenance | RUTHERFORD COUNTY | ADMINISTRATION |  | RUTHERFORD | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 232000
TK-6161 | Public Transportation (Transit) | Operations and Maintenance | RUTHERFORD COUNTY | ADMINISTRATION |  | RUTHERFORD | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2049000
TK-6161 | Public Transportation (Transit) | Operations and Maintenance | RUTHERFORD COUNTY | ADMINISTRATION |  | RUTHERFORD | 13 | Foothills RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 392000
TK-6162 | Public Transportation (Transit) | Operations and Maintenance | SAMPSON COUNTY | ADMINISTRATION |  | SAMPSON | 3 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 64000
TK-6162 | Public Transportation (Transit) | Operations and Maintenance | SAMPSON COUNTY | ADMINISTRATION |  | SAMPSON | 3 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 192000
TK-6162 | Public Transportation (Transit) | Operations and Maintenance | SAMPSON COUNTY | ADMINISTRATION |  | SAMPSON | 3 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1640000
TK-6162 | Public Transportation (Transit) | Operations and Maintenance | SAMPSON COUNTY | ADMINISTRATION |  | SAMPSON | 3 | Mid-Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 316000
TK-6163 | Public Transportation (Transit) | Operations and Maintenance | SCOTLAND COUNTY | ADMINISTRATION |  | SCOTLAND | 8 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 48000
TK-6163 | Public Transportation (Transit) | Operations and Maintenance | SCOTLAND COUNTY | ADMINISTRATION |  | SCOTLAND | 8 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 136000
TK-6163 | Public Transportation (Transit) | Operations and Maintenance | SCOTLAND COUNTY | ADMINISTRATION |  | SCOTLAND | 8 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1188000
TK-6163 | Public Transportation (Transit) | Operations and Maintenance | SCOTLAND COUNTY | ADMINISTRATION |  | SCOTLAND | 8 | Lumber River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 236000
TK-6164 | Public Transportation (Transit) | Operations and Maintenance | SCUSA TRANSPORTATION | ADMINISTRATION |  | STANLY | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 88000
TK-6164 | Public Transportation (Transit) | Operations and Maintenance | SCUSA TRANSPORTATION | ADMINISTRATION |  | STANLY | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 272000
TK-6164 | Public Transportation (Transit) | Operations and Maintenance | SCUSA TRANSPORTATION | ADMINISTRATION |  | STANLY | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2352000
TK-6164 | Public Transportation (Transit) | Operations and Maintenance | SCUSA TRANSPORTATION | ADMINISTRATION |  | STANLY | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 452000
TK-6165 | Public Transportation (Transit) | Operations and Maintenance | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION |  | SWAIN | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 132000
TK-6165 | Public Transportation (Transit) | Operations and Maintenance | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION |  | SWAIN | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 101000
TK-6165 | Public Transportation (Transit) | Operations and Maintenance | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION |  | SWAIN | 14 | Southwestern RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 1659000
TK-6166 | Public Transportation (Transit) | Operations and Maintenance | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 120000
TK-6166 | Public Transportation (Transit) | Operations and Maintenance | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 360000
TK-6166 | Public Transportation (Transit) | Operations and Maintenance | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 3108000
TK-6166 | Public Transportation (Transit) | Operations and Maintenance | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION |  | CLEVELAND | 12 | Gaston-Cleveland-Lincoln MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 577000
TK-6167 | Public Transportation (Transit) | Operations and Maintenance | TRANSYLVANIA COUNTY | ADMINISTRATION |  | TRANSYLVANIA | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 54000
TK-6167 | Public Transportation (Transit) | Operations and Maintenance | TRANSYLVANIA COUNTY | ADMINISTRATION |  | TRANSYLVANIA | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 126000
TK-6167 | Public Transportation (Transit) | Operations and Maintenance | TRANSYLVANIA COUNTY | ADMINISTRATION |  | TRANSYLVANIA | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1820000
TK-6167 | Public Transportation (Transit) | Operations and Maintenance | TRANSYLVANIA COUNTY | ADMINISTRATION |  | TRANSYLVANIA | 14 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 341000
TK-6168 | Public Transportation (Transit) | Operations and Maintenance | TYRELL COUNTY | ADMINISTRATION |  | TYRRELL | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 19000
TK-6168 | Public Transportation (Transit) | Operations and Maintenance | TYRELL COUNTY | ADMINISTRATION |  | TYRRELL | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 3000
TK-6168 | Public Transportation (Transit) | Operations and Maintenance | TYRELL COUNTY | ADMINISTRATION |  | TYRRELL | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 242000
TK-6168 | Public Transportation (Transit) | Operations and Maintenance | TYRELL COUNTY | ADMINISTRATION |  | TYRRELL | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 44000
TK-6169 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY | ADMINISTRATION |  | UNION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 139000
TK-6169 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY | ADMINISTRATION |  | UNION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 209000
TK-6169 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY | ADMINISTRATION |  | UNION | 10 | Rocky River RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2167000
TK-6170 | Public Transportation (Transit) | Operations and Maintenance | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 1756000
TK-6170 | Public Transportation (Transit) | Operations and Maintenance | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 455000
TK-6170 | Public Transportation (Transit) | Operations and Maintenance | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2416000
TK-6170 | Public Transportation (Transit) | Operations and Maintenance | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION |  | WAKE | 5 | Capital Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 795000
TK-6171 | Public Transportation (Transit) | Operations and Maintenance | WASHINGTON COUNTY | ADMINISTRATION |  | WASHINGTON | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 32000
TK-6171 | Public Transportation (Transit) | Operations and Maintenance | WASHINGTON COUNTY | ADMINISTRATION |  | WASHINGTON | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 104000
TK-6171 | Public Transportation (Transit) | Operations and Maintenance | WASHINGTON COUNTY | ADMINISTRATION |  | WASHINGTON | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 929000
TK-6171 | Public Transportation (Transit) | Operations and Maintenance | WASHINGTON COUNTY | ADMINISTRATION |  | WASHINGTON | 1 | Albemarle RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 176000
TK-6172 | Public Transportation (Transit) | Operations and Maintenance | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION |  | WILKES | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 88000
TK-6172 | Public Transportation (Transit) | Operations and Maintenance | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION |  | WILKES | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 272000
TK-6172 | Public Transportation (Transit) | Operations and Maintenance | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION |  | WILKES | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2376000
TK-6172 | Public Transportation (Transit) | Operations and Maintenance | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION |  | WILKES | 11 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 456000
TK-6173 | Public Transportation (Transit) | Operations and Maintenance | WILSON COUNTY | ADMINISTRATION |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 33000
TK-6173 | Public Transportation (Transit) | Operations and Maintenance | WILSON COUNTY | ADMINISTRATION |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 105000
TK-6173 | Public Transportation (Transit) | Operations and Maintenance | WILSON COUNTY | ADMINISTRATION |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 912000
TK-6173 | Public Transportation (Transit) | Operations and Maintenance | WILSON COUNTY | ADMINISTRATION |  | WILSON | 4 | Upper Coastal Plain RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 225000
TK-6174 | Public Transportation (Transit) | Operations and Maintenance | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION |  | DAVIE, STOKES, SURRY, YADKIN | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 168000
TK-6174 | Public Transportation (Transit) | Operations and Maintenance | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION |  | DAVIE, STOKES, SURRY, YADKIN | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 512000
TK-6174 | Public Transportation (Transit) | Operations and Maintenance | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION |  | DAVIE, STOKES, SURRY, YADKIN | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 4432000
TK-6174 | Public Transportation (Transit) | Operations and Maintenance | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION |  | DAVIE, STOKES, SURRY, YADKIN | 9, 11 | Northwest Piedmont RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 890000
TK-6175 | Public Transportation (Transit) | Operations and Maintenance | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION |  | YANCEY | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 56000
TK-6175 | Public Transportation (Transit) | Operations and Maintenance | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION |  | YANCEY | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 176000
TK-6175 | Public Transportation (Transit) | Operations and Maintenance | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION |  | YANCEY | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 1508000
TK-6175 | Public Transportation (Transit) | Operations and Maintenance | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION |  | YANCEY | 13 | High Country RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 290000
TK-6176 | Public Transportation (Transit) | Operations and Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | OPERATIONS | 22000
TK-6176 | Public Transportation (Transit) | Operations and Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 66000
TK-6176 | Public Transportation (Transit) | Operations and Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 2314000
TK-6176 | Public Transportation (Transit) | Operations and Maintenance | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION |  | NEW HANOVER | 3 | Wilmington Urban Area MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 461000
TK-6177 | Public Transportation (Transit) | Operations and Maintenance | DUPLIN COUNTY | ADMINISTRATION |  | DUPLIN | 3 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 80000
TK-6177 | Public Transportation (Transit) | Operations and Maintenance | DUPLIN COUNTY | ADMINISTRATION |  | DUPLIN | 3 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 248000
TK-6177 | Public Transportation (Transit) | Operations and Maintenance | DUPLIN COUNTY | ADMINISTRATION |  | DUPLIN | 3 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 2593000
TK-6178 | Public Transportation (Transit) | Operations and Maintenance | LENOIR COUNTY | ADMINISTRATION |  | LENOIR | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | S | ADMINISTRATIVE | 105000
TK-6178 | Public Transportation (Transit) | Operations and Maintenance | LENOIR COUNTY | ADMINISTRATION |  | LENOIR | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | ADMINISTRATIVE | 314000
TK-6178 | Public Transportation (Transit) | Operations and Maintenance | LENOIR COUNTY | ADMINISTRATION |  | LENOIR | 2 | Eastern Carolina RPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | ADMINISTRATIVE | 3288000
TK-6179 | Public Transportation (Transit) | Operations and Maintenance | IREDELL COUNTY | ADMINISTRATION |  | IREDELL | 12 |  | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5311 | OPERATIONS | 3120000
TK-6181 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5311 ADMINISTRATIVE |  | STATEWIDE | 99 | STATEWIDE PROJECT | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS | Public Transit |  | 5311 | ADMINISTRATIVE | 15025000
TL-0001 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | CONSTRUCT AN URBAN FIXED-ROUTE SATELLITE TRANSFER FACILITY FOR JACKSONVILLE TRANSIT TO INCLUDE PUBLIC PARKING, SHELTERS, RESTROOMS AND PESSENGER TERMINAL |  | ONSLOW | 3 | Jacksonville Urban Area MPO | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | CONSTRUCTION | 1000000
TL-0002 | Public Transportation (Transit) | Capital (Non-STI) | JACKSONVILLE TRANSIT | CONSTRUCT PEDESTRIAN ACCESS AND SAFETY IMPROVEMENTS FOR JACKSONVILLE TRANSIT WITHIN 1/2 MILE OF HIGH VOLUME URBAN FIXED ROUTE BUS STOPS. IMPROVEMENTS WILL INCLUDE NEW SIDE WALK CONNECTIONS, ADA RETROFIT OF EXISTING SIDE WALKS AND CONSTRUCTION OF HIGH VISIBILITY CROSSWALKS AT KEY ROADWAY INTERSECTIONS. |  | ONSLOW | 3 | Jacksonville Urban Area MPO | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | CONSTRUCTION | 900000
TL-0005 | Public Transportation (Transit) | Locally Selected | CONCORD KANNAPOLIS AREA TRANSIT | EXPANSION BUS |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 |  | BGDA | CONSTRUCTION | 580000
TL-0005 | Public Transportation (Transit) | Locally Selected | CONCORD KANNAPOLIS AREA TRANSIT | EXPANSION BUS |  | CABARRUS, ROWAN | 9, 10 | Cabarrus-Rowan MPO |  | Division 9, 10 |  | L | CONSTRUCTION | 145000
TL-0006 | Public Transportation (Transit) | Capital (Non-STI) | GO RALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT WESTERN CORRIDOR (DOWNTOWN RALEIGH TO DOWNTOWN CARY). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 1500000
TL-0006 | Public Transportation (Transit) | Capital (Non-STI) | GO RALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT WESTERN CORRIDOR (DOWNTOWN RALEIGH TO DOWNTOWN CARY). |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 45168000
TL-0007 | Public Transportation (Transit) | Planning | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN ON BUS RAPID TRANSIT IN WAKE TRANSIT PLAN NORTHERN CORRIDOR. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 5540000
TL-0008 | Public Transportation (Transit) | Planning | GOTRIANGLE | EARLY PROJECT DEVELOPMENT ACTIVITIES FOR COMMUTER RAIL FROM GARNER TO WESTERN DURHAM |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 9200000
TL-0009 | Public Transportation (Transit) | Capital (Non-STI) | GREENVILLE AREA TRANSIT | FLEET SERVICE BUILDING EXPANSION. |  | PITT | 2 | Greenville Urban Area MPO |  | Public Transit |  | L | CONSTRUCTION | 98000
TL-0009 | Public Transportation (Transit) | Capital (Non-STI) | GREENVILLE AREA TRANSIT | FLEET SERVICE BUILDING EXPANSION. |  | PITT | 2 | Greenville Urban Area MPO |  | Public Transit |  | CARES | CONSTRUCTION | 878000
TL-0011 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | ENGINEERING | 32000
TL-0011 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 32000
TL-0011 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | RIGHT-OF-WAY | 9000
TL-0011 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | RIGHT-OF-WAY | 9000
TL-0011 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | BGDA | CONSTRUCTION | 126000
TL-0011 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 126000
TL-0012 | Public Transportation (Transit) | Operations and Maintenance | GTA | EXPANDED SUNDAY SERVICE, NEW SERVICE OPERATIONAL FUNDING |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | CMAQ | OPERATIONS | 2164000
TL-0012 | Public Transportation (Transit) | Operations and Maintenance | GTA | EXPANDED SUNDAY SERVICE, NEW SERVICE OPERATIONAL FUNDING |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 541000
TL-0013 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT SOUTHERN CORRIDOR ( DOWNTOWN RALEIGH TO DOWNTOWN GARNER) |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | PLANNING | 1500000
TL-0013 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT SOUTHERN CORRIDOR ( DOWNTOWN RALEIGH TO DOWNTOWN GARNER) |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 27777000
TL-0014 | Public Transportation (Transit) | Locally Selected | DAVIDSON COUNTY TRANSPORTATION SYSTEM | INSTALLING COVERED BUS SHELTERS WITH ADA ACCESS TO MAJOR STOPS SUCH AS WALMART AND BIG LOTS. INSTALL SIMME SEATS AT THE REMAINDER OF BUS STOPS. SIMME SEATS PROVIDE TWO SEATS ATTACHED TO THE BUS STOP SIGN POLE. |  | DAVIDSON | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CAPITAL | 112000
TL-0014 | Public Transportation (Transit) | Locally Selected | DAVIDSON COUNTY TRANSPORTATION SYSTEM | INSTALLING COVERED BUS SHELTERS WITH ADA ACCESS TO MAJOR STOPS SUCH AS WALMART AND BIG LOTS. INSTALL SIMME SEATS AT THE REMAINDER OF BUS STOPS. SIMME SEATS PROVIDE TWO SEATS ATTACHED TO THE BUS STOP SIGN POLE. |  | DAVIDSON | 9 | Winston-Salem Area TPO |  | Division 9 |  | L | CAPITAL | 28000
TL-0015 | Public Transportation (Transit) | Capital (Non-STI) | TAR RIVER TRANSIT | PURCHASE AND INSTALL 20 BUS SHELTERS |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Public Transit |  | CARES | CAPITAL | 150000
TL-0016 | Public Transportation (Transit) | Capital (Non-STI) | TAR RIVER TRANSIT | UPDATE THE TAR RIVER TANSIT AUTOMATED VEHICLE LOCATOR SYSTEM |  | EDGECOMBE, NASH | 4 | Rocky Mount Urban Area MPO |  | Public Transit |  | CARES | CAPITAL | 300000
TL-0017 | Public Transportation (Transit) | Locally Selected | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPITAL IMPROVEMENT PROJECT TO SECURE AUTOMATIC PASSENGER COUNTER (APC) TECHNOLOGY FOR THE PURPOSE OF COLLECTING STOP LEVEL BOARDINGS AND ALIGHTINGS FOR FIXED ROUTE PUBLIC TRANSPORTATION SERVICES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | BGDA | CAPITAL | 160000
TL-0017 | Public Transportation (Transit) | Locally Selected | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPITAL IMPROVEMENT PROJECT TO SECURE AUTOMATIC PASSENGER COUNTER (APC) TECHNOLOGY FOR THE PURPOSE OF COLLECTING STOP LEVEL BOARDINGS AND ALIGHTINGS FOR FIXED ROUTE PUBLIC TRANSPORTATION SERVICES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Division 3 |  | L | CAPITAL | 40000
TL-0018 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | CMAQ | PLANNING | 80000
TL-0018 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | PLANNING | 20000
TL-0018 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | CMAQ | CONSTRUCTION | 400000
TL-0018 | Public Transportation (Transit) | Capital (Non-STI) | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | CONSTRUCTION | 100000
TL-0019 | Public Transportation (Transit) | Capital (Non-STI) | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | ENGINEERING | 38000
TL-0019 | Public Transportation (Transit) | Capital (Non-STI) | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | ENGINEERING | 13000
TL-0019 | Public Transportation (Transit) | Capital (Non-STI) | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | RIGHT-OF-WAY | 125000
TL-0019 | Public Transportation (Transit) | Capital (Non-STI) | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | RIGHT-OF-WAY | 42000
TL-0019 | Public Transportation (Transit) | Capital (Non-STI) | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | CMAQ | CONSTRUCTION | 858000
TL-0019 | Public Transportation (Transit) | Capital (Non-STI) | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. |  | WAKE | 5 | Capital Area MPO |  | Exempt |  | L | CONSTRUCTION | 286000
TL-0020 | Public Transportation (Transit) | Locally Selected | GORALEIGH | RALEIGH UNION STATION BUS FACILITY INTER-CITY/COMMUTER RAIL PARK AND RIDE |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | CMAQ | CONSTRUCTION | 4500000
TL-0020 | Public Transportation (Transit) | Locally Selected | GORALEIGH | RALEIGH UNION STATION BUS FACILITY INTER-CITY/COMMUTER RAIL PARK AND RIDE |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 1125000
TL-0021 | Public Transportation (Transit) | Locally Selected | CONCORD | PURCHASE NEW 35 FOOT HYBRID ELECTRIC HEAVY DUTY LOW FLOOR BUS |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | BGDACV | CONSTRUCTION | 602000
TL-0021 | Public Transportation (Transit) | Locally Selected | CONCORD | PURCHASE NEW 35 FOOT HYBRID ELECTRIC HEAVY DUTY LOW FLOOR BUS |  | CABARRUS | 10 | Cabarrus-Rowan MPO |  | Division 10 |  | L | CONSTRUCTION | 123000
TL-0023 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | BUILD PARK AND RIDE FACILITY AT GORMAN STREET AT I-40 IN RALEIGH |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | ENGINEERING | 1432000 | FY 2025: 1432000
TL-0023 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | BUILD PARK AND RIDE FACILITY AT GORMAN STREET AT I-40 IN RALEIGH |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 1614000 | FY 2027: 1614000
TL-0025 | Public Transportation (Transit) | Locally Selected | WINSTON SALEM TRANSIT AUTHORITY | THE INNOVATIVE COORDINATED ACCESS AND MOBILITY (ICAM) GRANT WILL BE USED TO IMPROVE PARATRANSIT TRACKING AND ACCESSIBILITY THROUGH GPS AND NOTIFICATION SERVICES, AS WELL AS PROVIDE MOBILE TICKETING OPTIONS FOR WINSTON SALEM TRANSIT AUTHORITY`S (WSTA) FIXED ROUTE BUS SERVICES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 80000
TL-0025 | Public Transportation (Transit) | Locally Selected | WINSTON SALEM TRANSIT AUTHORITY | THE INNOVATIVE COORDINATED ACCESS AND MOBILITY (ICAM) GRANT WILL BE USED TO IMPROVE PARATRANSIT TRACKING AND ACCESSIBILITY THROUGH GPS AND NOTIFICATION SERVICES, AS WELL AS PROVIDE MOBILE TICKETING OPTIONS FOR WINSTON SALEM TRANSIT AUTHORITY`S (WSTA) FIXED ROUTE BUS SERVICES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5307 | OPERATIONS | 320000
TL-0026 | Public Transportation (Transit) | Locally Selected | ORANGE COUNTY | UPDATE THREE BUS SHELTERS IN ORANGE COUNTY ON GOVERNMENT PROPERTY. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 100000
TL-0026 | Public Transportation (Transit) | Locally Selected | ORANGE COUNTY | UPDATE THREE BUS SHELTERS IN ORANGE COUNTY ON GOVERNMENT PROPERTY. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | TADA | CONSTRUCTION | 24000 | FY 2025: 24000
TL-0026 | Public Transportation (Transit) | Locally Selected | ORANGE COUNTY | UPDATE THREE BUS SHELTERS IN ORANGE COUNTY ON GOVERNMENT PROPERTY. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L | CONSTRUCTION | 25000
TL-0026 | Public Transportation (Transit) | Locally Selected | ORANGE COUNTY | UPDATE THREE BUS SHELTERS IN ORANGE COUNTY ON GOVERNMENT PROPERTY. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 6000 | FY 2025: 6000
TL-0027 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | THE NC 54-FALCONBRIDGE CONSTRUCTION PROJECT AIMS TO ADDRESS CRITICAL TRANSIT ACCESS AND TRANSIT OPERATIONS SAFETY CONCERNS ALONG NC 54 IN THE FALCONBRIDGE AREA IN SOUTHWESTERN DURHAM COUNTY, THEREBY INCREASING TRANSIT RIDERSHIP AND REDUCING EMISSIONS. THE PROJECT IS LOCATED WITHIN CITY OF DURHAM CITY LIMITS FROM FARRINGTON ROAD TO HUNTINGRIDGE ROAD. THE PROJECT WILL PROVIDE SAFE PEDSTRIAN CONNECTIONS FOR TRANSIT USERS TO EXISTING AND PLANNED SIGNALIZED CROSSINGS IN THIS CORRIDOR, GIVEN THE HIGH SPPEDS AND TRAFFIC VOLUMES ON NC-54. THE PROJECT INCLUDES CONSTRUCTION OF BUS STOPLANDING PADS, SHELTERS, BENCHES, BUT PULLOUT AND TAPERS, SIDEWALK, CURB AND GUTTER, CURB RAMPS, CROSSWALKS, PEDSTRIAN MEDIAN REFUDE ISLANDS, APPROPRIATE SAFETY SIGNAGE, PEDSTRIAN SIGNAL HEADS AND COMPLIMENTARY TRAFFIC SIGNAL MODIFICATIONS, AND OTHER SUPPORTING ROADWAY MODIFICATIONS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | CMAQ | CONSTRUCTION | 903000
TL-0027 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | THE NC 54-FALCONBRIDGE CONSTRUCTION PROJECT AIMS TO ADDRESS CRITICAL TRANSIT ACCESS AND TRANSIT OPERATIONS SAFETY CONCERNS ALONG NC 54 IN THE FALCONBRIDGE AREA IN SOUTHWESTERN DURHAM COUNTY, THEREBY INCREASING TRANSIT RIDERSHIP AND REDUCING EMISSIONS. THE PROJECT IS LOCATED WITHIN CITY OF DURHAM CITY LIMITS FROM FARRINGTON ROAD TO HUNTINGRIDGE ROAD. THE PROJECT WILL PROVIDE SAFE PEDSTRIAN CONNECTIONS FOR TRANSIT USERS TO EXISTING AND PLANNED SIGNALIZED CROSSINGS IN THIS CORRIDOR, GIVEN THE HIGH SPPEDS AND TRAFFIC VOLUMES ON NC-54. THE PROJECT INCLUDES CONSTRUCTION OF BUS STOPLANDING PADS, SHELTERS, BENCHES, BUT PULLOUT AND TAPERS, SIDEWALK, CURB AND GUTTER, CURB RAMPS, CROSSWALKS, PEDSTRIAN MEDIAN REFUDE ISLANDS, APPROPRIATE SAFETY SIGNAGE, PEDSTRIAN SIGNAL HEADS AND COMPLIMENTARY TRAFFIC SIGNAL MODIFICATIONS, AND OTHER SUPPORTING ROADWAY MODIFICATIONS. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | CONSTRUCTION | 233000
TL-0029 | Public Transportation (Transit) | Locally Selected | LINK TRANSIT | CAPITAL IMPROVEMENTS FOR TRANSIT VEHICLES. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 295000 | FY 2025: 45000; FY 2026: 45000; FY 2027: 45000; FY 2028: 45000
TL-0029 | Public Transportation (Transit) | Locally Selected | LINK TRANSIT | CAPITAL IMPROVEMENTS FOR TRANSIT VEHICLES. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 1255000 | FY 2025: 185000; FY 2026: 185000; FY 2027: 185000; FY 2028: 185000
TL-0030 | Public Transportation (Transit) | Locally Selected | INDIAN TRAIL | INSTALL TYPE TWO ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSINGS PATH PARK. |  | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 468000
TL-0030 | Public Transportation (Transit) | Locally Selected | INDIAN TRAIL | INSTALL TYPE TWO ELECTRIC VEHICLE CHARGERS AT CROOKED CREEK PARK, CHESTNUT SQUARE PARK, AND CROSSINGS PATH PARK. |  | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 117000
TL-0031 | Public Transportation (Transit) | Locally Selected | UNION COUNTY TRANSPORTATION | LOW EMISSION ALTERNATIVE FUEL CONVERSION (MOTOR POOL FACILITY). |  | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 160000
TL-0031 | Public Transportation (Transit) | Locally Selected | UNION COUNTY TRANSPORTATION | LOW EMISSION ALTERNATIVE FUEL CONVERSION (MOTOR POOL FACILITY). |  | UNION | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 40000
TL-0032 | Public Transportation (Transit) | Locally Selected | CATS | INSTALL ELECTRIC BUS CHARGERS AT NORTH DAVIDSON AND SOUTH TRYON BUS GARAGES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 5341000
TL-0032 | Public Transportation (Transit) | Locally Selected | CATS | INSTALL ELECTRIC BUS CHARGERS AT NORTH DAVIDSON AND SOUTH TRYON BUS GARAGES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1205000
TL-0032 | Public Transportation (Transit) | Locally Selected | CATS | INSTALL ELECTRIC BUS CHARGERS AT NORTH DAVIDSON AND SOUTH TRYON BUS GARAGES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 1335000
TL-0032 | Public Transportation (Transit) | Locally Selected | CATS | INSTALL ELECTRIC BUS CHARGERS AT NORTH DAVIDSON AND SOUTH TRYON BUS GARAGES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 302000
TL-0033 | Public Transportation (Transit) | Locally Selected | INTERGRATED MOBILITY DIVISION | COMMUNITY PROJECT FUNDING FOR CITY OF WILSON RIDE MICROTRANSIT EXPANSION. |  | WILSON | 4 | Upper Coastal Plain RPO |  | Public Transit |  | CPF | CAPITAL | 2000000
TL-0033 | Public Transportation (Transit) | Locally Selected | INTERGRATED MOBILITY DIVISION | COMMUNITY PROJECT FUNDING FOR CITY OF WILSON RIDE MICROTRANSIT EXPANSION. |  | WILSON | 4 | Upper Coastal Plain RPO |  | Public Transit |  | L | CAPITAL | 500000
TL-0034 | Public Transportation (Transit) | Locally Selected | CHAPEL HILL TRANSIT | THE TOWN OF CHAPEL HILL. ACQUIRE FIVE (5) ELECTRIC TRANSIT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CAPITAL | 2040000
TL-0034 | Public Transportation (Transit) | Locally Selected | CHAPEL HILL TRANSIT | THE TOWN OF CHAPEL HILL. ACQUIRE FIVE (5) ELECTRIC TRANSIT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | CAPITAL | 668000
TL-0035 | Public Transportation (Transit) | Locally Selected | TOWN OF CHAPEL HILL | NORTH-SOUTH BUS RAPID TRANSIT CORRIDOR (NSBRT). | 8.2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | ENGINEERING | 2737000
TL-0035 | Public Transportation (Transit) | Locally Selected | TOWN OF CHAPEL HILL | NORTH-SOUTH BUS RAPID TRANSIT CORRIDOR (NSBRT). | 8.2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | 5307 | ENGINEERING | 8000000
TL-0035 | Public Transportation (Transit) | Locally Selected | TOWN OF CHAPEL HILL | NORTH-SOUTH BUS RAPID TRANSIT CORRIDOR (NSBRT). | 8.2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | CONSTRUCTION | 33863000 | FY 2027: 33863000
TL-0035 | Public Transportation (Transit) | Locally Selected | TOWN OF CHAPEL HILL | NORTH-SOUTH BUS RAPID TRANSIT CORRIDOR (NSBRT). | 8.2 | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 138400000 | FY 2027: 138400000
TL-0046 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A WAITING PAD AND LANDING PAD AT 5 STOPS ON THE 305. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 48000
TL-0046 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A WAITING PAD AND LANDING PAD AT 5 STOPS ON THE 305. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 12000
TL-0046 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A WAITING PAD AND LANDING PAD AT 5 STOPS ON THE 305. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | RIGHT-OF-WAY | 12000
TL-0046 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A WAITING PAD AND LANDING PAD AT 5 STOPS ON THE 305. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | RIGHT-OF-WAY | 3000
TL-0046 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A WAITING PAD AND LANDING PAD AT 5 STOPS ON THE 305. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 200000
TL-0046 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A WAITING PAD AND LANDING PAD AT 5 STOPS ON THE 305. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 50000
TL-0047 | Public Transportation (Transit) | Locally Selected | RURAL FERRY | SHIPYARD PAINT FACILITY REHABILITATION - RURAL FERRY PROGRAM. |  | DARE | 1 | Albemarle RPO |  | Public Transit |  | S | CONSTRUCTION | 500000
TL-0047 | Public Transportation (Transit) | Locally Selected | RURAL FERRY | SHIPYARD PAINT FACILITY REHABILITATION - RURAL FERRY PROGRAM. |  | DARE | 1 | Albemarle RPO |  | Public Transit |  | 5307 | CONSTRUCTION | 1500000
TL-0048 | Public Transportation (Transit) | Locally Selected | GTA | GTA ROUTE 15 NEW SERVICE |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | CMAQ | CAPITAL | 1450000
TL-0048 | Public Transportation (Transit) | Locally Selected | GTA | GTA ROUTE 15 NEW SERVICE |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 362000
TL-0049 | Public Transportation (Transit) | Locally Selected | VARIOUS | MOBILITY ON-DEMAND - 2 ADA ACCESSIBLE MINIVANS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 150000
TL-0049 | Public Transportation (Transit) | Locally Selected | VARIOUS | MOBILITY ON-DEMAND - 2 ADA ACCESSIBLE MINIVANS. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | IMPLEMENTATION | 37000
TL-0050 | Public Transportation (Transit) | Locally Selected | GTA | GTA NEW CROSSTOWN NEW ROUTE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | CMAQ | CAPITAL | 5905000
TL-0050 | Public Transportation (Transit) | Locally Selected | GTA | GTA NEW CROSSTOWN NEW ROUTE. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | CAPITAL | 1775000
TL-0051 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | IMPROVE (3) BUS STOPS IN ORANGE COUNTY AT SITES 701, 705, AND 706. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | CMAQ | CONSTRUCTION | 200000
TL-0051 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | IMPROVE (3) BUS STOPS IN ORANGE COUNTY AT SITES 701, 705, AND 706. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L(M) | CONSTRUCTION | 50000
TL-0052 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | THIS TRANSIT PROJECT WILL IMPROVE 13 STOPS ON THE GOTRIANGLE 805 CORRIDOR ON WOODCROFT PARKWAY PLUS TWO STOPS ON NC 54. 12 STOPS WILL ADD ADA-COMPLIANT LANDING PADS AND CONTINUOUS PEDESTRIAN CONNECTIVITY TO THE EXISTING SIDEWALK/SIDEPATH NETWORK FROM EACH STOP WHERE NEEDED. STOP 1208 MEETS BOARDING WARRANTS FOR SEATING AND WILL ALSO INCLUDE SEATING. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | BGDA | CONSTRUCTION | 134000
TL-0052 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | THIS TRANSIT PROJECT WILL IMPROVE 13 STOPS ON THE GOTRIANGLE 805 CORRIDOR ON WOODCROFT PARKWAY PLUS TWO STOPS ON NC 54. 12 STOPS WILL ADD ADA-COMPLIANT LANDING PADS AND CONTINUOUS PEDESTRIAN CONNECTIVITY TO THE EXISTING SIDEWALK/SIDEPATH NETWORK FROM EACH STOP WHERE NEEDED. STOP 1208 MEETS BOARDING WARRANTS FOR SEATING AND WILL ALSO INCLUDE SEATING. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | BGDA | CONSTRUCTION | 492000 | FY 2025: 492000
TL-0052 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | THIS TRANSIT PROJECT WILL IMPROVE 13 STOPS ON THE GOTRIANGLE 805 CORRIDOR ON WOODCROFT PARKWAY PLUS TWO STOPS ON NC 54. 12 STOPS WILL ADD ADA-COMPLIANT LANDING PADS AND CONTINUOUS PEDESTRIAN CONNECTIVITY TO THE EXISTING SIDEWALK/SIDEPATH NETWORK FROM EACH STOP WHERE NEEDED. STOP 1208 MEETS BOARDING WARRANTS FOR SEATING AND WILL ALSO INCLUDE SEATING. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L(M) | CONSTRUCTION | 33000
TL-0052 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | THIS TRANSIT PROJECT WILL IMPROVE 13 STOPS ON THE GOTRIANGLE 805 CORRIDOR ON WOODCROFT PARKWAY PLUS TWO STOPS ON NC 54. 12 STOPS WILL ADD ADA-COMPLIANT LANDING PADS AND CONTINUOUS PEDESTRIAN CONNECTIVITY TO THE EXISTING SIDEWALK/SIDEPATH NETWORK FROM EACH STOP WHERE NEEDED. STOP 1208 MEETS BOARDING WARRANTS FOR SEATING AND WILL ALSO INCLUDE SEATING. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L(M) | CONSTRUCTION | 123000 | FY 2025: 123000
TL-0053 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A LANDING PAD AT 24 STOPS BETWEEN EXISTING SIDEWALK AND BACK OF CURB. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. ROUTE 305. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | ENGINEERING | 80000
TL-0053 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A LANDING PAD AT 24 STOPS BETWEEN EXISTING SIDEWALK AND BACK OF CURB. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. ROUTE 305. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | ENGINEERING | 20000
TL-0053 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A LANDING PAD AT 24 STOPS BETWEEN EXISTING SIDEWALK AND BACK OF CURB. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. ROUTE 305. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 192000
TL-0053 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ADD A LANDING PAD AT 24 STOPS BETWEEN EXISTING SIDEWALK AND BACK OF CURB. TRASH CAN PADS MAY BE INCLUDED AS WARRANTED. ROUTE 305. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CONSTRUCTION | 48000
TL-0054 | Public Transportation (Transit) | Locally Selected | WINSTON SALEM TRANSIT AUTHORITY | WSTA BUS REPLACEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CAPITAL | 3200000 | FY 2025: 3200000
TL-0054 | Public Transportation (Transit) | Locally Selected | WINSTON SALEM TRANSIT AUTHORITY | WSTA BUS REPLACEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CAPITAL | 2959000
TL-0054 | Public Transportation (Transit) | Locally Selected | WINSTON SALEM TRANSIT AUTHORITY | WSTA BUS REPLACEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CAPITAL | 740000
TL-0054 | Public Transportation (Transit) | Locally Selected | WINSTON SALEM TRANSIT AUTHORITY | WSTA BUS REPLACEMENTS. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CAPITAL | 800000 | FY 2025: 800000
TL-0055 | Public Transportation (Transit) | Locally Selected | GTA | J. DOUGLAS GAYLON DEPOT RENOVATION PHASE 3 |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | BGDA | CONSTRUCTION | 1600000 | FY 2025: 1600000
TL-0055 | Public Transportation (Transit) | Locally Selected | GTA | J. DOUGLAS GAYLON DEPOT RENOVATION PHASE 3 |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L(M) | CONSTRUCTION | 400000 | FY 2025: 400000
TL-0055 | Public Transportation (Transit) | Locally Selected | GTA | J. DOUGLAS GAYLON DEPOT RENOVATION PHASE 3 |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L(M) | CONSTRUCTION | 213000 | FY 2025: 213000
TL-0055 | Public Transportation (Transit) | Locally Selected | GTA | J. DOUGLAS GAYLON DEPOT RENOVATION PHASE 3 |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5339 | CONSTRUCTION | 850000 | FY 2025: 850000
TL-0056 | Public Transportation (Transit) | Locally Selected | CATS | BALLANTYNE I-485 SERVICE. PURCHASE TWO BATTERY ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | CRPDA | CONSTRUCTION | 1750000 | FY 2026: 1750000
TL-0056 | Public Transportation (Transit) | Locally Selected | CATS | BALLANTYNE I-485 SERVICE. PURCHASE TWO BATTERY ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Exempt |  | L | CONSTRUCTION | 438000 | FY 2026: 438000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 58000 | FY 2025: 58000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 14000 | FY 2025: 14000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 14000 | FY 2025: 14000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 4000 | FY 2025: 4000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 350000 | FY 2025: 350000
TL-0057 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | GODURHAM ROUTE 2 STOP IMPROVEMENTS-BRIER CREEK IN WAKE COUNTY. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 88000 | FY 2025: 88000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | ENGINEERING | 86000 | FY 2025: 86000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | ENGINEERING | 22000 | FY 2025: 22000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | RIGHT-OF-WAY | 22000 | FY 2025: 22000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | RIGHT-OF-WAY | 5000 | FY 2025: 5000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | TADA | CONSTRUCTION | 324000 | FY 2025: 324000
TL-0058 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | ROUTE 305 APEX BUS STOP IMPROVEMENTS-SOUTH OF US 64. IMPROVE ALL BUS STOPS TO ADA STANDARD. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 81000 | FY 2025: 81000
TL-0059 | Public Transportation (Transit) | Locally Selected | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CONSTRUCTION | 271000
TL-0059 | Public Transportation (Transit) | Locally Selected | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L(M) | CONSTRUCTION | 68000
TL-0059 | Public Transportation (Transit) | Locally Selected | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | OPERATIONS | 271000 | FY 2025: 271000
TL-0059 | Public Transportation (Transit) | Locally Selected | GOCARY | PURCHASE AND INSTALL NEW RADIOS FOR THE GOCARY BUS SYSTEM, INCLUDING EQUIPMENT FOR A BASE CONSOLE OPERATION FOR DISPATCH. |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | OPERATIONS | 678000 | FY 2025: 678000
TL-0060 | Public Transportation (Transit) | Locally Selected | CITY OF FAYETTEVILLE TRANSIT DEPARTMENT (FAST) | IMPLEMENT A CASHLESS FARE SYSTEM ACROSS THE FIXED ROUTE AND PARATRANSIT FLEET. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Exempt |  | CRPDA | CONSTRUCTION | 125000 | FY 2025: 125000
TL-0060 | Public Transportation (Transit) | Locally Selected | CITY OF FAYETTEVILLE TRANSIT DEPARTMENT (FAST) | IMPLEMENT A CASHLESS FARE SYSTEM ACROSS THE FIXED ROUTE AND PARATRANSIT FLEET. |  | CUMBERLAND | 6 | Fayetteville Area MPO |  | Exempt |  | L(M) | CONSTRUCTION | 31000 | FY 2025: 31000
TL-0062 | Public Transportation (Transit) | Locally Selected | CHAPEL HILL TRANSIT | IMPROVE BUS STOPS AT VARIOUS LOCATIONS IN DOWNTOWN CHAPEL HILL. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CONSTRUCTION | 361000 | FY 2025: 361000
TL-0062 | Public Transportation (Transit) | Locally Selected | CHAPEL HILL TRANSIT | IMPROVE BUS STOPS AT VARIOUS LOCATIONS IN DOWNTOWN CHAPEL HILL. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | CONSTRUCTION | 90000 | FY 2025: 90000
TL-0063 | Public Transportation (Transit) | Locally Selected | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE CUTAWAY VEHICLES AND HEAVY DUTY BUSSES |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | BGDA | CAPITAL | 1650000 | FY 2025: 1650000
TL-0063 | Public Transportation (Transit) | Locally Selected | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE CUTAWAY VEHICLES AND HEAVY DUTY BUSSES |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Division 9 |  | L(M) | CAPITAL | 413000 | FY 2025: 413000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | BGDA | ENGINEERING | 4400000 | FY 2025: 4400000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L(M) | ENGINEERING | 1100000 | FY 2025: 1100000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | DP | CONSTRUCTION | 19000000 | FY 2026: 19000000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | BGDA | CONSTRUCTION | 1100000 | FY 2026: 1100000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L | CONSTRUCTION | 14125000 | FY 2026: 14125000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L(M) | CONSTRUCTION | 275000 | FY 2026: 275000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | DP | CAPITAL | 6000000 | FY 2026: 6000000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L(M) | CAPITAL | 1500000 | FY 2026: 1500000
TL-0064 | Public Transportation (Transit) | Locally Selected | TRIANGLE MOBILITY HUB | CONSTRUCT TRANSIT CENTER ON NEW LOCATION, SIGNALIZED SITE DRIVEWAY ON NC 54 WITH TRANSIT SIGNAL PRIORITY, AND TRANSIT OPERATIONAL IMPROVEMENTS ALONG NC 54, MIAMI BLVD, AND SLATER ROAD. PURCHASE BATTERY-ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO | "DP" FUNDING REFLECTS RAISE GRANT AWARD. | Exempt |  | L | CAPITAL | 4500000 | FY 2026: 4500000
TL-0065 | Public Transportation (Transit) | Locally Selected | GODURHAM | PURCHASE BATTERY ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGDA | CAPITAL | 863000 | FY 2027: 863000
TL-0065 | Public Transportation (Transit) | Locally Selected | GODURHAM | PURCHASE BATTERY ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L(M) | CAPITAL | 216000 | FY 2027: 216000
TL-0065 | Public Transportation (Transit) | Locally Selected | GODURHAM | PURCHASE BATTERY ELECTRIC BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CAPITAL | 103000 | FY 2027: 103000
TL-0066 | Public Transportation (Transit) | Locally Selected | CHAPEL HILL TRANSIT | PURCHASE ELECTRIC BUS |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | BGDA | CAPITAL | 920000 | FY 2027: 920000
TL-0066 | Public Transportation (Transit) | Locally Selected | CHAPEL HILL TRANSIT | PURCHASE ELECTRIC BUS |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Division 7 |  | L(M) | CAPITAL | 230000 | FY 2027: 230000
TL-6110 | Public Transportation (Transit) | Locally Selected | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PROGRAM ADMINISTRATION |  | ALEXANDER, BURKE, CALDWELL, CATAWBA | 11, 12, 13 | Greater Hickory MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 262000 | FY 2025: 30000
TL-6111 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | PURCHASE TWO 40 FOOT BUSSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | BGDA | CAPITAL | 909000 | FY 2025: 909000
TL-6111 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | PURCHASE TWO 40 FOOT BUSSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L(M) | CAPITAL | 227000 | FY 2025: 227000
TL-6111 | Public Transportation (Transit) | Locally Selected | GOTRIANGLE | PURCHASE TWO 40 FOOT BUSSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Division 5 |  | L | CAPITAL | 224000 | FY 2025: 224000
TM-0002 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311 ADMIN/OPERATING/CAPITAL AND 5311(F) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 3950000
TM-0004 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311CAPITAL-ADTAP) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 150000
TM-0010 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | OPERATIONS | 142000
TM-0012 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | OPERATIONS | 129000
TM-0014 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | OPERATIONS | 75000
TM-0015 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | ADMINISTRATIVE | 145000
TM-0020 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | L | OPERATIONS | 1073000
TM-0020 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | OPERATIONS | 1073000
TM-0020 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | ADMINISTRATIVE | 45000
TM-0022 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5307 OPERATING FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. | Public Transit |  | 5307 | ADMINISTRATIVE | 18000
TM-0023 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5310 ADMIN/OPERATING/CAPITAL PURCHASE SERVICE) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5310 | ADMINISTRATIVE | 1022000
TM-0024 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5312 | OPERATIONS | 250000
TM-0024 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 63000
TM-0025 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5310 OPERATING PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 2106000
TM-0025 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5310 OPERATING PROJECTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5310 | OPERATIONS | 2106000
TM-0026 | Public Transportation (Transit) | Locally Selected | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | BGDA | CAPITAL | 427000
TM-0026 | Public Transportation (Transit) | Locally Selected | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 |  | WAKE | 5 | Capital Area MPO |  | Division 5 |  | L | CAPITAL | 183000
TM-0027 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | ADMINISTRATIVE | 5084000
TM-0027 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | ADMINISTRATIVE | 13748000
TM-0027 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 55758000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | OPERATIONS | 1000000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 8064000
TM-0028 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | OPERATIONS | 8064000
TM-0029 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 STATE ADMINISTRATIVE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 3361000
TM-0030 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311 ADTAP STATE ADMINISTRATIVE FUNDS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | ADTAP | ADMINISTRATIVE | 177000
TM-0031 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | RTAP STATEWIDE FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | RTAP | ADMINISTRATIVE | 1628000
TM-0032 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | OPERATIONS | 12607000
TM-0032 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | OPERATIONS | 16834000
TM-0033 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | 5311(F) INTERCITY BUS - STATE ADMIN |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5311 | ADMINISTRATIVE | 494000
TM-0035 | Public Transportation (Transit) | Operations and Maintenance | GOTRIANGLE | OPERATING ASSISTANCE FOR TOWN OF MORRISVILLE NODE BASED SMART SHUTTLE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 3621000 | FY 2025: 730000; FY 2026: 740000
TM-0036 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5310 STATE ADMINISTRATIVE FUNDS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5310 | ADMINISTRATIVE | 567000
TM-0037 | Public Transportation (Transit) | Operations and Maintenance | WINSTON-SALEM TRANSIT AUTHORITY | CONTINUATION OF WSTA NIGHT, SATURDAY, AND SUNDAY SERVICES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | CMAQ | OPERATIONS | 810000 | FY 2025: 810000
TM-0037 | Public Transportation (Transit) | Operations and Maintenance | WINSTON-SALEM TRANSIT AUTHORITY | CONTINUATION OF WSTA NIGHT, SATURDAY, AND SUNDAY SERVICES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Exempt |  | L(M) | OPERATIONS | 203000 | FY 2025: 203000
TM-0038 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS. (ARP/CRRSAA 5301 OPERATING) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | S | ADMINISTRATIVE | 86000
TM-0038 | Public Transportation (Transit) | Operations and Maintenance | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS. (ARP/CRRSAA 5301 OPERATING) |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | FEDT | ADMINISTRATIVE | 1415000
TM-0039 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CONSTRUCTION | 1000000
TM-0039 | Public Transportation (Transit) | Capital (Non-STI) | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 1000000
TM-0040 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE TRANSIT AREA | FIRST MILE-LAST MILE PROJECT WILL PLAN NEW AND REPLACEMENT CIRCULATOR ROUTES WITH A NEW ON-DEMAND STRATEGY OF MICRO-TRANSIT ZONES TO REDUCE TRAVEL TIMES AND IMPROVE CONNECTIVITY TO HIGH-FREQUENCY ROUTES AT MOBILITY HUBS. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | ARP | PLANNING | 750000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | DP | CONSTRUCTION | 15000000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | L | CONSTRUCTION | 70718000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | CMAQ | CAPITAL | 2040000
TM-0041 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT | REBUILD CATS MAIN TRANSIT HUB AT THE CHARLOTTE TRANSPORTATION CENTER IN UPTOWN CHARLOTTE. |  | MECKLENBURG | 10 | Charlotte Regional TPO | DP REPRESENTS FEDERAL RAISE GRANT AWARD. AWARD AMOUNT IS $15,000,000. | Public Transit |  | L | CAPITAL | 668000
TM-0042 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | CMAQ | ACQUISITION | 871000
TM-0042 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | S | ACQUISITION | 1393000
TM-0042 | Public Transportation (Transit) | Operations and Maintenance | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE ELECTRIC BUSES. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | L | ACQUISITION | 475000
TM-0043 | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | ACQUISITION OF SIX (6) ELECTRIC TRANSIT BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | CMAQ | ACQUISITION | 846000
TM-0043 | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | ACQUISITION OF SIX (6) ELECTRIC TRANSIT BUSES. |  | DURHAM | 5 | Durham-Chapel Hill-Carrboro MPO |  | Public Transit |  | L | ACQUISITION | 846000
TM-0045 | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | GASTONIA TRANSIT PAYMENT KIOSK. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CAPITAL | 44000
TM-0045 | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | GASTONIA TRANSIT PAYMENT KIOSK. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CAPITAL | 175000
TM-0046 | Public Transportation (Transit) | Operations and Maintenance | LINK TRANSIT | PREVENTATIVE MAINTENANCE. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 714000 | FY 2025: 102000; FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0046 | Public Transportation (Transit) | Operations and Maintenance | LINK TRANSIT | PREVENTATIVE MAINTENANCE. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 2870000 | FY 2025: 410000; FY 2026: 410000; FY 2027: 410000; FY 2028: 410000
TM-0047 | Public Transportation (Transit) | Capital (Non-STI) | GASTONIA TRANSIT | CAPITAL ROLLING STOCK |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CAPITAL | 200000 | FY 2025: 200000
TM-0047 | Public Transportation (Transit) | Capital (Non-STI) | GASTONIA TRANSIT | CAPITAL ROLLING STOCK |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CAPITAL | 800000 | FY 2025: 800000
TM-0048 | Public Transportation (Transit) | Operations and Maintenance | DAVIDSON COUNTY TRANSPORTATION SYSTEM | OPERATE OUR DEVIATED FIXED ROUTES BASED IN THOMASVILLE, NC ALONG WITH DEMAND RESPONSE TRIPS. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 1650000 | FY 2025: 275000; FY 2026: 275000; FY 2027: 275000; FY 2028: 275000
TM-0048 | Public Transportation (Transit) | Operations and Maintenance | DAVIDSON COUNTY TRANSPORTATION SYSTEM | OPERATE OUR DEVIATED FIXED ROUTES BASED IN THOMASVILLE, NC ALONG WITH DEMAND RESPONSE TRIPS. |  | DAVIDSON | 9 | High Point Urban Area MPO |  | Public Transit |  | 5317 | OPERATIONS | 1650000 | FY 2025: 275000; FY 2026: 275000; FY 2027: 275000; FY 2028: 275000
TM-0049 | Public Transportation (Transit) | Operations and Maintenance | INTEGRATED MOBILITY DIVISION | MACON COUNTY AREAS OF PERSISTENT POVERTY (AoPP) GRANT. |  | MACON | 14 | Southwestern RPO |  | Public Transit |  | DP | CAPITAL | 470000
TM-0049 | Public Transportation (Transit) | Operations and Maintenance | INTEGRATED MOBILITY DIVISION | MACON COUNTY AREAS OF PERSISTENT POVERTY (AoPP) GRANT. |  | MACON | 14 | Southwestern RPO |  | Public Transit |  | L | CAPITAL | 55000
TM-0050 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SUPPORT VEHICLES AND EQUIPMENT: ACQUIRE OR REPLACE VEHICLES, EQUIPMENT, AND ELECTRONICS THAT SUPPORT THE OPERATION OF FIXED ROUTE BUS AND PARATRANSIT SERVICES AND PASSENGER FACILITIES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | L | CAPITAL | 62000
TM-0050 | Public Transportation (Transit) | Capital (Non-STI) | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SUPPORT VEHICLES AND EQUIPMENT: ACQUIRE OR REPLACE VEHICLES, EQUIPMENT, AND ELECTRONICS THAT SUPPORT THE OPERATION OF FIXED ROUTE BUS AND PARATRANSIT SERVICES AND PASSENGER FACILITIES. |  | NEW HANOVER | 3 | Wilmington Urban Area MPO |  | Public Transit |  | 5309 | CAPITAL | 249000
TM-0051 | Public Transportation (Transit) | Operations and Maintenance | ALAMANCE COUNTY TRANSPORTATION AUTHORITY | ROLLING STOCK-SHOP SERVICE VEHICLE (5307). |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | L | CAPITAL | 817000 | FY 2025: 805000
TM-0051 | Public Transportation (Transit) | Operations and Maintenance | ALAMANCE COUNTY TRANSPORTATION AUTHORITY | ROLLING STOCK-SHOP SERVICE VEHICLE (5307). |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Public Transit |  | 5307 | CAPITAL | 48000
TM-0052 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY TRANSPORTATION | OPERATIONAL EXPENSES AND ROUTINE CAPITAL |  | UNION | 10 | Charlotte Regional TPO |  | Public Transit |  | L(M) | CAPITAL | 971000 | FY 2025: 513000
TM-0052 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY TRANSPORTATION | OPERATIONAL EXPENSES AND ROUTINE CAPITAL |  | UNION | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CAPITAL | 971000 | FY 2025: 513000
TM-0053 | Public Transportation (Transit) | Operations and Maintenance | GTA | OPERATING MICROSTRANSIT. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | L | OPERATIONS | 2735000 | FY 2025: 547000; FY 2026: 547000; FY 2027: 547000; FY 2028: 547000
TM-0053 | Public Transportation (Transit) | Operations and Maintenance | GTA | OPERATING MICROSTRANSIT. |  | GUILFORD | 7 | Greensboro Urban Area MPO |  | Public Transit |  | 5307 | OPERATIONS | 2735000 | FY 2025: 547000; FY 2026: 547000; FY 2027: 547000; FY 2028: 547000
TM-0054 | Public Transportation (Transit) | Operations and Maintenance | HAYWOOD COUNTY | HAYWOOD COUNTY OPERATING ASSISTANCE |  | HAYWOOD | 14 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 492000 | FY 2025: 102000; FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0054 | Public Transportation (Transit) | Operations and Maintenance | HAYWOOD COUNTY | HAYWOOD COUNTY OPERATING ASSISTANCE |  | HAYWOOD | 14 | French Broad River MPO |  | Public Transit |  | 5307 | OPERATIONS | 492000 | FY 2025: 102000; FY 2026: 102000; FY 2027: 102000; FY 2028: 102000
TM-0055 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | LOW - NO EMISSIONS PROGRAM FOR THE PURCHASE OF FIVE (5) HYBRID-ELECTRIC BUSES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | CAPITAL | 788000
TM-0055 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | LOW - NO EMISSIONS PROGRAM FOR THE PURCHASE OF FIVE (5) HYBRID-ELECTRIC BUSES. |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5339(b) | CAPITAL | 4445000
TM-0056 | Public Transportation (Transit) | Operations and Maintenance | MECKLENBURG TRANSIT SYSTEM | CAPITAL COST FOR CONTRACTING RELATED TO DEMAND RESPONSE VENDOR TRIPS, PREVENTATIVE MAINTENANCE EXPENSES AND SECURITY RELATED SOFTWARE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 249000
TM-0056 | Public Transportation (Transit) | Operations and Maintenance | MECKLENBURG TRANSIT SYSTEM | CAPITAL COST FOR CONTRACTING RELATED TO DEMAND RESPONSE VENDOR TRIPS, PREVENTATIVE MAINTENANCE EXPENSES AND SECURITY RELATED SOFTWARE. |  | MECKLENBURG | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CAPITAL | 994000
TM-0058 | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | PURCHASE AN EV ADA VAN. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | L | CONSTRUCTION | 23000 | FY 2025: 23000
TM-0058 | Public Transportation (Transit) | Operations and Maintenance | GASTONIA TRANSIT | PURCHASE AN EV ADA VAN. |  | GASTON | 12 | Gaston-Cleveland-Lincoln MPO |  | Public Transit |  | 5307 | CONSTRUCTION | 94000 | FY 2025: 94000
TM-0059 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY TRANSPORTATION | OPERATIONAL EXPENSES, ROUTINE CAPITAL, AND PLANNING |  | UNION | 10 | Charlotte Regional TPO |  | Public Transit |  | L | CAPITAL | 716000 | FY 2025: 308000; FY 2026: 97000; FY 2027: 15000
TM-0059 | Public Transportation (Transit) | Operations and Maintenance | UNION COUNTY TRANSPORTATION | OPERATIONAL EXPENSES, ROUTINE CAPITAL, AND PLANNING |  | UNION | 10 | Charlotte Regional TPO |  | Public Transit |  | 5307 | CAPITAL | 1222000 | FY 2025: 369000; FY 2026: 483000; FY 2027: 74000
TM-5138 | Public Transportation (Transit) | Operations and Maintenance | CITY OF ASHEVILLE | JARC OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | L | OPERATIONS | 766000
TM-5138 | Public Transportation (Transit) | Operations and Maintenance | CITY OF ASHEVILLE | JARC OPERATIONS |  | BUNCOMBE | 13 | French Broad River MPO |  | Public Transit |  | 3037 | OPERATIONS | 766000
TM-5163 | Public Transportation (Transit) | Locally Selected | CITY OF ASHEVILLE | CITY OF ASHEVILLE ADMINISTRATIVE OVERSIGHT OF JARC PROJECTS IN THE ASHEVILLE UAZ |  | BUNCOMBE, HAYWOOD | 13, 14 | French Broad River MPO |  | Public Transit |  | L | ADMINISTRATIVE | 85000
TM-5301 | Public Transportation (Transit) | Operations and Maintenance | SUB REGIONAL | STATE ADMINISTRATION - JOB ACCESS NON-URBAN |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5316 | ADMINISTRATIVE | 5592000
TM-5309 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | L | OPERATIONS | 550000 | FY 2025: 55000
TM-5309 | Public Transportation (Transit) | Operations and Maintenance | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS |  | FORSYTH | 9 | Winston-Salem Area TPO |  | Public Transit |  | 5316 | OPERATIONS | 550000 | FY 2025: 55000
TM-6110 | Public Transportation (Transit) | Operations and Maintenance | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PROGRAM ADMINISTRATION |  | CATAWBA | 12 | Greater Hickory MPO |  | Public Transit |  | 5310 | ADMINISTRATIVE | 262000 | FY 2025: 30000
TN-0001 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | COORDINATED AREA TRANSPORTATION SYSTEM (RCATS) | ASHEBORO FLEXIBLE (DEVIATED) ROUTE TRANSIT LAUNCH. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Exempt |  | CRPANY | CAPITAL | 440000
TN-0001 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | COORDINATED AREA TRANSPORTATION SYSTEM (RCATS) | ASHEBORO FLEXIBLE (DEVIATED) ROUTE TRANSIT LAUNCH. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Exempt |  | L(M) | CAPITAL | 200000
TN-0001 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | COORDINATED AREA TRANSPORTATION SYSTEM (RCATS) | ASHEBORO FLEXIBLE (DEVIATED) ROUTE TRANSIT LAUNCH. |  | RANDOLPH | 8 | Piedmont Triad RPO |  | Exempt |  | L | CAPITAL | 93000
TN-5102 | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | OPERATING ASSISTANCE - NEW FREEDOM - URBAN |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | L | OPERATIONS | 504000
TN-5102 | Public Transportation (Transit) | Operations and Maintenance | GODURHAM | OPERATING ASSISTANCE - NEW FREEDOM - URBAN |  | DURHAM, ORANGE | 5, 7 | Durham-Chapel Hill-Carrboro MPO | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5317 | OPERATIONS | 1260000
TN-5112 | Public Transportation (Transit) | Operations and Maintenance | SUB REGIONAL | STATE ADMINISTRATION - NEW FREEDOM - 5317 |  | STATEWIDE | 99 | STATEWIDE PROJECT | FUNDS AUTHORIZED IN PROGRESS | Public Transit |  | 5317 | ADMINISTRATIVE | 4270000
TN-6116 | Public Transportation (Transit) | Operations and Maintenance | WAKE COORDINATED TRANSIT SERVICE | WAKE COORDINATED TRANSIT SERVICES OPERATING ASSISTANCE. |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | OPERATIONS | 4070000 | FY 2025: 800000; FY 2026: 868000
TN-6125 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5317 NEW FREEDOM |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | FEP | OPERATIONS | 3963000 | FY 2025: 460000; FY 2026: 470000; FY 2027: 480000
TN-6125 | Public Transportation (Transit) | Operations and Maintenance | STATEWIDE | 5317 NEW FREEDOM |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | L | OPERATIONS | 793000 | FY 2025: 92000; FY 2026: 94000; FY 2027: 96000
TN-6126 | Public Transportation (Transit) | Locally Selected | ORANGE COUNTY TRANSIT | ORANGE COUNTY MOBILITY ON DEMAND - PURCHASE 2 ADA ACCESSIBLE MINI-VANS. EXPAND MICRO-TRANSIT ZONES. |  | ORANGE | 7 | Central Pines RPO |  | Exempt |  | CMAQ | IMPLEMENTATION | 150000
TN-6126 | Public Transportation (Transit) | Locally Selected | ORANGE COUNTY TRANSIT | ORANGE COUNTY MOBILITY ON DEMAND - PURCHASE 2 ADA ACCESSIBLE MINI-VANS. EXPAND MICRO-TRANSIT ZONES. |  | ORANGE | 7 | Central Pines RPO |  | Exempt |  | L | IMPLEMENTATION | 38000
TN-6127 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | RUTHERFORDTON | PURCHASE FOUR ELECTRIC VEHICLES. |  | RUTHERFORD | 13 | Foothills RPO |  | Exempt |  | CRP550 | CAPITAL | 233000 | FY 2025: 233000
TN-6127 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | RUTHERFORDTON | PURCHASE FOUR ELECTRIC VEHICLES. |  | RUTHERFORD | 13 | Foothills RPO |  | Exempt |  | L(M) | CAPITAL | 58000 | FY 2025: 58000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 22000 | FY 2025: 22000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | L(M) | ENGINEERING | 6000 | FY 2025: 6000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | CONSTRUCTION | 301000 | FY 2026: 301000
TN-6128 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | US 25 / US 70 | CONSTRUCT PARK AND RIDE AT US 25 BUSINESS / US 70 BUSINESS INTERSECTION. |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | L(M) | CONSTRUCTION | 75000 | FY 2026: 75000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | WATAUGA | 11 | High Country RPO |  | Exempt |  | CRPANY | ENGINEERING | 144000 | FY 2025: 144000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | WATAUGA | 11 | High Country RPO |  | Exempt |  | T(M) | ENGINEERING | 36000 | FY 2025: 36000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | WATAUGA | 11 | High Country RPO |  | Exempt |  | CRPANY | CAPITAL | 3858000 | FY 2025: 3858000
TN-6129 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | APPALCART | PURCHASE TWO BATTERY ELECTRIC BUSSES, FIVE LIGHT TRANSIT VEHICLES, A 180KW CHARGER, AND ELECTRIC VEHICLE CHARGE MANAGEMENT AND DIAGNOSTIC TOOL. |  | WATAUGA | 11 | High Country RPO |  | Exempt |  | T(M) | CAPITAL | 965000 | FY 2025: 965000
TN-6130 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | MADISON COUNTY TRANSPORTATION | PURCHASE TWO TRANSIT VEHICLES |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | ENGINEERING | 8000 | FY 2025: 8000
TN-6130 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | MADISON COUNTY TRANSPORTATION | PURCHASE TWO TRANSIT VEHICLES |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | L(M) | ENGINEERING | 2000 | FY 2025: 2000
TN-6130 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | MADISON COUNTY TRANSPORTATION | PURCHASE TWO TRANSIT VEHICLES |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | CRPLT5 | CAPITAL | 189000 | FY 2025: 189000
TN-6130 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | MADISON COUNTY TRANSPORTATION | PURCHASE TWO TRANSIT VEHICLES |  | MADISON | 13 | Land-of-Sky RPO |  | Exempt |  | L(M) | CAPITAL | 47000 | FY 2025: 47000
TN-6131 | Public Transportation (Transit) | Locally Selected | SURF CITY | PURCHASE TWO ELECTRIC VEHICLES. |  | PENDER, ONSLOW | 3 | Cape Fear RPO, Jacksonville Urban Area MPO |  | Exempt |  | CRPANY | OTHER | 80000 | FY 2025: 80000
TN-6131 | Public Transportation (Transit) | Locally Selected | SURF CITY | PURCHASE TWO ELECTRIC VEHICLES. |  | PENDER, ONSLOW | 3 | Cape Fear RPO, Jacksonville Urban Area MPO |  | Exempt |  | L(M) | OTHER | 20000 | FY 2025: 20000
TN-6132 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | JOHNSTON COUNTY | PURCHASE ELECTRIC TRANSIT VEHICLES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | CRPANY | ENGINEERING | 8000 | FY 2025: 8000
TN-6132 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | JOHNSTON COUNTY | PURCHASE ELECTRIC TRANSIT VEHICLES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | L(M) | ENGINEERING | 2000 | FY 2025: 2000
TN-6132 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | JOHNSTON COUNTY | PURCHASE ELECTRIC TRANSIT VEHICLES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | CRPANY | CONSTRUCTION | 400000 | FY 2025: 400000
TN-6132 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | JOHNSTON COUNTY | PURCHASE ELECTRIC TRANSIT VEHICLES. |  | JOHNSTON | 4 | Upper Coastal Plain RPO |  | Division 4 |  | L(M) | CONSTRUCTION | 100000 | FY 2025: 100000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | CHAPEL HILL TRANSIT | PURCHASE FIVE ELECTRIC TRANSIT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | CMAQ | CAPITAL | 2040000 | FY 2025: 2040000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | CHAPEL HILL TRANSIT | PURCHASE FIVE ELECTRIC TRANSIT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L(M) | CAPITAL | 510000 | FY 2025: 510000
TN-6133 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | CHAPEL HILL TRANSIT | PURCHASE FIVE ELECTRIC TRANSIT BUSES. |  | ORANGE | 7 | Durham-Chapel Hill-Carrboro MPO |  | Exempt |  | L | CAPITAL | 158000 | FY 2025: 158000
TN-6134 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | LINK TRANSIT | PURCHASE TWO ELECTRIC PARATRANSIT VEHICLES AND INSTALL CHARGER. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Exempt |  | CRPDA | CAPITAL | 448000 | FY 2025: 448000
TN-6134 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | LINK TRANSIT | PURCHASE TWO ELECTRIC PARATRANSIT VEHICLES AND INSTALL CHARGER. |  | ALAMANCE | 7 | Burlington-Graham MPO |  | Exempt |  | L(M) | CAPITAL | 112000 | FY 2025: 112000
TN-6135 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | PITTSBORO | OPERATING ASSISTANCE FOR NEW TRANSIT SERVICE IN THE TOWN OF PITTSBORO. |  | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | CMAQ | OPERATIONS | 140000 | FY 2025: 140000
TN-6135 | Public Transportation (Transit) | NCDOT Selected (Other Selection Process | PITTSBORO | OPERATING ASSISTANCE FOR NEW TRANSIT SERVICE IN THE TOWN OF PITTSBORO. |  | CHATHAM | 8 | Central Pines RPO |  | Exempt |  | L(M) | OPERATIONS | 35000 | FY 2025: 35000
TO-0002 | Public Transportation (Transit) | Miscellaneous/Other | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | L | CAPITAL | 274000
TO-0002 | Public Transportation (Transit) | Miscellaneous/Other | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY |  | WAKE | 5 | Capital Area MPO |  | Public Transit |  | 5307 | CAPITAL | 1094000
TO-0003 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIGNS OF HUMAN TRAFFICKING. THE DEPARTMENT ALSO WILL DEVELOP HUMAN TRAFFICKING AWARENESS EDUCATIONAL MATERIALS TO BE POSTED ON TRANSIT VEHICLES AND STATIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5312 | ADMINISTRATIVE | 120000
TO-0003 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIGNS OF HUMAN TRAFFICKING. THE DEPARTMENT ALSO WILL DEVELOP HUMAN TRAFFICKING AWARENESS EDUCATIONAL MATERIALS TO BE POSTED ON TRANSIT VEHICLES AND STATIONS. |  | STATEWIDE | 99 | STATEWIDE PROJECT |  | Public Transit |  | 5307 | ADMINISTRATIVE | 30000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | CONSTRUCTION | 1000000 | FY 2025: 500000; FY 2026: 500000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | SSO | CONSTRUCTION | 2810000 | FY 2025: 1810000; FY 2026: 1000000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | ADMINISTRATIVE | 88000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | ADMINISTRATIVE | 600000
TO-0004 | Public Transportation (Transit) | Miscellaneous/Other | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. |  | STATEWIDE | 99 | STATEWIDE PROJECT | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD. | Public Transit |  | S | ADMINISTRATIVE | 88000